Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Making All Voices Count (MAVC)
Programme Value: £6.7m from DFID, US$45m in total		Review Date: Sep 2015
Programme Code:	Start Date: / Dec 2012	End Date: / May 2017

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	B	B
Risk Rating	Medium	High	High

Summary of progress and lessons learnt since last review
This review has been conducted for DFID by independent evaluators and covers the period of June 2014 – May 2015.

Substantial management changes have been made in response to the 2014 AR and management review. An interim Programme Director (PD) was brought in starting July 2015 and has strengthened the focus on delivery and integration of the Fund Manager Consortium (FMC). This includes: getting the FMC up to date on KPIs; getting all FMC partners to jointly map projects against the MAVC theory of change and to set out simplified hypothesis trees within the theory of change that are used to frame time-bound deliverables for programme staff. Responsibility for M&E has been transferred from Hivos to IDS and an IDS-based monitoring, evaluation and learning (MEL) manager started work towards the end of year 2. This has significantly increased programme M&E capacity for year 3. Country strategies are in place, reflecting investment in this strategic shift from global calls, and Country engagement developers – who have a critical engagement and brokering role – have been recruited and will be in post in October 2015.

Management changes, late contracting of projects and delays in project start-dates have led to fewer than anticipated grants: 37 rather than 92 scaling and innovation projects by the end of year 2[1]. Moreover, these 37 projects were on-going as of May 2015 (the date of milestone 2) rather than complete and as 11 projects were at a very early stage this review is effectively able to draw data from 26 grants. Project reporting has also been patchy reflecting the absence of an FMC M&E system or sufficient M&E staff until late in the year. While delays were foreseen given the substantial management changes implemented, the net outcome is that only 28% of the originally planned number of grants are sufficiently advanced to be contributing output data at the end of two years. 15 of the 30 research grants originally planned were contracted in Year 2, and research outputs have also been delayed: there are dependencies on granting of innovation and scaling grants to provide sufficient possible cases. Overall, as could be foreseen given the major investment in management structuring, performance against Y2 KPIs was poor (14 of 25 KPIs met; majority of KPIs designated payment milestones not met), which has implications for funding by donors for whom disbursements are conditional on past performance.
[1] According to FMC KPIs.

While the above factors have contributed to relatively poor scores against logframe output milestones the progress per project has been better than originally expected for those sampled. Independent evidence on progress is provided by a sample of four Evaluation Management Unit (EMU) case studies – summarised in Annex 1. Discussion in the FMC Annual Narrative Review (ANR) has been supplemented by the MEL manager contacting country staff – available evidence on each project is summarised in Annex 2. Although this evidence is limited it does indicate progress against outputs. There is also evidence of contribution to the programme outcome from two on-going projects at county level in Kenya and around a drug stock out project in South Africa.

Key findings are that:
- The combination of “traditional” community-level development activities and technology adds value (Caritas project in Kitui, Kenya; CAFOD in Kenya and Uganda). Likewise, off-line support is vital to implement tech tools (e.g. the ICW and Voice for Women projects in Indonesia and the limited Smartsol platform uptake in OCOS Ghana).
- Technology tested by MAVC has the potential to have an influence beyond MAVC: e.g., Bahawalpur Service Delivery Unit (BSDU) technology was built on to support flood victims in Pakistan; MAVC-funded innovative radio programmes in Kitui that brought local leaders into the studio to talk about issues raised by women encouraged a subsequent ”wake up the leader” radio programme that also reaches 900,000 people; and officials drawn into radio discussion by OCOS, Ghana have been engaged in subsequent radio programmes); and
- Devolution, with new requirements for participatory planning, is providing good opportunities for MAVC at the sub-national level (e.g., village level in Indonesia and county level in Kenya).

As the cost of brokering and capacity building is high relative to the spend on grants, effective learning and taking project results to scale is essential for VFM. A clear Research, Evidence and Learning (REL) strategy was produced in year 2. MAVC should now articulate how tested initiatives are positioned for the next stage of investment, what level of evidence is required to support the next investments, and who would be the potential investors for next stages.

On-going projects also indicate success factors that need to be in place for new grantees. Government engagement at the sub-national level at which the grantee is working is critical and MAVC will need to take advantage of opportunities this presents when it arises: (e.g., incentives for County Ministry of Health staff to achieve accessibility targets in Turkana, Kenya, pressure on and from elected county representatives in Kitui Kenya, the District Governor’s interest in the project, Bojenegoro, Indonesia). These opportunities or external drivers are highly context specific. Without external drivers, a supportive national policy context may not help grantees engage with government at a local level. If country strategies and CED brokering are effective we should expect to see a large proportion of grantees in year 3 gaining from this type of external driver.

There is a question of the appropriate mix of established and small, “unusual suspect” grantees that is consistent with the required pace of progress. This will be much clearer once CEDs are in place and should be reviewed in December 2015

Early evidence suggests that MAVC projects do have the potential to deliver expected outputs and, in time, the programme outcome. However, given the delays to date (in part reflecting implementing recommendations of the management review) it is unlikely that this can be achieved within the timeframe originally envisaged. Provided that management capacity has been sufficiently strengthened, there is a case for a no cost extension to the programme.

The review of management progress against recommendations was conducted in parallel with this programme review. It indicates that implementation of recommendations is underway in all areas, with completion expected in November (the FMC originally targeted September). The review assesses that while it is too soon to know the extent to which these management changes will result in improved performance, progress over the last six months provides a mix of positive and negative signs for the future. In summary:
- The Interim Program Director has provided positive leadership over recent months, strengthening delivery focus, coordination and communication.
- However, while progress has been made on identifying the core mission of MAVC and designing a tool for tracking grants, it remains difficult to define a clear synthesised reference for assessing the ‘health’ of the grant portfolio and the performance of the programme as a whole. The value addition of the significant investment in grants infrastructure, including the engagement and brokering function at country level needs to be demonstrated, in order to justify this investment. This not yet captured in the recently revised KPIs.
- Challenges in recruitment and turnover during the transition continue. Appointments have not yet been made for the two senior positions of Program Director and Country Program Manager; this presents considerable risk.
- Hivos continues to under-perform on financial management and there are still serious concerns over their ability to forecast accurately. The implementation of the accounting/ finance processes has not resolved underlying capacity. The turnover of staff does not appear to explain the degree of budgeting and reporting challenges.
- It seems unlikely that the project will deliver its planned results without a no cost extension, as was foreseen in the management review. A decision on the no cost extension should therefore be made as soon as possible. If not approved, continued investment in Years 3 and 4 should be justified against what can be delivered in that timeframe.

Summary of recommendations for the next year

General
1. The FMC will need to proactively ensure sufficient management oversight to address continuing risks, including the transition between interim and permanent program directors, maintaining focus on strong internal consortium coordination, and ensuring KPIs for Year 3 are met.
2. It is essential that sufficient financial management capacity is established and demonstrated through immediate improvements in budgeting and reporting to avoid further disruption to delivery of results and loss of confidence on the part of the donors.
3. A bi-annual report is due in December: output data from this report may be useful in reviewing the programme trajectory of travel, now that the management review recommendations are largely implemented. Re-scheduling the Steering Committee meeting to January would enable this data to be considered in decision-making
4. The FMC will need to put forward a revised proposal for a no cost extension for donor review before the planned Steering Committee, as well as a summary of what can be achieved by the end of Year 4 and what will be stopped if a no cost extension is not approved.
5. Evaluation Management Unit to work with FMC to review logframe milestones and indicators, for confirmation following the decision of donors on the no-cost extension, with additional evaluation advisory support as required
6. The FMC will need to ensure that the proposed mix of high risk “unusual suspect” and established grantees over year 3 is consistent with agreed milestones, and communicated with Steering Committee for endorsement.
7. While progress has been made on identifying the core mission of MAVC and designing a tool for tracking grants, it remains difficult to define a clear synthesised reference for assessing the ‘health’ of the grant portfolio and the performance of the programme as a whole. Perform qualitative assessments of the MAVC grant portfolio and synthesize findings and corrective actions planned to address gaps, and share this assessment with the Steering Committee.
8. Investment in the brokering function should be justified through evidence of its effectiveness, which should be captured in the KPIs
9. MAVC needs to strengthen relationships with governments and multilaterals to facilitate uptake of project findings

Scaling
1. The FMC should define their innovation pathway, with stages. It should explicitly identify who might be the next investors. This could be the national public sector such as a municipality, or county-level government, private sector or international institutions. This should form the backbone to understanding the evidence requirements for innovation-to-scaling, and scaling-to next stage. This should be presented to the next Steering Committee meeting.
2. The programme needs to put in place all the necessary ingredients to facilitate scaling of MAVC innovations by others (including stronger evidence of results and relationships with government). The FMC should report on this as soon as possible, at the latest by December 2015.

Operational
1. Technology Fellows and Research Mentors and EMU case study engagement with grantees should include a simple, clear statement of what is involved and expected from both parties including a statement of deliverables by December 2015.
2. The November 2014 Programme Engagement and Country Strategies contain useful ideas on how different stakeholders can be enageed to address country-specific issues, and the challenge is now to implement these effectively and efficiently. In particular, realistic and practical plans are needed on how to attract and engage the private sector. FMC to present to the next SC meeting.
3. Implement the 2014 AR recommendation that the FMC explain how they will put in place incentives for contracting out services (including host organisations for CEDs) where this will produce VFM and how this decision can be made transparent to donors. Action: FMC to produce a note on this for the next SC meeting.

MEL and communications
1. EMU and IDS to discuss the potential to document EMU case studies simultaneously and in coordination with Research mentoring in up to 3 cases and to report by December 2015.
2. FMC to continue to strengthen communications in order to provide donors with summary evidence on project progress against outputs and outcomes in semi-annual reports.
3. MAVC grantees should briefly document and report unplanned use of MAVC-funded technology that can be usefully investigated by FMC country programme staff
4. FMC should rapidly put in place the Qualitative Assessment Scoring (QAS) system proposed by IDS, with any necessary piloting (to inform results in time for the year 3 annual review).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
Making All Voices Count: a Grand Challenge for Development (MAVC) is a partnership between DFID, Omidyar Network (ON), the Swedish International Development Cooperation Agency (Sida), and the United States Agency for International Development (USAID). It is inspired by and supports the goals of the Open Government Partnership (OGP), which all MAVC donors are funding, through foundation contributions (Omidyar Networkand government contributions (UK, USA), and to which the UK, USA and Sweden have signed up as participating OGP countries. MAVC focuses global attention on innovative solutions and uses of technology that amplify the voices of citizens and enable governments to respond effectively. In turn, it aims to contribute to the creation of more effective democratic governance and accountability.

The UK is providing up to £6.7 million (approx. USD10m) to the partnership from 2013 – 2017 with overall combined funding of USD45 million. Our investment will (a) support innovative ideas, (b) help scale existing, successful initiatives, and (c) finance research to help us understand what works. The fund works in twelve countries in Asia and Sub-Saharan Africa, was approved in December 2012, and was contracted through a competitive procurement process to a fund manager consortium (FMC) led by Hivos, and supported by the Institute for Development Studies (IDS) and Ushahidi. A two month inception concluded in July 2013, and MAVC was launched by President Obama at the United Nations General Assembly (UNGA) in September 2013. The first call for proposals was opened on the back of this announcement on 23rd September 2013. MAVC reports to a Steering Committee (SC), chaired by DFID, tasked with determining and guiding overall strategy, policy, and learning design and providing feedback and advice on how to make MAVC more effective. To date the SC has met quarterly, but will be moving to meetings twice per year (once virtually, once face-to-face). As lead funder, DFID both holds the agreements with the individual funders and is the contract holder for the Fund Manager (Hivos). As such, DFID manages the contract informed by the views of the donor group and consistent with the SC steer where relevant. DFID and Hivos meet at least twice a year on contractual requirements, and often monthly on rolling issues. The broader group of donors (USAID, Sida, ON) contribute to the strategy, policy and overall design issues via the Steering Committee, and to management, delivery, and reporting issues via DFID. DFID coordinates a monthly meeting of the donor group.

MAVC has evolved a two tier approach: country strategies and extensive brokering in tier one countries (Kenya, South Africa, Indonesia, Philippines, Tanzania, Ghana) with lighter, strategic thematic targeting for tier two countries (Bangladesh, Pakistan, Mozambique, Nigeria, Uganda, Liberia).

The context in which UK and other donor support is provided
Democratic systems are inhibited by timescales and practices that provide only occasional opportunities for citizens to express their views formally about governments, such as during elections. Many people, including the poor and disadvantaged (women and girls less so) nevertheless have access to tools and data that can enable them to express their views and network with other people with similar problems on a more regular basis, through mobile phones and the internet. Increasingly, citizens expect to be able to use these data and tools in relation to government performance on specific policy issues, rather than waiting to use a single vote in a ballot box.

In reality, there can be few opportunities to do so. Even where citizens’ voice is communicated regularly and effectively, it is often given inadequate consideration by governments. Governments may lack incentives and face constraints on their ability to release useful government data, or to consult and respond to citizens’ concerns, particularly at local levels. Such limited interaction translates into few opportunities for officials to understand public expectations and few incentives to meet them. This results in poor governance, citizen alienation, and discrimination. In short, open government depends on closing that feedback loop between citizens and the government.

Making All Voices Count will help deliver that feedback loop in twelve countries in Africa and Asia. MAVC supports (1) greater opportunities for citizens to provide feedback, (2) improved capacity for governments to translate citizen feedback into policy action; (3) incentives and capacity for citizens to engage with government in policy improvement, (4) government to engage with and respond to citizens.

The spread of web and mobile technology offer new ways for citizens to engage with their governments. There is also potential to use local radio in new ways. Meanwhile, growing numbers of governments are opening up data to enable citizens to access and use it. In some MAVC countries (e.g. Kenya, Indonesia, the Philippines), devolution is increasing the scope for citizen-government engagement but also providing challenges of working with lower technological competencies. MAVC is particularly interested in solutions that embrace the opportunities presented by mobile and web technologies, and will focus on supporting a wide range of groups (technology-focused groups as well as civil society organisations with grassroots networks) to harness the potential of mobile and internet technologies and open data to expand their reach and impact.

Expected results
The expected impact of MAVC is “All people, including the poor are able to engage and call to account public and private institutions on policy issues that matter most to them”.

The expected outcome is “Improved relationships and increased opportunities for constructive dialogue between citizens and governments (in MAVC countries)”. By May 2017, the programme aims to have:
- 1.2 million citizens (50% female) receiving response from relevant government agencies where MAVC operates
- 20 improvements in relevant government policy
- A 20% increase in positive user/citizen satisfaction ratings for both men and women

The planned outputs are:
1. Increased access to innovative solutions for citizens and government agencies.
2. More citizens, intermediaries and government actors make regular use of innovative solutions to support constructive interactions between citizens and governments.
3. Evidence and learning generated through MAVC is taken up by grantees, donors, government agencies and CSOs.
4. Increased global network of funders, experts and mobilisers supporting MAVC objectives.

Year 2 saw implementation of 32 grants from the year 1 Open Call for Proposals (£1,925,251[2]); a second-round of the Global Innovation Competition (GIC, 8 awards sharing £300,000); ten tech brokering events and four Pitching Competitions; one tech and one research fellowship were awarded and 21 grants received mentoring support. 15 open research grants were awarded or underway in year 2.
[2] Figures reported by the FMC in the 2014 ANR.

Following the Sandstone Management Review and March 2015 SC, there has been a significant restructuring within the FMC including seeking a new Programme Director (PD) and Country programme manager. An interim PD was brought in starting July 2015 and she has significantly strengthened the focus on delivery and integration of the FMC. This includes: getting the FMC up to date on KPIs; getting all FMC partners to jointly map projects against the theory of change and to set out simplified hypothesis trees within the theory of change that are used to frame time-bound deliverables for programme staff.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
This review is based on the independent Evaluation Management Unit (EMU) analysis based on:
- Results from EMU case studies of 3 scaling and 1 innovation grant [source 1]
- The fund manager consortium annual narrative report for June 2014–May 2015 (FM ANR) supplemented by MEL manager follow-up with grantees [2];
- Documents submitted to the March 2015 Steering Committee (SC) meeting [3];
- EMU attendance at and review of the 2015 GIC event in Jakarta [4];
- An EMU review[3] of Research, Evidence and Learning component strategies, activities and outputs in year 2 and review of initial IDS-commissioned Learning Review findings [5]; and
  [3] Vogel (2015), Process Review of MAVC’s Research, Evaluation and Learning Component, September.
- Interviews with 11 key informants from the FMC, SC, donors and MAVC partners [6]

The following caveats need to be borne in mind when considering the progress against milestones. During year 2, following management changes, the late contracting of projects and delays in project start-dates led to fewer than anticipated grants (37 rather than 92). The 2015 milestones are based on the original plans for 92 grants, and are therefore now overly ambitious. In addition, data is only available on a total of 22 out of 37 innovation and scaling projects (depending on the output indicator), as the remainder are at a very early stage (9 projects), delayed by the ebola outbreak (2 projects) or have not reported (4 projects). Project reporting has also been patchy reflecting the absence of a programme M&E system or sufficient M&E staff until late in the year. Some indicators have not been disaggregated and so are assessed as totals rather than by gender. While some milestones are expressed as percentages and therefore technically met, the absolute results underlying the percentages are significantly lower than originally planned.

However, grants implemented in year 2 have produced some encouraging results with evidence of contribution to the programme outcome. This includes:
- Joint service plans between communities and four health facilities in Turkana county, Kenya resulting in improved health services on offer (reflecting government implementing monitoring of local health staff and providing access to budgets);
- Following engagement around GIS mapping, county governments in Marsabit and Samburu counties have responded to citizen concerns by recovering stolen livestock and purchasing ambulances; and
- Citizen journalism on drug stock-outs in South Africa has led to the National Department of Health following up on monthly reports, with documented cases emerging of improved service delivery.
- FMC reporting evidence of feedback loops are in place in 15 (out of 37) projects: for example, under Health e-news, the National Department of Health follows up on the monthly medicine stock-out reports, thus ensuring better service delivery for people served by these clinics. Likewise, the IRC score card in Turkana has secured a change in local government process for health facilities. In other cases (i.e. ICW, OCOS and Yowzit), there is work in progress but it is too early to see changes in core government processes

The challenge going forward will be to deliver effective country programmes using the new country engagement capacity in tier 1 countries. This will require active CED brokering and engagement to implement country strategies but also provide support to identify grant opportunities and the potential to scale up existing grantees and supervise grantees implementing clearly stated basic theories of change. An enhanced focus on delivery will need to be maintained to achieve the stated programme outcome. Early evidence suggests that MAVC projects do have the potential to deliver expected outputs and, in time, the programme outcome. However, given the delays to date (in part reflecting implementing recommendations of the management review) it is unlikely that this can be achieved within the timeframe originally envisaged. If there is sufficient confidence in management capacity going forward, there is a case for a no cost extension to the programme.

Overall output score and description:

Overall score = B

At the end of year 2, virtually all grants were on-going rather than complete but there are some early results from innovation, scaling and GIC grants:

- In terms of MAVC reach (Output 1), more than 1.5 million citizens were reported to be using innovative MAVC solutions by 19 grantees. This figure does not include listeners to project-related radio shows or those targeted by marketing campaigns. ‘Yowzit’ - providing information on, as well as rating and reviewing the quality of, public sector services - provides an example of a successful innovation grant with 650,000 users of content on their website (see Annex 2). Overall, evidence from the EMU case studies and the Learning Review suggest that innovative use of radio combined with community-based mobilisation can be particularly effective – see the Caritas Kitui summary in Annex 1.

Findings from reviewing the various evidence sources are also that:
- Devolution with new requirements for participatory planning is providing good opportunities for MAVC at the sub-national level (e.g., village level in Indonesia and county level in Kenya) [1,6]. This has been recognised in nearly all tier 1 Country Plans [2]
- Technology proven by MAVC may have an influence beyond MAVC (GIC, BSDU tech was built on to support flood victims in Pakistan [2], MAVC-funded innovative radio programmes in Kitui to bring local leaders into the studio to talk about issues raised by women encouraged a subsequent ”wake up the leader” radio programme that also reaches 900,000 people and officials drawn into radio discussion by OCOS, Ghana have been engaged in subsequent radio programmes [1])
- Government engagement at the sub-national level is proving critical and MAVC will need to take advantage of opportunities produced where this engagement is present (e.g. incentives for County Ministry of Health staff to achieve accessibility targets in Turkana, Kenya [1], pressure on and from elected county representatives in Kitui Kenya [1], the District Head’s interest in the project, Bojenegoro, Indonesia [6]). These opportunities or external drivers are highly context specific. Without external drivers, a supportive national policy context may not help grantees engage with government at a local level (e.g. local officials withholding data for investigation of local corruption cases, ICW [1] or learning reported by CMRA [5])
- The combination of “traditional” community-level development activities and technology adds particular value (Caritas in Kenya [1]; CAFOD in Kenya and Uganda [2]). Likewise, off-line support is vital to implement tech tools (e.g. traditional evidence gathering to follow-up reports of corruption, ICW [1]; Voice for Women in Indonesia [2], and limited Smartsol platform uptake in OCOS Ghana [1]).
- A corollary of relying on combined technological and traditional inputs is that successful scaling grants may deliver improved engagement outcomes and impact but only test an innovative technology component (e.g. IRC score card, in Turkana [1])
- Tech competencies matter – although documented in the literature and highlighted in the EMU inception report; some grantees are “discovering” the illiterate cannot use SMS [1,5].
- Innovative use of radio combined with community-based mobilisation has been the most successful tech in the 5 EMU case studies in supporting increased access to innovative solutions. This is illustrated in the results from the EMU evaluation of the Caritas Kitui innovation grant (Annex 1). The Learning review also finds that grantees have learned that radio – a traditional technology – can be used in innovative ways.

Key lessons

The current thematic focus of Country plans is useful and there needs to be sufficient operational flexibility to take advantage of opportunities for engagement with government at national level (e.g. restricting grants to just one or two counties is unlikely to allow this).

Factors influencing citizen engagement (e.g. power relations and technological competencies) are clearly articulated (including in the MAVC theory of change) even if grantees have not always picked these up, or been supported to do so. The set of factors influencing local government engagement is less clearly articulated (appearing as capacity to respond in the ToC). However, MAVC findings in this area are relevant. External political drivers encouraging or constraining local government/service provider response to citizen engagement appear to be important. Below this level, a number of practical issues determine responses. A recent MAVC research output[4] that systematically reviews the literature on ICT reporting of water service outages and service provider response finds that availability of funding but also parts, a mechanic and clear responsibilities determine whether repairs are undertaken. Evidence from case studies in Kenya (health) and Ghana (multi-sector) confirm the key role of capital budgets held above the level of those engaging with citizens. Yet, the Kenya score card example also shows that some important government responses (“enforcing central government rules” by monitoring and disciplining absent staff) are less budget dependent. Grantees could therefore gain by systematically thinking through the assumptions behind the expected government response from citizen engagement. Examples from completed grants and interaction with programme engagement staff should be used to help new grantees think through factors likely to determine both citizen and government engagement and response.
[4] Welle, Williams, Pearce and Befani (2015), Testing the waters: a qualitative comparative analysis of the factors affecting success in rendering water services sustainable based on ICT reporting, Wateraid, June.

If scaling grants are expected to test solutions and position them for scale[5] we should know how much difference a scaling grant makes to the quality of public services as a result of improved citizen-government engagement as well as how and why it contributes to this engagement. Research grants are not currently designed to systematically provide this evidence. The FMC should determine how this can be achieved.
[5] Equivalent to stage 2 in the USAID innovation chain - see https://www.usaid.gov/div/apply.

Key actions
Actions are associated with each recommendation in the Summary Sheet

Has the logframe been updated since the last review?
No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased access to innovative solutions for citizens and government agencies
Output number per LF		1	Output Score	B
Risk:		High	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
Risk of not achieving output (40%)		Medium	Risk if output fails to outcome (60%)	High

Indicator(s)	Milestones	Progress	Comments
1.1 # citizens using innovative solutions for improved participation that are linked to MAVC (supported by MAVC or MAVC innovations taken up by others). Where possible gender disaggregated	The milestones at May 2015 (end of year 2) for this indicator are 2.5 million men and 2.5 million women	B-moderately did not meet expectation. Based on 1,497,020 from 19 projects	The milestone is based on 92 grants originally expected at this point rather than 37. Data is drawn from 19 projects providing data. Data has not been disaggregated; disaggregation appears not to be feasible across the board. Reported figures exclude listeners to the Caritas Kitui radio programmes & an influenced radio programme. These reached > 1 million.
1.2 # of MAVC innovation and scaling initiatives in which citizen (gender disaggregated where possible) and government actors have engaged.	25 by May 2015	B-moderately did not meet expectation 20, based on 23	Milestone based on 92 grants. Indicator assessed against 23 projects
1.3 % of MAVC initiatives that provide additional opportunities for participation in governance to people (individuals, groups) that normally lack influence in society i.e. Women, LGBT, Disabled people, marginalised ethnic communities	15% by May 2015	A–met. 24%	Calculated as % of 37 grants, and thus the indicator is technically achieved, but representing lower absolute value than originally planned. 9 projects were able to provide opportunities for marginalised groups, 15 were not specifically targeting marginalised groups.

Key points related to this output
- The move to brokered grant making is intended to bring in smaller, less experienced grantees. This may well lead to funding earlier stage innovations with a more limited reach than has been the case for existing grantees. In order to reach milestones, scaling projects will need to offset this.
- Innovative use of radio combined with community-based mobilisation has been the most successful tech in the 5 EMU case studies in supporting increased access to innovative solutions. This is illustrated in the results from the EMU evaluation of the Caritas Kitui innovation grant (Annex 1). The Learning review also finds that grantees have learned that radio – a traditional technology – can be used in innovative ways.
- Technical challenges on the gender disaggregation of data exist; the transition of M&E responsibilities within the consortium should provide sufficient capacity to address this in Y3, including through proposing revision of indicators as appropriate.

Summary of responses to issues raised in previous annual reviews (where relevant)
As recommended in 2014 but not achieved, future FMC annual narrative reports (ANR) should report by gender for Output indicator 1.1, and provide a basis for any estimates made.

Recommendations
1. Tech Fellows, Research mentors and EMU case study engagement with grantees should include a simple, clear statement of what is involved and expected from both parties including a statement of deliverables by December 2015.
2. The FMC will need to ensure that the mix of high risk “unusual suspect” and established grantees over year 3 is consistent with agreed milestones.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	More citizens, intermediaries and government actors make regular use of innovative solutions to support constructive interactions between citizens and governments
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	36%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
Risk of not achieving output (40%)		High	Risk if output fails to outcome (60%)	High

Indicator(s)	Milestones	Progress	Comments
2.1 Number of citizens that are actively interacting with government agencies using SMS, call-in, online platforms funded by MAVC. This will be measured once the platforms start to be used, from Year 2 onwards.	Women: 300,000 Men: 300,000 by May 2015	A–met. 757,692 based on 13 projects	Milestone based on 92 grants. Grantees did not disaggregate by gender. In some cases, grantees did not have the capacity to compile data by gender e.g. Analysis of Facebook likes and comments. In some cases it would require separate survey work e.g. to all users of SMS. However, FMC should be able to support some grantees to report by gender and certainly where the gender of platform users is known (e.g. Caritas Kitui or OCOS).
2.2 Number of partnerships bringing together citizens and government bodies supported by MAVC that continue at least a year beyond grant life or brokering activity.	10 by May 2015	B-moderately did not meet expectation.	Delays to contracting at the start of the programme prevent this milestone from being achieved at this point. Evidence from the one completed project suggests that MAVC supported women will continue to engage with sub-county and county government in formal consultative spaces and also that county administration representatives will continue to be held to account on local radio as radio stations now see this as a popular radio show format. FMC provide evidence of an additional 6 grantees where partnerships with government look likely to continue post project.
2.3 % of (local) governments or government champions that are participating in MAVC that integrate feedback loops in their core processes	30% by May 2015	A–met. 40% based of 37 grants	FMC claim feedback loops as a result of 15 projects. As these are on-going projects, evidence is based on changes made to delivery by government. This varies. So, for example, under Health e-news, the National Department of Health follows up on the monthly medicine stock-out reports, thus ensuring better service delivery for people served by these clinics. Four stories detailing complaints followed up directly and resolved by government officials. Likewise, the IRC score card in Turkana has secured a change in local government process for health facilities. In other cases claimed by the FMC (i.e. ICW, OCOS and Yowzit), there is work in progress but it is too early to see changes in core government processes.

Key Points
The main contributors to progress against indicator 2.1 are three on-going projects: Yowzit (innovation grant), Stat.io (innovation) and BDSU (GIC).

For indicator 2.2, FMC examples of partnerships that look likely to continue include: Black Sash-Government of South Africa on integration and institutionalisation of citizen feedback into the government's performance monitoring and evaluation system; Health e-news – Government of South Africa (Department of Health) on monthly medicine stock-out reports; and ODI - Uganda Ministry of Finance for on-line budget publication (see Annex 2). Evidence from EMU beneficiary surveys and interviews with county government officials suggests that the women supported by the Caritas Kitui project in Kenya will continue to engage with local government post-project (see Annex 1).

For indicator 2.3, there are examples of both sector and local government champions integrating feedback loops as a result of on-going projects. In some cases it is too early to be confident that this has resulted in changes in core processes. The strongest evidence of progress comes from the Health sector but in very different contexts: the South African Department of Health-Health e-news partnership and the Kenya Turkana county – community joint sector plans supported by the IRC score-card (see Annex 1)

In response to recommendations in the 2014 AR the FMC proposed a number of actions to the November 2014 Steering Committee meeting to strengthen government engagement. Having Country Engagement Developers (CEDs) with the required skills and experience, with support of the Country Programme manager, is critical to achieve this improved engagement. Following the management review and restructuring, the CEDs will be in post in October 2015 and the Country Programme manager in Dec 2015. This is expected to have a significant impact on this Output in year 3.

It will not always be possible for grantees to disaggregate reporting by gender. However, it is certainly possible where the gender of platform users is known (e.g. Caritas Kitui or OCOS) and there will be other cases where the FMC may be able to support grantees to analyse platform data by gender.

Summary of responses to issues raised in previous annual reviews (where relevant)
The country planning approach, CEDs and a new approach to strategic partnerships is expected to have a significant impact in Tier 1 Countries but a limited effect in Tier 2 Countries. The engagement strategies for Tier 2 countries should be defined and presented to the Steering Committee

The 2013 AR stated that “Should limited responses from private sector emerge, committing to targeting this sector, providing an update by February 2014, and adapting the theory of change as is necessary”. There has indeed been a limited response from the private sector and the FMC agreed with the SC in June 2014 that the overall Theory of Change did not require alteration but the focus needed to be on the context and mechanisms for improved engagement within country plans. However, incentivising private sector involvement in MAVC has only really been successful in South Africa and MAVC lacks the commercial incentives that exist in the Water for Food Grand Challenge, for example[6]. The closest equivalent of private sector actors with an incentive to participate identified by the FMC are social entrepreneurs and some thought will be needed to engage with them.
[6] The agriculture sector provides a significant market for commercial suppliers of technology for water in agriculture

Recommendations
The November 2014 Programme Engagement and Country Strategies contain useful ideas on how solution providers can be engaged and the challenge is now to implement these effectively and efficiently. In particular, realistic and practical plans are needed on how to attract and engage the private sector, particularly social entrepreneurs. Advice may be sought from donors with specific expertise in this sector (e.g., Omidyar Network). FMC to present to the next SC meeting (Dec 2015).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Evidence and learning generated through MAVC is taken up by grantees, donors, government agencies and CSOs
Output number per LF		3	Output Score	B
Risk:		Low	Impact weighting (%):	19%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
Risk of not achieving output (40%)		Low	Risk if output fails to outcome (60%)	Low

Indicator(s)	Milestones	Progress	Comments
Number of MAVC research outputs accepted for publication in peer-reviewed journals	2 by May 2015	B-substantially did not meet expectation.	IDS staffing was brought up to strength during Year 2, following challenges detailed in Y1 AR and Management Review. Broader delays to grantee contracting in the program as a whole has also delayed research grants, and hence the production of research outputs.A number of peer-reviewed journal and other articles are underway for publication in Y3, as the research grants pick up pace.
Number of MAVC countries’ OGP Action Plans reflecting MAVC research findings	Research project based on first 2 years of IRM data completed including research uptake plan duly implemented	B-moderately did not meet expectation.	Research plans were revised as a number of others in the sector were already looking at IRM data and the decision was made to focus on case studies of vertical integration in the Philippines and Ghana. The first phase of research in the Philippines is complete (6 case studies and a synthesis paper). The 2nd and 3rd phases are about to begin.
% of MAVC Learning Event participants who report resulting behaviour change	50% by May 2015	B–moderately did not meet expectations.	A survey of 37 attendees a year after the event produced 13 responses (35%). Of these, 92% report using learning from the event. The data is not available to demonstrate the indicator is met. However, EMU de-brief of all attendees at the end of the event in July 2014 found that almost all grantees reported relevant learning.

Key Points

The recent EMU review of the REL component was based on the following: REL Strategy including revised Theory of Change; MAVC Learning Strategy; interim outputs from nine Practitioner Grants; outputs from IDS research funds; the concept note for Learning Event 2015, documentation from the 2015 research and practitioner calls, including internal selection documents; EMU Case Studies; and an interview with the REL manager). This review finds:
- Although the programme’s research strategy (produced in July 2013) has guided the programme’s research work, the revised and published REL strategy is clear and responds well to the 2014 AR recommendation to define clearly the different types of research, their purpose and how the grants fit together to a wider group of stakeholders;
- The REL strategy describes the linkages between REL and Innovation and Scaling Grants in terms of Practitioner Research Grants which would produce evidence and lessons about individual initiatives; However, difficulties in sourcing suitable practitioner projects within MAVC has led a change in strategy whereby non-MAVC practitioners will be considered for Practitioner Research Grants to produce evidence and lessons from a wider variety of projects.
- MAVC has not defined its ‘Innovation Pathway’ and it unclear how to position tested initiatives for the next stage of investment, what level of evidence is required to support the next investments, or who would be the potential investors for next stages. Consequently, it is not clear within MAVC what evidence is required to support scaling from innovation to scaling grants and scaling beyond this. Interviews with donor partners suggest a desire to know how much difference a scaling grant makes to the quality of public services as a result of improved citizen-government engagement as well as how and why it contributes to this engagement.
- The engagement and uptake strategies are developed at the level of each project and the REL team provides detailed coaching and mentoring to develop an engagement and uptake strategy. This seems appropriate as an approach. Going forwards, engagement and uptake at country and portfolio level will be needed.
- Outputs from Practitioner Grants look interesting, because the learning from these projects could have more resonance and credibility with practitioners involved in innovation grants, compared to more academically produced outputs.

Preliminary conclusions of the REL-commissioned learning review are that:
- There has been implicit experientially based learning and some empirically based learning & adaptation related to key assumptions in the TOC, though it is not new:
  - that MAVC could identify & mobilise key actors through grantmaking and brokering
  - that these actors, particularly government could develop the capacity to make tech accessible & citizens would use it
- There is a need to achieve greater depth of learning, with reference to empirical research and a power lens to ask ‘so what questions’? Do some of the key assumptions in the MAVC TOC hold? What assumptions or approaches need to change?
- This process may be supported by the development of clear definitions for how empirical research and related learning differs from experiential learning and the implications for internal and external use and communication

Recommendations

The FMC should define their innovation pathway, with stages. It should explicitly identify who might be the next investors. This could be the national public sector such as a municipality, or county-level government, private sector or international institutions. This should form the backbone to understanding the evidence requirements for innovation-to-scaling, and scaling-to next stage. This should be presented to the next Steering Committee meeting.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased global network of funders, experts and mobilisers supporting MAVC objectives
Output number per LF		4	Output Score	B
Risk:		Low	Impact weighting (%):	9%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
Risk of not achieving output (40%)		Medium	Risk if output fails to outcome (60%)	Low

Indicator(s)	Milestones	Progress	Comments
4.1 Partnerships formed to support MAVC objectives	MAVC-based partnerships support MAVC objectives in at least 1 citizen-state policy process (national or international)	A–met.	MAVC formed a partnership with the Department of Performance Monitoring and Evaluation (DPME) in South Africa, and subsequently an MOU was signed between DPME and Black Sash, a CSO, to pilot the integration and institutionalisation of citizen feedback into the government's performance monitoring and evaluation system.
4.2 Number of times MAVC demonstrably contributes policy input to relevant multi-national policy development process leading to change at national level	2 examples of MAVC substantive input into multilateral and multinational policy discourse on open governance	C-substantially did not meet expectation.	MAVC staff made presentations at events held by the African Union, the Open Government Partnership and the 8th Pan African congress, and at the 3rd Global Open Data Conference and the launch of the World Bank Group’s Massive Open Online Course (MOOC). Work will continue with OGP in year 3. However, the FMC does not claim these as already providing substantive input into multilateral and multinational policy discourse.
4.3 % of innovations funded by MAVC that receive subsequent scale-up funding (by MAVC or others)	3% by end of May 2015	A–met.	Although the first innovation grant only finished in May 2015 and so no scale-up funding by MAVC has been possible, two projects (BSDU, Caritas Kitui) have seen replication of MAVC-funded ideas. The FMC have identified 3 on-going innovation projects as likely candidates for scaling (see Annex 2).

Key Points

The examples of BSDU and Caritas Kitui illustrate unplanned replication of different technologies proven in a local context. The GIC winner, BSDU (led by the District Coordination Officer of Bahawalpur district in Punjab, Pakistan) used a mobile app combined with geo-tagging to monitor health and education services in his district, and make that information available to the public. In September 2014, as severe floods swept across Pakistan, the District Coordination Officer was asked to build on the BSDU project to develop an application to track flood-affected victims to facilitate distribution of food and medicine. In the case of the Caritas-Kitui project, MAVC-funded innovative radio programmes in Kitui that brought local leaders into the studio to talk about issues raised by women encouraged a subsequent ”wake up the leader” radio programme that also reaches 900,000 people. There is potential for other unplanned use of MAVC-funded technology to occur but grantees will not necessarily document this unless they are asked to. As grants complete in year 3, we should also expect to see the planned scaling of MAVC innovations based on evidence of what works, for whom and in what circumstances. This requires a clearer idea of the “Innovation Pathway”: how to position tested initiatives for the next stage of investment, what level of evidence is required to support the next investments, or who would be the potential investors for next stages.

MAVC needs to strengthen relationships with governments and multilaterals to facilitate uptake of project findings.

Communications within MAVC has been strengthened by appointment of a Head of Communications. This has helped to eliminate the need for grantees to report to multiple consortium partners and once CEDs are in place they will be the primary point of contact for grantees. Nonetheless, donor partners believe there is still a need for improvement, particularly given that meetings are mainly virtual rather than in person. In year 3 as project and research results come through and both Head of Communication and Country programme manager roles are staffed, there is a better chance of seeing progress for this output.

Recommendations

1. FMC to continue to strengthen communications in order to provide donors with summary evidence on project progress against outputs and outcomes in semi-annual reports, and qualitative information and case studies about what the project is achieving
2. MAVC grantees should briefly document and report unplanned use of MAVC-funded technology that can be usefully investigated by FMC country programme staff
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Budgeted FMC fee costs as a share of total programme spend are 30.4% over the life of MAVC. Allocating this proportion of programme spend to consortium staff is unusual for DFID grant management programmes. However, this is not a conventional grant management programme and allowance has to be made for the costs of engagement and brokering, very small grants and a significant spend on research, evidence and learning and catalysing global action. In year 2, actual programme management costs were 21% of spend (budget=18%), grants were 28% (budget=26%), brokering was 34% (budget=33%) and capacity building 17% (budget=23%).

Implications are firstly that grants are clearly a relatively small proportion of total spend and so high value needs to be demonstrated by the results of brokering and capacity building. Secondly, this is an expensive programme in terms of fees spent on the consortium itself. To be consistent with VFM this approach must produce sufficient results and be justified as more efficient or effective than an alternative e.g. contracting expertise from outside the consortium.

Recommendation:
1. Implement the 2014 AR recommendation that the FMC explain how they will put in place incentives for contracting out services where this will produce VFM and how this decision can be made transparent to donors. Action: FMC to produce a note on this for the Dec 2015 SC.
2. Ensure that costs of brokering are clearly explained in budget narrative, and results of brokering activities are captured in the KPIs

The total programme cost/beneficiary reached by MAVC (Output indicator 1.1, 2017 target) is approximately £2.60 (US$4). Looking more narrowly at those directly engaging with the programme (Outcome indicator 1), the cost is much higher, around £22/person. Hence a key determinant of whether this provides VFM is the extent to which programme innovations are scaled and adopted by MAVC and, particularly, by others. For example, the cost/beneficiary is likely to fall to conventional levels if just one MAVC innovation is adopted nationally in one programme country.

Recommendation:
The programme needs to put in place all the necessary ingredients to facilitate scaling of MAVC innovations by others (including stronger evidence of impact and relationships with government). The new programme director should report on this as soon as possible, Dec 2015 SC latest.

VfM performance compared to the original VfM proposition in the business case
The original business case VFM proposition supported the selected option for 3 reasons:
1. By engaging on a joint effort with like-minded donors, DFID is likely to attract increased and sustainable traction to the technology for transparency field.
2. By pooling funds with the ON in particular, selected programmes are likely to benefit from their expertise in the technology for transparency field and thus be more effective and sustainable.
3. By pooling its funds with other donors, DFID will manage to increase the scale and geographical coverage of technology for transparency initiatives.

Discussions with donor partners indicate that the logic of this VfM proposition is sound but there have been challenges in making this pooled funding model work (discussed in Section F).

Assessment of whether the programme continues to represent value for money
The underlying programme logic and the VFM proposition in the original business case remain valid. Early evidence from EMU case studies confirms the potential for MAVC interventions to help secure improved public services for large numbers of beneficiaries (e.g. better health services in Turkana and women in Kitui preventing a sub-county having to rely on a failed agriculture scheme). Provided targets for reach are achieved, the grants themselves do appear to have the potential for transformational change. This combination is likely to represent value for money.

Quality of financial management
The Management Review highlighted the need for improving the management of project finances and to-date Hivos have made the following progress against the recommendations made in the review on financial management:

1. Simplified the MAVC budget structure and aligned it to deliverables, activities, budgets and resources
2. Agreed authority for PD to make cost-neutral budget adjustments within a 10% variance per budget line and to control a contingency budget of 5% of total budget (excluding grants) within the proposed criteria for use
3. Revised the timesheet template to correspond to the budget structure
4. Invoices are based on timesheets
5. Monthly financial reporting is occurring within the consortium

Recommendations still to be actioned are as follows;

1. Ensure each consortium's accounting system is coded according to the revised budget structure
2. Calculate realized staff costs against budget lines using data from timesheets for invoices
3. Introduce probability weighting in quarterly forecasting approach
4. Perform random checks for backup documentation (in addition to the annual Agreed Upon Procedures audit)

Despite implementation of the accounting/finance processes this has not resolved underlying capacity issues and raises questions as regards the organisational infrastructure (in particular of Hivos as the lead consortium member). The quality of financial management by Hivos continues to be inadequate.

The year 2 (June 2013 – May 2014) budget was not finalised until September 2014 and as yet the year 3 (June 2014 – May 2015) budget remains unapproved after multiple submissions. The poor process for the year 2 budget was one of the main triggers for the management review therefore the delay in the year 3 budget is particularly damaging in terms of donor perception of FMC competence. After agreeing the year 3 budget structure the first draft of the budget was submitted on 28 May. Revisions were requested by donors to ensure that budget planning was not overly ambitious. Several budget iterations were submitted between end May and end August: Issues included inaccurate spreadsheets (calculation errors and an absence of explanation for major variances).

Forecasting continues to be a major concern and for year 2 the budget forecast was £7.78m and actual spend was £3.65. This is also causing internal management issues for the donors who in order to earmark funds for the programme need realistic forecasts.
There have been staff changes and the departures of the Grant Manager and Finance Manager have had a negative impact. Specifically, the timing of the relocation of the finance function (consisting of the Finance Manager and Finance Officer) has led to some disruption in leading the implementing of the financial management changes and in ongoing financial management (i.e. the Finance Manager’s departure coincided with development of Year 3 budget as well as the Agreed Upon Procedures audit). It is concerning that the Hivos financial infrastructure was not sufficiently robust to prevent that the departure of two individuals had such a negative impact on the financial management of the program. If this was foreseen as a risk some mitigation measures should have been possible (e.g. delaying the relocation of the finance function).

The year 2 Financial Audit Report, which was due at the end of August, is still outstanding. The auditors have had issues with the documents presented to them, which are not yet addressed.

Recommendation: Quarterly forecasts and invoices should be within a 10% variance, unless greater variance is negotiated in advance

Date of last narrative financial report	Narrative annual report received 11 September 2015
Date of last audited annual statement[7]	Y2 Audited Financial statement received 7 August 2014: 2015 statement pending (due August 2015)
[7] Technically, Hivos produce an “AUP”, agreed upon procedure that DFID accepts as an audited annual statement

E: RISK (½ page)

Overall risk rating: High
The overall risk rating incorporates the following: Output Risks and Programme Risks.

Output Risks
Output Risks refer to the likelihood of the output not being achieved combined with the risk to the programme if the output fails to lead to the outcome.

Outcome: Improved relationships and increased opportunities for constructive dialogue between citizens and governments (in MAVC countries)”.
OUTPUT	RISK
	Risk of not achieving output (40%)	Risk if output fails to outcome (60%)	Total risk
Output 1 / Increased access to innovative solutions for citizens and government agencies	High	High	High
Output 2 / More citizens, intermediaries and government actors make regular use of innovative solutions to support constructive interactions between citizens and governments	High	High	High
Output 3 / Evidence and learning generated through MAVC is taken up by grantees, donors, government agencies and CSOs.	Medium	Low	Low
Output 4 / Increased global network of funders, experts and mobilisers supporting MAVC objectives.	Medium	Low	Low

Overview of programme risk [Update from Sandstone and DFID]
The 2014 AR identified three key programme risks:

Programme Risks
Issue	RISK
	Risk of not achieving output (40%)	Risk if output fails to outcome (60%)	Total risk
Country plans fail to identify cost-effective opportunities for MAVC	Medium	High	High
Good country plans are produced but the FMC does not have or does not bring in sufficient brokering and strategic engagement capacity to deliver ambitious country plans at the speed required to meet programme targets	High	High	High
Successful innovations occur but are not scaled up	Medium	High	High

In addition, the potential failure to put in place consistent and integrated budget reporting across consortium partners, the ambition of plans moving forward, and the investment of time required to make management changes, were noted as contributing to significant concerns of the project delivering by the end of the four year timeframe.

The risks identified in the 2014 AR remain pertinent to this review. While progress has been made in establishing capacity and plans to deliver – for example, appointment of Country Engagement Developers, appointment of Interim Program Director and progression of recruitment for permanent Program Director – whether the FMC will be able to utilise this capacity to deliver the intended results of the program will be tested during Y3.

The management review progress assessment highlighted a number of risks that may influence the effectiveness of the changes in increasing performance. The multiplicity of risks listed below is an indication that the capacity to address the risks above, and related operational challenges, is not yet assured:

1. Depending on how the CED role is supported by the Grant Management team there is a risk that internal/project management demands may limit the time for external engagement; especially in countries with many existing grantees.
2. Ambiguous roles and expectations for Country Programs Manager (and Country Engagement Developers) with respect to the Ushahidi Innovation Engagement Officers in Tier 2 countries
3. There is a potential discontinuity in the transition between the interim and permanent Program Director and Country Programme Manager positions (Program Director is currently contracted through to January 2016)
4. While the Program Director being perceived as ‘MAVC’ and not ‘Hivos’ has had positive impact, but there is some ambiguity in who is the point-person within MAVC to ensure Hivos delivers both as a member within the FMC and as the consortium lead and contract holder with DFID.
5. Information available in the grants tracker may be seen as a substitute for synthesized grant portfolio analysis, which is needed to inform discussions at the CLT and SC level about the success/current health of the grant portfolio, strategic approaches and priorities.
6. Communication of priorities to all stakeholders is key in order to avoid a mismatch in expectations. For example, while the FMC members seemed to be clear of there being a ‘donor directive’ to focus on Tier 1 countries until December, donors other than DFID did not seem to be aware of this. Furthermore, the FMC arrangements/division of tasks is likely to have some implications for the strategies, dynamics and FMC member prioritisation of tier 1 versus tier 2 countries. This does not seem to be commonly understood within the FMC and with donors and so presents a risk in terms of overall portfolio coherence.

Recommendation: Effective communication among all stakeholders should be assured by Hivos, as the Consortium lead and DFID as the donor lead.

Implementation of the accounting/finance processes has not resolved underlying capacity. The turnover of staff alone does not seem enough to explain the degree of dysfunction and may imply deeper organisational infrastructure issues. Poor performance in financial management could lead to programme disruption through delays or withholding of invoice payments

Recommendation: Substantive management oversight is required until the situation is resolved.

Uncertainty about the pending program extension decision and how it will be taken creates a risk that MAVC has invested in changes which will have time to pay off. On the FMC side there seems to be a lack of clarity in terms of the basis and timing of an application for approving a no-cost extension. Donors expect to see, by October On the donor side, there does not seem to have been much discussion of the requirements/ limitations they might have in order to process a no-cost extension knowing that an application is likely: it is understood that evidence of sufficient management progress against actions agreed in March 2015 Steering Committee meeting is required to confirm any decision. While it is reasonable that final approval for a no cost extension might only be possible after the FMC demonstrates concrete progress of MAVC, some donors are seriously considering continuing with current levels of funding and are moving into their own annual planning period which could pre-empt decisions in December or thereafter.

Recommendation: FMC is asked to prepare no-cost extention proposal and summary of what can be achieved without a no cost extension prior to the Steering Committee meeting

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
DFID on behalf of the donors has concerns about delivering within the timeframe. The budget submitted by the FMC on September 10 2014 proposes allocating unspent year 1 funds as follows: £1.17m in year 2, £1.39m in year 3 and £0.44m in year 4. Following the management review and restructuring, only 68% of the Year 2 budget was spent. The management review anticipated that restructuring would impose substantial delays that would require a no-cost extension.

Recommendation
The FMC will need to put forward a revised proposal for a no cost extension for donor review before the Dec 2015 SC

Performance of partnership(s)
Amongst the Donor Group
The donor group has worked hard to overcome some practical challenges. There was a lack of common donor vision at the outset (e.g. ON looking for small scale but SIDA and USAID looking for larger grants). There are also quite different management styles and requirements and it has taken some time for ON and USAID to become comfortable with DFID systems. The ambition of a new programme was combined with an untried and unique constellation of FMC partners and weaknesses in FMC management systems. This increased the management burden on the donor group and DFID in particular. MAVC has required significantly more DFID time than would normally be spent on a programme of this size and donors also note the challenge presented by the high turnover of DFID staff since the start of the programme life. DFID are now confident that sufficient staffing resources are available. Fortnightly calls with the Interim Program Director are held, currently, and regular updates provided to donors through email and conference calls.

Amongst the Steering Committee (SC)
The SC has moved to bi-annual meetings and the two meetings since the 2014 AR have been effective. Following the management review and restructuring the view expressed in the 2014 AR continues to hold: that we are much closer to having a shared understanding of “the rules of the game”, a clear division of responsibilities between the SC and FMC and good communications between Hivos and DFID as contract holders.

Asset monitoring and control
The issue of programme assets is defined clearly in the contract and at this point in time DFID does not have any issues with their management. DFID will review the FMC inventory of assets within the programme life.

G: CONDITIONALITY (½ page)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme evaluation design is based on evidence from EMU case studies and analysis of output indicator reporting by grantees based on a Survey Monkey and follow-up by the MEL manager. The FMC M&E system was not able to provide adequate evidence from grantees in year 2 and more emphasis is therefore placed on findings from 4 EMU case studies (in Indonesia, Ghana and Kenya x 2) for which there are midline or endline results in year 2. Additional case studies are running in Kenya and Indonesia. Funding of £50,000 transferred from the FMC for baseline surveys in year 1 has been repeated for endline surveys in year 2.

It is essential for the EMU to engage with grantees to design case studies (including baselines) well before project implementation but this has proved difficult as by the time that the FMC has approval from donors, projects are about to commence. In some cases, discussions with potential case study grantees have been undertaken but it has not been possible to mobilise regional specialists who are in high demand in the time available. EMU and IDS should discuss and identify how these challenges can be addressed. The eligibility of innovation, scaling or GIC grantees identified for research fellowships to be included as EMU case studies should be re-considered.

Responsibility for M&E has been transferred from Hivos to IDS and an IDS-based MEL manager started work towards the end of year 2. This has significantly increased programme M&E capacity. The Hivos OSIRIS system was not able to provide M&E data required for output indicators and the FMC is planning to use a new spreadsheet-based system going forward. This is likely to be fit-for-purpose but in order to deliver consistent and comparable logframe indicator evidence for grantees progress is also required in:
1. Ensuring programme staff are well trained in supporting M&E requirements. Hands on M&E support to most grantees is necessary for them to provide meaningful data; and
2. Putting in place the Qualitative Assessment Scoring (QAS) system proposed by IDS.

Given that following the management review, posts will only be filled in October 2015, we will only start to see the results of this new M&E system in the second half of year 3.

Recommendations:
EMU to work with FMC to review logframe milestones and indicators, to be confirmed following decision of donors on the no-cost extension.

EMU and IDS to discuss the potential to run EMU case studies concurrently and in coordination with Research mentoring in up to 3 cases and to report by December 2015.

FMC should put in place the Qualitative Assessment Scoring (QAS) system proposed by IDS, with appropriate piloting, to inform results available in Y3.

Monitoring progress throughout the review period
Following the delay to granting (and hence selection of case studies), the Evaluation Reference Group (ERG) met only once in year 2. It has been agreed that the ERG will meet (virtually) with the EMU twice a year. During year 2, the ERG was chaired by Julie McCarthy from Open Society Foundations. As OSF is no longer part of the donor consortium, Laura Bacon from ON will chair the ERG in year 3.

The inclusion of MEL manager in the ERG is recommended to support synergy between the MEL system and evaluation functions.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process