Annual Review

Title: Anti-Corruption Evidence (ACE) Programme / £14.1m GCSD, RED / £0.5m GOSAC (funding closed)
Programme Value £ (full life): £13.6 million (over 3 components) / £3.6m DFID-British Academy Anti-Corruption Evidence Partnership (BA ACE) – closed. / £6m Anti-Corruption Evidence (ACE) Research Partnership Consortium / £4.1m DFID-Global Integrity Anti-Corruption Evidence Partnership (DFID GI-ACE)		Review Date: / Jan 2020
Programme Code: / 203752	Start Date: / Component 1: BA ACE April 2015 (closed Sept 2018) / Component 2: SOAS ACE August 2016 / Component 3: GI ACE November 2018	End Date: / Aug 2021

Summary of Programme Performance
Year	2016	Jan 2017	Jan 2018	Jan 2019	Jan 2020
Programme Score	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	Link to all published documents
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Anti-Corruption Evidence (ACE) research programme will produce new, operationally-relevant evidence on tackling corruption. Research outputs will, in turn, support more effective, evidence-based anti-corruption initiatives by DFID and its partners in a range of DFID priority countries.
DFID committed up to £9.6m for ACE (April 2015 -July 2021); and in June 2017 approved a further £4m to fund a second round of research grants. DFID’s total commitment is now £13.6m.
The ACE programme has two parts:
1. Anti-corruption research grant competition. One round of 8 grants on ‘what works to reduce corruption’ was managed under the DFID-British Academy Anti-Corruption Research Partnership (DFID-BA ACE). Two grants won extensions. The DFID-BA ACE Partnership was closed by mutual agreement in 2018.
DFID negotiated a new ACE granting partnership with the Washington DC-based organisation ‘Global Integrity’ (‘GI-ACE’) in 2018 and a second round of research grants was let.
2. ACE Research Programme Consortium: DFID-SOAS Anti-Corruption Evidence Research Partnership Consortium (ACE RPC) focussing on two themes:
1. The inter-dependencies between anti-corruption interventions and their impact on corruption;
2. The private sector and economic growth.
The ACE programme has three outputs which span all activities. These are production of new research; engaging policy makers and practitioners; and demonstrating the uptake and use of new research to inform better anti-corruption strategy, policy, and operations.
ACE meets DFID’s need for operationally relevant research in priority countries, though research products are also public goods. ACE contributes to DFID’s management response to ICAI’s 2014 report on DFID’s approach to corruption and is a target in RED’s Operational Plan. Both components require stakeholder engagement through the research process, and uptake facilitates the operational application of new evidence, including by DFID. This Annual Review (AR) covers the period Jan 2019 to Jan 2020.

Summary supporting narrative for the overall score in this review – Overall score A (1/2 page)
The ACE Programme has continued to build its profile and reputation (for high quality, politically realistic, problem-focused research) both in the field of development research, and with practitioners in the sectors and countries in which the research focuses. Much of the research is on politically sensitive issues and therefore understanding, and managing risk – to the research and researchers – remains very important. This sensitivity relates to partner governments, but also other development actors engaged in sectors and investments in which the ACE research may expose corruption problems. ACE’s positive focus on anti-corruption, and identifying politically feasible approaches to reform helps to manage this sensitivity.
SOAS ACE
The SOAS ACE Research Programme Consortium (SOAS ACE) contract has passed its mid-point and can demonstrate success across research production; engagement with- and generating demand from- policy makers and practitioners; and credible ‘pathways to impact’ via the emerging real-world effects of the new research.
SOAS ACE focusses primarily on Bangladesh, Tanzania, and Nigeria. Tanzania’s political environment means that it has been a challenging year for accessing data and securing research approval, which has caused some implementation delays. Overall SOAS ACE is slightly behind targets in research production (working papers), though we expect it to get back on track by the end of FY19/20. In some cases, SOAS ACE has delayed publication of a working paper until it can be validated by major policy actors – also a good pathway to ensuring that new evidence is taken up.
Strong demand for SOAS ACE’s work is evidenced by serious engagement by the major actors in focal sectors (such as the World Bank in the power sector; DFID Bangladesh and partners in skills); requests for additional SOAS ACE-framed work by global organisations such as UNCTAD (on Illicit Financial Flows); and DFID country programmes, resulting in the ‘spin off’ programme by the ACE core team supporting DFID Nepal in its new decentralisation programme; and interest from DFID Nigeria.
SOAS ACE’s annual report can demonstrate a range of examples of strong research performance and engagement which could help influence significant anti-corruption effects in large, important sectors for growth and development. Highlights from the three focal countries include:
- Bangladesh skills sector: SOAS ACE has researched largescale fraud in the performance-based payment system for skills programmes. Training providers are paid i) when trainees are registered, ii) when they complete a course, and iii) when trainees are placed in work – with fraud happening mostly at the last stage.  Research demonstrates that otherwise effective training providers engage in fraud because many manufacturers are unable to effectively utilise skilled trainees, preferring cheaper unskilled ones. This blocks the last payment to training providers and induces fraud. Policy that linked loans or subsidies to improve firm capacity with complementary investments in skills would have a profound impact on fraud reduction and achieve significant productivity and employment growth in a sector in which donor investments in Bangladesh exceed $1 Bn, with demonstration effects globally.  The SOAS ACE research input cost is less than £130,000.
- Bangladesh power sector: SOAS ACE’s forthcoming paper on high-level corruption in the power sector shows how a small and potentially reversible change in subsidies to de-risk private investments resulted in the adverse selection of politically-connected companies, leading to an unsustainable increase in the volume of subsidies (currently close to $1 Bn), and the growth of environmentally damaging diesel and furnace oil technologies. These collusive relationships could be fully or partially reversed by changing the form of subsidies provided to the sector to reduce the risk for politically unconnected companies to invest longer term in cleaner generation.  Preliminary interest from the World Bank in the research and its results has been very high.
- Nigeria power sector: the sector is very differently organized from that in Bangladesh, and with different corruption problems, including in distribution, the grid, and energy supplies.  The reform of the entire system is likely to take a long time given the situation of the distribution companies many of which are technically bankrupt. This affects payments to upstream members of the value chain, making the sector increasingly unviable. The research indicates that the most suitable anti-corruption strategy, to achieve better welfare outcomes, is one that focuses on off-grid supplies for the SME sector in the short to medium term.  The research shows the feasibility of these investments and why the corruption that the SME sector currently has to engage in to access power supplies can thereby be reduced with positive social impact. The research team are working closely with the World Bank.
- Tanzania skills sector: SOAS ACE research on vocational training institutions showed how millions of dollars were lost as a result of rent-seeking in the collection, allocation and management of the ‘national skills levy’. To generate this new evidence, a joint SOAS ACE-World Bank research team was set up, followed by experimental research involving more than 200 companies that provided evidence of how corruption in the sector can be feasibly reduced by replacing the existing levy with a sector-specific skills levy and differentiated tax rebates to companies linked to their performance. The strategy has been presented at workshops and is supported by leading business associations in Tanzania.
Based on its strong performance, high demand, and despite risks and constraints, there is a good case for DFID to consider extending the SOAS ACE contract.
GI ACE
GI ACE is just over a year old. It has performed extremely well, awarding and implementing the second round of grants, and supporting 14 grantees through the first year of their two year research projects with a range of general and bespoke support to ensure that new grantees meet the expectations of ACE’s framing. At the same time, GI ACE has developed and is implementing an impressive communication and policy engagement strategy. The GI ACE team has also put effort into resolving ACE’s branding problem (2 separate programmes – a contract and a grant – under one brand) by developing a single landing page and web address through which both components can easily be found.
Following the London corruption summit in 2016, the second round of ACE grants was designed to explicitly include a focus on international dimensions of corruption and anti-corruption (round 1 focused on national issues only). This has been a success with GI ACE grantees delivering promising new research on subjects such as beneficial ownership, flows to offshore havens, and international money laundering. At the same time, the portfolio of strong sector and national research continues.
GI ACE’s research implementation is generally on track, and strong pathways towards policy uptake are already visible.
Some of the most successful and potentially impactful GI ACE grantees have built on the backbone of their ACE research funding, by winning complementary resources to expand their ACE approach, or for policy engagement. These are on a credible path towards helping to deliver significant real world changes.
Highlights include:
- ‘Red Flags in public procurement’ securing further support and partnership for scale up – including as a World Bank internal control tool, an instrument for identifying corruption risk by national governments, and working with Transparency International to apply the approach in health.
- ‘Social norms’ (Baez Camargo) has won funding in 2 rounds of ACE grant competitions (as well as an earlier East Africa Research Hub grant) and, in addition to expanding work in Tanzania and adding an experimental approach, is working on DFID Malawi’s new anti-corruption strategy.
- ‘Effectiveness of Civil Service Training’ (Meyer-Sahling) has worked with government of Nepal to revise existing ethics training curricula in order to track and measure whether the revised, contextualized ethics training will make a measurable difference in tax collection effectiveness.
- ‘Positive recognition to promote good governance’ (Buntaine) is negotiating with Uganda’s Office of the Auditor General to explore a major expansion to national-level integrity awards.
Based on GI ACE’s rapid mobilisation, quality of implementation, and our assessment of the strong further demand (from policy makers and practitioners) for further research using the ACE framing, we consider that there is a good case for DFID to fund a further round of GI ACE research grants.
Programme level:
At programme level, ACE is having an increasingly visible and tangible influence. Research has been presented at, and used to frame, a range of global-level policy and research events, including with SOAS ACE and GI ACE teams and researchers co-presenting. Research outputs are starting to inform significant growth and development programmes. ACE has benefitted from the sustained presence of the two research leads – GI ACE’s Prof Paul Heywood and SOAS ACE’s Prof Mushtaq Khan.
ACE is therefore making clear progress towards the expected outcome set out in the business case:
“Robust new knowledge and evidence on anti-corruption lead to development of- and investment in- more effective anti-corruption policies and programmes, including by DFID and partners”.
Programme-level joint milestones are used in the logframe to monitor progress on each element.
GI and SOAS are collaborating in each other’s events, and research communication is becoming more integrated following GI ACE developing a common landing page for both components. Efforts are made at research and policy events to present ACE as a single programme but we need to ensure more of this.
DFID’s challenge for the year ahead is for GI and SOAS to draw emerging themes from across the portfolio, and deliver truly joint evidence-based products (e.g. Blogs, Webinars, Podcasts) which will help to drive further progress towards a single visible ACE programme brand and body of evidence. There is a good case for extending and expanding the programme, with additional funding for both contract and grant components. This will be strengthened with a demonstration of such programme-level joint outputs.
Gender: There are some examples of gender analysis within the ACE sub projects, but there is not a clear programme-wide strategy towards a more evidence-based understanding of gender in anti-corruption.

Recommendations for the year ahead (1/2 page)
SOAS ACE
Extension: SOAS ACE to draft a short concept note for potential contract extension, setting out potential themes and geographic focus of further SOAS ACE research. This should also incorporate plans for utilising current projected underspend and plan for any further rounds of granting competition. Action: SOAS ACE by end Feb 2020.
GI ACE
Extension: GI ACE to draft a short concept note for potential further rounds of granting competition, setting out potential themes and geographic focus for further GI ACE research. Action: GI ACE by end Feb 2020.
ACE Programme level / both components
1. Joint outputs: The target of 4 joint outputs (Blogs, Podcasts etc) between SOAS and GI will be rolled over to the first 6 months of 2020. Action: GI ACE and SOAS ACE by 01 June 2020.
2. Gender: Both SOAS ACE and GI ACE should develop and communicate a clear gender theme or strategy, with ambitious intermediate outputs throughout the year. Action: By mid year GI ACE and SOAS ACE should produce a joint product on the status of ACE’s work on gender in anti-corruption, and propose to DFID an action plan for further thematic work.
3. Review Logframe: In the next quarter SOAS ACE and GI ACE will review the output milestones and targets for research products (working papers, journal articles, blogs, etc); social media audiences and engagement; and policy engagement to ensure that all targets reflect performance to date, and delivery plans in the year ahead. We anticipate that some targets will be increased. Action: GI ACE and SOAS ACE, by April 2020.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Output 1: Research Production: High quality, policy relevant new evidence and methodological advances produced on: / Component BA / GI ‘what works to reduce corruption’ / Component RPC i. anti-corruption in the private sector / Component RPC ii. which combinations of anti-corruption approaches work best, where, and why?
Output number per LF		1	Output Score	A
Impact weighting (%):		60%	Impact weighting % revised since last AR?	No

Indicator(s) / Indicator	Milestone(s) for this review	Progress
SOAS 1.1 / Number of working papers and policy briefs produced	21 working papers / 21 policy briefs / (cumulative 2018-2019)	Milestone slightly delayed but will be achieved by April 2020. / 11 working papers were published this year; 16 (cumulatively) since the project began; with 9 more expected by end of FY 2019/20. This will brings the cumulative total to 16+9 =25 working papers / (see annex for links to all outputs)
SOAS 1.2 / Number of peer reviewed journal articles produced/submitted	5 journal articles	Milestone slightly delayed. / 3 articles published; 1 submitted; and 1 about to be submitted / (see annex for links to journals)
SOAS 1.3 / Number of new evidence/ research products generated by SOAS grantees meeting requisite quality standards	(no measure for evidence / research products this year) / 2nd call for proposals issued	On track: / Research will be complete and products published in the next quarter. / SOAS is designing a 2nd grant call, expected to be advertised in early 2020
GI ACE 1.1 / Grants awarded and implemented for high-quality research to improve evidence of ‘what works’ to reduce corruption.	Grant awards made by January 2019 after agreement of workplan, final budgets, and completion of due diligence	On track: / All 12 new grant awards made, and 2 extension BA ACE grants transferred to GI ACE management.
GI ACE 2.1 / Number of policy briefs, reports, and working papers produced	Milestone for Dec 2019: 5 / (end of contract 35)	Target exceeded: / 8 / Public: - 1 policy brief by David-Barrett - 1 working paper by Watson Available on request, not yet public: / - 1 report by Harvey - 1 report by Klopp / - 2 datasets by Dhillon - 1 dataset by Jablonski / - 1 dataset by David-Barett / (9 separate country datasets compiled)
GI-ACE 2.2 / Number of peer-reviewed articles submitted	Milestone for Dec 2019: 3 / (end of contract: 30)	Target Exceeded: / 9 articles submitted; so far / - 2 accepted (1 by Harvey; and 1 by Meyer-Sahling) / - 4 Revise and Re-submit; / - 3 awaiting first response. - 3 additional articles submitted by Meyer-Sahling; 3 by David-Barrett; 1 article by Anders

Provide supporting narrative for the score
SOAS ACE 1.1: working papers	Although short of the milestone target for 2019 there are 9 working papers ready to be published by March 2020, by which time the cumulative milestone for Dec 2019 will be exceeded. Several projects have experienced delays, including due to difficulties with research approval by national entities (e.g. Tanzania) or difficulties in accessing data. Delayed publication also includes some – e.g. Bangladesh power sector – for which working papers are complete but publication has been delayed ahead of meeting to share and validate key findings with major policy makers. DFID endorses this approach.
3 policy briefs have been published to date. Policy briefs are generally based on a finished working paper, therefore more are in preparation based on the flow of completed working papers.
Despite delays for reasons outside its control, SOAS is focused on the full delivery of all research projects within the contract lifetime (to mid 2021). SOAS ACE has extended some delivery plans for phase 1 and 2 projects while bringing forward work on phase 3 projects. As a consequence, there are 27 projects and 4 grants running concurrently. This has increased the monitoring and programme management load on the core team. 4 new projects will commence in 2020.
The research environment in the three focus countries continues to be challenging. So far 8 projects from the original list have been ended, and replaced by additional, more viable and potentially influential research projects, to ensure that output targets will be met and also to ensure that SOAS ACE’s research can adapt to meet emerging policy and operational priorities.
Core projects
End by Dec 2019	End by Mar 20	End by June 20	End by Dec 20
-Skills (B) / -Power (B); / -Power (N); / -Capitalist Accumulation and Corruption: Business Groups (T) / -The Nigerian Economic & Financial Crimes --Commission (EFCC) (N) / Media (N)	-Skills (T) / -Power (T); / -Port - focus on smuggling rice/sugar (T) / -Climate Change (B) / -Extractives (N) Completed by Dec 2020	-Capitalist Accumulation and Corruption: Business Groups (N) / -Health Providers (T) / -Health Providers (N) / -Health Providers (B) / -Tax Authorities EPZ (T) / -Media (B) / -Pharmaceutical (T) / -Fertilizers (N) / -Bribery Games (N)	-Pharmaceutical (B) / -Rice (N) / -Smuggling and enforcement of NBR tax codes (B) / -Garments Industry Regulatory Enforcement (B) / -Cooperatives and community-based fisheries (B) / -Capitalist Accumulation and Corruption: Business Groups (B)

(B = Bangladesh, T = Tanzania, N = Nigeria)
In addition, SOAC ACE’s core team has produced additional working papers on themes emerging from the SOAS ACE analytical strategy, such as working papers on Digital ID and Illicit Financial Flows (IFFs), which have attracted global interest. They draw on the research in focus countries, but take a more international perspective and are ‘pro bono’ products under the SOAS ACE brand.
New Projects (Jan 20 to June 21)
Food Value Chain Tanzania / Land Tanzania / Illicit Financial Flow Nigeria / ACE Methodology Nigeria, Bangladesh, Tanzania

SOAS ACE 1.2: journal articles submitted:	This is on track. SOAS ACE and consortium partners such as the LSHTM have made a particularly tangible impact in global health policy discussions, where there is strong interest in the novel approach to longterm constraints to health service delivery such as absenteeism and drug supply in the context of Universal Health Care (UHC). This strong demand is part of the reason why the 3 publications this year are on Health Policy in Nigeria and West Africa, in which the SOAS ACE consortium’s rigorous literature review is clearly worthy of publication; with another on corruption in health in South and South East Asia.
SOAS ACE 1.3: grantee publications	There was no measure set for the research outputs for 2019 although results and publications by the 4 grantees (see table below) are expected in 2020. The four grants, let through competition, are:
Lead institution	Project title	Country	End by
1. Centre for Competition, Regulation and Economic Development (CCRED), University of Johannesburg	Cartels as private corruption in Malawi, Tanzania and Zambia: the steel sector and enforcement of competition law	Malawi, Tanzania, Zambia	June 20
2. Collective of Social Science Research PVT Ltd (CSSR)	Tackling private corruption in Pakistan’s pharmaceutical sector	Pakistan	March 20
3. London School of Hygiene and Tropical Medicine (LSHTM)	Acting on rent-seeking among drug shop vendors in Uganda	Uganda	June 20
4. Mercu Buana University, Indonesia	Corruption risk in Indonesia’s upstream oil and gas industry	Indonesia	March 20

GI ACE 1.1: Grants awarded	GI met its exacting targets to negotiate and award 12 new grants and transfer the management of 2 extension grants (from BA), ensuring that the cohort of new grantees could engage in a single programme of inception and capacity building events such as on policy engagement and communication. This maximised the efficiency of GI ACE’s support and has also enabled DFID’s SRO to engage with all of the researchers at key events in the year.
All grantees have reported on a quarterly basis, on time, with detail about the progress made, including on the finances spent. This reporting frequency allowed grantees to take stock of their efforts against submitted work plans and provided a basis for the programme team to structure check-ins about risks or obstacles and provide advice and guidance on mitigation measures and possible next steps.
PI Name	Institution	Project Title
Gerhard Anders	University of Edinburgh, UK	Fighting high-level corruption in Africa: Learning from effective law enforcement
Claudia Baez Camargo	Basel Institute on Governance, Switzerland	Addressing bribery and favouritism in the Tanzanian health sector: a behavioural approach
Mark Buntaine	University of California, Santa Barbara, USA	Rewarding good governance through community recognition
Thorsten Chmura	University of Nottingham, UK	International anti-corruption laws and local social norms: interactions and implications for policy
Amrita Dhillon	King's College London, UK	Centralised vs decentralised monitoring to reduce corruption: insights from comparisons across Indian states
Daniel Haberly	University of Sussex, UK	Does transparency bring cleanliness? Offshore financial secrecy reform and corruption control
Jacqueline Helen Harvey	Northumbria University, UK	Practical interventions for uncovering and identifying ‘beneficial ownership’ as a mechanism to recover the proceeds of corruption – a Nigerian case study
John Heathershaw	University of Exeter, UK	Testing and evidencing the effectiveness of beneficial ownership checks: investigating the laundering of monies and reputations by African and Central Asian elites
Ryan Jablonski	London School of Economics and Political Science, UK	Identifying and deterring the theft and diversion of medicinal drugs in Malawi
Jacqueline Klopp	Columbia University, USA	Ethical border trading between Kenya and Uganda for small scale businesses
Jan-Hinrik Meyer-Sahling	University of Nottingham, UK	Civil service reform and anti-corruption: does ethics training reduce corruption in the civil service? [Phase 1 extension]
Vanessa Watson	University of Cape Town, South Africa	A central corruption problem in development: urbanisation and the role of professional integrity in urban planning
Phase 1 extensions transferred from BA management:
Liz Dávid-Barrett	University of Sussex	Curbing corruption in procurement
Claudia Baez Camargo	Basel Institute on Governance, Switzerland	Harnessing informality: Designing anti-corruption network interventions and strategic use of legal instruments

The GI ACE projects are overall on track. The two-year grant period (rolled over from the BA ACE strategy in round 1, and also reflected in the call documents for round 2) is challenging for the full delivery of fieldwork, analysis, writing up, and publication. Most researchers are more used to a 3+ year project duration. Moreover, the drive by DFID to commence the grants immediately after signing (to make up for delays during the DFID-BA partnership) also made mobilisation difficult.
Some projects have had to delay activities within the two-year grant period because of external factors and the needs of their policy partners. Meyer-Sahling (University of Nottingham) has pushed the ethics training in Nepal into March 2020 and Jablonski (London School of Economics) field work will start about 6 months later than originally planned following partner delays. These do not present a major risk to projects completing by December 2020, but require researchers and the programme team to stay vigilant.
A second aspect of these delays—often necessitated by projects working closely with partners on the ground—is that they have caused a slight underspend against plan as major field expenditures are postponed. However, GI ACE is confident that project spending will increase to the originally anticipated levels when research activities are fully underway.
GI ACE 2.1: policy briefs, working papers:	The GI ACE grants were structured to deliver research outputs throughout the two-year grant period, particularly where the GI ACE grant builds on a research team’s earlier work (e.g. in the extension grants), and where inception activities under GI ACE are sufficiently novel or significant to support a new output, including new data sets. GI ACE has exceeded its first-year target.
Amongst the highlights are the nine country data sets on World Bank, IADB, and Europe Aid development aid funded contracts as part of the Red Flags project (Dávid-Barrett) and a working paper by Zinnbauer for the Cities of Integrity project (Watson) exploring points of intersection for scholars, practitioners, and activists in the anti-corruption and urban development fields.
GI ACE 2.2: peer-reviewed articles:	As in 2.1, GI ACE has a clear strategy to incentivise publication throughout the grant period and has exceeded its targets. Although the production cycle of articles in peer-reviewed outlets is lengthy, two articles derived from the projects have already been accepted for publication and a further seven are either under review or awaiting a response.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons: The two-year duration and sequencing of grants under BA and GI ACE warrants reconsideration. The original motivation was to ensure that the granting mechanism could be tested, avoid the delays typical in grant portfolio approaches, and then be adapted if required in further rounds of grants. If DFID funds further rounds of competitively awarded GI ACE grants, we should consider the ideal grant duration and/or options, such as allowing a notice period (e.g. 3 months) after awards have been announced, but before teams mobilise; possibly with an orientation meeting in this period.
Gender: Both SOAS ACE and GI ACE can demonstrate a range of projects in which gender analysis is a core part of the anti-corruption research (see summaries in Annex B). However, there is not yet an overarching framework for structuring, delivering, and synthesising emerging findings on gender and anti-corruption.
Recommendations:
SOAS indicator 1.2 for policy briefs should be expanded to include other policy relevant research products such as feature articles in leading national newspapers and quality assured research Blogs.
Output Title	Stakeholder engagement through research process and uptake facilitates the operational application of new evidence, including by DFID (both GI and RPC components) / *n/b the ACE programme level logframe is compiled from the 2 component logframes. SOAS ACE’s logframe has 4 outputs, and some indicators from SOAS outputs 2 and 3 are compiled below into overall programme output 2. For ease of reference they are numbered using the SOAS ACE output numbers.
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Nono

Indicator(s)	Milestone(s) for this review	Progress

SOAS ACE 3.1* / Number of workshops and public events held with key stakeholders where ACE research findings are disseminated.	5 workshops and/or public events	Target exceeded. / 8 country stakeholder project workshops were held in 2019 plus 30 focus groups and 5 high level presentation events. / Plus 14 global high level public events
SOAS 3.2* / Extent to which a range of stakeholders are engaging with research produced by SOAS-ACE through the programme’s website / learning platform.	10,000 unique visitors to website / (End of contract: 30,000 visitors to website)	Target not met. / Total of 7,074 unique visitors with 10,366 visits to the ACE site during period Jan 18 to Jan 19. / Top countries for website visitors were (in order) the UK, USA, Nigeria, Tanzania and India. / 85% of web visitors this reporting year were new visitors.
SOAS 3.3* / Evidence that ACE research is being disseminated in accordance with a flexible and adaptive social media strategy.	550 followers on twitter / (End of contract: 1150 followers on twitter)	Target exceeded. / ACE’s twitter profile has 711 followers (as at Jan 2019). The account attracts an average of 30 new followers each month. The posts are clear with good use of branding and infographics. / Social media strategy is flexible and adaptive, demonstrated by engagement with news and other events and tailored campaigns. Eight blogs have been published on prominent sites. / In addition to this SOAS ACE has produced 2 podcasts by Mushtaq Khan on i) the SOAS ACE approach and ii) understanding and countering corruption in skills and employment programmes.
SOAS 2.1 / Number of sector specific corruption and governance diagnostics developed based on new evidence of corruption drivers and mechanisms.	Evidence from relevant completed projects (10) included in data platform / (End of contract: Evidence processed into useful range of diagnostics including indicators)	Target on track / All research projects include application of SOAS ACE conceptual framework in the target sector.
SOAS 2.2 / 20-25% active learners (a key indicator of those who engage with some parts of the course and acquire the skills that those weeks provide) from the total number of MOOC participants.	Not measured in 2019. / (End of contract: TBD)	Not measured in 2019. / This indicator will be based on roll out of the SOAS ACE RPC capacity development strategy that targets users with the implementation of an anti-corruption Massive Open Online Course (MOOC) provided by SOAS and an open access data platform which will be available on the ACE RPC website.
GI-ACE 3.2 / Number of engagement events (speeches, engagements, panel appearances, participation in workshops, requests for input, etc.) & resultant feedback.	Milestone for December 2019: / 28 / (End of contract: 70)	Target exceeded: / 49 instances recorded in GI M&E system. / The 14 projects recorded 33 substantive appearances and presentations for practitioners. 17 out of these 33 are based on the extended Phase 1 David-Barrett project that has now closed out. / Without this project, the count would have been at 32 instances and therefore still exceeded the target. / Projects furthermore recorded 16 substantive appearances or presentations at academic conferences and panels.
GI-ACE 3.3 / Assessment of social media traffic & views & visitors	Milestone for December 2019: / 1.5 % engagement (End of contract: 1.5% engagement)	Target exceeded: / The average engagement rate through social media is at 2.6%. This is a much better engagement rate than typically achieved by other, specialized non-profit organizations (the basis of the target).
ACE Programme Level 2.5 / Number of joint initiatives by SOAS and GI that advance ACE’s agenda (workshops, joint publications, data sharing)	4 joint initiatives	Milestone met. / 4 joint events (listed below)

SOAS ACE 3.1	The SOAS ACE consortium has exceeded the target number of workshops and events held in the 3 focus countries, and its annual report documents a wide variety of engagement efforts with policy makers and other interest groups. SOAS ACE also notes that some of the most promising policy engagement opportunities have been from small meetings and chance encounters, rather than formal events – such as the attendance of government officials at NGO events in Bangladesh, followed by requests for briefings by the research team and the development of further research ideas or policy advice. Examples of SOAS ACE events organised include:
Tanzania: SOAS ACE organised a 2 day workshop (March 2019) at DFID Tanzania. Day 1 was attended by DFID governance advisers and BHC staff, to present the SOAS ACE research in Tanzania. The aim was to discuss how SOAS ACE research could inform DFID and HMG programming and policy. Day 2 was a workshop for the Dar es Salaam Economists Forum, with 25 participants focussing on specific sector projects (ports and smuggling; electricity; business conglomerates; tax incentives; and special economic zones). Feedback from participants was positive.
Bangladesh: ‘BIG-D’ (BRAC University) and Mushtaq Khan organised a closed session in June 2019 to share and validate initial findings of the Skills project with DFID-B and skills programme partners Sudokkho and UCEP. Initial concerns about the implications of SOAS ACE research were allayed. There was agreement that the research results are important, and the partners are in discussion to take the results forward in policy and for further research.
Nigeria: SOAS organised a stakeholder workshop in Abuja in July 2019 led by Pallavi Roy to discuss the artisanal oil refining and the expectations of the project using SOAS ACE framework. Participants included the Stakeholder Democracy Network (SDN), the Facility for Oil Sector Transparency and Reform (FOSTER), Centre for Democracy and Development (CDD), and civil society organisations with interests in artisanal oil refining in the Niger Delta.
SOAS ACE 3.2 and 3.3	Visitors to the SOAS ACE website increase each time that new content – particularly working papers – are posted, and advertised on social media such as Twitter (see box for example). In the next few months, a wave of new working papers will be published from the first phase of research. With suitable social media coverage, this should boost website visits and help to ensure that the ‘unique visitors’ targets for next year, and for end of project, are achieved.
SOAS ACE could do more to maximise engagement, such as by producing and posting additional ‘intermediate’ research content such as Blogs and Podcasts, and also revising the SOAS ACE social media strategy. Currently the Twitter account is managed by the part time communications consultant. Posts could be more frequent, and opportunistic (e.g. hooking to news events or other research), if the core team also used the SOAS ACE handle, and tweeted more regularly, including around events in the 3 focus countries. The key here is building an audience for future research engagement and uptake, not just increasing web and social media metrics.
SOAS ACE Tweet with highest engagement (774)
SOAS ACE 2.1	There was no new milestone this year. All SOAS ACE sub-project include a diagnostic product.
SOAS ACE 2.2:	Not measured this year. The MOOC will be launched, and engagement measured, when the phase 1 projects have reported and thus the new body of evidence (working papers, blogs, etc) can be the basis for the new course.

GI-ACE 3.2:	Policy engagement and supporting evidence uptake is a particular strength of Global Integrity. The GI ACE grantees exceeded this year’s target for engagement events, despite several possibly under reporting the actual numbers. A condition for the GI ACE research grants is development of a clear engagement plan, and GI-ACE also held structured technical development sessions for all grantees (starting at the launch workshop in Jan 2019), including advice and exercises in engaging policy makers. Some grantees were already well experienced in this, so also offered their own practice-based advice to others. The DFID SRO has also linked research teams with DFID teams, and their networks, in country and in HQ.
Notable examples this year include expert testimony by Heathershaw to the House of Commons Foreign Affairs Committee, and invitation for follow-up consultation. Programme-level activities not counted as part of these GI-ACE project level indicators include a headline event by Heywood and Marquette (DFID Senior Research Fellow - SRF) at the OECD Integrity Forum; and presentation to the OECD Anti-Corruption Task Team by GI’s Johannes Tonn in November 2019.
Heywood and Tonn furthermore promoted new approaches to practically engaging with specific instances of corruption through the third round of the ACE ‘Rethinking Corruption’ Workshop in Ghana in March 2019 and through various other events, including with international anti-corruption expert Mark Pyman at the World Bank, as well as with Columbia University’s Center for Sustainable Investment on Applied Political Economy Analysis to fight corruption in the Extractive Industries
.GI ACE 3.3:	GI ACE built a commitment to communication and policy engagement into each grant (so generating content such as Blogs, and incentivising grantee effort), and has supported grantees with a strong overarching communications strategy and tools such as the new website. This has paid off, with GI ACE far exceeding its targets (e.g. social media engagement scores – see box).

GI ACE has worked to promote the visibility of GI-ACE, both in its own right as an innovative research programme, and also as part of the wider ACE brand alongside SOAS ACE. This should continue. GI ACE has developed an engaging communications strategy, driven by Kaaryn Keller (GI Communications Manager) who joined in May 2019. GI ACE created a web-based ‘landing page’ for both elements (GI ACE and SOAS ACE) and a programme-specific website. Taking design cues from both Global Integrity and SOAS ACE sites, the website promotes GI ACE activities, providing easily accessible information about the rationale behind the ACE investment, the three core themes that underpin it, the individual projects and the geographical scope.
The GI ACE site hosts a weekly series of project-focused blogs and project explainers (47 to date). This number exceeds the anticipated target and has been achieved despite a slow first six months of 2019 when projects started to set out their research agenda. The Blogs have attracted significant attention, averaging around 100 page views after 30 days. Two blogs in particular - by Buntaine and by Haberly and Gullo - generated a lot of traffic. A resources section offers additional information, as well as working papers, videos, and other project-related outputs. GI ACE has also tracked down and curated dispersed materials from the now-defunct Phase 1 site hosted by the BA, so providing continuity from the initial eight projects, particularly the two receiving follow-on funding.
The average engagement rate through social media is at 2.6%. This is a much better engagement rate than typically achieved by other, specialized nonprofit organizations (the basis of the target). Since the website went live, GI-ACE’s monthly audience was made up of more than 80% new visitors for each of the following three months.

ACE Programme Level 2.5:	Joint activities were interrupted in 2018 following the delay in awarding the second-round grants, and the end of the DFID-BA partnership and instigation of the DFID-GI ACE partnership. This year has seen interaction between SOAS and GI mainly through participation in each other’s events.
1. SOAS ACE’s Mushtaq Khan and Sonia Sezille attended the GI ACE Grantee workshop (London, Jan 2019) and presented the SOAS ACE approach.
2. GI ACE’s Paul Heywood participated in the SOAS ACE annual partners’ meeting (London, Sept 2019)
3. GI ACE and SOAS ACE researchers working on anti-corruption in health met and presented at DFID HQ in Jan 2019.
4. SOAS ACE is hosting the second leg of the GI-ACE/Columbia University workshop on extractives (London, Jan 2020).
However, the challenge for the next 6-12 months is a high quality joint products.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations:

GI ACE to update project-level system for recording instances of engagement events to benchmark quality, significance, ‘what happened as a result’, and mapping onto GI ACE Theory of Change and, if necessary, revise logframe target for this indicator. Action: GI ACE to report any action to DFID by June 2020.

SOAS ACE to update its social media strategy, including sharing responsibility for posting on programme Twitter across core team (e.g. Directors) and increasing production and promotion of ‘intermediate’ research content such as Blogs and Podcasts.

Output Title	Output 3: Policy influence and operational application of new evidence, including by DFID (both GI and RPC components).
Output number per LF		3	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
ACE Programme Level 3.1 / Number of cases where ACE research directly or indirectly influences policy, programme design or implementation by DFID / HMG.	SOAS ACE: 3 / GI-ACE: 3	SOAS ACE: >3 e.g. / DFID governance position paper / DFID Nepal’s SOAS ACE-framed programme. / DFID Bangladesh skills programme. / GI-ACE: 3 / Recruitment – Stabilisation Unit CSSF programme in Kosovo / Red Flags – DFID-research application for IMF funding / Social Norms – DFID Malawi A/C strategy
ACE Programme Level 3.2 / Number of cases where ACE research directly or indirectly influences policy, programme design, or implementation by other development partners and stakeholders.	SOAS ACE: 3 / GI-ACE: 3	SOAS ACE: >3 e.g. / 1. Bangladesh power sector – WB / 2. Bangladesh skills sector – Donors/IFIs / 3. Bangladesh digital ID- GoBangladsh / 4. Tanzania skills sector - WB / GI-ACE: 3 / 1. Red Flags Uganda & Jamaica, World Bank, / 2. Meyer-Sahling: Civil Service Ethics Training in Nepal; / 3. Watson: Integrity training in Zambia.

n/b these two programme-level indicators combine activities from SOAS ACE logframe and GI-ACE indicator 3.1 (Numbers of research uptake examples – de facto and as per project plans – and data/ reflections about why/ how ‘pathway to impact’ happened).
SOAS ACE and GI ACE have each developed their own Theory of Change, and from this a mechanism for mapping research engagement, uptake, and progress towards outcomes across their diverse portfolio of research projects.
At the last review, DFID recommended that GI ACE participate in SOAS ACE’s outcome mapping activities with the aim of helping GI ACE to develop its own approach. The GI ACE Programme Director attended SOAS ACE partners’ meeting in September 2019, but by this time GI ACE grants were well underway and GI had developed its own approach and was including this in its grant and programme level monitoring.
To date, SOAS ACE’s ‘outcome harvesting’ approach has documented 40 possible or actual outcomes (i.e. research influences steps towards real world change), up from 24 in 2019. These relate to 13 projects. Given the sensitive anti-corruption themes that ACE focuses on, and the politically sensitive environments in which the research operates, these examples can appear relatively modest, yet can be unusual or novel steps towards change in some very large and important growth and development sectors. An example is SOAS ACE’s engagement with the association managing changes to the President’s Fertiliser Initiative in Nigeria, resulting in a new openness to share data on fertiliser pricing, and to reconsider aspects of the policy when SOAS ACE delivers a comparison of the old and new policies. These are potentially clear steps towards large reforms and outcomes.
GI ACE has easily exceeded its milestone this year, even with a conservative approach to reporting. All grantees have a research engagement strategy included in the grant, and therefore are already engaging with policy makers, including providing evidence-based advice derived from their previous research, sector expertise, and current research implementation (e.g. providing new data; new analysis of data; new insights into understanding and addressing longstanding corruption challenges).
At the programme level, GI-ACE has focused its efforts on presenting the program at the OECD, to the World Bank and in settings in which a significant number of practitioners and academics might seek additional information from the projects. Secondly, GI-ACE has connected research projects to specific practitioner audiences to broker relationships and contribute to achieving the desired impact.
 3.1	Research influencing DFID/HMG
Both SOAS ACE and GI ACE researchers are engaged with DFID and other HMG policy and programme teams, in the UK and at country level. The researchers typically engage with HMG teams throughout the process, providing evidence-based advice, and honing research to meet real world needs, as well as presenting new research products. This ‘cradle to grave’ approach is embedded in the ACE business case and the design of both components. Key examples are:
SOAS ACE
1. DFID governance strategy: DFID’s 2019 position paper ‘Governance for Growth, Stability and Inclusive Development’ (March 2019) refers to the work of Mushtaq Khan on inclusive growth and governance, and the ‘political feasibility’ approach developed by SOAS ACE.
2. HMG briefing: SOAS ACE has been requested to provide a wide range of briefings to DFID and FCO teams, including briefing for senior HMG staff in Tanzania, Bangladesh, and Nigeria, based on SOAS ACE’s country political economy analysis, and sector research projects. Written feedback has been exemplary. SOAS has also engaged with DFID funded researchers working in Iraq to share the SOAS ACE framework. Again, written feedback has confirmed that this has had a positive effect.
3. DFID Nepal decentralisation programme: The DFID Nepal-funded SOAS ACE ‘spinoff’ project has now completed its inception. There is now strong interest from DFID Nigeria to develop its own bespoke approach, following a briefing and concept note from the SOAS ACE core team.

4. DFID Health: Researchers from both GI ACE and SOAS ACE working on corruption in health held an internal workshop with DFID’s health adviser cadre in January 2019 (see box), resulting in a range of follow up engagements from DFID country and policy teams, and DFID’s global health partners (see below).

GI ACE

1. DFID Malawi anti-corruption: Following their BA/GI ACE grant funded research on social norms in round 1 and 2, and additional research funding from the East Africa Research Hub (EARH) GI ACE’s Baez Camargo team are now working with DFID Malawi on a national anti-corruption strategy.
2. DFID Uganda and DFID PFM and Tax policy team: Dávid-Barrett and Fazekas continue to engage with DFID U and PFMT governance programme partners in Uganda to inform the developing strategies for procurement reform; and are partnering with PFMT in a proposal for IMF anti-corruption fund support.
3. HMG Conflict, Security, and Stabilisation Fund (CSSF): Meyer-Sahling is advising the UK Government’s Stabilisation Unit (SU) on tackling political corruption in public sector recruitment processes in its CSSF project in Kosovo.

3.2	Research influencing other partners
Even more significant (in terms of potential impact) are the examples of influence on other partners, including country governments and IFIs, particularly the World Bank.
SOAS ACE
WHO, Global Fund, UNDP Global Health strategy: In February 2019, SOAS ACE consortium members Dina Balabanova and Eleanor Hutchinson (LSHTM) presented their ACE research on health sector absenteeism in ‘Consultation towards formation of a Global Network on Anti-Corruption, Transparency and Accountability (ACTA network) in Health Systems’ in Geneva, co-organised by WHO, Global Fund, and UNDP, with the meeting convened with financial support from DFID policy team.
Mushtaq Khan presented the SOAS ACE approach in the health and was then asked to contribute to the strategy 'Reinforcing the focus on anti-corruption, transparency and accountability in national health policies, strategies and plans' with a SOAS ACE section on ACE’s Political Settlements approach to changing incentives between powerful groups and so designing more effective health policies. The ACTA paper will inform WHO national strategies.
IFI and bilateral skills programmes, Bangladesh, Nepal: SOAS ACE’s paper on fraud in skills programmes has identified feasible ways to potentially save millions of pounds of public money, and (even more importantly) improve outcomes in skills programmes that have achieved poor results across the world. The budgets of current IFI and donor funded skills programmes in Bangladesh exceed a billion US dollars and therefore even marginal reductions in fraud and leakage could deliver very large savings as well as better development impacts.
SOAS ACE has demonstrated the necessity of recognizing the critical role of capabilities on the demand side of the skills market if corruption and fraud in skills programmes are to be reduced. The organization of this research was particularly sensitive and required the participation of implementation partners in Bangladesh, particularly the DFID funded programme led by Palladium. Before publication of the working paper, SOAS ACE organised validation of findings with DFID Bangladesh and partner Palladium. SOAS ACE is now in discussion with DFID and Palladium on how to take the findings forward to improve employment and wage outcomes in skills programmes and to further refine understanding through additional research. DFID Nepal is also using SOAS ACE’s paper to inform design of its own ongoing skills programmes.
Skills levy, Tanzania: SOAS ACE’s analysis of the skills levy and the leakages it results in has fed into a paper jointly written with the World Bank. The ongoing research examines the anti-corruption implications of matching skills levy rebates to the organizational capabilities of firms, testing the hypothesis that the latter determines the ability of firms to use rebates productively to invest in the skills of their workers. This promises to be a feasible response to development partners assisting the Tanzanian government to improve skills levels without losing significant amounts of public resources in corruption and leakage.
Nigeria fertilizer: SOAS ACE research examines the President’s Fertilizer Initiative as a programme to curb corruption in fertiliser distribution compared to an earlier programme that used a very different set of instruments. The comparison identifies strengths and weaknesses of both that can be used to improve anti-corruption design. SOAS ACE is working closely with the Fertilizer Producers Association of Nigeria (FEPSAN) - the organization responsible for designing the PFI including discussing uptake of interim research findings.
Digital identities, global policies, Bangladesh: SOAS ACE’s paper on digital identities and their implications for anti-corruption and governance has been enthusiastically received by practitioners and policymakers. SOAS ACE is engaged with OECD DAC and discussing applications and next steps with DFID’s governance and digital inclusion team.
In Bangladesh, SOAS ACE’s presentation at BRAC led to a presentation and meeting the next day with a high-powered team consisting of the ICT minister, Cabinet Secretary, Chief Election Commissioner (in charge of NID cards) and staff. There is interest in using the SOAS ACE framework to assess corruption and governance risks in different parts of the ambitious digital strategies and identify areas where better data and systems are required before rolling out digitization. A2i, the Bangladesh government’s lead digital agency, is keen to sign an MOU with BIGD and SOAS-ACE to take this work forward. This is a significant policy breakthrough for SOAS-ACE and a chance to make important policy contributions in Bangladesh that may help to avoid some of the adverse consequences of digital systems that can increase some types of corruption or damage the welfare of poor people.
DFID Nepal has also found the paper useful as they are considering areas where they may potentially support Nepal’s digital identity programme.
Bangladesh Power Sector and World Bank: SOAS ACE’s research on high-level collusive corruption in the power sector in Bangladesh has identified an evidence-based strategy offering a feasible way of reducing a costly variant of collusive corruption between business and politics. The research demonstrates that this collusion can be broken or significantly weakened by changing the form of subsidies provided to the sector. SOAS ACE has postponed publication of the paper (to Jan 2020) until after a high-level validation meeting of the results at the World Bank office in Bangladesh. The sensitivity of the findings means that SOAS ACE will not publish without taking into account responses from this high-level validation. Preliminary interest from the World Bank in the research and its results has been very high.
Illicit Financial Flows and UNCTAD/OECD: SOAS ACE’s paper on illicit financial flows has been presented at a number of conferences, and with a high level of interest in our paper, particularly in UNCTAD and the OECD, but is still awaiting a clear breakthrough in relation to policy implications.
GI ACE
‘Red Flags in Public Procurement’ research (Dávid-Barrett) is a successor to earlier work funded by the EC’s Digiwhist programme. Under ACE, successful Red Flags research on donor-funded procurement (round 1) was succeeded by an extension grant (won through further competition) to focus research on country procurement systems; and an additional impact grant to develop the country ‘deep dive’ approach (Jamaica and Uganda) and a more user-friendly online portal. With DFID’s support, the Red Flags team are negotiating an MoU with the World Bank to use Red Flags as an internal risk management tool in WB programmes, and in WB client countries (Mexico, Algeria). Red Flags has secured funding from Transparency International Health Initiative (TI-HI) for research on health procurement in Kenya and Uganda; is working with Open Contracting (funded by DFID policy division) on research in Mexico and Columbia, and in partnership with DFID Public Finance and Tax policy team has applied for IMF anti-corruption challenge funding.
Integrity training: As well as engaging with the Nepal and Bangladesh governments to design and test new training modules for the public service, Meyer-Sahling has presented findings at events involving practitioners from the World Bank, the IDB, the European Commission, the OECD and the Regional School of Public Administration based in the Western Balkans.
Cities of Integrity: Watson (University of Cape Town), in partnership with the Centre for Urban and Regional Planning at the University of Zambia and the Zambian Institute of Planners (ZIP), has designed and conducted a qualitative action experiment after which the ZIP committed to institutionalise integrity trainings and support Zambia’s planning community to act as champions of urban integrity.
In addition, the U.S. State Department has signaled a high level of interest to follow and learn from the research undertaken on Illicit Financial Flows, Anti-Money Laundering and Beneficial Ownership questions conducted by Haberly (Sussex University), Harvey (Northumbria University) and Heathershaw (Exeter).  The OECD has also expressed significant interest in GI ACE, with a particular focus on work that further promotes its emphasis on integrity promotion as a key element in combating corruption.
GI ACE has also collaborated closely with the sector-based approach to anti-corruption that has been led by Mark Pyman via the innovative CurbingCorruption.com initiative.
Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons: The ACE programme’s framing (anti-corruption research that is problem-focussed, focussed on politically feasible reform, with measurable results, and engagement with policy and operational actors throughout the research cycle) has been operationalised by SOAS and GI and is delivering even more successfully than envisaged, with conceptual frameworks supported by more granular, practical research, from creation and analysis of large data sets to case studies and experiments. There is strong demand for this research approach.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The ACE Business Case, SOAS ACE’s contract, and GI’s proposal for GI ACE, are based on a standard theory of change for DFID research programmes. This same ToC is reflected in the ACE log frame. Both SOAS ACE and GI ACE have further refined this Theory of Change for their own activities.
- ACE (GI and SOAS) research frameworks and strategies identify priority research questions and themes that will contribute to the evidence base for policy makers and other interest groups, including DFID and its partners.
- Programme leads design and oversee implementation of a portfolio of research projects (with fieldwork in specific settings and with appropriate methods and analysis) to deliver this new evidence (output 1).
- Throughout the research cycle researchers and programme teams engage with policy makers to ensure that the research addresses real needs, and also to prepare audiences for uptake of the new research products.
- ACE produces a range of research outputs tailored to different audiences, and actively disseminates these, including through publication, online, and at events (output 2).
- Where required, ACE builds capacity as it works with research partners in order to deliver the research to expected quality and on time (output 3).
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The ACE Programme is on track – both in terms of the output milestones for this reporting year, and output milestones and outcome at current programme end.
Both programme teams – the SOAS ACE contract and GI ACE grant programme – have worked hard and flexibly to overcome implementation barriers and to make up for lost time. For both components, political developments and a changing research environment in Tanzania have caused delays in research approval and access to data. SOAS ACE has also had to evolve its strategy, putting more core-team time into country research projects, rather than managing these relatively remotely.
To recover lost time, SOAS ACE is now running several rounds of research concurrently to ensure that contract timelines for research completion can still be met. GI ACE managed to mobilise a team, and negotiate grants, and make awards, in a very short time, in order to make up for time lost during the delay and then termination of the second round of grants during the DFID-BA partnership. This is particularly commendable.
Both components are making strong progress towards research uptake and impact. All research teams – whether sub-contractors within the SOAS ACE consortium, or GI ACE grantees – have engaged with policy makers and operational partners from the start of the research, and this has helped them to adapt the research strategies to meet specific needs, access new sources of data, and prime external partners to think about and use the new research evidence when it emerges. This type of approach – set out in the ACE Business Case, but refined and developed by the partners – has maximised the likelihood of real- world impact. Moreover both partners are carefully logging credible progress made in each ‘pathway to impact’.
At overarching programme level, SOAS ACE and GI ACE have participated in each others’ events and technical sessions but as yet they have not produced joint evidence products which project the overall ACE approach and programme ‘brand’. This should be a priority for the next reporting year.
Explain major changes to the logframe in the past year
Both components continue to have their own results frameworks. These are summarised in the overall programme logframe that is the basis of this Annual Review.
In the first 6 months of the year GI ACE refined its grantee monitoring framework, and from this developed a more detailed logframe than the simple indicators used in the last review (generally grantee processes being completed). GI ACE’s refined logframe was submitted to DFID and accepted in June 2019.
Describe any planned changes to the logframe as a result of this review

In the next quarter SOAS ACE and GI ACE will review the output milestones and targets for research products (working papers, journal articles, blogs, etc); social media audiences and engagement; and policy engagement to ensure that all targets reflect performance to date, and delivery plans in the year ahead. We anticipate that some targets will be increased, including targets for joint products.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

Across the ACE programme the key cost drivers are salary and fee costs, travel costs, research communication and uptake costs (such as for publication, and events), and monitoring and evaluation activities.
SOAS ACE: SOAS ACE uses SOAS’s well established systems in place to ensure VFM throughout the project life-cycle. It has clear policies on anti-bribery and fraud that must be followed by staff, partners and contractors. SOAS applies stringent policies on expenses controls when monitoring expenditure, including linking payments to delivery of outputs by consortium partners and grantees.
SOAS ACE’s project management and budget monitoring processes use a ‘payment by results’ mechanism. This helps to ensure that the programme delivers outputs on time and within budget. Reimbursing actual spend on receipt of invoices submitted quarterly in arrears helps ensure that funds are released appropriately against approved budget lines. Invoices are supported by a short narrative report on the main areas of expenditure.
SOAS carries out due-diligence checks on all partners and sub-contractors to ensure all partners can deliver to the standards expected.
GI -ACE: To implement the granting programme, GI ACE has further developed Global Integrity’s already robust financial management systems, rolling out due-diligence checks on all grantee organisations and ensuring that appropriate downstream partner monitoring mechanisms were put in place.
Contracts were drawn up with partners to ensure they understand their responsibilities to help ensure the GI ACE programme meets overall requirements in regard to VFM, budget monitoring, reimbursement processes and record-keeping. A comprehensive tracking system enables GI to keep abreast of developments and expenditure at project level.
Examples of VfM are listed below under the DFID’s “4 E” framework.
1.ECONOMY
SOAS ACE
- SOAS local partners’ fees are benchmarked according to the country market (Tanzania, Nigeria and Bangladesh).
- SOAS outsources specific expertise for functions required intermittently – e.g. communications experts (graphics and communication) and Organisational Management. This saved £22k over the period April to September 2019 (compared to a full-time post) and funded additional activities and outputs.
- The Executive Director does not charge SOAS ACE for the accommodation costs of long-term (3-4 week) ACE assignments in Bangladesh, generating savings per year e.g. £5k over April to December 2019 (based on 60 days at £85pd).
GI ACE:
- GI engaged a website developer who provides the full scope of requirements at a significantly lower rate than envisioned in the original budget. Savings (£10,000-£15,000) will be invested in developing additional content for the website and additional channels of communication and engagement.
- GI worked with Columbia Center for Sustainable Investment (CCSI) at Columbia University and SOAS-ACE on a series of executive session workshops on ‘Advancing anti-corruption in the extractives industries through a political economy lens’. Costs were shared - GI-ACE paid for two flights (~ £2,000) while CCSI took on the majority of the cost for the U.S. workshop in December (~ $8,500).
- GI ACE secured free meeting space (Oct-Nov 2019) at CASS Business School, SOAS, London School of Economics, and Open Gov Hub, DC. Estimated savings of around £2,700 will fund future events and meetings.
- Meetings are arranged where possible to work with the schedule of project partners and minimise travel costs: for instance, a stakeholder workshop was organised in Denver, Colorado (rather than London), to facilitate attendance by the U.S.-based projects and minimise total travel.
2.EFFICIENCY
SOAS ACE
- Rigorous expenditure verification every quarter with partners, and on a case by case basis with individuals, to ensure adherence to financial protocols including the travel and expenses policies, with quarterly reconciliations to manage expenditure
- Regular communication across the RPC to ensure all expectations are clear, and realistic, with payments only made upon satisfactory completion of agreed workplans against planned deliverables.
- SOAS’s financial management mechanisms and reporting are regularly scrutinised by external auditors (their general audit in 2019 found no issues of concern).
- Partners are translating methodology documents and press articles into Bengali/local language to be available for local use, expanding their reach.
- SOAS has developed a publication strategy focussing on ‘Gold Standard’ publication in high impact journals and media outlets which will be implemented and revised throughout the life of the RPC.
- SOAS ACE is committed to open access data. All the publications including data sets produced will be available to download directly from the RPC website, aiding the efficiency of uptake and for further research.
GI-ACE
- GI-ACE rapidly and efficiently negotiated contracts with all grant holders in Q1 of 2019, established easy-to-use tracking tools to ensure financial reporting and quality control are on track, communicating with grantees and using digital platforms to enhance its reach and to communicate with downstream partners.
- To ensure any exchange rate losses are kept to a minimum, GI ACE established a programme account with JPMorgan to operate in GBP, thereby making transfers to the majority UK-based grantees simpler and more efficient.
3.EFFECTIVENESS:
SOAS ACE
- SOAS ACE has produced twenty Working Papers (nine awaiting publication) and three accompanying Briefing Papers – an important step towards Impact (effectiveness) and the greatest potential VFM returns. All have included engagement with policy makers and practitioners, paving the way for research uptake and outcomes.
- The input : output ratio of SOAS ACE research is expected to be high in terms of public money saved, and improved development impact. For example, the input costs of the Bangladesh skills research estimated at £120,000 and could influence programmes in which the ADB alone is investing $1Bn. Even a marginal effect of around 1% (money saved from corruption, and/or additional development outcomes) would more than pay for the research investment.
- SOAS ACE team have conducted numerous consultations with NGOs, academia, government officials, policy makers and the business community, ensuring that the ACE framework focuses on and produces research that tackles real problems – so increasing the chance of impact.
- The results of the digital systems work is expected to lead to new collaboration with Governments of Bangladesh, with implementing systems that draw on SOAS ACE findings.
GI ACE:
- To help ensure effective coordination, GI-ACE invested significant effort in developing clear and efficient management structures, e.g. weekly check-ins involving the programme management team, as well as regular close contact with Principal Investigators (PIs) through workshops, electronic communications and a series of in-depth one-to-one meetings (October and November in both London and DC).
- The Communications Manager has developed an easily accessible system for scheduling blogs and other relevant outputs ensuring project leaders know well in advance the deadlines resulting in a continuous flow of high quality communications material.
- The GI ACE management team has sought wherever possible to explore opportunities to promote the programme amongst key players in the anti-corruption space, notably the World Bank, OECD, and Transparency International.
VFM 4: EQUITY
SOAS ACE
- SOAS ACE country partners are co-PIs of the projects that they implement.
- SOAS ACE’s national partners have continued to host or co-host research meetings (see section 2.3 Research Engagement through research process) and present at major conferences such as the Rethinking Corruption event in Accra in 2019.
- Partners have published six Working Papers, three journal articles and five blogs on online media
GI ACE
50 percent of the project PIs are women, and representatives from partner institutions in developing world countries have been actively encouraged to attend programme events (notably the GI ACE inception and midpoint workshops).

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The ACE research programme is meeting its objectives and has demonstrated strong VFM performance across the 4 E framework, and therefore should continue, based on its own merits.
Moreover, there is a strong external demand for ACE’s research from DFID offices, the World Bank, Country Governments and other actors, with requests for more applications of ACE’s applied, politically realistic research strategy – in more sectors and more countries. In the GCIH portfolio, ACE has extended RED’s reputation for delivering applied, politically framed research to understand and tackle real world constraints to growth and development, and has also helped to inform GCIH’s developing research strategy.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating:  Major

Overview of programme risk - The main risks identified in the Business Case were:
a. Risks in design, procurement and implementation: including to limited pool of experts to produce quality bids; slow procurement; lack of coherence between different components and contractors; misuse of DFID’s funds.
-	With RPC procurement complete and phase 1 research under both components underway, these risks were downgraded in 2017 to ‘minor’. They are mitigated through DFID’s programme and contract management practices; rigorous financial management by SOAS; and active efforts by SRO and team to engage DFID policy and country teams in design and implementation of the programme.
-	The new partnership with Global Integrity that started January 2019 has proved successful in achieving a quick start-up and has regained some of the time lost with the end of DFID’s partnership with the British Academy in 2018. This change in partner benefitted from Global Integrity retaining the BA’s Programme Lead (Prof Paul Heywood) to ensure continuity, research quality, and strategic consistency with the intention of the original Business Case.
-	There is good interaction between SOAS ACE and GI ACE core teams and researchers, including participation in each other’s events. The next step in ensuring coherence between the components is to produce common products in the next 6 months.
b. External risks: delays because of challenging environments (conflict, political instability), sensitive focus (corruption) and vested interests; policy makers are not receptive to learning from new evidence.
-	This continues to be major risk with major potential impact. In the last year, political complexities have affected research in Tanzania, with delays in research permission, reduced engagement from government partners, a reluctance to share data, and some new conflicts of interest declared by researchers being requested to take on new additional roles. Both SOAS and relevant GI ACE sub teams are working hard to work through these challenges and ensure that the risks of delay or termination are reduced, as are any political risks to the researchers themselves.
-	The mitigation described in the business case includes contracting researchers specialising in challenging environments, and research uptake, and active engagement by DFID teams in country. In practice we have found that research teams do have necessary expertise; and engagement with DFID teams is strong and ongoing which has helped to manage risks.
Examples of mitigation action include:
-	The SOAS team continuing to use country visits to refine research plans, including shifting sector focus in cases where stakeholders – including DFID – advised that original plans were not feasible or not high priority. SOAS continues to develop and maintain strong contacts with implementation partners, including government. In several cases, despite generally difficult environments for corruption research, policy makers and officials have been unexpectedly positive in offering engagement and requesting engagement by the researchers. Where appropriate, the SOAS ACE research is not explicitly referred to as ‘Anti Corruption Research’ at public events and meetings in which this would deter key partners from taking part or being open about sector problems.
-	SOAS ACE collaborates directly with World Bank programmes on Skills and Power in Tanzania and the World Bank in Bangladesh has expressed interest in the power and skills sector project. SOAS ACE partner LSHTM has observed some changes with WHO at global level which is starting to change its narrative in response to ACE anti-corruption strategies. The OECD is taking an interest in illicit financial flows and digital identities databases.
-	GI ACE actively engages with global partners such as the World Bank and OECD to build their interest in the new body of research produced by the programme, and to support grantee’s own engagement efforts.
-	The DFID SRO also assists the GI ACE grantees and SOAS ACE projects in networking with DFID policy and programme teams and virtually all have had some contact with relevant DFID teams.

c. Delivery risks in DFID: Failure to engage DFID country teams would threaten the operational focus of the research and make outcome and impact unlikely to be achieved.
Medium probability but high (major) potential impact. Mitigation measures set out in BC are underway, including i) ensuring that ACE is a component of DFID/HMG’s high level ‘offer’ on corruption, including by BA/GI and SOAS Leads’ active engagement with DFID/HMG corruption leads and governance cadre ii) DFID country programme heads have ‘opted in’ to be focal countries. DFID policy and/or country advisors have been part of the SOAS RPC and BA/GI grant assessment panels and the GI ACE Technical Lead and SOAS core team are engaging regularly with DFID governance cadre and policy teams. SOAS ACE has maintained and renewed regular contact with DFID country offices in Tanzania, Bangladesh and Nigeria, including presentations on ACE to the country teams, and briefing for incoming Head of office. GI ACE PIs have regularly engaged with appropriate DFID country office teams (e.g. Uganda, Nepal, India, Tanzania, Malawi, Central Asia).

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

SOAS
Payments are made quarterly in arrears to reimburse actual spend and to ensure that costs are only paid against the approved budget. There is also a payment mechanism which retains 10% of all fees. This amount is released on confirmation of expected performance (time, and quality) being achieved. All performance levels have been met.
Key costs set out in the contract include personnel, associated travel and subsistence, and research uptake. SOAS applies its organisational regulations to downstream partners, ensuring compliance with DFID requirements.
This year’s implementation and spend is on track against the financial forecast and workplan. Costs charged to the SOAS contract to date totals £2,600,840.
During this reporting period there has been a 2% variance in the accuracy of actual spend against the budget forecast although we expect to meet the original forecast of £1.4m for this financial year (April 2019 – March 2020).
Global Integrity (GI)
GI ACE’s new two-year projects commenced work on 1 January 2019 and are due to be completed on 31 December 2020. GI worked rapidly to ensure that contracts could be drawn up from scratch within a very tight time frame; conducted due diligence checks on all partners; developed a risk registry and downstream partner mapping. This was in addition to recruiting a finance manager. GI has done well in continuing to achieve deadlines and required quality standards.
The new GI ACE team developed a programme-level Theory of Change to frame the problem-focused, solutions-oriented approach that is central to the ACE programme. By mid year GI ACE had produced a detailed results framework (Logframe) to track outcomes focused on accountability, research generation, stakeholder engagement and communications and pathways to impact. Significant attention was paid to communications, including recruiting an experienced communications manager to help identify and develop a suite of engagement media: both internally (e.g. online collaboration and management tools such as Slack, Asana and Tettra); and externally, notably through developing a dynamic website and various forms of programme- and project-focused outputs.
GI ACE has developed clear and efficient management structures, with weekly check-ins with the programme management team, and regular close contact with PIs This has helped to ensure that all projects are largely on track.
GI ACE’s grant reporting structures have enabled the team to identify and respond to other emerging risks. One extension grant, originally led by SOAS, was slow to deliver meaningful research results and it was agreed to transfer responsibilities to ensure that the project delivered on its plan.
This year’s implementation and spend is lower than anticipated as there has been a slower spend on two of the grants based at Nottingham Trent (Chmura) and at Nottingham (Meyer-Sahling), but these are still expected to meet their commitments and will be reflected in next year’s financial forecast and workplan. Costs charged to the GI grant to date totals £3,169,619.

Recommendations from the due diligence was introducing a risk register and recruiting a financial manager for this project. Both have been fully addressed.

Date of last narrative financial report(s)	November 2019
Date of last audited annual statement (s)	Not yet available

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring
Both SOAS ACE and GI ACE have clear research sub-team /grantee monitoring systems, developed from their respective Theories of Change, logframes and budget systems. These combine research progress (against delivery plans) with financial management. These systems are actively managed by the core teams, and used to compile component level summary reports, into reporting to DFID.
The DFID SRO and PM have quarterly check ins calls with the GI ACE and SOAS ACE, plus ad hoc meetings, calls and email interaction around and at Programme events and activities.
This annual review was conducted by the SRO and PM. SOAS ACE and GI ACE submitted their respective annual reports and the DFID team reviewed these, and a sample of research products and working papers, before holding meetings with SOAS ACE in London in December 2019; and with GI ACE in Washington DC in January 2020. The PM dialled into both meetings.
GI ACE and SOAS ACE reports include a range of feedback from DFID, country government, and other research users. In addition, the SRO has noted examples of feedback on the ACE research throughout the year.
The SRO also participated in the series of ACE internal events throughout the year, including the GI ACE inception workshops (London, January 2019); SOAS ACE annual partners’ meeting (London, Sept 2019) and GI ACE mid-point workshop (Washington, January 2020).
The SRO has also had direct contact with a range of ACE researchers, particularly to facilitate networking with policy and programme teams in DFID, across HMG, and other partners. This is an important activity for the GCSD team to support research uptake and impact.
The SRO and PM drafted the Annual Review and shared with SOAS ACE and GI ACE teams for fact checking, before finalising in January 2020.
Evidence
The ACE programme is premised on delivery of operationally relevant evidence on ‘what works’ in anti-corruption; and new evidence being taken up to improve programmes. The focus of the programme’s research reflects a DFID funded evidence review of corruption research in 2012.
No formal evaluation is planned as the Theory of Change, contract management, and logframe monitoring should be sufficient to assess the numbers and quality of outputs.
The SOAS ACE RPC’s terms of reference include a detailed component on how RPC delivery will be monitored. Programme-wide logframe development has included a focus on appropriate indicators at outcome level, and means of verification. This involves a systematised qualitative evaluation strategy using an Outcome Mapping method.
Learning
The original framing in the ACE programme business case (politically feasible anti corruption, real world problems, measuring effects) continues to strongly inform the programme, being well articulated and applied by both SOAS ACE and GI ACE, and now reflected and applied by downstream partners. This has taken a concerted effort but is a success, and has helped in the development of an emerging ACE ‘brand’ and unique identity as a body of new, different, evidence on anti-corruption. ACE has benefitted from the sustained effort of the two research leads – GI ACE’s Prof Paul Heywood and SOAS ACE’s Prof Mushtaq Khan.
Establishing a single programme identity can be difficult when several different components are under a one banner. ACE was designed to include a parallel granting programme, and separate research contract, and with no additional overarching programme structure other than DFID’s oversight. The change of partnership from DFID-BA to DFID GI slowed the emergence of a unified ACE identity, but in the last 12 months GI ACE and SOAS ACE have put increasing effort into collaboration and mutual learning, and the emerging body of new ACE research is helping the programme to gain further visibility and credibility. This should continue. The key action for the year ahead is joint products, not just activities.
Progress on recommendations from previous reviews (1/2 page)

SOAS ACE:
1. Revised spending plan: SOAS ACE team to revise strategy to address potential underspend over life of programme – such as through accelerating project development and ACE staffing in Bangladesh; adding a further round of grants; and/or expanding research engagement and uptake plans (SOAS ACE to submit note to DFID by Apr 2019) – done, though further contextual delays have caused a further underspend. SOAS ACE will update spending plan and submit to DFID by end Feb 2020.
2. Measurement of research uptake. SOAS ACE and DFID team to reconsider current logframe indicators for research uptake (including social media) to more effectively monitor and record key examples of most significant impact (e.g. reach, quality and usefulness, uptake and use). To achieve these new goals, this could involve different mediums of communication involving Research Directors (e.g. podcasts). Ongoing. SOAS ACE will again update its social media strategy.
3. Sharing of findings with DFID. SOAS ACE to more proactively share papers with DFID Research and Evidence division and country offices so material can be circulated to relevant advisers. Done. SOAS ACE has engaged widely with DFID this year, including presentation of research in HQ, at cadre conferences, and in country; briefing for DFID country offices; and new partnerships with DFID Nepal and potentially DFID Nigeria.
GI ACE
Research uptake strategy document. GI ACE to produce communications and research uptake strategy document and circulate to DFID by Apr 2019. This should include plans of how GI can work with existing and new grantee holders to maximise the impact of individual research projects, as well as at programme level (GI research portfolio and ACE programme level). Done
ACE Programme
1. ACE Programme identity: SOAS and GI to agree plan to better establish an overall ACE brand and easy to navigate online resources (action: SOAS and GI by Apr 2019). Done: new single landing page for both components, but need for further development of overall programme branding.
2. Programme level policy engagement: SOAS and GI to develop common programme level plan for policy engagement and research uptake including programme level events; and specific support that GI can provide SOAS ACE on policy engagement and uptake. (action: SOAS and GI by Apr 2019). Action taken on joint events – see new recommendation on joint products.
3. Joint products: SOAS and GI ACE leads and core teams to develop at least 4 joint ACE products (blogs or similar) per year. SOAS and GI to agree and submit plan to DFID by April 2019 potentially including joint ‘blog’ on all new grant awards; thematic outputs and events that draw together research under both components, such as anti-corruption and health; and specific country analysis. (action: SOAS and GI to agree and submit plan by Apr 2019). Rolled over into 2020.
4. Outcome and impact monitoring: SOAS and GI to share approaches to outcome and impact monitoring and propose methods to DFID for programme wide monitoring (by Apr 2019). Superceded as GI ACE has developed its own system
5. Update logframe: GI, and DFID, to update logframe to incorporate aggregated GI ACE grant results. (GI to draft GI ACE logframe by end Feb 2019; DFID to compile and circulate updated programme logframe by April 2019). Done, though further minor updates of targets may be necessary.

Annex A: ANTI-CORRUPTION EVIDENCE (ACE) RESEARCH OUTPUTS IN 2019

1.SOAS ACE
Working Papers:
- Antonio Andreoni, Luca Tasciotti, December 2019 - Working Paper 019 – Lost in trade: towards a red-flag system to target trade misinvoicing and tax evasion in Tanzania
- Mushtaq Khan, Sumaiya Kabir and Joseph Ajefu, November 2019 - Working Paper 018- Better jobs: A strategy to end fraud on skills training in Bangladesh
- Emilia Onyena, Pallavi Roy et al., November 2019 - Working Paper 017-Anti-corruption agencies as debt recovery agents: the unintended consequences of anti-corruption efforts in Nigeria
- Adeshola Komolafe, Jamie Hitchen and Oliver Kala-Amah, November 2019 - Working Paper 016-Corruption coverage: the role of the media during Nigeria's 2019 elections
- Mushtaq Khan and Pallavi Roy, October 2019 - Working Paper 015-Digital Identities: a political settlements analysis of asymmetric power and information
- Obinna Onwujekwe, September 2019 - Working Paper 014- Exploring health-sector absenteeism and feasible solutions: Evidence from the primary healthcare level in Enugu
- Mushtaq Khan, Pallavi Roy and Antonio Andreoni, September 2019 - Working Paper 013-Anti-corruption in adverse contexts: strategies to improve implementation
- Kabeer Dawani and Asad Sayeed, August 2019 - Working Paper 012 - Pakistan's pharmaceutical sector
- Adeshola Komolafe, Elor Nkereuwem and Oliver Kalu-Amah, July 2019 - Working Paper 011- Corruption reporting in the media in the 2015 Nigerian elections
- Mushtaq Khan, Antonio Andreoni, Pallavi Roy, April 2019 - Working Paper 010-Illicit Financial Flows: Theory and Measurements Challenges
- Eleanor Hutchinson, Martin McKee and Dina Balabanova, May 2019Working Paper 009- What drives health workers to break the rules and use public resources for private gain?
Briefing Papers:
- Briefing Paper 007- Better jobs: a strategy to end fraud in skills training in Bangladesh, December 2019
- Briefing Paper 006- Anti-corruption in adverse contexts: strategies for improving implementation, December 2019
- Briefing Paper 005-Setting the agenda or toeing the line? Corruption news coverage during Nigeria's elections, November 2019
Journal articles:
- Obinna Onwujekwe et al - International Journal of Health Policy and Management, December 2019, Where Do We Start? Building Consensus on Drivers of Health Sector Corruption in Nigeria
- Obinna Onwujekwe et al - Health Policy Planning, Vol. 34, Issue 7, September 2019, Corruption in Anglophone West Africa Health Systems: a systemic review of its different variants and the factors that sustain them
- Eleanor Hutchinson, Dina Balabanova, Martin McKee - International Journal of Health Policy and Management, Vol. 8, Issue 4, April 2019, We need to talk about corruption in health systems
Journal submissions:
''Corruption in the delivery of frontline healthcare services in low and middle-income countries of south and south-east Asia: a scoping review of current realities and future prospects' to BMC Public Health on October 24, 2019
Blogs
- Digitisation of land administration: Will it work? (Mehnaz Rabbani and Faruq Hossain, BIGD, BRAC; originally published in the Daily Star)
- Tackling corruption to achieve universal health coverage (Dina Balabanova, LSHTM, and Onwujekwe Obinna, UNN; originally published on Devex)
- African Conglomerates and Their Links to the Public Sector: Three Insights and Areas for Research (by Agata Slota, Palladium)
- Pakistan’s hike in drug prices may be painful, but it is necessary, (originally published in Prism)
  Talking corruption at the African Health Economics and Policy Association conference
- Another victory for Buhari – but what will it mean for corruption? (Joseph Ajefu)
- Could women in Lagos be less likely to engage in corruption than men? (Agata Slota, Palladium)
- Combatting corruption the smart way (originally published by The Premium Times)

Research projects summaries (one pager)
- Improving the procurement of essential drugs in Bangladesh
- Reducing private sector risk to increase competition and reduce corruption in the electricity sector in Bangladesh
- Reducing incentives for fraud and corruption in skills programmes in Bangladesh
- Understanding business development under regimes of capitalist accumulation in Tanzania
- Enhancing, targeting and diversifying electricity generation in Tanzania
- A new approach to strengthening accountability for better health outcome in Tanzania
- Curbing smuggling of rice and sugar towards productive development in Tanzania
- Governance tax incentives for productive investments in Tanzania
- Skilling up Tanzania
- Improving the procurement of essential drugs in Tanzania
- Improving Nigeria's electricity supply industry
- Business houses and capitalist accumulation in Nigeria
- The politics and effectiveness of Nigeria's economic and financial crimes commission (EFCC)
- Corruption interdependencies in the extractives sector in Nigeria
- Increasing agricultural productivity through fertiliser use in Nigeria
- Combatting corruption in health providers in Nigeria
- Anti-Corruption in the Nigerian media

Podcasts
- Jobs, corruption and major development donors: applying the ACE approach to a thorny development problem (Mushtaq Khan)
- Why are off the shelf approaches to anti-corruption failing? New podcast (Mushtaq Khan)

Other

Health Webinar: What are we missing on health corruption?

Facebook BIGD-BRAC Public lecture recording: Digital identities (Mushtaq Khan, Pallavi Roy)

Digital Identities local print media and online press in Bangladesh

2. GLOBAL INTEGRITY ACE
Policy briefs, reports, working papers, datasets:
- Data update of World Bank, IADB, and EuropeAid datasets on development aid funded contracts and projects (David-Barrett, February 2019)
- Dieter Zinnbauer, July 2019: Leveraging the Role of the Urban Planning Profession for One of the Central Policy Challenges of Our Times
Journal Articles:
Accepted (not yet published)
- Harvey: Tracking the international proceeds of corruption and the challenges of national boundaries and national agencies: the UK example
- Meyer-Sahling: (Un)Principled Principals, (Un)Principled Agents: The Differential Effects of Managerial Civil Service Reforms on Corruption in Developing and OECD Countries
Submitted
- Meyer-Sahling: Oiling the Bureaucracy?Political Spending, Bureaucrats and the Resource Curse
- Meyer-Sahling: Exit, Voice, Sabotage: Public Service Motivation and Guerrilla Bureaucracy in Times of Bad Government
- Meyer-Sahling: Merit recruitment, tenure protections and public service motivation: Evidence from a conjoint experiment with 7,300 public servants in Latin America, African and Eastern Europe
- Anders: Corruption and the impact of law enforcement: Insights from a mixed-methods study in Malawi
- David-Barrett: Controlling Corruption in Development Aid: New Evidence from Contract-Level Data.
- David-Barrett: Anti-Corruption Interventions in Development Aid: Is Corruption Reduced or Merely Displaced?
- David-Barrett: Explaining systemic corruption: The case of public procurement in Ghana
Websites and related resources:
- GI ACE website: http://ace.globalintegrity.org
- ACE landing page: http://anticorruptionevidence.org or http://anti-corruption-evidence.org
- Curbing Corruption in Government Contracting (David-Barrett) website: http://redflags.govtransparency.eu/
Blogs
- Kicking off GI-ACE: Three Anti-Corruption Themes & 14 Projects (January 2019)
- How to Reduce Corruption: Reflections, including from the Paris Integrity Forum (May 2019)
- Heathershaw: How effective are beneficial ownership checks? (June 2019)
- Klopp: Realising the dream of Pan-African trade: Giving women voice in improving borders (June 2019)
- Harvey: Hiding the beneficial owner and the proceeds of corruption (June 2019)
- Buntaine: Fighting corruption by recognizing integrity (June 2019)
- David-Barrett: Using ‘red flag’ indicators to identify corruption and analyse reform efforts in the procurement process (July 2019)
- Dhillon: Are top-down audits complements or substitutes to social audits? (July 2019)
- Christian Alexander (Watson): Strengthening integrity within the urban planning profession to combat corruption in urban development (July 2019)
- Jablonski: Identifying and preventing drug theft in Malawi (July 2019)
- Baez Camargo: Harnessing informality to promote integrity and design better anti-corruption programmes – new research project (July 2019)
- Meyer-Sahling: Toward a more professional and ethical civil service in Nepal
- Haberly: Does transparency bring cleanliness? Offshore financial secrecy reform and corruption control (August 2019)
- Anders: Effective or falling flat? A fresh look at high-level corruption prosecutions in three African jurisdictions (August 2019)
- Chmura: From citizen science to global anti-corruption: Two sides of the same coin (August 2019)
- Baez-Camargo: Working with social norms to develop effective anti-corruption interventions (September 2019)
  - Quick Guide to Social Norms and Corruption
- David-Barrett: Why is collecting and analysing data about public procurement so damned difficult? Data scientists explain some common problems (September 2019)
  - Red Flags Explainer / FAQs
- Anders: Does innovative enforcement help or hurt anti-corruption efforts? (September 2019)
- Haberly: A new map of financial transparency reform: 2000-2015 (October 2019)
- Buntaine: Pairing field experimental and ethnographic methods to study anti-corruption (October 2019)
- Baez Camargo: Harnessing informality for anti-corruption practice: Shifting the unit of analysis from individuals to networks (October 2019)
- Isabelle Adam (David-Barrett): Where does pressure for public procurement transparency come from? Reflections from Uganda and Tanzania (October 2019)
- Tom Mayne (Heathershaw): The challenges in researching enablers of the corrupt  (October 2019)
- Dhillon: How can top-down audits and social audits respond to the changing technology of service delivery in India? (November 2019)
- Harvey: Statistical challenges and ‘cash for penguins’ (November 2019)
- Anders: African anti-corruption agencies and the problem of independence (November 2019)
- Klopp: From whistleblowing to community monitoring on East African borders (November 2019)
- Baez Camargo: Harnessing Informality (Pt. 2): What could a network intervention to tackle anti-corruption look like? (December 2019)
- Dorothy Ndhlovu, Gilbert Siame, and Laura Nkula-Wenz (Watson): Qualitative Action Experiment tackles professional integrity in the Zambian planning sector (December 2019)
- Tobias Stark (Baez Camargo): Social network interventions to tackle corruption (December 2019)
One-pagers / brochures
- Global Integrity Anti-Corruption Evidence (GI-ACE) research programme
- Addressing bribery in the Tanzanian health sector: A behavioural approach (Baez Camargo)
- Can positive public recognition lead to good governance? (Buntaine)
- Centralized versus decentralized monitoring to reduce corruption: Insights from comparisons across Indian states (Dhillon)
- Cities of integrity: Urban planning and corruption in Africa (Watson)
  - Cities of Integrity brochure
- Civil service reform and anti-corruption: Does ethics training reduce corruption in the civil service? (Meyer-Sahling)
- Curbing corruption in procurement (David-Barrett)
- Detecting and deterring medication theft: A field study in health clinics in Malawi (Jablonski)
- Does transparency bring cleanliness? Offshore financial secrecy reform and corruption control (Haberly)
- Ethical border trading between Kenya and Uganda for small-scale businesses (Klopp)
- Fighting high-level corruption in Africa: Learning from effective law enforcement (Anders)
- Harnessing informality: Designing anti-corruption network interventions and strategic use of legal instruments (Baez Camargo ext)
- Hiding the beneficial owner and the proceeds of corruption (Harvey)
- International deal-making, beliefs, and local social norms (Chmura)
- Testing and evidencing compliance with beneficial ownership checks (Heathershaw)
Other:
- Kickback podcast, episode 7, "Which questions to ask to gain new insights into the wicked problem of corruption" (April 2019; repurposed Dec 2019: The Basics)
- Heathershaw: Evidence before the House of Commons Foreign Affairs Committee (June 2019)
- Haberly: Tax Justice Network conference: Introducing the Atlas of Offshore Foreign Direct Investment (July 2019)
- Harvey: Suspicious Transaction Report podcast, episode 6: "What's the Risk?" (November 2019)

Annex B	GENDER ANALYSIS IN ACE RESEARCH

SOAS ACE
Five projects have anti-corruption strategies that could have clear developmental impact on gender-based asymmetries.
1)	The study on corruption in the enforcement of land rights in Bangladesh will focus on the informal processes through which land conflicts are resolved. Without an understanding of these informal processes and the issues that lead to corruption, feasible anti-corruption strategies cannot emerge. We have already found in our scoping studies that more than a third of land disputes involve disputes within families, particularly involving the women’s inheritance rights. Our research on informal processes will help devise strategies that make it easier for women to protect their rights.
2)	Our research on the effects of ‘artisanal mining’ in the Niger Delta suggests the apt anti-corruption response is to work on mitigating the externalities that hurt the more vulnerable sections of society—children, youth and especially women. Addressing the causes of this corruption will need systemic reform and in the medium to short term this looks difficult to achieve. We use the ACE framework and strategy clusters of incentive restructuring and designing for differences to see if some of the most damaging spillover effects can be addressed in the meantime. Another focus of research emanating from our work in the Niger Delta is to explore mitigating strategies where our framework-based analysis suggests addressing intractable corruption through our strategy clusters is not feasible in the short to medium term. Our initial results suggest female respondents have been very receptive towards mitigation-based policy solutions like providing healthcare services to address skin and respiratory diseases that arise due to the environmental effects of ‘artisanal’ mining.
3) A strong area of gender focus lies in the LSHTM-ACE health sector work that focuses primarily on frontline healthcare providers. We have identified three possible strands and hypotheses for further research on gender in 2020-21, in seeking to operationalise the ACE approach to anti-corruption.
First, work on strengthening health systems and the care economy shows that the health workforce is feminised, female providers are more likely to suffer from a lack of career and training opportunities and supportive supervision. In some settings, working in unsafe environments creates additional vulnerability and threats of sexual violence for female providers. In this knowledge, our findings highlighted initial ideas for the influence of gender relations on corruption, and the incentives and networks that underpin them to emerge.
- In Nigeria, women’s position in the care economy (as poorly paid providers of care in the health sector with considerable unpaid care responsibilities within homes including working in farming alongside the health system) are drivers of absenteeism.
- In Bangladesh, women were concerned about sexual violence at night in rural health facilities, but the informal ways of getting out of these rural placements may also be gendered – women called on their husband’s political networks to get new postings.
- In Ugandan drug shops, rule-breaking takes place in predominantly female spaces – run by women to provide medicines for predominantly (although not exclusively) female customers. Becoming more rule abiding, refusing to sell particular medicines or half doses will likely cause friction, go up against social relationships that underpin illegal medicine sales in these settings. But, new lobby groups set up to support the interests of drug shops are dominated by men – and this has implications for the configurations of actors and possible alliances in the anti-corruption space.
Second, there is evidence that power structures, networks and distribution of resources are gendered. These operate at the societal level and are replicated in the health systems bureaucracy and affect how gender affects actor behaviour and policy outcomes. This has been documented but not in relation to corruption particularly in the health sector.
Third, if anti-corruption strategies of realigning incentives and creating novel forms of collective action (critical approaches from SOAS ACE for the health sector) are to be successful then they will need to have strategies that take these gender differences into account. Given that gender relations are rooted in power, we need further analysis of the ways in which power is distributed in order to understand how the intersection of the socio-political and institutional (health systems) structures, formal and informal relations is manifest and shape corrupt behaviours among men and women.
Building on the ACE approach, we will first study providers, service users and population using a gender lens, to: 1) understand how corruption is rooted in power and health system bureaucracies and its differential gender impact, 2) identify how incentives to engage in rent-seeking differ among different gender and socio-economic strata and 2) identify entry points that help to engage women as actors for change – individually and collectively.
Examples of health and gender studies that will be conducted in 2020-21 include:
3)	Understanding the root causes and mobilising women through the health facility committees in addressing absenteeism in Nigeria
4)	Social networks, career growth and workplace experience of female doctors in Bangladesh
5)	Uganda, examining the networks of women who provide financial and business assistance (to the more established drug shops), exploring how these networks can be mobilised against informal drug shops and considering the possibilities and difficulties associated with becoming rule-abiding around medicine sales.
Other consortium efforts to increase our gender focus in 2020 will be to publish a methodology paper as part of our ACE Working Paper series. The paper will outline how the ACE framework is well-suited to address issues of gender-based inequalities and how anti-corruption strategies can help address these asymmetries. Gender inequalities are both often rooted in deep structures of asymmetric power. To be effective, anti-corruption strategies have to take account of asymmetries of power that underpin specific types of corruption and develop strategies that either address these asymmetries or find ways of working around them. Many types of corruption adversely affect women, who are often vulnerable in terms of their own economic and social power, and in terms of access to powerful networks, particularly in developing countries. The forthcoming paper will highlight how anti-corruption strategies that target the most socially damaging types of corruption can also address corruption that adversely affects women. These anti-corruption strategies can benefit from an investigation of gender inequalities to see how the latter affect the impact of and responses to specific types of corruption.
Finally, in Jan 2020, SOAS ACE is launching a second round of competitive grants call on corruption in the private sector with a key criterion for anti-corruption strategies that will have a direct impact on improving gender inequalities. Given this priority we hope to attract proposals that will take effective gender analysis further in SOAS-ACE research in 2020-21.

GI ACE
1) Klopp's project on "Ethical border trading" has a specific focus on women traders, including the differential exploitation that they face, including violence and sexual exploitation.
2) Jablonski's project on "Drugs theft in Malawi" scrutinizes the impact of theft on family access to healthcare. Since it is predominantly women who are responsible for family access to medicines, the project measures the effects of gender on experiences with corruption. (Caveat: effects may have to be interpreted with caution as the relevant sample is not randomized).
3) Watson's Cities of Integrity Project conducted a qualitative action experiment training urban planners in Zambia on Integrity. 35% of participants were women - which stood out to the project team as a useful/hopeful observation in order to ensure diversity.
4) At programme level, GI AC strives to balance female/ male representatives from projects on panels and panel proposals; and works to ensure there are no ‘manels’ at events and/or during our workshops (including by asking more women to be outside observers than men, for example).