## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
Empowering communities in the context of commercial agriculture
IMPACT | Impact Indicator 1 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
Communities empowered to influence public decisions and private sector conduct in favour of bottom-up, locally beneficial and more sustainable investments in commercial agriculture | Extent to which public or private-sector policies or practices reflect communities' position or recommendation | Planned |  | N/A | N/A | Public or private-sector policies/ practices reflect communities' position or recommendation | Public or private-sector policies/ practices reflect communities' position or recommendation | Public or private-sector policies/ practices reflect communities' position or recommendation
|  | Achieved |  |  | tool elaborated
Source
Outcome harvesting with • Programme staff • May also include the impact group as part of the participatory self-assessment process
OUTCOME | Outcome Indicator 1 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31 | Assumptions
Outcome 1. Improved evidence, insight and guidance on how to empower communities for bottom-up, locally beneficial and more sustainable investments in commercial agriculture. | Added value of evidence generated by the project in terms of novelty, insightfulness (including consideration of intra-community differentiation e.g. gender), quality of evidence and positioning for use as perceived by key stakeholders (e.g. project steering committee) | Planned |  | N/A | N/A | N/A | N/A | Key stakeholders' perception of the added value of the evidence generated is positive. | The project will empower communities to engage with public and private sector decision-makers in order to ensure agribusiness investments respond to local development agendas and improve rural livelihoods. The action will take a three-pronged approach: First, by generating rigorous evidence and distilling lessons from best practice, the project will develop practical insights and constructive guidance on socio-legal community empowerment approaches that enable people to have a greater say and get a better deal in agribusiness investment processes. Second, building on the evidence generated, and feeding lessons back into evidence generation, the project will work with communities in selected sites to develop and use approaches that empower them to articulate their development agenda, make more informed choices, exercise their rights, and where relevant develop equitable partnerships with the private sector. Third, to make a substantial difference given the scale of the challenge, the project will promote the uptake of community empowerment approaches in the policy and practice of agribusiness investment, through effective outreach both nationally (policy engagement) and internationally (e.g. lesson-sharing webinars, workshops and blogs), aiming to make grassroots-level interventions, national policy and legislation, and private sector practice more conducive to community empowerment at scale.
|  | Achieved |  |  | tool designed
Source
Survey using tailored RQEA tool, (written survey, interviews – video or scribed) • Strategic Advisory Group members using the RQEA tool, individually or both. • Key informants identified from practitioner and researcher pools using the Research Quality & Effectiveness Assessment (e.g. 3 additional experts – tbc at end of project) • (Self-assessment by project teams the Research Quality & Effectiveness Assessment as a group, individually or both)
| Outcome Indicator 2 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
Outcome 2. In two low or middle-income countries, small-scale rural producers and/or wider communities empowered to make informed choices, exercise rights and where relevant develop equitable partnerships with the private sector. | Degree to which small-scale rural producers and/or wider communities feel they have been empowered through project, assessed considering intra-community differentiation (e.g. wealth, status, gender, age, disability) - | Planned |  | N/A |  | Small-scale rural producers and/or wider communities reporting feeling empowered through project, across all relevant characteristics of identity | Small-scale rural producers and/or wider communities reporting feeling empowered through project, across all relevant characteristics of identity | Small-scale rural producers and/or wider communities reporting feeling empowered through project, across all relevant characteristics of identity
|  | Achieved |  |  | tool elaborated
Source
Self-assessment by small-scale rural producers and/or wider communities living in project sites against dimensions and degrees of empowerment decided upon in participatory manner
| Outcome Indicator 3 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
Outcome 3. Effective community empowerment approaches upscaled through strategic outreach | Extent to which key actors have used and applied i) evidence/insight/guidance and ii) approaches developed by the project | Planned |  | N/A | N/A | N/A | N/A | Key actors have used and applied evidence/insight/guidance and approaches developed by the project
Achieved
Source
Combined use of stakeholder survey of in-country project key stakeholders and documentation of substantiated harvested outcomes.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31 | Assumptions
Evidence, insight and guidance generated on socio-legal empowerment approaches that enable people to have a greater say and get a better deal in commercial agriculture | Number of research reports, briefing notes and guides produced | Planned | n/a | 0 | 1 Research report, 1 Briefing Note, | 1 Research reports, 1 Briefing Notes, 1 insight workshop, 1 briefing note on the workshop, | 1 Research report, 1 Briefing Note, | 1 Research report, 1 Briefing Note, 1 guidance tool | Willingness by key stakeholders to engage in the strategic advisory group. Practitioners and researchers willing to engage in project activities including in distilling lessons from the empowerment approaches they have developed in the context of agribusiness investments. Lean operating procedures maximise time-efficiency and minimise transaction costs in project implementation.
|  | Achieved |  | 0 | Research report 1, Briefing note 1
Source
Project documentation
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Number of downloads, number of citations | Planned | n/a | 0 | 1000 downloads | 1000 downloads | 1000 downloads | 1000 downloads (6months beyond project end?)
|  | Achieved |  | 0 | Report 677 (32.5% GS); BN 86 (48.8% GS)
Source
Download and citation stats
| Output Indicator 1.3 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Extent to which evidence/insight/guidance responds to challenges to small-scale rural producers and/or wider communities and commercial agriculture emerging from the two target countries, e.g. with regard to community-investor relations, differentiation within and between communities (including gender), or overarching legal and policy frameworks | Planned |  | 0 | Review and revise planned products accordingly to keep on track | Review and revise planned products accordingly to keep on track | Challenges responded to or deviation justified | Challenges responded to or deviation justified
|  | Achieved |  |  | Strategies being tailored to context mapping - finalised July 2019
Source
Country scoping will assess context, conduct policy analysis and identify relevant challenges in each country to be summarised as rationale in country work plans S+D10coping and policy analysis, stakeholder survey (end of project) • Programme staff in CSRC/NACCFL, IIED and WOLREC • Stakeholders in-country via stakeholder survey response to “Please tell us about the extent to which you feel the EPIC project responded to the key challenges facing smallholders and commercial agriculture in your country. “
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%) |  | RISK RATING
371949.3196
INPUTS (HR) | DFID (FTEs)
1.7389
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-03-01 | 2021-03-01 | 2021-12-31 | Assumptions
Tools for grassroots-level capacity support developed and used in two low or middle-income countries. | Number and type of tools developed | Planned |  | Countries identified | 1-2 interventions underway in both countries | Clarity on sphere of action in each site and 2 bounded actions delivered in each country (e.g. gender audit, e.g. FACT method) | X tools |  | Country selection will draw heavily on the country diagnostics that DFID is conducting as part of its wider work on commercial agriculture. Site selection within each country will be based on criteria to be fine-tuned and including: local demand; opportunity and relevance to DFID’s geographic priorities. Opportunities for synergies with other DFID-linked work, including the CASA smallholder development facility and the work of CDC, will be a key consideration in both country and site selection. Political space in each country, and genuine and sustained buy-in from key stakeholders including communities, government and the private sector.
|  | Achieved |  | Countries identified | Interventions underway in 2-3 sites each country with activities at local and national level
Source
Project documentation
| Output Indicator 2.2 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Number and basic profile of households reached | Planned |  | Countries identified | Target groups identified and target reach defined | 1512 people (Malawi: 187 Nepal: 1325) 64% women (Malawi: 53% Nepal: 65%) | 1512 people (Malawi: 187 Nepal: 1325) 64% women (Malawi: 53% Nepal: 65%) | 1512 people (Malawi: 187 Nepal: 1325) 64% women (Malawi: 53% Nepal: 65%)
|  | Achieved |  | Countries identified | Target districts and groups identified
Source
Project documentation
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Extent to which tools reflect social differentiation in terms of age, gender, income, ethnicity, disability, etc. as relevant to the context | Planned |  | Countries identified | All tools developed reflect social differentiation as relevant to the context. | All tools developed reflect social differentiation as relevant to the context. | All tools developed reflect social differentiation as relevant to the context. | All tools developed reflect social differentiation as relevant to the context.
|  | Achieved |  | Countries identified | Assessment tool elaborated
Source
Survey using the RQEA tool, document review, FGDs/interviews • Members of the impact group who used the tool, via FGDs/interviews • Key informants using the RQEA and stakeholder survey • Self-assessment by project teams as a group, individually or both • Impact group through the disaggregated self-assessment data
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%) |  | RISK RATING
786369.6406
INPUTS (HR) | DFID (FTEs)
2.0601
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31 | Assumptions
Lessons shared for mainstreaming community empowerment in the policy and practice of agribusiness investments in the target countries and internationally. | Number of i) national outreach events, ii) annual partner events, iiI) international outreach workshops | Planned |  | 0 | i) 0, ii) 1, iii) 0 | i) 1, ii) 1, iii) 0 | i) 1, ii) 1, iii) 0 | i) 1, ii) 0, iii) 1 | Political space in each country enables effective outreach, lesson sharing and alliance building over project duration. Evidence from outputs is well distributed across stakeholders
|  | Achieved |  |  | i) 0, ii) 1, iii) 0
Source
Project documentation
| Output Indicator 3.2 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Number of attendees at above events | Planned |  | 0 | i) 0, ii) 10, iii) 0 | i) 20, ii)10, iii) 0 | i) 20, ii) 10, iii) 0 | i) 20, ii) 0, iii) 30
|  | Achieved |  |  | i) 0, ii) 20, iii) 0
Source
Download stats, project documentation
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Number of i) lesson learning products, ii) webinars iii) blogs | Planned |  | i) 0, ii) 1, iii) 0 | i)1, ii) 2, iii) 3 | i) 1, ii) 2, iii) 3 | i)1, ii) 2, iii) 3 | i) 1, ii) 1, iii) 1
|  | Achieved |  | i) 0, ii) 1, iii) 0 | i) 0, ii) 1, iii) 1 [Lesson-sharing report in review with companies. Webinar blog awaiting webinar. Other blog (research report-related) in production]
Source
Project documentation
| Output Indicator 3.4 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Number of downloads/attendess/views at above events | Planned |  | i) 0, ii) 20 iii) 0 | i)300, ii) 20, iii) 500 | i) 300, ii)20, iii) 500 | i) 300, ii) 20, iii) 500 | i) 300. ii) 20, iii) 500
|  | Achieved |  | 20 | i) n/a, ii) 25, iii): Pre-webinar news story: 319; Post-webinar blog: 373
Source
Download stats, project documentation
| Output Indicator 3.5 |  | Baseline | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2021-12-31
| Extent and nature of outreach, including as reflected in active participation in international policy debates | Planned |  | 0 | Participation in / contribution to at least one key relevant international policy event | Participation in / contribution to at least one key relevant international policy event | Participation in / contribution to at least one key relevant international policy events | Participation in / contribution to at least one key relevant international policy events
|  | Achieved |  |  | 1 Event (World Bank Land and Povery Conference presentation)
Source
Project documentation including events attendance register and event reports / report backs
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
380880.7289
DFID (FTEs)
INPUTS (£) | 2.474 | [7 empty] | RISK RATING

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.