ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Multi Year Humanitarian Programme
Country or region targeted	Pakistan (Nationwide)
Type of cost extension (if applicable)	No cost extension
Original project budget	£100 million
Original project start and end dates	December 2014 – September 2019
Cost extension value (if applicable)	£0
New project end date (if applicable)	September 2020
Business Case Quest Document No.	8818934

INFORMATION
What is the project’s purpose?
The programme aims to reach more than 2 million people with emergency assistance and early recovery support whilst also enabling a stronger humanitarian system and greater collation and use of evidence in programming.
What is the objective of the cost extension or other changes?
There are three main objectives for this no-cost extension. It meets the criteria as outlined in the Smart Rules for either (a) to use unspent funding to deliver further results in line with DFID’s objectives and (b) delays in implementation due to a change in context. / The three objectives are: / Reallocate unspent funding to provide ongoing recovery assistance to people in need and to further strengthen the humanitarian system in Pakistan; / Enable scale up and testing of innovations and learning from the MHYP, including increased learning from the Pakistan Evidence and Learning Platform (PELP) established under the MYHP; / Ensure humanitarian funding is in place whilst DFID Pakistan aligns and learns lessons from its resilience and humanitarian work, and designs and procures a new merged humanitarian and resilience programme beyond 2020.
What is the additional and total support the UK will provide?
The total cost remains the same (£100 million).
What are the expected results?
It is expected that the extension will enable around 500,000 additional people to be provided with emergency and early recovery interventions (dependent on needs).
What is the approach to implementation?
The implementation arrangements are outlined as below. Reporting and other requirements (e.g. progress meetings) will be maintained as outlined in the existing business case. See footnote for acronyms. / Does the intervention meet the requirements of the Gender Equality Act? / The design of this intervention is strongly focused on how it will contribute to reducing gender inequality. One of the programme’s aims is to target women and female headed households who are amongst the most vulnerable to natural disasters and conflict. When reviewing the results of the programme, the impact on women and girls will be a criterion and all results will be disaggregated by sex. / What are the risks of terrorist financing? / The potential for terrorist financing associated with this intervention is assessed as possible. Working with locally-based civil society organizations naturally entails some risk of diversion, particularly in a country such as Pakistan which has a high threat profile. However, we assess, based on our experience with similar programming, that these risks can be sufficiently managed through a due diligence process and financial controls. UN procedures are in line with UN Security Council Resolutions relating to terrorism, including UN Security Council Resolution 1373 (2001) and 1267 (1999) and related resolutions. Cash disbursements in conflict affected areas go through more scrutiny by all partners and the Government of Pakistan.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The context has shifted on two main fronts: / The lack of a major natural disaster in the past few years has resulted in an increase in the numbers of people supported with early recovery and longer term rehabilitation. The needs remain high, especially in remote areas of KP where access is harder. / The humanitarian needs of FATA have changed, with support being needed for those who are now returning rather than only for those who were displaced. More than 70% of the original displaced population have now returned but face very low levels of access to basic services, shelter and food. Continuing humanitarian support to people in the most recent return phase is required. / Through partner evaluations, there has been some learning and assessment of different approaches to delivery of some interventions. For example, an extension to previous DFID funded research into shelter has shown how changes can be made which reduce costs and help improve longevity. Partners are currently working to assess the evidence of other interventions – for example, kitchen gardens – with a view to informing future programming. / No new risks have been identified which are only relevant to this extension. The risks remain in line with those outlined in the original business case. Risks are monitored and update on a regular basis in quarterly and other meetings with project partners.
[note] Acronyms: Pillar I - International Office for Migration (IOM) with Food and Agriculture Organisation (FAO),UN International Children’s Fund (UNICEF), and civil society organisations HANDS (local) and ACTED (international); Pillar II: International Rescue Committee (IRC)-managed IVAP is the IDP Vulnerability Assessment Profiling, used by all organizations working in FATA to identify people and communities most in need; UN Development Programme (UNDP) and World Food Programme (WFP); Pillar IV: UN Office for the Coordination of Humanitarian Affairs (OCHA) managed PHPF is the Pakistan Humanitarian Pooled Fund which provides quick funding to local and international organizations to respond to new emergencies.