# Annual Review

Title: Multi-Year Humanitarian Programme in Pakistan (MYHP)
Programme Value £ (full life): £100 million		Review Date:
Programme Code: 204603	Start Date: 10-12-2014	End Date: 30-09-2020

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	B	A	A	A	A
Risk Rating	Low	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4811609.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204603/documents

A. Summary and Overview

Description of programme
Pakistan is one of the most disaster-prone countries in the world, with the poorest most at risk. Protracted crises in areas of the country have also displaced millions. The six-year Multi-Year Humanitarian Programme (MYHP, 2014 - 2020) is a £100 million programme and aims to reach at least two million people with life-saving assistance and early recovery activities following natural disasters and conflict. MYHP is delivered through four main pillars. Details of these components can be found in Annex I. A summary is shown below:
[note] https://reliefweb.int/sites/reliefweb.int/files/resources/68230_7pakistandrmstatusreport.pdf
[note] Conflict affected areas in erstwhile FATA (Federally Administered Tribal Areas) or the Newly Merged Districts. While more than 1.5 million internally displaced people have returned to their places of origin following an acceleration of returns over the past few years, over 96 000 people remained displaced as of December 2018.
[note] Pillar I - International Office for Migration (IOM) with the Food and Agriculture Organisation (FAO), UN International Children’s Fund (UNICEF), and civil society organisations HANDS (local) and ACTED (international); Pillar II: International Rescue Committee (IRC)-managed IVAP is the IDP Vulnerability Assessment Profiling, used by all organizations working in FATA to identify people and communities most in need; UN Development Programme (UNDP) and World Food Programme (WFP); Pillar IV: UN Office for the Coordination of Humanitarian Affairs (OCHA) managed PHPF is the Pakistan Humanitarian Pooled Fund which provides funding to local and international organizations to respond to new emergencies. Approximately £1.2 million were allocated to the emergency response of 2014 conflict induced displacements in FATA. These costs are not reflected in the diagram above. To Note: Common partners are seen across the various consortia under the programme. There is no duplication of funding to these partners nor is there an overlap of activities as partners continue to operate under different projects in different geographical areas. Further details can be seen in Annex I.

This year MYHP has reached approximately 4.7 million people with emergency assistance and recovery through a mix of interventions including: water and sanitation, livelihoods support, protection mechanisms and shelter. This figure includes around 2.8 million people who were reached through the Natural Disaster Consortium (NDC’s) emergency drought response in Sindh and Baluchistan. In addition to responding to natural disasters, MYHP has provided emergency support to internally displaced persons (IDPs) from the conflict in the Khyber Pakhtunkhwa Merged Districts (KPMD), formerly known as the Federally Administered Tribal Areas (FATA), and the wider Khyber Pakhtunkhwa (KP) Province.
[note] The number of people in a household varies particularly between districts. In Sindh the average number in a household is 6.0 people while in KP numbers often exceed 10. Therefore, beneficiary numbers are calculated by the number of households reached with an intervention multiplied by the average family size in that area.
[note] The Federally Administered Tribal Areas (FATA) were a  semi-autonomous tribal region in north-western Pakistan that existed from 1947 until being merged with neighbouring province Khyber Pakhtunkhwa (KP), in 2018. In May 2018, the National Assembly of Pakistan voted in favour of an amendment to the Constitution of Pakistan for the FATA-KP merger which was presented for approval in the Khyber Pakhtunkhwa Assembly, and passed with majority vote. The 25th Amendment received assent from the President of Pakistan, after which FATA was officially merged with Khyber Pakhtunkhwa. FATA is the poorest region of Pakistan. 73% of its 5 million population lives in poverty compared to a national average of 39%. Pakistan Multidimensional Poverty Report, Ministry of Planning Development and Reform with support from the University of Oxford and UNDP (2016). Following the merger of the former FATA with Khyber Pakhtunkhwa in May 2018, FATA agencies have been brought under the control of the KP Provincial Government. The transfer of powers has been uneven with changes in Government policies and uncertainties over roles. Working in KP and the newly-merged districts continues to provide challenges. In some tribal areas the security situation remains volatile and restrictions on travel often at short notice, impacts on delivery schedules and restricts access for monitoring. Tight security along the border and the construction of a border fence (reportedly 60% being completed) will have serious implications on both legal and illegal cross border trade, an important livelihood option for many frontier communities. KPMD and other DFID funded programmes working in the Newly Merged Districts will need to relook at the changing political economy to help inform and improve programming

The programme aligns with the UK Humanitarian Reform Policy and supports UK commitments to the World Humanitarian Summit and the Grand Bargain. The programme complies with the UK International Development (Gender Equality 2014) Act and ensures inclusion of people with special needs. This year the programme has helped reach more than 22,700 Persons with Disabilities (PWDs).
[note] The Grand Bargain Commitments the MYHP focusses upon are: localisation of the response and; increasing the use of cash-based transfers.

For 2019/20, £8.7 million (50%) of the MYHP budget is classified as International Climate Finance (ICF). Interventions such as livelihood activities, shelter and water, sanitation and hygiene help people become more resilient to disasters. Many disasters are exacerbated by climate change and resilience to future climate change is built into the design of these interventions.

Summary supporting narrative for the overall score in this review
The programme scored an A – (‘Outputs met expectations’). While all partners have complaints mechanisms, partners have demonstrated awareness of these rather than a demonstration of their effectiveness, resulting in a score of B for Output 4. However, this lower score has been offset by the Output indicators having met their expectations. This leads to the programme overall receiving an A, due to the weighting of the Outputs. In the absence of a major flood or earthquake this year, the programme initially prioritised support to those displaced by conflict. However, following the declaration of drought in parts of Sindh and Baluchistan this year, programme priorities were reassessed, and emergency support was provided to stabilise assets and assist recovery.

Progress against Outcomes during the year were:
- Over 3.1 million people reached with relevant assistance within 3 months of a disaster;
- Technical and Value for Money (VfM) improvements demonstrated by 85% of the programme partners;
- Over 1.5 million people reached through recovery assistance during the year.

Assistance within three months:
Drought response - In Sindh and Baluchistan, the National Disaster Consortium reached 2.3 million people through a mix of support interventions including food security and livelihoods (FSL) while a further 117,067 people received Water, Sanitation and Hygiene services (WASH). Additionally, 339,620 people were assisted through nutrition-sensitive health advice. DFID support to the Pakistan Humanitarian Pooled Fund (PHPF) assisted 336,265 beneficiaries through a mix of needs-based interventions. Although the drought was a slow onset disaster, DFID support was provided as a relief intervention as the NDC reacted and implemented programmes within two weeks of the drought emergency being declared. In addition, 4,400 shelter/Non-Food Items (NFI) kits were provided to flood-affected families (27,280 beneficiaries) in 3 districts of Baluchistan namely Nushki, Killa Abdullah and Killah Saifullah.
[note] PHPF allocated £3.95 million through the its first standard allocation 2019 to support the country drought response plan and to augment government efforts to provide immediate, life-saving assistance and life-sustaining assistance to the population affected by drought in Sindh and Baluchistan. The sectors prioritised in 2019 are food security, health, nutrition, and water and sanitation.

Technical and VfM Improvements:
With multi-year financing and using a consortia approach, all partners have shown the ability to incorporate VfM improvements. While they have demonstrated a strong understanding of economy, this review also recorded partners improving their reporting on effectiveness and equity, mostly through qualitative data. This is now being tracked through individual VfM frameworks under the programme. Partners have started undertaking independent evaluations of their work which will inform the 2020 final review, particularly around cost effectiveness of interventions and the broader benefits of the work delivered under MYHP.
[note] For example, NDC has demonstrated significant reduction on office costs (£2,300 per month) by sharing office space with consortium partners in Sindh and Baluchistan and in case of FAO, sharing office space with Government line departments as part of the drought response.

Numbers reached through recovery assistance
The NDC reached 350,223 people under their Residual Recovery programmes following flooding in previous years in KP, Punjab and Sindh provinces. The PHPF reached 112,266 people with Post Conflict Assistance in the Newly Merged Districts through WASH, Shelter and Health interventions. RELIEF’s Integrated model of WASH, FSL and Protection helped reached 369,037 individuals in Peshawar, Kohat and Bannu districts of Khyber Pakhtunkhwa, ensuring inclusion of the elderly and PWDs. The UN Joint Programme remained active until February 2019 in the North Waziristan district and despite harsh winter conditions the UN programme exceeded targets reaching 511,885 people through recovery assistance. WFP’s cash-based recovery assistance reached 235,200 people affected by natural disasters in Chitral and conflict in the former FATA districts.

No.	Recommendations for the year ahead	Owner	Deadline	Tracking
1.	DFID to ensure all outstanding recommendations from the previous annual review are taken forward as part of this review (particularly recommendation 1 around better understanding of implications of host nation guidelines).	Deputy Programme Manager (DPM)	Ongoing/March 2020	Programme Delivery Plan (PDP)
2.	NDC and RELIEF partners to provide a comprehensive analysis of lessons learned during implementation of the programme with respect to programme governance, delivery of benefits and ensuring both the equity and effectiveness of interventions to beneficiaries	Deputy Programme Manager (DPM) / VfM Adviser	Ongoing/March 2020	PDP
3.	NDC and RELIEF to increase the number of evaluations to identify best practices and learning. Evaluations should also capture how adaptation and how learnings might benefit other programmes.	Deputy Programme Manager (DPM)	Ongoing/March / 2020	PDP
4.	With no major sudden onset disasters occurring since 2015 there is a need to revise NDC disaster response triggers to ensure they are in tune with the evolving context.	Deputy Programme Manager (DPM)	February / 2020	PDP
5.	Partners to conduct tracer studies/assessments particularly around trainings (vocational/ preparedness) to assess whether these were / are being used for their intended purposes and increasing employment opportunities	Deputy Programme Manager (DPM)	March 2020	PDP
6.	As part of the programme completion review due next year, all partners are encouraged to identify and report on improved quality of interventions over the course of the programme.	Deputy Programme Manager (DPM)	April 2020	PDP

Acronyms
AAP	Accountability to Affected Populations
AJK	Azad Jammu and Kashmir
ACTED	Agency for Technical Cooperation and Development
AKRSP	Agha Khan Rural Support Programme
BDRP / CBI	(DFID Pakistan’s) Building Disaster Resilience Programme / Cash Based Interventions
CHASE	Conflict, Humanitarian and Security Department
CFU	Counter Fraud Unit
CFW	Cash For Work
CLTS / CSC	Community Led Total Sanitation / Community Support Centres
DDMC	District Disaster Management Centre
DFID	Department for International Development
DDA	Due Diligence Assessment
DPM	Deputy Programme Manager
DRR	Disaster Risk Reduction
FAO	UN Food and Agriculture Organisation
FATA	Federally Administered Tribal Areas
FSL	Food Security and Livelihoods
GoP	Government of Pakistan
HANDS	Health and Nutrition Development Society
HNG	Host Nation Support Guidelines For Foreign Assistance to Pakistan During Disasters
ICF	International Climate Finance
IDP	Internally Displaced Person
(I)NGO	(International) Non-Governmental Organisation
IOM	International Organisation for Migration
IRC	International Rescue Committee
IVAP	IDP Vulnerability Assessment Profiling
KP	Khyber Pakhtunkhwa Province
KPMD	Khyber Pakhtunkhwa Merged Districts
LVC	Low Value Criteria
MYHP	Multi Year Humanitarian Programme
M&E	Monitoring and Evaluation
NFI	Non-Food Items
NDC	Natural Disaster Consortium
NOC	No-Objection Certificate
OIA	Office of Internal Audit
OCHA	(UN) Office for Coordination of Humanitarian Affairs
PC	Planning Commission
PDMA	Provincial Disaster Management Authority
PDP	Programme Delivery Plan
PELP	Pakistan Evidence and Learning Platform
PHPF	Pakistan Humanitarian Pooled Fund
PPA	Partnership Principles Assessment
PSEA	Protection from Sexual Exploitation and Abuse
PWD	Persons with Disabilities
RELIEF	Responding to the Evolving and Long-term IDP Emergencies in the Federally Administered Tribal Areas and Khyber Pakhtunkhwa
TPM / UN	Third Party Monitoring / United Nations
UC	Union Council
UNDP	United Nations Development Programme
UNICEF	United Nations International Children’s Emergency Fund
UNRCO	United Nations Resident Coordinator’s Officer
VfM	Value for Money
WASH	Water, Sanitation and Hygiene
WFP	UN World Food Programme

## B: DETAILED OUTPUT SCORING

Output Title	Timely delivery of appropriate relief in the immediate aftermath of disasters
Output number per LF		1	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes (reduced from 30%)
[note] Captured under Section C Theory of Change – changes to the logframe in the last year.

Indicator(s)	Milestone(s)	Progress	Score
Time taken for DFID partners to deliver assistance after acquiring NOCs	1 month	2 weeks	A+
Time taken for PHPF (UNOCHA) from submission of funds to initiation of high-quality projects	1 month	1 month	A

Output 1 relates to speed of the humanitarian response following large scale natural disasters (likely at provincial level). The key assumption driving this output was that (on average) natural disasters displace 3 million people annually with a smaller number displaced by conflict. This year the Government’s National Drought Plan estimated that 5 million people were affected by drought in 26 districts of Sindh and Baluchistan. The realignment of NDC Year 4 recovery interventions to implement the response was approved by DFID in March 2019. Consequently, NDC members applied for No Objection Certificates (NOCs) in relevant districts to initiate the response. UN agencies however, such as FAO and UNICEF, due to their long-standing relationship and coordination with Government departments, were able to initiate drought response interventions as soon as funding was confirmed. Partners were able to respond quickly (in some cases exceeding targets) and the NDC implemented drought response programmes in both provinces reached a total of 2,802,360 people.

For PHPF, the time from the call for proposal to the disbursement of funds varies between projects. Various steps are required. PHPF insists that potential partners already have NOCs to operate prior to project approval. Mobilisation then takes place after receipt of PHPF funding and after consultation with line departments and local communities. Most project activities start within 10 days after receipt of funds into the partner’s bank account.

No.	Key lessons learnt
1.	Slow onset disasters like drought have become more widespread and important than was foreseen during programme design and they may be well advanced before remedial actions are taken.
2.	While the use of cash-based responses is relevant to broader UK humanitarian policy objectives, this assumes that cash responses are always the most appropriate (and therefore value for money) response. This assumption does not always hold true.
3.	The NDC capacity to respond to natural disasters quickly (within 2 weeks) remains good. In some areas it is reinforced by District Disaster Management Centres (DDMCs) constructed under the programme since 2013. Stocks of relief response supplies are held in readiness for local use in the event of disasters.
4.	Many project interventions particularly infrastructure and crop packages are seasonally critical. Schedules are easily disrupted by adverse weather. All programme interventions should factor into their planning the crucial dates in cropping calendars and possible delays with delivery schedules.
5.	Where there is a rapid onset disaster and delays occur in responding, factor in whether these delays are in the control of the response or an external entity when reviewing performance.
[note] In the case of business grants provided by the UN joint programme an evaluation showed that 30% were not used to rebuild and re-stock but was spent largely on debt repayment and health.

No.	Recommendations	Owner	Deadline	Tracking
1.	Prior to extending support in any area and assisting communities, situation analysis and baseline studies should be conducted. This will refine the partners’ ability to identify gaps in the existing response and demonstrate how their interventions will add value and improve their ability to quantify change resulting from the project.	Deputy Programme Manager (DPM)	January 2020	PDP

Output Title	Integrated post disaster recovery supported that restores living conditions and reduces vulnerability to future shocks.
Output number per LF		2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	Yes (increased from 30%)

Indicator(s)	Milestone(s)	Progress	Score
Number of rebuilt houses/shelters more resilient to disasters provided to number of people.	Number of rebuilt houses: 1,500 / Number of people: 11,300	Number of rebuilt houses: 1,648 / Number of people: 12,233	A
Number of people with access to water and/or sanitation and/or hygiene services (WASH)	400,000	420,826	A
Number of people receiving livelihoods and food security support that assists their recovery	550,000	579,266	A

Output 2 focuses on recovery and increasing the resilience of beneficiaries by ‘building back better’ where possible. It focuses on the key sectors of WASH, shelter and livelihoods. The impact weighting has been increased from 30% last year to 40% this year. This is due largely to a shift in the programme focus from immediate assistance to an emphasis on recovery in the absence of any major sudden onset disasters. The UN consortium and PHPF continued with recovery interventions in the newly merged district of Khyber Pakhtunkhwa while NDC and PHPF shifted their focus to assisting recovery in the drought-affected areas. All targets moderately exceeded expectations. Given that provision of water and sanitation services often benefit the same households there is an element of double counting of beneficiaries. This is compounded further when figures of those receiving health and hygiene training are also included. To address some of these concerns, the currently review looks at a breakdown of WASH beneficiaries.

Shelter
With no major damage to houses during the year shelter recovery assistance was largely confined to residual recovery from floods in 2015 and reconstruction in the Newly Merged Districts. Beneficiaries received support grants, construction materials and training in shelter construction. Differences within the NDC on how beneficiaries were targeted have been resolved by only targeting vulnerable households within a village.

WASH
Partners have exceeded anticipated progress on WASH with all partners providing levels of support for rehabilitation or installation of new sources of water supply to provide potable drinking water. Associated with improved water supplies there has been support for improved sanitation backed with messages on safe hygiene practices and its impact on health through group instruction and raising awareness, e.g. through information on posters. The UN consortium extended health and hygiene education to primary schools; especially girls' primary schools. This figure in Output 2.2 covers WASH interventions delivered by the programme.

FSL
Food security and livelihoods was provided through a range of interventions. Many partners operate cash for work schemes to rehabilitate critical infrastructure such as irrigation schemes and access roads. In addition, cash support was provided to small businesses while crop packages, fodder seed and livestock vaccinations were made available to re-start cultivation and to maintain existing assets particularly in North Waziristan. While the cash option is preferred, UNDP under the Joint UN programme, was prevented from using cash for work interventions in parts of the former FATA region due to Government concerns over cash not being used for its intended purposes. Instead, 1,400 individuals were provided with in-kind grants in the form of business kits.

No.	Key lessons learnt
1.	Having multiple partners working on similar shelter interventions in adjacent villages or Union Councils (UCs) requires agreement on both the targeting methodology used and the degree of support to be provided to ensure compatibility.
2.	Beneficiaries receiving health and hygiene messages should be counted separately and not included with WASH of FSL targets. Many recipients of health and hygiene interventions which are largely delivered through focus group discussions and promotional material, receive additional material interventions under the programme.

No.	Recommendations	Owner	Deadline	Tracking
1.	DFID and partners need to review targets for Output 2 of the logframe to ensure that the target set for 2020, the final year of the programme is realistic.	Deputy Programme Manager (DPM)	March 2020	Logframe
2.	Data on beneficiaries only covered by lower cost and widely disseminated health and hygiene promotion activities should be recorded separately from those receiving for clean water and sanitation infrastructure.	Deputy Programme Manager (DPM)	From January 2020	PDP

Output Title	Improved access to humanitarian assistance and protection services for disaster-affected people
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress	Score
Number of people supported with preventive and responsive protection activities.	220,000	369,037	A+

Output 3 refers to the ability of people (principally displaced and host communities) affected by protracted conflict in KP and the KPMD to access humanitarian aid from the programme. This output relates to the RELIEF component which provides a mix of prevention and response services to conflict-affected populations in three districts of KP. It has established Community Support Centres (CSCs) that provide psychosocial support services, life skills education for children, youth and adults including PWDs and the elderly. It raises awareness on access to basic services using the referral pathways of service providers. While responsive measures help alleviate immediate effects of violence and abuse, preventive measures help to deter its reoccurrence. During the review period RELIEF reached 261,179 individuals with preventive protection activities including awareness raising and counselling, and 107,858 individuals with responsive protection activities including referral mechanisms. Mobile teams promoted awareness of hygiene demonstrations and life skills to more remote populations.

The Output scores an A+ as the Output exceeds expectations. This was made by possible by the RELIEF Consortium reprogramming its focus to districts where unmet needs remained high and access did not pose any challenges.

No.	Key lessons learnt
1.	Throughout the life of the RELIEF project, the operating environment has remained challenging. RELIEF over the year has worked on numerous scenarios/ contingency plans allowing the project to swiftly switch operational areas so that timeliness for implementation, meeting targets and the relevance of the project could be assured. This learning has also been incorporated in other projects being implemented by consortium partners.

No.	Recommendations	Owner	Deadline	Tracking
1.	RELIEF closes in December 2019. In addition to covering the achievements and relevance of the programme, the current independent evaluation of the project must clarify how the lessons and sustainability of the project approach will continue post project and inform future programmes.	Deputy Programme Manager (DPM)	End December 2019	PDP
2.	Given the large number of CSCs established and their importance to communities, RELIEF needs to have a clear exit strategy agreed by mid-November that identifies how these centres and staffing will continue to be supported to ensure the sustainability of investments.	Deputy Programme Manager (DPM)	December 2019	PDP

Output Title	Improved coordination and technical design of humanitarian projects
Output number per LF		4	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress	Score
Number of surveys / information consultations carried out by IVAP for humanitarian actors for data driven decision making	6	3	B
Percentage of partners systematically documenting inclusion of cash-based interventions in the analysis of potential response options.	100%	100%	A
Number of people affected by crisis who consider the complaints mechanisms accessible, effective, confidential and safe.	100,000	2,624,568	B
[note] All partners have complaints mechanisms, the figures quoted represent awareness of these mechanisms rather than a demonstration of their effectiveness. A change in the indicator is recommended and this output scores a B.

This output focusses on improving the quality of the response through better systems of feed-back and increased use of evidence to improve performance. Key to this is the encouragement of research and innovation; seeking to incentivise the use of cash-based transfers and adaptive programming, linked to improved accountability to affected populations (AAP).

Surveys
The IDP Vulnerability Assessment Profiling (IVAP) conducted a survey of returnees returning to host districts. Findings were shared with DFID, key humanitarian stakeholders of IVAP and also with RELIEF, who repositioned their third phase of implementation to address the findings. IVAP used its technical expertise to plan and support a joint assessment with UNOCHA in the Baka Khel camp which required immediate attention from the humanitarian community. IVAP also conducted a post-return pilot of 4,000 IDP families who had returned to their home areas to identify the constraints and challenges that they were facing. The next round of assessments will resume later in the year.
[note] In total, 4,470 families were surveyed till 31st Jan 2019, with the response rate of 58%. Gender ratio of the families for the whole data was 28% female and 72% male respondent. Of the families responded to the survey, 48% of the total are still residing in the areas of displacement, while 9% of the families reportedly mentioned that they have returned to their area of origin. Families who opted for secondary displacement or those who never returned at first place were further asked for the main reasons stopping them from return. The question was left open ended and the exact responses were recorded to capture all possible reasons. Accordingly, the most commonly reported reasons were; a) there is no proper shelter available for the families as their houses/ shelter are damaged and the displaced families do not have enough resources to rebuild their damaged shelters/homes. b) Livelihood stood second big reason for the family’s relocation, those who somehow managed to adjust themselves in the return area, could not found appropriate income generation opportunities in their area of return. c) lack of basic educational facilities in respective areas is another primary concern of the families who relocated to displacement so that their children can have access to basic education services.

IVAP was not able to meet the target set given access issues in the Newly Merged Districts.

Documentation
The need for cash is confirmed through multi-sector needs assessments. The NDC Drought Needs Assessments in Sindh and Baluchistan showed that cash assistance was the primary requirement of households to meet basic food and Non-Food Item (NFI) needs and to decrease dependence on debt.

All partners are now documenting how cash interventions are used in an analysis of potential response options. NDC documented options for floods and drought in 2019 and shared the analysis with DFID.

The Pakistan Evidence and Learning Platform (PELP) was designed as key to programme research and innovation. UNITAR was identified as the partner to operate PELP within the UN Resident Coordinator’s Office (UNRCO). However, the previously identified risk that UNITAR would not receive accreditation from the Pakistani authorities was realised and to mitigate further risks, DFID in September 2018 took the decision to close this project. In the absence of PELP, most partners now conduct their own surveys and follow-up assessments of interventions.

The Joint UN consortium assessed the effectiveness of their cash-based business grants and showed that 31% of recipients had used their cash grants for other purposes such as food and urgent medical needs which they prioritised over the re-establishment of their business. In addition, the NDC has commissioned specific studies on the potential for Climate Smart Agriculture in Sindh and the Punjab and research into the effectiveness of kitchen gardens and earthquake testing of shelter models.

Feed-back mechanisms
All partners have beneficiary feedback mechanisms embedded in their programmes. These are one element of ensuring Accountability to Affected Populations (AAP) and critical to informing programme/project adaptation. Mechanisms vary but include the use of individual and key informant interviews, focus group discussions, post distribution monitoring and feedback loops to take corrective action and inform those affected. RELIEF through their extensive beneficiary feedback mechanism, estimate that approximately 60% of the beneficiaries reached considered the complaints mechanism acceptable. This finding is based on the distribution of accountability cards, feed-back sessions provided and the display of accountability banners within the targeted communities followed by monitoring of the type of complaints received and the assessment of the rapidity of response.

However, all partners had problems addressing Output Indicator 4.3. Some reported on all beneficiaries being aware of the feedback mechanism while others recorded only those who used beneficiary feedback mechanisms. This led to confusion and resulted in a spurious and highly inflated number indicating satisfaction. The recommendation below suggests an alternative and clearer indicator.

While all partners have complaints mechanisms, the figures quoted represent awareness of these mechanisms rather than a demonstration of their effectiveness. A change in the indicator is recommended and this output continues to score B.

No.	Key lessons learnt
1.	Approximately 60% of the 114 complaints received through RELIEF’s Feedback and Complaint Response Mechanism between July to September 2019 were related to cash programming. Most of the beneficiaries had problems with receiving text messages due to poor mobile connectivity in remote areas. To overcome these challenges standard operating procedures for cash disbursement have been revised. The mobile supplier maintains a data base of beneficiaries that they have provided with cash. This information is shared with consortium partners. Where a beneficiary is unable to receive cash payment from the mobile company, RELIEF partners are able to use the common database to identify and pay cash directly to the beneficiary.

No.	Recommendations	Owner	Deadline	Tracking
1.	All partners to conduct assessments particularly around grants to assess whether the cash for these grants was used for its intended purpose.	Deputy Programme Manager (DPM)	February 2020	PDP
2.	IVAPs’ exit strategy needs to demonstrate how they will proactively work with the wider community to ensure longer term sustainability and improved effectiveness of the systems they have promoted.	Deputy Programme Manager (DPM)	Ongoing	PDP
3.	Indictor of beneficiary feedback is revised to read: “percentage of complaints received that are resolved successfully within 3 months”	Deputy Programme Manager (DPM)	Ongoing/ January 2020	Logframe

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The overall impact is "Reduced impact from humanitarian disasters in Pakistan".
The theory of change remains that people affected by disasters have access to timely, appropriate and good value humanitarian assistance to recover which leads to reduced vulnerability to future shocks (outcome). This can be achieved by the following outputs:

1. Timely delivery of appropriate relief in the aftermath of disasters;
2. Relief and recovery which is integrated, reducing vulnerability to future shocks;
3. More effective systems which help people gain access to services; and
4. Improved coordination and targeting of humanitarian projects.

The theory of change itself remains valid but key underlying assumptions have been tested this year:

Assumption 1: Natural disasters (floods) displace an average of 3 million people a year.
The programme was designed following recurrent large-scale disasters and assumed that these would continue in the coming years. This assumption on displacements has not held true. Many partners continued to operate residual recovery programmes following an earthquake in Chitral (KP Province) and flooding in Sindh during 2015. This reduced the need for large reactive responses but resulted in recovery focused interventions and an overlap with DFID’s ‘Building Disaster Resilience Programme’ (BDRP).

Assumption 2: The Government of Pakistan grants access for delivery partners.
The closing of civil society space continued during the year, although to date no MYHP partners have ceased operations. However, it continues to represent a risk to the programme - diverting the time and attention of partners as they seek to manage potential risks and, in some cases, partners have had to change their local implementing partners. Many partners continue to experience delays over obtaining NOCs to allow them to operate particularly in KP. The Pakistan Humanitarian Pooled Fund (PHPF) has addressed this issue by only approving the release of funds once the implementing partner has secured NOCs for the area in which it wishes to operate. Unavailability of NOCs resulted in RELIEF being unable to implement its programmes in D.I.Khan district and after some delays, it shifted its target areas to Bannu and Kohat districts.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The overall programme remains on track and in line with the outcome and impact foreseen (detailed above). Where the programme is not on track – progress on achieving results for emergency humanitarian response to disasters – this is context driven, does not require action at the level of implementing partners but rather a theory of change and logframe review that will also inform the design of the next phase of DFID’s programming in Pakistan from 2020 onwards.

Explain major changes to the logframe in the past year
Last year’s annual review (2018) highlighted a number of recommendations regarding the logframe. The logframe was reviewed and finalised in August 2019 to reflect these. The logframe also factors in the 12 month no-cost extension to the programme, building on proposed extensions and revised milestones from partners.

The major changes to the logframe are summarised below:
Revision to impact weightings:
Output 1: Timely delivery of appropriate relief in the immediate aftermath of disasters.
Impact weighting revised from 30% to 20%. This is due to absences of any large-scale disasters in the last three years but with more localised small to medium scale disasters being seen in the country.
Output 2: Integrated post disaster recovery supported that restores living conditions and reduces vulnerability to future shocks.
Impact weighting revised from 30% to 40%. This is due to a shift of focus of the programme to respond to increasing recovery needs resulting from widespread drought in Sindh and Baluchistan.

Revision to Outcome and Output indicators:
- Outcome Indicator 2 revised to ‘Number of programmes that demonstrate technical and VfM improvements over the life of the programme’, to help partners document and monitor VfM improvements that result in programme adaptation.
- Output Indicator 4.1 revised to ‘Number of surveys / information consultations carried out by IVAP for humanitarian actors for data driven decision making’. This indicator has replaced an earlier indicator around PELP which is no longer operational.
- Output Indicator 4.3 revised to ‘Number of people affected by crisis who consider the complaints mechanisms accessible, effective, confidential and safe.’

Describe any planned changes to the logframe as a result of this review
The major planned changes to the logframe for next year are:
1. Review impact weighting in the light of disasters that occur during the review period three months before the next Annual Review is due;
2. Output Indicator 4.3 to be revised to ‘Percentage of complaints successfully resolved within 3 months.’

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year
The business case highlights that substantial value for money gains can be made by shifting to multi-year humanitarian funding. Among other advantages, multi-year donor commitments give grant holders the financial latitude to invest in preparedness, and to manage early responses to shocks. This is particularly appropriate in a context of recurrent disasters such as Pakistan’s, where preparedness can lower the cost of post-event emergency responses. Increasingly, DFID Pakistan has been moving towards an ‘integrated’ approach to immediate relief and early recovery. Where there are opportunities to re-use materials from the early relief phase (such as shelter kits) this will be done, saving money and ensuring a more continuous relationship between delivery partners and communities. This can only be done if partners have the ability to start planning early recovery in the immediate phase after a disaster. Multi-year funding ensures DFID is able to build towards this approach, saving up to 15% on some interventions.
[note] Value for Money of Multi-year Approaches to Humanitarian Funding, Courtenay Cabot Venton, April 2013. See also Venton, Courtenay Cabot; Fitzgibbon, Catherine; Shitarek, Tenna; Coulter, Lorraine; Dooley, Olivia “The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia” DFID, June 2012.

Delivery through multi-partner/multi-year approaches has helped improve economic and efficiency gains including cost-effectiveness. Shelter, and WASH facilities have been improved by adopting either improved design and sustainability or cost-effectiveness. HANDS have agreed a joint methodology and approach to shelter design with ACTED as both are consortium partners under the NDC. Through learning locally and incorporating evidence gathered globally, UNICEF has reduced the unit cost of WASH related hygiene kits by 48%.

While partners have been delivering VfM analysis on specific activities at the level of ‘effectiveness’ (outcome level) and ‘equity’, as the programme enters its last year of implementation, partners have been encouraged to deliver VfM analysis for all interventions. Recognising the challenges of quantifying ‘effectiveness’ during the initial stages of the project, this review makes an attempt to focus on ‘effectiveness’ and ‘equity’ through a qualitative lens.

In line with the Business Case, key cost drivers for the programme (procurement of goods and services) remain consistent. These costs vary between regions where the programme has delivered assistance. The cost of procuring and providing emergency tents is relatively higher in the north (Chitral) compared to Southern Punjab and Northern Sindh. This is primarily due to Chitral being a new area of focus following the floods, which did not allow prepositioning while difficult terrain and remoteness increased transportation and procurement costs of goods and services

Collectively these cost drivers are at two broad levels: environment/external issues over which there is less control; and project intervention/internal issues over which there is greater control.

External cost drivers include insecurity and delays in access in the absence of NOCs from the authorities. Delays and uncertainty of access have increased costs. However, some of these risks have been mitigated by changing the geographical focus to areas where needs remain high and working with downstream partners who continue to have access.

Economy
Examples of project intervention/internal cost drivers include the geographical location of targeted beneficiaries (costs increasing in remote and/or insecure locations) and logistic costs related to interventions (such as warehousing and procurement). The latter, at a basic level, can and are being addressed by partners sharing facilities and infrastructure. For example, NDC continues to save at least £17 per day by storing emergency stocks in the HANDS and ACTED warehouses in Sindh. Moreover, NDC has seen an estimated cost saving of £2,300 per month in office costs by having IOM field teams sharing HANDS sub-offices in Quetta and Hyderabad.

Similarly, under the WFP standby arrangement, analysis suggests that as the Agha Khan Rural Support Programme (AKRSP) – a downstream partner of WFP, already had basic administrative infrastructure available in Chitral, WFP saved approximately 15% of its total budget through cost sharing with AKRSP. WFP also rehabilitated irrigation channels for 197 acres of land through cash for work. Cost benefit analysis of the activity shows that for every investment of 1 unit (GBP), a return of 2.7 units is achieved.
Under the RELIEF programme, lessons learnt from Phase I have contributed to the increased economy and efficiency of the project. RELIEF critically appraised how their initial community centres were established and the services they delivered resulting in a cost reduction from £12,500 per centre in Phase 1 to £2,100 in the current phase. The two CSCs in built in Phase I cost £25,057 and these were visited by 5,177 individuals. In Phase II the savings achieved resulted in a further 40 centres being provided at an approximate cost of £86,060 attended by 81,303 people. Initially the costs remained high as they involved establishing larger centres offering a wide range of activities and equipment. Realising that the centres were too large for their potential catchment areas, the consortium reduced the size, targeted activities more carefully to women and children, and brought down costs.

Information sharing linked with all RELIEF project interventions is done through a single Information & Assistance Desk in respective villages. This saves both time, human and financial resources. Information dissemination desks also increased access to information about basis services (protection, FSL, health, WASH etc.) The cost (£5,403) of forty desks that were established during the lifetime of RELIEF would have been multiplied by three (£16,209) if separate desks were setup. This represents savings of £10,806. While the project has seen cost savings here, effectiveness has increased as these information desks were not only used by all consortium partners but also used by other relevant stakeholders for information dissemination.

Efficiency
Examples of efficiencies made include:

NDC, by virtue of its active coordination with the Provincial Disaster Management Authorities (PDMAs) in Baluchistan and Sindh, managed to acquire NOCs for conducting drought needs assessments in these provinces. NDC was the only entity requested to conduct the assessments and the findings from these informed the national drought response by provincial governments and humanitarian agencies, beyond NDC.
Due to multi-year financing, the overlap of the Year 4 workplan extension approved until September 30, 2019, and Year 5 drought recovery activities approved in July 2019, enabled NDC partners to transition from response to recovery seamlessly.

As part of the flood response in Baluchistan, NDC mobilised Shelter/NFI kits that had been prepositioned in warehouses across the country. The availability of prepositioned kits saved NDC vital time in procurement of the kits.

For the Joint UN Programme, contingency planning for the fast-evolving security environment allowed the programme to mitigate potential delivery risks, e.g. when the Government restricted the distribution of cash-grants, the programme conducted a thorough analysis and through consultation with DFID, decided to switch from cash-grants to in-kind grants helping to keep the programme interventions relevant.

Effectiveness
Outreach protection services by the RELIEF consortium has reached up to 68,647 beneficiaries during the review period. The consortium originally did not design such services however, based on learning from its first phase of implementation, the consortium initiated outreach services in Phase II. This has helped contribute to increased effectiveness of the project as outreach protection services have enabled more people to benefit from project interventions.

In terms of effectiveness, WFP monitors the short and medium-term effect of the interventions on the lives of beneficiaries, and relevant outcome indicators have showed improvement against baseline values. The WFP M&E team conducted systematic assessments to document the results of WFP assistance using DFID funding. The assessment indicated a 45% increase in households having an acceptable level of food consumption and a corresponding 15% decrease in households adopting negative coping strategies in order to meet their food needs.

As part of NDC, HANDS has implemented shelter recovery interventions in District Thatta. The shelter recovery support included provision of Disaster Risk Reduction (DRR) construction training and shelter support grants to beneficiaries. In August 2019, some of HANDS intervention villages in Thatta faced flooding due to the heavy monsoon rains. In response, the HANDS field team conducted a follow-up visit to these villages to assess if damage had been incurred. The team verified that the shelters were intact, despite the floods, as they incorporated key DRR measures, including a raised platform, toe wall/back fill for reinforcement of walls, roof projections and appropriate framing of the structure. Only minor damage was noted in the structures such as to the outside rendering of some walls due to the impact of direct rain. Encouragingly the team noted that shelter owners had already started minor repairs of their walls and roof screeds in accordance with the training provided to them on shelter maintenance.

FAO has provided quantitative analysis of several of their livelihood interventions under NDC. These provide evidence of the financial returns from outcomes and FAO continue to assess the range of interventions they provide. The table below is an indicative assessment of the profitability of two major interventions, designed to increase farmer assets and increase food availability. The grain produced on one acre through the dissemination of improved wheat varieties provides an additional 15-20 weeks of a household wheat requirements

Incremental benefits of Wheat and Rice (PKR/acre)

Indicator	Wheat		Rice
	Traditional	Improved	Traditional	Flood Tolerant
Revenue	52,800	66,000	56,820	67,020
Expenditure	22,000	26,000	27,100	22,400
Gross margin	30,800	40,000	29,720	44,620
Increment/acre		9,200		14,900

For the Joint UN Programme, approximately 130,977 people including 66,798 women, now have access to sustainable and safe drinking water. All water supply schemes rehabilitated under the project are government schemes. This ensures that the government allocates budgets in their annual development plans for the operation and maintenance of these schemes. Similarly, for community-based schemes (e.g. handpumps), training was provided to the communities for their continued maintenance and repair.

Equity
Equity is a cross-cutting theme for MYHP. All interventions are designed to channel maximum benefits to vulnerable individuals and households. All data collection tools used by partners are designed to collect disaggregated data on gender, age, and disability of the potential beneficiaries.

NDC aims to assist the most vulnerable, disaster affected populations. Accordingly, NDC partners ensure that beneficiary selection is conducted using vulnerability criteria which prioritize economically, socially and ethnically marginalized community members. During the review period and in response to DFID’s previous annual review recommendations, NDC has harmonized the beneficiary selection approach between ACTED and HANDS, ensuring the consortium adheres to a single and strict vulnerability assessment for beneficiary selection.

The RELIEF consortium focuses on inclusion of persons with specific needs especially those with disabilities and older people. Separate centres for men and women have been established which serve as a common hub for all project services. In order to ensure that people with specific needs can participate, an outreach programme was introduced. This has enabled the consortium to increase its focus on equity, ensuring that people hardest to reach are included in project activities. To improve equity further, specialized support has been extended to critical cases of people with specific needs through targeted grants.

The Joint UN Programme in some project interventions, was positively biased towards the selection of women for assistance. These interventions included: poultry assistance, grants (cash and in-kind) assistance, technical and vocational training, and education. The programme has seized all opportunities of extending humanitarian assistance to women and children including 21,152 persons with disabilities this year.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The MYHP continues to deliver VfM in part because of its multi-year nature. Although it cannot and is not intended to address structural causes of vulnerability and poverty it provides much needed predictability to partners and allows for a potentially faster and more appropriate response.
[note] Draft findings of Thematic evaluation of Multi Year Humanitarian Financing in Pakistan (VALID Economics for DFID)

A consortia approach focusing on different areas of humanitarian need (natural disasters, people in displacement, and people returning post-conflict) allows the programme to provide a wide range of interventions through a multi-sectoral and coordinated response. This has resulted in more needs being met and offers better value than a single-sector response. Delivering through consortia has also helped build on individual organisations’ geographical presence, historical footprint and community acceptance in specific areas, as well as individual organisations’ sector and technical expertise. This has allowed the programme to increase its outreach and capacity and to benefit a greater number of beneficiaries. Project planning has also benefitted from joint assessments which has helped save on multiple assessments in common geographical areas. The approach has allowed downstream partners to preposition stocks through sharing warehouses.

Longer term support to partners also encourages relationship-building with authorities. Partners can position themselves in relation to the wider natural disaster response in a way that short term unpredictable funding does not allow. For example, the NDC is now a partner of choice for the Sindh and Baluchistan Provincial Disaster Management Authorities (PDMAs) – both of which have requested and provided access for drought assessments. The multi-year stand-by agreement with WFP (currently under review) continues to enable a rapid and flexible response to natural disasters, in part because of the sound relationship WFP has with the Government.

In an increasingly constrained operating environment such benefits of multi-year funding should not be overlooked if the UK is to remain at the forefront of humanitarian response. Given the range and frequency of natural disasters that Pakistan experiences, an ability to support a humanitarian response in-country in a timely and appropriate manner remains relevant. The MYHP is essential to the wider portfolio because it provides a UK capacity for an immediate humanitarian response that complements our development investments. Put simply, without pre-existing in-country capacity it is possible that despite intent to support the UK could not do so in a timely/appropriate manner.
[note] Saving lives, building resilience, reforming the system: the UK Government’s Humanitarian Reform Policy

No.	Recommendations	Owner	Deadline	Tracking
1.	With the growing focus on equity and greater use of qualitative data partners to ensure that their assessments and findings are made available throughout the final year in regular reports and not retained until project completion.	Deputy Programme Manager (DPM) / VfM Adviser	January 2020 onwards	Quarterly Reporting
2.	Programme team to ensure lessons learned on VfM from MYHP are documented as part of the project completion review due next year and these learnings are shared with programme teams in DFID as well as with the wider humanitarian community.	Deputy Programme Manager (DPM)	March 2020	Quarterly Reporting

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation
DFID works with partners to maintain and update risk management frameworks on a quarterly basis. These frameworks contribute to assessing the overall risk for the programme. Risks are escalated or reduced as necessary. The principal risks remain in force, but during the year partners have adopted mitigating measures. Overall, the programme risk rating is ‘Major with no change since the last annual review.

Context
The volatile security environment continues to limit access. Obtaining NOCs for travel and project implementation continued to be a major constraint to operational effectiveness. Humanitarian actors face a restrictive environment and the renewal process for INGOs has become cumbersome. Various measures were adopted to mitigate this risk; RELIEF closed operations in one targeted area and realigned their work to the parts of KP where they already had permission to operate.

Implications of OCHA closure
Pakistan remains a disaster-prone country and during the year there were several small-medium scale emergencies including: drought in Sindh and Baluchistan, flash flooding in parts of Baluchistan, and an earthquake in AJK. OCHA Pakistan we are informed, is transitioning into a Humanitarian Advisory Team raising concerns around a possible gap, particularly with regards to coordination, communication and response during a humanitarian emergency. It also has implications for the capacity and the capability of the Humanitarian Advisory Team to scale up in case of an emergency. DFID is considering extending arrangements with OCHA/PHPF till Sep 2020, while lobbying for an OCHA/PHPF sustained presence.

Delivery:
Collaboration with both BDRP and KPMD programmes has improved with joint field visits and data sharing. MYHP and the other two programmes have common implementing partners. More efforts are required to unpack lesson learned and to modify programmes accordingly.

Multi-layered monitoring mechanisms have emerged as a new risk. The MYHP multi-partner approach results in each partner monitoring its own project(s), the results of which are then fed to the consortium lead. While the independent TPM provides an additional layer of monitoring, understandably, partners need to continue monitoring from their perspectives, independent oversight and uniformity is required at consortium secretariat rather than at partner level. The MYHP programme team will engage with partners to revisit the monitoring arrangements to bring clarity on roles and responsibilities and explore what are the cost implications. This may also come as cross-cutting learning from the consortium approach.

Fiduciary:
Fraud and the diversion of resources remains a risk. Operating in some of the most vulnerable situations with limited access by DFID teams poses challenges. Consequently, the programme relies on TPM visits, reports and independent audits to mitigate risks. Delivery chain maps are updated on an annual basis allowing DFID to follow the flow of funds. DFID central Counter-Fraud team also helps the programme to monitor allegations. The Internal audits undertaken by partners are informative and provide additional levels of control.

The recent WFP ‘qualified’ County Office Internal Audit by their Office of Internal Audit (OIA) recommended a set of priority recommendations. With regards to fiduciary risk, the OIA recommended WFP reassess its Cash for Work terms of reference and Cash Based Transfers (CBT) assessments and establish improved mechanisms to verify beneficiary payments. The arrangement with WFP ended in Sep 2019. However, in the light of the recent audit observations, DFID is currently carrying out a comprehensive due diligence assessment of WFP. In addition, DFID is also scrutinising WFP’s cash transfers through DFID’s third-party monitors. These additional measures will inform DFID whether to extend its agreement with WFP.

Utilisation of contractors under the Joint UN Programme:
Despite vigilance by partners and oversight by third-party monitors there remain reputational and delivery risks along with opportunities for fraud associated with infrastructure interventions in remote areas. The UN joint programme in KP works through local Government and utilises their standard audits and bills of quantity for larger infrastructure schemes primarily rehabilitation of water supply and irrigation schemes. The physical work is implemented by contractors selected by the Government using standard contracting procedures. UNICEF pay the contractors directly while UNDP makes payment through the local government line department. UNDP have put in place a series of controls and there has been no evidence of the misuse of funds in contractual arrangements,:

- Prior to the initiation of civil works, UNDP Engineering teams visit schemes (on a sample basis) to validate and verify the Planning Commissions (PCs-1) reports prepared and shared by the line departments. These visits enable UNDP to confirm the actual scale of the rehabilitation work required for the schemes;
- Payments are made to the line departments in three tranches of 50% and 30% with a final tranche of 20%. Tranches are released in advance against settlements submitted by the line departments. Settlements are approved and tranches released only after UNDP’s Third-Party Monitors have validated and verified the work on-site;
- The final payment is based on the work done and following a Low-Value-Criteria (LVC) agreed between the UNDP and line departments. If there is a difference between work-done as verified by the TPM, and the amount claimed by the line departments, then UNDP pays the smaller amount;
- If the certified amount is less than that disbursed to the line departments through tranche payments, then the department returns the uncertified amount to UNDP.

Helping communities in building back better, the programme also focuses on rehabilitation of shelter, latrines and pathways. Shelter guidelines developed by IOM and DFID are strictly adhered to by all partners. Beneficiaries are identified based on their vulnerability and through cash for work support, are employed to help rebuild their communities. Cash for work grants are divided into multiple tranches and payments are subject to completion of agreed activities. For instance, cash grant for construction of recovery shelters may be divided into three tranches. Each tranche is released to beneficiaries upon completing specific stages of shelter construction; completion of the foundations, then the walls and finally the roof to complete the shelter. Similarly, conditional cash may be distributed through implementation of cash for work schemes such as rehabilitation of hand pumps, irrigation channels, and other communal infrastructure by the project beneficiaries. Adopting a payment by results approach helps ensure continuity to work as well as holding partners accountable for cash disbursements

Safeguarding:
The programme disaggregates beneficiaries by sex, age and people with disabilities. Their needs are specifically addressed through outreach programmes. The risk that women, minorities and other marginalised groups could be excluded from programme activities has been mitigated through the design of interventions that focus on vulnerability and inclusiveness. Vulnerable and at-risk groups exposed to sexual/exploitation/abuse have been protected, through revised enhanced due diligence assessments of partners with a particular focus on safeguarding standards. Due diligence and safeguarding recommendations are monitored on quarterly basis to remain compliant with prevention of sexual exploitation and abuse (PSEA). The programme team also held specific safeguarding sessions with partners to assess how well their approach to safeguarding is understood and put into practice. TPM also cover this aspect in their regular reporting. Partners provide disaggregated data beneficiaries by sex, age and people with disabilities and their needs are specifically addressed through outreach programmes.

Outstanding actions from risk assessment:
There are no outstanding actions from the previous risk assessment. The due diligence assessments of lead partners of the NDC, RELIEF and OCHA/PHPF have been completed following DFID’s new enhanced due diligence guidance on safeguarding standards. WFP’s DDA refresh is currently underway and will be concluded in November 2019. The original DDA was finalised in 2015. Partners report on DDA recommendations on a quarterly basis and this exercise has allowed partners to reassess / revise their policies and SOPs in line with DFID’s expectations.

Update on partnership principles
The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at Federal level. The PPA was last discussed in March 2019 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

MYHP is a humanitarian programme which provides emergency assistance based on humanitarian needs of people in crises in Pakistan. It is being implemented through a number of UN and other humanitarian non-government agencies. It does not contain any elements of budget support or financial aid. The programme is part of the wider aid relationship between the UK and Pakistan, which is based on an assessment of the Pakistan Government’s commitment to our partnership principles. Although the Partnership Principles do not need to play a role in management and monitoring the programme, the future sustainability of NGO operations depends on government buy-in, collaboration, policy and financial support, and to demonstrate greater commitment to the principles, the government will need to work more with non-state actors.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
The programme has spent 82.4% of its overall £100 million budget and all partners anticipate utilising their allocated budgets by the end of the programme. Contingency or reserve funds under the programme remain unallocated and are likely to remain unutilised unless there is an emergency where DFID decides to mobilise a response.

In June 2019, a no cost extension to the MYHP was approved, extending the programme to September 2020. It responds to an evolving context where:
1. other funding streams are now concentrating in KPMD supporting early recovery;
2. conflict related displacement has significantly reduced; and
3. there has been less than anticipated need for emergency responses.

During the year agreements under MYHP were amended:
- IVAP – A costed extension of amount £450,000 was given to the project until September 2020
- NDC – A costed extension of £5.7 million was given to the project until September 2020
- RELIEF – Project extended until December 2019

Over the last year a number of challenges resulted in the slow utilisation of allocated funds;
- Delays were encountered with NDC over finalising the proposals for the re-appropriated budget for drought response and the project extension.
- Access remained a challenge for the RELIEF consortium, resulting in a repositioning of its work to areas where access had already been granted and where needs remained high. To address challenges and delays in implementation, RELIEF was awarded a 4 month no-cost extension allowing the project additional time to implement all activities.
- Reporting from some partners (particularly the PHPF and WFP), remains limited in terms of information and budget breakdown. Reporting by both OCHA and WFP is subject to their global reporting requirements and is currently not subject to in-country requests. However, there is scope for local flexibility which is being explored further by DFID.

In the absence of emergencies during the past year the MYHP has not needed to fully utilise its contingency (reserve funds) under Pillar 3.

The NDC, RELIEF, IVAP and the Joint UN Consortia programmes submit regular quarterly reports against templates which allow DFID to monitor closely their programme deliverables. Reporting by WFP and the PHPF remains limited under their global agreements. Relationships with partners remain good; all remain open to discussion and accept feedback on programme activities, adjusting or adapting where necessary. Partners then capture improvements within their reporting as these specific interventions and the wider programme evolves.

Financial audited statements of partner’s country programmes are received annually. An internal audit of WFP in June assessed that governance arrangements, risk management and controls were functioning but needed improvements. Prompt management action was required on cash-based transfers, cooperating partnership management, and on targeting and registration including beneficiary feedback systems. All recommended actions are being implemented by WFP Country Office and are expected to be certified as completed by the UN Office of Audit & Investigations by December 2019. The WFP component of MYHP is now complete and no further disbursements are foreseen until due diligence is complete.

Asset Monitoring:
All partners follow DFID’s asset management policy. Assets purchased using DFID funds are registered and reported on quarterly. As the programme team is unable to travel to project sites in remote areas, asset spot checks were undertaken through TPM. In addition to TPM field checks, one asset spot check visit of NDC was conducted in IOM’s head office in Islamabad by DFID. There were no reports of discrepancies. In some cases, proper tagging of items had not taken place and corrective measures were taken to resolve this issue. Follow up visits confirmed action had been taken.

As part of the final year of implementation, all partners will be prepared for asset disposal exercises in 2020 as the programme enters into closure.

No.	Recommendations	Owner	Deadline	Tracking
1.	NDC to improve financial planning and provide monthly high and low case financial projections enabling the DFID programme team to plan and monitor expenditure ensuring potential underspend is identified and flagged to finance teams in time.	Deputy Programme Manager (DPM)	Ongoing / December 2019	PDP
2.	DFID to revise WFP’s due diligence assessment (DDA) in light of the internal audit observations. Future partnerships with WFP to be determined on the basis of the DDA recommendations. Any future funding will be contingent on WFP fully complying with DFID requirements and meeting its DDA recommendations.	Deputy Programme Manager (DPM)	December 2019	PDP
3	WFP to provide a more detailed breakdown of its budget heads under the Standby agreement to better understand and mitigate cost drivers improving VfM.	Deputy Programme Manager (DPM)	December 2019	PDP
4	As MYHP moves to closure next year, all partners are to prepare their asset disposal plans in line with DFID’s requirements. DFID to prepare TORs and an approach paper for commissioning during the asset disposal exercise.	Deputy Programme Manager (DPM)	March 2020	PDP

Date of last narrative financial report(s)	30-Oct-2019 [NDC]; 14-Sept-2019 [RELIEF]; 30 Sept-2019 [IVAP]; 15-Sept 2019 [Joint UN Programme]; 01-APR-2019 [WFP Standby]; 18-July-2019 [PHPF]
Date of last audited annual statement (s)	May-2019 [UNDP]; 30-Sept-2018 [IRC]; 31-Dec-2018 [IOM]; June-2018[WFP]; 31-Dec-2017[UN OCHA]

G: MONITORING, EVIDENCE & LEARNING

Monitoring
The programme delivery plan is the primary performance monitoring tool. In addition to quarterly progress review meetings and reviewing formal quarterly reports on progress, finances and assets, DFID also carries out a more detailed technical progress review every six months. In addition, each consortium maintains strong governance structures. These include having secretariats and a consortium lead ensuring accountability, coordination, work planning, lesson learning and reporting to DFID. Partners hold regular project steering committee meetings and minutes of these are shared with DFID. This provides an opportunity to assess progress and consider best practices as well as a basis to hold more in-depth discussions on risks, finances, contingency planning and workplans as projects continue to evolve with the changing context.

This year Glow Consultants were appointed third-party monitors for MYHP replacing VTT Global who had been contracted through PELP. The Glow Consultants contract runs for two years (Nov 2018 – Oct 2020) and they have already successfully completed six monitoring visits of MYHP partners. Findings from each monitoring round were shared with partners and discussed with DFID before being finalized. Glow also shared recommendations related to overall activity design and implementation process under NDC and these were reviewed by Glow, DFID and NDC partners in joint sessions after each visit. Wherever necessary and feasible, the recommendations were taken up by NDC partners.
[note] Examples of such recommendations include the harmonization of ACTED and HANDS recovery shelter approach under the NDC. The recommendation, reiterated by DFID, was taken up by NDC

This Annual Review was led by DFID’s Conflict Humanitarian and Security Department (CHASE) livelihoods adviser and the MYHP programme manager, supported by the programme team. All partners were briefed in advance and each provided a summary sheet of activities against outcomes and outputs paying attention to VfM and risks, as these impacted on their own programmes. Meetings were held over a week with all implementing partners but unfortunately a planned field visit to southern Sindh to ground truth some of the findings could not materialise.

Evidence
The MYHP contributes to building evidence at three different levels: global, Pakistan national and technical.

At a global level, the MYHP has been one of the case studies in the evaluation of multi-year humanitarian and resilience funding undertaken by the centrally managed team. This evaluation generates important evidence for the UK’s wider humanitarian programming. It also shapes and influences DFID Pakistan’s thinking on vulnerability and resilience. It is unlikely that a separate or further evaluation of the MYHP will generate sufficient significant additional evidence to justify the investment. Instead resources should be used to focus on ensuring partners assess project level outcomes.
[note] A multi-year thematic evaluation of DFID’s Multi-year humanitarian funding approach in Pakistan -VALID

At sub-national level, the Government of Sindh identified eight districts as “calamity affected” in September 2018. No Government appeal for international assistance was made at that time. However, the Provincial Disaster Management Authority (PDMA) Sindh formally requested and granted a NOC to the NDC to conduct a drought needs assessment in coordination with WFP, WHO, UNFPA and OCHA. The Government endorsed the findings in January 2019 and partners began response activities. Similarly, in Baluchistan, the PDMA Baluchistan requested NDC to conduct a drought assessment in December 2018 covering 14 districts. The findings of the report were delayed and were only endorsed by the Government in April 2019 when NDC began operations.

At the technical level evidence has been generated by MYHP through project implementation. Examples include published research on flood resilient housing. This looked at specific typologies of construction that would withstand flooding focussing on low-cost improvements to traditional/existing buildings. The research results have informed the NDC and their approach to ensuring best possible VfM in recovery housing design. Future technical level evidence will be generated in other areas such as the Community Led Total Sanitation (CLTS) efforts undertaken within the NDC with the aim to understand better the outcomes and impact on morbidity and mortality of reduced prevalence of diarrhoea.

Learning
Joint Programming
Project activities within consortium should be rationally planned with joint workplans developed. The UN Joint programme and RELIEF have established mechanisms for more proactive planning and coordination. Monthly coordination meetings were established, during which individual agencies shared their experiences, challenges and mitigation measures, resulting in more efficient reporting and improved cost effectiveness. Coordination mechanism among participating UN agencies has considerably strengthened and the lessons learned transferred to other non-MYHP programmes.

Standardized reporting calendar and requirements:
Variance between the annual/quarterly reporting timelines of different partners and DFID poses challenges in consistent reporting of programme updates and achievements. Moreover, reporting requirements, such as Logframe indicators, VfM matrix, DFID Results Tracker are often revised several times during the year. Ideally the reporting requirements should be standardized at the start of the programme to ensure uniform reporting over the project’s life time.

Revision of CASH disbursement methodologies
Approximately 60% of a total of 114 complaints received through RELIEF’s Feedback and Complaint Response Mechanism between July and September 2019, were related to cash programming. Other partners have also encountered difficulties using bio identification methods for payments. Most complaints are due to the non-recognition of thumb print data and especially problems receiving text messages based on which they receive cash. In certain cases partners have reverted to cash disbursement. Partners recognise they must be prepared to modify their SOPs in the light of cash payment problems and have fall-back mechanisms in place.

Coordination with Government counterparts
Efficient and effective coordination with Government entities has supported the smooth implementation of NDC and the Joint UN consortium activities. These relationships resulted in the NDC being requested by the Local Government to conduct the Drought Needs Assessments in Sindh and Baluchistan provinces. Other partners established a district level Technical Working Group which was effective in coordinating monthly meetings with line departments. These initiatives heighten ownership by Government Departments and the partnerships developed are beneficial in terms of accessing and acquiring NOCs.

Capacity building of local organizations:
Capacity building and communication with local organizations through preparedness trainings enables partners to collect timely information related to disasters occurring across Pakistan. Preparedness trainings by NDC has reached 353 organizations in 99 districts, serving as first point of contact in the field. By tapping into implementing partners’ operational strengths the programme benefits from the strengths and local capacities of partners to deliver maximum VfM.

Joint Interventions
Joint interventions with other MYHP partners working in in adjacent districts reduces costs and avoids overlapping programmes for example, female beneficiaries under the FAO kitchen gardening programme were supported through WFP cash programming and involvement in compost making for their kitchen gardens to promote organic farming.

Progress on recommendations from previous reviews
Key Recommendation 1 - Better understand implications of the recently finalised ‘Host Nation Support Guidelines for Foreign Assistance to Pakistan during Disasters.
The HNG provide guidelines for foreign assistance to Pakistan during a disaster. These guidelines were approved and made public by the military and the Government of Pakistan. While all partners continue to be aware of the implications of the HNG on their programmes they have yet to share their analysis of how the HNG is affecting their response. The Government of Pakistan is currently looking into revising its guidelines again. This recommendation has only been addressed in part.

Key Recommendation 2 - Improve DFID Pakistan understanding of the reasons why displaced people remain or return to areas of displacement to inform wider policy and programming.
IVAP met with DFID programme teams working in the newly merged districts of KP (KPMD and MYHP programmes) in March 2019, to present an overview of their assessment and mapping tool. IVAP continue to have annual snapshots using tracer studies of families. The reasons why people return to host areas are varied but revolve around lack of services in home districts and security concerns. In September 2019 discussions were held with IVAP to identify means in which IVAP could potentially be used and improved under the KPMD programme.

Key Recommendation 3 - Review Theory of change, logframe and assumptions
This has been completed and captured in Section C: Theory of Change and progress towards outcomes.

Key Recommendation 4 - Partners to specifically focus VfM analysis on effectiveness at the outcome level and assess outcome level results / effectiveness of contracting technical assistance if required.
While partners have demonstrated improved level of analysis compared to last year, (Section D: Value for Money) partners are encouraged to focus on effectiveness at the outcome level. Evaluations planned for December this year would help inform our next review. The recommendation remains valid and work will continue as part of this review’s key recommendation.