## LogFrame amended Apr. 2015
PROJECT NAME | Support to the National Plan to Eliminate Cholera in Haiti
National and Grande-Anse Department Level
IMPACT | Impact Indicator 1 |  | Baseline 2013 | Milestone 30/09/2014 | Milestones 30/03/2015 | Milestones 30/09/2015 | Target Dec 2015 |  | Should have a baseline as of 01 Apr 2014 and semi-annual milestones 30/9/14, 31/3/15, 30/9/15 and Target
Cases of cholera-related mortality and cholera transmission rates decline on a trajectory to eliminate cholera within ten years | Cholera incidence rate reduction | Cholera cases | 58574 | 10317 | 11721 | 25329 | 25000
|  | Cholera incidence | 0.55% | 0.096% | 0.107% | 0,25% | 0.25%
Source : MSPP and National Cholera Elimination Plan reduction of incidence from 3% to 0.5% (2014) and 0.15% (2017)
| Impact Indicator 2 | [5 empty] | Target Dec 2015 |  | both impact indocators should have separate rows to reflect impact at national and GA Department level
| Fatality rate reduction | CFR | 1.05% | 1.12% | 0.9% | 1.2% | <1% |  | UNICEF: GA impact indicator inserted as measurement of Outcome 2
Source: MSPP
OUTCOME 1 | Outcome Indicator 1.1 | [5 empty] | Target Dec 2015 | Assumptions
The national cholera epidemiological surveillance system provides timely and accurate cholera data | % communes reporting to DELR in a timely and accurate manner (<7 days) | Planned | NA | NA | 75% | 75% | 80% | The timely and accurate provision of cholera surveillance data will facilitate improved epidemiological analysis | DELR started top measure promtpness after UNICEF-APHM advocacy early 2015
Source: MSPP
| Outcome Indicator 1.2 | [5 empty] | Target Dec 2015
| Number of APHM epidemiological quarterly reports disseminated | Planned | 6 | 1 | 3 | 3 | 6
Source: UNICEF
| Outcome Indicator 1.3 | [5 empty] | Target Dec 2015
INPUTS (£) | DFID (£) | [5 empty] | DFID SHARE (%)
452215
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 | [5 empty] | Target Dec 2015 | Assumptions | Each output should have an Impact Weighing % of no less than 10% and add to 100%
Impact weight: 20%
Effective coordination at the National, Departmental and Communal levels that informs cholera response activities and resource allocation | % planned meetings held at the national level | Planned | NA | 90% | 100% | 100% | 100% | Regular meetings between the partners will facilitate strong coordination
|  | Source: UNICEF | [5 empty] | Risk Rating: Medium
|  | Planned | 50% | 60% | 75% | 90% | 100% | Regular meetings between the partners will facilitate strong coordination
| % planned meetings held departmental level | Source: UNICEF
| Output Indicator 1.2 | [5 empty] | Target Dec 2015 | Assumptions
| Number of departments with well-defined effective coordination mechanisms. | Planned | NA | 8 | 8 | 9 | 10 | Defining coordination mechanisms will lead to concerted action
|  | Source MSPP | [5 empty] | Risk Rating: Medium
| Output Indicator 1.3 | [5 empty] | Target Dec 2015 | Assumptions
| Terms of Reference/MoU available at the departmental health directorate, MSPP, DINEPA and NGOs actively involved in the fight against cholera | Planned | NA | 0% | 20% | 40% | 75% | ToRs will facilitate action
|  | Source MSPP | [5 empty] | Risk Rating: Medium
OUTPUT 2 | Output Indicator 2.1 | [5 empty] | Target Dec 2015 | Assumptions
Impact weight: 10%
The Directorate of Epidemiology Laboratory and Research (DELR) provides timely and accurate laboratory support and epidemiological analysis sharing it with the partners. | % suspected cholera cases tested on RDT | Planned | 13% | 70% | 70% | 70% | 100% | If adequately resourced DELR will provide timely and accurate epidemiological analysis
Source MSPP
| Output Indicator 2.2 | [5 empty] | Target Dec 2015
| % of monthly suspected cholera cases confirmed by culture test in a laboratory | Planned | NA | NA | 10% | 5% | 50%
Source MSPP DELR
OUTCOME 2 | Outcome Indicator 2.1 | [5 empty] | Target Dec 2015 | Assumptions
Reduce the transmission of cholera in Haiti | Grande Anse: Cholera annual departmental incidence rate (number of new suspected cases) | Planned | 4332 | 823 | 105 | 798 | 500 | Maintaining the cholera response will continue to decrease cholera transmission
|  | Source MSPP | [5 empty] | Risk Rating: Low
INPUTS (£) | DFID (£) | [5 empty] | DFID SHARE (%)
1500000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 | [5 empty] | Target Dec 2015 | Assumptions
Impact wieght: 30%
Cholera mobile rapid response teams are adequately supported to respond to every cholera alert within 48 hours with appropriate epidemiological investigation and response. | % cholera alerts responded in less than 48 hours | Planned | 80% | 99% | 90% | 81% | 80%
|  | Source: UNICEF reporting | [5 empty] | Risk Rating: Low
OUTPUT 4 | Output Indicator 4.1 | [5 empty] | Target Dec 2015 | Assumptions
Impact weight: 20%
Improved access to safe drinking water in Grande Anse. | Number of persons provided with safe water for drinking, cooking and personal hygiene use (% of samples with no sign of fecal contamination) | Planned | NA | 0 | 2250 | 22000 | 100000 | No major emergency occur in Grande Anse department
Source: UNICEF monitoring
| Output Indicator 4.2 | [5 empty] | Target Dec 2015
| Number of water points protected from external contamination supplying safe water at the end of the implementation period | Planned | NA | 0 | 3 | 11 | 20
|  | Source: UNICEF monitoring | [5 empty] | Risk Rating: Medium
OUTPUT 5 | Output Indicator 9.1 | [5 empty] | Target Dec 2015 | Assumptions
Impact weight: 20%
Improved hygiene and sanitation behaviour. | % population with improved hygiene behavior (KAP study) | Planned | NA | 0 | To be measured in May | 75% | 80% | Community outreach will lead to improved hygiene and sanitation behaviours
|  | Source: KAP survey from ACTED | [5 empty] | Risk Rating: Medium