Annual Review - Summary Sheet

Title: Increasing sustainable access to water sanitation and hygiene in the Democratic Republic of Congo.
Programme Value: £164.8 million		Review Date: July 2016
Programme Code: 203445	Start Date: July 2013	End Date: December 2019

Summary of Programme Performance
Year	13/14	14/15	15/16
Programme Score	A	B	A
Risk Rating	H	H	Maj

Summary of progress and lessons learnt since last review
Despite continued slow progress in the first half of the year under review, the programme has caught up and achieved most of its targeted milestones. In some cases the milestones have been exceeded, demonstrating that the programme is on track to achieve its final targets, despite an extremely challenging environment. With the good progress that has been made to date, outputs meet expectations and the programme this year scores an A.

The operating context still remains complex, as was anticipated in the Business Case, but implementing partners have gained experience and learnt lessons over the last three years. Particular challenges experienced during the period under review result from the changing political and administrative environment. The Government of DRC’s “Decoupage” process broke-up the country’s 11 administrative provinces into 26 and in addition, the long-awaited water law has been promulgated – changing the legal context for the provision of water services.

Results in water and hygiene have continued to be on target and good progress has been made towards achieving sustainable results. While delivery failed to meet the milestone for access to sanitation, most programme milestones have been achieved. Three outputs scored A, one scored A+ and one scored B. Out of the 20 output indicators: 15 are on track and 6 have not achieved their milestones. In some cases reporting wasn’t as comprehensive as it should be, due to lack of data in making the required analysis, or due to the changes made to the indicators as part of the logframe review which have yet to be reflected in monitoring systems.

The Healthy Villages and Schools and the WASH Consortium components of the programme have contributed to exceeding the programme’s annual targets for improving hygiene practices, reaching 1,337,208 people against the target of 900,000 people, and improving access to water for 1,136,024 people against a target of 800,000 people.

Key highlights for the year include the following:
In total 8 field visits were made over the reporting period. Four of which were focussed on the rural components of the programme, where DFID sought to monitor progress and foster better collaboration between partners by performing joint missions with more than one delivery partner: Bandundu, Kasai Central (twice) and Equateur. Two of these, Kasai Central and Equateur, were aimed at supporting Water and Sanitation sector learning and included the attendance of senior Government of DRC representatives. The missions to Kasai Central and Equateur (which visited two post decoupage provinces Mongala and Nord Ubangi), also increased coherence between DFID programmes by the inclusion of the health programme (ASSP, project number: 202732) which has a Water and Sanitation component. The Independent Commission for Aid Impact (ICAI) reviewed the WASH programme in April 2016 as part of their report on Fiduciary risk in fragile states, which included a further visit to Kasai Central Province. The other four field visits this year were focussed on monitoring the urban WASH component in the east of DRC (with DFID’s technical advisers, Mott MacDonald) and monitoring UNICEF’s audit of Health Zone management in Kinshasa. In addition to this, DFID DRC hosted three successful technical learning events in Kinshasa, where Mercy Corps shared their important gender approach, another with sector partners presenting some of the lessons learnt and best practice, and another discussing the pros and cons of different WASH approaches – and how these could inform policy and programming in the next few years.

Rural WASH, UNICEF Healthy Villages and Schools:
After a slow start, the UNICEF delivered Healthy Villages and Schools component (Villages et Ecoles Assainis, VEA) has caught up its early delays in certifying villages and schools. All changes made to Phase 2 of the programme (2013-2019) are now fully operational. The piloting of the certification of health centres, as part of the community-wide approach, as well as third party monitoring are also underway.

Rural WASH, WASH Consortium:
The Consortium’s mid-term evaluation recommendations were shared in August 2015 and have been taken into consideration and implemented by the partners. The Consortium narrowly missed its targets, due principally to the under-performance of one of its members, the effect of which other consortium members sought to mitigate by increasing their share of delivery. The Consortium held two successful national learning events in Kinshasa for the sector. It combined province level “training of trainers” for key staff and partners together with a planning process for field-level training needs.

Urban WASH, Mercy Corps:
The baseline study for the project revealed positive impacts on gender-based violence in areas where the project manages tapstands. All project areas have moved from inception to implementation, although the project is accumulating delays. The design and supervision consultancy firm for the infrastructure component was selected after an open tender and started work in January 2016. Mott MacDonald, DFID’s contracted technical advisors, completed quarterly missions with special focus on sanitation, infrastructure procurement, behaviour change and gender. Findings of all missions were compiled in reports.

Urban WASH, Oxfam Sanitation Marketing pilot:
The pilot has reached the end of its planned duration. After some delays in the first year, a demonstration site was set-up, 20 local entrepreneurs were trained, and 88 improved sanitation products have already been sold to early adopters. In view of uncertainty over the up-take in the market place, we are currently reviewing whether the approach has potential to work at scale. There have been some important secondary benefits in terms of the governance of basic services and the marketplace: A local steering committee led by a woman and composed of private sector (local entrepreneurs), government institutions, religious representatives, women’s groups and civil society formed spontaneously. It supports the marketing and improving the enabling environment for the take-off of this market based approach.

Summary of recommendations for the next year
Please refer to Annex A for a full list of recommendations made in this review.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4109740.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5038153.xlsx

The general context analysis in the business case and since the previous annual review remains valid, including the contribution of the programme to the reduction of poverty in the DRC. There has been some shift in the economic, political and social context, as well as in the sector but this does not affect the way in which UK support should be delivered.

This programme’s results from 2013 to 2015 have contributed to the UK’s achievement of improving access to water for 62.9 million people by 2015. From April 2015 onwards, results will contribute to the UKs renewed commitment to reaching the international Sustainable Development Goals, with an additional 60 million people gaining access to water.

In the Democratic Republic of Congo, the political context continues to be fragmented, with limited public accountability. Years of high growth have created few jobs, and additional government spending has not led to higher spend on social and basic services. Despite moderate improvements in the business environment, the constraints to private sector investment are huge, ranging from poor infrastructure, to corruption and high taxation. The cost of making decentralisation effective is also a factor that further constrains the government’s budget.

The DRC now ranks 176 of 188 countries on the Human Development Index. Slow, but steady progress has been made with respect to the provision of basic services, although it has only met one of the MDGs (reduction in HIV prevalence). It has the eighth highest under-five mortality rate in the world and the sixth highest maternal mortality ratio. Some 3.5 million girls and boys remain out of school. Gender equality has not progressed significantly: the DRC ranks 149 of 155 countries on the Gender Inequality Index.

There has been some progress on access to water and sanitation across the country. Currently 52% of the population has access to improved water facilities (81% urban and 31% rural), while only 29% of the population has access to improved sanitation facilities (29% urban and 29% rural) according to the JMP (2015). The DRC has an important challenge to achieve the Sustainable Development Goals (SDG) 6.1 (by 2030, achieve universal and equitable access to safe and affordable drinking water for all) and 6.2 (by 2030, achieve access to adequate and equitable sanitation and hygiene for all and end open defecation, paying special attention to the needs of women and girls and those in vulnerable situations).

Despite impressive progress in the child mortality rate between 2010 and 2014, diarrhoea is attributed as the cause of death for 14% of children under 5 years (WHO). Chronic malnutrition (stunting) remains obstinately stuck at 43% of all under 5 children, as it has for over a decade. Acute malnutrition rates are among the world’s worst.

In July 2015, DRC’s planned decentralisation came into effect, with 11 provinces becoming 26. The implications for the WASH programme were:
- Government officials re-shuffled and appointed to new provinces
- New provinces operating with little resources
- Some setbacks from ‘losing’ trained staff and needing to train newly appointed staff.

The programme continues to work on delivering equitable, inclusive and quality services as well as establishing the state’s ability to resource and govern service delivery in the longer term. To achieve this in practice this programme, along with other human development programmes in the DRC, strikes a flexible and pragmatic balance between delivering value for money in achieving increased access and use of services on one hand, and on the other hand building capacity of the state system for longer term sustainability and a pathway out of fragility. The programme works in parallel with other donor programmes in enhancing state capability to deliver services and promoting local accountability chains.

The programme continues to work on strengthening WASH sector actors, including the Ministry of Health, supported by UNICEF to deliver the rural Healthy Villages and Schools component. There has been some progress by all components in working with decentralised authorities. Learning lessons from DFID DRC’s Tuungane governance programme (project number 105862) have also been particularly helpful at acting on some of the recommendations issuing from last year’s review. So, despite the governance and accountability complexities, the programme is engaging positively with state actors.

DRC’s water law was promulgated in January 2016. Despite a need for further legislation to be passed in order to render it fully operational, this presents a significant positive step for reinforcing the sector and laying the foundation for new sector policies to enhance access to drinking water, as well as integrated water management. In terms of public water services, it allows for private sector participation in water provision, which in itself is not enough, but will contribute to diversifying the possibilities for improving water services delivery, and the law provides for a separate regulator.

Outline of the programme
In order to deliver the theory of change as described in the Business Case, the DFID DRC WASH programme increases the availability of sustainable WASH services over the short, medium and long term by targeting four key pillars: enabling environment, quality, service delivery and behaviour change.

The programme supports the delivery of equitable and sustainable services to 3,755,000 million men and women through four programme components:
- Healthy Villages and Schools (VEA) programme, implemented by UNICEF: £85 million from 2013 to 2019.
- A rural WASH Consortium programme, led by Concern Worldwide: £30 million from 2013 to 2018 of which only £24.8million has been programmed so far.
- A pilot sanitation marketing programme, implemented by Oxfam GB: £6 million from 2013 to 2019, of which only £ 1.5 million has been programmed so far.
- An urban WASH programme, implemented by Mercy Corps: £38 million from 2013 to 2019, of which £28 million has been programmed so far.

An impact evaluation is currently in preparation and £1.35 million is available for specific support to institutional strengthening. The later includes £0.6 million already programmed as technical assistance to the Urban WASH programme.

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
In spite of the challenging environment in which the programme is being implemented there have been noticeable improvements in the results achieved and reported. Assuming the remaining funds earmarked for urban WASH are programmed, the programme is on track to achieve its objective of reaching 3,755,000 million Congolese people with sustainable WASH services through support to government, civil society, and communities. Apart from VEA, the three remaining components spent the first year of the programme mainly on inception activities. During the second year, implementing partners were consolidating their systems for programme implementation, monitoring and reporting. In the third year, that which is under review, processes have bedded in and the programme components are by-and-large generating results in line with their milestones. With particular reference to UNICEF and VEA, the challenges to roll-out of recommendations made at the end of phase 1 have now largely been addressed, and delays have been caught up.

There are three outcome indicators for the programme:

Outcome indicator 1: Number of people collecting water from an improved source within a 30 minute round trip. Monitoring data from three partners shows that there is an improvement for 369,120 people (exceeding the milestone of 330,400) who are using water from either urban tapstands or a handpump[1]. Further surveys will be needed to determine improvements that have been made in the reduction of time it takes for girls, women and boys to draw water. The survey has to take into consideration the types of technologies that are being used in the provision of water in the programme.
[1] Most safe water sources provided by the programme are rehabilitated springs, which restricts the programme’s ability to reduce the time spent collecting water as the safe water source will often be in the same location as that which was used previously.

Outcome indicator 2: Percentage of households in targeted urban areas using service provider managed tap stands. The urban component is currently continuing to support 130,000 people with a service provider managed tapstand system, established under a previous DFID funded project. The urban component of this programme will expand the current network and extend the same management system to new infrastructure built by the programme. This outcome milestone has been exceeded with 71% of the people in the targeted area using existing tapstands (milestone: 64%). As new infrastructure is added, the overall number of users is expected to grow and this outcome will continue to monitor uptake of the expanding service.

Outcome indicator 3: Proportion of services operational and functioning two years after implementation. Most water points have not yet been functioning for two years. However, survey data from one province on the VEA component shows that 92% of the water points are functional after follow-up through community action planning and measured through a second post-certification visit.

Overall output score and description
The overall output score is “A’’ Outputs met expectation. This is composed of the following:

Output indicator	Output Indicator Description	Weighting	Output Score	Remarks
1	Individuals and communities are incentivised to deliver lasting behaviour change	30%	A+	The certification approach for hygiene promotion is proving to be effective and should be continued
2	A network of local actors exists which is capable of meeting the demands for the implementation and monitoring of the delivery of WASH services.	20%	A	Communities are given support by all the actors implementing the programme thus Ministry of Health, Ministry of Education UNICEF and the WASH Consortium.
3	Communities – members and community representatives – service providers and government (local & provincial) own, and are held accountable for, the delivery of WASH services.	10%	A	Communities and their representatives are aware of their roles and responsibilities but the performance of water management committees need to be improved
4	Increased access to affordable and improved water and sanitation for 3,755,000 million men and women.	30%	A	The programme is on track to achieve its objective and the momentum that has been achieved should be maintained
5	Improved capacity of national government to coordinate, monitor and set appropriate priorities in the WASH sector.	10%	B	Issues of capacity and coordination still remains a challenge at all levels

Performance against output milestones:
The Healthy Villages and Schools component (VEA) has accelerated the delivery of results, after experiencing delays in the previous year. The project has achieved most of this year’s indicator milestones, is now back on track to achieve its output indicator targets by December 2019 and also now reports on most of its output indicators. There still remain challenges in addressing gender issues at the community level, but there is active participation of girls and women in the programme implementation. The Business Case required the project’s re-assessment against the “moderate case”, which has been performed and shows that the Business Case’s selection of this delivery case continues to be relevant and achievable – having achieved UNICEF’s January 2016 milestones, as reported to DFID in March 2016.

The WASH Consortium component has continued to refine its intervention strategy to ensure a harmonised approach and continued incorporation of lessons learnt to deliver a sustainable project. It has achieved almost all of the milestones that contribute to this review’s logframe. The only milestone that was not met is output indicator 4 (sanitation). The Consortium’s innovative implementation of a life-cycle cost approach to the construction of infrastructure has been well received by communities, as demonstrated during several field visits.

The Sanitation Marketing component has progressed faster in the last part of the year under review and has met its milestones. As a pilot and research project, it also met most of its qualitative targets. The crucial question of whether the pilot can be scaled up is currently under review, and will govern DFID’s decision on whether to continue the project.

The Urban WASH component has suffered significant delays (approximately 6 months) since the beginning of implementation in January 2015. The behaviour change activities are on track, whilst the governance, service delivery and infrastructure targets are delayed but progressing at different paces. The procurement of a design and supervision consultant for the project’s water infrastructure work was completed, albeit with some delays. This in turn means that key preparatory activities related to the procurement of the infrastructure contractor, a crucial process for the development of infrastructure is similarly delayed.

Although performance against milestones is critical for ensuring value for money, for a WASH programme of this size, sustainability is critical to ensuring the longer term value for money. Accordingly, a number of activities have been incorporated into the programme’s design and implementation methodology in order to achieve sustainability. These include ensuring that: communities are able to raise funds for the operation and maintenance of their water points, high quality water points are being constructed with adequate site supervision, and that there is increased participation of women in the water management committees that are established. Sustainability is firmly centred in the programme’s delivery approach, ensuring that enough time is spent with communities in the post certification process that is being rolled out. Based on the observations made during the field visits for this review and reports from the implementing partners, the activities followed are contributing to ensure sustainability of the programme.

Key lessons
For the Rural WASH components of the programme, there are two main lessons that have been learnt. The WASH Consortium has demonstrated that it is possible to work with local decentralised government structures, in spite of the challenging context and environment. During the field visit for this Annual Review the team had a meeting with local government representatives and some of the members of local government accompanied the teams for the field visits in their areas.

Sector leadership has been weak since the beginning of the programme, notwithstanding strong Ministry of Health ownership of the VEA National programme. Over the years, there have been changes in leadership in the coordination of the sector, which means that priorities are ill defined, and actors are not united behind one vision or goal. DFID has not supported sector coordination directly, but rather complemented support from other donors to sector coordination. Without direct support to government coordination, it is unlikely that output 5 can be fully achieved, notably indicator 5.3.

On the Mercy Corps Urban WASH component, the main lessons learned relate to procurement of the design and supervision consultants and behaviour change. On procurement, the lesson learned for the larger procurement of a civil works contractor is that Mercy Corps need to engage early with potential bidders to refine the procurement process, timeframe and scope of work in order for the eventual procurement to be successful and receive sufficient high quality bids. Review and approval times have also entailed delay, which are now being appropriately factored-in to timelines. On behaviour change, different activities have been run in parallel such as training of community health representatives, radio messages and street theatre. It transpired that running these activities in parallel caused confusion. Mercy Corps’ have reconsidered and since evolved their approach to begin with training, then follow-up with radio messages and finish with street theatre.

Key actions for the coming year:
1. Although staffing of new District Provincial Health Offices (Directions Provinciales de la Santé, DPS), which are not in former district capitals, is outside of the programme’s control, UNICEF should encourage the Ministry of Health and the VEA coordination unit to train officials that are newly appointed and new to the programme.
2. Step-up and continue the post certification activities in the VEA programme to ensure that villages which lose their “Healthy” (Assaini) certification are supported to regain it, to maximise the programme impact.
3. UNICEF and the WASH Consortium should develop strong research products of the programme, in order to capitalise on what is being done in the programme to inform DRC’s WASH sector and continue exchanges of best practices and lessons learnt on the programme.
4. The Business Case provided for the urban component of the programme to reach 3 towns in eastern DRC, yet DFID has to date only approved implementation in two: Goma and Bukavu. Whether the programme does include a third town, or how the funds are reassigned to Goma and Bukavu, should be resolved with Mercy Corps by the end of summer 2016 in order to avoid causing further delays to implementation.
5. The procurement by Mercy Corps of an international contractor for civil works on Urban WASH is a high priority for the next year of the programme. Further delays to this procurement are likely to engender delays to the achievement of access to water results by this component. DFID, Mercy Corps and DFID’s technical Advisers Mott MacDonald must focus on ensuring that this procurement takes place on time and to a high enough standard as to contract an appropriate supplier. This procurement should be launched and completed within the next 12 months.
6. Amid the ongoing political and legislative changes to the water sector, Mercy Corps must define a sustainable business model and administration structure for the management of the water networks to be built and expanded by the programme in Goma and Bukavu. This is currently anticipated to be done by the end of 2016.
7. DFID must finalise a decision on whether or not to scale up the sanitation marketing component with Oxfam, and ensure sector learning takes place.
8. DFID to work with UNICEF on design of the impact evaluation on the VEA programme, with a goal of contracting an evaluation within the next 12 months.

Has the logframe been updated since the last review?
The logframe has been revised since the last review, in accordance with recommendations made in the 2015 review. The revision process was initiated in September 2015 and finalised in March 2016. The changes are limited to indicator definitions and milestones, including Outcome indicators. There have been no changes to final indicator targets, output or outcome descriptions. An itemised list of the changes made can be found at Annex B.

The reasons for making the changes fell into the following 3 categories:
- Adjusting milestones to implementing partners’ revised delivery schedules, following delays incurred in the first 2 years for the programme and acknowledged in the 2015 review;
- Aligning milestones to monitoring data available from partners at the time of reviews;
- Improving indicator definitions and aligning them with and across partners’ systems.

The process by which the logframe was updated was consultative and required significant investment from DFID’s partners. As DFID’s overall logframe is a composite of the sub-logframes it holds with the delivery partner for each component of the programme, each sub-logframe was also revised. Where there are shared indicators or where data from different partners is combined, further work was required to ensure coherence and compatibility of the data.

The overall trend in revisions to milestones was a deceleration in the pace of delivery through the middle of the programme, with a significant uplift anticipated in the final 3 years. Key output indicators where this was the case were: 1.1, 4.1 and 4.2, which respectively monitor: hygiene promotion, access to safe water and access to sanitation. The above trend was derived from experience of performance to date, communication with partners and review of each component’s work plan and delivery schedule.

As noted throughout this review, the programme has overachieved against some indicators. Given that this overachievement has been recorded against milestones which have been revised, it could be argued that the revised milestones have in some cases proven to be under ambitious. To temper the appearance of over achievement, this review has included pre revision milestones for comparison. For example, given significant overachievement across indicators under Output 1, an A+ has been awarded for this output, but this review has also ensured to reflect on performance against pre-revision milestones – against which an A+ would also be justified. Following this review, further minor revision of indicators is possible, which may include milestones, but this is not expected to substantively reassess the results trajectory plotted in this year’s logframe review.

C: DETAILED OUTPUT SCORING

Output Title	Individuals and communities are incentivised to deliver lasting behaviour change
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Remarks
1.1 Number of men and women with access to improved hygiene / (VEA, WASH Consortium, Urban WASH)	900,000	1,337,208	The milestone has been exceeded by 48%. Previous to the logframe changes mentioned above, the milestone was 1.3 million people. It would have been exceeded even without the change.
1.2.1 Number of men and women who know the transmission chain of water-borne diseases / (VEA, WASH Consortium, Urban WASH)	630,000	1,151,902	The milestone has been exceeded and would have done without the logframe changes. The initial milestone was 800,000 people.
1.2.2 Number of people in households with soap or ash and water at a handwashing station near the latrine / (VEA, WASH Consortium, Urban WASH)	360,000	844,343	The milestone has been exceeded and would have been met without the logframe changes. The initial milestone was 800,000 people.
1.2.3 Number of males and females, boys and girls who demonstrate correct hand washing behaviour with soap/ash / (VEA, WASH Consortium, Urban WASH)	540,000	1,180,259	The milestone has been exceeded and would have done without the logframe changes. The initial milestone was 800,000 people.
1.3 Percentage of villages that have maintained or regained their certification after 24 months / (VEA only, but WASH Consortium in future)	40%	91% after second post-certification visit (on a limited sample of villages). Up from 2.3% after the first post-certification.	Although the data is limited (because only a small minority of villages have been in post certification for 24 months), it is encouraging to see the positive leap in results between first and second post-certification assessments.
1.4 The number of households (early adopters that have accessed the products and services developed by the programme through the market place / (Sanitation marketing only)	A number of early adapters using the products provide feedback about the service	76 people bought the products and 75 of these provided feedback	Progress has started to be reported and recorded

All components are important to achieving this output, but not all contribute to the indicators in the same way. For instance, indicator 1.4 relates only to the sanitation marketing component, whereas indicator 1.1 tracks progress of three programme components (VEA, WASH Consortium, Urban WASH) against one overall milestone. Component monitoring inputs are specified in the table above for each indicator.

Key Points:
The programme has overachieved against milestones for both participation in hygiene behaviour change activities (indicator 1.1) and effective change in behaviour and practices (indicator 1.2.1 to 3). This is mainly due to the acceleration of programme activities by implementing partners. Even if milestones had not been revised following the last review, previous targets would have been met – showing that despite a slow start, the rate of progress picked up in the second half of the year. Even measuring against pre-revision milestones, this output would have scored an A+ given over achievement against behaviour change indicators. UNICEF remains the main contributor to these results and the increase in delivery of results underlines similar improvement in its performance in the second half of the year.

Knowledge attitude and practices surveys carried out on the VEA, WASH Consortium and Urban WASH measure actual behaviour change, based on reported and observed behaviours and practices. New adopters of positive hygiene behaviours are on target (indicator 1.2), however the programme aims to sustain these behaviours over time. Analysis of the VEA post-certification figures, continue to show that 65% of villages have maintained the norm on handwashing (norm 5). 78% of villages retain norm 6 related to knowledge of the faecal-oral route of transmission of disease.

Distances still remain long for girls and women and boys to walk to collect water especially for those that are being supplied through improved springs. This has an impact on hand washing, considering the fact that the communities’ access to clean water is challenging.

Indicator 1.3 tracks the sustainability of changes which are stimulated by the programme, predominantly by VEA, but also by the WASH Consortium. The certification of a village as healthy covers 7 norms, of which most require a sustained change to behaviour in the target population. The 2013 sustainability survey commissioned by UNICEF showed that only 2% of villages actually manage to maintain all the norms. For this reason, and to ensure sustainability of the programme’s impact, post-certification was introduced as part of the current phase 2. As full implementation of phase 2 was delayed, only a small sample of VEA villages have so far been in post certification for the required 24 months (circa 2% of the total case load), results from this sample are however encouraging.

In order to support villages to re-gain certification, a number of community-led activities take place, the success of which can only be measured after two post certification visits. First results (after two rounds of post-certification) are available for one Province (Bandundu) and show a very positive trend, with 91% of villages re-gaining their certification. Several visits aimed at observing this in the field were made throughout the period. Positive activities seem to be the role of the committee in reviewing the community action plan on a regular basis, and the separation of roles and responsibilities amongst a number of community members.

Considering the difficulties the communities have in maintaining their certification these new results reflect the level and quality of engagement that communities have with the supporting structures on the ground. In an environment where supporting structures are weak, it is difficult to make quick gains for ensuring that communities are living in a clean environment.

The WASH Consortium has marketed some of the activities that lead to behaviour change as ‘Small-doable actions’. This concept is positive in that it encourages communities and creates a sense of ownership of the changes that are induced by the hygiene promotion activities. This approach may help in maintaining certification, and this could merit with further study for the benefit of both rural programmes.

The Urban WASH component’s approach to hygiene behaviour change through the implementation of care groups is proving to be successful. In Goma it is on track, and has just started in Bukavu. The difference with the rural approaches is that the topics for hygiene behaviour change sessions are based on an analysis of determinants of certain behaviours. The quality of the intervention, the materials used and the facilitation was observed to be very high. The mixed messaging approach, using different communication channels seems to also have a very good effect, as measured by feedback from beneficiaries. The only issue being that it is progressing much faster than some of the other urban components (i.e. infrastructure) and risks raising expectations earlier than they can be met.

Indicator 1.4 measures part of the success of the sanitation marketing pilot. All elements of the pilot have been implemented almost by the book (based on sector best practice), with formative research informing the communication and marketing, work on the enabling environment, as well as understanding consumer habits and the supply chain. Since the demonstration site for sanitation products was finished in November 2015, there have been 3,626 visits and 76 households have purchased sanitation products. Although it is still too early to tell whether there will be a large scale uptake of the products, it should be noted that the number of sales has increased in the last month.

Summary of responses to issues raised in previous annual reviews (where relevant)
Significant progress has been made on implementing recommendations from the sustainability survey. Field visits confirm that communities that lost their certification are elaborating action plans through self-assessments. The community-wide approach is being rolled out, with schools only targeted together with villages. More recently the strategy for integrating health centres has been finalised. As described above, data from third party monitoring and regular monitoring is available.

The health authorities have certified 50 WASH Consortium villages to date, but the mechanism for entering them into the database and then responsibility for post-certification remains with the WASH Consortium. The last joint field visit and recommendation from a partner’s workshop is that the VEA programme and the partners finalise the manner in which villages enter into the database. The logframe has been updated with hygiene behaviour change and maintaining certification by both rural programmes

A brief review of evidence underpinning the VEA programme norms for reaching certification was undertaken by UNICEF. It concluded that there is some evidence that 80% sanitation coverage starts to tackle ‘herd immunity’. Third party monitoring will provide some indication as to which norms are being maintained in the villages. Further study is necessary on this subject.

Recommendations:
1. The quality of locally made latrines for households in rural areas is generally poor, notwithstanding an observed tendency for those under the Consortium to be better than VEA’s, and significant barriers to improved materials exist due to distance as well as lack of income generation. Both VEA and WASH Consortium’s programmes do not market sanitation products. Oxfam should prioritise transferring relevant lessons from the sanitation marketing component to UNICEF and the Consortium during the next period.
2. There are still different policies and practices with regards to the subsidy of sanitation materials on both rural programmes, VEA and WASH Consortium. Over the longer term, a policy on subsidies should be developed by VEA (the government and UNICEF), taking into account that subsidies might be better placed in a sanitation marketing approach, rather than as a direct subsidy to households through the provision of slabs, as is currently the practice.
3. Post certification is well under way now, with 1,483 villages having received a post-certification visit, which represents 42% of villages certified in phase 1 of VEA. DFID should continue to monitor post certification results closely and encourage its continued roll out, including to phase 2 villages, in order to grow the sample of results and provide stronger confirmation that post certification is proving successful.
4. UNICEF should disaggregate VEA post-certification data for villages certified under Phase 1 or 2, in order to start understanding whether the changes brought into Phase 2 actually foster sustainability.
5. The WASH Consortium should assess their care group approach to understand how important the determinants analysis was in the uptake of positive behaviours and share lessons from the approach with VEA.
6. Previous recommendations made on the systematic review of evidence still hold. A literature review could be conducted by UNICEF, the WASH Consortium or DFID 10% Advisory input to complement some of the monitoring data that is coming out of the programme, with the aim of building the evidence base generated by the programme.

Output Title	A network of local actors exists which is capable of meeting the demands for the implementation and monitoring of the delivery of WASH services
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Remarks
2.1 Number/percentage of local service providers showing improvements in administrative and technical capacity / (VEA only)	10%	30%	Progress has exceeded the milestone and should be continued: 32 out of 109 partners have gone up 1 point in the classification, of whom 8 were government partners and 24 NGOs.
2.2 Existence of a demonstration site for latrine models/products and services and number of visits made by members of public / (Sanitation marketing only)	5% of Gemena Households	6.59%of Households / (3,626 visits)	Milestone has been met
2.3 Percentage of stakeholder trainings completed / (VEA and WASH Consortium)	100%	100%	Milestone has been achieved
2.4 Number of water points established which are managed by a committee or user management group after 24 months of certification / (VEA and WASH Consortium)	1,533	43 (of 47 water points in villages having passed 24 months of certification)	Unmet due primarily to delays to implementation of post-certification.

Although reporting towards this output is only recorded from the rural WASH programmes, VEA and WASH Consortium, WASH service delivery by the urban component is monitored – but in the sub-logframe particular to urban WASH.

Key Points
All programmes are continuing to work very closely with local service providers, whether it is the state via its institutions, the private sector or local NGOs and civil society organisations. This is a key aspect of ensuring that longer term gains can be made, beyond the lifetime of the project. The programme through the implementing partners UNICEF and the WASH Consortium have created the enabling environment for the building of capacities of local service providers.

UNICEF, through its quality assurance team (previously known as the WASH internal audit team), continues to audit and build the capacity of implementing partners. A UNICEF comparison of the progress in risk levels of their partners at provincial level shows a positive evolution of capacity over the two periods 2008 – 2013 and 2013-2015. Indicator 2.1 is on track with milestones, showing that the programme is building the capacity of local actors to provide WASH services. The WASH consortium has provided a province level training of trainers to help local partners better plan interventions for the next period, based on objective selection criteria of villages and on supporting villages committees to manage WASH services.

In response to the changes to the organisation of the provincial health teams, due to decentralisation mentioned in the last annual review, UNICEF is developing a performance based financing system with government partners. This will in part help resolve the need to have a robust system in place with the new organisational model, but also provide better capacity building initiatives/incentives.

The VEA programme is decentralising responsibility even further, in response to the additional workload that phase 2 represents. The local health post nurse and health extension workers (relais communautaires) have a greater role and responsibility in the programme. This requires additional training and also better planning on the part of the zonal health team – which UNICEF is supporting.
UNICEF also supports the professionalization of manual drilling, with private sector actors now being trained to provide these services. In addition, the partnership with private hand-pump and spare parts suppliers continues to build a network of actors able to meet the needs of repairs and maintenance.

The sanitation marketing component has reached a critical stage, where all programme activities are complete and the market can be observed for take-up. According to the records, 6.6% of the population (3,626 visits) have visited the demonstration site of the programme, which corresponds to a theoretical ‘early adopters’ of new technologies (5% of the population). 20 local craftsmen and artisans as selling the products, and have adopted the branding that grew out of the project, as a gage of quality of the product. In the first few months of the launch of the product range – 70 toilets have been sold.

A similar approach to sanitation was envisaged on the urban WASH programme, but this has been delayed due to mainly to the fact that the sanitation strategy was not robust enough. Mercy Corps are exploring different options, especially for some of the more sensitive neighbourhoods of the town of Bukavu, where sanitation presents a significant challenge.

Indicator 2.4 is important, as part of the sustainability rests with the community and its water committee. Delays in the implementation of phase 2 of VEA and the Consortium are such that very few villages have been through 24 months of post certification by this stage in the programme – only 2% of UNICEF’s current caseload of VEA villages. While this indicator has been missed by a significant margin, it also sits further out of the control of DFID’s partners than the other 3 indicators in this output, so it is not accorded the same assessment weighting as indicators more within the control of partners’ delivery. Milestones for the remaining years will require adjustment following this review, in order for meaningful assessment in future reviews.

Evidence gathered during the VEA sustainability survey showed when the village chief was part of the water committee it stood a better chance of being active. This is now fully part of phase 2 of the programme and was observed during the field visits. The WASH Consortium’s results are not yet available for 24 months after implementation, but 372 water committees are already active. UNICEF data shows that only 21% of the water committees are still active after the first post-certification visit, but 90% are after the second post certification visit.

Summary of responses to issues raised in previous annual reviews (where relevant)
Local government structures that are found at the zones are not elected since there has been no Local Government election in DRC. Even though the local structures might be influential, the sustainability of the structures is limited. The structures have no official mandate from the people and this makes it difficult for them to operate effectively. The WASH consortium has had some success as seen in the technical learning events, as well as on field visits at including local authorities.

Terms of Reference for a participatory planning study are written, but publication was delayed whilst awaiting confirmation of the water law. The programmes have also interacted with the PFMA programme, in identifying decentralised territories in which participatory budgeting will be supported.

There is no formalised strategy for integrating rural villages that have been certified outside of the national Healthy Villages and Schools programme yet. It has been the subject of renewed discussions during the last joint sector visit and an indicator for villages entered into the database will be included in logframes.

A study on hand pump supply chains made a number of recommendations on steps that should be taken to address issues identified in the establishment of supply chains for water point spare parts. These recommendations should be implemented where possible, noting that a vibrant private sector is important in the setting up of supply chains and plays an important role in ensuring sustainability of the water points that are being constructed under the programme. UNICEF guidelines encourage local purchases where feasible. The possibility of sourcing pumps locally has been discussed with local suppliers, but transition into this new strategy requires more analysis and a feasibility study.

Recommendations:
1. The rural components, UNICEF and the Consortium, should reinforce their respective efforts to support the capacity of local suppliers and service providers , to increase local capacity to deliver WASH services to communities including, where possible, supply of spare parts for water points. In the absence of a national strategy on rural water supplies and supply chains, the work that Vergnet is undertaking, as well as the handpump supply chain work done by the WASH consortium should continue. UNICEF should carry out a feasibility analysis for procuring pumps locally.
2. Documentation and keeping of records including collection and processing of data for the VEA programme still remains a challenge. Therefore, UNICEF should consider how to increase or supplement their existing capacity building for data collection and management at all levels of the Ministry of Health involved in implementation of the VEA programme.
3. External support is required for the water management committees after certification of the villages to ensure the sustainability of the interventions. The programme should continue exploring the length of time required for the support.
4. Both the UNICEF and the WASH Consortium logframe should mirror the need to respectively integrate and feed into the national database of the healthy villages and schools programme.
5. The sanitation marketing component has delivered a number of interesting knowledge products, and events should continue to advertise these, whilst following up on the take up of sanitation products in the town of Gemena.
6. Revise logframe milestones for indicator 2.4 to provide realistic and achievable targets which are up to date with current expectations of villages in post certification.

Output Title	Communities – members and community representatives – service providers and government (local & provincial) own, and are held accountable for, the delivery of WASH services
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		H	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Remarks
3.1 % of population [measured by households] satisfied with water management committee performance / (WASH Consortium, Mercy Corps)	60%	73%	The population benefiting from the WASH Consortium’s project, as well from urban access to water is satisfied with the performance of the committees.
3.2 Percentage of women and men on water committees / (WASH Consortium, Mercy Corps, UNICEF)	40%	38%	Good progress made in the achievement of the milestone. The VEA programme has reached the 40% target.
3.3 Number of Zone de Sante who are assessed as functioning “well” or “very well” in organisational, technical and response capacity assessment / (WASH Consortium)	30%	33%	Milestone has been achieved
3.4 Number of WMCs that perceive that they receive useful support from local authorities. / (WASH Consortium)	50%	79%	Good progress in achievement of this milestone

The sustainability of rural water and sanitation infrastructure rests mainly with the communities themselves, but the programme aims to build stronger accountability links between users, their representatives and the authorities. It also builds on the existing strengths of the health system. Gender, although inherent in all activities, is measured here specifically in terms of the water committee. Good progress has been made here. Most indicators are measured by the WASH Consortium.

Key Points
Having a functioning and dynamic water committee continues to be a determinant for the sustainability of the behaviour change and of the water points put in place. Two components measure the satisfaction of users with their water committees, the WASH Consortium and the urban project. The fact that the monitoring data shows a majority satisfaction is an important mark of success. This was also observed in the field on numerous occasions during community-wide meetings and also in focus group discussions. Leadership in the community by representatives is important to achieve change and ensure gains are made for the entire community rather than a few.

The WASH Consortium and UNICEF have been emphasising the role of the water committee in providing the community with information about their activities and transparency in the accounts, in order to build accountability. In addition, the village chief and the committee play an important role in equity of use of improved water sources. In the model developed by both programmes, the committee must ensure that they can provide for repairs and maintenance and yet ensure equitable access to clean drinking water and sanitation for the whole village.

On the urban WASH component, monitoring of satisfaction with water committees showed that users did not trust the water users committees that had initially been put in place by the project. Mercy Corps then decided to revert to using the existing structures, local development committees, which are judged by the users to better represent their needs and views.

The division of gender roles is still very strong in the DRC, but also in the populations the programme targets. It is observed in rural villages that water, sanitation and hygiene are still subject to these well-defined roles. Getting women in key positions on water committees is still a challenge and although almost 40% of positions are filled by women, this still hides the fact that women still bear the burden of water collection and domestic hygiene. Men often build the latrines. Discussions held with committees seemed to indicate that when women would leave the committee, they would be replaced by men. Of the six water management committees that were visited during the most recent field visit, only one had a woman as a chairperson. This example serves to indicate the impact of dynamics at play at the community level, which hinder women from playing a fuller role in the implementation and management of WASH programmes.

The healthy villages and schools programme undertook a gender study of the project over the period reported on. The report shows that more can be done to improve its approach to gender equality and that VEA has a tendency to reflect, rather than challenge, the status quo and existing gender roles. The WASH Consortium has planned a gender audit/review as part of additional programming in the coming year. Programme monitoring systems also pick up gender inequality in other ways, for instance in the proportion of women attending VEA health zone level training events, where only 10% of the trainees were women. In Provincial government posts there are a higher percentage of women (23%) and NGOs are roughly comparable (18%), but at more local levels (e.g. health zone) percentages of women employed are as low as 6%.

The baseline for the urban WASH component delivered its results in July 2015. The data fed into the Gender Status Index, and showed that women perceived less violence in project areas where water is readily available at public tapstands, than in areas where supply is more distant and erratic. Integrating gender into each facet of the programme still features centrally in this component.

The two other indicators in this output aim to measure the sustainability as linked to the role of political and administrative authorities in service provision. The Health Zones implementing the programme that were visited during the field trip demonstrated the key roles that the health workers are playing in programme implementation. The health workers including nurses at the health centres, and the zonal medical teams are actively involved in building the capacities of the communities, and in implementing the programme’s aims including collection and management of data.

The field visits on the WASH consortium project did confirm that there is positive engagement by local authorities and the implementing partners’ efforts at integrating local political and administrative authorities is an important preparation to the decentralisation of responsibilities for water and sanitation services to decentralised government.

The governance pillar of the urban WASH component has been delayed, but has gathered information that will help measure the strength of civil society links and networks, which in turn will help focus on building demand-side accountability of services. Changes brought about by the water law, have also meant that Mercy Corps have had to identify new key stakeholders, and are starting to work with those local authorities who now have the responsibility for ensuring that water and sanitation services are provided. The National water utility REGIDESO, remains the main service provider in urban areas and Mercy Corps has continued to support them and a service provider for the tapstands to maintain a regular and quality service to tapstand users.

Summary of responses to issues raised in previous annual reviews (where relevant)
There was noticeable involvement of local government in the areas where the WASH Consortium is implementing the programme. Local Government representatives accompanied the teams for the field visits this was the way of expressing their support and commitment to the implementation of the programme.

The Tuungane programme presented lessons learnt on empowerment and accountability during the WASH Consortium’s external technical review (29/01/16), as well as during a DFID WASH partner’s meeting (20/11/15).

A gender study was undertaken on the healthy villages and schools programme. No gender focal point was appointed on either of the rural WASH programmes.

Recommendations:
1. A number of recommendations were made by the UNICEF/Oxfam GB gender study on healthy villages and schools. In the coming months, UNICEF and the WASH Consortium should consider how to integrate them into the programme and ensure that they are tracked as part of the recommendations matrix. An action plan should be in place within 6 months and activities underway by the time of the next review.
2. Also in response to the Gender study, UNICEF and the WASH Consortium to each consider appointing gender leads within their programmes. A decision to be taken within 6 months – in line with broader discussions on how to take gender forwards.
3. DFID to secure input from a Social Development Adviser or Gender Lead to ensure that DFID is learning as much as it can from the urban WASH programme’s approach to gender.
4. UNICEF and the WASH Consortium should ensure that the results and lessons learnt in the implementation of the programme at the community level should be documented to influence and inform policy dialogue amongst sector stakeholders.
5. UNICEF and the Ministry of Health should include a split in responsibilities for certification of villages and supporting villages towards certification assessment in their considerations of a likely phase 3 of VEA. At the moment, the health authorities both implement and certify the villages as healthy. Although these responsibilities are split between different individuals, the certification process would benefit from being done by a more independent actor. This of course has a cost, and in a country where the presence of other government departments is limited, poses a particular challenge. This should however be noted and taken into consideration in future.
6. Partners should ensure that the principles of equity in access to water and sanitation services are an integral part of the water committee’s role together with the recovery of funds for maintenance and operation.

Output Title	Increased access to affordable and improved water and sanitation for 3,755,000 million men and women
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Remarks
4.1 Number of men and women with access to a clean drinking water source / (WASH Consortium, Mercy Corps, UNICEF)	800,000	1,136,024	The milestone has been exceeded by 42%, but the initial target was 1,6 million
4.2 Number of men and women with access to an improved sanitation facility at the household level / (WASH Consortium, UNICEF)	1,100,000	1,038,983	Good result - the challenge is the stricter criteria used by the WASH Consortium
4.3 Number of households who collect at least 15 litres per person per day of potable water from safe water sources / (WASH Consortium, Mercy Corps)	67,126	183,754	Achieved, but most of these results come from the urban programme. The rural programmes are not yet measuring this systematically.
4.4 Number of committees collecting fees for maintenance and operation of the water point / (WASH Consortium, UNICEF)	60%	54% / VEA: 40% / Cons: 68%	Progress has been made in the achievement of this milestone, particularly by the Consortium.

This output mainly measures access to water and sanitation services. The aim is to also track the quantity of water available, as this is also an enabler of positive hygiene behaviours such as handwashing. In order to measure how many people do actually benefit from an improvement in time spent collecting, this is being measured where there are water points that are built in the village or public tapstands in urban areas.

Key Points
The number of men and women with access to a clean drinking source has been over achieved by 30% according to the new milestone. However, the milestones had been revised downwards from January 2016 when it became apparent that the delays in implementation across the portfolio meant the original targets from 2013 were not realistic anymore, or in line with the project’s progress since then. Despite this, the trend is positive with UNICEF having met their target, and results from the WASH Consortium starting to come in. The urban component is not yet contributing to the overall access to water results, as the infrastructure is not yet built. However, there is a pre-existing pilot network (built under a previous DFID programme) which serves a population of 130,000 people, the management of which is monitored for quantity of water collected by users by Output 4.3 and uptake of the service by Outcome indicator 2. The current programme’s logframe monitors management of the current network as all new urban infrastructure will, once built, come under the same management as that which already exists – so how the existing network is managed has direct implications for the current programme.

Both rural components (UNICEF and WASH Consortium) offer different drinking water technologies to communities, depending on the hydrogeological configuration and the cost of the technology. In many areas, the option of drilling a borehole equipped with a handpump is a solution that is too costly, or technically unfeasible. In the meantime, springs can be capped, but they often do not allow for a reduction in collection times, making it challenging for girls, women and boys when collecting water. Often the walk to the spring is also difficult, with steep and muddy tracks. Over the course of the project, studies should look at the relative benefits of capping springs with regards to the overall change the project is trying to achieve.

UNICEF has continued to expand manual drilling of boreholes to 4 new provinces. Although this is not specifically captured in the logframe, UNICEF have trained 97 local artisans and entrepreneurs to create the drill bits, and to drill manually. This technology allows reaching communities at low cost in the appropriate hydrogeological settings. With the issue of distance to water points, and sustainability through building network of private sector services providers, this is a very promising approach. The need to ‘professionalise the sector’ is seen as an important step in legitimising this as a viable low-cost technology and there is continued support from the Chadian organisation of manual drillers which helps transfer technical but also qualitative skills.

The numbers of men and women that have access to clean sanitation facilities at household level has not been fully met, as displayed in output indicator 4.2 above. Communities have taken up the messages as was demonstrated by answers to questions that were asked during the field visit, and by the hygiene behaviour change results related to output 1. Constructing and reconstructing latrines is definitely challenging for families (latrines have to rebuild regularly after rains, or because of termites). Some WASH Consortium partners have included some aspects of Community Led Total Sanitation (CLTS) in their approach. Whether this means that there is a better uptake of sanitation should be monitored.

On the basis of observations made during field trips involving both UNICEF and the WASH Consortium, the quality of latrines built seems to differ amongst the two different components. Typically, the latrines built in Consortium villages appear to be of better quality and the criteria to assess them stricter than in VEA villages. It may mostly be due to the level of intensity of intervention by external actors (i.e. under the WASH Consortium methodology or VEA’s), but could also be due to the integration of CLTS approach in the WASH Consortium’s approach. It would be good to better understand these differences and decipher what approach might bring about a more lasting change – but there should also be parity between the two components with respect to assessment of the VEA norms.

A majority of the Urban water service users (users of the existing network, established under a prior DFID project) purchase more than 15 litres per person per day. Evidence shows that there is a real increase in consumption only once water is available in the user’s yard. However, it is important that a minimum is used for drinking and personal/domestic hygiene, which is why this indicator helps indirectly track whether there is a real improvement in terms of distance. In areas where the water source is an improved spring it is difficult to expect water consumption amongst communities to increase as long as distances still remains long.

Financial sustainability for water supply interventions is important and it was observed during field visits that the levels of contribution for the operation and maintenance of the water point made by each household per month were low. As long as the economic performance of communities remains low the levels of the contributions will remain low. It was also observed during the field visits that communities have tried other methods of raising more money like investing in communal gardens or rabbits. In the absence of rural banks and a certain level of distrust between people, committees prefer to invest the funds into something than keeping large sums in their cashbox. In the areas where the WASH Consortium is implementing the programme a life cycle cost analysis is done before the water point is provided, which allows communities to understand what maintenance and repair costs they are likely to incur over time, and have a discussion over how to pay for those once the time comes. It also allows the community to make their own decision as to whether they can maintain a handpump or only a protected spring.

Although results were not yet expected on the urban WASH component, the procurement of infrastructure components is delayed. The Supervision and design consultancy was contracted over the past year, and is now reviewing the masterplans, carrying out the detailed design and preparing the tender for the civil works. The sanitation strategy was not judged as sufficiently robust, or sustainable. As the sanitary disposal of faecal matter does remain a priority in some of the neighbourhoods, Mercy Corps are exploring new partnerships for the provision of sanitation.

Summary of responses to issues raised in previous annual reviews (where relevant)
The logframe update that was required in order to include the WASH Consortium results was done.

The sanitation strategy was reviewed, and changes were made. Mott MacDonald were also involved in the recommendations, and carried out a field visit to the sites. The approach initially recommended was for the urban component to support the creation of sanitation masterplans for Goma and Bukavu, which would have been analogous to how the programme tackles access to water. However, the lack of institutional commitment to sanitation problems in these towns and the overriding need to improve existing services meant that this approach was unlikely to yield a workable plan, or one that had few chances of successful implementation, so in the event this approach was not adopted. Facing up to the reality of what the component can achieve on urban sanitation, the scope of the intervention was revised to focus on one priority neighbourhood – with the possibility to expand this effort.

On the sanitation marketing piloted by Oxfam GB, a number of events for disseminating learning from the sanitation marketing programme have been organised. These include an event at the University of Kinshasa, a sector event with government officials, and presentations at two WASH partner sector meetings.

Recommendations:
1. VEA and the WASH Consortium should look at the relative costs and benefits of improving springs, including the improvement in water quality in order to ensure that wherever possible, there is a reduction in distances for girls, boys and women for the collection of the water.
2. Given apparent differences in the quality of latrines built under the rural components, VEA and the WASH Consortium, the Consortium should ensure its assessment of norms mirrors that of UNICEF, to ensure parity in certification. The Consortium should equally consider how to demonstrate what the approach might add to the chances of bringing about a more lasting change and what it can offer to the national VEA programme’s methodology.
3. The life cycle approach adopted by the WASH Consortium should be documented and shared, in order to see whether it has potential to work at scale. It is an intensive approach, but is possibly an important enabler of sustainability. It is still too early to really tell whether this is the case but the Consortium should assess its particular impact and share any lessons arising for VEA and the broader WASH sector.
4. UNICEF and the WASH Consortium ensure that messages around payment for water and equity of access are understood by the entire community. It is not sufficient to assume that a community will look out for the vulnerable people, equitable access to water must be entirely thought through, communicated and monitored effectively.

Output Title	Improved capacity of national government to coordinate, monitor and set appropriate priorities in the WASH sector
Output number per LF		5	Output Score	B
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Remarks
5.1 Number of Provinces implementing 5 year VEA plans and 2 year action plans / (UNICEF)	22	22	Good progress in meeting the milestone
5.2 National database of rural points is up to date and accurate at all times / (UNICEF)	95%	75%	Milestone not achieved
5.3 CNAEA monitoring sheet for the road map is in place / (UNICEF)	0	0	No result anticipated

This output is to acknowledge that a favourable enabling environment is important for the gains to be made from the different programme components to be sustained over time.

Key Points
Governance in WASH in the DRC still remains weak in spite of the efforts that have been made by the programme and other stakeholders to improve sector coordination. Despite this, 22 out of 22 provinces have implemented 5 year healthy villages and schools plans and 2 year action plans. Updating and ensuring accuracy of the National Database of rural water points continues to be a challenge as 75% has been achieved over the reporting period against a milestone of 95%. However, the UNICEF’s M&E officer and third party monitoring contractor should help resolve conformity issues and strengthen the reliability of the data collected. UNICEF have also facilitated a number of training and diagnostic sessions of the DHIS2 database by consultants, who have examined the quality of the database and provided supplementary training. It is likely that this will help to improve the accuracy of the database over time.

Coordination at the local level has continued to be a challenge because of perceived absence of legitimacy (unelected representatives were appointed in certain regions) and gaps in the capacity of local government structures at the district level. Often where structures are present, they do not have the means (human resources or financial), or sufficient experience to manage the implementation of a WASH programme. Efforts made by the WASH Consortium to work with local authorities are a welcome development, showing that there is some support for basic services available. However, in the absence of means it is unlikely that local government structures will be able to take on their new roles as decentralised providers of water and sanitation services. Nonetheless, in view of their growing responsibilities under the new water law, the rural components should aim to establish links and work with local government.

Although this output does not concern the urban WASH component, significant efforts are being made by the urban project to work with local authorities with their confirmed role in the provision of water and sanitation services. The law formalises the new role of local authorities, and puts the role of the national water utility – REGIDESO – into new light. However, in the absence of implementation measures for the law, and an appropriate contract between the government and the national water utility, there are still unanswered legal questions over the ownership of water and sanitation infrastructure, with which the urban component has to work within.

Over the reporting period positive developments have been made towards improving the enabling environment. The passing of the water law by parliament in December 2015, and promulgation in 2016 is a big achievement for the sector in the DRC. This helps complement the decentralisation laws which already confer competencies for water and sanitation service provision to the decentralised authorities.

The decree for restructuring the national water and sanitation committee (CNAEA is the committee’s French acronym) to include the ministry of health has been signed. This organisation will now be referred to as the CNAHEA. It has organised two sector coordination meetings with implementing partners and donors over the last 6 months. Unfortunately, the international forum organised by the CNAHEA with financial support from the international community met with limited success. The event provided opportunities for coordination and lesson learning, but the CNAHEA has yet to undertake any follow-up to capitalise on the event.

Summary of responses to issues raised in previous annual reviews (where relevant)
The government’s budget allocation to the water sector still remains low and this makes it difficult to address key challenges facing the WASH Sector in DRC. The current reform of the CNAEA/CNAHEA for its French acronym is mostly linked to the integration of hygiene as part of its core mandate, which is a positive step but still does not address the more fundamental issue of its inability to coordinate the sector effectively.

The water law was adopted after review by both parliamentary chambers in January 2015 but dissemination of the law to key stakeholders at all levels still remains a challenge. This is supported by GiZ (German Corporation for International Cooperation) and is expected to lay the foundations for a more effective institutional framework, but the policy options and effective powers will largely rely upon political will.

Donor coordination for WASH in the DRC still remains weak in spite of the efforts that have been taken by DFID though the programme. UNICEF is the current chair of the donor group and meetings are supposed to be held quarterly but meetings have not been held as scheduled.

Recommendations:
1. Continued engagement by the donor group with key ministries in the sector, including the ministry of plan and the CNAEA/CNAHEA to support sector coordination initiatives.
2. In the medium to long term, donor coordination should aim to support Government in coming-up with a rural sector programme that is supported and implemented by all stakeholders.
3. There currently seems to be limited opportunity to engage positively with central government on coordination and planning and the overall situation for coordination is not following a positive trend. The components should continue to focus on provincial and decentralised coordination and planning, where authorities are present on field visits and seem to be better engaged in the programmes.
4. The VEA database is potentially a very powerful tool, especially since it is aligned with the national health information system and should ensure compatibility for data analysis. This could be used to refine some of the impact data, some of which can already be used in the verification of self-reported diarrhoeal disease results.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
A comparison of budgeted key costs and spend for each programme component is displayed in the table below.

Table: Comparison of key costs in budget and spend to date

UNICEF, WASH Consortium and Oxfam’s spend to date has broadly been in line with their budgeted proportions of costs allotted to key cost centres. Mercy Corps’ spend to date has not, but this is understandable given that key infrastructure procurements are still in progress – which in turn has increased the relative proportion of spending on personnel. Once a civil works contractor is procured, this distribution of costs should increasingly look more like the budgeted proportions.

The above analysis of budgeted cost categories underlines the delivery model of each partner. UNICEF’s support to the National VEA programme principally spends its resources on support to NGOs and performance payments to low level Government bodies, who jointly share the primary burden of working with villages and schools across DRC. UNICEF’s second cost centre is contractual services, which comprises manual drilling of boreholes, third party monitoring (established this year) and other consultancy work, for example on operational research. Unlike UNICEF, the INGOs delivering the other 3 components of the programme have each budgeted a significant proportion of costs for their staffing - which is consistent with their methodology of direct intervention. The Consortium and Oxfam’s second largest cost centres are also aligned with the scope of work they are delivering: providing access to water through boreholes or rehabilitated springs, or formative research on sanitation marketing. Mercy Corps’ approach, which entails delivery directly by Mercy Corps staff as well as through contracted parties, results in a more balanced distribution of staffing and contracted costs – which has evolved since the inception phase to an increased proportion of contracted costs relative to staffing.

VfM performance compared to the original VfM proposition in the business case
The Business Case identified the cost per beneficiary as the principal measure of VFM for the programme. This review’s analysis of the programme’s VFM, at the mid-point of its duration, focuses on measures of Economy (input costs) and Efficiency (cost per beneficiary) as well as early indications of Effectiveness (achievement of Outcomes & Impact). As more Outcome data becomes available, subsequent reviews will be able to more comprehensively assess measures of Effectiveness.

Economy is ensured by each partner’s control of input costs, some highlights of which include:

UNICEF:
- Uses benchmarked costs as a basis for field Offices’ procurements, updated in January 2015.
- Assesses its downstream partners’ procurement capacity and capability, entrusting those which it has evaluated as low or medium risk to conduct their own local procurement of construction materials.
- Has access to UNICEF’s network of global Long-Term Agreement (LTA) suppliers, to purchase high value/volume items cost-effectively and timely – for example: vehicles, motorcycles, and programme communication materials.

WASH Consortium:
- Shares expertise across members, for example hydrogeological studies in ACF’s work areas were carried out by CRS technical staff, with hydrogeological expertise, saving costs of recruiting external consultants.
- Is developing a comprehensive VFM policy to cater to different audiences (DFID, the Consortium Board, implementing agencies, the sector). The Consortium anticipates using this policy to support a proposal for a potential scale-up of the project between 2016 and 2019.

Mercy Corps:
- Avoided duplication of staff and functions between Goma and Bukavu, by making Goma their coordination hub. While this entails higher travel costs, these are exceeded by savings on staff costs.
- Minimised accommodation costs in Bukavu by opening a guest house, which over the longer term will be cheaper than hotels.
- Saved $1,500 and 4,500 plastic bottles by reusing water bottles provided to participants during training courses. Each participant was given a new bottle, refilled using 20L containers.
- Mitigated exchange rate losses over the life of the design consultancy contract by procuring in GBP.

Efficiency, measured by cost per beneficiary, is displayed in the table below. The calculation of costs per beneficiary is based on total cost of each partner’s project and the number of beneficiaries they intend to reach. Figures for 2013 are from the Business Case or implementation proposals, in the case that updates were made to the Business Case’s figures after approval. Figures for 2016 are updated projections, not a reflection of performance to date, based on projected end of programme costs and total numbers of targeted beneficiaries. As such, where there is difference between 2013 and 2016, there has been a change in our partners’ planning.

Table: Anticipated cost per beneficiary, original and current (USD)

The cost per beneficiary of the programme has changed for the WASH Consortium and Mercy Corps. Although there have been changes to annual milestones and budgets for UNICEF since 2013, the overall budget and targeted beneficiaries remains the same – hence also the cost per beneficiary.

Following the last review and in response to the delays incurred and noted in the review, the WASH Consortium requested a 12 month no-cost extension, with changes to delivery methods. The Consortium’s early programme waves had suffered from targeting issues in certain geographical areas – working both in areas of severe hydrogeological challenges and villages with lower than planned populations. The consequence of these two issues was that the Consortium was, in the affected areas, unable to provide complete WASH access to the number of beneficiaries intended. This reduced their number of beneficiaries by 25,037, while costs remained stable, such that the cost per beneficiary has increased by $3 per person. However, to mitigate the impact on beneficiaries themselves, the Consortium have provided alternative solutions for improving the quality of water consumed to 80,000 people - without the construction of an improved water point. Including people in receipt of alternative water solutions, the cost per beneficiary of the Consortium’s adjusted programme is $58, $6 below the amount in the project proposal.

The last review outlined the changes in between Mercy Corps’ inception and implementation plans, which result in the above change in cost per beneficiary. A further consideration not revealed by the above, but which will likely coalesce by the next review is the decision by DFID not to approve Mercy Corps’ plan to deliver the programme in a third town. This was considered too much of a stretch and DFID requested a further proposal from Mercy Corps on how to use the funds intended for an alternative but relevant purpose. No decision has yet been taken on how to utilise the funds for the third town but it is possible that such a change will have an impact on the cost per beneficiary for this project.

The Effectiveness of the programme can be assessed through the impact on Outcome and Impact indicators, both addressed earlier in this report. As already noted, the programme has met all its Outcome and Impact indicator milestones for this year, which suggests it is on course to achieve the Business Case’s intended effects on sustainable access to WASH services and an improvement in diarrheoa rates in children under 5.

Assessment of whether the programme continues to represent value for money
The programme is on track to achieve the majority of its objectives and remains within the approved budget. There have been changes to implementation, including schedules and methodology, which have impacted on annual milestones and costs per beneficiary, but overall the programme targets remain un-changed and cost per beneficiary within acceptable margins of the VFM proposition laid out in the Business Case. As such, the programme continues to represent value for money.

Quality of financial management
A statement of programme finances (for active components) is displayed in the table below, where the “Revised” column displays currently agreed budgets for the period:

Table: Cumulative budget and spend by component

Financial performance
Overall financial performance of the WASH programme has been strong since the last review, albeit with issues on the Urban WASH component in 2015/16. The 2015 review noted changes to component budgets and implementation plans caused by revision of DFID DRC’s overall budget in 2014/15, which imposed a reduction in annual budgets and a consequent slower pace of delivery. Since the review, no-cost extensions to the Accountable Grants with Oxfam (4 months) and the WASH Consortium (12 months) have been signed, which take into account DFID’s revised budget and partners’ delivery planning – both at a lower pace than intended at approval. Overall, our partners are on track with these revised budgets. The exception being Mercy Corps, where delays to the implementation phase scale up of staffing and activities, including key procurements for infrastructure work, resulted in a 50% underspend (£5.7m) versus the revised budget for 2015/16. A further revised budget has since been produced by Mercy Corps which incorporates these delays to their work plan, to cover delivery from 2016/17 and onwards.

Financial management
Our partners’ financial management has been strong in the last 12 months, improving since the last review and resulting in expenditure which is by and large consistent with revised budgets and work plans. All partners bar Mercy Corps have managed their expenditure in line with plans revised last year, and in Mercy Corps’ defence, the delays they have suffered are similar to those addressed by other partners following the last review. DFID DRC’s Finance Manager performed a spot check review of UNICEF and the Consortium’s financial management in Kananga, which included the Consortium’s downstream partners.

DFID DRC has worked closely with all partners on their financial reporting, who have responded positively to requests for clarifications and alterations in presentation. The investment of our partners’ time in this has been appreciable and has been key to improving financial management across the WASH programme. UNICEF have accommodated DFID’s requirements following a global change in their reporting, which has improved clarity of how UNICEF utilises funding provided. Since the last review, the Consortium have made far greater linkages between financing and results in their planning and reporting to DFID. The issue of a 50% underspend by Mercy Corps’ in 2015/16 is noted above, caused by an over-optimistic schedule in their implementation plan. Mercy Corps’ forecasting and reporting systems have otherwise been strong since the last review, featuring strong links between workplans and financial forecasts.

Date of last narrative financial report	08/04/2016
Date of last audited annual statement	02/02/2016

E: RISK

Overall Gross risk rating: Major	Overall Net risk rating: Moderate

Overview of programme risk
The programme’s overall risk rating is Major, at Gross level, mitigated to Moderate at Net level. This rating is based on the application of DFID’s new risk assessment system, composed of 6 risk areas: External Context, Delivery, Operational, Fiduciary, Safeguards and Reputational. The overall rating is an aggregate of the 6 areas, themselves a synthesis of DFID DRC’s assessment and that of partners’ and their risk matrices. The table below displays an overview of the programme’s gross and net levels of risk under each category.

Table: Overview of programme Gross and Net risks

DRC is a high risk environment for DFID to operate in. The programme’s ambition limits the available options to completely isolate it from particular areas of risk – for example, delivering in isolated/conflict affected areas or delivering sustainable results oblige engagement in contexts with inherent residual risks. That said, where possible the WASH programme by design seeks to minimise exposure to the most egregious risks. The DFID DRC WASH team seeks also to verify this assessment, as well as play its part in mitigation, though a continuous programme of field visits – prioritised according to key areas of risk. As such, the team have sought to visit Mercy Corps in Goma at least quarterly and also reached Mongala Province and Kasai Central.

While mitigation measures aim to reduce the likelihood and impact of risks materialising, it is not always possible to attenuate both aspects – such that some of the above net risks remain as likely or with the same impact as the gross risk. This is true for risks linked to the external context, where our mitigation reduces the impact from major to moderate - but risks are still likely to emerge, and delivery risks, where our mitigation reduces the likelihood – but the impact remains major.

The following is a summary of key risks and their mitigation:
- Anticipated disruption around presidential elections (intended for 2016), or their delay, present the most significant contextual risks - to mitigate which we have worked with our partners on contingency planning, which will help ensure our programmes can continue to deliver (albeit not to the full extent) in a more challenging context.
- Coordination among WASH sector stakeholders (including Government) and aspects of the Urban WASH project (infrastructure procurement, service provision) constitute the main delivery risks, to mitigate which DFID DRC continues to invest its resources in coordination and assurance. Here, our mitigation efforts have more effect on the likelihood of risks materialising, as the high risk/reward ambition of the programme inherently limits our ability to reduce the impact.
- The decision not to work directly with Government of DRC institutions helps mitigate DFID’s exposure to many fiduciary risks, as does our choice of reputable, reliable partners with proven track records for delivering in DRC.
- Our choice of partners and DFID DRC’s own continuous monitoring of delivery and due diligence follow-up action plans are key mitigating factors of risks to our Safeguards.
- Mitigation of Operational risk centres on continuing to ensure appropriate resource for the WASH team, as well as seeking opportunities to reduce the management burden of the programme.
- Maintaining a strong and collegiate relationship with the institutions of the Government of DRC which operate in the WASH sector remains our principal mitigation to a variety of reputational risks.

Outstanding actions from risk assessment
Follow up of Due Diligence action plans continues to be performed quarterly. The single high priority action outstanding at the last review was UNICEF’s procurement of third party monitoring services. Although delayed, this is now contracted and the first report anticipated imminently.

Partner’s risk matrices are also reviewed on a quarterly basis (bi-annually with UNICEF). The trend and materialisation of a particular risk is flagged and additional mitigating actions taken if necessary.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The overall programme was approved with a life of 6 years, to run from July 2013 to December 2019. Despite delays in the achievement of results against milestones in the previous year, the programme is now on track and on course to deliver its targeted objectives. As noted above, the logframe revision performed during 2015 adjusted annual milestones, taking previous delays into account and updated the trajectory of delivery. The anticipated trend in delivery is now that the programme’s component projects (with the exception of Mercy Corps) are expected to hit their stride in 2016 and deliver significant annual results until its completion – which has largely been borne out in this review.

A large part of the programme’s results are dependent on the contribution of UNICEF’s support to VEA. UNICEF has met most of its milestones for this year, exceeding a few, but has also yet to report adequately against some indicators. The revision of logframe milestones undoubtedly helped reset expectations of UNICEF’s performance this year but good progress has nonetheless been made, all the more so given delays noted in the previous review. While VEA’s post certification has now been rolled out, the initial delays are undeniable and their impact is such that there is now less time in which certified villages can be supported in follow up and the sustainability of VEA’s gains be entrenched.

The WASH Consortium project was extended in July 2015 by 12 months. The end date of the Accountable Grant is now 30 June 2018. The Consortium’s request for extension followed delays incurred and noted in the last review. Although the updated logframe took prior delays into account, as has been noted above, the Consortium was unable to achieve all its milestones for this year - in large part due to continuing difficulties of one Consortium member organisation and despite efforts by other Consortium members to compensate by taking on a larger share of planned results.

The last review also noted delays incurred by Oxfam and the prospect of extensions to allow for a proper conclusion of the Sanitation Marketing Pilot. The revised end date of the pilot, extended at no-cost, is 30 June 2016. At the time of writing, DFID and Oxfam are in discussion about the end of the pilot phase and the shape of a successor to it.

Having started implementation later than other components and necessitating the completion of infrastructure work before yielding key access to water results, the bulk of Mercy Corps’ Urban WASH results are anticipated at the end of the programme – in 2018 and 2019. Within the year under review, Mercy Corps has fallen behind its initial timeline by up to 6 months. Despite these delays, they have completed a large part of planned recruitments, set up their presence in Bukavu and have also contracted engineering consultants for design and construction supervision work, with an effective start in January 2016. All of which are key steps to enabling the next phases of the programme. The delays in the procurement of Engineering Consultants were due to extended review and approval processes (partly due to DFID’s scrutiny) as well as protracted contract negotiations. Learning lessons from the previous procurement, and otherwise ensuring Mercy Corps do all they can to ensure a successful and timely procurement of civil works, continues to be a focus for DFID’s management of the programme.

Performance of partnership (s)
DFID DRC works closely with its partners and seeks to maximise lesson learning across programmes, an approach which is applicable within the WASH programme as much as across the DFID DRC Office. The WASH team holds meetings with each partner at least quarterly and face to face as often as possible. Our close working and regular contact with partners mean that we are heavily invested in the management of the programme and are equipped with the necessary knowledge to make intelligent, risk based decisions.

Partnerships amongst stakeholders implementing the programme are working well, as observed during the joint field visit for this Annual Review. Although not a direct DFID partner, the Ministry of Health has continued to provide leadership for the implementation of the programme and communities across DRC continue to participate in the programme’s implementation.

The Business Case required a review of progress in January 2016 against planned results under UNICEF’s “moderate case” for VEA. This was deferred to March 2016 due to changes in reporting timelines, when UNICEF were scheduled to submit their narrative report. DFID DRC has performed the review against the moderate case, which has shown that the programme has reached the moderate case scenario and is in gear to continue delivering at that pace.

DFID has continued the efforts made last year to convene and encourage lesson learning across the programme’s components. Joint visits with UNICEF and the WASH Consortium, also including the Director of the National VEA programme and IMA (delivery partner on DFID DRC’s Health programme) have contributed to a better mutual understanding among rural WASH partners and a platform for further cross-pollination of ideas and methodology. Furthermore, DFID’s hosting of three separate WASH sector learning events, coupled with the two hosted by the WASH Consortium, have throughout the year united representatives from across the sector, including donors and implementers, forging a more connected community of practice in DRC. This has gone beyond DFID DRC’s immediate partners to include sessions led by GiZ (German Corporation for International Cooperation) on the new water law and Tearfund (who implement a centrally managed DFID WASH programme in DRC) on payment by results.

Asset monitoring and control
DFID is confident in its partners’ ability to appropriately manage programme assets but performs regular checks on stocks and systems. Issues are reported to DFID and dealt with through DFID’s Counter Fraud Unit where appropriate. Partners each have their own standard operating practices on the management of assets, reviewed by DFID’s due diligence assessments. The Consortium, Mercy Corps and Oxfam are required by DFID to provide updated asset lists to DFID, in line with their regular reporting requirements. DFID conduct asset checks of each partner during every field visit, including Health Zones supported by UNICEF.

G: CONDITIONALITY

N/A

H: MONITORING & EVALUATION

Evidence and evaluation
On sustainability in VEA, the evidence baseline remains the sustainability survey of 2013 which showed that only 2% of villages fully maintained the norms after certification. Post-certification data now included in the VEA database shows that only 6% of villages maintain all 7 VEA norms, which is consistent with the findings of the sustainability study. Data following the second post-certification visit, after a community action plan has been devised and catch-up activities have taken place, shows a more promising trend with 91% of villages regaining their healthy status.

Source: UNICEF report on VEA.

UNICEF is launching a series of operational research and studies on different topics, including:
- A study assessing the effectiveness, coherence and efficiency of post-certification processes (i.e. rattrapage processes).
- Value for money study
- The role of decentralised authorities in VEA
- VEA in endemic cholera areas
- Water safety plans

Over the last period, the VEA UNICEF team has undertaken a bottleneck analysis in order to identify priority actions for the monitoring and evaluation systems of the healthy villages programme. There is now support from a database professional on the DHIS2 database for more technical issues. The aim being that the quality of the data input is constantly improving, but also to ensure that the new information generated on post-certification is entered into the database with the same level of quality across the provinces. In the following year, and due to poor internet access in rural areas, but high mobile coverage, the programme will explore the compatibility of mobile technology for data collection and transmission in order to reduce risk of errors in paper data transmission and input.

Third party monitoring is now underway, and will report monthly at provincial level and quarterly at national level on a number of subjects: strategic planning, operational management, achievement and maintaining results, collaboration and coordination with local actors, management capacity and more. There were some issues with the online data collection and analysis tool, which meant that a new service provider is being sought. This has not delayed the data collection process at local level, but may impact on the initial timeliness of the analysis of the results.

Impact evaluation:
DFID DRC has commissioned an evaluability study to help define how and what the evaluation should cover. Several meetings have already been held with the UNICEF team, in order to discuss research questions and governance arrangements. These will be picked up once the evaluability study has given its results.

Although procuring the impact evaluation has been delayed, for reasons explained in the previous annual review, and that have remained, it is still possible to conduct an impact evaluation. The evaluability study will inform on what type of evaluation is possible to carry out. Next steps will include finalising terms of reference and setting up a steering committee.

Monitoring progress throughout the review period
DFID DRC have conducted the following monitoring visits since the last review:
- July 2015 – Goma (Mercy Corps)
- August 2015 – Goma (Mercy Corps)
- September 2015 – Nord Ubangi and Mongala (UNICEF, Oxfam and IMA)
- November 2015 – Goma (Mercy Corps)
- December 2015 – Kasai Central (UNICEF, Consortium, IMA)
- December 2015 – Kinshasa (UNICEF)
- February 2016 – Goma and Bukavu (Mercy Corps)
- April 2016 – Kasai Central (UNICEF, Consortium, IMA)

The DFID DRC WASH team seek to ensure a minimum of 1 field visit per quarter and target particular partners and locations according to risk, as well as seeking synergies with other programmes’ field trips (for example the DFID DRC Health programme delivered by IMA). Each field visit has bespoke terms of reference but each seeks to ensure meetings of the DFID team with beneficiaries, implementing partners and key stakeholders. Mott MacDonald, as technical advisers to DFID on Urban WASH, have also carried out four quarterly missions over the last year, in accordance with their contract.

Given the sensitive phase of the Urban WASH programme in Goma and Bukavu, this has been, and is likely to continue to be, a focus of the team’s field trips in the last 12 months. As noted, the team’s ability to access all areas of the programme’s coverage is limited by the context of DRC and the resources available, although this also serves as an imperative to reach the areas less travelled – to understand the context of remote operation as well as perform asset and other process checks in these areas.

Added to the above visits by the DFID WASH programme team were three separate visits to Goma and Kasai by PUSS Hurd, the Independent Commission for Aid Impact (ICAI) and DFID’s Director for West and Central Africa. Each visitor met beneficiaries, delivery partners and stakeholders.

Review team
This review was conducted by the DFID DRC WASH team with the support of DFID Malawi’s WASH advisor on the rural components of the programme, Mott MacDonald on the Urban WASH component and DFID DRC’s Finance Manager on partners’ financial management and asset monitoring and control.
ANNEX A – Recommendations issuing from the 2016 review

1. General
  1. UNICEF to encourage the Ministry of Health and the VEA coordination unit to train officials that are newly appointed and new to the programme.
  2. Step-up and continue the post certification activities in the VEA programme to ensure that villages which lose their “Healthy” (Assaini) certification are supported to regain it, to maximise the programme impact.
  3. UNICEF and the WASH Consortium to develop strong research products of the programme, to capitalise on what is being done in the programme to inform DRC’s WASH sector and continue exchanges of best practices and lessons learnt on the programme.
  4. The Business Case provided for the urban component of the programme to reach 3 towns in eastern DRC, yet DFID has to date only approved implementation in two: Goma and Bukavu. Whether the programme does include a third town, or how the funds are reassigned to Goma and Bukavu, should be resolved with Mercy Corps by the end of summer 2016 in order to avoid causing further delays to implementation.
  5. The procurement by Mercy Corps of an international contractor for civil works on Urban WASH is a high priority for the next year of the programme. Further delays to this procurement are likely to engender delays to the achievement of access to water results by this component. DFID, Mercy Corps and DFID’s technical Advisers Mott MacDonald must focus on ensuring that this procurement takes place on time and to a high enough standard as to contract an appropriate supplier. This procurement should be launched and completed within the next 12 months.
  6. Amid the ongoing political and legislative changes to the water sector, Mercy Corps must define a sustainable business model and administration structure for the management of the water networks to be built and expanded by the programme in Goma and Bukavu. This is currently anticipated to be done by the end of 2016.
  7. DFID must finalise a decision on whether or not to scale up the sanitation marketing component with Oxfam, and ensure sector learning takes place.
  8. DFID to work with UNICEF on design of the impact evaluation on the VEA programme, with a goal of contracting an evaluation within the next 12 months.
2. Output 1
  1. The quality of locally made latrines for households in rural areas is generally poor, notwithstanding an observed tendency for those under the Consortium to be better than VEA’s, and significant barriers to improved materials exist due to distance as well as lack of income generation. Both VEA and WASH Consortium’s programmes do not market sanitation products. Oxfam should prioritise transferring relevant lessons from the sanitation marketing component to UNICEF and the Consortium during the next period.
  2. There are still different policies and practices with regards to the subsidy of sanitation materials on both rural programmes, VEA and WASH Consortium. Over the longer term, a policy on subsidies should be developed by VEA (the government and UNICEF), taking into account that subsidies might be better placed in a sanitation marketing approach, rather than as a direct subsidy to households through the provision of slabs, as is currently the practice.
  3. Post certification is well under way now, with 1,483 villages having received a post-certification visit, which represents 42% of villages certified in phase 1 of VEA. DFID should continue to monitor post certification results closely and encourage its continued roll out, including to phase 2 villages, in order to grow the sample of results and provide stronger confirmation that post certification is proving successful.
  4. UNICEF should disaggregate VEA post-certification data for villages certified under Phase 1 or 2, in order to start understanding whether the changes brought into Phase 2 actually foster sustainability.
  5. The WASH Consortium should assess their care group approach to understand how important the determinants analysis was in the uptake of positive behaviours and share lessons from the approach with VEA.
  6. Previous recommendations made on the systematic review of evidence still hold. A literature review could be conducted by UNICEF, the WASH Consortium or DFID 10% Advisory input to complement some of the monitoring data that is coming out of the programme, with the aim of building the evidence base generated by the programme.
3. Output 2
  1. The rural components, UNICEF and the Consortium, should reinforce their respective efforts to support the capacity of local suppliers and service providers , to increase local capacity to deliver WASH services to communities including, where possible, supply of spare parts for water points. In the absence of a national strategy on rural water supplies and supply chains, the work that Vergnet is undertaking, as well as the handpump supply chain work done by the WASH consortium should continue. UNICEF should carry out a feasibility analysis for procuring pumps locally.
  2. Documentation and keeping of records including collection and processing of data for the VEA programme still remains a challenge. Therefore, UNICEF should consider how to increase or supplement their existing capacity building for data collection and management at all levels of the Ministry of Health involved in implementation of the VEA programme.
  3. External support is required for the water management committees after certification of the villages to ensure the sustainability of the interventions. The programme should continue exploring the length of time required for the support.
  4. Both the UNICEF and the WASH Consortium logframe should mirror the need to respectively integrate and feed into the national database of the healthy villages and schools programme.
  5. The sanitation marketing component has delivered a number of interesting knowledge products, and events should continue to advertise these, whilst following up on the take up of sanitation products in the town of Gemena.
  6. Revise logframe milestones for indicator 2.4 to provide realistic and achievable targets which are up to date with current expectations of villages in post certification.
4. Output 3
  1. A number of recommendations were made by the UNICEF/Oxfam GB gender study on healthy villages and schools. In the coming months, UNICEF and the WASH Consortium should consider how to integrate them into the programme and ensure that they are tracked as part of the recommendations matrix. An action plan should be in place within 6 months and activities underway by the time of the next review.
  2. Also in response to the Gender study, UNICEF and the WASH Consortium to each consider appointing gender leads within their programmes. A decision to be taken within 6 months – in line with broader discussions on how to take gender forwards.
  3. DFID to secure input from a Social Development Adviser or Gender Lead to ensure that DFID is learning as much as it can from the urban WASH programme’s approach to gender.
  4. UNICEF and the WASH Consortium should ensure that the results and lessons learnt in the implementation of the programme at the community level should be documented to influence and inform policy dialogue amongst sector stakeholders.
  5. UNICEF and the Ministry of Health should include a split in responsibilities for certification of villages and supporting villages towards certification assessment in their considerations of a likely phase 3 of VEA. At the moment, the health authorities both implement and certify the villages as healthy. Although these responsibilities are split between different individuals, the certification process would benefit from being done by a more independent actor. This of course has a cost, and in a country where the presence of other government departments is limited, poses a particular challenge. This should however be noted and taken into consideration in future.
  6. Partners should ensure that the principles of equity in access to water and sanitation services are an integral part of the water committee’s role together with the recovery of funds for maintenance and operation.
5. Output 4
  1. VEA and the WASH Consortium should look at the relative costs and benefits of improving springs, including the improvement in water quality in order to ensure that wherever possible, there is a reduction in distances for girls, boys and women for the collection of the water.
  2. Given apparent differences in the quality of latrines built under the rural components, VEA and the WASH Consortium, the Consortium should ensure its assessment of norms mirrors that of UNICEF, to ensure parity in certification. The Consortium should equally consider how to demonstrate what the approach might add to the chances of bringing about a more lasting change and what it can offer to the national VEA programme’s methodology.
  3. The life cycle approach adapted in the WASH Consortium programme should be documented and shared, in order to see whether it has the potential of working at scale. It is an intensive approach, but is possibly an important enabler of sustainability. It is still too early to really tell whether this is the case but the Consortium should assess its particular impact and share any lessons arising for VEA and the broader WASH sector.
  4. UNICEF and the WASH Consortium ensure that messages around payment for water and equity of access are understood by the entire community. It is not sufficient to assume that a community will look out for the vulnerable people, equitable access to water must be entirely thought through, communicated and monitored effectively.
6. Output 5
  1. Continued engagement by the donor group with key ministries in the sector, including the ministry of plan and the CNAEA/CNAHEA to support sector coordination initiatives.
  2. In the medium to long term, donor coordination should aim to support Government in coming-up with a rural sector programme that is supported and implemented by all stakeholders.
  3. There currently seems to be limited opportunity to engage positively with central government on coordination and planning and the overall situation for coordination is not following a positive trend. The components should continue to focus on provincial and decentralised coordination and planning, where authorities are present on field visits and seem to be better engaged in the programmes.
  4. The VEA database is potentially a very powerful tool, especially since it is aligned with the national health information system and should ensure compatibility for data analysis. This could be used to refine some of the impact data, some of which can already be used in the verification of self-reported diarrhoeal disease results.
Annex B – Logframe changes in 2015-16
Outcome	Improved and sustainable WASH services are available for 3,755,000 Congolese men and women through support to government, civil society and communities
Indicator	Old indicator		New indicator		Rationale for change
1	Time saved by women and girls on collecting drinking water		Number of people collecting water from an improved source within a 30 minute round trip		Changed DFID indicator to align with DHS and improve measurability. Previous DFID indicator hard to measure - partners’ measurement of time savings differed. New indicator is easier to measure and is aligned with Demographic Health Survey (DHS) data under section 2.1.1 Household water utilisation.
	New milestone and targets
	Baseline	2015/16		2016/17		2017/18	2018/19
	41.3% of population	330,400		660,800		1,115,100	1,550,815
	Rationale for revisions to milestones
	New milestones and targets follow DHS 2013 statistic of people gathering water within 30 minute round trip (41.3% of combined rural and urban population), applied to programme’s targets for access to clean drinking water (Output 4.1). Basing these milestones on the revised targets for access to water ensures they are adjusted to the most realistic results forecast, where results are now distributed more significantly into the final two years of the programme. Although the programme aims to provide water to as many beneficiaries as possible within a 30 minute round trip, in rural areas this may not always be possible due to the terrain, but also the approach of the programme. In urban areas, a 30 minute round trip will not take into account queuing time. We feel that using the national average from the DHS is our best proxy to account for the context and provide realistic and achievable milestones and target.
2	Number of households in urban areas with cost-savings on the purchase of water		% of Households in target area using service provider managed tap-stands.		Changed DFID indicator to improve relevance and reflect Mercy Corps' monitoring. Old indicator assumed cost savings for all users of DFID supported programme but previous users of un-improved water sources may see increased costs of access to now improved water sources. New indicator measures user adoption of newly available improved water sources, into which are factored cost considerations.
	New milestone and targets
	Baseline	2015/16		2016/17		2017/18	2018/19
	Goma: 64% / Bukavu: 0%	Goma: 64% / Bukavu: 0%		Goma: 64% / Bukavu: 0%		Goma: 75% / Bukavu: 30%	Goma: 80% / Bukavu: 60%
	Rationale for revisions to milestones
	New milestones and targets follow Mercy Corps’ revised delivery schedule, which features redistribution of results to the two final years due the procurement of infrastructure work – only expected to provide new access to water from 2017. Lower than universal usage of tap-stand water is anticipated given alternative (if unsafe) options for water and unavoidable (if minimised) cost barriers.
3	Number of men and women who reported a reduction in sick days per year		None –indicator deleted.		Indicator deleted as difficult to measure through regular monitoring and would incur additional cost, which does not seem justified, because the Impact already measures reduction in diarrhoeal disease in children. Partners were collecting data on child morbidity rates for impact 1, but not for adults'. Reductions in sick days were also considered to be hard to robustly measure without accessing Health Zone data, and then difficult to attribute trends in overall sick days to a prevalence of diarrhoeal related sick days..

Output 1	Individuals and communities are incentivised to deliver lasting behaviour change
Indicator	Old indicator			New indicator				Rationale for change
1.1	Number of men and women with access to improved hygiene			No change				No change to indicator definition.
	New milestone and targets
	*Achieved	2014/15			2015/16				2016/17			2017/18			2018/19
	Old	800,000			1,300,000				1,600,000			3,000,000			3,000,000
	New	773,752*			900,000				1,200,000			2,600,000			3,000,000
	Rationale for revisions to milestones
	Delays to delivery were noted in the 2015 AR, which were compounded by the need to adjust programme delivery for the government of DRC implementing decentralisation laws and breaking down the 11 Provinces into 26 (‘decoupage’ in French). Partners’ reporting schedules are such that previous results were not fully achieved but included estimates. The new milestones are adjusted to count only achieved results as well as taking delays into account.
1.2.1	Number of men and women who know the transmission chain of water-borne diseases			No change				This indicator and the other 2 sub indicators have been split for clarity and improved reporting of results.
	New milestone and targets
		2015/16				2016/17				2017/18			2018/19
	Old	1,300,000				1,600,000				3,000,000			3,000,000
	New	630,000				840,000				1,820,000			2,100,000
	Rationale for revisions to milestones
	Evidence from current programming suggests interventions can expect to result in 70% of target population knowing about the transmission of water-borne diseases. Milestones and Target are taken as 70% of total population reached (Output 1.1).
1.2.2	Number of people in households with soap or ash and water at a handwashing station near the latrine			No change				This indicator and the other 2 sub indicators have been split for clarity and improved reporting of results.
	New milestone and targets
			2015/16				2016/17				2017/18			2018/19
	Old		1,300,000				1,600,000				3,000,000			3,000,000
	New		360,000				480,000				1,040,000			1,200,000
	Rationale for revisions to milestones
	Sector wide evidence suggests interventions can expect to result in 40% of target population to have soap or ash for handwashing. Milestones and Target are taken as 40% of total population reached (Output 1.1).
1.2.3	Number of males and females, boys and girls who demonstrate correct hand washing behaviour with soap/ash			No change				This indicator and the other 2 sub indicators have been split for clarity and improved reporting of results.
	New milestone and targets
			2015/16				2016/17				2017/18			2018/19
	Old		1,300,000				1,600,000				3,000,000			3,000,000
	New		540,000				720,000				1,560,000			1,800,000
	Rationale for revisions to milestones
	Evidence from programmes suggests interventions can expect to result in 60% of target population to be able to correctly demonstrate handwashing. Milestones and Target are taken as 60% of total population reached (Output 1.1).
1.3	Number and % of people living in villages that have maintained or regained their certification.			Percentage of villages that have maintained or regained their certification after 24 months.				Indicator simplified and clarified. No change to milestones. Maintenance of certification after 24 months in post-certification, measured by the 2nd post-certification visit, clarifies how this indicator is measured by both VEA and the WASH Consortium.
1.4	% of communities undertaking monthly actions for the improvement of their living environment			None –indicator deleted.				Indicator removed. Both UNICEF and Consortium base their indicators on the VEA norm of whether a village is observed to be clean at least once a month by the community. As the number of villages observed to be clean will differ little from the data for indicator 1.1 (number of certified villages & their total population), this indicator would be largely redundant.

Output 2	A network of local actors exists which is capable of meeting the demands for the implementation and monitoring of the delivery of WASH services
Indicator	Old indicator		New indicator		Rationale for change
2.3	Number of visits per month to WASH infrastructure and community institutions at village level by zone de santé staff which are documented correctly.		Percentage of planned stakeholder trainings completed		New indicator will better report on aspects of the Output within the programme's control. New indicator measures training of stakeholders (government, NGOs and private sector) in WASH and programme methodology. Consortium data will incorporated into the indicator, alongside UNICEF’s, at a later date.
2.4	Number of committees or user/management units/groups set up per water point.		Number of water points established which are managed by a committee or user management group after 24 months of certification.		New indicator to replace previous, in order to better measure sustainability. Previous indicator target was for 1 committee to be established per water point, which has been so thoroughly integrated by the programme methodology that no water point will be improved/constructed without the prior establishment of a committee. Reporting could therefore only ever be 100% of target. / The new indicator monitors persistence of water committees, found to be a crucial factor in sustainability of WASH behaviours. This is out of the direct control of the programme, but much more useful and relevant to the output.
	New milestone and targets
		2015/16		2016/17		2017/18	2018/19
	New	1,533		2,418		3,338	3,338
	Rationale for revisions to milestones
	Milestone and targets are set at 80% of the planned cumulative target for the establishment of water committees. The target is ambitious, given experience of the longevity of water committees, but is crucial to the programme’s approach to sustainability.

Output 3	Communities – members and community representatives – service providers and government (local & provincial) own, and are held accountable for, the delivery of WASH services
Indicator	Old indicator				New indicator				Rationale for change
3.1	% of population [measured by households] satisfied with water management committee performance				No change				No change to indicator definition.
	New milestone and targets
			2015/16				2016/17					2017/18			2018/19
	Old		70%				80%					80%			80%
	New		60%				60%					60%			60%
	Rationale for revisions to milestones
	Milestones revised as original targets likely to be unrealistic. The partner’s monitoring tools record respondents’ satisfaction with 100% of the role of the committee, which is unlikely.
3.2	Percentage of women on water committees				Percentage of committee members who are female				Rewording of indicator for clarity.
	New milestone and targets
	*Achieved	2014/15				2015/16				2016/17			2017/18			2018/19
	Old	50%				50%				50%			50%			50%
	New	*38%				30%				30%			40%			50%
	Rationale for revisions to milestones
	Milestones revised down in accordance from the evidence generated so far on the projects, which are more realistic and achievable. Given the context of DRC and experience to date, 50% female membership of water committees is unlikely to be achievable immediately. 50% female membership remains the programme’s ambition.
3.3	Percentage of Zone de Sante who are assessed as functioning “well” or “very well” in organisational, technical and response capacity assessment				No change				No change to indicator definition.
	New milestone and targets
				2015/16				2016/17			2017/18			2018/19
	New			30%				40%			60%			60%
	Rationale for revisions to milestones
	Milestones have been set from 2015/16. These may be revised again if UNICEF data can be added (dependent on 3PM monitoring) and depending on the Consortium’s own revisions.

Output 4	Increased access to affordable and improved water and sanitation for 3,755,000 million men and women
Indicator	Old indicator		New indicator		Rationale for change
4.1	Number of men and women with access to a clean drinking water source (reported usage)		No change		No change to indicator definition.
	New milestone and targets
	*Achieved	2014/15		2015/16		2016/17	2017/18	2018/19
	Old	800,000		1,600,000		1,950,000	3,755,000	3,755,000
	New	*609,358		800,000		1,600,000	2,700,000	3,755,000
	Rationale for revisions to milestones
	This indicator was recorded as off-track in the 2015 AR, due to delays in implementation linked to context and internal DFID annual budget changes. The revised milestones account for delays to delivery noted in the AR, revised reporting schedules which ensure reporting of achieved results (not estimates), and reflect Mercy Corps’ implementation plans for water infrastructure in Goma and Bukavu, where the bulk of their results will be provided in the final 2 years of the programme.
4.2	Number of men and women with access to an improved sanitation facility at the household level		No change		No change to indicator definition.
	New milestone and targets
	*Achieved	2014/15		2015/16		2016/17	2017/18	2018/19
	Old	700,000		1,300,000		1,600,000	2,500,000	2,500,000
	New	*897,018		1,100,000		1,600,000	2,100,000	2,500,000
	Rationale for revisions to milestones
	Although on track in the 2015 AR, the delays felt more acutely in other areas have also impacted the pipeline of sanitation results, so we advise modestly reducing the present milestones. The new schedule is in line with partners’ delivery planning and should be achievable.
4.3	Number of households who collect at least 15 litres per person per day of potable water from safe water sources		No change		No change to indicator definition.
	New milestone and targets
	*Achieved	2014/15		2015/16		2016/17	2017/18	2018/19
	Old	143,348		303,256		513,961	522,506	522,506
	New	*47,976		67,126		92,229	100,103	102,720
	Rationale for revisions to milestones
	Incorporation of Mercy Corps’ data and adjustment for updated delivery plans. UNICEF have to date been unable to report on this indicator due to shortcomings in VEA’s monitoring system and delays to the procurement of a third party monitoring supplier, who are intended to complement the information gathered through the National programme. Our ambition remains to include UNICEF results at a later date, when they are reported, but in the short term it is more useful to monitor the results which are being captured. The milestones and target from 2015/16 are now based on Consortium data, with the inclusion of Mercy Corps’, while the milestone for 2014/15 had included UNICEF and was hence higher. UNICEF may be added at a later stage (after AR 2016).

Output 5	Improved capacity of national government to coordinate, monitor and set appropriate priorities in the WASH sector
Indicator	Old indicator		New indicator		Rationale for change
5.1	Number of Provinces implementing 5 year VEA plans and 2 year action plans		No change		No change to indicator definition.
	New milestone and targets
	*Achieved	2014/15		2015/16		2016/17	2017/18	2018/19
	Old	11		11		11	11	11
	New	*11		22		22	22	22
	Rationale for revisions to milestones
	Updating results to account for new number of post-decentralisation division of provinces from 11 to 26. The VEA programme is only operational in 22 out of the 26 Provinces.