Annual Review – Summary Sheet

Title: Reducing Maternal and Newborn Deaths in Kenya 2013–2019
Programme value: £79.8 million		Review date: November 2016
Programme code: 202549	Start date: 14 November 2013	End date: 31 March 2020

Summary of programme performance
Year	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19
Programme score	B	A	B
Risk rating	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review
The maternal and newborn health (MNH) programme began in November 2013 and is due to finish in March 2020. It is a fairly complex programme because it covers a number of components and has several partners. The key components of the programme include; scale-up of training for health workers in emergency obstetric and neonatal care (EmONC) in 32 counties; health systems strengthening (HSS), demand-side[1] financing (DSF) and implementation of a County Innovation Challenge Fund (CICF) to support testing and scale-up of innovative MNH approaches in six counties; an evaluation component to assess the impact of the programme; and a component focused on improving health infrastructure through green energy solutions. The implementing partners are the UN Children’s Fund (UNICEF), Marie Stopes International (MSI)/ Options Consultancy Services (referred to throughout as Options) and the Liverpool School of Tropical Medicine (LSTM). The programme has a break point in 2017 which provides an opportunity to review its complexity and to simplify its management by redefining the role of different partners.
[1] Addressing financial barriers, such as transport, which limit poor women’s access to maternal and newborn health services

Progress against the outcome measure of increased access to and utilisation of quality MNH services is mixed, although overall progress is in the right direction. Against output milestones the programme has made good progress on the training of health workers on EmONC and is helping to strengthen these services with a focus on continuous quality improvement. Progress in increasing demand for MNH services and on HSS, in particular human resources for health (HRH), has been slower.

There is good progress against some components which fell below target in 2015 and which were subjected to a performance improvement plan. These include targets on trainings, quality improvement, maternal and perinatal death surveillance and response, demand side financing, slow pace of contracting and delivery by UNICEF. LSTM has accelerated progress on trainings and quality improvement, despite challenges on indirect trainings as discussed in sections below. UNICEF has made progress in contracting partners to accelerate work on health systems strengthening and demand side financing, which were off track, but this is yet to translate into results. For UNICEF, progress remains slow and requires acceleration to achieve the target milestones within the timeframe of the current contract. The programme management oversight function provided by UNICEF is only partly functioning.

Contextual and political risks around low and slow domestic financing presents risks to sustaining the gains made. Maternity services are now free at the point of service, with reimbursements from the Government of Kenya (GoK), but ensuring timely reimbursements to health facilities remains a key challenge. Kenya ambitiously devolved responsibility for financing and delivery of health services to 47 counties. There are considerable delivery challenges at national and county level, notably around planning, budgeting and human resources (most notably staff shortages).

Programme achievements:

Performance against outcomes
Performance against the six programme outcome indicator is mixed, but overall trajectory of progress is on track. There is good progress against three outcome indicators on skilled birth attendance (SBA) rate, additional births delivered by a skilled birth attendant and obstetric case fatality rate (i.e. % of women with obstetric complications admitted to a facility who die). Notable achievement is in Garissa County with the the proportion of women delivering with the help of a skilled health worker increasing to 45% in 2016 compared to 28% in 2013. The target on skilled birth attendance for 2016 has been suprassed, but we also note that the ambition on this target was lowered after the 2015 annual review due to significant changes in the implementation context. The progess on skilled birth attendance is in line with the general improvement noted in Kenya, with skilled birth attendance improving from from 44% in 2008 to 61% in 2014. The proportion of women with obstetric complications admitted to a facility who die has reduced from 2.9% in 2012 to 2.7% in 2016 and is below 2% in all the programme counties, except in Bungoma. The underperfomance in Bungoma is attributed to temporary closure of the operating theatre at the County Referral Hospital for refurbishment.

Performance against three other outcome indicators is mixed. The programme has achieved the target on functioning health facilities able to provide Basic EmONC in four counties and Comprehensive EmONC in three out of six counties for 2016. Despite the general progress on this indicator, delivery is significantly dependent on close monitoring and mitigation of contextual and political risks around devolution and GoK resource allocation for health. Performance against the outcome indicators on caesarean section (CS) rate (i.e. % live births delivered by CS in the population) and still birth rate is slightly offtrack. The 2016 target for CS rate has been achieved nationally and in two counties, but is offtrack in four counties. The national still birth rate has reduced from 3.9 in 2013 to 2.5 in 2016, surpassing the 2016 milestone of 2.7. There is however limited improvement at county level, with only two out of the six Counties recording significant improvement. The overall trajectory is however positive to achieve the targets by the end of the programme, with accelerated progress on MPDSR.

Outputs
Output 1 – Health workers have the knowledge and skills to provide quality care and EmONC: The programme is making good progress in providing in-service training. Follow-up mentoring to embed best practices and skills training is well underway, but not for all trainees. There is progress against targets set for reporting of maternal and perinatal deaths, and learning from maternal and perinatal death surveillance and response (MPDSR). That said, reporting of perinatal deaths remains a significant challenge, with varying capacities in reporting.

Output 2 – Health systems strengthened to manage and deliver MNH services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties: Progress against milestones has been mixed. Strong management of the CICF continues. Another six projects have been selected for funding, bringing the total to 12 and meeting milestone targets for 2016. Implementation of HSS in Bungoma is on track. UNICEF is providing good support to policy and guidelines development and quality of care, with scale-up of initiatives such as Kangaroo Mother Care and community strategy. However, the systematic approaches to HSS applied by UNICEF is relatively weak.

Output 3 – Increased demand for maternal health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties: The last review noted slow progress on this output but some progress has been made since then. Most notably, for UNICEF, PwC has been contracted to address demand side financing. However, work is yet to start in full and the programme is in its third year. In Bungoma, Options is on track to meet the financing targets for 2016 on transport vouchers.

An evaluation component with three retrospective studies is planned to assess programme impact. UNICEF’s evaluation partner, HERA, has completed a detailed inception report and evaluation plan (2016–2018). Plans are on track with an ‘Assessment on the Maternal and Perinatal Death Reporting System’ complete and data collection is underway in all five counties. The introduction of energy-efficient and environmentally friendly health systems is underway, with resource audits (energy, water and sanitation) completed for 210 health facilities in the six programme counties.

Summary of lessons learnt: More consideration should have been given to synergy and enhanced sustainability, learning and equity as partners deliver this programme (e.g. by focusing on pre-service EmONC training, thematic learning events and evaluation to ensure the programme always reaches the poorest and most vulnerable within communities. The management function and coordination of the programme is not fully functional as originally envisaged, with programme components still operating largely as single independent projects, and this impacts on reporting and M&E. The oversight and coordination function is with UNICEF, who are also implementing a large component of the programme with many sub-partners. There is a need to review the efficiency of the current coordinating mechanisms and to implement more effective mechanisms which enhance synergy within the programme.

Summary of recommendations for 2016 (DFID and partners):
What	Who	When
Review the current oversight and coordination mechanism and consider opportunities for strengthening the current UNICEF-led coordination function and explore additional mechanisms to enhance synergy	DFID	January / 2017
Consider the changing donor context, ensuring a good strategic fit with other DFID programmes, such as those with a reproductive, child health and nutrition and geographic focus (e.g. in north-eastern Kenya) and consider opportunities for strengthening the programme to deliver results in its remaining period, as well as options for succession plans.	DFID	January / 2017
Improve M&E and tracking of value for money (VfM) and other indicators and ensure the programme focuses on reaching the most vulnerable populations. Some key aspects include: (i) aligning VfM monitoring for the programme with VfM indicators proposed by the independent evaluation; (ii) a joint VfM workshop to embed VfM practices; (iii) exploring opportunities for potential cost savings for indirect costs; and (iv) Options and UNICEF to provide more details to fully assess the cost structure and overall efficiency of these components.	DFID	January / 2017
Improve synergy, learning and enquiry to augment change; the programme is lacking depth here. Improve how this learning shapes the programme and draw lessons from it that can be used within Kenya and more widely by DFID.	Options / UNICEF/ / LSTM	Dec / 2016
Continue the performance improvement measures for UNICEF on HSS and demand sde financing to accelerate programme	UNICEF	Nov 2017
Update the log frame with indicators for pre-service training, performance based financing and green energy solutions; review weighting for output two in relation to output one and three; review milestones on HSS to accurately reflect the work that is being done on HSS; clarify roles on MPDSR for all partners and include national level indicators on MPDSR	DFID/UNICEF/Options/LSTM	February 2017
In parallel with the CICF extension, consider the options for extending the Bungoma MNH component to the programme period	DFID	February2017

A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4264533.odt
DevTracker Link to Logframe:	http://iati.dfid.gov.uk/iati_documents/4264580.xls

Kenyan country context. Maternal mortality ratio dopped by 44% globally to 216 per 100,000 live births, over the last 25 years[2]. Kenya is among eighteen countries in sub-saharan Africa with the highest maternal mortality. Maternal mortality remains high (360/100,000) in Kenya and represents 14% of all deaths among women between the ages of 15 and 49 (Kenyan Demographic Health Survey (DHS), 2014). Neonatal deaths have been slow to decline (with 22 deaths per 1,000 live births in 2014 (DHS, 2014), down from 31 in 2008/09 and 33 in 2003). Socioeconomic inequities in coverage of MNH services remain, between the poorest and richest quintiles (DHS, 2014). Health system challenges include shortages of health workers, equipment and supplies, and weak referral systems. Financial, cultural and geographical barriers, including long distances and lack of transport to facilities, limit uptake of maternal health services.
[2] WHO, 2015, Trends in Maternal Mortality: 1990 to 2015

The UK government, through the MNH programme, is addressing these issues by providing support to four key areas:
1. Scale-up of training for health workers in EmONC. This training in 32 counties complements the centrally DFID-funded Making it Happen (MiH) programme (implemented in Kenya’s other 15 counties), thus achieving national coverage. Implemented through LSTM. Budget: £9.318 million for in-service training and from July 2016 an additional £0.999 million for pre-service training.
2. HSS and DSF in Homa Bay, Nairobi, Garissa, Kakamega and Turkana. National-level HSS for MNH and provision for oversight management function for the whole programme by UNICEF Kenya. Budget: £32.2 million.
3. HSS and DSF in Bungoma and implementation of the CICF in all six programme counties. Implemented by Options. Budget: £29.3 million.
4. Evaluation component. Implemented by HERA. A total of £4.1 million is allocated to operational research, monitoring, independent review, evaluation and contingency. In 2015, DFID allocated an additional £4.5 million to integrate climate change interventions.

The impact of the programme is reduced maternal and neonatal mortality in Kenya. The programme is expected to contribute to preventing 1,092 maternal and 3,836 neonatal deaths by 2018. The expected outcome is increased access to and utilisation of quality MNH services. The programme is designed to contribute to DFID Kenya’s commitment to provide skilled birth attendance to an additional 77,968 mothers by the end of 2018. It complements other areas of DFID health sector support in Kenya, including the Kenya Health Programme, which provides health policy and systems strengthening support at national level. Overall, the programme and the theory of change remain relevant.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The programme has six outcome indicators with mixed performance, but the trajectory of progress is in the right direction overall. Progress is shown below.

Performance against outcomes
	Baseline 2013	Milestone 2016	Progress	Comments
Outcome Indicator 1: Skilled birth attendance (SBA) rate
National	51%	65%	58%	In Turkana, the milestone indicator is set too low (lower than baseline). / *Milestones and data for Nairobi sub-counties of over 100% demonstrate weakness in population data, particularly the denominator in Nairobi County. This is probably because of unregistered populations in urban settlements and is compounded by the fact that these sub-counties host the largest referral hospitals in Kenya attending to clients outside their catchment area.
Homa Bay	48%	63%	58.4%
Turkana	31%	24%	43.1 %
Kakamega	44%	60%	63.3%
Garissa	28%	42%	45.1 %
Bungoma	42%	48%	60%
Nairobi Embakasi	(N/A)	*147%	*139.8%
Nairobi Kamunkunji	131%	*162%	*214.7%
Outcome Indicator 2: No. additional births delivered by a skilled birth attendant
National	N/A	35,000
Options		5,705	2,399
UNICEF		29,295	37,207
Outcome Indicator 3: Functioning health facilities able to provide basic EmONC (BEmONC) and comprehensive EmONC (CEmONC): (i) nationally (%) and (ii) No./500,000 population for six counties
National	N/A	(i)BEmONC 30% (ii)CEmONC 40%	Not Available
Homa Bay	N/A	(ii) In each county: 12 health facilities providing BEmONC	16	Bungoma is on track to have four health facilities providing BEmONC by December 2016. Options use ‘QUIC’ , a particular methodology for measuring EmONC functionality. This more stringent measure may be impacting on results. Options have, however, given this indicator high priority and the programme looks set to make good progress in 2016 and 2017.
Turkana			18
Kakamega			23
Garissa			16
Bungoma			0
Nairobi			9
Homa Bay	N/A	(ii) In each county: three hospitals providing CEmONC	4
Turkana			2
Kakamega			4
Garissa			3
Bungoma			2
Nairobi			2
Outcome Indicator 4: Caesarean section (CS) rate (% live births delivered by CS in the population)
National	12.5%	13%	12.8%	The previously recommended international rate of 10%–15% has been achieved nationally and in Garissa. / Recent World Health Organization (WHO) guidance (2015) concludes that at population level CS rates higher than 10%
Homa Bay	4.2%	7%	3.7%
Turkana	6.7%	9%	6.3%
Kakamega	5.7%	7%	5.9%
Garissa	10.5%	12%	10.4%
Bungoma	6.9%	9%	9%
Nairobi	11.7%	13%	15%
Outcome Indicator 5: Obstetric case fatality rate: (% of women with obstetric complications admitted to a facility who die)
National	2.9%	2.7%	2.7%	*The operating theatre at the County Referral Hospital, Bungoma, closed for refurbishment during some of the reporting period and thus MNH cases were referred elsewhere. The theatre will re-open and the first maternity operating theatre has now opened (Webuye Hospital). Options anticipate meeting target by December 2016.
Homa Bay	2.4%	<2%	< 2%
Turkana	1.8%	<2%	< 1.7%
Kakamega	1.16%	<0.5%	< 0.5%
Garissa	2.25%	No figure given	< 0.5%
*Bungoma	2.5%	1.7%	2.1%
Nairobi	0.5%	<0.5%	< 0.5%
Outcome Indicator 6: Still birth rate; number of still births per 1,000 total births
National	3.9	2.7	2.5	Indicator wording is per 1,000, but targets are per 100.
Homa Bay	2.8	2.5	1.9
Turkana	4.1	2.7	4.1
Kakamega	4.8	1.5	2
Garissa	3.6	2.8	2.6
Bungoma	3.6	1.6	2
Nairobi Embakasi	1.6	0.6	2
Nairobi Kamunkunji	2.3	1.5	1.9

Key points
- There is need to review targets for Turkana and Nairobi on outcome one to ensure consistency with baselines figures, context and data quality.
- The national data is not yet available, until 2017, to ascertain progress against the national target for outcome three. The outcome indicator on BEmONC in Bungoma is offtrack but the service provider has put measures in place to fast track progress in 2017.
- The indicator on obstetric case fatality rate (i.e. % of women with obstetric complications admitted to a facility who die) is off track in Bungoma due to temporary closure of the theatre for refurbishment. Performance against this indicator is expected to improve, with a more functional theatre.
- Close monitoring of external and delivery risks remains critical for the success of this programme. The risks include; insufficient numbers of health workers and slow reimbursements for free maternity services (by GoK), forthcoming 2017 national elections, and slower-than-planned start to parts of the programme; including the refurbishment of facilities and the human resources for health components

Overall output score and description
The overall programme has been scored B, reflecting progress with some programme components since the last review while recognising that other components, especially around outputs 2 and 3, are still struggling and, despite some limited progress, remain behind schedule.

Output	Output description	Impact weight (%)	Output performance
1	Health workers have the knowledge and skills to provide quality care and EmONC.	30%	B
2	Health systems strengthened to manage and deliver MNH services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma	50%	A
3	Increased demand for maternal health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma	20%	B

Key lessons
  (i) Managerial structure and systems
- Programme coordination is complex and requires strong oversight of the whole MNH programme across counties. UNICEF has technically competent, committed staff but lacks in-house systems to provide the required oversight and coordination function. The programme team is exploring additional mechanisms to strengthen this function, such as expanding roles of some other partners to cover ceratin coordination functions.
- Flexible and responsive approaches to implementation are working well within the dynamic devolution context in Kenya, e.g. at county level in Bungoma Options is using a systematic approach to their work and focusing on developing tailored plans with county partners. Consideration has been given to cross learning within the programme on health systems strengthening, for example, UNICEF has engaged partners who are working with Options on HSS to fast track implementation.

(ii) Country context, risks and implications
- Slow reimbursements for free maternity services, staffing shortages and governance are contextual risks that limit country absorptive capacity. Health systems support therefore needs to be flexible and technical support needs to be sequenced carefully to avoid overloading staff.
- The changing donor context now includes the World Bank-administered Multi-Donor Trust Fund, which provides technical assistance and capacity development of Kenya’s devolved health system, which is supported by DFID and others, and the US Agency for International Development (USAID) shifting its focus for MNH work toward new focal counties.
- Although most counties are receiving more health funding, allocation and resource limitations remain.

(iii) Programme content, tracking progress and harnessing learning
- Progress could be accelerated by enhancing synergy, by scaling up more integrated[3] approaches to delivering packages of essential reproductive, child health and nutrition interventions across the continuum of care.[4],[5]
  [3] This does not mean these elements should be included in the programme but rather that opportunities for greater synergy with other existing programmes should be explored.
  [4] Black R. E. et al. (2016). ‘Reproductive, maternal, newborn and child health. Key messages from disease control priorities. 3rd Edition’. The Lancet. Published online 09 April 2016: http://dx.doi.org/10.1016/ S0140-6736(16)00738-8.
  [5] Bhutta Z. A. et al. (2010). ‘Countdown to 2015 decade report (2000–2010): Taking stock of maternal newborn and child survival’. The Lancet. 2010; Vol 375: 2032–44.
- The VfM approach is not uniformly developed throughout the programme and it is not always clear whether the programme reaches the poorest and most vulnerable people within communities. The vfm indictaors being tracked on the programme vfm framework differ slightly from those being tracked by the evaluation consultant and should be harmonised.
- The depth and quality of each partner’s experience should be harnessed and partners should learn to work more strategically and to shift from a project management approach focused on individual results to a dynamic and flexible partnership. There are unique learning opportunities, including the devolution agenda and how the programme continually adds value to this dynamic process in Kenya. A successful learning forum was held in 2016 and there are plans for further such events, which are encouraged.

Key actions
See key recommendations at the start of the report and detailed recommendations provided under each output.

Has the logframe been updated since the last review? YES
The logframe has been revised based on recommendations from the previous annual review. Major changes include: revised targets for SBA downwards; measurements of functionality of community units; division of roles and responsibilities among core partners on MPDSR indicators (although not fully completed); revised target for number of additional births attributable to the project (calculation of attribution methodology is pending final approval from DFID); and DSF targets for Bungoma need to align to the revised target in the programme log frame.

## C: DETAILED OUTPUT SCORING
Output title	Health workers have the knowledge and skills to provide quality care and EmONC
Output number per logframe		1	Output score	B
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last annual review?		No	Impact weighting % revised since last annual review?	No

Indicators	Milestones 2016	Progress 2016
1.1. No. additional health workers trained in EmONC (disaggregated by sex). LSTM indicator	Direct: 1,600	2832 (Female [72%] & Male [28%]) / Score: A
	Indirect: 1,000	495
1.2 The proportion of health facilities followed up quarterly. / LSTM indicator	70%	97.6% (By end June 2016: 40 facilities out of total of 41 eligible have been followed up). / Score: A+
1.3 Percentage (%) of: / 1.3.1 maternal deaths; / *1.3.2. perinatal deaths (facility level) for which the death review forms are submitted to DHIS; and / 1.3.3. Health facilities in the counties that have made required adjustment to service provision and/ or management practices based on MPDSR / LSTM indicator – except Bungoma (Options)	1.3.1	Score: C[6] (see notes on scoring below)
	Homa Bay: 100%	52.8%
	Turkana: 100%	27.8%
	Kakamega: 100%	95.6% (100% COEs)
	Garissa: 100%	8.3% (100% COEs)
	Bungoma: 50%	100%
	Nairobi Embakasi: 100%	33.3% (100% COEs)
	Nairobi Kamukunji: 100%	66.7% (100% COEs)
	1.3.2.	Score: B
	Homa Bay: 25%	1.7%
	Turkana: 25%	27%
	Kakamega: 25%	25%
	Garissa: 25%	0%
	Bungoma: 25%	67%
	Nairobi Embakasi: 25%	50%
	Nairobi Kamukunji: 25%	>75%
	1.3.3	Score: C (Data not available)
	Homa Bay: 30%	The roles between different partners on MPDSR have not been fully clarified. LSTM reports MPDSR data at the national level
	Turkana: 30%
	Kakamega: 30%
	Garissa: 30%
	Bungoma: 15%	57%
	Nairobi Embakasi: 30%
	Nairobi Kamukunji: 30%
[6] UNICEF note some coding challenges for DHIS data on perinatal deaths, which is likely to be impacting on data. This is being addressed.

Key points
The overall output score reflects a B. Although there is good progress on indicator 1.1 and 1.2, these are input measures and the weight lies on output 1.3 which is an outcome measure and is currently offtrack.

Output Indicator 1.1:
- There has been good progress with health worker training. Progress has been most marked in training provided directly by LSTM, where targets have been exceeded. The programme is on track to meet the target of training 9,000 health workers by the end of March 2019. LSTM has continued to reduce training costs (per trainee) with its emphasis on the use of national master trainers for EmONC training (138% of the end-of-programme target). However, milestones for indirect training remain off track, with reductions from 767 trained in 2014 to 495 in 2016 and the target is unlikely to be met by the end of the programme. Tracking of idirect trainings is challenging since the programme does not have direct control over these trainings and they require considerable quality assurance. The programme is taking steps to increase indirect training numbers and ensure sustainability, but there is need to review the proportion between the direct and indirect trainings.
- All EmONC training is quality assured, although quality assurance of indirect training is more time intensive. A total of 88 master trainers and course directors have been trained in quality assurance. Since May 2016, when quality assurance of all training commenced, 2,214 health care workers have been trained through quality assured training courses.
- Generate wider benefits. The programme through LSTM, provides support to 25 partners conducting indirect EmONC training. Six-monthly coordination meetings are held to ensure good coordination but opportunities to strengthen coordination have been missed, e.g. the GoK and USAID HRH initiative.[7]
  [7] USAID has supported the MOH in relation to developing a training database (iRHISTrain).
- The turnover of trained health workers is high. The programme is supporting a pilot of an electronic database which could potentially improve the tracking of trained staff, pre-service training and to make better use of on-the-job training and training of trainers.

Output Indicator 1.2
- There has been improvement on this indicator since the last annual review and against a performance improvement plan to accelerate progress. Supportive supervision by LSTM has been ongoing as part of regular facility visits since April 2016. These visits help strengthen and sustain skills retention. In response to 2015 recommendations, LSTM has trained 74 supervisors and separated the M&E and supervision processes. Tailored follow-up sessions are conducted at three, six, nine and 12 months after training.
- Although this indicator scores well, there is need to revisit the follow-up approach. Currently, follow-up only begins after a minimum of 80% of all maternity staff within a health facility have been trained in EmONC. This may potentially have delays for larger facilities and could leave out smaller facilities where only a lower proportion of staff are trained. There is currently no national mentorship package by the ministry of health (MoH) and standard MoH supervision does not include EmONC. LSTM has picked this up and is discussing potential solutions with the MoH.
- LSTM has developed strong partnerships with stakeholders, including the central MoH and county health teams. These partnerships have been important in dealing with insecurity and in planning monitoring and supportive supervision visits.

Output Indicator 1.3
- Acceleration of progress against this indicator was part of a performance improvement plan for UNICEF and LSTM after the last annual review. There has been some progress, although minimal. LSTM has provided technical support to the ministry of health to develop a strategy on MPDSR and an action plan, establish a functional national steering committee and conduct the first ever national maternal deaths audit.
- Options have focused intensively on Maternal and Perinatal Death Surveillance and Response (MPDSR) since mid-2015, with commendable improvements in the reporting and the use of data for action planning. Options and UNICEF are supporting and reinforcing MPDSR committees at all levels. The process of streamlining MPDSR into the national District Health Information System (DHIS2) is underway but has yet to be completed. There is good progress in the automatic compilation of maternal death summary forms.
- Underperformance on this indicator is partly due to inconsistencies between the data which is collected by health facilities on maternal deaths and what is captured by the national health information system (DHIS2), and some inaccuracy in how the system interprets data. The programme partners together with other players are addressing this with the MoH.
- The 2015 annual review recommended that partners determine how to measure the combined contribution of each partner to output 1.3.3. This has not yet been fully addressed. LSTM collects national-level data while the indicator requires county-level data. There is still need to clarify roles on MPDSR among all the programme partners. The support provided by the programme on coordination of MPDSR at the national level and on quality improvement at health care facility is not adequately captured in the log frame.

Summary of responses to key issues raised in previous annual reviews
(i) LSTM in particular have made good progress against issues raised in previous annual reviews and in their performance improvement plan, including quality issues around indirect training. A quality assurance package has been developed and master trainers and course directors have been trained. All courses are quality assured.

(ii) A further recommendation was to ‘Monitor the effectiveness of participant selection and verification procedures for training.’ A pilot of biometrics software to enhance participant tracking will be in place by November pre-service training.

Recommendations
What	Who	When
Accelerate implementation of the pilot of biometric software. LSTM should coordinate this initiative with the GoK and USAID HRH database initiative. More broadly, LSTM should improve coordination of EmONC training through wider coordination efforts with the GoK and other related partner-funded initiatives (e.g. USAID HRH programme).	LSTM/	January 2017
Follow-up mentoring for EmONC training needs to be strengthened as part of creating sustainable change in embedding quality and best practices. Advocacy for a national mentorship package and inclusion of EmONC in standard supervision needs to be expedited. LSTM should develop an advocacy plan for this work.	LSTM	Ongoing
Consider the resources provided to pre-service training as part of wider considerations under Recommendation 2 (see Section A). LSTM to advocate with MOH to promote the EmONC training as part of mandatory annual maternity care worker requirements for practice licences. Plans for achieving this should be set out by LSTM.	DFID/ LSTM	December 2016
Update logframe, including: / -Amend Indicator 1.1 (EmONC) to reduce indirect training and increase direct training proportionally . / - Indicator 1.3.1. Establish a consistent approach using county-level data for all partners across all counties. / - Amend Indicator 1.3 (MPDSR) to capture LSTM’s contribution to central-level MPDSR. LSTM should continue to champion MPDSR at the national level and continue support to MPDSR through EmONC training and supportive supervision. / - Include pre-service logframe indicators.	DFID/ LSTM/ Options/ UNICEF	February 2017

## C: DETAILED OUTPUT SCORING

Output title	Health systems strengthened to manage and deliver MNH services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties
Output number per logframe		2	Output score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last annual review?		No	Impact weighting % revised since last annual review?	No

Indicators	Milestones 2016	Progress
2.1 Innovation fund projects demonstrate successful new approaches to improving delivery of quality MNH services (Options)	Six projects selected and contracted for Round 2	Score: A / 6
2.2: Counties have consolidated operational plans and budgets that include MNH services	Counties recruit sufficient staff to ensure at least one health worker can provide BEmONC in every health centre	Score: A Nine out of nine government health centres in Bungoma and all UNICEF supported centres of excellence have at least one health worker who can provide BEmONC services.
2.3: No. management systems supported and strengthened to objective standards and implemented at county level	6	Score: B Four Capacity building plans are being implemented in Bungoma and the target for six looks likely to be reached by December 2016. / UNICEF has supported and strengthened eight management systems, including: evidence-based planning, coordination, HRH, quality of care, leadership and governance, social accountability, evidence-based planning and child-friendly budgeting. However, county HRH plans are not yet complete, despite this being a key recommendation in 2015. Work on social accountability is still in early stages

Key points
- This output is important for sustanability and lays the foundation for quality service and delivery of the programme outcomes including the county innovation challenge fund, hence carries the highest weigthing (50%) and impacts on the overall programme score. However, this weighting should be reduced slightly to create the right balance with the other two outputs and to accurately reflect programme performance.
- The current logframe does not adequately capture the component of the programme focused on improving health infrastructure through green energy solutions. Architectural plans have been finalised for all UNICEF-supported COEs. Work at several facilities has already begun: e.g. Mukuru Health Centre in Nairobi, where deliveries have increased from no newborn deliveries in 2015 to over 50 deliveries per month in 2016. Infrastructural development delays have, however, impacted on service delivery. In the Sub-County Hospital in Garissa, neonatal equipment was not being used due to lack of adequate space, while issues with the provision of water at the COE visited in Nairobi and at Garissa County Referral Hospital were impacting on service delivery.

Output Indicator 2.1
- The CICF continues to be well managed and efficient under the fund management partnership between Options, KPMG and the Population Council. The CICF’s first Annual Learning Event is planned for 2016 as part of the fund’s communication and dissemination strategy.
- Innovation fund grants have been designed to run for two years. Two years is however considered too short, especially given the types of research and grantees’ limited experience.

Output Indicator 2.2
- UNICEF and Options supported counties to develop AWPs, identifying MNH core priority high-impact interventions and costed activities with the allocation of funds from both the county governments and partners.
- There is good evidence that health workers have benefitted from partner systems strengthening initiatives, especially in Bungoma, Homa Bay and Turkana. Consideration should be given to strengthen systems in all programme counties, especially in Garissa.
- Health care financing is a high priority for MNH in the context of devolution, and several existing mechanisms are not working routinely (e.g. GoK free maternity service resources are not reaching health facilities on time). Options has shown good flexibility and responsiveness to local county context. After building strong county relationships in Year 1 Options used this to advocate for increased support to MNH financing. UNICEF, in Garissa county, has advocated with county government and secured increased allocation for MNH interventions.
- The programme is implementing a Performance Based Financing (PBF) approach in 35 health facilities in Bungoma. The PBF incentives are provided via the procurement and provision of equipment and supplies, but this does not promote autonomy, a core PBF principle, and hence the freedom to spend additional funds as the facility deems appropriate. The programme needs to monitor the impacts of the current approach to PBF on performance in the longer term. Because facilities will not be free to make direct use of PBF, there is a potential risk that facilities may not be as motivated by PBF as intended. The programme log frame does not yet include indicators on PBF. These should be included.

Output Indicator 2.3
- Performance against this indicator has been relatively slow as indicated in the last annual review, although some progress has been made. UNICEF has now engaged partners with comparative strength on health systems strengthening (HSS) such as WHO and MannionDaniels to improve performance and accelerate progress. WHO is supporting national-level systems strengthening for referral systems, while ManionDaniels is to support counties in reviewing and tracking HSS. Prioritising support to counties to establish effective HRH information systems was a key recommendation from 2015 and although development of county-based HRH databases has been finalised, quality HRH plans have not yet been finalised.
- Options uses an Organisational Capacity Assessment for HSS, which allows for a systematic approach to assessing and improving HSS gaps and builds the capacity of the Community Health Management Team to ultimately take the lead on HSS.
- UNICEF’s strengths seem to be in policy and guidelines development, quality of care, and the scaling up of initiatives, such as Kangaroo Mother Care and the community strategy. UNICEF has supported focus counties to contextualise MNH approaches to better serve their unique populations, be they pastoralist, agrarian or urban. Initiatives include maternity waiting shelters, alternative birthing positions and nomadic clinics. They have supported capacity development of county MOH staff to conduct CEmONC and BEmONC assessments of health facilities and improve MPDSR systems.
- The milestones for indicator 2.3 should be reviewed to include milestones which accurate reflect progress against the specific systems which are being strengthened by the programme.

Recommendations
What	Who	When
Consider extending innovation fund grant period as part of the overarching recommendation 2 in Section A.	DFID	December 2016
In parallel with the CICF extension, consider the options for extending the Bungoma MNH component to June 2019 (should form part of considerations under Recommendation 2, Section A)	DFID	February 2017
Add an indicator to the programme logframe to capture the climate change / facility upgrade component	DFID/ Options/ UNICEF	February 2017
Continue to prioritise health facilities that are to receive climate change upgrading. Advocate for ongoing operation and maintenance costs for equipment in county budgets to maximise sustainability and ensure VfM from DFID investment	UNICEF/ Options	Ongoing as part of county AWPs
As part of HSS, UNICEF to prioritise county-specific HSS plans with the new supplier ManionDaniels.	UNICEF / DFID	November 2016

## C: DETAILED OUTPUT SCORING
Output title	Increased demand for maternal health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties.
Output number per logframe		3	Output score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last annual review?		No	Impact weighting % revised since last annual review?	No

Indicator(s)	Milestones 2016	Progress
3.1 No. of poor women covered by DSF schemes (disaggregated by service type)	Homa Bay – 9,200 / Turkana – 8,200 / Nairobi – N/A / Bungoma – 12,000	Score: C / UNICEF has contracted PwC to undertake DSF in Homa Bay and Turkana and PWC arecurrently working on the design. / Options distributed 6,183 vouchers to pregnant women in Bungoma by July 2016. The intervention has been rolled out to all sub-counties and is on track to distribute 12,000 vouchers by December 2016
3.2.1 No. of community units established in the six focus counties by end 2018		Score: B / In most counties, the focus is now on functionality
	Homa Bay: n/a	Already at 100% coverage from 2013 baseline. Focus is on functionality
	Turkana: 45	154 Turkana restructured their community health service. Focus is on functionality
	Kakamega: 0	120. Focus is on functionality
	Garissa: 52	75
	Bungoma: 50	Options is not supporting the establishment of new community units but rather is focused on improving functionality of existing ones
	Nairobi Embakasi: 55	0. Planned for November 2016
	Nairobi Kamukunji: 60	0. Planned for November 2016
3.2.2 No. of established community health units fully functional as per national guidelines for functionality		Overall Score: B
	Homa Bay: 75	100
	Turkana: 65	100
	Kakamega: 75	100
	Garissa: 65	67
	Bungoma: 73	53 are fully functional and 31 semi-functional.
	Nairobi Embakasi: 50	0 planned for November 2016
	Nairobi Kamukunji: 50	91
3.3: Percentage of women receiving at least four antenatal care (ANC) contacts during pregnancy		Overall Score: C
	National: 68	52%
	Homa Bay: 64	51%
	Turkana: 47	38%
	Kakamega: 89	66%
	Garissa: 54	54%
	Bungoma: 54%	47%.
	Nairobi Embakasi: 120	58%
	Nairobi Kamukunji: 89	43%

Key points
Performance against this output is mixed, with good performance on establishement and functionality of community units and slow progress on financing approaches and antenatl care. Although the components on the community units score a B, there has been realtively good progress in most counties. This progress together with the confidence of achieving the financing target in Bungoma by December 2016 has impacted the overall output score.

Output Indicator 3.1:
This indicator for UNICEF in Year 3 of the programme is still not on track. PwC has been contracted to address this. An inception phase and assessment in Homa Bay and Turkana has been completed and the design of a DSF intervention is underway. In addressing demand-side barriers, UNICEF has been implementing other initiatives, including mothers’ waiting shelters (MWS) in Turkana, strengthening an already established MWS in Garissa County and the piloting of a Mama Pack – a pack designed to encourage mothers to deliver at health facilities.[8] UNICEF has provided some anecdotal evidence to support this intervention; however, at this stage it is uncertain whether the Mama Pack addresses priority financial barriers for women in Nairobi’s informal settlement. The indicator is not on track and reviews of health impact and cost-effectiveness are required before any scale up. Options delivery is on track in Bungoma and is set to achieve the target by December 2016.
[8] Packs are given to mothers who deliver at selected health facilities and include one baby shawl, one bucket or basin, eight packs of nappies and sanitary towels and one khanga.
Output Indicators 3.2.1, 3.2.2 and 3.3
At national level, the Kenya Community Health Policy was finalised (April 2016, awaiting final approval). UNICEF also supported the finalisation of the community-based MNH training manuals for community health volunteers. At facility level, they have introduced initiatives such as the Respectful Maternity Care initiative delivered by World Vision International and county MOHs to address gaps in ANC attendance. UNICEF has largely exceeded targets for the number of community health units fully functional as per national guidelines for functionality. However, overall, there has been mixed progress against these indicators, with least progress against the percentage of women receiving at least four ANC contacts during pregnancy. Establishment of community units was not possible in Nairobi due to lack of Community Health Extension Workers (CHEWs) in the county. UNICEF has negotiated and advocated for the employment of CHEWs who are now trained. Formation of community units is now planned for November.

Summary of responses to issues raised in previous annual reviews
1. UNICEF and Options to consider how to measure the effectiveness of community units, in particular community health volunteers, and revise Indicator 3.2 milestones to include effectiveness measures. The logframe has been revised to include measurement of functionality for community units. Measures of effectiveness will be addressed through the HERA-led evaluation.
2. UNICEF and Options to prioritise support for community units that are linked to COEs in the five counties and facilities with a high volume of deliveries in Bungoma. Ongoing.
3. UNICEF and Options to assess the underlying reasons for drop out between first and fourth ANC visits and identify demand-side interventions to address these factors. Options and UNICEF have reviewed this and reasons include lack of financial resources/ time, mothers needing permission to attend ANC, a lack of appropriately equipped health facilities, a lack of staff at the facility who treat the mother with respect and weak client tracking systems. There is evidence that these findings are being used to target programme approaches (e.g. Options is piloting a defaulter tracing system for ANC), although the effectiveness of these initiatives needs to be assessed.
4. UNICEF and Options to give higher priority to ensuring that counties and facilities have effective accountability mechanisms in place. Implementation underway.
5. UNICEF to accelerate programme implementation. Currently, all the MNH thematic areas have been contracted and works initiated in the focal counties.

Recommendations
What	Who	When
Ensure the health impact and cost-effectiveness of all DSF interventions can be tested. In particular, in regard to the Mama Pack for UNICEF and transport vouchers for Options – prepare for obtaining relevant data and gather data.	UNICEF/ Options	November 2016 onwards
Continue to track systematically whether supply is able to meet demand for services and plan demand creation activities carefully, using clear criteria for prioritisation. Especially important here are the newly developed HRH situation analysis report databases and HRH plans for all counties	UNICEF and Options	November onwards
Continue the performance improvement measures for UNICEF, especially for Indicator 3.1 (DFS) and HSS (Output 2.3). UNICEF has recruited partners to help with this indicators and are in a position to accelerate progress	DFID	November 2016

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key costs, cost drivers and performance

Key costs for implementing partners
Implementing partner	Key costs and percentage of total expenditure
	1	2	3
LSTM	EmONC direct training costs (60%)	Staff and office costs (23%)	Overheads (8%)
UNICEF	Transfer of cash to partners (67.7%) / Supplies (8.6%)	Salaries (15.4%)	Indirect support costs (8%)
Options / (including CICF)	CICF and Voucher Funds (58%)	Fees (26%)	Activities and expenses (16%)

N.B. These are the three main costs, not all the costs, and thus do not total 100%.

Key factors affecting costs continue to include security, global market prices and the devolution process (in terms of it causing delays). Also, following the outcome of the UK’s referendum on leaving the European Union in June 2016, sterling has lost 11% against the Kenyan shilling. This is likely to impact on the programme in the coming year and should be monitored closely.

Performance against vfm indicators:
The MNH programme has a VFM framework which was agreed with all partners in November 2015 but is not yet adequately implemented. Programme partners have made some progress in monitoring economy and efficiency, however gaps exist in making reference to appropriate comparators, setting benchmarks, collecting adequate data and limited internal capacity among the programme partners to assess cost-effectiveness. LSTM is collecting good quality data on training costs which allow for good approximations of VfM. The other two programme partners require support in further understanding the VFM framework. The data gaps within this review period do not allow for a comprehensive review of VfM measures across the whole programme. The programme is supporting assessmement of VFM as part of the evaluation work through UNICEF/HERA, and a comprehensive analysis should be available during the 2017 annual review. Programme partners have been taken through a training session previously but a follow up training will be facilitated to address the gaps identified on implementation of the VFM framework. Overall, all programme partners have some good practices to maximise vfm around bulk procurement, use of local consultants and trainers.

Progress against VFM indicators
VfM Component and Measure	Frequency of reporting	Progress
ECONOMY
Real value of vouchers	Annually	N/A
Unit cost per trainee (LSTM)	Routine	2014		2015		2016
		432		305		250
Consultancy daily fee rates	Annually	N/A
EFFICIENCY
Proportion of EmONC trainers who are Kenyan (LSTM)	Annually	2013	2014		2015		2016
		86%	90%		96%		100%
Unit cost per voucher utilised (transport voucher/and other incentives)	Annually	£13.34 – transport voucher / £88 – Mama packs
COST-EFFECTIVENESS
Unit cost per maternal death averted	Two years / End of programme	This will be assessed by the programme evaluation consultant
Unit cost per DALY averted

The average costs per trainee on EmONC have been reduced from £432 (2014) to £250 (July 2016), which shows a clear improvement at the economy level. Furthermore, all EmONC trainers are now Kenyan nationals. Using volunteer health care professionals from the UK is highly cost-effective and, with coordinated centralised support, results in demonstrable benefits for both the recipient countries and the volunteers and their working environment back in the UK. The cost per voucher uitlised is expected to reduce over time once trainings are completed and more vouchers are utilised. The distribution of mama packs by UNICEF has just started with less than 1000 packs distributed. The cost is expected to reduce with increased distribution. Suitable comparators for the voucher and mama packs should be identified to increase analysis of costs.

VfM performance compared to the original VfM proposition in the business case
The business case listed possible VfM indicators which the programme is tracking with minimal revisions to a few indicators on skilled birth attendance. The programme includes an evaluation component with assessment of VFM, although some of the indicators proposed by the external evaluator are not in line with the programme VfM Framework.

The programme is still expected to deliver within the estimated unit cost per DALY as set out in the business case. The cost is still subject to variation as anticipated in the business case with the effect of devolution, free maternity services. As the Business Case acknowledges, the unit cost metrics omit the potential benefit of much systemic change that this programme seeks to secure (e.g. improving maternal health policy, equity, addressing broader health sector financing, health management and service delivery issues in the newly devolved counties, and contributing via piloting experiences and the evidence base in Kenya). The current VFM indicators do not adequately address equity and costs are insufficiently linked to results.

There is a clearly formulated Theory of Change behind the programme. Programme components on training and demand side financing provide a quantitative theory to model attribution in order to link measured outputs (e.g. health professionals trained, vouchers distributed) with impact (disability-adjusted life years (DALYs) / deaths averted). However, the programme impact goals are based on a model with a substantial level of uncertainty. It would be valuable to measure programme-related impact vis-à-vis general developments in Kenya. The Difference-in-Difference (D-I-D) method is a potential approach to address this. This approach will calculate the effect of the MNH programme on a defined outcome by comparing the average change over time in the programme counties to the average change over time for a control group. The success of this approach is dependent on good baseline data, and the potential for its implementation will be considered in 2017 if the programme receives quality data from the independent evaluation.

Assessment of whether the programme continues to represent VfM
In principle, the programme represents very good VfM. By 2022 the programme is expected to save about 650,000 disability-adjusted life years at a unit cost of just over £100. These calculations, however, come with a high degree of uncertainty and difficulties in regard to establishing causality. The ongoing devolution of health service responsibilities to the county level adds to this. It remains to be seen whether the availability of data (particularly baseline data) will allow advanced calculations on cost-effectiveness.

VfM practices are adequate in regard to economy, but need improved result indicators.
VfM measures need to be reviewed. We recommend all partners have: (i) a joint understanding of the VfM indicators; (ii) provide sufficiently detailed and attributable cost data; and (iii) link these to the available effectiveness data. A VfM workshop involving all partners would help expedite this process.

Quality of financial management

Against recommendations from the 2015 annual review:
(i) LSTM has adequately responded to recommendations from previous spot checks and audits on financial management systems. A senior Finance Officer is now in post in LSTM Kenya and all issues raised in the audit have been fully addressed, and robust financial systems are in place. LSTM is providing regular financial forecasts to DFID and continues to monitor programme expenditure against the overall workplan and budget.
Options and their six sub-contractors have implemented financial management through narrative and financial reporting and due diligence processes. Spending by UNICEF has improved slightly. The management of funds on behalf of recipients remains a challenge for UNICEF, who has now contracted UNOPS to manage funds for county- and/or national-level government activities. This management of funds by a third party is necessary for UNICEF in engaging with county governments although it adds complexity and impacts on speed and effectiveness. However, UNOPS is working, albeit at a slow rate due to more lengthy preparatory phases and tendering processes. DFID has instituted monthly updates from UNICEF to track progress on spend.

The following table shows the funds disbursed to date.
Implementing partner	Total budget / (£)	Yr. 1, 2 and 3 budgets / (£)	Funds disbursed by DFID July/ September 2016 (£)	Balance (£)
LSTM	10,317,232* (Incl. pre-service training)	2,776,415 (Yr. 1) / 2,016,200 (Yr. 2) / 2,537,012 (Yr. 3)	4,275,860	6,041,372
UNICEF	25,793,796 / (incl. evaluation and CICF funds)	6,532,616 (Yr. 1) / 8,353,067 (Yr. 2) / N/a (Yr. 3)	14,885,683	10,908,113
Options (Bungoma)	9,975,512	3,044,663 (Yr. 1) / 2,711,603 (Yr. 2) / 4,219,246 (Yr. 3)*	3,977,973	5,997,539
Options (CICF)	10,845,158	N/A	2,311,302	8,533,856

*Year 3 budget high as most of the £1.14 million voucher funds will be spent in the final year and withheld funds (£717,000) payable at the end of Year 3 when targets are met.

Date of last narrative financial report	18/07/2016 (UNICEF), July 2016 (LSTM), June 2016 (Options)
Date of last audited annual statement	15/09/2015 (UNICEF), December 2014 (LSTM), December 2015 (Options)

E: RISK
Overall risk rating: Moderate. The overall risk rating is unchanged.

Overview of programme risk
UNICEF, Options and LSTM have separate risk matrices and systems for monitoring risk in place, and these risk matrices are updated on a quarterly basis. Risk matrices for sub-partners are in place and are reviewed quarterly for Options, while UNICEF reports that these risk matrices are assessed when contracts are first issued and subsequently on ‘a needs basis’. This should be done quarterly. This programme was reviewed by DFID’s Internal Audit Department in 2016 and we expect recommendations around the programme risks to be included in the report.

The risks identified in the business case and partner risk matrices remain and some risks have increased and continued since the business case was developed – in particular, those associated with insecurity and continuing risks relating to county health budgets, changes in staffing and governance within the new country health structures.

- The risk context: The risks associated with insecurity and conflict increased, following the terrorist attack on Garissa University (2015) and other incidents, and sporadic violence in Turkana and West Pokot; the probability should remain as high risk. In Garissa, we heard evidence of staff shortages, with staff leaving the county.
- Key risks affecting successful delivery of results: A key risk that continues to affect county capacity to deliver consistently high quality MNH services is the increase in demand resulting from the GoK’s free maternity care policy in settings that continue to experience shortages of health workers. Counties are recruiting health workers but attracting and retaining staff in some counties (e.g. Turkana and Garissa) remains a challenge. Shortfalls in county health budgets for primary care services and MNH more specifically, and competing demands on County Health Management Teams’ time and budgets, compound these risks. Continued support for county planning and budgeting and advocacy with county governments for MNH will be critical. There are also new risks and opportunities. The forthcoming elections present risks and opportunities. There could be increased attention on the health sector and MNH, or changes of priorities. Election preparedness plans are already underway to minimise risks. Other risks include duplication and inefficiency due to poor coordination and new shifts in other large donor partner programmes, such as those of USAID and the World Bank.
- Additional checks and controls needed: UNICEF, UNOPS and Options will need to monitor renovations and green energy inputs carefully, so as to ensure the quality of the work and effective management of assets. This was raised in the 2015 annual review but is yet to be fully implemented as renovations and works on green energy begun in 2016.

Outstanding actions from risk assessment - None.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
A key recommendation from the 2015 annual review was for UNICEF to get programme activities on track as quickly as possible. Contractual processes with all UNICEF implementing partners have been finalised.

Overall, delivery is partly on track. Workplans and milestones are submitted regularly to DFID. LSTM and Options are broadly on track but UNICEF delivery is not on track in some areas. There have been delays (e.g. in facility improvement measures, DSF). UNICEF is confident that with facility plans now finalised and a supplier contracted for DSF roll-out and subsequent spending will progress more rapidly.

Performance of partnerships
Recommendation from 2015 annual review: Partnerships could be strengthened through more thematic meetings between programme implementing partners and more systematic sharing of reports, assessments and other documents. There has been improvement on the engagements between the programme partners through regular meetings but effectiveness and efficiency could be further improved by enhancing synergy across the partnership in regard to achieving objectives and in the approaches used. PwC, for example, refers in its inception report to DSF but only mentions the ongoing Options programme and experiences in passing.

The current programme structure is top-heavy, with UNICEF both managing the majority of subcontracts as well as liaising with DFID and having responsibility for the oversight and coordination function between the implementing partners – although this oversight role has diminished in the last year and partners now report individually to DFID rather than through UNICEF. The programme should consider opportunities for strengthening the current UNICEF-led oversight and coordination function.

The relationship between the implementing partners and DFID remains positive, in particular partners welcomed timely feedback on reports and the participation of DFID in field missions. Partners continue to request significantly more direct engagement with DFID staff and would like DFID to take a more active role in programme management, despite the programme structure funding UNICEF to take on the oversight function. Partners also expressed concerns about frequent ad hoc requests for information and felt that response times for responses to reports and requests for support were too short. This raises questions about programme structure and whether the current structure, governance and partnership arrangements offer good VfM. DFID is exploring additional mechanisms to improve coordination of the programme.

Asset monitoring and control
Assets financed by this programme include training equipment procured centrally by LSTM. UNICEF, LSTM and Options have systems in place to record and monitor assets. UNICEF maintains a computerised record of all items procured and conducts regular spot checks, while LSTM and Options also maintain asset registers. The programme partners submit asset registers every six months to DFID for review and updates. DFID includes verification of physical assets during regular field visits and spot checks. There is visible evidence in the field of UK Aid branding on equipment.

G: CONDITIONALITY
Update on partnership principles
Since DFID is not providing financial aid using GoK systems in the delivery of the programme, partnership principles do not apply to the management and monitoring of the programme.

H: MONITORING & EVALUATION

Evidence and evaluation
The overall programme design and theory of change remain relevant. Although some parts of the assessment raised some questions especially around targeting and reaching the poorest, the evaluation is assessing design choices to test this. In response to recommendations from 2015, UNICEF initiated the compilation of a comprehensive list of all operational studies across the programme and progress status was tracked on a bimonthly basis. Attribution methodology has been established for most logframe indicators. HERA will produce independent evaluation assessments on the efficiency, effectiveness, relevance, equity and impact of the programme. The evaluation questions and methodology are sound and the evaluation implementation plan is on track. Challenges to evaluation include the set of VfM indicators proposed by HERA being somewhat different to those proposed in the programme vfm framework, missing baseline data, and some limitations in regard to partners’ understanding of VfM. HERA have designed the evaluation[9] to address the issue of limited baseline data using retrospective counterfactual analysis of specific programme interventions on the basis of household surveys in intervention and non-intervention areas.
[9] HERA. 2016. Inception Report Kenya MNH_FINAL-3.

Monitoring progress throughout the review period
Partners provide individual progress reports to DFID rather than one consolidated report. While UNICEF has taken steps to improve and streamline its processes, the long lead-times required by UNICEF make joint reporting unfeasible. The logframe is not yet fully satisfactory in terms of agreed milestones and indicators. A review of the logframe in line with the recommendations provided here is required and once the amended logframe is fully developed and agreed this should enhance monitoring for all partners. This review should include finalisation of any outstanding issues from current discussions on the logframe.

The annual review included meetings in Nairobi with UNICEF, LSTM, UNOPS, Options, KPMG and GoK staff at national and country levels. Field visits to Garissa, Bungoma, Homa Bay and Embakasi sub-county in Nairobi included meetings with county and sub-county health teams, UNICEF and Options, local implementing partners, hospital and health centre staff, community units, community health volunteers and beneficiaries of MNH services. These visits provided an opportunity to observe the delivery of MNH services at a range of facilities and HSS support to government at county and national levels. The review included direct beneficiary feedback from mothers who had delivered their babies at one of the DFID-supported facilities or who had used the waiting mother shelters, attended ANC or follow-up visits, or used a transport voucher for delivery. We heard positive stories from many of the mothers about how staff had treated them with respect and how they felt confident about the treatment received: ‘staff encouraged me, I felt more relaxed than [with] my first pregnancy...at another place [health facility]… staff helped …I’d encourage others to use this place [health facility]’. Waiting times remain an issue and there were calls for other services, such as family planning. One woman who had recently delivered her eighth child spoke of her fears of the side-effects of family planning and wanted family planning advice. We met nursing staff who had benefitted from EmONC training. A critical benefit of training reported by interviewees was the confidence and ability to handle tasks that they would previously have referred to doctors: ‘I’m now handling tasks like vacuum extraction [vacuum assisted vaginal delivery] which I’d normally have referred … I’m much more confident after training [EmONC training]’.
The annual review included internal and external health and VfM consultants and inputs from a national consultant who undertook a visit to Garissa.