## Annual Review

Title: Global Risk Financing Facility
Programme Value £ (full life): £90m		Review date: 9 August 2020
Programme Code: 300751	AMP start date: 9 August 2019	AMP end date: 1 December 2025

Summary of Programme Performance
Year	2020
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/49549277.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/49690962.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
The Global Risk Financing Facility (GRiF) provides grants to test, pilot, and scale up coverage of pre-arranged financing instruments (e.g. insurance) that help developing countries better manage the financial impacts of shocks and crises. GRiF support can be in the form of establishing risk financing mechanisms (e.g. up-front costs of setting up different instruments), sharing the cost of risk financing mechanisms (e.g. co-payment of insurance premiums) and improving delivery channels for response and recovery (e.g. technical assistance).
The GRiF is principally delivered through a Multi-Donor Trust Fund (MDTF) hosted by the World Bank and funded by DFID and the Government of Germany (Federal Ministry of Economic Cooperation and Development, BMZ). There is scope for GRiF funding to go through other premium subsidy pools and multilateral organisations in future. At least £2m will be delivered through the African Disaster Risk Financing (ADRiFi) framework at the African Development Bank.
The objective of the GRiF is to strengthen financial resilience of vulnerable countries by enabling earlier and more reliable response and recovery to climate and disaster shocks and, over time, demonstrate the benefit of ex-ante approaches to the wider multilateral disaster response system. By providing early and reliable financing, the GRiF will help poor and vulnerable people and the services and infrastructure they depend on to recover more quickly. GRiF funding is also intended to create incentives for countries to invest in risk reduction and disaster prevention, preparedness, and response as well as resilient reconstruction.
The GRiF works through country systems where financial solutions are embedded as part of larger World Bank country projects and within broader efforts of risk management. The GRiF is designed to integrate financial resilience into wider fiscal risk management agendas to build comprehensive financial packages, including market-based solutions.
This year, the Steering Committee has endorsed over $91m of GRiF grants, in six projects. Five of these are country specific (Malawi, Jamaica, Indonesia, Afghanistan and Morocco) and one is regional (strengthening financial resilience through the Southeast Asia Disaster Risk Insurance Facility). This adds to three country projects (Mozambique, Sri Lanka, Sierra Leone) and several global public goods that were endorsed in the pilot phase.
The UK has committed £90m to the GRiF initiative. Most of this will be directed through the World Bank GRiF MDTF and an initial £2m has been allocated for the African Disaster Risk Financing (ADRiFi) initiative at the African Development Bank (AfDB).
Summary supporting narrative for the overall score in this review
The GRiF has performed well in the first year of implementation and has met almost all milestones.
Six projects worth over $91m total have been endorsed by the Steering Committee and the World Bank has built a strong pipeline of projects, despite the challenges of engaging with governments during the COVID-19 pandemic.
The World Bank has made progress on a multi-part Monitoring, Evaluation and Learning (MEL) strategy, although the full strategy is not ready for publication yet. The GRiF is intended to be a catalyst for innovation and test new approaches, so it is important to share this learning globally.
The programme pivoted quickly to respond to the effects of the COVID-19 pandemic, releasing $38m from projects in development and adapting projects in implementation to respond to the changing needs and priorities.
There have been some teething problems to resolve, which is to be expected in the first year of programme delivery. Stakeholders felt this was driven by a lack of common understanding of what the GRiF can and should prioritise.
The GRiF’s focus on new and innovative risk financing initiatives means projects carry an inherently high level of risk and uncertainty. This justifies a higher than usual level of DFID involvement in and scrutiny of project design. However, the amount of information we have access to at decision points does not currently reflect that higher risk. We often lack assurance that the benefits will be targeted to reach the poorest and most vulnerable beneficiaries, and justifications of costs or comparison with other options that may offer better value for money (VfM). We have a much higher level of control and influence over the GRiF than other comparable trust funds, particularly as more trust funds consolidate and tend to have donor engagement only at the highest strategic level.
The GRiF subsidises insurance premiums and funds the set-up of risk finance to incentivise countries to invest in disaster resilience. This is on the expectation that the recipient country will take ownership of its risk in the long term and continue funding the premiums after GRiF support ends. However, this is a difficult and politically unacceptable trade-off for many of the poorest and most fragile countries. There may be a case for part paying premiums in the long term, to incentivise countries to develop robust preparedness plans embedded within strong local and national systems for disaster response and recovery.
Major lessons and recommendations for the year ahead
[note] The Centre for Disaster Protection has written an independent stocktake of the GRiF, which I have considered when making these recommendations.
1. In order that gender and disability considerations are given due priority, a member of the Secretariat or Steering Committee should take explicit responsibility and champion role on gender and disability issues. Technical experts on gender and disability issues in disaster risk management should be available for consultation, perhaps as members of the technical working group.
2. The MEL strategy should be finalised, endorsed by the Steering Committee and published as soon as possible. If the GRiF is going to successfully build global standards and best practice, it is important to have global, as well as organisational, learning.
3. We will continue to raise the need for better VfM analysis and focus on target beneficiaries when concept proposals come to Steering Committee members for endorsement.
4. Work with the World Bank and Germany to agree Terms of Reference for the Technical Committee, to be approved at the next Steering Committee in October 2020.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change includes two key theories:
Governments are not well incentivised to financially plan for disasters. The opportunity costs of spending on uncertain future outcomes and the perceived political benefit of spending on a response effort discourage financial planning. Risk financing instruments can be complex, with the intangible benefits accruing at some indeterminate point in the future, so there is lack of awareness and lack of trust in market-based instruments.
As such, risk financing is not regularly considered in country budget decision making on development and financial planning. When disasters strike, governments are often unable to provide enough immediate financing to address response and recovery needs, so they must shift money away from other critical development programming or incur debt, both of which inhibit the country’s economic growth and affect the poorest households. External ‘free’ humanitarian assistance is unpredictable and often comes too late to salvage development gains.
If the GRiF:
- provides principle-based subsidies for risk financing instruments,
- funds preparedness plans and strengthened national systems and
- provides related technical assistance for DRF strategies,
then the Theory of Change expects that governments of disaster-prone countries will have:
- risk financing solutions that are linked to preparedness plans and delivery systems and
- holistic, strategic national disaster risk finance approaches.
- In the long term, more disaster finance will flow through pre-arranged systems and vulnerable countries will have greater financial resilience and earlier, more coordinated responses.
The second theory is around the multilateral system of disaster response and how GRiF investments will contribute to shifting the system towards more ex-ante approaches and away from ex-post finance. The potential market for risk transfer instruments is small, with inconsistent demand, so it is difficult for the private sector to provide disaster risk finance products. Multilaterals do provide disaster risk finance, but the instruments tend to be biased toward ex-post finance and have weak incentives for preparedness and prevention.
If the GRiF:
- invests in innovation, learning and public goods related to the larger eco-system surrounding risk finance;
- supports multi-partner projects;
- develops new ex-ante approaches; and
- supports development of global standards and best practice in DRF,
the Theory of Change expects that there will be:
- more effective, coordinated and coherent approaches to risk financing
- increased relevant knowledge, data and capacity for risk financing
- an enhanced range of risk financing instruments
- systems and capabilities to integrate risk finance within investments.
The impact of the GRiF is:
- A global shift towards more ex ante approaches to disaster finance.
- Reduced short-term impact of disasters (human suffering, financial losses) and faster recovery.
- Reduced long term impacts, including fewer people driven into poverty by disasters.
The Theory of Change has not changed since the business case was approved in August 2019. The GRiF secretariat at the World Bank have developed their own Theory of Change for the GRiF MDTF. This version is very similar but includes a greater emphasis on the longer-term continuous cycle of demonstration and learning that happens as pre-arranged financing instruments funded by GRiF investments activate due to disaster. As more of these pre-arranged financing mechanisms are triggered across different geographies and contexts, we (and our stakeholders) will be able to learn how risk planning and preparedness linked to risk finance solutions leads to improvements in DRF policy, data, and delivery systems.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
This is the first annual review. This year, six projects have been endorsed by the Steering Committee and are in progress (as well as the nine that were approved in the 2018-19 pilot). GRiF projects are usually embedded in larger World Bank programmes, which leverages extra resources and encourages these larger programmes to focus on preparedness. Naturally, it takes several months for a project to move from Steering Committee endorsement through the World Bank approval system and finally to the point where the risk financing mechanisms are in place. None of the projects have active risk financing arrangements yet, though the World Bank has made good progress with the technical assistance and set-up elements of several projects (Malawi, Sierra Leone). The impacts of the GRiF could only start to be achieved once these projects have live risk financing instruments. We expect projects to start to reach this stage in the next year.
Both outcomes are on track to be met within the time and total budget originally planned. The business case suggested a disbursement schedule spread over all years of the project, but we intend to frontload payments over the first few years. This is because projects take several months of implementation before the risk transfer mechanism is in place and results can be seen.
The first outcome (40%) is that the multilateral system has the right instruments and capabilities to enable a global shift toward more ex-ante approaches to disaster financing. This is starting to be realised within the World Bank, where the GRiF has increased awareness of risk financing and increased integration within other areas of development work in the Bank. For example, GRiF proposals are approved by country directors and the Vice President, whereas a straightforward TA project would not need such senior engagement. Country teams engage in the technical committee, review meetings, peer reviews and a QA process. Risk financing lessons are also shared through seminars and wider communications within the Bank. The GRiF's co financing element has a strong demonstration effect and can show that these innovative and high-risk investments can work, and the risks can be managed. This can only be achieved if the lessons from GRiF projects are assessed and shared openly, where appropriate.
The second outcome (60%) is increased sustainable financial resilience to disasters due to ex-ante risk financing linked to preparedness plans. The indicators include the cumulative number of countries with GRiF funded risk financing instruments in place, the value of risk covered by GRiF funded sovereign risk financing instruments and arrangements, and the percentage of GRiF projects with premium subsidy fully phased out. The GRiF supports investment in disaster resilience on the expectation that the recipient country will take long term ownership of its risk and continue funding the premiums after GRiF support ends. It is too early in the life of the programme to see results under any of these indicators, given the long lead time needed to build new domestic institutions and processes to manage risks, backed by political will and institutional capability. We expect to see some progress against these in the next year.
It is important that this increased financial resilience is sustainable. The GRiF requires countries to co-finance specific eligible expenditures to ensure full country ownership of the risk finance solution and work towards sustainable solutions that can continue even after grant funding ends. For IDA countries, grants from the GRiF match up to 100% of the funds committed by the government toward the costs of their financial protection strategy. For IBRD countries, grants from the GRiF match up to 50% of the funds committed by the government toward the costs of their financial protection strategy. The GRiF grant award could be up to $10 million per year and per project, with a maximum of $25 million per project for three years. The grant amount is typically expected to decline over the lifetime of the project, particularly in IBRD countries, to be financed by the country itself in the long term.
Some countries will not be able to afford to continue paying insurance premiums after GRiF funding ends, and some may not be able to afford even heavily subsidised premium payments. There may be a case for part paying premiums in the long term, to incentivise countries to develop robust preparedness plans embedded within strong local and national systems for disaster response and recovery. However, this would need a long-term commitment to continue subsidising premiums for decades, long after the end of the GRiF.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme’s outcomes and impact are on track to be met within the time and total budget originally planned. This is the first year of delivery, so the outcomes will become clearer in future years. Based on the above analysis of outcome and output achievement, theory of change and VfM analysis, the programme shows evidence of value for money and should be continued.
The GRiF complements other centrally managed programmes like African Risk Capacity, the Centre for Disaster Protection and country-based disaster resilience programmes. In line with DFID’s Single Departmental Plan, disaster risk finance will help to deliver finance more quickly during an emergency and support efforts to adapt to climate change.
The GRiF is intended to develop global standards and best practice for Disaster Risk Finance. The continuous cycle of demonstration and learning is a key part of this, so we will revise the Theory of Change to reflect this more clearly.

## C. DETAILED OUTPUT SCORING

Output Title	Countries purchase risk financing with premium subsidy and link to preparedness plans/national systems
Output number:		1	Output Score:	A
Impact weighting (%):		60	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of GRiF projects ongoing or implemented (and number in scoping ensuring a strong pipeline)	5 (15)	Not fully met / The Steering Committee have approved six GRiF projects for implementation this year, in addition to the three approved in the pilot phase. There are 19 projects in scoping, although only nine of these are actively being developed.
Number of gender-sensitive preparedness plans developed, or national systems strengthened with support from the GRiF	0	N/A / The projects are in early stage of implementation so GRiF support has not yet developed gender sensitive preparedness plans or strengthened national systems. This is expected in future years.
Roadmap to shifting from climate and natural disasters risk financing to broader crisis risk financing developed	Roadmap agreed by steering committee	Met / The Steering Committee endorsed the strategy for prioritisation of projects in April 2020, which includes a plan to broaden to new sectors and risks where appropriate.
Number of ongoing GRiF projects focusing on risk financing of risks from wider crises	0	Met / The GRiF has expanded to focus on other types of risk.

Briefly describe the output’s activities and provide supporting narrative for the score.
Number of GRiF projects and preparedness plans / strengthened national systems
In the first year of the GRiF’s implementation, the Steering Committee has approved six new grants worth $91.87m total in Indonesia, Morocco, Afghanistan, Jamaica, Malawi and support to the South East Asia Disaster Risk Insurance Facility (SEADRIF). There are 19 projects in scoping phase, nine of which are expected to be ready for Steering Committee endorsement later in 2020 and early 2021. The other 10 projects in scoping phase are not being actively developed at the moment but these could be brought back into the pipeline if circumstances change. See annex A for detail on each project.
The GRiF responded quickly and effectively to commit funds to projects. This rapid progress makes sense given that most are multiyear projects and it will take several months for the risk transfer instrument to be sourced.
The GRiF moved quickly to support the COVID-19 economic response by facilitating the release of essential liquidity through IDA for vulnerable countries. For example, the Sierra Leone grant (endorsed by the Steering Committee in the pilot phase) included pandemics as one possible risk to which the safety net could scale up. The GRiF grant is being used to mobilise $4 million in IDA funds held in contingency, which are being channelled to 29,000 informal sector workers impacted by COVID-19. The Malawi grant (endorsed September 2019) is providing technical assistance to support the Government of Malawi’s efforts to target assistance to around 315,000 households.
GRiF projects that were in the pipeline (Afghanistan, Indonesia) pivoted to include a COVID-19 response element to support countries in managing compound risks from COVID-19 and other disasters. The next 6-12 months is when countries will be most exposed to compound risks, so these interventions will reduce the risk of COVID-19 causing a larger economic and humanitarian crisis.
The Steering Committee furthermore agreed to repurpose $38m of GRiF funding for new, dedicated COVID-19 response projects. This will fund several new GRiF projects that will support countries in preparing for future pandemic impacts, including through scalable social protection programmes. The Steering Committee has not been asked to endorse any of these new projects yet, although there are some in scoping phase.
Roadmap to shifting to broader crisis risk financing
The Steering Committee endorsed the strategy for prioritisation of projects in April 2020, which includes a plan to broaden to new sectors and risks where appropriate. Initially GRiF support was given to World Bank projects that were already in development. In October 2019, the Steering Committee requested that the Secretariat outline its strategy for programming future investments. This strategy, including criteria for resource allocation based on geography, innovation, type of peril and priority sectors, was agreed at the April 2020 Steering Committee meeting, based on a stock take of existing investments and priorities for strengthening financial resilience to shocks.
Focus on risk financing of risks from wider crises
The GRiF has expanded to focus on other types of risk. For example, a project in Somalia (in the pipeline for Steering Committee endorsement in 2021) is working with UNOCHA towards joint development humanitarian planning for financial solutions to famine. The crisis risk analytics global analytics work program includes plans to extend risk financing to complex risks. This includes work to further strengthen the World Bank internal capacity on risk financing related to pandemics.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Economy: Most project proposals do not provide evidence to donors that grants are value for money. We lack information about targeting beneficiaries and assurance that the benefits will reach the poorest and most vulnerable for almost every project. Several projects are in middle income countries, so it is important that the World Bank is clear about how the intended beneficiaries are being targeted. Projects come to the Steering Committee for endorsement at an early stage of development, so we do not expect full details at this stage. However, proposals should include justifications of costs or comparison with other options that may offer better VfM. Some project proposals are not clear in distinguishing between TA, operational costs, start-up costs and premium financing. In one case, start-up costs were erroneously omitted from the original proposal so an additional request for $1.5m was received later.
Effectiveness and efficiency: It is too early to know the quality and reliability of the instruments due to be co-financed by the GRiF. This is because this information only really becomes apparent later in the process, once the instrument has been developed and its VfM can be assessed.
Equity: As disasters disproportionately impact women and people with disabilities, the GRiF will inevitably help to reduce the scale of impacts on these groups. Several of the project proposals include a gender and disability element, but these don’t have much detail on how the proposed financial instruments target marginalised groups such as women, people with disabilities and refugees, or how the linked preparedness plans and resilience-building activities will consider gender and disability.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
We have not made changes to this output during the past year. Given the changing crisis risk financing landscape due to COVID-19, we will consider changes to the indicator: “number of ongoing GRiF projects focusing on risk financing of risks from wider crises”.
The logframe includes several indicators which disaggregate gender data reporting, or which incorporate gender considerations. We will consider changes to the logframe indicators to include a focus on disability.
Lessons learned this year and recommendations for the year ahead
Some project proposals do not give enough information to assure us that the guiding principles of GRiF support are met. Some lack value for money analysis and detail on how support is targeted to beneficiaries.
It is important that preparedness plans and resilience-building activities consider gender and disability and financial instruments target marginalised groups. GRiF projects should also incentivise improvements in financial inclusion to ensure that women and people with disabilities have access to any benefits attributable to risk financing.
Gender, disability and inclusion considerations should be mainstreamed at scoping, implementation and evaluation stages of GRiF projects.
Stakeholders have expressed concern that World Bank instruments and internal technical assistance could be preferred to other insurance products available on the private market or private sector expertise. Using World Bank instruments and consultants allows complementarity with other work in that country, but some private market instruments align with World Bank strategy and should be considered..
[note] GRiF stocktake 2020, Centre for Disaster Protection
Recommendations
- In order that gender and disability considerations are given due priority, a member of the Secretariat or Steering Committee should take explicit responsibility and champion role on gender and disability issues, to hold project teams to account on progress. Technical experts on gender and disability issues in disaster risk management should be available for consultation, perhaps as members of the Technical Committee.
- Donors and the GRiF secretariat to have a working level discussion on gender and disability, to be elevated to the Steering Committee if necessary. This should include a discussion on how to ensure gender- and disability-sensitive preparedness plans which explicitly consider the financial, economic, health, social, and educational needs of women and people with disabilities. It should also include how to build on evidence around the disability- and gender-related impacts of disasters and their role to play in preparedness and resilience (for example, requiring financial instruments to account for assets owned by women and people with disabilities, including property, and if possible, indirect losses in damage estimates.
  [note] The World Bank’s Handbook for estimating the socio-economic and environmental effects of disasters gives innovative methods which may be able to address this. http://siteresources.worldbank.org/INTDISMGMT/Resources/10women.pdf
- Continue to raise the need for better VfM analysis and focus on target beneficiaries when concept proposals come to Steering Committee members for endorsement.

Output Title	Global standards, best practice, and innovative global public goods developed
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Percentage of GRiF projects implemented collaboratively through multiple partners / (total: humanitarian partners)	-	N/A / One project, endorsed in the pilot phase, is implemented in partnership with the Start Network.
Publication of M&E strategy and learning reports	M&E strategy completed	Partially met / The M&E strategy and learning reports have not been published, but we expect this soon.
Global risk financing standards and best practice developed and publicly available	Under development	Met / Global standards and best practice for risk financing are under development.
Cumulative number of global public goods supported by the GRiF (number collaborating with, using the expertise of, or building on the work of the Centre)	1 (0)	Met / 1 (0)

Briefly describe the output’s activities and provide supporting narrative for the score.
Implementation through multiple partners
Multi stakeholder GRiF projects are important to ensure ownership, suitable approaches and development impact for the poorest and most vulnerable people. The GRiF is supporting the Start Network to undertake a feasibility study and design for the Start Financing Facility, which would leverage different financial instruments to more efficiently provide funds to Start member organisations for crisis response.
Monitoring and Evaluation strategy
The GRiF is intended to be a catalyst for innovation and test new approaches, so it is important to have rigorous M&E and a commitment to learning. Stakeholders have commented that the World Bank has published very little on the GRiF so far and could be more transparent about how GRiF funding is used.
In 2019, the GRiF Secretariat began the process of designing a Monitoring, Evaluation, and Learning (MEL) Framework for the GRiF. The Steering Committee saw a draft at the April 2020 meeting, but it is not yet ready for publication. The Framework includes:
[note] World Bank GRiF annual report 2019
- A Theory of Change diagram and narrative
- A monitoring framework with indicators linked to the Theory of Change and processes for reporting.
- An evaluation framework linked to the results expected in the Theory of Change and Evaluation Framework, with a plan for evaluation over the lifetime of the GRiF trust fund.
- A learning plan with process and methods to ensure research, monitoring and evaluation findings feed back into programming to allow for internal adaptive learning.
This strategy will be used to assess the VfM of GRiF grants, monitor the GRiF’s implementation progress and provide independent evaluations and assessments of program impact.

Standards and best practice
A set of principles has been established to evaluate GRiF grants, which ultimately helps task teams reduce risks for recipient countries, donors, and implementing partners, and move toward increased standardisation in concessional support for risk finance and insurance. See Annex B for the full list.
The GRiF secretariat at the World Bank has developed a detailed communications strategy to better engage with key stakeholders and inform the global conversation on financial resilience. The approach involves explaining the GRiF’s role in enabling early action on climate shocks, disasters, and crises to unfamiliar audiences, elevating its visibility among World Bank teams and country governments to build momentum for GRiF support requests, and contributing to the general discourse on risk finance. Very little information about GRiF projects has been released to the public so far.
Global public goods
The Crisis & Disaster Risk Finance Analytics grant is supporting a programme of technical assistance that leverages innovative analytics at global, country, and project levels to create an enabling environment for improved risk financing and risk management. It is leveraging remote sensing, online/social media and big data to support global level identification of risks, national and sectoral diagnostics, and project-specific activities to enable better informed and earlier financial response to crises. It will finance the development of objective, timely, reliable risk metrics and triggers as well as innovative approaches to assess overlapping risks in complex situations.
[note] World Bank paper for the GRiF Steering Committee “Crisis and Disaster Risk Finance Roadmap”
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The GRiF is intended to be a catalyst for innovation and is “structured to allow flexibility to learn and adapt…” The MEL Framework developed by the World Bank emphasises the importance of a long-term continuous cycle of demonstration and learning. However, it does not include a commitment to share this learning externally and an independent, public evaluation of the GRiF. Few details about the GRiF’s activity are shared publicly, and stakeholders have noted that project proposals often lack comprehensive plans for monitoring progress and sharing learning widely.
[note] Business case p.iii
Describe any changes to this output during the past year, and any planned changes as a result of this review.
We have not made changes to this output during the past year. One global public good in the pipeline has been deprioritised due to external circumstances, so we may need to revise this milestone.
Lessons learned this year and recommendations for the year ahead
- If the GRiF is going to successfully build global standards and best practice, it is important to have global, as well as organisational learning. The MEL framework should be finalised and published as a priority.
- A summary of Steering Committee meetings should be made public.
Output Title	The GRiF’s governance is operational and effective
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of Steering Committee meetings completed	2	Met / Two Steering Committees have taken place, in October 2019 and April 2020.
Percentage of projects approved meeting minimum standards of the GRiF principles (unless agreed by SC)	100%	Met / 100% of approved projects meet the minimum standards of the GRiF principles.

Briefly describe the output’s activities and provide supporting narrative for the score.
The GRiF is intended to be a catalyst for innovation and experimentation, so GRiF funded projects will naturally carry a high level of risk and uncertainty. This justifies tighter governance processes than most other DFID trust funds at the World Bank.
The Steering Committee is the primary governing body and provides overall guidance and strategic advice on the priorities of activities. The Steering Committee comprises the World Bank (Chair), donors and observers agreed by the members. It met in October 2019 in Washington to discuss operational and governance processes and in April 2020 (virtually) to agree a response to the COVID-19 pandemic, endorse the strategy for prioritising projects and agree revisions to co-financing rules. It also met virtually in May 2019 and in Brussels in November 2018, during the pilot phase of the GRiF.
Steering Committee members are asked to endorse scoping and concept proposals for each grant. To inform our decision, we scrutinise the proposal against the GRiF principles and draw on expertise and technical analysis from the Centre for Disaster Protection. All endorsed projects meet at least the minimum standard of the principles agreed in the operations manual.
The operations manual describes the role of the multi-disciplinary Technical Committee, which supports the GRiF secretariat and teams at the World Bank as projects are developed after Steering Committee endorsement. We have no interaction with projects following Steering Committee endorsement, so the Technical Committee (which will include a DFID-appointed representative expert) is an important function to provide assurance that the project is VfM and designed to a high technical standard.
We have not been able to agree Terms of Reference for the Technical Committee. In the absence of participation in a functioning Technical Committee, we have fed back technical comments at the Steering Committee endorsement stage. When the Technical Committee is functioning well and has DFID representation, the Steering Committee may be able to step back from the technical aspect of project proposals.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
Efficiency and Effectiveness: We have very little influence over project design after Steering Committee approval, and often do not know exactly how DFID funds are spent. It is not possible for the Bank teams to provide enough detail at the Steering Committee endorsement stage, while the project is still in early stages of development, but we need assurance that projects are being designed to a high technical standard and continue to align with the GRiF principles, and an understanding of how DFID funds are being spent. Without the Technical Committee, the Steering Committee is not provided with enough information to fulfil its strategic oversight role adequately.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
We have not made changes to this output during the past year. It is important to agree Terms of Reference for the Technical Committee as soon as possible, so we will include an indicator to measure progress.
Lessons learned this year and recommendations for the year ahead
Work with the World Bank and Germany to agree Terms of Reference for the Technical Committee, to be approved at the next Steering Committee in October 2020.
D: RISK

Overview of risk management
The overall risk rating is major, increased from moderate.
This is the first year of delivery for the GRiF, so several of the risks in the early risk register have been closed or downgraded as the demand for GRiF grants, governance processes and key stakeholders became clearer. For example, two major delivery risks were that there would be insufficient technical capacity and expertise in the Bank, and that the pipeline for GRiF grants within the Bank would be weak. Early experience showed that both these risks were less likely than first expected, so both risks have been downgraded to moderate. Similarly, as the GRiF’s weaknesses became clearer, some new risks were added – the risk of delayed projects due to budget pressure, and the moderate operational risk that GRiF grants duplicate existing DFID funded work, due to lack of communication within DFID and the World Bank.
The GRiF focuses on innovative projects and “learning by doing” so there is a high level of inherent risk within the programme. However, most GRiF activities have been delivered comfortably within risk appetite. Our lack of influence over how GRiF grants are spent is putting increasing pressure on our operational risk. This will increase in the next year, unless we can agree terms for a well-functioning Technical Committee with DFID representation.
There are nine delivery risks, four of which are major.
These are the risks that DFID becomes a smaller donor and loses strategic influence or does not achieve the key outcome of integrating disaster risk finance into multilaterals. There is also a risk that countries are not able to continue to fund insurance premiums after GRiF support ends (usually after three years). All premium subsidies must be co funded by the recipient country, but many use their IDA allocation rather than committing funds from the domestic budget. The economic effects of the COVID-19 pandemic mean countries may be unable to prioritise disaster financing, so this risk may increase in the next year.
There is a new risk that budget pressure in 2020 (due to COVID-19 impacts and reduced GNI) means we can't fund any new GRiF projects that the Bank have developed. We intended to spend up to £50m on new projects in 2020, but it was reduced to £23.1m to help DFID fund immediate COVID-19 priorities. This was added as a severe risk, given the risk of not being able to pay for projects that have already been developed, and the need to rely on the Government of Germany, as the other donor to the GRiF, to provide funding to cover immediate shortfalls. The risk was reduced to major in July, following clarity of DFID’s overall budget position for 2020 and our subsequent payment to the GRiF MDTF. This budget pressure does not affect this year’s results but may delay results in future years and the logframe milestones will be adjusted accordingly.
Two delivery risks were downgraded from major to moderate in June and one new delivery risk was added. This is the moderate risk that lack of communication within DFID and the Bank on GRiF funded technical assistance and capacity building activity leads to DFID funding the same support twice. This is mitigated by monitoring DRF capacity building activities and asking the World Bank to work alongside other organisations where there is a potential overlap.
There are four operational risks (all moderate or minor), one context risk (moderate) and one reputational risk (minor).
There is minor fiduciary risk, that implementing partners and recipient governments spend GRiF grants on areas outside the scope of approved GRiF activity. We are content that the World Bank’s internal procurement and fraud risk processes are robust, so management of this risk is delegated to the World Bank. Similarly, the safeguarding risk is minor, as all GRiF grants implemented through the World Bank incorporate, and are subject to, the Bank’s Anti-Corruption Guidelines, the Procurement and Consultant Guidelines, and the Standard Conditions for Trust Fund Grants. Grants can be suspended, cancelled and/or refunded in the event of fraud or corruption.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The total cost of the programme to DFID is £90m over seven years. This includes all implementing activities, such as monitoring and evaluation and management costs. Germany has committed €115m over the same period and all costs are split 50:50 between Germany and the UK.
Of the total £90m UK contribution, at least £45m and up to £90m will be paid to the GRiF multi donor trust fund at the World Bank. So far, DFID has made contributions to the MDTF of £35m in December 2019 and £7m in July 2020. Most of this has been allocated to projects. Implementing partners have commented that the amount and timing of DFID payments into the GRiF trust fund is uncertain and unpredictable, which makes planning difficult.
This year, $91.87m has been allocated across six GRiF projects. In addition to the grants, $5m has been allocated for management costs since the start of the programme (including the 2018-19 pilot). $1.8m of this has been spent so far. Before the end of 2020, we expect a further c$77m of GRiF grants to come to the Steering Committee for endorsement.
The pipeline for 2021 is strong, although 10 projects previously approved for scoping have been deprioritised or delayed due to the effects of the COVID-19 pandemic and changing external contexts.
There are clear and significant benefits to working through the World Bank. For example, it allows access to the Bank’s experience and links with finance ministries. GRiF projects delivered through the World Bank are embedded in larger Bank resilience initiatives and concessional finance, so are more attractive to governments. However, working solely through the World Bank also brings disadvantages. For example, institutional bias to the Bank’s own strategy and instruments, a smaller footprint in fragile and conflict affected countries, limited transparency and limited partnerships with regional organisations (like ADB, IDB and ARC).
[note] GRiF stocktake 2020, Centre for Disaster Protection
The African Disaster Risk Financing framework (ADRiFi) was set up by the African Development Bank (ADB) to subsidise insurance premiums for African Risk Capacity products. Some GRiF support will be delivered through the ADRiFi mechanism, to increase the ADB’s capacity and support the relationship between African Risk Capacity and ADB. The ADB has a strong relationship with country governments and provides an additional avenue for the GRiF programme to meet its objectives. £2m is due to be paid to ADRiFi in September, with scope to allocate more in future.
We monitor the GRiF’s progress through donor reports, reporting from the World Bank and financial reports on the World Bank Development Partner Centre, using the logframe and workplans from the World Bank as benchmarks. At the fourth GRiF Steering Committee meeting in April 2020, the Secretariat was asked to share periodic updates on its portfolio. We received the first of these donor updates in July 2020. They are a useful summary of Trust Fund activity, to be read in parallel with the financial reports on the World Bank Development Partner Centre.
The GRiF secretariat at the World Bank have been responsive to requests for programme management information and open about forthcoming grant proposals, which are always sent to donors with enough time for review. We received the World Bank’s annual report on the GRiF in October, as requested.
There have been some teething problems to resolve, which is to be expected in the first year of programme delivery. Stakeholders felt this was driven by a lack of common understanding of what the GRiF can and should prioritise.
Stakeholders have commented that DFID has a high turnover of staff, which means there is lack of continuity and institutional knowledge.
Date of last narrative financial report	July 2020	Date of last audited annual statement	N/A – due in September 2020

Annex A – GRiF projects in implementation
GRiF projects in implementation:
Project	Grant amount	Steering Committee endorsement	Description
Indonesia	$14m	July 2020	Supports a $500 million Investment Project Financing operation to support the establishment of a pooling fund for disasters in Indonesia under the supervision of the Ministry of Finance. This will finance activities supporting investments and technical assistance to build the capacity in and systems of the pooling fund. It will not provide any capital to the pooling fund itself.
Morocco	$5m	June 2020	Technical work to expand the financial resilience of Morocco’s public solidarity fund by supporting a parametric flood bond and modelling and raising awareness on drought risk.
SEADRIF	$10.5m	June 2020	Work to expand and enhance SEADRIF to improve access to cost-effective and pre-arranged financing for responding to climate shocks and disasters, through a regional insurance mechanism.
Afghanistan	$25m	June 2020	Work to develop a social protection delivery system, targeted to the needs of the chronically and seasonally food insecure households, which would be scaled up to respond in a shock.
Jamaica	$16.37m	September 2019	Payment of premiums for sovereign risk transfer coverage for three years, through a catastrophe bond, and start-up costs for the cat bond. The GRiF contribution will reduce over time and the Government of Jamaica will make increasing payments.
Malawi	$21m	September 2019	Technical assistance associated with strengthening the social protection system, setting up the contingency fund, capacity building, risk analysis, and policy strengthening and financial support for a risk transfer instrument investment to protect against drought and flood risks.
Total in reporting period	$91.865m

There are a further nine projects in implementation, endorsed and funded as part of the pilot phase.
Annex B – Guiding principles of GRiF support
[note] World Bank 2019 GRiF annual report