## Impact
Girls' Education South Sudan Phase 2
IMPACT | Impact Indicator 1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
Increased number of South Sudanese children (particularly but not exclusively girls) whose life chances are transformed through education. | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1)) (Per Year) | Planned | 0.87 | 0.84 | 0.88 | 0.92 | 0.96 | 1 | State, Gender, Disability. | The impact may be permanent, although a long-term impact on the sustainability of the education sector requires positive changes in the context (in particular the economy and the conflict with peace holding) and the political will of the Government of the Republic of South Sudan (GRSS). Thus a major assumption is that there will be a conducive atmosphere that will support the donor operations in contributing to the achievement of Ministry of General Education and Instruction (MoGEI) strategic goals and the overall development goals of the nation.
|  | Achieved |  | 0.83 |  |  |  |  | See tab 10 for details.
Source and Comments:
Source: Schools' Attendance Monitoring System (SAMS). Comments: Reasons for missing the target are beyond the control of the Programme. This suggests that there is still a concern regarding enrolment and completion of girls, some barriers to girls’ education persist. GESS is making all efforts to contribute towards closing this gap.
| Impact Indicator 2 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) (Per Year) | Planned | 0.65 | 0.64 | 0.68 | 0.72 | 0.76 | 0.8 | State, Gender, Disability
|  | Achieved |  | 0.63 |  |  |  |  | See tab 10 for details.
Source and Comments:
Source: SAMS. Comments: Reasons for missing the target are beyond the control of the Programme. This suggests that there is still a concern regarding enrolment and completion of girls, some barriers to girls’ education persist. GESS is making all efforts to contribute towards closing this gap.
| Impact Indicator 3 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Total Number of children enrolled in schools (Annually - Academic Year) | Planned | 1784664 | 2088056.88 | 2284632.88 | 2500645.88 | 2739624.88 | 2978603.88 | State, School type, Gender, Grade, Disability
|  | Achieved |  | 2186024 |  |  |  |  | See tab 10 for details.
Source and Comments:
Source: GESS 1 Endline Results and SAMS. Comments: (1.) Baseline is for 1st May 2019. Milestones are set for December 2019 to follow academic calendar. The last quarter is used to triangulate Education Management Information System (EMIS) and SAMS data as part of final validation and reporting ahead of cut-off date of 31st March. (2.) All data with regard to targets and milestones to be disaggregated by age, disability, gender and location. (3.) Enrolment data is based on schools reached by GESS interventions. It is assumed that DFID funding accounts for significant percentage. At year end, GESS will report on the percentage of learners attributed to DFID based on funding share and other relevant factors. (4) Attribution for Impact Indicator 3 will be updated and reported annually while progress on enrolment will be reported quarterly.
INPUTS | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Outcome
Girls' Education South Sudan Phase 2
OUTCOMES | Outcome Indicator 1 |  | Baseline 2018 PLE | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
An improvement in girls' educational attainment from that already achieved in GESS Phase 1; building further gains on school enrolment, reducing barriers to education and promoting equity in access for all children. | % of girls passing Primary Leaving Examination (PLE) | Planned | 76.27% | 77.5% | 76% | 75.3% | 75.5% | 73.8% | State, Grade, Gender, Disability. | Political situation remains stable and conflict does not start. Educational facilities/infrastructure is redeveloped and rehabilitated (schools and classrooms) to accommodate the increase number of learners including in upper primary and secondary schools. Access to upper primary and secondary education facilities expands. Data of learners is effectively disaggregated. The number of teachers present in schools in South Sudan remains the same or increases. The attitude in the South Sudanese society is changed towards support of girls’ education. South Sudan continues to hold National Examination and the Programme is able to access disaggregated examination results to inform analysis.
|  | Achieved |  | 84.9% |  |  |  |  | See tab 10 for details.
Source and Comments
Source: MoGEI Examination Reports, SAMS/HRIS/RA/PMT Reports & Analysis. Comments: Baseline for PLE and SSCSE is 2018 exams results. Examination milestones and targets was set after a review historical examination records at the MoGEI at the start of the implementation phase of the Programme. There is no easily accessible disaggregated examination for PLE and SSCSE which could be used to analyse examination results trends. Consideration also needs to be taken of the expected influx of returnees and OOSC during the course of the GESS2 programme.
| Outcome Indicator 2 |  | Baseline 2018 SSCSE | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| % of girls passing South Sudan Certificate of Secondary Education (SSCSE) | Planned | 76.3% | 73.4% | 76.3% | 77.8% | 79.2% | 79.3% | State, Grade, Gender, Disability.
|  | Achieved |  | 93.2% |  |  |  |  | See tab 10 for details.
Source and Comments
Source: MoGEI Examination Reports, SAMS/HRIS/RA/PMT Reports & Analysis. Comments: Baseline for PLE and SSCSE is 2018 exams results. Examination milestones and targets was set after a review historical examination records at the MoGEI at the start of the implementation phase of the Programme. There is no easily accessible disaggregated examination for PLE and SSCSE which could be used to analyse examination results trends. Consideration also needs to be taken of the expected influx of returnees and OOSC during the course of the GESS2 programme.
| Outcome Indicator 3 |  | Baseline 2018 (March 2019) | Milestone (December 2019) | Milestone (December 2020) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Number of girls enrolled in upper primary (P5-P8) | Planned | 298220 | 330087 | 375362 | 415769 | 458081 | 527893 | State, Grade, Gender, Disability.
|  | Achieved |  | 344635 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/EMIS/PMT Reports and Analysis.
| Outcome Indicator 4 |  | Baseline 2018 (March 2019) | Milestone (December 2019) | Milestone (December 2020) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Number of girls enrolled in secondary schools (S1-S4) | Planned | 36555 | 39202 | 46846 | 52462 | 56462 | 70243 | State, Grade, Gender, Disability.
|  | Achieved |  | 44544 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/EMIS/PMT
| Outcome Indicator 5 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| % of teachers demonstrating inclusive practices during lessons | Planned | 218 head teachers and 1918 teachers in 218 schools. | N/A | 10% | 15% | 20% | 25% | State, Gender, Disability.
|  | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
Source and Comments
Source: Regional Anchor and Sub-output 4.1 Training Reports. Comments: GESS Phase 1 TPD included elements of disability inclusion. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and implementation rolled out. Outcome 5 will be aligned with sub-output 4.1 in terms of training provided to these teachers which will include disability inclusion and gender-responsive pedagogy.
INPUTS (£) | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Output 1
Girls' Education South Sudan Phase 2
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021 - Midline) | Milestone (March 2022) | Target (March 2023 - Endline) | (March 2024) | Disaggregation | Assumptions
Communication to girls, boys, women and men to shift attitudes and behaviour related to the education of girls and children with disabilities. | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children. (Non Cumulative) | Planned | 1.9 million | N/A | 1.9 million | N/A | 2.0 million | N/A | State, Gender, Disability | Changing attitudes towards the importance of girls' education will lead to an increase in enrolment, retention and completion rates of girls and reduction of dropout rates at secondary school level.
|  | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
Source and Comments
|  |  | Source: Quantitative Surveys / Population Reference Bureau. Comments: Baseline already set and is derived from GESS Phase 1 Endline achieved September 30th 2018. Sub-output 1.1 will subsequently be measured at Midline in 2021 and at Endline in 2023 (this is also the overall target of the Programme reached by March 2024). To avoid double counting, March 2024 reads not applicable (N/A) as endline overall target of the Programme measured at midline which covers the Programme period of April 2023 - March 2024 - year 5 of the Programme. 2020 and 2022 milestones are N/A. Two nationally representative quantitative surveys will be conducted at Midline (early 2021) and Endline (early 2023). Among other questions, respondents will be asked whether they have listened to the girls’ education radio outputs and when they last listened. Those who have listened within the last year will be counted as “reached”. The percentage of survey respondents reached will be multiplied by the population figure for South Sudan (an estimate taking into account population movements) to find out the number of South Sudanese adults reached by the radio outputs. Non cumulative means targets are only counted for that particular milestone period. | Non cumulative. BBC MA mid and endline survey
| Output Indicator 1.2 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Number of school communities' reached with the community mobilisation (Cumulative) | Planned | 1763 | N/A | 300 | 1000 | 1800 | 2700 | State, Gender, Disability
|  | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
Source and Comments
|  |  | Source: Community Mobilisation Reports. Comments: Baseline already set and is derived from GESS Phase 1 Endline achieved by September 30th 2018. Milestone for March 2020 is N/A as community mobilisation activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation of community mobilisation activities. Community mobilisation officers/volunteers will be responsible for the measurement of the number of school communities taking part in the community mobilisation activity. They will use Kobo Collect Toolbox, a free open-source tool for mobile data collection, to collect the data and submit it to Sub-output 1.2 Community Mobilisation technical lead. The mobile data will be analysed and reported throughout the project. | Cumulative. GESS activity reports
INPUTS | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Output 2
Girls' Education South Sudan Phase 2
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
Cash transfers to girls to improve enrolment, retention, transition and completion rates. | Cumulative number of (unique, individual) girls receiving cash transfers | Planned | 295415 | 315000 | 375000 | 440000 | 487500 | 574599 | State, Gender, Grade, Disability | The current peace agreement holds resulting in schools affected by conflict reopening. Access to upper primary and secondary education increases. Transition to secondary education increases. The financial institutions continue to develop and expand with agency banking and other cheaper/cost-effective options of delivering cash to eligible beneficiaries within the VfM framework. Cash transfers will have positive impact on enrolment, retention and completion rates; improving on the number of beneficiaries receiving a payment more than once over the life of the Programme.
|  | Achieved |  | 374127 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/PMT/RA/MoGEI Reports and Analysis. Comments: Baseline is endline figures of girls paid at in 2017 of GESS Phase 1. Output 2 is adaptive to the extent that differentiated value amounts are being paid to specific year groups. For 2019 these year groups are: P5 to encourage transition of girls from lower to upper primary; and P8 and S4 examination candidate classes transitioning to next level - secondary and post-secondary respectively.
| Output Indicator 2.2 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
| Cumulative Number of cash transfers received | Planned | 522000 | 315000 | 627000 | 900000 | 1200000 | 1900000 | State, Gender, Grade, Disability
|  | Achieved |  | 398499 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/PMT/RA/MoGEI Reports and Analysis. Comments: Baseline is endline figures of girls paid at in 2017 of GESS Phase 1. Output 2 is adaptive to the extent that differentiated value amounts are being paid to specific year groups. For 2019 these year groups are: P5 to encourage transition of girls from lower to upper primary; and P8 and S4 examination candidate classes transitioning to next level - secondary and post-secondary respectively.
INPUTS (£) | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Output 3
Girls' Education South Sudan Phase 2
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
Capitation Grants to schools to improve learning environment for all learners. | Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GRSS. | Planned | 4387 | 4200 | 4300 | 4370 | 4500 | 4800 | State, Ownership (Government School, Community School, Faith-based). | Capitation grants allow schools to remain open. Government continues to pay teachers (even in an ad hoc manner). Government continues to support secondary schools teachers incentives. EU IMPACT project continues to pay top-ups incentives to primary school teachers and the GRSS has budget provisions to take over when funding comes to an end. Improvement of school learning environment including sanitation facilities result in increased enrolment, attendance, retention and completion rates of girls and children with disabilities.
|  | Achieved |  | 4312 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/MoGEI/PMT/RA. Comment: A significant percentage of schools that were reached under GESS 1 are now not operational, as they were affected by conflict particularly in 2016 onwards. The Programme will have to make efforts in assisting these schools to reopen/operationalisation.
| Output Indicator 3.2 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | Planned | 4055 | 3800 | 3900 | 4000 | 4100 | 4300 | State, Ownership (Government School, Community School, Faith-based).
|  | Achieved |  | 3899 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/MoGEI/PMT/RA. Comment: IMPORTANT to note that GESS is not in control of Primary Schools CGs' payments being made therefore this sub-output tracks the efforts and support provided by GESS to influence MoGEI/GRSS to adequately budget for Primary Schools CGs, influence GRSS/MoFEP/MoGEI to ensure disbursements are made timely and correctly, help schools qualify, utilise and account for CGs.
| Output Indicator 3.3 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative Number of Secondary Schools that have received Capitation Grants by GESS (Schools that received Capitation Grants in GESS 1) | Planned | 317 | 185 | 215 | 250 | 295 | 300 | State, Ownership (Government School, Community School, Faith-based).
|  | Achieved |  | 190 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/MoGEI/PMT/RA. Comment: A significant percentage of schools that were reached under GESS 1 are now not operational, as they were affected by conflict particularly in 2016 onwards. The Programme will have to make efforts in assisting these schools to reopen. Operationalising some of these schools may not be possible because of ongoing conflict/instability. *Consequently the original target of 420 is currently under review and potential amendment.
| Output Indicator 3.4 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | Planned | N/A | 45 | 50 | 60 | 75 | 80 | State, Ownership (Government School, Community School, Faith-based).
|  | Achieved |  | 48 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: SAMS/MoGEI/PMT/RA. Comment: This sub-output will target and track schools that were not reached in GESS 1.
INPUTS | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Output 4
Girls' Education South Sudan Phase 2
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
Quality of Education, Learning Groups & Resilience to contribute to improving learning outcomes. | Cumulative number of teachers who participated in training, including training on gender-responsive and inclusive teaching methods | Planned | 218 head teachers and 1918 teachers in 218 schools. | N/A | 500 | 1250 | 1750 | 2500 | State, Gender, Disability | Government and sector donors support the rollout of the new curriculum. Teachers are deployed, have teaching scripts/guides, follow the new curriculum, introduce teaching standards and raise pupil attainment. Learning from Teacher Professional Development (TPD) and sector wide evaluation will be used to make improvements to the delivery of all sub-outputs. Head teachers and teachers willing and able to use new skills in their schools. Mentoring, school governance is necessary to improve enrolment, transition and completion. Causes of teacher demotivation other than lack of professional development opportunities do not hinder teachers in putting new skills into use. Teachers trained stay in the profession.
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: Baseline already set and is derived from GESS Phase 1 Endline achieved September 30th 2018. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation. Training will include inclusive and gender-responsive pedagogy (which links to Outcome Indicator 5).
| Output indicator 4.2 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of learners in primary Accelerated Learning Programme (ALP) | Planned | 30376 | N/A | 34279 | 37021 | 40723 | 47500 | State, Gender, Grade, Disability
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: 2018 SAMS data of learners enrolled in ALP schools informs our baseline. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation.
| Output Indicator 4.3 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of learners in Accelerated Secondary Education | Planned | 0 | N/A | 500 | 1250 | 1750 | 2500 | State, Gender, Grade, Disability
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: No baseline because ALP was not part of GESS Phase 1 and there are no ALP Secondary Schools in Country. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation.
| Output Indicator 4.4 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of learners participating in mentoring programme | Planned | Estimated 7,015 girls in 305 schools | N/A | 7500 | 22500 | 37500 | 70000 | State, Gender, Disability
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: Baseline for learners and schools is derived from GESS Phase 1 Endline achieved September 30th 2018. During GESS 1, schools were targeted, tracked consistently however learners were not. Therefore, the baseline of number of learners is an estimate. In GESS 2, learners will be targeted, tracked and counted systematically, disaggregated by school to show coverage. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and implementation rolled out.
| Output Indicator 4.5 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of School Management Committees Trained | Planned | 2699 | N/A | 3259 | 3819 | 4379 | 4500 | State
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: Baseline for schools reached already set and is derived from GESS Phase 1 Endline achieved September 30th 2018. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation.
| Output Indicator 4.6 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of Education Management Staff Trained | Planned | 0 | N/A | 250 | 500 | 750 | 1000 | State, Gender, Disability
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: Baseline not available as training of education managers was not part of GESS Phase 1. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation.
| Output Indicator 4.7 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Cumulative number of Payam Education Supervisors (PES) trained on Supportive Supervision | Planned | 500 | N/A | 100 | 200 | 350 | 500 | State, Gender, Disability
| TPD - No. of schools provided with SLPs | Achieved |  | N/A |  |  |  |  | See tab 10 for details.
| TPD - No. of teachers receiving English language training (at least 20% female) |  | Source and Comments
Source: Regional Anchor and Output 4 Training Reports. Comments: Baseline Payam Education Supervisors (PES) already set and is derived from GESS Phase 1 Endline achieved September 30th 2018. Milestone for March 2020 is N/A as activities will only start in 2020 when new Regional Anchors have been contracted, trained and then roll out implementation.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Output 5
Girls' Education South Sudan Phase 2
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation | Assumptions
Building a knowledge base for support to girls’ education. | Number of research and evaluation studies conducted for GESS 2 (Cumulative) | Planned | 17 | 2 | 7 | 11 | 15 | 19 | None | Policymakers willing and able to use new research skills, competencies and findings to improve quality of education particularly for girls and children with disabilities.
|  | Achieved |  | 2 |  |  |  |  | See tab 10 for details.
Source and Comments
Source: Research reports and learning assessment records. Comments: Data collection and entry is disaggregated by location, gender and disability where applicable.
| Output Indicator 5.2 |  | Baseline 2018 (March 2019) | Milestone (December 2019) | Milestone (December2020) | Milestone ( December 2021) | Milestone ( December 2022) | Milestone (December 2023) | Disaggregation
| % of schools reporting regular attendance through SAMS | Planned | 81.61% | 35% | 50% | 60% | 70% | 82% | State
|  | Achieved |  | 55% |  |  |  |  | See tab 10 for details.
|  |  | Source and Comments | [7 empty] | ,
Source: SAMS Data Analysis
| Output Indicator 5.3 |  | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024) | Disaggregation
| Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG) (Cumulative) | Planned | 0 | 8 | 20 | 32 | 44 | 56 | Attendees: MoGEI, GESS |  |  | .
|  | Achieved |  | 7 |  |  |  |  | See tab 10 for details.
|  |  | Source and Comments | [7 empty] | ,
Source: TWG Reports/Minutes. Comments: Baseline is 0 as TWGs are yet to be formulated and consistently organised and monitored. Target for 2020 not met due to COVID-19 restrictions.
INPUTS | DFID (£) |  | GRSS (£) | Other (£) | Total (£) | DFID SHARE (%)
68.4m *
Abbreviations
ALP | Accelerated Learning Programme
BoGs | Board of Governance
DFID | Department for International Development
DFATD/GAC | Department of Foreign Affairs, Trade & Development/Global Affairs Canada
EMIS | Education Management Information System
EU | European Union
GESS | Girls' Education South Sudan
GPI | Gender Parity Index
GRSS | Government of Republic of South Sudan
HRIS | Human Resource Information System
IDP | Internally Displaced Person/s
M&E | Monitoring and Evaluation
MoGEI | Ministry of General Education & Instruction
MoFEP | Ministry of Finance and Economic Planning
N/A | Not Applicable
OOSC | Out Of School Children
P | Primary
PES | Payam Education Supervisors
PLE | Primary Leaving Examinations
PMT | Project Management Team
RA | Regional Anchor
S | Secondary
SAMS | Schools' Attendance Monitoring System
SMC | School Management Committee
SSCSE | South Sudan Certificate of Secondary Education
TBD | To Be Determined
TPD | Teacher Professional Development
TWG | Technical Working Group
VfM | Value for Money
* Note: DOES NOT INCLUDE DFATD/GAC FUNDS

## Summary
Result | Indicator # | Indicator description
Impact Increased number of South Sudanese children (not particularly but not exclusively girls) whose life chances are transformed through education | 1.1 | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1))
| 1.2 | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1))
| 1.3 | Total Number of children enrolled in schools
Outcome An improvement in girls' educational attainment from that already achieved in GESS 1; building further gains on school enrolment, reducing barriers to education and promoting equity in access for all children. | 1.1 | % of girls passing PLE
| 1.2 | % of girls passing SSCSE
| 1.3 | Number of girls enrolled in upper primary (P5-P8)
| 1.4 | Number of girls enrolled in secondary schools (S1-S4)
| 1.5 | % of teachers demonstrating inclusive practices during lessons
Output 1 Communication to girls, boys, women and men to shift attitudes and behaviour related to the education of girls and children with disabilities. | 1.1 | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children.
| 1.2 | Number of school communities' reached with the community mobilisation.
Output 2 Cash transfers to girls to improve enrolment, retention, transition and completion rates. | 2.1 | Cumulative number of (unique, individual) girls receiving Cash Transfers.
| 2.2 | Cumulative Number of cash transfers received
Output 3 Capitation Grants to schools to improve learning environment for all learners | 3.1 | Cumulative Number of Primary Schools that are approved for Capitation Grant payment by MoGEI/GRSS.
| 3.2 | Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS.
| 3.3 | Cumulative Number of Secondary Schools that have received Capitation Grant by GESS (Schools that received Capitation Grants in GESS 1)
| 3.4 | Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2
Output 4 Quality of Education, Learning Groups & Resilience to contribute to improving learning outcomes. | 4.1 | Number of Teachers who participated in training
| 4.2 | Number of learners in primary Accelerated Learning Programme (ALP)
| 4.3 | Number of learners in Accelerated Secondary Education
| 4.4 | Number of learners participating in mentoring programme
| 4.5 | Number of School Management Committees Trained
| 4.6 | Number of Education Management Staff Trained
| 4.7 | Number of Payam Education Supervisors (PES) trained on Supportive Supervision
Output 5 Building a knowledge base for support to girls’ education | 5.1 | Number of research and evaluation studies conducted
| 5.2 | % of schools reporting regular attendance through SAMS
| 5.3 | Number of research sharing/dissemination meetings held by M&E Technical Working Group

## Overall Targets
Result | Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Impact | 1.1 | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1) | 0.87 | 0.84 | 0.88 | 0.92 | 0.96 | 1
| 1.2 | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1) | 0.65 | 0.64 | 0.68 | 0.72 | 0.76 | 0.8
| 1.3 | Total Number of children enrolled in schools | 1784664 | 2088056.88 | 2284632.88 | 2500645.88 | 2739624.88 | 2978603.88
Outcome | Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
| 1.1 | % of girls passing PLE | 76.3% | 77.5% | 76% | 75.3% | 75.5% | 73.8%
| 1.2 | % of girls passing SSCSE | 76.3% | 77.5% | 76% | 75.3% | 75.5% | 73.8%
| 1.3 | Number of girls enrolled in upper primary (P5-P8) | 298220 | 330087 | 375362 | 415769 | 458081 | 527893
| 1.4 | Number of girls enrolled in secondary schools (S1-S4) | 36555 | 39202 | 46846 | 52462 | 56462 | 70243
| 1.5 | % of teachers demonstrating inclusive practices during lessons | 218 head teachers and 1918 teachers in 218 schools. | N/A | 10% | 15% | 20% | 25%
| Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Output 1 | 1.1 | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children | 1.9 million | N/A | 1.9 million | N/A | 2.0 million | N/A
| 1.2 | Number of school communities' reached with the community mobilisation | 1763 | N/A | 300 | 1000 | 1800 | 2700
| Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Output 2 | 2.1 | Number of girls receiving cash transfers for the first time | 295415 | 315000 | 375000 | 440000 | 487500 | 574599
| 2.2 | Total Number of girls cash transfers received | 522000 | 315000 | 627000 | 900000 | 1200000 | 1900000
| Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Output 3 | 3.1 | Cumulative Number of Primary Schools that are approved for Capitation Grants payment by MoGEI/GRSS | 4387 | 4200 | 4300 | 4370 | 4500 | 4800
| 3.2 | Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | 4055 | 3800 | 3900 | 4000 | 4100 | 4300
| 3.3 | Cumulative Number of Secondary Schools that have received Capitation Grant by GESS (Schools that received Capitation Grants in GESS 1) | 317 | 185 | 215 | 250 | 295 | 300
| 3.4 | Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | N/A | 45 | 50 | 60 | 75 | 80
| Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Output 4 | 4.1 | Number of Teachers who participated in training | 218 head teachers and 1918 teachers in 218 schools. | N/A | 500 | 1250 | 1750 | 2500
| 4.2 | Number of learners in primary Accelerated Learning Programme (ALP) | 30376 | N/A | 34279 | 37021 | 40723 | 47500
| 4.3 | Number of learners in Accelerated Secondary Education | 0 | N/A | 500 | 1250 | 1250 | 2500
| 4.4 | Number of learners participating in mentoring programme | Estimated 7,015 girls in 305 schools | N/A | 7500 | 22500 | 37500 | 70000
| 4.5 | Number of School Management Committees Trained | 2699 | N/A | 3259 | 3819 | 4379 | 4500
| 4.6 | Number of Education Management Staff Trained | 0 | N/A | 250 | 500 | 750 | 1000
| 4.7 | Number of Payam Education Supervisors (PES) trained on Supportive Supervision | 500 | N/A | 100 | 200 | 350 | 500
| Indicator # | Indicator description | Baseline 2018 (March 2019) | Milestone (March 2020) | Milestone (March 2021) | Milestone (March 2022) | Milestone (March 2023) | Target (March 2024)
Output 5 | 5.1 | Number of research and evaluation studies conducted | 17 | 2 | 7 | 11 | 15 | 19
| 5.2 | % of schools reporting regular attendance through SAMS | 81.68% | 35% | 50% | 60% | 70% | 82%
| 5.3 | Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG) | N/A | 8 | 20 | 32 | 44 | 56

## Disaggregation Categories
Disaggregation Category
Result | Indicator # | Indicator description | State | School Ownership | Gender | Grade | Disability
Impact | 1.1 | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1)) | x |  | x |  | x
| 1.2 | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) | x |  | x |  | x
| 1.3 | Total Number of children enrolled in schools | x |  | x | x | x
Outcome | 1.1 | % of girls passing PLE | x |  | x | x | x
| 1.2 | % of girls passing SSCSE | x |  | x | x | x
| 1.3 | Number of girls enrolled in upper primary (P5-P8) | x |  | x | x | x
| 1.4 | Number of girls enrolled in secondary schools (S1-S4) | x |  | x | x | x
| 1.5 | % of teachers demonstrating inclusive practices during lessons | x |  | x |  | x
Output 1 | 1.1 | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children | x |  | x |  | x
| 1.2 | Number of school communities' reached with the community mobilisation | x
Output 2 | 2.1 | Number of girls receiving cash transfers for the first time | x |  | x | x | x
| 2.2 | Total Number of girls cash transfers received | x |  | x | x | x
Output 3 | 3.1 | Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GRSS | x | x
| 3.2 | Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | x | x
| 3.3 | Cumulative Number of Secondary Schools that have received Capitation Grant by GESS (Schools that received Capitation Grants in GESS 1) | x | x
| 3.4 | Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | x | x
Output 4 | 4.1 | Number of Teachers who participated in training | x |  | x |  | x
| 4.2 | Number of learners in primary Accelerated Learning Programme (ALP) | x |  | x | x | x
| 4.3 | Number of learners in Accelerated Secondary Education | x |  | x | x | x
| 4.4 | Number of learners participating in mentoring programme | x |  | x |  | x
| 4.5 | Number of School Management Committees Trained | x
| 4.6 | Number of Education Management Staff Trained | x |  | x |  | x
| 4.7 | Number of Payam Education Supervisors (PES) trained on Supportive Supervision | x |  | x |  | x
Output 5 | 5.1 | Number of research and evaluation studies conducted | n/a |  | n/a | n/a | n/a
| 5.2 | % of schools reporting regular attendance through SAMS | x
| 5.3 | Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG) | n/a |  | n/a | n/a | n/a

## Y1 (FY1) Disagg Data Tracker
GESS2 (FY) Y1 Logframe Progress - Disaggregated Data
Indicator | Disaggregation |  |  | Planned milestones for 31st March 2020 | Progress against milestones | Progress % | Comment
| Location | Gender
|  | Boys | Girls
Impact 1: Gender Parity Index (GPI) for primary schools (%boys>girls (1:1) | overall | 1063236 | 889830 | 84% | 83.69% | 99.63% | This indicator is calculated by dividing number of girls enrolled in primary school by number of boys enrolled. Milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by dividing overall progress by overall planned milestone. Disaggregarion by grade will be provided in annual report 2. Disaggration by disability not yet availiable.
| CES | 101068 | 92143 |  | 91.17%
| EES | 59007 | 50916 |  | 86.29%
| JGL | 129619 | 88155 |  | 68.01%
| LKS | 141315 | 110871 |  | 78.46%
| NBG | 133963 | 117906 |  | 88.01%
| UNS | 56924 | 53290 |  | 93.62%
| UTY | 126094 | 106015 |  | 84.08%
| WBG | 69228 | 58426 |  | 84.4%
| WES | 79508 | 78435 |  | 98.65%
| WRP | 166510 | 133673 |  | 80.28%
Impact 2: Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1) (Per Year) | overall | 70360 | 44573 | 64% | 63.35% | 98.98% | This indicator is calculated by dividing number of girls enrolled in secondary school by number of boys enrolled. Milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by dividing overall progress by overall planned mileston. Disaggregarion by grade will be provided in annual report 2.Disaggration by disability not yet availiable.
| CES | 19145 | 13898 |  | 72.59%
| EES | 5210 | 3239 |  | 62.17%
| JGL | 6192 | 2366 |  | 38.21%
| LKS | 6352 | 3516 |  | 55.35%
| NBG | 3756 | 2563 |  | 68.24%
| UNS | 2874 | 1631 |  | 56.75%
| UTY | 4003 | 2620 |  | 65.45%
| WBG | 8026 | 6220 |  | 77.5%
| WES | 5219 | 3957 |  | 75.82%
| WRP | 9583 | 4563 |  | 47.62%
Impact 3: Total Number of children enrolled in schools (Annually - Academic Year) | overall | 1195459 | 990565 | 2088057 | 2186024 | 104.7% | The milestone for this indicator was set as an overall. The progress is disaggregated by state and by gender. Disaggregarion by grade will be provided in annual report 2.Disaggration by disability not yet availiable.
| CES | 145236 | 127730 |  | 272966
| EES | 69526 | 59006 |  | 128532
| JGL | 141324 | 95032 |  | 236356
| LKS | 149079 | 115305 |  | 264384
| NBG | 143733 | 127604 |  | 271337
| UNS | 62785 | 57416 |  | 120201
| UTY | 137178 | 114062 |  | 251240
| WBG | 79872 | 67369 |  | 147241
| WES | 89886 | 88278 |  | 178164
| WRP | 176840 | 138763 |  | 315603
Outcome 1:% of girls passing Primary Leaving Examination (PLE). |  |  |  | 72.5% | 84.9% | 117% | Examination reports shared with us by MoGEI did not include disaggregated level data, hence unable to report as required. We followed up with authorities but we did not manage to get the examination dataset. We will continue engaging the ministry on this issues. Disaggration by disability not yet availiable.
Outcome 2: % of girls passing South Sudan Certificate of Secondary Education (SSCSE). |  |  |  | 73.4% | 93.2% | 127%
Outcome 3:Number of girls enrolled in upper primary (P5-P8). | overall | 0 | 344635 | 330087 | 344635 | 104.4% | The milestone for this indicator was set as an overall. The progress is disaggregated by state.Disaggregarion by grade will be provided in annual report 2.Disaggration by disability not yet availiable.
| CES |  | 37203 |  | 37203
| EES |  | 16446 |  | 16446
| JGL |  | 25593 |  | 25593
| LKS |  | 49684 |  | 49684
| NBG |  | 42557 |  | 42557
| UNS |  | 17840 |  | 17840
| UTY |  | 48931 |  | 48931
| WBG |  | 22569 |  | 22569
| WES |  | 29456 |  | 29456
| WRP |  | 54356 |  | 54356
Outcome 4:Number of girls enrolled in secondary schools (S1-S4) | overall | 0 | 44544 | 39202 | 44544 | 113.6% | The milestone for this indicator was set as an overall. The progress is disaggregated by state. Disaggregarion by grade will be provided in annual report 2.Disaggration by disability not yet availiable.
| CES |  | 13898 |  | 13898
| EES |  | 3239 |  | 3239
| JGL |  | 2363 |  | 2363
| LKS |  | 3516 |  | 3516
| NBG |  | 2563 |  | 2563
| UNS |  | 1607 |  | 1607
| UTY |  | 2620 |  | 2620
| WBG |  | 6218 |  | 6218
| WES |  | 3957 |  | 3957
| WRP |  | 4563 |  | 4563
Outcome 5: % of teachers demonstrating inclusive practices during lessons. | [6 empty] | No milestone set for March 2020
Output 1.1:Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children. (Non-Cumulative)
Output 1.2: Number of school communities reached with the community mobilisation. (Cumulative)
Output 2.1:Cumulative number of (unique, individual) girls receiving Cash Transfers. | overall |  | 374127 | 315000 | 374127 | 118.8% | The indicator targets only girls. The progress of the indicator is disaggregated by state. Disaggregarion by grade will be provided in annual report in QPR4. Disaggration by disability not yet availiable.
| CES |  | 54896 | 78028 | 54896 | 70.35%
| EES |  | 19704 | 21858 | 19704 | 90.15%
| JGL |  | 25078 | 12600 | 25078 | 199%
| LKS |  | 52062 | 34810 | 52062 | 149.6%
| NBG |  | 40636 | 41459 | 40636 | 98.01%
| UNS |  | 15725 | 10724 | 15725 | 146.6%
| UTY |  | 54967 | 14775 | 54967 | 372%
| WBG |  | 26216 | 27905 | 26216 | 93.95%
| WES |  | 27603 | 21758 | 27603 | 126.9%
| WRP |  | 57240 | 51083 | 57240 | 112.1%
Output 2.2:Cumulative Number of cash transfers received | overall |  | 398500 | 315000 | 398500 | 126.5% | The indicator targets only girls. The progress of the indicator is disaggregated by state. Disaggregation by grade will be provided in annual report in QPR4. Disaggregation by disability not yet available.
| CES |  | 62126 | 78028 | 62126 | 79.62%
| EES |  | 21344 | 21858 | 21344 | 97.65%
| JGL |  | 26068 | 12600 | 26068 | 206.9%
| LKS |  | 53859 | 34810 | 53859 | 154.7%
| NBG |  | 43645 | 41459 | 43645 | 105.3%
| UNS |  | 16477 | 10724 | 16477 | 153.6%
| UTY |  | 57508 | 14775 | 57508 | 389.2%
| WBG |  | 28690 | 27905 | 28690 | 102.8%
| WES |  | 29257 | 21758 | 29257 | 134.5%
| WRP |  | 59526 | 51083 | 59526 | 116.5%
Output 3.1: Cumulative Number of Primary Schools that are approved for Capitation Grant payment by MoGEI | overall |  |  | 4200 | 4312 | 102.7% | The milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by dividing overall progress by overall planned milestone target.Disaggration by disability not yet availiable.
| CES |  |  |  | 583
| EES |  |  |  | 297
| JGL |  |  |  | 470
| LKS |  |  |  | 431
| NBG |  |  |  | 550
| UNS |  |  |  | 248
| UTY |  |  |  | 406
| WBG |  |  |  | 288
| WES |  |  |  | 434
| WRP |  |  |  | 605
Output 3.2: Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | overall |  |  | 3880 | 3881 | 100% | The milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by dividing overall progress by overall planned milestone target.Disaggration by disability not yet availiable.
| CES |  |  |  | 536
| EES |  |  |  | 202
| JGL |  |  |  | 435
| LKS |  |  |  | 336
| NBG |  |  |  | 528
| UNS |  |  |  | 226
| UTY |  |  |  | 392
| WBG |  |  |  | 273
| WES |  |  |  | 372
| WRP |  |  |  | 581
Output 3.3: Cumulative Number of Secondary Schools that have received Capitation Grants by GESS (Schools that received Capitation Grants in GESS 1). | overall |  |  | 185 | 191 | 103.2% | The milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by diving overall progress by overall milestone.Disaggration by disability not yet availiable.
| CES |  |  |  | 51
| EES |  |  |  | 17
| JGL |  |  |  | 15
| LKS |  |  |  | 14
| NBG |  |  |  | 9
| UNS |  |  |  | 7
| UTY |  |  |  | 12
| WBG |  |  |  | 28
| WES |  |  |  | 12
| WRP |  |  |  | 26
Output 3.4: Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS2. | overall |  |  | 45 | 48 | 106.7% | The milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by diving overall progress by overall milestone.Disaggration by disability not yet availiable.
| CES |  |  |  | 17
| EES |  |  |  | 6
| JGL |  |  |  | 1
| LKS |  |  |  | 4
| NBG |  |  |  | 1
| UNS |  |  |  | 5
| UTY |  |  |  | 5
| WBG |  |  |  | 5
| WES |  |  |  | 1
| WRP |  |  |  | 3
Output 4.1:Cumulative number of teachers who participated in training, including training on gender-responsive and inclusive teaching methods | [6 empty] | No milestone set for March 2020
Output 4.2: Cumulative number of learners in primary Accelerated Learning Programme (ALP).
Output 4.3:Cumulative number of learners in Accelerated Secondary Education.
Output 4.4:Cumulative number of learners participating in mentoring programme.
Output 4.5:Cumulative number of School Management Committees Trained
Output 4.6:Cumulative number of Education Management Staff Trained
Output 4.7:Cumulative number of Payam Education Supervisors (PES) trained on Supportive Supervision
Output 5.1: Number of research and evaluation studies conducted for GESS2 (Cumulative) |  |  |  | 2 | 2 | 100% | This indicator is measured cumulatively
Output 5.2: % of schools reporting regular attendance through SAMS | overall |  |  | 35% | 55% | 157.1% | The milestone for this indicator was set as an overall, however the progress is disaggregated by state. Overall % progress is calculated by diving overall progress by overall milestone
| CES |  |  |  | 91%
| EES |  |  |  | 29%
| JGL |  |  |  | 60%
| LKS |  |  |  | 11%
| NBG |  |  |  | 70%
| UNS |  |  |  | 42%
| UTY |  |  |  | 52%
| WBG |  |  |  | 43%
| WES |  |  |  | 28%
| WRP |  |  |  | 77%
Output 5.3: Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG). (Cumulative) |  |  |  | 8 | 7 | 87.5% | This indicator is measured cumulatively

## Y2 (FY2) Disagg Data Tracker
GESS2 Quarterly Progress Against Year 2 Milestones (TBC in QPR4)
Indicator | Planned milestones for Year 2 (April 2020-March 2021) | Progress disaggregated by |  |  |  |  | QPR4 (April-June 2020) Progress against milestones | Progress % Toward Annual Milestone | Comment
|  | Location | Gender |  | Disability
|  |  | Male | Female | Male | Female
Impact 1: Gender Parity Index (GPI) for primary schools (%boys>girls (1:1) | 88% | Overall | 0 | 0 | 0 | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Impact 2: Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1) (Per Year) | 68% | Overall | 0 | 0 | 0 | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Impact 3: Total Number of children enrolled in schools (Annually - Academic Year) | 2284632.88 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Outcome 1:% of girls passing Primary Leaving Examination (PLE). | 76% | [7 empty] | Annual indicator
Outcome 2: % of girls passing South Sudan Certificate of Secondary Education (SSCSE). | 76.3%
Outcome 3:Number of girls enrolled in upper primary (P5-P8). | 46846 | Overall |  | 0 |  |  | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Outcome 4:Number of girls enrolled in secondary schools (S1-S4) |  | Overall |  | 0 |  |  | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Outcome 5: % of teachers demonstrating inclusive practices during lessons. | 10% | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 1.1: Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children. (Non-Cumulative) | 1900000 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 1.2: Number of school communities reached with the community mobilisation. (Cumulative) | 300 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 2.1:Cumulative number of (unique, individual) girls receiving Cash Transfers. | 375000 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 2.2.Cumulative Number of cash transfers received | 627000 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 3.1: Cumulative Number of Primary Schools that are approved for Capitation Grant payment by MoGEI | 4300 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 3.2: Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | 3900 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 3.3: Cumulative Number of Secondary Schools that have received Capitation Grants by GESS (Schools that received Capitation Grants in GESS 1). | 215 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 3.4: Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS2. | 50 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.1:Cumulative number of teachers who participated in training, including training on gender-responsive and inclusive teaching methods | 500 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.2: Cumulative number of learners in primary Accelerated Learning Programme (ALP). | 34279 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.3:Cumulative number of learners in Accelerated Secondary Education. | 500 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.4:Cumulative number of learners participating in mentoring programme. | 7500 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.5:Cumulative number of School Management Committees Trained | 3259 | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.6:Cumulative number of Education Management Staff Trained | 250 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 4.7:Cumulative number of Payam Education Supervisors (PES) trained on Supportive Supervision | 100 | Overall | 0 | 0
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 5.1: Number of research and evaluation studies conducted for GESS2 (Cumulative) | 7
Output 5.2: % of schools reporting regular attendance through SAMS | 50% | Overall
CES
EES
JGL
LKS
NBG
UNS
UTY
WBG
WES
WRP
Output 5.3: Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG). (Cumulative) | 20

## Sources
Result | Indicator # | Indicator description | Data Source
Impact | 1.1 | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1)) | SAMS/EMIS/PMT/RA
| 1.2 | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) | SAMS/EMIS/PMT/RA
| 1.3 | Total Number of children enrolled in schools | SAMS/EMIS/PMT/RA
Outcome | 1.1 | % of girls passing PLE | MoGEI Examination Reports
| 1.2 | % of girls passing SSCSE | MoGEI Examination Reports
| 1.3 | Number of girls enrolled in upper primary (P5-P8) | SAMS/EMIS/PMT/RA
| 1.4 | Number of girls enrolled in secondary schools (S1-S4) | SAMS/EMIS/PMT/RA
| 1.5 | % of teachers demonstrating inclusive practices during lessons | HRIS/RA/PMT
Output 1 | 1.1 | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children | Quantitative Surveys/ Population Reference Bureau
| 1.2 | Number of school communities' reached with the community mobilisation | Community Mobilization Reports
Output 2 | 2.1 | Number of girls receiving cash transfers for the first time | SAMS/PMT/RA/MoGEI
| 2.2 | Total Number of girls cash transfers received | SAMS/PMT/RA/MoGEI
Output 3 | 3.1 | Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GRSS | SAMS/EMIS/PMT/RA
| 3.2 | Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | SAMS/EMIS/PMT/RA
| 3.3 | Cumulative Number of Secondary Schools that have received Capitation Grant by GESS (Schools that received Capitation Grants in GESS 1) | SAMS/EMIS/PMT/RA
| 3.4 | Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | SAMS/EMIS/PMT/RA
Output 4 | 4.1 | Number of Teachers who participated in training | RA and Output Training Reports
| 4.2 | Number of learners in primary Accelerated Learning Programme (ALP) | RA and Output Training Reports
| 4.3 | Number of learners in Accelerated Secondary Education | RA and Output Training Reports
| 4.4 | Number of learners participating in mentoring programme | RA and Output Training Reports
| 4.5 | Number of School Management Committees Trained | RA and Output Training Reports
| 4.6 | Number of Education Management Staff Trained | RA and Output Training Reports
| 4.7 | Number of Payam Education Supervisors (PES) trained on Supportive Supervision | RA and Output Training Reports
Output 5 | 5.1 | Number of research and evaluation studies conducted | Research reports and learning assessment records
| 5.2 | % of schools reporting regular attendance through SAMS | SAMS/EMIS/PMT/RA
| 5.3 | Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG) | TWG Reports

## Methodology
Result | Indicator # | Indicator description | Data Source | Numerator (x) | Denominator (y) | Unit | Measurement Approach | Frequency | Responsible for Data Collection | Responsible for Data Analysis
Impact | 1.1 | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1)) | SAMS/EMIS/PMT/RA | Total number of girls in primary school | Total number of boys in primary school | ratio | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Annually | Output 5 M&E Team, RA offices and EMIS | Output 5 M&E Team
| 1.2 | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) | SAMS/EMIS/PMT/RA | Total number of girls in secondary school | Total number of boys in secondary school | ratio | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Annually | Output 5 M&E Team, RA offices and EMIS | Output 5 M&E Team
| 1.3 | Total Number of children enrolled in schools | SAMS/EMIS/PMT/RA | Total number of children in primary and secondary school | None | number | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Enrolment is reported quarterly and attribution Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
Outcome | 1.1 | % of girls passing SSCSE | MoGEI Examination Reports | Total number of girls passing PLE | Total number of children passing PLE | % | Desk Review of MoGEI Examinations excel database, Interviews with MoGEI Examinations department | Annually | Output 5 M&E Team and MoGEI Examinations department | Output 5 M&E Team
| 1.2 | % of girls passing SSCSE | MoGEI Examination Reports | Total number of girls passing SSCSE | Total number of children passing SSCSE | % | Desk Review of MoGEI Examinations excel database, Interviews with MoGEI Examinations department | Annually | Output 5 M&E Team and MoGEI Examinations department | Output 5 M&E Team
| 1.3 | Number of girls enrolled in upper primary (P5-P8) | SAMS/EMIS/PMT/RA | Total number of girls enrolled in upper primary | None | number | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 1.4 | Number of girls enrolled in secondary schools (S1-S4) | SAMS/EMIS/PMT/RA | Total number of girls enrolled in secondary school | None | number | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 1.5 | % of teachers demonstrating inclusive practices during lessons | HRIS/SAMS/EMIS/PMT | Total number of teachers trained in inclusion of disabled children and gender-responsive pedagogy | Total number of teachers | % | Desk Review of SAMS, Interviews with RA, verifying results by cross referencing data with EMIS | Annually | Output 5 M&E Team | Output 5 M&E Team
Output 1 | 1.1 | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disables children | Quantitative Surveys | Total number of people over the age of 15 reached by radio programmes | None | number | Desk Review of Output 1 quantitative surveys, interviews with BBC MA staff and RA offices to validate data | Ad-Hoc | Output 5 M&E Team, Output 1 team and RA offices | Output 5 M&E Team
| 1.2 | Number of school communities' reached with the community mobilisation | Community Mobilization Reports | Number of school communities' reached with the community mobilisation | None | number | Desk Review of BBC MA community mobilization report, interviews with BBC MA staff and RA offices to validate data | Ad-Hoc | Output 5 M&E Team, Output 1 team and RA offices | Output 5 M&E Team
Output 2 | 2.1 | Number of girls receiving cash transfers for the first time | SAMS/PMT/RA/MoGEI | Number of girls receiving cash transfers | None | number | Desk Review of SAMS, Interviews with RA and MoGEI to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 2.2 | Total Number of transfers received | SAMS/PMT/RA/MoGEI | Summation of Number of CT paid year on year | None | number | Desk Review of SAMS, Interviews with RA and MoGEI to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
Output 3 | 3.1 | Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GRSS | SAMS/MoGEI/PMT/RA | Number of unique Primary Schools that are approved for Capitation Grant payment (Cumulative) | None | number | Desk Review of SAMS, Interviews with RA and MoGEI to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 3.2 | Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS. | SAMS/MoGEI/PMT/RA | Number of unique Primary Schools that have recieved for Capitation Grant payment (Cumulative) | None | number | Desk Review of SAMS, Interviews with RA and MoGEI to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 3.3 | Cumulative Number of Secondary Schools that have received Capitation Grant by GESS (Schools that received Capitation Grants in GESS 1) | SAMS/MoGEI/PMT/RA | Number of Secondary Schools that are receiving Capitation grant (Cumulative) | None | number | Desk Review of SAMS, Interviews with RA and MoGEI to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 3.4 | Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | SAMS/EMIS/PMT/RA | Number of Secondary Schools that are receiving Capitation grant | None | number | Desk Review of SAMS, Interviews with RA to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
Output 4 | 4.1 | Number of SMC/BoGs trained on school governance | RA and Output Training Reports | Number of Head Teachers (or responsible for school governance) trained in school governance | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
| 4.2 | Number of Teachers who participate in regular Teacher Professional Development (TPD) programme | RA and Output Training Reports | Number of Teaching staff who received Teacher Professional Development (TPD) training | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
| 4.3 | Number of schools in receipt of school based mentoring for girls | RA and Output Training Reports | Number of schools in receipt of school based mentoring for girls | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
| 4.4 | Number of schools using low cost teaching and learning materials | RA and Output Training Reports | Number of schools using low cost teaching and learning materials | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
| 4.5 | Number of Accelerated Learning Programs supported in primary schools | RA and Output Training Reports | Number of Accelerated Learning Programs run in Primary schools | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
| 4.6 | Number of Accelerated Learning Programs run in Secondary schools | RA and Output Training Reports | Number of Accelerated Learning Programs run in Secondary schools | None | number | Desk review of RA and output 4 training reports, interviews with RA offices and output 4 to verify results | Annually | Output 5 M&E Team, Output 4 team and RA offices | Output 5 M&E Team
Output 5 | 5.1 | Number of research and evaluation studies conducted | Research reports and learning assessment records | Number of research and evaluation studies conducted | None | number | Desk Review of Research reports and learning assessment records and interviews with output 5 research staff | Annually | Output 5 M&E Team | Output 5 M&E Team
| 5.2 | % of schools reporting regular attendance through SAMS | SAMS/EMIS/PMT/RA | Number of Primary/Secondary schools reporting regular attendance | Total Number of Primary and Secondary schools | % | Desk Review of SAMS, Interviews with RA to verifying results | Annually | RA Offices and Output 5 M&E Team | Output 5 M&E Team
| 5.3 | Number of meetings held by M&E Technical Working Group | TWG Reports | Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG) | None | number | Desk Review of TWG reports | Annually | Output 5 M&E Team | Output 5 M&E Team

## Equations
Result | Impact |  |  | Outcome |  |  |  |  | Output 1 |  | Output 2 |  | Output 3 |  | Output 4 | [5 empty] | Output 5
Indicator # | Impact Indicator 1.1 | Impact Indicator 1.2 | 1.3 | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 1.1 | 1.2 | 2.1 | 2.2 | 3.1 | 3.2 | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6 | 5.1 | 5.2 | 5.3
Indicator description | Gender Parity Index (GPI) for primary schools (%boys>girls (1:1)) | Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) | Total Number of children enrolled in schools | % of girls passing PLE | Girls' pass rate at Examinations for South Sudan Certificate in Secondary Education (SSCSE) | Number of girls enrolled in upper primary (P5-P8) | Number of girls enrolled in secondary (S1-S4) schools | Number of teachers trained in the are of inclusion of disabled children in learning | Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and disabled children | Number of school communities' reached with the community mobilisation | Cumulative of individual unique girls receiving cash transfers | Cumulative Total Number of girls receiving cash transfers | Number of schools Primary schools that are approved for capitation grant payment | Number of Secondary Schools that are receiving Capitation grant | Number of SMC/BoGs trained on school governance | Number of Teachers who participate in regular Professional Development (TPD) programme | Number of schools in receipt of school based mentoring for girls | Number of schools using low cost teaching and learning materials | Number of Accelerated Learning Programs supported in primary schools | Number of Accelerated Learning Programs supported in Secondary schools | Number of research and evaluation studies conducted | % of schools reporting regular attendance through SAMS | Number of research dissemination/sharing meetings held by M&E Technical Working Group
| For impact indicator 1.1, the result is derived from: | For impact indicator 1.2, the result is derived from: | For impact indicator 1.3, the result is derived from: | For outcome indicator 1.1, the result is derived from: | For outcome indicator 1.2, the result is derived from: | For outcome indicator 1.3, the result is derived from: | For outcome indicator 1.4, the result is derived from: | For outcome indicator 1.5 the result is derived from: | For output indicator 1.1 the result is derived from: | For output indicator 1.2 the result is derived from: | For output indicator 2.1 the result is derived from: | For output indicator 2.2 the result is derived from: | For output indicator 3.1 the result is derived from: | For output indicator 3.2 the result is derived from: | For output indicator 4.1 the result is derived from: | For output indicator 4.2 the result is derived from: | For output indicator 4.3 the result is derived from: | For output indicator 4.4 the result is derived from: | For output indicator 4.5 the result is derived from: | For output indicator 4.6 the result is derived from: | For output indicator 5.1 the result is derived from: | For output indicator 5.2 the result is derived from: | For output indicator 5.2 the result is derived from:
| 1. Sum the total number of children in primary school as reported in SAMS | 1. Summing the total number of children in secondary school as reported in SAMS | 1. Summing the total number of children in primary and secondary school as reported in SAMS | 1. Sum the total number of children in school that passed the PLE as recorded by MoGEI Examination Council | 1. Sum the total number of children in school that passed the SSCSE as recorded by MoGEI Examination Council | 1. Sum the total number of children in upper primary (P5-P8) school as reported in SAMS | 1. Sum the total number of children in secondary (S1-S4) school as reported in SAMS | 1. Sum the total number of teachers trained in the are of inclusion of disabled children in learning from HRIS | 1. The sum of the total number of people that are over the age of 15 that responded to the BBC MA quantitative survey will be calculated | 1. Sum total number of schools that have been reached with community mobilization activities from BBC MA database | 1. Sum the total number of individual unique girls receiving cash transfers as reported in SAMS in the school year | 1. Sum the total number of girls receiving cash transfers from SAMS in the school year | 1. Sum the total number of Primary schools that are approved for capitation grant payment from SAMS in the school year | 1. Sum the total number of Secondary schools that have received a capitation grant payment from SAMS in the school year | 1. Sum the total number of SMC/BoGs trained on school governance from Output 4 training reports | 1. Sum the total number of teachers who participate in regular Professional Development (TPD) programme from Output 4 training reports | 1. Sum the total number of schools in receipt of school based mentoring for girls from Output 4 training reports | 1. Sum the total number of schools using low cost teaching and learning materials Output 4 training reports | 1. Sum the total number of Accelerated Learning Programs supported in primary schools from Output 4 training reports | 1. Sum the total number of Accelerated Learning Programs supported in secondary schools from Output 4 training reports | 1. Sum the total number of research and evaluation studies conducted from Output 5 research reports | 1. Sum the total number of schools from SAMS | 1. Sum the total number of meetings held by M&E Technical Working Group from Output 4 reports
| 2. If EMIS enrolment data is available a cross reference will be made to verify the totals | 2. If EMIS enrolment data is available a cross reference will be made verify the totals | 2. If EMIS enrolment data is available a cross reference will be made verify the totals | 2. Sum the total number of girls in school that passed the PLE as reported by MoGEI Examination Council | 2. Sum the total number of girls in school that passed the SSCSE as reported by MoGEI Examination Council | 2. Sum the total number of girls in upper primary (P5-P8) school as reported in SAMS | 2. Sum the total number of girls in secondary (S1-S4) school as reported in SAMS | 2. Sum the total number of teachers trained in the are of inclusion of disabled children in learning from RA reports | 2. The sum of the total number of people that are over the age of 15 that responded saying that they listened to radio broadcasts in the quantitative survey will be calculated | 2. Output 1 Lead to verify reports with RA offices | 2. Verify cash transfer data from SAMS with RA offices and MoGEI responsible staff | 2. Verify cash transfer data from SAMS with RA offices and MoGEI responsible staff | 2. Verify capitation approval data from SAMS with RA offices and MoGEI responsible staff | 2. Verify capitation receipt data from SAMS with RA offices and MoGEI responsible staff | 2. Sum the total number of SMC/BoGs trained on school governance from RA reports | 2. Sum the total number of teachers who participate in regular Professional Development (TPD) programme from RA reports | 2. Sum the total number of schools in receipt of school based mentoring for girls from RA reports | 2. Sum the total number of schools using low cost teaching and learning materials from RA reports | 2. Sum the total number of Accelerated Learning Programs supported in primary schools from RA reports | 2. Sum the total number of Accelerated Learning Programs supported in secondary schools from RA reports | 2. Sum the total number of research and evaluation studies conducted from RA reports | 2. Sum the total number of schools that submitted attendance data to SAMS a minimum of 5 times in the school year. | 2. Sum the total number of meetings held by M&E Technical Working Group from TWG reports
| 3. Sum the total number of girls in primary school as reported in SAMS | 3. Summing the total number of girls in secondary school as reported in SAMS | This provides the ratio of girls in school compared to boys or the GPI | 3. Dividing the total number of girls (1) that passed PLE examinations by the total number of children (2) that passed PLE examinations | 3. Dividing the total number of girls (1) that passed SSCSE examinations by the total number of children (2) that passed SSCSE examinations | 3. If EMIS enrolment data is available a cross reference will be made verify the totals | 3. If EMIS enrolment data is available a cross reference will be made verify the totals | 3. Sum the total number of teachers trained in the are of inclusion of disabled children in learning from Output 4 PMT reports | 3. The sum of the total population of South Sudan that are over the age of 15 will be calculated from the XXXX data source | This provides the total number of school communities taking part in community mobilization activities |  |  |  |  | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Cross check data from both data sources | 3. Divide the total number of schools (1) by the total number of schools that submitted attendance to SAMS 5 times in the school year (2) | 3. Cross check data from both data sources
| 4. If EMIS enrolment data is available a cross reference will be made verify the totals | 4. If EMIS enrolment data is available a cross reference will be made verify the totals | =(z) Total number of children in primary and secondary school | 4. Represent the result as a % | 4. Represent the result as a % | 4. Subtract total number of girls in upper primary (P5-P8), (2) from total number of children in upper primary (P5-P8), (1) | 4. Subtract total number of girls in secondary (S1-S4) school, (2) from total number of children in secondary (S1-S4) school, (1) | 4. Triangulate data from three data sources and discuss and agree most accurate estimate of teachers trained in the are of inclusion of disabled children in learning | 4. Divide the total number of people that took the survey (1) that are over the age of 15 by the total population of South Sudan (3) that are over 15 |  | This provides the number of unique girls receiving cash transfer each year: | This provides the total number of girls receiving cash transfer each year: | This provides the total number of Primary schools approved for capitation each year: | This provides the total number of Secondary schools receiving a capitation grant each year: | 4. Agree and document the number of SMC/BoGs trained on school governance | 4. Agree and document the number of Teachers who participate in regular Professional Development (TPD) programme | 4. Agree and document the number of schools in receipt of school based mentoring for girls | 4. Agree and document the number of schools using low cost teaching and learning materials | 4. Agree and document the number of Accelerated Learning Programs supported in primary schools | 4. Agree and document the number of Accelerated Learning Programs supported in secondary schools | 4. Agree and document the number of research and evaluation studies conducted | 4. Represent the result as a % | 4. Agree and document the number of meetings held by M&E Technical Working Group
| 5. Dividing the total number of girls (1) by the total number of children (3) | 5. Dividing the total number of girls (1) by the total number of children (3) | Output 1 1.1: 5. Multiply the total number of people that took the survey and are over 15 that listened to the broadcast (2) with the result of step (4); Output 1 1.2: =(z) Total number school communities reached with community mobilization activities; Output 2 2.1: =(z) Total number of unique girls receiving cash transfers; Output 2 2.2: =(z) Total number of girls receiving cash transfers; Output 3 3.1: =(z) Total number of Primary schools approved for capitation each year; Output 3 3.2: =(z) Total number of Secondary schools receiving a capitation grant each year
| This provides the ratio of girls in school compared to boys or the GPI | This provides the ratio of girls in school compared to boys or the GPI |  | This provides the % pass rate of girls taking PLE | This provides the % pass rate of girls taking SSCSE | This provides the total number of girls in upper primary (P5-P8) school | This provides the total number of girls in secondary (S1-S4) school | This provides the estimate of teachers trained in the are of inclusion of disabled children in learning | [6 empty] | This provides the number of SMC/BoGs trained on school governance: | This provides the number of teachers who participated in TPD: | This provides the number of schools in receipt of school based mentoring for girls : | This provides the number of schools using low cost teaching and learning materials : | This provides the number of Accelerated Learning Programs supported in primary schools : | This provides the number of Accelerated Learning Programs supported in secondary schools : | This provides the number of research and evaluation studies conducted: | This provides the % of schools that submit attendance data to SAMS | This provides the number of meetings held by M&E Technical Working Group :
[6 empty] | (x) total number of girls in upper primary (P5-P8) school - (y) total number of children in upper primary (P5-P8) school | (x) total number of girls in secondary (S1-S4) school - (y) total number of children in secondary (S1-S4) school | =(z) Total number of teachers trained in the are of inclusion of disabled children in learning | This provides the estimated total number of people that should have listened to the broadcast nationally | [5 empty] | =(z) Total number of SMC/BoGs trained on school governance | =(z) Total number of teachers who participate in regular Professional Development (TPD) programme | =(z) Total number of schools in receipt of school based mentoring for girls | =(z) Total number of schools using low cost teaching and learning materials | =(z) Total number of Accelerated Learning Programs supported in primary schools | =(z) Total number of Accelerated Learning Programs supported in secondary schools | =(z) Total number of research and evaluation studies conducted |  | =(z) Total number of meetings held by M&E Technical Working Group
| (x) total number of girls in primary school | (x) total number of girls in secondary school | Outcome 1.1: (x) total number of girls that passed the PLE; Outcome 1.2: (x) total number of girls that passed the SSCSE; Output 5 5.2: (x) total number of schools on SAMS
| (y) total number of children in primary school | (y) total number of children in secondary school | Outcome 1.1: (y) total number of children that passed the PLE; Outcome 1.2: (y) total number of children that passed the SSCSE; Outcome 1.3: =(z) Total number of girls in upper primary (P5-P8) school; Outcome 1.4: =(z) Total number of girls in secondary (S1-S4) school; Output 1 1.1: ((x) total number of people that took the survey / (y) total number of people in South Sudan) * (w) total people that listened to the survey; Output 5 5.2: (y) total number of schools that submitted attendance data to SAMS 5 times in the school year
| =(z) GPI score for primary schools (%boys>girls (1:1)) | =(z) GPI score for secondary schools (%boys>girls (1:1)) | Outcome 1.1: =(z) % pass rate of girls taking the PLE; Outcome 1.2: =(z) % pass rate of girls taking the SSCSE; Output 1 1.1: =(z) Total number of people that listened to the radio broadcasts (reached); Output 5 5.2: =(z) % of schools reporting regular attendance through SAMS
6. This number is the actual ratio which then should be comparted against the indicator milestone
7. If (z) < Indicator milestone, then the analysis of why the gap happened needs to take place and lessons learned for achievement of next milestone
7. If (z) > Indicator milestone, then the analysis of why the gap happened needs to take place

## Change Log
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | INDICATOR NUMBER | DETAILS OF CHANGE | AUTHOR | DATE
1 | Output 3, Overall target | All indicators | All targets have been updated from what was originally in the contract from ''GESS2 will reach between 4100 and 5000 unique primary schools and 500 unique secondary schools with capitations grants.'' (Contract page 102) to targets approved on 13th January 2020 3.1 - 4800 Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GRSS; 3.2 - 4300 Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GRSS; 3.3 - 300 Cumulative Number of Secondary Schools that have received Capitation Grants by GESS (Schools that received Capitation Grants in GESS 1); 3.4 - 80 Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2 | Akuja de Garang | 2020-01-13
2 | Outcomes 1 and 2 milestones | Outcomes 1 & 2 | Milestones for the during of the Programme now set. | Akuja de Garang | 2020-05-15
3
4
5
6
7
8
9
10

## Calculation Sheet
23 | 23
24 | 24
26 | 26
33 | 33
21.7 | 21.7
24.9
28.1
31.3