## Log frame Revise RRU
LOGFRAME REVISED_RRU_DFID-PNUD-31 December 2016
PROJECT NAME | Reduction des Risques Urbains (RRU)
IMPACT | Impact Indicator 1 | Weight of the indicator% |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016
Disaster resilience in the urban centers of the Grand-Anse is strengthened and the urban planning of the targeted communes is influenced by disaster risk sensitive policies | % of targeted departments and communes that have strengthened their knowlede on their vulnerability to disaster risks |  | Planned: 100% | 5% | 25% | 30% | 65% | 100% | 100%
|  |  | Achieved | [5 empty] | 100%
|  |  |  | Source: |  |  |  |  | 164 people interviewed in Grand Anse including masons (Final external independent evaluation)
| Impact Indicator 2 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016
| % of targeted departments and communes that have reduced their vulnerability by implementing urban planning policies influenced by the developed disaster knowledge tools |  | Planned: 100% | 0% | 0% | 0% | 50% | 100% | 100%
|  |  | Achieved | [5 empty] | 100%
|  |  |  | Source: |  |  |  |  | Retour d'experience post-Mathew: le nombre de mort associes au cyclone a ete limitee grace a l'application des consignes de mise en securite post-Mathieu (voir temoignages des maires).
OUTCOME 1 | Outcome Indicator 1.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
The departmental and communal stakeholders are aware of the most relevant urban disaster risks | 75% of 92 interviewed departmental stakeholders (6 Institutional technicians (recruited and trained), 48 staffs for the 12 municipalities, 4 technical people of the delegations, 4 technical staff of two operational centers Emergency Departemental,24 representatives of the Communal Committees Civil Protection (CCPV), 6 representatives of NGOs working in the study area) who demonstrate an appropriate knowledge of geographic destribution and degrees of the different risks affecting the departements of Grand Anse, |  | Planned: 75% | 0% | 0% | 25% | 65% | 75% | 75% | The departmental stakeholders have demonstrated a continuous engagement in the project implementation and have shown interest in the developed knowlede tools
|  |  | Achieved | [5 empty] | 75%
|  |  |  | Source: |  |  |  |  | 164 people interviewed in Grand Anse including masons (Final external independent evaluation)
OUTPUT 1.1 | Output Indicator 1.1.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
An integrated departmental multi-risk assessment(earthquake, tsunami, marine submersion, flood, land slide, rock falling, debris flow, storm,..) is developed, disseminated and implemented in the department of Grand-Anse | 1 departmental integrated multi-risk map at an appropriate scale (1/50 000e) is developped for the department of Grand-Anse: 1 map for each specific risk and 1 multi-risk map for the departement (so 5 maps for the department) | 50% | Planned: 5 | 0 | 0 | 0 | 2 | 5 | 5 | Regular meetings between the departmental stakeholders will allow to collect the necessary data for risks throughout the department
|  |  | Achieved | 0 | 0 |  | 4 | 5 | 5
|  |  |  | Source: |  |  |  |  | Five maps produced (Final external independent evaluation)
Source:
| Output Indicator 1.1.2 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
| 2 workshops to validate the developed risk assessments | 2% | Planned: 2 | 0 | 0 | 0 | 1 | 2 | 2 | The major departemental stakeholders will participate to the validation workshops to ensure that the risk assessment faithfully corresponds to the characteristics of each department
|  |  | Achieved | 0 | 0 |  | 1 |  | 2
|  |  |  | Source: |  |  |  |  | Validation through field work and through the events surrounding Hurricane Matthew Reports of preliminary results meetings (Port au Prince and Grand Anse): 19-21 April 2016 (Final external independent evaluation)
| Output Indicator 1.1.3 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
| 2 of events to present and disseminate the main steps/results/recommendations of the Departmental Risk Assessments | 3% | Planned: 2 | 0 | 0 | 0 | 1 | 2 | 2 | the targeted stakeholders participate actively to the event
|  |  | Achieved | 0 | 0 |  | 1 | 2 | 2
|  |  |  | Source: |  |  |  |  | Reports of meetings in Grand Anse to disseminate maps: 15-16 June 2016 Report of in-depth training 25-28 July 2016 (Final external independent evaluation)
OUTPUT 1.2 | Output Indicator 1.2.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
Dissemination, communication and awareness raising towards the general public and manjor stakeholders on the integrated departemental multi-risk assessments | 75% of interviewed individuals who affirm to have had adequate access to information related to the findings of the developed departmental multi-risk assessments | 2% | Planned: 75% | 0% | 0% | 0% | 50% | 75% | 75% | The major departmental stakeholders contributed to the dissemination of the findings towards the general public in order to enhance their outreach
|  |  | Achieved | [5 empty] | 75%
|  |  |  | Source: |  |  |  |  | 164 people interviewed in Grand Anse including masons (Final external independent evaluation)
INPUTS (£) | DFID (£) |  |  |  |  | Total (£) |  | DFID SHARE (%) | DFID SHARE (%)
| 226784 |  |  |  |  | 226784 |  | 100% | 100%
DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
Departmental and communal stakeholders engage in the development and implementation of specific Risk Prevention Plans for the six targeted communal | The Six (6) targeted communes have necessary information to reduce their vulnerability while pleading for implementing urban planning policies influenced by the developed urban reduction plans tool |  | Planned: 6 | 0 | 0 | 0 | 2 | 6 | 6 | the departmental and communal stakeholders demonstrate an active and constant interest in influencing their urbanization policies by the findings of the risk assessments and the recommendantions of the risk prevention plans.
|  |  | Achieved | 0 | 0 |  | 2 | 6 | 6
|  |  |  | Source: |  |  |  |  | The Six (6) targeted communes had develop six (6) post-Mathew recovery plans based necessary information to reduce their vulnerability and are pleading for implementing urban planning policies influenced by the developed urban reduction plans tool- six (6) post-Mathew recovery plans -
OUTPUT 2.1 | Output Indicator 2.1.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
Risk Prevention Plans of six targeted communes in the department of Grand-Anse are developed on the basis of the departmental risk assessment | Development of 6 Risk Prevention Plans in six(6) prioroty municipalities of Grand'Anse (Dame-Marie, Jeremie, Beaumont, Abricots, Roseaux and Moron) | 27% | Planned:6 | 0 | 0 | 0 | 2 | 6 | 6 | The communal stakeholders demonstrate an active participation in the consultations and workshops to validate the Risk Prevention Plans
|  |  | Achieved | 0 | 0 |  | 0 | 6 | 6
|  |  |  | Source: |  |  |  |  | Six PPRNs elaborated (Final external independent evaluation; appendix ?)
| Output Indicator 2.1.2 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
| 12 of workshops to validate the developed Risk Prevention Plan | 1% | Planned: 12 | 0 | 0 | 0 | 6 | 12 | 12 | The major communal stakeholders will participate to the validation workshops to ensure that the risk prevention plans faithfully correspond to their expectations
|  |  | Achieved | 0 | 0 |  | 0 |  | 12
|  |  |  | Source: |  |  |  |  | Presentations resulting from Planning Workshop: 28-29 September 2016 See Table 7 and 8 (workshops to develop recovery plans and communication products informed by PPRNs) (Final external independent evaluation)
| Output Indicator 2.1.3 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
| 12 of events to present and disseminate the recommendations of the Risk Prevention Plans to departmenta and communal authorities and major urban risk stakeholders | 1% | Planned: 12 | 0 | 0 | 0 | 6 | 12 | 12 | The departmental and communal stakeholders participate with interest to the events organized to present the developed Risk Prevention Plans
|  |  | Achieved | 0 | 0 |  | 0 |  | 18
|  |  |  | Source: |  |  |  |  | As above. It was 12 workshops in total for both validation and dissemination (Final external independent evaluation)
OUTPUT 2.2 | Output Indicator 2.2.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
Construction professionals from the public and private sector are trained on disaster resilient building practices in Grand-Anse | 6 trainings of construction professionals from the public and private sector on adequate anti-risk measures | 4% | Planned: 6 | 0 | 0 | 0 | 3 | 6 | 6 | Construction professionals so interest and engagement in influnecing their building techniques by disaster resilient practices
|  |  | Achieved | 0 | 0 |  | 3 |  | 6
|  |  |  | Source: |  |  |  |  | Training reports and lists of participants See Table 9 for dates and locations (Final external independent evaluation)
OUTPUT 2.3 | Output Indicator 2.3.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
The general public in the Grand-Anse (including donors and partners) is educated and sensitized around the findings and recommendations of the Risk Prevention Plans | 75% of (200) interviewed individuals who declare to have benefitted of awareness raising initiatives related to urban disaster risk | 4% | Planned: 75% | 0% | 0% | 0% | 40% | 75% | 75% | The communication and visibility initiatives were implemented through the use of the primary mass media channels which ensure the outreach of the targeted population
|  |  | Achieved | [5 empty] | 75%
|  |  |  | Source: |  |  |  |  | 164 people interviewed in Grand Anse including masons (Final external independent evaluation)
INPUTS (£) | DFID (£) |  |  |  |  | Total (£) |  | DFID SHARE (%) | DFID SHARE (%)
| £315,108 |  |  |  |  | £315,108 |  | 100% | 100%
DFID (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
The capacity of local government to absorb the findings and adequately implement the recommendations of the Departmental Risk Assessments and of the Risk Prevention Plans is reinforced in the Grand'Anse Departement. | 80% of 92 interviewed departmental stakeholders (6 Institutional technicians (recruited and trained), 48 staffs for the 12 municipalities, 4 technical people of the delegations, 4 technical staff of two operational centers Emergency Departemental,24 representatives of the Communal Committees Civil Protection (CCPV), 6 representatives of NGOs working in the study area) who demonstrate an appropriate knowledge of geographic destribution and degrees of the different risks affecting the departements of Grand Anse, |  | Planned: 80% | 0 | 0 | 20% | 60% | 80% | 80% | The local government representatives are highly engaged in the development of the departmental risk assessments and of the communal risk prevention plans
|  |  | Achieved | [5 empty] | 80%
|  |  |  | Source: |  |  |  |  | 164 people interviewed in Grand Anse including masons (Final external independent evaluation)
OUTPUT 3.1 | Output Indicator 3.1.1 |  |  | Baseline: Janvier 2015 | Milestone 1: 31 Mars 2015 | Milestone 2: 30 September 2015 | Milestone 3: 31 March 2016 | Target (project end): 30 September 2016 | Target (project end): 31 December 2016 | Assumptions
1 Institutional technicians support the technical capacity of local government to ensure the sustainability and implementation of the Departmental Risk Assessments and of the Risk Prevention Plans | One (1) technical staff to support the technical capacity of local government (MPCE or MTPTC) to ensure the sustainability and implementation of the Departmental Risk Assessments and of the Risk Prevention Plans | 6% | Planned: 1 | 0 | 0 | 0 | 1 | 1 | 1 | The capacity of local government to absorb findings and recommendations of the Departmental Risk Assessment and of the Risk Prevention is reinforced
|  |  | Achieved | 1 | 1 | 1 | 2 | 2 | 2
|  |  |  | Source: |  |  |  |  | UNDP staff member based in Jérémie and a trained technical staff member from MPCE (Final external independent evaluation)
INPUTS (£) | DFID (£) |  |  |  |  | Total (£) |  | DFID SHARE (%) | DFID SHARE (%)
| 20000 | 100% |  |  |  | 20000 |  | 100% | 100%
| Total weight for direct costs in % | 100% |  | Total funds for direct costs |  | 561892
INPUTS (HR) | DFID (£)
| 300923 |  |  |  |  | 300923 |  | 100% | 100%
INPUTS (Cost OFFICE+GSM) | DFID (£)
| 187652 |  |  |  |  | 187652 |  | 100% | 100%
INPUTS (Monitoring and Evaluation) | DFID (£)
| 44840 |  |  |  |  | 44840 |  | 100% | 100%
|  |  |  | Montant total du financement |  | 1095307