Type of Review: Annual Review

Project Title: Punjab Education Sector Project II

Date started: Jan 2013	Date review undertaken: 3 – 14 February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The Punjab Education Sector Programme (PESPII), which is DFID’s largest and most complex education programme, builds on the UK’s previous support to the Government of Punjab (GoPb) to reform and transform the delivery of education in Punjab. It also includes the UK-supported Punjab School Reform Roadmap. / In addition to working through government to ensure that every child in Punjab has access to a good quality education, PESP II focuses on 11 districts identified as low-performing compared to the rest of the Province. Through a range of innovative interventions with the government, private sector and civil society organisations (CSOs), the programme aims to deliver equitable access to better quality education across the whole province. / The UK will provide up to £350.3 million over six years between January 2013 and March 2019. / Sector Budget Support (£100m) provides funds to GoPb to improve access to education and to improve the quality in government schools (active) / School infrastructure (£104m) provides missing facilities and additional classrooms (Service provider approved - on stream end of February /March 2014) / Capacity and Quality building of Punjab’s low-cost private sector through the Punjab Education Foundation (PEF) (£68.6m) (active) / Access to Finance (£9m) focuses on expanding the low-cost private sector in underserved areas (research results available 26 February 2015) / Targeted support, through civil society in 11 low performing districts (£10.8m) (on stream March 2014/15) / A scholarship programme for higher education and girls’ higher secondary education (£18.2m) (active) / Technical assistance, split into four areas (£39.7m) / Technical Assistance Management Organisation (TAMO) (£25m) which will underpin the delivery of the six components (service provider selected and being contracted - on stream in March 2014). / Punjab School Reform Roadmap programme (£10m) (active) / Evaluation and Research (£2.5m) (service provider selected and being contracted – on stream in April 2014) / Assessment (£2.2m) (first pilot underway; first results will be reported in April 2014 Stocktake)

What are the expected results?
Under PESP II the UK is providing £350.3m over six years to reform and transform the delivery of education in Punjab. It builds on the UK’s previous support to GoPb and includes the UK-supported Punjab School Reform Roadmap. / PESP II accounts for 75% of DFID’s forecast of primary school children benefiting from DFID support. The forecast is to benefit 2.5 million in 2014/15 having already benefitted 1.4 million children. On secondary PESP II is forecast to benefit at least 1 million secondary children, having already benefitted 800,000. This is already exceeding DFID-P’s forecast in the Operational Plan of 800,000 by 2014/15. / In addition, the UK’s support to the GoPb will have a significant impact on tackling the binding constraints to reform and improving the quality of teaching and learning outcomes. Structural reforms will impact positively on future cohorts of children in schools across Punjab.

What is the context in which UK support is provided?
The UK’s top priority in Pakistan is to help deliver better quality education to those who need it most. It aims to support four million children in school by 2015 and be part of a concerted effort to ensure that Pakistan makes rapid progress towards ensuring that all children, particularly girls and other marginalised groups, receive a quality education. / Pakistan cannot hope to end its education emergency without a substantial, rapid, and sustained increase in the quantity and quality of schooling in Punjab. Punjab is the largest of Pakistan’s provinces, comprising 56% of the country’s population, and currently contributes 58% of Pakistan’s Gross Domestic Product (GDP).[1]By improving education, the UK will: increase life chances for children, youth and their families; strengthen Pakistan’s long term economic competitiveness; and make an important contribution to security. Improving delivery of basic services and making the state relevant is a core pillar of the UK’s strategy for engagement in Pakistan. / As a result of its size, Punjab has the highest number of out-of-school children aged 6-16 years in Pakistan (approximately six million[2]), and the highest number of children with low learning levels. / The Government of Punjab continues to display strong political commitment to education reforms under the leadership of the Chief Minister and the Secretary School Education. A consistently strong message from the various stakeholders consulted was that this is a stable, committed Government that will focus on delivering education reforms. This has been demonstrated by the appointment of highly competent civil servants to key education posts following the elections. / The Annual Review team were impressed with the transformative drive and commitment of the education personnel they met and the quality of the data systems at both the Programme Management Implementation Unit (PMIU) and the Department of School Development (DSD). Much is clearly being achieved, some of which is reported in the Chief Minister’s two monthly Roadmap stock takes. Indications of accelerated delivery include: the disbursement of 42% of the development budget in the first quarter of the year; the impressive results of the recent enrolment drive; the determined focus on retention and quality; and the emphasis on providing support to teachers through recruiting on merit and building the capacity of classroom mentors( DTEs).
[1] Punjab Economic Research Institute and Govt of Punjab (2007). NB: Punjab has not produced any subsequent economic reports, while Pakistan Economic Surveys do not report disaggregated provincial GDPs.
[2] UNESCO Institute of Statistics (2012). Local estimates are far higher.

## Section A: Detailed Output Scoring

Output 1: Better managed, more accountable, education system
Output 1 score and performance description: Outputs met expectation (A)
Progress against expected results: / Indicator On track? Score / 1.1 Functional School Councils Index covering monthly meetings, expenditure of grants/ budgets and improvement in teacher presence (50%, 20% and 30% weighting in the index) No milestone Positive trajectory A / 1.2 Education Management (% coverage of schools by monitoring visits) Milestone met A / 1.3 Real increase in non-salary school expenditure as % total current school expenditure Positive trajectory? (anecdotally) A data pending) / Under this output, PESP II aims to support GoPb to improve the management of the education system and to increase the accountability of the Government for delivering inclusive, quality education, particularly for girls and the poorest. Two programme components are recognised in the Business Case as contributing to the achievement of this output: sector budget support under the World Bank PAD and, indirectly, the community-based advocacy programme in low-performing districts. It is also important to acknowledge the role being played by the high-level political commitment to reform created by the Roadmap. This is part of PESP II, even though the indicators are not yet reflected in the log frame. / Contextual Evidence: / Sector Budget Support / PMIU has continued to improve its monthly monitoring processes and can present and use data collected from the districts within ten days of the end of each month. PMIU have conducted validation exercises showing the data to be mostly reliable. They have also identified further opportunities for improvement in terms of collection methods, quality assurance, analysis and dissemination. These will be included in their forthcoming Chief Minister’s Monitoring Force (CMMF) institutional plan. PMIU also plans to establish an integrated Management Information System (MIS) and has recently procured a software consultant to develop this. / In December 2013, a Joint World Bank-DFID Review Mission concluded that eight out of ten Disbursement Linked Indicators (DLIs) for 2012/13 had been achieved and two others were almost achieved and therefore recommended almost full disbursement (Aide Memoire, December 2013). DFID subsequently disbursed the first annual tranche of SBS. This AR team reviewed the WB Aide Memoire against available evidence (including progress reported by the PMIU and other education departments). All preparations for the DLI on teacher rationalisation have been met but this issue is stayed in the High Court because teachers who were to be moved have taken up cases against their move. It is thought likely that the remaining DLis will be met within the year. / In November 2013, it was agreed by DFID-P Head of Office that an additional £47m of SBS would be front-loaded for disbursement in UK FY 2013/14 and 2014/15. This was at the request of the GoPb on the basis that five new DLIs would be achieved by March 2015. The first tranche of £30m was disbursed in December 2013, with the approval submission (18/11/13) noting that release of the second tranche (£17m) would be linked to progress measured by this Annual Review. Whilst it is too early to say whether the five additional DLIs will be achieved, it is the opinion of this Review team that adequate progress is being made against each indicator. / The first additional DLI is to enable School Councils to hire up to 50,000 classroom interns. PMIU reported that this initiative has been approved. Plans for the recruitment and training of 50,000 classrooms interns are in place. They will be appointed on one-year contracts and paid Rs5,000 a month. This is intended to provide a short-term solution to the overcrowding of classrooms, partially created by the success of the recent enrolment drive, until the teacher rationalisation policy is rolled out. / The second additional DLI was for more credible school-based exams and the introduction of additional mid-year school-based exams for poorly-performing children in Grade 3 and above. DSD reported that the first pre-PEC mid-year examination took place in 1,337 weak schools whose results were below 30% and 3,516 schools whose teachers obtained an E or F grade in their Continuous Professional Development (CPD) evaluation. The assessment took place after three weeks of intensive preparatory studies. This achieved some significant improvement in performance. / DSD is also strengthening learning through a programme of structured training and the merit-based selection of 582 new DTEs. DSD has undertaken investigative studies to establish whether cluster heads are overseeing learning and on how to make professional development days more needs-based and relevant. DFID-P has committed to undertaking an independent six-monthly assessment of Grade 2 children to measure learning progress. This will provide a baseline for both public and private schools. The Roadmap stock take will routinely report on the progress of each district. / The third additional DLI is to improve the examination and assessment systems through the implementation of the Punjab Examination Commission’s (PEC) existing improvement plan. PEC has just been merged with the Punjab Education Assessment System (PEAS) so there should be a more coherent institutional focus on examination and assessment. The improvement plan aims to redefine the examination modality, improve examination conduct, and report exam results in a timely and transparent manner. The Government has reduced the number of subjects examined by PEC from eight to five, which should provide a more manageable focus for PEC to improve both the quality and rigour of the examination process. This has also resulted in a reduction in the number of Student Learning Outcomes (SLOs). This represents a significant and ambitious programme of work. There is however a shortage of staff with the required specialist skills in PEC. It is recommended that the PEC request technical assistance to implement this agenda. This would be particularly timely given the recent merger of PEAS and PEC. / The fourth additional DLI is to improve development expenditure on education. Historically, the expenditure trend for education from the development budget in Punjab is quite low. Last year GoPb spent only Rs.6 billion out of an allocation of Rs.15 billion. This year, the Schools’ Department and the Planning and Development Department (P&D) agreed to release at least 40% of the development budget by 31 December 2013 ( It is expected that up to 80% of the allocated budget will be spent by the end of the year and that this trend will continue in 2014-15. To date 42% of the budget has been disbursed and the Chairman P&D has voiced his personal commitment to working with the Schools’ Department to achieve this target. / The fifth additional DLI is to support an inclusive education programme, to be executed by the Special Education Department in collaboration with the Schools’ Department, DSD and PMIU. This will tackle exclusion in the 11 low-performing districts. The total value of this programme is £7m which has been front-loaded. Funds will be provided to the Special Education Department. A PC1 has already been prepared and submitted. / It is recommended that the additional five DLIs be set out in an activity tracking matrix and that this be used as a monitoring tool. This will structure dialogue between DFID and PMIU around achievement of the additional five DLIs over the remainder of the programme (to March 2015). / Roadmap / The 14 February 2014 stocktake recorded the best ever enrolment results and a strong start on improving teacher quality. Sustained progress should result in significant transformation and will be supported by many of the new PESP II components coming on stream from March 2014. The stock take reported on the enrolment campaign, preparation for the DEAs rollout, implementation of the PEC/PEAS merger, record utilisation of the development budget and interim stocktakes to drive progress conducted by the Secretary. This record of success has been taken into consideration in the assessment of the PESP II AR score. More detailed recommendations are set out in the conclusions. / Impact Weighting :20% / Revised since last Annual Review? /N / Risk: Low/Medium/High / Revised since last Annual Review? /N

Output 2: Better teacher performance and better teaching in the classroom
Output 2 score and performance description: Outputs moderately did not meet expectation (B)
Progress against expected results: / Indicator On track? Score / 2.1 % classrooms in which lessons plans are available and being used in government schools Off-track B / 2.2 Teacher absentee rates in government schools Milestone exceeded (8% vs 15%) A+ / 2.3 Average no of instructional hours received by learners in government schools No milestone - awaiting TA component B / 2.4 No of new schools accessing finance through the Access to Finance Initiative attributable to DFID (cumulative) No milestone - awaiting research B / Output 2 aims to improve teacher performance by supporting better teaching in the classroom. This output is critical to the achievement of improved student learning as captured under outcomes 5, 6 and 7 in the PESP II logframe. It will be delivered through the Sector Budget Support and the achievement of the ten DLIs under the World Bank PAD, the additional five DLIs agreed by DFID and GoPb, as well as through financial aid provided to the Punjab Education Foundation (PEF). / This output is being monitored through four indicators, only one of which is being monitored on a monthly basis by the Chief Minister with the support of the Roadmap Team. One of indicators relates to the Technical Assistance component which has not yet started (contractor agreed in February 2013), while another relates to the Access to Finance component, which has not fully started (although initial research is expected in late March). The expectation was that the TA component would have progressed further than this, spending £0.5m in 2013/14, whereas no spend was forecast for the Access to Finance component. / Contextual Evidence / Sector Budget Support / The GoPb is implementing an extensive teacher development programme led by the Directorate of Staff Development (DSD). DSD has carried out a rigorous analysis as to why things were not working, identified weaknesses in the delivery chain and set out an extensive remedial plan. The percentage of effective monitoring visits to schools has risen from 82.3% in October 2013 to 91.5% in December 2013. Plans are in train to report learning results to parents. There are many reported achievements including improvements to the Continuous Professional Development (CPD) process and Professional Development (PD) day (based on a teacher observation checklist), improvements to student assessment, increased mentoring and modelling of good practice, actions to improve teacher content knowledge and subject delivery, and actions to address system weaknesses. / At the school level, teachers reported variable quality of the District Teacher Educators (DTEs) and Teacher Educators (TEs) assigned to support improved teacher performance, though the team was impressed with the enthusiasm and commitment of the three DTEs they met. The Government are in the process of removing DTEs who are not performing and have taken actions to ensure the quality of those currently being recruited. / DLI 10 under the WB PAD is to strengthen the collection and use of data on school, teacher and student performance. DSD has detailed information on teacher, student and school performance and it is recommended that this be linked to the PMIU Education Management Information System (EMIS) database. There is also an opportunity to link the planned PEF database to the national EMIS, to include attendance and performance data of low cost private schools (LCPS). It is recommended that PMIU explore these possibilities using technical assistance available under PESP II. / Data strengthening is also being supported by the Chief Minister’s School Reform Roadmap which has introduced a monthly system for monitoring key school-level indicators. There is now joint planning process with the Roadmap team on new quality indicators. These were agreed and communicated to EDOs in a workshop on 11 October 2013. These will report on leadership at the district and school levels and on teacher quality and learning outcomes, while ensuring that the success achieved on quantitative indicators is maintained. / Punjab Education Foundation / PEF is implementing a targeted CPD programme for low-performing teachers in schools participating in the Foundation Assisted Schools (FAS), Education Voucher Scheme (EVS) and New School Programme (NSP). Professional development is provided for teachers in schools that fail to ensure that 75% of students achieve 30% or more in the Quality Assurance Test (QAT). / In the opinion of the Review Team, PEF will need additional TA support to deliver improved teaching and learning at scale, given the ambitious targets for scale-up under the present log frame. The school visit, although not representative, gave some indication of the challenge of delivering quality education through low cost private schools. / Failing the Quality Assurance Test (QAT) assessment test can result in a loss of PEF funding by the school. This could drive a narrow focus on teaching the grades and areas assessed under the QAT to the detriment of broader student learning objectives. It is recommended that PEF use the available TA to review the design of the QAT (or to explore other approaches to teacher assessment). The new learning assessment system that DFID is supporting will provide a model for PEF to build upon. / PEF recognises that schools established under the New Schools Programme (NSP) will need additional support in order to become functional institutions with acceptable learning outcomes. PEF indicated that they are recommending to the Board that schools established under the NSP are initially exempted from losing PEF funding should they fail the QAT and instead continue to be supported to improve teacher performance. The review team would support this approach. / The business model of LCPS has been investigated. Research demonstrates that LCPS are profitable and may be able to attract commercial bank loans. Pay to teachers in LCPS is often significantly below the official minimum wage (Rs 8,000) and in many cases below a dollar a day. This finding was shared with the Secretary Schools at the PESP II Annual Review wrap-up meeting and he agreed that an acceptable minimum wage should be agreed with PEF. It is recommended that agreement on a minimum wage for teachers in schools supported by PEF is prioritised for follow up by the PESP II team. / Impact Weighting:20% / Revised since last Annual Review?/N / Risk: Low/Medium/High / Revised since last Annual Review? Y

Output 3: Better learning environment in schools
Output 3 score and performance description: No score assigned. / The team felt that it was not possible to score this output at this time.
Progress against expected results: / Indicator On track? Score / 3.1: % of schools with i) boundary walls ii) electricity iii) running water and iv) sanitation (equal weight) Infrastructure component procured Too early to score / 3.2: (i) # of classrooms and (ii) % of the intended classrooms built to recognised standards of durability, aesthetics and resilience to climate/disaster Infrastructure component procured Too early to score / 3.3: Beneficiary Happiness Index (boys, girls) No milestone - slight decrease No score / Under this output, PESP II aims to support GoPb to improve the learning environment in schools. Three programme components are contributing to achievement of this output; Sector Budget Support, School Infrastructure, and Access to Finance. The log frame indicators are not helpful. They fail to acknowledge the scoping processes and time needed before implementation can begin. It is too early to score against the last two components mentioned. There is some evidence that under SBS the learning environment has improved, however this evidence is insufficient to make a judgement. DSD’s teacher training reform plan will impact on this output but it is too early to draw conclusions. The conclusion is therefore that it is too early to score this output. This will be possible at the next annual review. / Contextual Evidence / School Infrastructure / GoPb has committed Rs7bn to provide missing facilities in government schools during FY 2013/14. Separately, a contract has been awarded through an OJEU process to IMC for the delivery of the school infrastructure component. The Secretary has requested that DFID funds be used to build additional classrooms instead of providing missing facilities which will now be delivered by GoPb. He also asked that shelterless schools be provided with two classrooms, in a change to the agreed programme design. Where schools already exist, this would make a significant difference to children’s educational experience and it is recommended that DFID consider this request in discussion with the contractors, IMC. / Access to Finance / A workshop on March 31, 2014 will disseminate findings from a pilot lending scheme to assist LCPS and enable this PESP II component to be designed and implemented. / Impact Weighting: 20% / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? /N

Output 4: More schools, with a focus on low performing districts
Output 4 score and performance description: Outputs met expectation (A)
Progress against expected results: / Indicator On track? Score / 4.1: Number of additional children in school supported through the Punjab Education Foundation (cumulative) / i) EVS ii) NSP iii) FAS PEF - Milestones incorrect - progress deemed on track A / 4.2: Number of additional children enrolled in schools where DFID has invested in additional classrooms Infrastructure component procured Too early to score / Under this output, PESP II aims to support GoPb to facilitate additional school places by enabling additional schools to open in the 11 low-performing districts. This output is a pre-condition for the delivery of the outcome of improved enrolment of girls and the poorest under outcomes 1 and 2. Three programme components are contributing to the achievement of this output; the school infrastructure programme in Low Performing Districts (LPD), financial aid for PEF, and Access to Finance for Low Cost Private Schools (LCPS). As noted under output 3, IMC have been contracted to construct schools under the school infrastructure programme. / Contextual Evidence / PEF are being funded under PESP II to scale up dramatically the number of additional children supported in primary, middle and high schools. This is being achieved through three PEF programmes (EVS, NPS and FAS). / PEF intend to reach 2.2 million students by 2017/18. This overall target is a significant expansion and will be challenging for the organisation to deliver. PEF has strong leadership, a clear vision, and a willingness to improve. It is recommended that the PESP II team prioritise TA support to PEF as a critical contribution to of DFID P’s Operational Plan commitment to supporting an additional four million children in school by 2015. / Impact Weighting: 20% / Revised since last Annual Review? /N / Risk: Low/Medium/High / Revised since last Annual Review? /N

Output 5: Enhanced demand for quality education for parents
Output 5 score and performance description: Outputs moderately met expectation (A) / Output 5 focuses on increasing parental demand for quality education in Punjab. The Low Performing Districts Programme (LPDP), the Punjab Inclusive Education Programme for children with disabilities (PIEP), stipends for girls, and the tertiary scholarship programme through the Punjab Education Endowment Fund (PEEF) and Lahore University of Management Studies (LUMS) directly contribute to this output. / LPDP and PIEP are not yet operational, although considerable progress has been made. The LPDP strategy and PIEP PC-1 have been prepared. These components will come on stream fairly quickly once the TA team is on the ground. The number of stipends being disbursed has fallen slightly due to the slow introduction of pilots which are shifting the payment process to on-line payment, though the 2012-13 DLI target is still on track. The scholarship component is making good progress and has met its milestones.
Progress against expected results: / Indicator On track? Score / 5.1: (i) Number of children previously not in school now in school as part of the community mobilisation programme, by grade (ii) No. of these children who stay in school and complete a full school year and (iii) indicator on disability mainstreaming (tbc) iv) The recent enrolment drive assisted by the Chief Ministers Roadmap team brought 435,000 into school from the period August 14th- to the present day No milestone - awaiting TA component but deemed to have met expectations A / 5.2: Number of secondary school girls' stipends in 16 target districts Milestone not met (data being checked) B (pending data check) / 5.3: No of (i) tertiary level scholarships for poor and able student (boys: girls) (ii) higher secondary scholarships for poor and able girls per year. Milestone met A / B: Contextual Evidence / Despite better enrolment in Punjab relative to other provinces, a large number of boys and girls are still out of school. In some parts of Punjab, particularly rural communities in the South, there is a need to develop parental demand for education and understanding of its value, especially among parents of girls. PESP II responds to this need by bolstering engagement of parents and communities in schools and providing incentives to overcome demand-side barriers. / LPDP and PIEP: These two programmes will mobilize parents and tackle social and cultural barriers to schooling in 11 low performing districts, with a focus on girls and children with mild disabilities. No milestones for additional enrolments from these two programmes in 2013/14 were set in the log frame. Once the TA is on the ground, they will contract civil society organizations to identify out-of-school children and ensure their enrolment. Considerable progress has been made in that direction. An operational strategy for LPDP was prepared in January 2013. This will fast track implementation when the TA comes on stream in March/April 2014. / PIEP will work alongside social mobilization activities under LPDP. A PC-1 has already been prepared. The Special Education Department, Schools Department, PMIU, DSD, Planning, and Finance are working together on this. This is a major breakthrough given the historically weak coordination among these departments on inclusive education. / Girls’ stipends: GoPb is providing stipends to secondary school girls in 16 districts. This DLI is part of the Sector Budget Support. Progress was reviewed in detail in the joint DFID-World Bank Mission in November 2013. The Review team also collected information about the number of stipends disbursed. The data indicate that the number of stipends disbursed has fallen. This is mainly due to issues in the collection of beneficiary data and delays in electronic payments in the two districts where the Supplemental Stipends Programme is being piloted (Bhakkar and Kasur) and the three pilot districts where the Branchless Banking Pilot is taking place (Muzaffargarh, Khanewal and Okara). PMIU is expediting actions to resolve the delays. / PEEF and LUMS Scholarships: This programme came on stream with the signing of grant agreements with LUMS in May 2013 and PEEF in July 2013. PEEF aims to provide stipends to 27,500 girls attending upper high schools (Grade 11 and 12) and 500 undergraduate students up until 2017/18. It is on track relative to the PESP II log-frame. So far 7,500 scholarships for Grade 11 and Grade 12 girls have been awarded along with 250 undergraduate scholarships in 2013/14. The Review team judged that PEEF is a highly capable organisation with strong systems in place to identify, award and monitor scholarships. / The LUMS scholarships will support 400 high-performing students from disadvantaged households to gain undergraduate degrees. The grant agreement was signed in May 2013 and the first tranche was paid by DFID in September 2013. 278 students (23% females) are being sponsored by DFID in 2013/14. Out of this number, 31 are ’returning’ students previously sponsored by LUMS. A new unit has been established to coordinate the National Outreach Programme (NOP) to recruit scholarship awardees and subsequently manage the scholarships. / While progress is satisfactory, DFID and partner organizations need to concentrate on the original idea of this programme, specifically that scholarship awardees will become role models inspiring girls and boys from marginalized backgrounds in their home towns to continue their education to higher secondary level and beyond. It is too early to show evidence of that impact but this will be one of the areas to be evaluated under the research and evaluation component. / Impact Weighting: 20% / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Progress and results
Has the log frame been updated since last review? / No, this is the first Annual Review and the log frame has not been reviewed since approval of the business case. / The log frame is problematic, and not fit for purpose due to: / Missing baselines and milestones; / Unrealistic milestones at odds with the business case and revised targets; / Unsatisfactory indicators; / The use of indicators drawn from the World Bank’s PAD document, which has not been updated since project inception. / ‘Placeholder’ indicators – scheduled to be updated when the infrastructure, technical assistance and community mobilization elements started up. (These elements are only now beginning.) / Data availability – it was time-consuming to obtain data from the relevant partners during the mission period, all of whom seemed unfamiliar with the log frame. / As a consequence the AR score has been arrived at through a laborious and intense assessment of both quantitative and qualitative evidence gathered during the AR mission. / A drastically revised log frame, in tune with ground realities and with realistic milestones for each year, needs to be developed by the end of April 2014. This should sit beneath the new Punjab Education Sector Plan to ensure Government ownership of the DFID programme outputs. It should be populated with the milestones which can be included now that the various components are becoming operational and include process milestones for the first and second years of the programme. The DFID TA team should work with PMIU to finalise the programme’s outputs and indicators and to develop a monitoring tool to track progress against the additional five DLls. / 1.2 Overall Output Score and Description: / The overall output score has been calculated as: Outputs met expectation (A) The final score was automatically generated by the system after inputting scores for each output. The team deliberated long and hard on each output, weighing both the quantitative and qualitative evidence available. / 1.3 Direct feedback from beneficiaries / The AR team visited two Government primary schools and one low-cost private school supported by PEF, all in Okara district. The team met students, members of a School Council, a District Education Officer (DEO), school principals, teachers and three Teacher Educators. The visit is not representative of those schools and children reached through PESP II, but it did allow some observations to be made of the impact and awareness of the programme at school level. / Both Government schools appeared well-managed with an attractive school environment. There was good availability – and to some extent use – of textbooks in all three schools, but use of other teaching resources were limited. Both Government school principals were aware of the Chief Minister’s Roadmap and the reasons for submitting data on education indicators. School Report Cards were visible in the School Principals’ offices, but there was limited understanding of how this information could be used to engage parents and community members. The School Principal confirmed that girls in Grade 6 to 10 were receiving a government stipend. / The team spoke with Grade 4 students in one of the Government schools. The students impressed the Team with their fluency reading in both Urdu and English. The two Government schools were supported by the CPD programme coordinated by DSD. The Team met with three female teacher educators who clearly articulated the support they provided to poorly-performing teachers, based on assessment, observation and modelling of good practice. They viewed being a DTE as a positive career opportunity, though they also mentioned challenges in mobility. / Harassment and the safety of children in schools were raised as concerns. The Schools’ Department should consider collecting data on fear of or incidence of harassment as part of the routine monitoring system of PMIU. This can then feed into a wider child protection strategy at school level. / The PEF-supported school was located in a large purpose-built building. The Team spoke briefly with a number of female students in the school who confirmed that they were benefiting from the Education Voucher Scheme but it was unclear why they had been targeted and whether they had previously been ‘out of school’. The school principal said there was more demand for vouchers in the catchment area. / The AR Team was told that a strong relationship of trust and mutual respect exists between DFID and GoPb. Evidence of the effectiveness of DFID engagement with the Punjab Schools’ Department includes (i) the high esteem in which DFID team members are held by Department officials, including the Secretary Schools, (ii) evidence of the policy and strategic advice given to the PMIU; and (iii) the level of partnership displayed in jointly achieving the DLIs under the WB PAD and the additional five DLIs. The Secretary Schools noted that PESP II was ‘a wonderful project’ and highlighted outcomes which he viewed the programme as supporting: increased enrolment, reduced dropout, and improved quality of education outcomes. Additional meetings were held with PEF, PEEF, LUMS, PEC, DSD, and the Textbook Board.
1.4 Summary of overall progress / The AR team were impressed with the transformative drive and commitment of the education personnel they met and the quality of the data systems at both PMIU and DSD. Much is clearly being achieved, some of which is reported in the Chief Minister’s Roadmap stock takes. Indications of accelerated delivery include: the disbursement of 57% of the development budget in the first quarter of the year; the impressive results of the recent enrolment drive; the determined focus on retention and quality in the classroom; and the emphasis on providing support to teachers. The work undertaken by DSD is particularly noteworthy in this respect. Significant progress has been made on improving continuous professional development, the creation of feedback loops to inform planning, more effective training especially for mentors (with greater emphasis on learning outcomes) and plans to communicate progress to parents. / The Punjab Education Sector Plan, Results Framework and revised log frame should be the basis for more coordinated oversight and monitoring of progress including through a steering committee structure and joint reviews. / Log frame data: Two out of five outputs (outputs 1 and 4) were assessed as meeting expectations (A). Two further outputs (outputs 2 and 5) were assessed as moderately not meeting expectations (B). / The AR team felt that it was not possible to score output 3 at this time, largely due to the lack of milestones but also due to the fact that it was unlikely to expect results against the infrastructure indicators listed within the first year of the project. / Contextual Evidence: According to the monthly data collected by PMIU, enrolment increased by around 435,000 during the summer enrolment campaign (August – October 2013) supported by the Road Map element of the TA component.
1.5 Key challenges / The key challenges to the achievement of the overall results are: / The need for the Provincial government to maintain its current levels of financial and political commitment / Potential resistance to reform by vested interests, including teachers / Insufficient capacity to deliver such an ambitious programme
1.6 Annual Outcome Assessment / The programme outcome is “more children in school, staying longer and learning more”. Based on the evidence currently available it is assessed as A. During the first year of the programme there has been strong progress across some elements (SBS, PEF and scholarships), with delays across others (infrastructure, TA) resulting from delays within DFID’s internal systems and the fact that decisions were taken to procure services for both Punjab and KP within larger contracts to ensure provision for KP which slowed the process. / Looking at the seven outcome indicators: / Absolute number of children in school: PMIU data shows an increase in head count of around 600,000 between October 2012 and October 2013. Analysis of the summer 2013 enrolment drive, showed enrolment increased by around 435,000 (+/- 150,000), between May and November 2013. / NER Primary (6-10), Middle (11-13) and Secondary (14-16) for all schools: Data not available. Indicator taken from WB’s PAD document which is not yet updated. / Completion rates/Transition rates – primary, middle: Data not yet available. This information is collected through Punjab’s Multiple Indicator Cluster Survey (MICS) which is next scheduled for 2014/15. / Percentage of students able to read a story in rural areas at Grade 3: The 2013 Annual Status of Education Report (ASER) Pakistan survey showed that 15% of Grade 3 students were able to read a story in Urdu, Sindhi or Pashtu. This is similar to previous years but inconsistent with the baseline set out in the log frame. It is assumed the milestone and/or indicator in the log frame is incorrect and should be reviewed. / Score in Urdu, Maths and Social Sciences for Grade four: This data is not available as there have been no Pakistan Education Assessment System (PEAS) assessments since 2011. / Mean total raw score for class five (out of 400) in PEC Exams (English, Urdu, Maths and Science) Data not yet available – awaiting information from PEC. / Independent tests at Grades 5 and 8. The baselines were taken from a WB assessment which has now been cancelled. It will be replaced by the new student assessments (being piloted in February 2014), supported by DFID.

2. Costs and timescale (in £million)
Description	Spend 2012/13	Spend 2013/14 to date
SBS	20 (20)	45.3 (47)
Design	0 ( 0)	0(0.03)
Access to finance	0 ( 0)	0 ( 0)
Infrastructure	0 ( 0)	0(0.5)
Civil Society	0 ( 0)	0(0.5)
Scholarship (LUMS)	0 ( 0)	0.71(0.75)
PEEF	0 ( 0)	1.5 ( 1.5)
PEF	5 ( 5)	5 ( 6.6)
TA (This amount is for Mckinsey Roadmap TA)	0 (0)	0.7( 1.3)
Total	25 (25)	53.21( 58.68)

Figures for the forecast in brackets.

In November 2013 it was agree to front load £47m of SBS in the financial year 2013/2014.
The first tranche was disbursed in 2013 against original DLIs and the last tranche will be disbursed
against the progress against five new DLIs in March 2014

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / It has been difficult to assess the evidence proposed by the log frame, due to the issues set out above (see Progress & Results section). Reviewing the log frame in partnership with the GoPb should help to better reflect the evidence available and provide a more robust assessment of progress against outputs. It would also allow an opportunity to revisit the Theory of Change. / A thorough assessment of any change in evidence can be made when the impact evaluation report is carried out. This could cover the evidence underpinning the business case Theory of Change, particularly around the evidence between the scholarships component and any changes in secondary education enrolment. / 3.2 Where an evaluation is planned what progress has been made? / In August 2013 it was decided that the PESP II and KESP evaluations should be integrated. This was i) due to the similarity between the reviews and ii) to safeguard against the likelihood of being unable to contract one and not the other. This resulted in a considerable delay in contracting. The evaluation involves a number of research and evaluation studies over several years. There will be two evaluations including: / An impact evaluation of the community mobilisation programme over the first two years of PESP II; / A system wide evaluation over the life of the PESP II and KESP programmes. / The evaluation will also involve a large multi-year research study on the low cost private sector in both Punjab and KP, in collaboration with Pakistani research institutions, looking at market dynamics, regulation, access and outcomes. / The evaluation contract is currently in the process of being awarded to OPM who were the successful bidder in the recent procurement exercise. An initial meeting will be held once the contract has been signed.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The team reviewed the programme risks set out in the business case and did not find that the overall assessment of risk had changed from medium. However the team did make some specific recommendations regarding the risk matrix set out in Annex 1. The main points were: / Opposition to reform on the basis of vested interests: This risk remains relevant, however the team reduced the risk probability from “high” to “moderate” due to the on-going political commitment to education reform across the political spectrum. The mitigation strategies have been updated accordingly. / Insufficient capacity to implement the programme at provincial level: The team assessed that the risk to the programme of insufficient capacity was reduced both from a probability and impact perspective. This assessment was made based upon the recent experience of civil servant turnover (in October 2013), where the new civil servants appointed to key positions remained equally able and committed to education reform. At the same time merit-based recruitment for key positions is on-going and is being actively pursued by senior political and bureaucratic figures. The mitigation strategies have been updated accordingly. / Conditions in low cost private schools pose a reputational risk to DFID: The reputational risk posed to DFID by LCPS was assessed to have a “high” not “moderate” probability, while the impact would remain the same. This was based upon existing and regular questioning by UK academics over the cost structure of private schools. The mitigation strategies have been updated accordingly. / The private sector does not respond to incentives to establish schools in under-served areas: This risk probability was increased from “moderate” to “high” due to the lack of progress in the past six months. The team made no changes to the mitigation strategies. / The risk that “support to low-performing districts is seen as DFID support for Southern Punjab, causing reputational damage” has been removed. This is due to the change in political situation post-election with the PML-N firmly in control and the decline in active calls for a separate Southern Punjab province. Moreover two of the low-performing districts remain in Central Punjab, while the selection criteria were shifted away from an exclusive focus on geography.
Risk of funds not being used as intended / This risk remains moderate, see risk matrix annex 1. / 4.4 Climate and Environment Risk / The assessment of the climate impact of PESP II is minimal. Only two interventions; the provisions of missing facilities and classroom construction, and text books have any potential environmental impact which is considered low. In the design of PESP II, DFID-P considered detailed steps it and partners would take to minimise the environmental impact of construction in Punjab

5. Value for Money
5.1 Performance on VfM measures / PESP II has only been operational for one year and the management of many of its sub-components has only very recently been awarded to a variety of contractors through competitive tendering processes. It is therefore impossible to draw robust conclusions about whether VfM is being achieved by the programme as a whole at this early stage. The following section provides a very partial analysis of VfM to date. / Sector Budget Support: During the review period two SBS payments were made including a substantial payment in December 2013 related to the front-loading of SBS. These funds are notionally allocated towards employee-related expenditure, grants to schools councils, PEF, the girls’ stipends programme, a performance based incentive system for schools, and school monitoring. An additional area – classroom assistants – was added on an interim basis to accommodate the enrolment surge generated by the Chief Minister’s enrolment drive while teacher rationalisation is rolled out. / The picture on value for money is mixed. One definitive area of success has been progress against the DLIs. During last year’s joint review ten out of ten DLIs were met by the Government. This year, the Government is currently on track to meet eight of the ten DLIs for 2013/14, and of the additional DLIs agreed with Government as part of the frontloading agreed in November, tangible progress has already been recorded on all five. If SBS is viewed as a reward for designing and implementing stretching policy reforms then against this criterion it has been successful to date. / It is less certain what impact SBS has had on increasing enrolment in Government schools, reducing drop-out, and improving learning achievement. These are the headline issues that the programme will ultimately be expected to address. While last year’s enrolment campaign appears to have been a short term success, it remains to be seen whether the children newly enrolled into Government schools will complete their education or drop-out over the next year or two. / Further, the picture on Government education expenditure – which SBS is notionally earmarked towards – is mixed. The review period covers two Government financial years – one pre-election and the other post-election. Both years saw substantial pay awards in excess of inflation offered to Government employees including teachers and the staff of the Schools’ Department. There is little evidence to suggest that these pay increases were warranted or that they have directly contributed to better education outcomes. The large increase in the allocation to the development budget in 2012/13 was vastly underutilised and non-salary recurrent expenditure to pay for operations and maintenance costs was woefully inadequate. / However, expenditure against the development and non-salary recurrent budget appears to have improved in 2013/14. The Government has already managed to execute around 42% of its development budget this year[1] and has increased the budget for non-salary recurrent expenditure several fold. This is an encouraging development, but one that will need to be sustained for many years to achieve real impact. / PEF: During the review period one payment was made to PEF to support the expansion plan. The table below compares actual unit costs per child with those estimated in the business case. / Actual Unit Costs per Child Unit Cost Estimates in Business Case / PEF Tranche 1 Primary: Rps450 per month / Middle: Rps450 per month Primary: Rps400 per month / Middle: Rps500 per month / Since programme design, PEF has taken the decision to offer a uniform rate to partner schools on a child per month basis and has thereby abandoned the differentiated rate previously in place. The costs incurred by the programme are therefore very close to the actual costs estimated during design, particularly when inflation is taken into account. Notwithstanding concerns raised by the review around the terms and conditions of some teachers employed in PEF schools, PEF therefore continues to achieve good value for money on inputs. Further, the cost per child to DFID has declined by around 10% since programme design due to the depreciation of the exchange rate. This suggests DFID is achieving better value for money than originally envisaged. / A uniform and robust assessment system will need to be rolled out in both public and PEF schools before an attempt to measure value for money on outputs is undertaken. / Infrastructure: This component was not operational at the time of the review and therefore no assessment of value for money was undertaken. / Low-Performing Districts: This component was not operational at the time of the review and therefore no assessment of value for money was undertaken. / Scholarships: The first round of scholarships through LUMS and PEEF were awarded during the review period. While there has clearly been no impact to date, the cost to DFID has been compared to estimates made during the design phase of the programme in the table below. / Actual Unit Costs per Scholarship Unit Cost Estimates in Business Case / PEEF Scholarships (Matric) Rps1,500-3,000 per month Rps1,000 per month / PEEF Scholarships (Higher Education) Rps17,750 per month Rps25,000 per month / LUMS Scholarships Rps54,500 per month Rps56,250 per month / The comparison of actual and estimated costs shows that: / PEEF matriculation scholarships are costing significantly more than originally estimated. Despite this, it remains the highest return component of PESP II with an estimated internal rate of return of 22% / PEEF higher education scholarships – which are awarded to six different institutions with different fee structures – are on average costing less than estimated in the business case / LUMS scholarships are more or less in line with original estimates / All three programmes continue to represent a sound investment with internal rates of return above 10%. As mentioned above, the cost to DFID of supporting these activities has also declined due to a depreciation of the exchange rate. / Access to Finance: This component was not operational at the time of the review and therefore no assessment of value for money was undertaken. / Technical Assistance: The bulk of this component was not operational at the time of the review and therefore no assessment of value for money was undertaken / During the review period the stand-alone technical assistance contract covering the Roadmap team came to an end and a new contract was negotiated which is now part of the PESP II programme. The team composition and fee rates were unaffected by the transition from one contract to another and so costs have remained the same. The procurement of the two large contracts for TACE and TAMO were competitively tendered in full compliance with the requirements of the EU public procurement regulations and the proposals assessed against a proportionate balance of technical (70%) and commercial (30%) criteria. The choice and balance of funding mechanisms is optimal in terms of degree of control, projected results, opportunity to transfer risk away from DFID, and value for money. / This will be continuously reviewed throughout the TACE programme. For school facilities, as a means to drive economies of scale, to prevent the supply market cherry-picking opportunities, and to avoid internal competition for the same supply resource, the procurement requirements for both provinces have been combined when approaching the market. Significant value for money will be achievable from advanced bulk purchase of certain materials, and from the sharing of cost and unit price data across the programmes to identify trends and spot exceptions. / The proposed approach for TAMO has a consistent focus on achieving better value for money. / a) One integrated team to manage both the Punjab Roadmap and technical assistance for PESP II in a seamless manner. / b) The combination of Adam Smith International and McKinsey will provide integration opportunities and synergies with DFID’s education programme in KP province (ASI provides technical assistance to the KP Education Programme as well). It will achieve this by combining project leadership and management across both projects institutionalising lesson learning and extending the resource sharing and VfM principles between KP and Punjab that have been initiated during programme implementation in KP. / c) A very lean and efficient full-time core team will be employed and supported by a short-term technical specialist resource pool. / d) Agreed 100% output-based payments during the inception and implementation phase. This results in a strong incentive to make the correct strategic choices and achieve maximum VfM / e) The proposed methodology is focused on achieving results.
[1] Covers the first 6 months of the 2013/14 financial year

6. Conditionality
None

7. Conclusions and actions
There are six overarching recommendations that, in the opinion of the Review Team, would strengthen the implementation of PESP II in the coming year. / 7.1. Project Management: The DFID Programme log frame should be revised, in a collaborative and participative way, to reflect the changing context and reality, by the end of March 2014. / Recommendation 1 The log frame should be substantially revised by the end of April 2014. It should sit beneath the new Punjab Education Sector Plan to ensure Government ownership of the DFID programme outputs. It should also be populated with the necessary milestones now that the various components are becoming operational and should include process milestones for the first and second years of the programme. The DFID technical assistance team should work with PMIU to finalise the programme’s outputs and indicators and develop a monitoring tool to track progress against the additional five DLls. The Punjab Education Sector Plan, Results Framework and revised log frame should be the basis for more coordinated oversight and monitoring of progress through a steering committee structure and joint reviews. / 7.2. Communication: The review team would encourage the strengthening of internal and external communication in the education sector to ensure that key stakeholders, especially teachers, understand the change process and are clear about its benefits. / Recommendation 2 1) An improved communication plan should be developed and implemented to ensure that the maximum impact on school management is achieved from the presence of the School Report Cards and data tools. 2) The communication strategy developed under the PMIU should be implemented, potentially through TA support. 3) The PMIU and DSD should develop a feedback loop to enable schools to report low performing DTEs. / 7.3.PMIU: The PMIU is an extremely able and competent body with access to and oversight of a wide range of information on the Punjab education sector. It is clear that this information and the PMIU are a significant reason for the success of education reform in Punjab. However, the Review team noted that the not all data on the education system is joined up within the PMIU and that there are other separate information systems (for example the DSD database on teacher training). Moreover, the team has some concerns about the location of the PMIU within the Government structure. / Recommendation 3 Consideration should be given to how to regularise the key functions of the PMIU to ensure the long-term sustainability of this clearly able and competent body, and the PMIU should continue to develop plans for an integrated Management Information System (MIS) and for the Chief Minister’s Monitoring Force (CMMF) institutional plan. / 7.4. Textbooks: The approval and publishing of poor quality textbooks is a reputational issue for both the GoPb and the UK Government. Good progress has been made in the Punjab Textbook Board (PTB) on implementing the recommendations from DFID’s continuous audit report to strengthen procurement and management practice. However, it is essential that this good start is sustained to enable effective learning in Punjab. The quality of the standard learning materials remains a concern, and improving quality is essential for improving learning outcomes in Punjab. / Recommendation 4 The Team recommends that GoPb clarify the mandates of the Punjab Curriculum Authority (PCA) and PTB, in line with international best practice, and that DFID and GoPb consider the provision of technical assistance to support on-going improvement in the oversight functions of text book procurement and management practices. / 7.5. Examinations: the recent merger of PEC and PEAS requires support during the integration and a skills audit to ensure that it is technically equipped with specialists and generally fit for purpose. The challenges facing the new organisation are immense. Not only does the organisation need to improve the quality of the examinations but also the integrity and over sight of the invigilation and marking processes. / Recommendation 5 Technical assistance support should be provided to PEC and PEAS to underpin and support these activities. / 7.6. Punjab Education Foundation (PEF) / The expansion of PEF is an ambitious undertaking and the Review team remain concerned about expansion capacity and targeting. In addition, the team will raise two related issues here. The QAT assessment tests may need revisiting. It is hoped that the new child-friendly diagnostic tests, currently being piloted for Grade 2 children in a sample across all districts, and involving both public and private schools, may assist PEF in improving their assessment strategy. In addition, lengthy protocols for getting sufficient new schools up and running may constrain the numbers of children they can attract. PEF and DFID should discuss this issue with Education Foundation Sindh (EFS) in Sindh and with BRAC Pakistan. There are also other NGOs, such as PLAN and Save the Children able to deliver education in remote and challenging environments. / Recommendation 6 That PEF considers a) revising the QAT Assessment Tests, b) allowing BRAC, or other NGOs with a track record in delivering education in challenging environments, to open up new schools in Punjab and c) setting a minimum level of pay for teachers in LCPS. DFID needs to be able to report significant additional children in schools as part of its overarching results commitment for Pakistan. The Review team is proposing this as a specific mechanism for going to scale swiftly.

8. Review Process
DFID-P invited the Education Adviser from Rwanda to take part in the review as well as inviting other DFID-P personnel not actively engaged in PESP II. The review process included the consideration of key programme documents, including third-party validations as well as relevant data sets and secondary sources. Core team members for the delivery of PESP II, government officials as well as the Chief Minister’s Roadmap team were consulted to provide additional details and supplement findings. The review took place from February 2 to 7, 2014.

## Annex 1: Risk Matrix

The team reviewed the programme risks set out in the business case and has made the following recommendations:
1. The current working of this risk is no longer valid, as the elections have past. Instead this risk should read, “reduced political will for education reform”. The mitigation strategies have been updated accordingly.
2. This risk remains relevant, however the team reduced the risk probability from “high” to “moderate” due to the on-going political commitment to education reform across the political spectrum. The mitigation strategies have been updated accordingly.
3. There was no change to this risk.
4. The team assessed that the risk to the programme of insufficient capacity was reduced both from a probability and impact perspective. This assessment was made based upon the recent experience of civil servant turnover (in October 2013), where the new civil servants appointed to key positions remained equally able and committed to education reform. At the same time merit based recruitment for key positions is on-going and being actively pursued by senior political and bureaucratic figures. The mitigation strategies have been updated accordingly.
5. This risk was not changed.
6. The reputational risk posed to DFID by low cost private schools was assessed to have a “high” not “moderate” probability, while the impact would remain the same. This was based upon existing and regular questioning by UK academics over the cost structure of private schools. The mitigation strategies have been updated accordingly.
7. This risk probability was increased from “moderate” to “high” due to the lack of progress in the past six months. The team made no changes to the mitigation strategies.
8. The risk that “support to low-performing districts is seen as DFID support for Southern Punjab, causing reputational damage” has been removed. This is due to the change in political situation post-election with the PLM-N firmly in control and the decline in active calls for a separate Southern Punjab province. Moreover two of the low-performing districts remain in Central Punjab, while the selection criterion was shifted away from a focus on geography.
9. The probability of this risk has been downgraded from “moderate” to “low”. This is largely due to the overall positive reception the scholarship programme has received in Pakistani press. The mitigation strategies have been updated accordingly.
10. There was no change to this risk however, the mitigation strategies have been updated based upon recent DFID programming changes.

	Risks	Mitigation Strategies	Probability/ Impact
1	Reduced political will for education reform	DFID will address this risk by ensuring that politicians from all parties, as well as the media, are fully briefed on the importance of education to the development and security of Punjab, and the role PESP II will play. This work will be carried out through the TEP programme, and regular briefings at senior level. DFID is also actively engaging senior political and bureaucratic figures to ensure that the continued rotation of key civil servants is reduced. / The team will also continue to build strong linkages with position leaders from across the political spectrum through the Education and Governance advisers based in Lahore.	L/H
2	Opposition to reform on the basis of vested interests	DFID will address this risk using a range of strategies. These will include piloting controversial measures before widespread implementation, supporting the development of stronger school councils to exert upward accountability, participatory involvement of all stakeholders in design and implementation or interventions, and ensuring that the programme is based on a thorough understanding of political economy to inform its interventions. / Teachers Unions will be kept involved in reform designs and implementation to ensure their interests are properly represented and taken care of with an aim to cultivate ownership of reforms. / Publishers and journalists will be kept abreast of on-going discussion related to education reforms and the overall benefit these changes will bring to the province. In addition, PESP II will benefit from public messages being communicated through the TEP programme.	M/M
3	Fiduciary and corruption risks	DFID will address this risk in three principal ways. The first two are designed to reduce fiduciary and corruption risks for the long term, while the third focuses on design decisions. / The Road Map process will continue to address a range of issues connected to fiduciary and corruption risks, including teacher attendance, merit-based appointments and teacher transfers. / PESP II SBS to GoPb in collaboration with SNG Programme will provide technical assistance to GoPb to support better public financial management especially in areas of procurement, budget expenditure, anti-corruption, and pay roll audit. DFID has already prepared a draft plan on mitigation of financial risk. / PESP II has been designed with this risk in mind. For example, the school infrastructure component will be implemented outside the GoPb procurement and management systems, while loans made under the access to finance programme will be subject to stringent criteria.	M/H
4	Insufficient capacity to implement the programme at provincial level	DFID will address this risk through the programme’s TA intervention with GoPb to encourage politicians and officials to build on progress towards developing flexible, merit-based management of the education system (for example, open recruitment practices). / DFID will work with the GoPb to encourage the PMIU to be a centre for long term sustainability and capacity building – exploring opportunities for salary incentives as required.	L/M
5	Insufficient capacity to implement the programme at district and sub-district level	Mitigation of this risk will be managed partially through the steps taken at programme level to reduce fiduciary and corruption risks. In addition, TA for PESP II will include building the capacity of officials at district and sub- district level. There will be a particular focus on capacity building in LPDs.	M/M
6	Conditions in low cost private schools pose a reputational risk to DFID	Mitigation of this risk will be managed by attaching conditions to DFID’s financial aid to PEF-run programmes, and to loans made as part of the access to finance programme. / DFID has undertaken research which demonstrates that PEF schools are profitable and will be working with PEF to roll out a better employment model for teachers.	H/M
7	The private sector does not respond to incentives to establish schools in under-served areas	Mitigation of this risk will be managed by attaching conditions to DFID’s financial aid to PEF, and to loans made as part of the access to finance programme. Conditions will focus on ensuring that private entrepreneurs expand or open their operations in under-served areas, with a focus on LPDs. DFID will pilot and monitor a range of approaches (for example, the development of incentive packages) to encourage entrepreneurs to focus in those areas where more schools are most clearly needed.	M/H
9	Scholarships programme attracts negative press in Pakistan and the UK	DFID will address this risk in three principal ways. First, DFID will commission regular evaluation of the private and societal returns of the programme and ensure course correction. Second, DFID will design a proactive communications strategy. This will focus on publishing case studies of success stories, working through TEP, focusing on increasing parental demand for education, awareness of private and societal returns, the importance of role models and their impact on raising the educational aspirations of poor girls and boys. / Third, DFID will seek to work with LUMS to demonstrate the targeting approach of this programme produces value for money.	L/M
10	Poor economic conditions limit job opportunities and restrict the fiscal space needed for sector reform	DFID will address this risk by monitoring closely the economic situation in Punjab and Pakistan, and taking appropriate action. The team will develop close links between PESP II and other DFID-funded programmes on pro-poor growth. / DFID will provide support for the IMF programme through the stability and growth programme. As part of this programme DFID will continue to advocate for increased spend on social sectors, including education.	M/M

Table 1: Risk analysis for PESP 2

		Impact
		High	Medium	Low
Probability	High		[2]
	Medium	[3]	[4] [5] [6] [8] [9] [10]
	Low	[1] [7]

Table 2: Risk rating matrix for PESP 2