Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Punjab Education Support Programme (PESP) II
Programme Value: £350.5 million		Review Date: November 2014
Programme Code: 202697	Start Date: 22/02/2013	End Date: 31/03/2019

Summary of programme performance:
Year	2013	2014
Programme Score	A	A
Risk Rating	Moderate	Moderate

This is the second annual review of the Punjab Education Support Programme II (PESP II). The first annual review was completed in February 2014 and the fieldwork for this review took place in November 2014. PESP II is investing £350.5m in the education system in Punjab and aims to drive whole system education reform at multiple levels through seven components. The Punjab Education Reform Roadmap, a mechanism for reporting jointly to the Chief Minister of Punjab and DFID Special Representative for Education in Pakistan through a bi-monthly stocktake, is also supported by PESP II. The Roadmap helps drive political commitment to education reform and give impetus to delivery and accountability at the highest level.

Summary of progress and lessons learnt since last review:
The review team found continued political commitment from the Government of Punjab (GoPb) to ambitious education reform at all levels, and overall had confidence in the Technical Assistance team’s knowledge and understanding of the Punjab education system.

Since the last Annual Review, significant progress has been made in the following areas:
- The establishment of the technical assistance team (TAMO) by Adam Smith International (ASI) in partnership with McKinsey. The TAMO team has been up and running since 1 June 2014 and includes staff who have formally worked on the Punjab Roadmap.
- The development of 2018 goals, designed to increase the ambition of education reform in Punjab, with a strong emphasis on better learning outcomes through improved teaching, leadership and infrastructure.
- An improved focus on learning and assessment, including the implementation of the first independent assessment of Grade 3 students’ proficiency in Urdu, maths and English.
- The reshaping of PESP II’s targets and priorities to reflect the increased focus on learning outcomes.

Summary of recommendations for the next year:
The scale and complexity of PESP II indicates the level of ambition and the potential for the programme to be transformational. However, there are also significant risks which must be acknowledged and managed carefully. The summary below sets out long, medium and short term recommendations to: build on and ensure the transformational impact of PESP II; and improve ways of working by streamlining processes, coordination and management. The recommendations are categorised as short term (next six months) , medium term (before next annual review) and long term (in the next 18-24 months).

Transformational reform

1. Ensure effective and irreversible reform. This means combining the already strong top-down approach with a continued and increased focus on buy-in and mobilisation from the bottom up. TAMO will need to reflect constantly on its approach to building capacity and ensure that it is strengthening institutional capacity as well as individual capability mainly of various departmental heads and the staff in the department of education. PESP II is due to end in 2018/19 but it will also be important to look ahead to 2025 and consider the sustainability of the education reform agenda in the long run. (Long-term but must be kept in mind for short-term planning and to maintain the focus on transformation).
2. Develop ambitious Grade 3 learning targets, tracked with reliable and valid data. The results from the first six-monthly assessment have provided a baseline. At the time of the review, consideration was being given to a reading target as part of the Roadmap process. This should be endorsed and simliar basic minimum standards considered for maths and English. There is a clear opportunity to support this with the assessment, curriculum and textbook reform all currently under way as part of PESP II. (Short-term)
3. Focus on continuous professional development support that robustly demonstrates impact. This should include support for better teaching and more effective leadership of schools and sub-Provincial units. The current approach could be simplified and strengthened with better evidence of what works. A focus on teaching essentials[1] might help, together with efforts to encourage students’ critical thinking and problem-solving skills. (Short-medium term)
  [1] For teaching this could focus on four key ingredients: (1) better teaching technique – especially of early Grade reading foundations; (2) use of quality textbooks and reading books; (3) children receiving enough learning and practice time; and (4) testing of learning outcomes – to help students learn more and teachers teach better.
4. Develop a long-term public private partnership (PPP) model that reaches the most marginalised with quality education. Support PEF to consolidate its expansion plan and finalise a long-term strategy for its evolution that demonstrates cost effective improvements in student learning while reaching the hardest to reach. (Medium term)
5. Consider creating a peer review mechanism to critique and challenge PESP II and TAMO in order to provide alternative perspectives and methodologies on areas of technical assistance channelled into the programme, for example on assessment and textbooks. A list of alternative experts should be compiled and DFID and TAMO review the points at which these peer to peer challenges are introduced. (Ongoing)

Ways of working

1. Consider consolidating future reporting and accountability mechanisms. The review team judged that there are currently too many reporting mechanisms (Roadmap, logframe, Disbursement Linked Indicators (DLIs)[2]). When looking at future support, there is an opportunity for DFID, the World Bank and the Government of Punjab (GoPb) to consider how to integrate subsequent reporting mechanisms and improve their ownership and management. This will increase efficiency and improve effectiveness of the monitoring. (Short-term)
  [2] This includes the ten World Bank DLIs and the additional five DFID DLIs
2. Explore the potential for a PESP II Steering Committee: PESP II is broader than the SBS elements however there is currently no suitable oversight/management forum that brings the SBS elements together with other PESP II activities critical to the reform effort e.g. the infrastructure and TA components. Various Government partners also raised concerns that, while the Roadmap process is positively driving the education reform agenda, the relationship between the Roadmap and PESP II implementation could be improved.  DFID should explore with the Government and development partners the demand for a PESP II Steering Committee, potentially jointly chaired by the Education Secretary, DFID and World Bank. (Short-term)
3. Clarify and improve ownership of data and evidence for programme reporting. There needs to be an overhaul of the way that data are managed and reported so that they are clear, consistent and easily accessible. This should include clarifying data management expectations as part of the ongoing work with TAMO to establish a monitoring and evidence framework. Revisions to the PESP II logframe are also recommended below and DFID should ensure TAMO develops a set of useful VFM metrics as part of broader efforts to establish a monitoring and evidence framework. (Short-term)

Delivery Risk. The ASI and McKinsey partnership is still bedding down and a costed workplan has yet to be agreed. TAMO needs to consider balancing a relatively heavy senior management structure with more technical resource to deliver the work streams. Additionally TAMO should clarify the roles and accountability chain within their senior management structure to DFID with a view to streamlining decision-making processes and costs. (Short-term)

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/

Outline of the programme

PESP II builds on the UK’s previous support to GoPb to reform and transform the delivery of education in Punjab. Through a range of innovative interventions with the government, private sector and civil society organisations (CSOs), the programme aims to deliver equitable access to better quality education across the whole province.

The UK will provide up to £350.5 million over six years between January 2013 and March 2019.

1. Sector Budget Support (£100m) provides funds to GoPb to improve access to education and to improve the quality in government schools (active).
2. School infrastructure (£104m) provides missing facilities and additional classrooms (active).
3. Capacity and quality building of Punjab’s low-cost private sector through the Punjab Education Foundation (£68.6m) (active).
4. Access to finance (£9m) focuses on expanding the low-cost private sector in underserved areas (this review makes recommendations on the future of this component).
5. Targeted support through CSOs to 11 priority districts (£10.8m) to fund social mobilization in the poor communities and set up community based schools in places where government schools are not available. (scheduled to commence March 2014/15).
6. A scholarship programme for higher education and girls’ higher secondary education (£18.2m) (active).
7. Technical assistance, split into two areas (£39.7m)
- Technical Assistance Management Organisation (TAMO) (£17.1m) which underpins the delivery of the six components (active).
- Punjab School Reform Roadmap programme (£2.9m) (active) The Reform Roadmap complements the wider programme by compiling robust data and presenting it to the Chief Minister. This secures political will to address tough issues like shifting from patronage to merit-based appointments and broadening the focus from access to quality.
Evaluation and Research (£2.5m) (active).

Expected results

The UK’s support to the GoPb will have a significant impact on driving reform and improving the quality of teaching and learning outcomes. Structural reforms will impact positively on future cohorts of children in schools across Punjab. PESP II accounts for over 90% of DFID’s forecast of primary school children benefiting from DFID support. Over 6 million primary school and 3 million secondary children will have benefitted from UK support in Punjab by March 2015.

Education context in Punjab
Pakistan cannot hope to end its education emergency without a substantial, rapid, and sustained increase in the quantity and quality of schooling in Punjab. Punjab is the largest of Pakistan’s provinces, comprising 56% of the country’s population, and currently contributing 58% of Pakistan’s GDP.[1] As a result of its size, Punjab has the highest number of out-of-school children aged 6-16 years in Pakistan (approximately six million)[2] and the highest number of children with low learning levels.
[1] Punjab Economic Research Institute and Govt of Punjab (2007). NB: Punjab has not produced any subsequent economic reports, while Pakistan Economic Surveys do not report disaggregated provincial GDPs.
[2] UNESCO Institute of Statistics (2012). Local estimates are far higher.

GoPb continues to display strong political commitment to education reforms under the leadership of the Chief Minister and the Secretary School Education. A consistently strong message from partners consulted was that this is a stable, committed Government that will focus on delivering education reforms. This has been demonstrated by the appointment of highly competent civil servants to key education posts and retaining them in post for a minimum of three years.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome of PESP II is “more children in school, staying longer and learning more”.

Outcome	Target by November 2014	Results (November 2014)*
Indicator 1: Participation rate for primary school aged population (ages 5-9)	Girls: 87%; Boys: 89%	Girls: 88.3% ; Boys: 90.3%
Indicator 2: Participation rate for secondary school aged population (ages 10-16)	Girls 78%; Boys 82%	Girls: 79.6%; Boys: 83.8%
Indicator 3: Student outcomes: / -Percentage of students able to read a sentence in Urdu (source: ASER / LND drive) / -Percentage of students able to conduct simple mathematical computations (source: ASER / LND drive) / -Average score on DFID funded 6 monthly assessment / -Optional: Average PEC scores for Grades 5 & 8 (2016/17 onwards)	Grade 3 that can read: 26% / Grade 3 that can do double digit subtraction: 31% / [ASER 2013]	Grade 3 (rural)[3] that can read sentences: 53% / Grade 3 (rural) that can read a simple story: 27% / Grade 3 (rural) that can do two digit subtraction: 32% / [ASER 2014] / % of students who can read a four line paragraph in Urdu and answer 3 questions: 50% / Grade 3 that can carry out two digit subtraction without borrow: 60%; two digit subtraction with borrow: 33% / [DFID 6 monthly assessment]
Indicator 4: Student attendance	92%	90.3%
[3] ASER only covers rural where 90% government schools are located. This is why it is representative but doesn’t include urban communities, however it is comparable with previous years.

* Data for indicators 1 and 2 updated in January 2015 and reflect situation as of December 2014.

Participation rates as at December 2014 marginally exceeded all November 2014 targets for primary and secondary school aged populations. With regards to learning outcomes, the new six-monthly assessment shows higher learning in terms of reading Urdu (50%) than the ASER-based targets anticipate (26%), and slightly higher learning on two-digit subtraction. ASER data for rural Punjab shows no change in reading levels over the last year. Student attendance has dropped slightly below the target. Disagreement exists on whether the target should be lower given that in other large and diverse systems students attence rates are lower than Punjab and are still considered acceptable due to the size of the system.

The ability to demonstrate change in student learning outcomes in Punjab is an increasingly important and urgent task. Building on the baseline established with the first bi-annual, sample-based Grade 3 assessment, it is now possible to map annual learning targets up until 2018 and beyond.
Recommendation (Short-term): The logframe should be reviewed as soon as possible and consensus reached on the indicators and milestones to ensure that all stakeholders are working towards agreed goals. Progress against the logframe should be built into routine meetings throughout the year. The logframe review should also consider (a) increasing the overall impact weighting of output 1 to acknowledge its importance in delivery of long-term reform; (b) revising output 1.3 should to measure the effectiveness of school councils; (c) ensuring indicators under output 2 are closely aligned with the GoPb vision for education in 2018; and (d) increasing the risk rating of outputs 3 and 4.

Has the log frame been updated since the last review?
Yes, a new log frame was developed by DFID and TAMO two months in advance of this annual review. However, there is a lack of clarity on some milestones. Further revisions are recommended.

## C: DETAILED OUTPUT SCORING

Output Title	Better managed, more accountable education system
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of districts with effective, targeted system wide performance management system	Performance management approach developed and pilot district selected	Achieved (but the approach could be strengthened). Pilots in at least 2 districts have been conducted already with plans to roll out to all districts.
1.2 Frequency of Monitoring and Evaluation Assistants (MEAs) visits and better reliability of data collected	90% school visit rate maintained every month / Tablet based real time data collection system successfully piloted in 8 districts with a minimum of two rounds of data collection.	96% (compared to 94% a year ago) / Tablet-based real-time data collection rolled out and in use in all districts. Paper system due to be replaced fully by January 2015.
1.3 Functional Primary School Councils covering monthly meetings, expenditure of grants/ budgets and improvement in teacher presence	50% schools	Not achieved: / Meetings: 44% / Expenditure: 34% / Attendance: 36%

Key points
Under this output, PESP II aims to support the GoPb to improve management of the education system and increase Government accountability for quality education. Achievement of this output is chiefly supported through the sector budget support component. The Punjab Roadmap secures and keeps the momentum for high-level political commitment to reform. This output qualifies as an ‘A’ taking into account actual progress against logframe indicators and wider contextual information.

Summary of progress
Output 1.1: Performance management of districts: the purpose of this stream of work is: (1) to improve capability of districts to manage and use data to inform district level decisions; and (2) to increase ownership at district level by Education District Officers (EDOs) to review district performance. Some progress has been made to introduce performance management approaches. The TAMO inception report proposes a soft and decentralised performance management system to drive accountability. This essentially means that rather than proposing a structural change , a more consent-based target monitoring system will be put in place to allow for district level performance stocktakes. Key performance indicators were being tested in two districts at the time of the review (Sheikhapura and Muzaffargarh), with plans to scale up in at least nine districts by December 2014. Regular meetings between the Education Secretary and EDOs have also been instated. This is an ambitious but important area of work which is likely to take time. Initial institutional structures are being put in place, but more work needs to be done to build on these and make them a success. An agreement has been secured to recruit an additional 3,000-4,000 Assistant Education Officers (AEOs) to manage primary schools but this has yet to be implemented.
Recommendation (Short-term): TAMO should set out a clear plan for refining the current KPIs being trialled in a small set of districts to achieve a fully functioning system of accountability; and build capability to run this in a decentralised manner. This needs to be integrated with existing mechanisms such as District and School Report Cards.

Output 1.2: 96% of schools are visited on average per month. A tablet-based real-time data collection system has successfully been piloted in all districts with a minimum of two rounds of data collection. Monitoring and Evaluation Assistants (MEAs) are currently collecting data in both tablets and paper form and will transition completely to tablets in January 2015. This will further help reduce the time lag in data collection and improve the validity of the data due to GPS tagging.

Data produced by the Programme Monitoring and Implementation Unit (PMIU) from MEA visits has helped to produce and communicate reliable and regular data on what is happening at different levels of the Punjab education system, including for use by the Roadmap for stocktake meetings. Steps have been taken to strengthen the reliability of MEA data and verifications have found the data to be credible. Questions were however raised about the adequacy of criteria for assessing actual functionality of facilities, over and beyond them simply being in place, and should be taken into consideration as part of future improvements to data collection.

In addition to overseeing data collection for the education sector, the PMIU has been central to delivery and monitoring of the ten Disbursement Linked Indicators (DLIS), with which World Bank support and DFID SBS are jointly aligned. The PMIU has not played a role in monitoring the additional five DLIs that were introduced when DFID’s SBS was brought forward for disbursement. The role of the PMIU should be taken into account when considering future reporting, co-ordination and accountability mechanisms.

Output 1.3: This indicator is linked to a DFID/World Bank DLI and has received technical assistance largely from the World Bank. DFID has participated in the working group for school councils. There are issues defining a functional school council which is currently measured in the logframe against three factors: meetings, expenditure of grants and teacher presence and improvement. PMIU data show that all three elements (regular meetings, expenditure, teacher improvement) fall short of the 50% logframe target. Data on school councils is monitored regularly by PMIU and includes reviews of financial records and meeting minutes, with plans to increase monitoring of numbers attending and issues discussed. However given the scale of the system (54,000 schools,) reviewing individual records of meetings minutes is likely to be challenging and unviable. Developing an approach to assess and strengthen school councils will require further thought and planning by TAMO.

In 2013, the Government of Punjab introduced a policy where every school must have a school council. A revised policy for school councils has been rolled out to 21 districts and is due to be in place in all 36 districts by March 2015. An innovative ICT-based model is being used to establish sustained contact with school councils, monitor their activity and provide support through a call centre/helpline. The World Bank has conducted a third-party implementation review, which showed promising results of this initiative, with 68% of council members engaged.

School Councils are responsible for deciding how to spend the proportion of the non-salary education budget allocated to them. However, there is often a reluctance, or risk aversion on their part to execute this confidently and effectively. A pilot that has seen additional non-salary budget channelled directly to school councils has had some success in improving expenditure on basic needs of schools.
Recommendation (Short-medium term): As part of its forward work on school councils, TAMO should consider providing assistance to ensure the guidance and support to school councils on school development plans includes more on effective budgeting and spending.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review acknowledged the important role of SBS and recommended that DFID’s additional five DLIs (agreed with Government as a mechanism against which to bring forward SBS disbursements) be set out in an activity tracking matrix for use as a monitoring tool. This was intended to structure dialogue between DFID and PMIU around achievement of the additional five DLIs over the remainder of the programme (to March 2015). A matrix was constructed to assess the DLIs for the latest World Bank review mission. The PMIU has played a central role in monitoring the original ten DLIs but has not been engaged in monitoring the additional five DLIs.

Output Title	Better teacher performance and better teaching
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 New textbooks, teacher guides, and workbooks developed in line with new curriculum	Work on 3 model textbooks and workbooks developed and approved by PCTB / Improved SOPs and criteria for manuscript review defined based on model textbooks / Diagnostic of PCTB's procurement process and opportunities for improvement identified and quantified	The milestone itself has not been met; however, this is because a much better approach was agreed/adopted. Progress includes: / Detailed plan developed, BRAC engaged, School Education Department and PCTB approved plan. Textbooks and teacher guides developed for English and maths with further work planned for Urdu and general studies materials.
2.2 Bi-annual learning assessment system in place.	First test conducted at acceptable standard of quality and reliability / Baseline levels of student learning established	Baseline established for six monthly independent assessment; second round due in February 2015
2.3 Integrity of Punjab Examination Commission (PEC) exams	PEC improvement plan developed and approved by School Education Department	Detailed PEC improvement plan developed, version approved w/c 17th November.
2.4 Quality and delivery of teacher training and mentoring.	Refine DTE schedule based on robust coaching model, and define proper monitoring mechanism for DTE visits to establish true baseline	DTE attendance at 85.93%; plan to increase frequency of DTE mentoring visits approved by DSD; pilot underway in five districts
2.5 Teacher absentee rates in government schools	8%	7.73% (compared to 8.09% a year ago)

Key points

Output 2 aims to improve teacher performance by supporting better teaching. Whilst not fully captured here, this workstream also includes significant efforts to support GoPb to rationalise teachers across all districts, and recruit additional teachers under a strengthened recruitment policy. Despite substantial resistance from teachers due to their transfers to crowded or hard to reach schools, these measures are progressing and should help to reduce mutliGrade teaching. Planned work under the infrastructure component to build additional classrooms should also help to address mutli-Grade teaching. As recommended above, DFID may want to consider revising the output indicators to reflect the GoPbs 2018 vision on high quality teaching and learning in the classroom. Output 2 is delivered through Sector Budget Support, the Punjab Education Foundation and technical assistance through TAMO and the Roadmap teams. DFID should monitor the risks around delivery, particularly of indicator 2.3, which was considered by the review team to be of higher risk.

Summary of progress

New indicators: Only indicator 2.5 (teacher absentee rates) has been carried over in the logframe from the previous annual review. All other indicators have been newly introduced. The inclusion of indicators relating to new and improved textbooks and materials, learning assessments and exams and improved teacher training and support speak to the required focus on improved quality in Punjab education service delivery across both government and Punjab Education Foundation schools. Indicators 2.1 to 2.4 speak to critical processes to ensure the delivery of quality education and should tie in with the 2018 goal to transform the quality of education in Punjab.
Textbooks: the textbook and curriculum boards were merged and brought under the new Punjab Curriculum and Textbook Board (PCTB) in September 2014. Following DFID’s advice, it was reported that the PCTB has now been reconstituted and includes external members to improve oversight. With improved enforcement of rules and greater transparency, cost savings were reported in the development of new textbooks. Future outsourcing of textbook development is being considered.

With the Chief Minister’s call to focus on quality education, the PCTB is engaged with the Roadmap in producing new and improved set of books but has had limited interaction with TAMO to date. In line with the review of Grades 1 to 3 curriculum, the PCTB plans to have externally quality-assured textbooks and teacher guides for Grade 1 ready by April 2015. Grades 2-3 textbooks and guides are planned for the year after. Apart from input from sector experts, it was unclear to the review team what evidence base is being drawn on to inform the curriculum and textbook review and what quality assurance and cost control measures are in place. [4]
[4] For example, in calculating the costs, the annual amortised cost of the new textbooks should be considered. This includes the unit cost of the textbook, the target classroom life of the textbook (in years) and the target textbook to pupil ratio (unit cost / target textbook life / target textbook to pupil ratio = amortised cost). It is not sufficient to focus only on the unit costs.
Recommendation (ongoing): Draw on additional external expertise to peer review and quality assure the new textbook development plans, including cost and budget considerations, as well as the potential role of the private sector.

Learning assessment, integrity of the Punjab Examination Commission (PEC) exams and Quality Assurance Test (QAT) within Punjab Education Foundation (PEF): There are multiple assessment and exam efforts in Punjab; the review team counted six carried out by various government and non-government agencies.[5] The existing efforts appear to be duplicative, are not coordinated, and do not form part of a coherent strategy or approach to student assessment in Punjab. There is already a recognised need for clarity of purpose, coordination and vision to join these efforts up and increase efficiency and effectiveness. It is of crucial importance to ensure that assessment is used to drive improvements in teaching and learning practice. To do this, the role of assessment as a diagnostic tool, used every day by teachers in the classroom, needs greater emphasis.
[5] PEC exams (Grades 5 and 8); DSD monthly assessments of students by DTEs; PEF QAT; DFID-funded bi-annual sample-based assessment (Grade 3); MEA literacy and numeracy monthly assessment; ASER household based literacy and numeracy assessments.

The Punjab Examination Commission (PEC) is undergoing significant reform, having now incorporated the Punjab Education Assessment System body (PEAS). The current effort includes recruiting new staff (it was reported that three assessment specialists with PhDs and five subject specialists have recently been recruited) and developing a new organogram. It was also reported that 4,000 staff have been trained to improve the administration of the PEC exams.

PEC appears to serve multiple purposes, including system diagnosis, student and school differentiation, and feedback to inform curriculum, pedagogy and broader policy. The PEC CEO was focused on the main aim of improving the credibility of the PEC exams. There is a challenge on both the content (e.g. item quality) and the conduct (e.g. cheating) of the exams and it remains unclear how credibility will be judged. TAMO has recently brought in a short-term expert to support both PEC and the PCTB. It is important that TAMO steps back and reflects on the overall strategy and approach to assessment and exams in Punjab without rushing to make quick fixes that lose sight of the bigger picture of whole system reform. It is also important to bring in an element of peer review into the process of assessment reform.

The PEC improvement plan is comprehensive in its focus on improving the reliability and validity of the PEC exams. The plan does not, however, situate PEC or its exams in relationship to the other assessment efforts in Punjab and nor does it clearly state the purpose of the PEC exams.

It was reported by TAMO that the Quality Assurance Test (QAT) assessment items used by PEF were better quality than PEC but there is still room for significant improvement. There is a plan to merge the QAT and PEC exams in the future. It is difficult to make a judgement on whether or not this is a sensible approach in the absence of an overall strategy for assessment and exams in Punjab and will require Government leadership. The QAT currently performs an important role in incentivising a focus on quality learning outcomes in PEF schools. An end of cycle, census exam (like PEC) may not be so successful in doing this. Plans to merge the QAT and PEC exams must be thought through within a longer term strategy for assessment and exams in Punjab

The first Grade 3 learning assessment was successfully completed and a baseline established in September 2014. It was unclear to the review team who wrote the test items as PEC appears to have played a minimal role in the assessment. Assistant Education Officers (AEOs) and District Teacher Educators (DTEs) were the main invigilators with significant monitoring from the Roadmap/TAMO team (89 schools) as well as by an independent monitoring body from PWC (80 schools). Plans are in place to include PEF schools in the next iteration. There is a real opportunity to build on this robust and independently verified assessment of foundation skills and for this to feed in to work on textbooks / curriculum / teacher development and support as well as improving the assessment / exam procedures for both public and PEF schools.
- Recommendation (short-medium term): Map out a long-term strategy for the development of a robust assessment system in Punjab that links all assessment and examination efforts (including the Grade 3 assessment, QAT and PEC). This should be led by PEC, but link across all the relevant education departments and relate to an understanding of students’ expected progression in core subject areas. There are opportunities to draw on the SABER assessment diagnostic carried out in Punjab in 2012, to learn from current efforts to develop a global common metric for reading and maths as well as bring in additional external expertise such as the Australian Council for Education Research.
- Recommendation (short-medium term): Given the priority placed on credibility of exams by PEC, and the high risks around examination reform, TAMO need to define how credibility will be assessed for PEC in relation to the points made above on both content and conduct.

Quality and delivery of teacher training and mentoring: It was reported that the Department for Staff Development (DSD) has recruited more than 3,900 District Teacher Educators (DTEs), to increase the coverage of mentoring that teachers receive. DSD has made moves to free up more time for DTEs to mentor by phasing out their present student assessment which is consuming a lot of time of DTEs. Reflecting the recognition that there are too many assessments, seven districts are no longer undertaking assessment, with plans for DTEs to eventually focus on coaching activities only. Support has been received from the Roadmap team and now TAMO on improving the structure of professional development days and setting up of dedicated District Training and Support Centres (DTSCs). KPIs for DTEs include coverage of schools, coverage of teachers, and in-time reporting. Positive feedback was received from teachers on mentoring with visible and systematic application to classroom practice.

There were several challenges raised related to the work of DTEs. Mobility of DTEs is a challenge, particularly for female DTEs. DSD has struggled to relieve poor performing DTEs of their duties and noted limited consultation on the development of reforms that it has had to implement later. As in other Departments, DSD faces risks related to the availability of funds and high turnover of key officials. Given the potential conflict of interest where DTEs are responsible for both improving the quality of teaching and assessment of students, the Roadmap has suggested that MEAs begin collecting data on literacy and numeracy using a tablet-based assessment.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous Annual Review made the following recommendations under this output:
1. PEC request technical assistance to implement this agenda. This would be particularly timely given the recent merger of PEAS and PEC.
2. PEF use the available TA to review the design of the QAT (or to explore other approaches to teacher assessment).
3. PMIU explore possibilities to link data from EMIS, PEF and DSD.

TAMO has engaged a short-term technical expert to support assessment reform both in PEC and PEF. Efforts have been made by PMIU to integrate data from across government and PEF in a single database. MEAs have largely moved to tablets to record data with help from the Punjab Information Technology Board (PITB). Full digitisation is expected by January. Validation exercises have found few discrepancies in the data. PMIU has not progressed improvement plans recorded in the Chief Minister Monitoring Force (CMMF).

Output Title	Better learning environment
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 School infrastructure	All districts with functioning facilities >90% or a clear plan to improve functioning of facilities to >90% within the current school year	Achieved. Two districts below 90% with clear plan in place
3.2 Aggregate number of schools rehabilitated to international standards	Implementation Phase workplan finalised and TACE rolling into implementation.	Partially Achieved. A comprehensive workplan has been completed. TACE is ready to start construction work, but the implementation phase has not yet started due to contractual difficulties.
3.3 Classrooms with multiGrade teaching	Identify districts / Identify list of schools for alternative year entry and double shifting / Create four year plan for classroom construction	Partially achieved. Districts identified. Infrastructure Plan proposes research into multi-Grade and multi-shift teaching. Milestone not reflective of the agreed approach to planning.

Key points
Under this output, PESP II aims to support the GoPb to improve the learning environment in schools. This output is predominantly supported by the PESP II school infrastructure component, implemented by IMC. The Roadmap also monitors functional school facilities every two months at stocktakes. School infrastructure is a high priority for the School Education Department. In addition to DFID’s support through TACE, the GoPb continues to allocate significant amounts of its own resources to missing facilities and school infrastructure. Contractual issues have delayed the commencement of building work, meaning that overall the output has not been fully achieved. DFID should review whether the risk weighting should be increased to ‘high’.

Summary of progress
School infrastructure: School facilities are monitored as part of stocktake reporting for the Roadmap. At the point of the review, only two districts were found to have less than 90% functioning facilities. Plans have been put in place to address this.
IMC: Since the last annual review, IMC has come on board to deliver the school buildings and construction component of PESP II. However, delays caused by lack of relevant data on which to prioritise in addition to IMC registration issues have meant that actual building work has not begun. IMC has managed this by increasing preparatory and baseline activities so that they are set to begin construction as soon as the issue is resolved.

A scoping study has been conducted to set a baseline for the current state of school facilities. IMC flagged a 5-7% variance with data reported by MEAs on school facilities. This was largely due to the interpretation of what constituted functioning school facilities. The scoping study has highlighted three initial priorities: shelterless schools; cases of severe overcrowding; and multi-grade teaching. An education infrastructure strategic plan has been developed and as per Government of Punjab priorties, majority of the funds will be used to construct extra classrooms. Phased implementation is taking place on a rolling basis starting with clusters of districts. A baseline survey of school facilities has been conducted in four districts: Lahore, Faisalabad, Sialkot and Rahimyar Khan. The study is intended to set a baseline to avoid duplication with the GoPb’s own construction projects, as there is some overlap and a risk of double counting as data were not easily available.

Overall, IMC inspired confidence in their ability to manage this large and ambitious school infrastructure programme, and had a robust plan to identify, manage and mitigate against risk. International evidence on child-friendly classrooms is also being examined. They are working collaboratively with other parts of the DFID Pakistan education portfolio, for example a design competition is being run to attract innovative classroom designs from university students. The planned approach to implementation is designed to be in collaboration with school councils, local civil society and community-based organisations to get buy-in and ownership of the new facilities. Schools councils will be given ownership of a development plan for their school, which will help them and DEOs to know where there is a shortfall in school facilities. Plans to build school council capacity to play this role are also in place.
Recommendation (short-medium term): GoPb to ensure that the Works Department (responsible for infrastructure) and School Education Department effectively share data on school construction to enable informed planning and avoid duplication of effort.

IMC plans to use a mix of commercial and community contracting to make the most of local communities’ skills, expertise and ability to contract at lower cost, whilst recognising capacity limitations. This approach should offer maximum efficiency and encourage community ownership of construction projects. Measures are also in place to understand the local market rates and identify opportunities for cost savings.

Summary of responses to issues raised in previous annual reviews (where relevant)
Logframe indicators have been revised since the last annual review to reflect scoping processes and time needed before implementation begins.

Output Title	Improved access to schools, especially in priority districts
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
4.1 Participation rate (primary, middle, secondary) disaggregated by gender in priority districts.	Primary - Girls: 75%, Boys: 82% / Middle - Girls: 72% Boys: 81% / Secondary - Girls: 54% Boys: 63%	Primary - Girls: 80%, Boys: 84.7% / Middle - Girls: 77% Boys: 84% / Secondary - Girls: 65% Boys: 75%
4.2 Number of children in school supported through the Punjab Education Foundation (cumulative) i) Education Vouchers Scheme (EVS) ii) New School Prorgamme (NSP) iii) Foundation Assisted Schools (FAS)	Logframe targets[6]: / (i) 358,000 ii) 111,000 iii) 430,000	Discrepancies in logframe targets makes assessing progress difficult. / Progress as at Nov 2014: / (i) 215,213 (93,015 additional) / (ii) 88,107 (29,083 additional) / (iii) 1,254,615 (93,015 additional) / Progress against PEF’s own March 2014 Targets: / Of the three 2013/14 PEF targets only EVS was achieved.
4.3 Number of children supported through Punjab Inclusive Education Programme	0	PC-1 approved, Programme Implementation Unit being established, PIEP to be piloted in districts Bahawalpur and Muzaffargarh
[6] PEF also has its own targets for March 2015: EVS: 108,000 additional children; NSP 28,000 additional children; and FAS: 112,000 additional children.

Key points

Under this output, PESP II aims to support the GoPb to maintain progress on improved access to schools, particularly amongst marginalised groups, including students with special educational needs. The Government plans for any new schools built in the province to be achieved through PEF. While this clearly politically endorses PEF, it will be important to ensure equitable financing for the most marginalised and poorest communities. On average, funding per student in PEF schools is significantly lower than funding per student in government schools. Output 4 will be delivered through SBS, PEF and technical assistance through TAMO and the Roadmap teams.

Summary of progress
PEF is being funded under PESP II to scale up dramatically the number of children supported in primary, middle and high schools through the three PEF programmes: Foundation Assisted Schools (FAS); Education Voucher Scheme (EVS); and New School Programme (NSP). PEF has a clear expansion plan but this is yet to be consolidated into a long-term strategy and vision for its model of service delivery. The model is talked of in terms of PPPs and Low-Cost Private Schools (LCPS) but in reality, the financing is heavily skewed towards public investment and there was no reported additional private finance (over and above household and owner contributions). Different models could be pursued e.g. publicly-funded, privately-managed schools (the FAS model) or something closer to an extensive chain of LCPS with vouchers for the poorest (more like EVS). Taking a longer-term view would also require additional analysis on the regulatory environment for low-cost private schools and encourage wider lesson learning on PPPs. As part of the expansion of PEF, a clear and consolidated, longer-term strategy (5 to 10 years) for PEF and its support from GoPb should be kept in mind. For example, in 5 to 10 years’ time, does PEF see itself as a PPP supporting a low-fee private school chain or is the aim to develop an alternative model of publicly- financed, independent schools? TAMO may need to engage a short term expert to support this work.
On regulation, the previous Annual Review (February 2014) had recommended that an agreement on a minimum wage for teachers in schools supported by PEF be prioritised for follow up with the PESP II team. Progress was not reported on this issue.
Recommendation (short-term): DFID should task TAMO to analyse teacher pay / profit margins / negotiability / affordability and use this analysis to take a final view on minimum wages. The analysis should clarify the incremental monthly student cost for ensuring that teachers are paid the minimum wage and the potential impacts on the current labour supply market for LCPS. The analysis should also highlight risks and mitigating factors in the context of longer-term PEF thinking.

PEF’s longer term strategy is linked, in part, to considerations on Access to Finance (A2F). The A2F component has been on hold since PESP II implementation began mainly due to reasons of sequencing and ensuring that TAMO prioritize more urgent work streams before going into more innovative components. TAMO has undertaken an analysis to review the potential of A2F and reflect on the best way forward. TAMO’s analysis asks: (1) how feasible is the recommended approach to providing financing for low fee private schools; and (2) how critical an enabler is A2F in achieving PESP II’s objectives of enhancing access and improving quality. The analysis questions the appropriateness of the A2F model and suggests an alternative way forward for promoting quality in LCPS. The analysis presents a strong case as to why A2F may not be the best use of resources if the principal objectives are access and quality.
Recommendation (short term): DFID needs to clarify the main purpose of the A2F component from two principal aims: (1) getting more children into school and learning; or (2) building and developing a sustainable market for private sector financing for LCPS. If (2) a case can be made to proceed. If (1) the annual review team recommends investing the funds in areas more likely to provide direct impact on access and quality. Given the overall purpose of PESP II and the number of existing components within the programme, a strong case for A2F would need to be presented to justify its finance. A fuller discussion of the arguments under the respective principal aims is provided in Annex 2.

Output 4 has a strong equity dimension, both in terms of ensuring the most marginalised can access education (e.g. through EVS and NSP) and that students with special educational needs access quality education through the Punjab Inclusive Education Programme (PIEP). PEF reported collaboration with the special needs department and an ability to cater for students with basic and moderate special educational needs but close monitoring will be required to ensure the most marginalised students are not being put at risk given the more restricted financing in PEF schools. There is also a need to ensure greater clarity around the exact processes associated with identifying recipients and redeeming vouchers for EVS schools (likely to be serving the most marginalised communities). Does PEF have the capacity to reach and provide quality services for the most marginalised?

The PC-1 for the Punjab Inclusive Education Programme (PIEP) has recently been approved and funds are with the Finance Department awaiting request from the Special Education Department for disbursement. With objectives covering teacher training, infrastructure and assistive devices, the PIEP sets out an ambitious pilot programme for inclusive education in two districts: Bahawalpur and Muzaffargarh. The PC-1 sets out the expected reach and unit costs associated with the pilot (R22,133 per direct beneficiary). From the PC-1, it is unclear who will be developing the inclusive education modules for teacher training and the expected role of the private sector. The PC-1 does not refer to any kind of impact assessment or evaluation to determine the effectiveness of the pilot. This will be important to inform future decisions on scale-up. The PC-1 refers to a two year timeline (2014-2016) which may be ambitious.

Output Title	Enhanced demand for education
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
5.1 No of secondary school girls' stipends in 16 target districts	411,000	Achieved: 436,527
5.2 No of (i) tertiary level scholarships for poor and able student (boys:girls) (ii) higher secondary scholarships for poor and able girls per year.	(i) 400 ii) 6500	Achieved (against both the original targets and queried logframe targets) / i) 325 new scholarships in 2014 vs the agreed target of 260 / (846 scholarships in total) / ii) 8,500 new scholarships (vs the agreed target of 7,000).
5.3 Number of households directly reached with behaviour change messages under social mobilization campaign in priority districts	Initial approach to social mobilization and community engagement / CSO participation developed	Work not started as at November 2014.
5.4 Number of people reached under communication plan, disaggregated by type of audience (e.g. teachers, parents, government officials, politicians and civil society)	Initial communication strategy articulated, communication specialist mobilized and embedded with SED	Not achieved.

Key points
The purpose of this strand is to stimulate demand, increase access to equitable education and support individuals to progress through the system up to higher education level. Direct accountable grants PEEF and LUMS directly contribute to this output as well as the priority districts component managed by TAMO and girls’ stipends funded through SBS.

Summary of progress
Girls’ stipends supported through SBS. The World Bank mid-term review identified these stipends as an important mechanism to improve gender parity in access. An impact assessment has been carried out to measure the effects of stipends of different values e.g. to incentivise access in harder to reach areas or for more marginalised groups. Results were not available at the time of the review. The outstanding steps are: (1) for PMIU to complete the awareness campaign for stipends for the academic year 2014/15; and (2) for follow up surveys to be conducted.

Scholarships: DFID has a separate Accountable Grant with the Lahore University of Management Sciences (LUMS) and exchange of letter arrangement with Punjab Education Endowment Fund (PEEF) to support poorer students to further their education.

PEEF: PEEF allocated a total of 9,060 scholarships with DFID support in 2013-14 of which 8,830 were for girls at matriculation level and the remainder for tertiary study at selected centres of excellence. PEEF was able to award more scholarships than projected due to lower than expected costs and is on-track to meet scholarship targets in 2014-15. PEEF uses public school enrolments and examination marks as a quick means to identify deserving students drawing on the assumption that students attending public school are generally from low income families. PEEF has responded positively to recommendations from the DFID programme team for improvements to its operations. This includes the adoption of an improved database and the pilot of an electronic grant disbursement system which was subsequently adopted for all PEEF operations. The CEO reported that they were open to further suggestions for improvement. DFID’s grant support remains the main external source of funding to the Fund.

LUMS: DFID is currently funding 68%[7] of students on the LUMS ‘National Outreach Programme (NOP) and NOP like (financial assistance) scholarships programme. 24% of scholarships were awarded to female students. This figure is in line with the overall LUMS student population, but there should be continued effort to improve female participation in the scheme. Currently DFID funds scholarships where other funding sources are not already established. In the longer term it is worth investigating whether the share of the scheme funded by other organisations could be increased with a view to ensuring sustainability. Possible funders such as LUMS alumni and local business leaders could be more sustainable sources of revenue for the scheme.
[7] Data taken from Quarterly Progress Report Sept – Nov 2014.

DFID funding has also been used to set up the administrative mechanisms within LUMS to manage the scheme. As the scheme expands, it is important that LUMS systems are sophisticated enough to track students and pull out analytical information as required.

Using the LUMS eligibility criteria, efforts are being made to recruit from across Pakistan to the scheme. LUMS also provides support to students from non-traditional backgrounds to prepare for the application process. An ambassadors’ programme has been established to attempt to use existing scholars to provide outreach to their communities. This has had only partial success due to poor timing with school and college holidays and the limited brief provided to students.
- Recommendation (short-term): DFID to ensure both LUMS and PEEF have clear plans in place for outreach activities to be initiated in the coming months. In particular, LUMS should strengthen its ambassador scheme, learning from good examples internationally. One suggestion is to look at models where students conduct outreach activities as a form of paid work experience following their final exams. Links to Alif Ailaan, a DFID-funded education advocacy programme, are also recommended to complement the outreach and publicity work conducted at local level.
- Recommendation (short-term): TAMO should work with LUMS to establish more robust management information systems to enable better reporting and tracking of students, alumni and scholarships. The DFID team should also investigate the trends in the number and costs of LUMS scholars, the proportion of the scheme DFID funds and the administration costs to ensure that confidence in the targeting and value of the scheme remains.

CSO strand: The civil society work in priority districts has been delayed due to questions over the sequencing of the component in relation to other elements of the reform programme, the delivery approach and questions over the capacity of civil society in priority districts to deliver. DFID and TAMO have agreed that this should remain a priority. A schedule of planned activity has been put in place to progress this over the next year, beginning with the recruitment of a social development adviser.

This appears to be the correct approach, as there will need to be significant upfront effort to identify and develop civil society before tangible education results can be delivered. Further delays could risk the ability of this component to deliver within the lifetime of the programme. There are also opportunities for links to other parts of the DFID portfolio, for example, the Alif Ailaan media and advocacy campaign.

Summary of responses to issues raised in previous annual reviews (where relevant)
The logframe target has been revised to include communications and behaviour change messages.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (See Annex 3 for further analysis)

VFM Summary
This is the second review, and whilst it is too early to say much about the effectiveness of components, the programme is overall assessed to be on track and has already supported a number of sizeable reforms and processes in the sector that have the potential to deliver value for money. These include rationalisation of teacher posts to improve student-teacher ratios, better and digitised data collection and strong use of data to manage performance in the sector, as well as development of a set of educational goals that put quality and learning at the centre of reform. Key cost drivers remain largely in line with original planning. Overall risk is assessed as moderate, but given the size and complexity of the programme, active management of risk is critical to ensure the programme’s transformative potential. In the last year, participation rates in both primary and secondary schools have all increased by over 1% point. The annual cost per child in public primary school continues at close to £80 per year and it costs around £40 a year to put a child in a PEF school. Learning levels are however low and reflect a major inefficiency in the system. The programme is responding to this challenge by supporting a much greater focus across the education sector on quality. Improvements may take time to show but are now being monitored and will be an important aspect for assessing whether the programme is delivering VFM in subsequent years.

Key cost drivers and performance
Sector Budget Support (SBS), the additional budget support provided to PEF, and the infrastructure component represent the largest areas of planned DFID spend under the PESP II programme, comprising 78% of the overall budget. This section summarises the main cost drivers. A detailed assessment of cost drivers for each of the programme components is provided in Annex 3.

Sector budget support
Teacher salaries remains the largest spend item in the education budget and saw a real increase of more than 2% in the 2014-15 budget allocations. Teachers’ salaries are a political issue making the programme susceptible to political drivers not necessarily linked to improving education outcomes. Non-salary allocations as a share of the budget did not increase. Continued monitoring of execution of the non-salary budget is important to ensure this spend is protected.

PEF and scholarships
The main cost drivers in PEF and under the scholarships programmes are the per-student grants or vouchers. The primary cost drivers are the schools fees, which in turn are driven by underlying salary and other operating costs. These costs determine the numbers of students that can be enrolled under any of the schemes. PEEF and LUMS scholarships also include stipends to cover living costs. PEF per-student rates have not changed in the last two years but are expected to increase going forward to reflect rising market rates. These rates have been reflected in PEF’s expansion plans and are not expected to affect numbers of children enrolled. PEEF grants have continued in line with the original budget. The average cost per LUMS student is lower than anticipated but is driven in part by the numbers of students receiving partial, rather than full support. The proportion of students receiving partial support scholarships has flagged a question about whether LUMS is attracting the most financially constrained students to the scheme.

TACE
The main anticipated cost driver for the infrastructure component is the price of materials, which is estimated by IMC to constitute 70% of total costs. Anticipated labour costs are relatively low. Budgets and work plans have been developed on the basis of a survey identifying school needs. There is a risk that further delays to the start of the implementation phase will lead to cost revisions if infrastructure needs begin to be addressed by government or others and further surveying is required.

Technical assistance
The primary cost drivers of the technical assistance are consultancy fees and travel which are normal and expected cost drivers for work of this nature. A rough benchmarking exercise across TA contracts within the DFID Pakistan office shows that rates are relatively high while the overall team size is relatively lean. A lean but high-quality technical team was a conscious decision during procurement, but will need to be monitored closely to ensure the resourcing mix does not in any way delay programme delivery.

VfM performance compared to the original VfM proposition in the business case
The business case assessed VFM chiefly through a cost-benefit analysis. The appraisal estimated an overall benefit-cost ratio for the programme of 1.5 and anticipated an additional almost 3 million enrolments over 6 years.

Data available for this review were insufficient to re-run the full analysis with updated costs, benefits and time adjustments. Nevertheless, a review of the original assumptions underpinning certain components in the appraisal suggests delays in implementation of components will have had some, albeit not substantial, bearing on the balance of costs and benefits in the original analysis. As the programme continues to evolve, the original programme assessment needs revisiting to conside the implications of changes for overall VFM as it may improve or worsen.

Assessment of whether the programme continues to represent value for money

A detailed assessment of VFM of the PESP II components is found in Annex 3.

Sector budget support, influence and technical assistance
DFID, facilitated by the Roadmap process and good political engagement, enjoys strong and regular dialogue with the Government on the design and implementation of reforms. This level of access is impressive for a budget support programme that constituted under 4% of the total GoPb education budget last year and just over 1.5% the year before. The efforts and staff time dedicated to dialogue have helped to prioritise and drive the pace of several reforms including on issues such as restructuring of the Punjab Curriculum and Textbook Board, and teacher rationalization to address crowded and far flung school, as well as more recently the development of the 2018 goals. The programme has already supported a significant number of system reforms that are driving efficiencies in the system. This includes the province-wide process of teacher rationalisation, coupled with a process to recruit 30,000 teachers by end of June 2015 under more robust recruitment criteria to improve student-teacher ratios in schools. Investments in monitoring and the use of data to monitor service delivery have vastly improved and have played an important role in sustaining improved teacher attendance at 92%, and identifying district needs. A pilot to channel non-salary budget directly to schools based on school development plans has seen much improved school-level spend on basic resources in pilot districts.

The review stresses that ensuring effective and irreversible reform is critical for the sustainability and long-term impact of PESP II. The TA under the Roadmap process has been effective in helping build urgency and focus around the need for system reform. This is evidenced by the pervasiveness of the roadmap indicators at all levels of government and the continued buy-in by the Chief Minister to the process supported by the UK’s special representative on Education to Pakistan. Developing and securing agreement on the 2018 goals for the sector can in part be attributed to the TA. With an increased focus on the long-term institutional environment, steps are now being taken with TAMO to think through what this means for capacity building efforts and planned work at the district level to embed reforms.

Importantly, large increases in the Government’s budget allocations for education in 2014-15 suggests sector budget support remains additional from a funding perspective. Compared with 2013-14 spend, the 2014-15 budget saw a 14% increase for current budget and a 67% increase for the development budget. Net of DFID’s SBS, these still represent an estimated 16% real increase year on year. Whilst it is impossible to know for sure what would have happened in the absence of SBS, these figures suggest SBS has not discouraged increases in government allocations to the sector and has remained additional. Education represents approximately 24% of total GoPb allocations for 2014-15. The share is estimated to have fallen marginally from 2013-14, suggesting that whilst education remains a priority, it continues to compete hard for resources. Budget execution provides further evidence of efficiency of spend. By the end of 2013-14, the Government successfully executed a large share of its budget, including 74% of its non-salary budget and 88% of its development budget, up from 38% in 2012-13. Budget execution for the first quarter of 2014-15 is showing similar trends to 2013-14. Maintaining these allocations in subsequent years of the programme and ensuring good and targeted execution will be important for sustaining reform.

In terms of unit costs, it cost the GoPb approximately £80 per child in primary and £120 per child in secondary in 2013-14. Spend per child at primary increased less than inflation since 2012-13 whilst spend per child at secondary level saw a real increase. These costs are low by international standards, but are comparable with spend in Khyber Pakhtunkhwa province and substantially higher than spend per child in PEF schools.

Meanwhile, the low numbers of children able to read at the right level is a signal that whilst input costs are relatively economical, the education system is not delivering the outcomes needed to demonstrate value from the perspective of learning. The recent DFID-funded sample-based assessment found that only 50% of Grade 3 children were able to read a basic 4-line passage in Urdu and answer 3 basic questions. Results were 23% in English (Grade 2 level). Comparable data is not currently available to assess how the difference in spend across private sector and across provinces is reflected in the quality of education. Learning however needs to improve to increase the effectiveness of government spend on education. The DFID team’s push on quality and the recent commitment by the Chief Minister to allocate additional resources for quality improvements are vital steps that hope to improve VFM.

PEF
PEF’s per-student fees continue to broadly match those estimated in the business case and at approximately £40 per child, offer good value for money on inputs, particularly in light of inflation. An initial view on the VFM of PEF outputs will be possible once a comparable and robust assessment of learning outcomes is undertaken in the coming months. PEF has seen increases in enrolment across its three funding schemes, with a particular expansion in children in FAS schools. There continues to be a question of whether VFM of the FAS model could be improved through better targeting of children and efforts should continue to encourage PEF to explore revisions to its model. The question of whether teacher salaries should be improved remains unresolved. The potential benefits of increasing salaries for productive efficiency needs to be weighed against the potential impacts on school fees and the labour supply market, particularly for female teachers. The review has recommended a deeper analysis of the market.

Scholarships
Under the scholarships component to date, an additional 8,500 girls from poor families have received scholarships to complete higher secondary education at an average unit cost of £99 per student. In addition, 846 scholarships have been awarded to poor students to study at LUMS and other tertiary institutions. Average unit costs per student at the tertiary level are substantially higher and vary depending on the institution, ranging from an average of £660 across PEEF tertiary scholarships to over £3500 for a new full support undergraduate scholarship at LUMS. Whilst higher than per sudent costs at lower levels of education, the potential rewards for those students completing are significantly higher. It will be important to track alumni of the programme in the coming years to assess the actual value of the scholarships programme to the scholars. Outreach activities also have the potential to build on the private returns to individual scholars by demonstrating and sharing the value of an education to a wider group. The review has recommended that DFID works with LUMS in particular to ensure its ambassador programme is taken forward.

Suggested Improvements to VFM Monitoring
Whilst the education system is itself generating a lot of useful data, there is a lack of discrete and identified VFM measures in the original business case by which to monitor VFM of the programme over time and across initiatives. As part of the headline recommendation to improve management of data, it is recommended that DFID take forward its initial work with TAMO to develop some useful VFM metrics to assess over time.

Quality of financial management

Timing of disbursement of different PESP II interventions
As demonstrated in the analysis in Annex 3, the SBS elements of PESP II were mobilised quickly relative to other components, in particular the technical assistance and infrastructure components which have had longer mobilisation periods due to the need for thorough procurement and inception phases.

The impact of this different timing is that the potential for the TA to support the early work through SBS has been missed. While the rationale for mobilising SBS as soon as possible is based on supporting the momentum of the GoPb reform programme, it is worth trying in future phases to more closely align the start of TA support with disbursement of significant SBS, even if this means slowing slightly the disbursement rate of SBS.

Complexity and financial risk
PESP II is a large scale, highly complex programme operating several funding mechanisms including budget support, direct contracting and providing direct and indirect grant funding. This complexity contributes to the acknowledged high risk rating of the programme overall. It is critical that DFID continues to maintain a deep understanding of how money flows through the various systems. Fund flow processes from the Finance Ministry to the Government implementing agencies are well-understood and documented.

Within the different funding mechanisms there are a range of interventions of varying degrees of financial risk and at varying levels of success in mitigating these risks. One particularly successful story appears to be the Accountable Grant to PEEF to disburse secondary school scholarships to poor students. In this case DFID encouraged the implementation of an electronic disbursement and tracking mechanism for DFID-funded student scholarships that appears to have reduced the potential for fraud within the system. The initiative has been so successful that PEEF has now rolled it out across all the scholarships it disburses. Other interventions such as the PEF Education Voucher Scheme appear to have had less success in implementing electronic disbursement mechanisms and instead disbursed their vouchers in a way that places significant control in the hands of individuals such as Head Teachers. There may be valuable lessons to share between these different interventions.

The DFID team are using audit processes such as Government and independent audits as well as the DFID Pakistan Risk Assurance Programme (PRAP) to identify areas of higher financial risk within the programme. Government audits are received annually however there is a reporting time lag of 9 months after completion of the Government’s fiscal year. To date only one Government audit has been received (Feb 2014) within the lifetime of PESP II. DFID has also used the PRAP programme early in the life of PESP II (2013) to conduct baseline reviews (systems audits), action plans and annual follow up to identify and mitigate areas of higher risk at various delivery levels. The combination of systems audits, follow up and annual Government/independent auditing appears to provide a good level of information to understand financial risk in the programme.

Sufficient follow-up of audit recommendations is critical and presents a significant resourcing challenge. The DFID team are already involving the TAMO team in supporting implementing agencies to deliver improvements identified by audits. This practice is planned to be formalised clearly in the costed workplan and TAMO is encouraged to play an increased role in monitoring the completion of audit action plans and safeguarding funds. The DFID programme team should incorporate follow up to audit recommendations clearly in the PESP II delivery plan to ensure actions are trackable.

Public Financial Management
Several of the Government implementing agencies raised concern over: (a) the timing of the SBS tranche from DFID; and (b) onward disbursement from the Ministry of Finance. DFID receives expenditure data for GoPb’s education budget on a quarterly basis. This provides a significant amount of information which needs to be interrogated and interpreted sufficiently by the DFID team.

During discussions with the Finance and Education Departments and implementing agencies the potential need for capacity building in financial management, in particular within line Ministries, was raised. A complementary DFID programme, the Sub-National Governance Programme (SNG), is providing support to the GoPb to build capacity in public financial management. While this programme is supporting the overarching framework for improvements in public financial management in Punjab, there is a clear and recognised need for TAMO support to both implementing agencies and, working with SNG at the Finance Department, to improve overall financial management and timely access to resources for education.

Date of last narrative financial report	Government expenditure report covering full year FY 13-14 covering period up to June 2014 plus Q1 FY 14-15 (up to Sept 2014) have been received / Various other financial reporting arrangements for other components.
Date of last audited annual statement	Auditor General report in Feb 2014

E: RISK

Overall risk rating: Low/Medium/High
Medium

Overview of programme risk
The annual review team reviewed the programme risks set out in the business case and have updated them. Two new risks (complexity and coordination; and delivery) have been added in the risk matrix. The overall assessment of risk is unchanged i.e. medium. Specific recommendations are made regarding the risk matrix, noting the lack of progress on some of the risk mitigation strategies given in the business case and recommended in the last annual review. Fuller detail is given in the Risk Matrix which also forms part of the PESP II delivery plan.
Complexity and coordination
This is a new risk identified by the review team as more components have come on stream and is rated as high. PESP II is a highly complex and challenging programme. The complexity of the design in itself presents risks to the ongoing management of the programme. The level of complexity makes it difficult to engage with and understand progress against the different elements of the programme while multiple stakeholders and limited coordination means the accountability chain for the programme (outside DFID) is unclear. The DFID team has a critical role to play in terms of managing multiple components and stakeholders. There is also further scope for TAMO to support DFID in coordinating across stakeholders.

On the government side, there are a number of coordination mechanisms to connect policy making at the provincial level with its implementation in the districts through DCOs, EDOs, DEOs, MEAs, DTSEs as well as TAMO divisional coordinators. Coordination across various provincial policy- making bodies including with TAMO/Roadmap however, seems weaker. PMIU have acted as a coordination platform for some of the earlier reforms linked to sector budget support but they have felt less engaged in the Roadmap process and wider PESP II reform programme. There is a risk that in the absence of an institutionalised coordination mechanism that can bring all components of the programme together, various reform initiatives would remain disjointed. The review has recommended that DFID explore with the School Education Department the potential for a coordination mechanism between different government agencies as well as with TAMO/Roadmap teams such as a PESP II Steering Committee.

Insufficient capacity to implement the programme at district and sub-district level
Success of PESP II depends to a large extent on the capacity of district and sub-district level officials to deliver. Capacity constraints at these levels are being addressed through various interventions but the risk can increase with the establishment of the district education authorities in the wake of local government elections. With pressure from the Supreme Court on provincial governments there is an increased likelihood that the local government elections will be held sooner than anticipated. There is a greater risk that the newly-established district education authorities may lead to increased system complexity and increased political interference, corruption and mismanagement at the district level. DFID should work through the TA team to ensure that institutional capacity building is undertaken in all entities and levels within the education system of Punjab to mitigate the impacts of changes in the system.

Fiduciary and corruption risks
There was no change to this risk. New mitigation strategies have been added that include more coordination with SNG, strengthening the validation mechanism and audit of PEF vouchers and the use of external and third party audit of DFID supported activities in PEF. The DFID programme team should focus effort on understanding disbursement mechanisms within this system.

Conditions in low-cost private schools pose a reputational risk to DFID
The reputational risk posed to DFID by low cost private schools was assessed as high probability (unchanged) and high impact (changed from moderate) given the sensitivities around the question of the minimum wage. Last year’s annual review recommended reaching an agreement on a minimum wage for teachers in schools supported by PEF as a priority but no progress has been made so far. A recommendation is made in this review to undertake analysis necessary to determine a way forward.

Delivery risk
The ASI and McKinsey partnership is still bedding down and a costed workplan has yet to be agreed. TAMO need to consider balancing a relatively heavy senior management structure with more technical resource to deliver the work streams. Additionally TAMO should clarify the roles and accountability chain within their senior management structure to DFID with a view to streamlining decision making processes and costs.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The business case set out the anticipated spending profile for PESP II shown in Fig 3. These figures include the TA element split across the different components rather than profiled separately. Figure 4 shows actual spend to date versus anticipated spend by 14/15 by component (NB the TA component cannot be compared directly as in Fig. 3 the anticipated spend on TA was spread across the components rather than profiled separately).

Activity	Year 1	Year 2	Year 3	Year 4	Year 5	Year 6	Total
SBS to GoPb	20	17	17	16	15	15	100
Financial aid for PEF	7	11	12	13	15	10.6	68.6
Pilot access to finance component	0	4.5	0	4.5	0	0	9
Infrastructure component	10	26	31	37	0	0	104
Civil society component in LPDs	2	3.1	3	2.7	0	0	10.8
Scholarship component	2	3.2	3.6	4.2	4.2	1	18.2
Sub Total	36	53.8	60.6	70.4	54.2	35.6	310.6
Technical Assistance	6	7	7.2	7.5	6	6	39.7
Total	42	60.8	67.8	77.9	60.2	41.6	350.3

Cost and annual profile for PESP II (£ million) (from business case)

Fig.4 PESP2 Expected and Actual Spend by Component (Dec 14)
PESP2 Components
Spend (£m)

Comparing the spend rates by work stream, the SBS component is spending in line with the anticipated timelines in the business case. Other components however have been slower to get underway.

There are various reasons for this slower disbursement depending on the component. Firstly, the two major contracts under this programme – the infrastructure and TA contracts have both been through competitive OJEU tender processes followed by inception phases. These processes take time and both contracts are only now set up and starting to deliver. The total time required for procurement most likely was not sufficiently factored into original business case timelines and also because IMC required a regiseration with the Board of Investment which has been a very protracted process preventing the organization to begin their construction work. It is too early to comment on the pace and quality of delivery of the TAMO and TACE components now that the contracts are in place – this will need to be assessed at the next review point.

Performance of partnership(s)

How well are formal partnerships working?

Complexity:
PESP II is an ambitious and incredibly complex programme which is engaging across the entire education reform sector in Punjab.

The potential transformative impact of a programme of this scale, working through and with so many different elements of the Punjab education sector is significant. However, this degree of complexity does make the variety of partnerships difficult to manage well. It should be recognised that the biggest risk to delivery of this programme is potentially its own complexity. This has been explicitly captured in the risk register as part of the review.

Co-ordination and management is a significant role that DFID is delivering in-house. The level of activity in the programme makes it difficult to track, understand and manage all aspects of the work. There is a significant amount of information/data handling and activity follow up that is critical to managing this programme well. DFID resourcing appears to be functioning although certainly not over resourced[8]. The new delivery plan approach should present opportunities to streamline and focus on key priorities such as M&E, safeguarding against fraud and steering programme interventions.
[8] The DFID PESP II team includes: 100% A2(L) PM overseeing the whole programme; 50% B1 PM focussed on infrastructure; 100% B2 PM focussed on TA and Scholarships; 100% C1 administrative support all based in Islamabad; 100% A2 Education Adviser based in Lahore; 45% A2 Governance Adviser based in Lahore; 20% Social Development Adviser based in Islamabad; 15% A2 Infrastructure Adviser; some support from an A2 Economist plus a share of the A1 Head of Education Policy and A1 Head of Education Programmes.

Recommendation (short-term): DFID and TAMO continue to clarify through the work planning process and monthly meetings the role and performance of TAMO in overseeing programme delivery. This will allow for better coordination and management specially in the early phase of the programme.

Coordination and Results Frameworks

There are currently a number of different organisations playing a coordinating role in education reform in Punjab, each with slightly different results frameworks and slightly different perspectives on the programme.

The Roadmap team support the high level political steering of Punjab education reform and have supported the development of the 2018 goals for sector reform. The TAMO team are supporting the Education Secretary’s team to respond to the Roadmap. The PMIU tracks progress against some reforms and coordinates the World Bank/DFID DLIs. They have been less involved in overseeing DFID’s additional DLIs or the additional components of the DFID PESP II business case. Finally there is the DFID role in coordinating across PESP II as described in the business case which includes a logframe that is broader than the SBS components.

This is a complex picture. For future phases, DFID, the World Bank and the GoPb should work towards rationalising the number of results frameworks. A recommendation for consolidating accountability and reporting mechanisms is therefore made in the summary.

Furthermore, one single coordinating body within Government of Punjab to steer the reform agenda would be preferable. This function could sit within PMIU or within the office of the Education Secretary but the programme would benefit from a clear decision on where it lies and then provide dedicated support through the TAMO contract to build its capacity to function.

The PESP II programme is much broader than the SBS elements and includes a number of activities that are critical to Punjab education reform and that are of significant interest to the Education Secretary, e.g. the infrastructure and TA components. There is currently no forum for discussing PESP II with Government partners in the way it is described in the business case. Various Government partners also raised concerns that, while the Roadmap process is positively driving the education reform agenda, the relationship between the Roadmap and implementation could be improved. A few examples were provided where Roadmap initiatives conflicted with existing delivery initiatives. As recommended in the summary, DFID should explore possible solutions, such as the potential to set up a PESP II Steering Committee, jointly chaired by the Education Secretary, DFID and World Bank. This would allow for better coordination across the different business case components, could improve the relationship between the Roadmap and the delivery agencies and could help to identify and agree critical areas for TAMO support.

Contract Management

SBS is managed through a set of DLIs. This is a Payment by Results model with Government. In addition there is one accountable grant and an exchange of letter arrangement to provide scholarships under PESP II. There is good evidence of a positive relationship between DFID and the scholarship organisations who appear to be broadly delivering as agreed under the grant arrangement.

There are four main contracts under PESP II – TAMO, Roadmap, Infrastructure and an evaluation contract. The TA contract (TAMO) is expected to work very closely with the Roadmap team although externally they need to present slightly different faces in order to play the slightly different roles of both challenging and supporting delivery by the GoPb . It is however managerially cumbersome that these are two separate contracts.

The number of staff within the TAMO team is leaner than other similar TA contracts managed by DFID Pakistan. However, a lean but high-quality technical team was a conscious decision taken by DFID during procurement. The ASI and McKinsey partnership is still bedding down and a costed workplan has yet to be agreed. The TAMO team themselves referred to a desire to avoid overstretch in their work planning while the DFID team has noted some delays in delivery. The balance of senior level management inputs at Director level on the programme is also comparatively high. The TAMO contract is milestone based which means the supplier has signed up to delivering this programme for set milestone based costs. DFID should be clear what the issues are regarding a slower pace of delivery than anticipated and request TAMO to propose solutions. The diffused senior management structure on TAMO is confusing and unless clearly specified could reduce the opportunity for individual responsibility and accountability and potentially present poor VFM.

The TAMO team are clearly very knowledgeable across the PESP II activities and have good access to all the key delivery partners. This could be maximised by clarifying a broader role for TAMO as the interface between DFID and the programme. TAMO has not yet engaged on the DLIs (WB nor DFID) however there is a potential role here in understanding progress against them and how that relates to the wider reform agenda. This is broadly in line with the original TORs and is a role that TAMO say they are increasingly playing.

It is critical in the way TAMO work that they develop the capacity and capability within GoPb to manage future education sector reform without TA support. TAMO need to consider now how they will ensure their legacy is sustainable and set plans in place to deliver in this way. TAMO need to ensure they are supporting Government of Punjab to coordinate its own reform rather than delivering that directly.

TAMO and DFID are currently agreeing a set of payment milestones for the first year of the programme. The agreement on the costed workplan and budget for year 1 is considerably delayed whereas both parties are keen to use this contracting style. A milestone-based payment model for a complex and dynamic, transformational change programme can be difficult to manage. Both parties need to be ready to be flexible and ensure that they build a strong partnership based on trust and a mutual desire to improve education in Punjab to enable issues to be worked through pragmatically as they arise. Thinking through up front how milestones can be verified and ensuring open and honest dialogue when objectives aren’t met is critical.

The infrastructure (TACE) contract has been operating for a shorter time than TAMO due to only recently completing the tender process. It is too early to comment on the performance of this contract.

Asset monitoring and control

Asset registers are held for the TAMO and TACE contracts and for the scholarships programmes. The DFID team plan to conduct annual spot checks of assets against these in the coming year. DFID is not creating assets under the SBS component as all assets are owned by Government of Punjab.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The majority of the UK’s investment in PESP II is in financial aid and technical assistance to GoPb. The political will to reform combined with ownership from SED and improved capacity of various departments like PEC, PCA, DSD etc. has significantly improved progress. Also there has been strong commitment on the part of the Finance Department, as evidenced by its work with the SNG programme.

The published business case states that funding is based on the Government of Pakistan’s commitment to poverty reduction, protection of human rights and strengthening PFM and accountability, as set out in the UK’s Development Partnership Arrangement (DPA) with Pakistan.

We assess that steady progress is being made against the four Partnership Principles which have superseded the DPA. Entrenched poverty denies opportunities to millions of people and undermines stability and prosperity. The recent Partnership Principles Assessment update considers that good progress was being made to progress human rights legislation. The 2014 Operational Plan refresh states that social and economic rights are on a positive trajectory with improving school enrolment rates and reducing maternal and child mortality, but inequality persists and serious concerns remain, particularly with regards to the rights of women and girls. There are currently no concerns that threaten the continued provision of sector budget support. If, however, there are significant changes, these would be discussed with the provincial government and also with Economic Affairs Department at federal level.

With support from the PESP II technical assistance team, GoPb is working on a medium term budgetary framework (MTBF) and formal budget execution reporting . PESP is working closely with SNG in the conduct of pay roll audit for education employees (approximately 30% of the Punjab civil service). DFID’s work on the Public Expenditure Review has also led to a focus within the overall budgeting process on primary education as well as on non-salary and development budget expenditure.

H: MONITORING & EVALUATION

Evidence and evaluation

The contract for the formal evaluation (covering both Punjab and KP education programmes) was awarded in early 2013 to OPM. The inception phase was due to end at the end of December 2014, but it is currently behind schedule. This may be due to OPM overstretching themselves including managing other DFID Pakistan evaluations (EFS, BISP & CDCP).

Another reason for the delay is that some of the sub-evaluations set out in the ToRs are either no longer appropriate or feasible (e.g. impact of increasing stipends). The inception workshop held in Islamabad in September/October between OPM and DFID failed to conclude the key issues the evaluation should address.

Whilst these issues are resolved, it is likely the inception period will be extended until March 2015.

Conflicting evidence exists on whether the A2F component should proceed. The review team looked at a range of evidence and discussed this with microfinance lenders. The analysis in Annex 2 underpins the recommendation in output 2 on whether this component should go ahead.

Monitoring progress throughout the review period

A broad range of monitoring information and evidence is regularly reported on across this project. Different reporting mechanisms exist for different aspects, sometimes by component and sub-component but also by stakeholder (e.g. LUMS and PEEF report separately each quarter). A variety of monthly and quarterly reports are received from stakeholders (e.g. PEF) and many meetings take place to discuss progress (e.g. monthly monitoring meetings with TAMO). More formally the monthly Roadmap provides a high level forum to discuss a range of key education indicators (such as student attendance and missing facilities) with the Secretary and Sir Michael Barber.

The Annual Review process has highlighted the challenges associated with managing large quantities of project level and contextual level data within such a large programme. Understanding and ownership of the data and trends must improve. Bringing the reporting data together in one place could help facilitate this.

Assessing progress against the logframe milestones was challenging due to difficulties obtaining access to the correct information. In some cases, stakeholders provided conflicting data making it difficult (or impossible) and time consuming to assess progress. Confusion existed around how the milestones were established (and by whom) and how the indicators were defined. In some cases, milestones were inconsistent with stakeholder milestones (e.g. PEF) or what DFID previously agreed (e.g. LUMS & PEF). In other cases it appeared there was no consensus (between DFID & TAMO) on what meeting the milestone should entail.

More broadly, the existence of ten original DLIs plus five additional DLIs as well as the logframe milestones, Roadmap targets and new 2018 targets further complicates what is an already complex programme and caused some confusion across stakeholders. For example, PMIU worked towards the original ten DLIs but seemed unfamiliar with the additional five DLIs (or who was delivering against these) and had no awareness of DFID’s Logframe.
Recommendation (short-medium term): It is recommended that monitoring processes are streamlined and key information is consolidated into one Monitoring & Evaluation framework that is updated regularly. It is imperative that this evidence base is owned, managed and used effectively across the programme – with the framework serving as a robust picture of progress.
As recommended in the summary, the logframe should be reviewed as soon as possible and consensus reached on the indicators and milestones to ensure that all stakeholders are working towards agreed goals. Progress against the logframe should be built into routine meetings throughout the year.

Beneficiary feedback: The review team was accompanied by an EDO to two relatively high-performing public schools in Lahore during the review, a boys’ school and a girls’ school, and spoke to head teachers, teachers and pupils. The team observed lessons in progress and a pre-deployment training for newly-recruited teachers. Teachers reported favourably on the training and mentoring that they have been receiving. One head teacher confirmed that the school was receiving regular visits from monitors but was concerned about the amount of time and pressure this was placing on the school. Both schools reported limited availability of funds for basic equipment and operational expenses. Pupils engaged with questions from the team but were not forthcoming with suggestions on how they might improve their schools.
Recommendation (medium term): The future review process can be further strengthened by allowing more time in Punjab and creating time for conversations at district level and below (e.g. with Education District Officers and Assistant Education Officers). This is essential to make a judgement on how the programme is performing, so the discussions and field visits must get beyond departmental heads.

Annex 1: Disbursement Linked Indicators

DLI 1	Field-based professional development: Strengthening field-based teaching advisory support for improved teacher performance.
DLI 2	Teacher recruitment: Improving teacher quality at entry
DLI 3	Teacher rationalization: Allocating teaching posts and teachers across schools based on school needs
DLI 4	School non-salary budgets: Setting and executing school budgets in line with school resourcing needs.
DLI 5	Decentralized resource management: Decentralizing resource management powers to schools/school clusters
DLI 6	Teacher performance incentives: Incentivizing teacher and student performance by strengthening the link between monetary rewards and student achievement .
DLI 7	Schools councils: Strengthening the capacity of and empowering communities to support, monitor, and promote school performance.
DLI 8	Provision and use of system and school performance information: Regularly feeding relevant and reliable information to various levels to improve evidence-based school performance management.
DLI 9	Private school vouchers: Strengthening program design and expanding coverage of tuition-replacement vouchers to children from disadvantaged, urban households by increasing school choice to include private schools under a quality-assurance system.
DLI 10	Stipends for secondary school girls Increasing incentives, efficiency, and delivery performance for promoting the transition to and retention of girls at the secondary level.
Additional DLI 1	Recruit 30,000 more teachers and 20,000 teachers to be moved to more crowded schools through the rationalisation process in FY 2014/15
Additional DLI 2	More credible school-based exams and introduction of additional mid-year school-based exam for poor-performing children
Additional DLI 3	Improve the examination and assessment system
Additional DLI 4	Improve development expenditure on education
Additional DLI 5	Support a Special Education component for inclusive schools

Annex 2 – Consideration of Access to Finance (A2F) component

The Terms of Reference for the review included a review of programme progress to develop the PESP II Access to Finance component, and tasked the team with making a recommendation about whether to proceed.

Following approval of PESP II, DFID funded a study to further assess the demand in the LCPS sector for finance[9]. The study found substantial demand for credit, largely for infrastructure investments on the back of which it developed a model for lending to LCPS which included a tool for determining maximum loan size and lending using cash-flow as collateral. The model has been piloted by two microfinance institutions[10].
[9] Access to Finance for Low Cost Private Schools, ILM Ideas, 2014
[10] First Microfinance Bank and Khushhali Foundation

TAMO’s own analysis found limited rationale for extending a credit guarantee model on the grounds that the instrument is poorly placed to drive improvements in PESP II’s overall outcomes (access, retention and learning) and estimated that the high default rate for start-up schools would limit scalability of efforts to incentivise new school expansion, offering poor value for money for a circa £10m outlay.

The PESP II business case envisaged A2F contributing to expanding LCPS in under-served areas in light of PEF’s capacity constraints. It considered access to finance a constraint for edupreneurs, in particular due to stringent collateral requirements and high interest rates, and proposed an instrument to underwrite loans so as to reduce the risk of lending to the sector.

The review found that the question of whether or how to proceed depends crucially on the primary purpose of A2F and considered two potential objectives:
1. Getting more children in school and learning (this could include a condition to use private sector channels);
2. Building and growing a sustainable private sector financing market for LCPS.

The first objective suggests DFID should be focussing on those interventions which contribute most both in the short term and long term to getting children in school and learning. The objective could be conditional on working through the private sector if this is viewed to offer better VFM given the overall balance in the PESP II programme. The second objective reflects a longer-term strategy to ensure sustainable private sector financing for the LCPS sector in Pakistan. It suggests an appetite for innovation to ensure the education sector is sufficiently resourced to deliver education services to an ever growing population.

This note summarises the review findings in the context of each objective drawing on previous analysis and discussions during the review[11]. Evidence was inconclusive to recommend a clear way forward, but suggests that the component would need moderate to substantial revision depending on the agreed objective. The DFID team will need to consider plans for further development of the component in light of an already complex programme, the appetite within PESP II to support further innovation with the private sector and the potential trade-offs from not pursing this component.
[11] The team met with TAMO, PEF and First Microfinance Bank and had email exchange with Khushhali Foundation.

Getting more children in school and learning

Under this objective, the role for A2F could be twofold:
1. to unlock private sector finance for new start-ups in underserved areas; and/or,
2. to develop private sector financing for investments in learning outcomes.

Given PESP II’s other activities targeting access, it is not clear if additional non-PEF schools in under-served areas will impact sufficiently on access to prioritise this approach. PESP II is already targeting access through several channels including expansion of PEF’s New School Programme and planned work with CSOs in priority districts to improve demand. TAMO’s analysis looked at constraints to access to locate the need for new non-PEF LCPS. The 2013 Neilson Survey of out-of-school children found that availability or proximity to schools was a constraint but not the primary constraint to access. PEF’s expansion plans already aim to support new schools in under-served areas. The team was unable to determine if current plans for PEF under the 2018 goals are sufficient to meet the need or if further measures in the private sector are likely to be needed.

Even if expansion of non-PEF LCPS is necessary to meet demand, more evidence is needed to determine if access to finance is indeed the binding constraint to LCPS expansion in under-served areas. There are a number of possible reasons why LCPS may not set up in some areas. Demand for private sector education might be low or limited ability to pay fees might deter entrepreneurs. There has been substantial growth in the sector in the last decades[12]. Start-up costs for new schools are reportedly low and typically funded by individuals’ own funds[13]. These are indications that access to finance may not be a binding constraint to start-up although it is unknown whether extending private sector financing for start-ups could stimulate further growth. TAMO’s analysis suggests high risks of default for start-ups would limit the reach of DFID’s funds if it were to support a market for new school financing. When asked, PEF did not consider that access to finance for capital investments in the sector is a major constraint to their expansion plans for existing or new schools.
[12] LCPS catered to an estimated 30% of children in 2012. Source: Access to Finance for Low Cost Private Schools, ILM Ideas, 2014.
[13] Access to Finance for Low Cost Private Schools, ILM Ideas, 2014

To invest in quality beyond infrastructure improvements, schools and financiers alike need to expect good returns. There is some evidence to suggest that edupreneurs do not prioritise investments in quality. A survey of LCPS found edupreneurs willing to invest their own savings in infrastructure but not in other types of quality improvements. Reasons for this include the important role that perceptions play in determining what LCPS invest in, with parents valuing infrastructure highly. The review was unable to determine if there is evidence of investments in quality leading to higher returns on investments but heard anecdotally that the market for education quality improvement services was limited and that schools are more reluctant to invest in areas where the pay-offs are less immediate. We were unable to determine whether banks would be willing to extend loans for quality improvements. Kashf Foundation is an exception that has trialled a few loans coupled with training on quality aspects and has plans for scale up. The MFI reported improvement in some physical measures of quality but the resulting impact on learning outcomes is unknown.

There are potential benefits to building the institutional infrastructure to establish quality standards in non-PEF LCPS. Non-PEF LCPS serve around one third of Punjab’s children, but there is little information currently available upon which to assess the quality of the education they provide. One area of consensus within the review was the need for a ‘game change’ on quality if LCPS are to be incentivised to invest heavily in learning outcomes. This includes improving both parents’ and LCPS’ understanding on what quality is and giving parents better information to compare performance across schools. A focus on improved learning outcomes is central to this. Altering perceptions on quality could change both demand for and improve returns on investments in quality.

The programme team should assess the potential, including the policy space, to support the establishment of an institution to standardise certain aspects of quality across non-PEF LCPS. There is a strong equity rationale for ensuring LCPS meet some minimum standards. Introducing any regulation however will need to be carefully designed to ensure opportunities for rent seeking are minimised and growth and innovation in the sector is not stifled. TAMO have proposed some initial options for improving parents’ and LCPS’ ability to assess quality, including improving visibility on student performance across schools and establishing an independent school certification body. The team should consider these options and their potential for transformative impact. This intervention by itself would not support access to finance for LCPS. To complement the introduction of quality standards and in the absence of a thriving market for loans for quality investments, the team might also want to still consider an A2F component for service providers or schools looking to invest in quality.

Building and growing a private sector financing market for LCPS

Under this objective, A2F could be used to grow a private financing market for LCPS by demonstrating its commercial viability, thereby enabling faster expansion in the sector. This approach would be more or less a first for development in the education sector and should be rooted in a strategy to secure sustainable non-government financing for LCPS in order to meet educational needs in Pakistan. The purpose of a guarantee is to bring down the price on loans to LCPS by lowering the risk exposure to either the lender or the borrower, with the view to incentivising lending to the sector and building loan experience within banks.

There is some evidence of unmet financing demand. A recent survey of LCPS estimated the total demand for finance from external sources at PKR 77.1 billion (£ 440 million), equivalent to around 1.5 times the total gross loan portfolio of the entire microfinance sector as of September 2013 and about 33% of the total SME outstanding loan portfolio (as of June 2013). The vast majority of this financing is currently unmet by banks. The same survey estimates that owner’s equity would meet only a third of their financing needs. Healthy profit margins, even amongst the low cost schools[14], suggest the sector has some commercial viability.
[14] The average net profit margin for LCPS has been estimated at 51%. Source: Access to Finance for Low Cost Private Schools, ILM Ideas, 2014.

Strong justification is needed to provide subsidy to the private sector. Time-bound subsidies are provided when there is market failure to overcome with scope for development impact. Subsidies to the private sector in the absence of a market failure can be distorting and should therefore only be used if there is no better instrument available. Assuming that the sector is commercially viable, the most obvious market failure in the LCPS financing sector is one of incomplete information, demonstrated by the lack of existing external finance. On the supply side, poor information about the sector can manifest itself in more expensive loans or more stringent collateral requirements. On the demand side, it can result in weak demand and limited investment in good business practices required to secure a loan. Guarantees can be used to improve information through exposure. Other non-finance interventions can also help improve access to information. A second case for subsidy is to support growth in a sector that has significant social returns in the form of access and school choice. Subsidy on these grounds would need to consider whether the social returns are deemed sufficiently pivotal for poverty reduction in order to proceed with allocating resources on this basis.

The need for donor subsidy or the size of the subsidy is uncertain but the potential gains from building a market could be sizeable. It is difficult to predict if financing would take off in the absence of encouragement of donor funds. Experience in the microfinance sector suggests banks are slow to move into new sectors and require both information and first-hand experience. MFIs interviewed for the review ranked the LCPS sector as medium to low risk, owing to relatively predictable cash flow, and expressed interest or plans to scale up loans to the sector with or without donor support. Both MFIs also identified useful lessons as a result of piloting the pricing tool and cash flow-based collateral that they intend to build into future lending, suggesting additional information on the sector is valued. Neither of these MFIs required guarantees to lend however the limited finance extended by other financial institutions with less of a social focus suggests there could still be a case for using funds to link up financiers with LCPS. If these assumptions are correct and the guarantee scheme is successful in establishing a private financing market for LCPS, then the gains of faster growth and improved leverage in the sector may be sizeable. The review was not able to determine if the funds available under the A2F component would be sufficient for this purpose.

To proceed with an A2F pilot, the sector needs to be allowed to focus on building links between financiers and LCPS with limited conditions on funding. Demonstrating market viability requires lenders to gain exposure to LCPS and various lending opportunities. Imposing too many conditions on loan products early on can stifle these opportunities and conceal demand. If the team decide to proceed with A2F, it must consider what results it is comfortable to focus on in the short term. The team can draw on the FIP Credit Guarantee Scheme and the newly approved SME finance scheme for ideas on what works in terms of conditions. Both schemes are however small in size and wide in scope, so whilst there may be potential to facilitate finance to LCPS through these existing schemes, the potential for impact at scale could be limited.

Recommendations
1. As a first step, the DFID team should determine the primary purpose of A2F.
2. Depending on the conclusion of the first recommendation, the programme team should decide whether or not to progress with developing a revised component. The team should consider the following:
1. Current capacity to develop further components in an already stretched and complex programme;
2. Scope for transformative impact and complementarity with other components. What support to the non-PEF LCPS sector is needed to complement the PEF model and expansion plans under the 2018 goals;
3. Appetite for innovation and the potential trade-off between uncertain but potentially sizeable benefits of building a market for private financing of LCPS and the additional results obtained by re-allocating funds within PESP II;
4. Willingness to provide donor support to the private sector under limited conditions; and
5. Opportunities to draw on existing DFID programmes, in particular DFID’s FIP Credit Guarantee Scheme managed by the State Bank of Pakistan.

Annex 3 – VFM Analysis

Cost drivers and performance
The respective fundings proportions of PESP II components to the total planned programme budget are shown in fig.1.

Fig. 1 Proportion of PESP II Budget by Intervention

Certain components have longer mobilisation periods than others, as a result there is a variation in the rate of spend under different elements. Contracts that have lengthy procurement and inception periods have been slower to start than SBS.

Fig 2. Proportion of PESP II Spend to Date by Intervention (December 2014)

Sector Budget Support
DFID invested in the sector alongside the World Bank which places a condition on donor support that no more than 70% of donor SBS funds can be used to cover salary costs. This is more a mechanism to incentivise spending on critical non-salary development items for schools as SBS funds are not strictly traceable in the budget. The World Bank monitors the expenditure of the non-salary budget as a sense check that the Government is providing funding to the non-salary elements of education reforms.

The largest cost driver within the education budget is salaries. Teachers’ salaries are a political issue, therefore the programme is susceptible to political drivers not necessarily linked to improving education outcomes. This may be a particular challenge on the approach to future elections or during other more politicised periods. DFID and the World Bank should continue to monitor the non-salary budget and maintain dialogue with the GoPb on the importance of protecting non-salary spend.

Punjab Education Foundation (PEF)
The PEF intervention operates through grants directly to PEF schools on a per student basis. These grants cover the fees the students would otherwise have to pay plus, under FAS, an additional top up to support school improvement. Grants are provided on a ‘per student’ basis therefore the primary cost driver is the number of students enrolled (in FAS schools) or receiving education vouchers (EVS scheme). As the grants are linked to school fees the underlying cost drivers relate to the schools’ operating costs (including pay elements). The review team was informed that these rates have not increased over the last two years but are due to increase going forward.

Any change to elements within the operating costs such as teachers’ salaries could have an impact on the number of children that the PEF scheme is able to support, if it means that the grant per child has to be raised. We do not know enough about the underlying cost drivers in PEF schools to be able to draw conclusions at this stage on tolerance. A recommendation is made for further investigation particularly given the link to the issue of low teachers’ salaries in PEF schools.
Scholarships - PEEF
DFID is covering some administrative and capital costs under the PEEF scheme which is supporting the additional students targeted by the scheme. In FY 13-14, administrative and capital costs made up 12% of the grant provided by DFID[15]. This is at the higher end of an acceptable range however we are aware of positive changes in administrative activities as a result of the DFID grant (e.g. electronic grant disbursement mechanism) thus providing a reasonable rationale for supporting such costs. The DFID team should ensure that the type of administrative activities being funded are reasonable and that consideration is given to longer term sustainability options for these costs.
[15] Data taken from ‘PEEF – DFID Scholarships UPDATE – II REVIEW 28 NOV’ PowerPoint presentation to the review team.

Scholarships - LUMS
Similar to PEEF, the cost of the LUMS intervention is driven primarily by numbers of students supported. The underlying cost drivers relate to the annual tuition fees and a means-tested stipend to cover living costs. Each potential scholarship student is means-tested to assess how much support they need to receive to enable their study. Scholarship awards are split into the primary categories – full support (fees and living costs) and tuition fee support only for either graduate or undergraduate support. The average cost per student of the scheme is lower than anticipated in the original LUMS proposal. This is partly explained by the numbers of beneficiary students receiving ‘partial support’ . As the level of support offered per student is means tested this is potentially an indicator that those students accessing the scheme are not as financially constrained as had originally been envisaged by the scheme. This raises questions about the targeting of the scheme which should be considered in greater detail by DFID.

TACE
The main anticipated cost driver for the infrastructure component is the price of materials, which is estimated by IMC to constitute 70% of total costs. Anticipated labour costs are relatively low. Budgets and work plans have been developed on the basis of a survey identifying school needs. There is a risk that further delays to the start of the implementation phase will lead to cost revisions if infrastructure needs begin to be addressed by government or others and further surveying is required.

TAMO
The contract model is milestone based and therefore the DFID team cannot expect sight of the exact costs of input elements used to deliver outputs post-delivery. This makes calculating VFM more challenging – in particular input to output analysis cannot be used as a measure. Each year an annual budget will be agreed in advance and this is the only opportunity to consider input in detail – DFID must ensure it invests sufficient effort during this annual cycle to agree appropriate annual expenditure.

There may be ways in which the TAMO team can provide some limited post-delivery information without compromising the underlying principles and benefits of milestone contracting (e.g. percentage of the contract spent against logframe/workplan outputs or percentage spend against different operating cost items). These options should be investigated.

VFM Assessment of PESP II Components

Sector budget support (SBS)
A total of £65.3m has been disbursed in SBS to date. These funds are notionally allocated towards employee-related expenditure, grants to schools councils, PEF, the girls’ stipends programme, a performance-based incentive system for schools, and school monitoring, in line with the World Bank’s IDA loan.

Performance of SBS is assessed against (i) the influence it affords; (ii) the economy and efficiency of public spend on education and (iii) additionality.

The policy dialogue and influence that SBS affords and the resulting policy reforms that government is encouraged to design and implement.

The fifteen disbursement-linked indicators (DLIs) to which DFID’s SBS is aligned commit the Government to a set of reforms and pilots to improve educational outcomes. Progress against the DLIs has been good. This year, the Government is currently on track to meet all DLIs for 2014/15. To the extent that these reforms have been stretching and effective in delivering outcomes, they demonstrate success for SBS.

DFID enjoys regular policy dialogue with the government, facilitated by the Roadmap process, strong political engagement and good working relationships. This dialogue has enabled DFID to support progress on a number of reform areas outside of the DLIs including some potentially politically challenging reforms. Examples include restructuring of the Punjab Curriculum and Textbook Board, large investments in monitoring and use of data and teacher rationalisation, as well as more recently the development of the 2018 goals. This level of access is impressive for a budget support programme that constituted under 4% of the total education budget last year and just over 1.5% the year before. Whilst it is still too early to assess the impact of these reforms and impossible to pinpoint the exact role that budget support plays, complemented with quality technical assistance and political engagement, the programme has made effective use of SBS from the perspective of supporting reform.

The economy and efficiency with which public funds, and by extension, SBS, is allocated and spent on the sector.

Teachers’ salaries and allowances constituted approximately 92% of the total current budget in 2013-14. The 2014-15 budget saw an estimated nominal 11% increase in primary salary allocations and a 15% rise in salary allocations at secondary level. Whilst teachers are one of the most important inputs to the education system, it is difficult to assess that these substantial real wage increases were commensurate with a rise in teaching quality. Measures to improve quality should help improve the economy of teacher inputs.

In a system where inefficient use of resources remains an ongoing concern, digitisation of monitoring processes was highlighted as an example where significant efficiency gains are being made. What is less clear is whether the higher costs of running tablets will result in overall cost-efficiency savings. More systematic use of monitoring data is playing an important role in improving efficiencies across the system, most notably helping to maintain teacher presence at an average of 92% over the last year. These data also provide an invaluable source of information to assist policy makers to make better allocation choices. On a regular basis now, EDOs and DCOs in the District Review Committees use PMIU data to identify key areas where further work is required. This includes identifying schools where toilets and other facilities are present but insufficient to cater to the size of the student body and looking at schools within a given markaz where there are large variations between student to teacher ratios and rationalizing the teachers accordingly.

The channelling of non-salary budget to school councils in selected pilot districts is a good example of where reforms are leading to more efficient utilisation of resources. A recent review of the non-salary budget pilot found that despite significant delays in disbursement, over 80% of funds received were spent by the year end representing a several times increase in spend per child on non-salary inputs for schools compared to the previous year. This is a noteworthy achievement given historically poor allocation and execution of non-salary budget.

The table below gives the approximate annual spend per enrolled child in government primary and secondary schools over the last 2 years.

	2012-13	2013-14
GoPB Primary*	£81	£82
GoPB Secondary	£130	£118
GoKP Primary	-	£62
GoKP Secondary	-	£166
PEF**	-	£41

*Unit costs computed on basis of EMIS enrolment figures and current budget outturn. Primary covers classes K-5. Secondary covers classes 6-10. ** PEF costs as per 2014 annual report.

Spend per child at primary increased less than inflation over the two years whilst spend per child at secondary level saw a real increase. Low by international standards, per child spend is comparable with spend in Khyber Pakhtunkhwa province and substantially higher than spend per child in PEF schools. To judge efficiency of spend, one must look at how well spend per child is translating into learning.

According to the Annual Status Education Report for Pakistan (ASER), the percentage of Grade 5 children in rural Punjab able to read a Grade 2 story was 67% in 2012, 66% in 2013 and 63% in 2014. Similar trends were found for children reading sentences in English, whilst arithmetic levels broadly showed some improvement. Although still low, learning levels for children of the same Grade in private schools were consistently several percentage points higher. The low numbers of children able to read at the right level is a signal that the education system is not delivering the outcomes needed to demonstrate value for money. These results are borne out by the recent DFID-funded sample-based assessment. The assessment found that only 50% of Grade 3 children were able to read a basic 4-line passage in Urdu and answer 3 basic questions. Results were 23% in English (Grade 2 level). Comparable data is not currently available to assess how the difference in spend across private sector and across provinces is reflected in the quality of education. Private schools are widely believed to offer better quality than the public sector and this, together with low cost, are key drivers in the GoPb’s decision to support PEF expansion. The decision to include PEF schools in the next sample-based assessment will provide critical data upon which to monitor and compare quality.

Learning needs to improve to increase the effectiveness of government spend on education. The DFID team’s push on quality and the recent commitment by the Chief Minister to allocate additional resources for quality improvements are vital steps that hope to improve VFM.

Budget execution provides further evidence of efficiency of spend. Execution remained reasonable for current expenditure in 2013-14, achieving almost 74% execution of the non-salary current budget. Execution of the development budget improved commendably from 38% in 2012-13 to 88% 2013-14, despite larger allocations. Budget execution for the first quarter of 2014-15 is showing similar trends to 2013-14. The review team nevertheless heard several complaints about timeliness and predictability of fund releases, impacting the ability of the sector to plan and spend well. Counter concerns were raised by the Departments of Finance and Planning and Development about the SED’s capacity to budget and monitor spend.
The additional impact that SBS has had on increasing enrolment in Government schools, reducing drop-out, and improving learning achievement.

The 2014-15 budget saw large nominal increases in allocations compared with 2013-14 spend – a 14% increase for current budget and a 67% increase for the development budget. Net of DFID’s SBS, these still represent an estimated 16% real increase year on year. Whilst it is impossible to know for sure what would have happened in the absence of SBS, these figures suggest SBS has not discouraged increases in government allocations to the sector and has remained additional. Education represents approximately 24% of total GoPb allocations for 2014-15. The share is estimated to have fallen marginally from 2013-14, suggesting that whilst education remains a priority, it continues to compete hard for resources.

Additionality can also be assessed against the trends in key education performance indicators over time, improvements in line with spend increases indicating that SBS is funding additional results. There are some positive trends roughly in line with the additional growth in government spend over the period since PESP II started. This relationship is only indicative however as there is likely to be a lag in impacts from spend increases and changes at the margin may be affected by factors other than spend. PMIU data on student attendance at public schools continues to fluctuate over the year but has shown a modest increasing trend in absolute terms. Teacher presence has improved from 81% in 2010 to 91% in October 2014.

PEF
The 2014 annual report estimated the average PEF monthly per student cost at Rs 511, including overheads. This is equivalent to approximately £41 per child per year, around half the cost to educate a child at primary level in the Punjab public sector and less than a third of the cost in secondary education. The per student cost represents a small increase on last year’s cost. PEF’s per student fees continue to broadly match those estimated in the business case as per the table below, suggesting PEF continues to offer good value for money on inputs, particularly in light of inflation. Expansion plans provide for a Rs 50 increase per student per year. One potential risk for economy of inputs is the slow appreciation of the PKR against the GBP over the last year. This affects the buying power of DFID’s funds and if the trend continues should be monitored for potential impact on results.

	Actual per Child Fees / (excluding overhead costs)	Unit Cost Estimates in Business Case
PEF Tranche 1	Primary: Rs 450 per month / Middle: Rs 500 per month / Secondary: Rps 600-700 per month	Primary: Rs 400 per month / Middle: Rs 500 per month / (no estimate)

An initial view on the VFM of PEF outputs will be possible once a comparable and robust assessment of learning outcomes is undertaken in the coming months.

FAS schools, which make up for the majority of PEF spend, continue to operate on a model that provides for 100% of fees for all students attending a FAS school, including previously paying students. Whilst there may be a case on equity grounds to provide free access to all, the large numbers of children that remain out of school suggest that this model is not making the most efficient use of funds. The review team heard about plans to trial a revised FAS model in new schools only, however changes to the FAS model have been put on hold until a better assessment can be made on the household income levels of students in FAS schools. Other aspects of the expansion plans propose a clearer focus on the most marginalised. EVS will support primary schools, providing poor students with financial aid to attend private schools, and NSP will focus solely on areas where there is no existing school but a sizeable population of out of school children present.

Low pay for teachers in PEF schools was highlighted in last year’s VFM analysis as an issue of concern. In addition to the general principle of paying an acceptable wage, low salaries are likely to affect turnover of staff in LCPS and potentially impact teacher performance. The team heard some evidence to suggest that turnover is a problem, but found reluctance to influence salaries, citing limited negotiability in the context of a public private partnership. Another concern is the impact that a rise in teacher salaries could have on the dynamics of labour supply and on the per student fees for LCPS as well as ability to maintain current enrolment levels. The review has recommended an investigation into the affordability and potential impacts of setting minimum salaries.

A final VFM consideration for support to PEF concerns the long term viability of the model. The review notes that the current terms of the PPP are heavily skewed toward public investment, raising questions about whether the PEF model could be improved to draw on more of the potential efficiency gains that a PPP might offer, including maximising opportunities to foster innovation whilst maintaining equity in access. PEF arguably offers a third way in the sector to compete with public and purely private schools, but the value and sustainability of its model needs testing.

Scholarships
Two rounds of scholarships have now been awarded under DFID’s support to PEEF and LUMS. PEEF unit cost allocations have not changed since last year suggesting that the scholarships to girls to complete matriculation continues to offer a high return. PEEF was able to award additional scholarships in 2014 due to lower than expected numbers of boarders, bringing down the average unit cost for matriculation scholarships against PEEF’s original proposal but remaining marginally higher than those estimated for the business case. Tertiary scholarship per student average costs are lower than originally forecast. Data on numbers of scholarships per institution was not available but the allocation of scholarships across institutions might explain the lower than forecast costs. Unit costs are presented in the table below.

(Monthly rates in PKR, unless noted otherwise)	Business Case	PEEF proposal (estimated unit costs in year 1)	2013-14 actual unit cost	2013-14 actual annual unit cost (£)
Matriculation scholarships	1,000	1,650	1,380	99
Tertiary scholarships	25,000	12,977	9,191	660

LUMS has been less successful in attracting scholars to its programme, reportedly due to difficulties in identifying deserving students. After a slow start in 2013, the numbers of scholarships have increased, but include partial scholarships and in some cases have funded final year students on existing scholarships. There is a risk that use of partial scholarships might fail to attract the most deserving students to study. LUMS performance on targeting has been mixed. It boasts a robust screening process for means-testing but has struggled to achieve the proposed 50% gender split, with only 23% of scholarships awarded to girls.

Of concern is the slow progress made on outreach initiatives. Scholarships can contribute to wider social returns beyond the potential private gains to the individual, particularly if they are successful in demonstrating the value of education or in motivating beneficiaries to invest back in society. Securing these returns are important for ensuring a clearly pro-poor dimension to the programme, as the per student costs for tertiary education are vastly higher than what it costs to support an additional child through primary school. The outreach activities can help extend the potential benefits of the programme to others. At the time of the review, LUMS was yet to properly start its outreach programme. PEEF highlighted some community activities of its scholars but did not indicate any clear plans for further activities.

While it is still too early to measure any clear impacts from the scholarship programmes, neither PEEF nor LUMS had any system in place for tracking alumni of their scholarship programmes. Providing it is not too costly, tracking alumni would help generate important information on the near term impacts of the programmes on their direct beneficiaries.

Access to Finance
This component was not operational at the time of the review and therefore no assessment of value for money was possible. Annex 2 considers issues for development of a model that can deliver value for money.

Technical assistance (TAMO and Roadmap)
Economy considerations for the technical assistance team are discussed below under cost drivers. Assessing effectiveness of TA is inherently difficult. The success of the Roadmap team is evidenced by the pervasiveness of the roadmap indicators at all levels of government and the continued buy-in by the Chief Minister to the process. Developing and securing agreement on the 2018 goals for the sector can in part be attributed to the TA. . The TAMO team have concentrated largely on analytical work during their inception phase.

Longer term impact however rests in the ability of the technical assistance teams to instil sufficient institutional change and capacity in the system to ensure reforms are sustained beyond the lifetime of the programme. The review team heard cases of officials feeling sidelined in policy reform and resentment of top-down governance. It is therefore positive that capacity building has become a priority for the TA teams going forward. TAMO’s support through its district teams will play an important role in ensuring sustainability of improvements in the sector.

Infrastructure
Delays to this component meant that the team had not moved to implementation at the time of the review. No assessment of VFM was therefore possible. The programme team nevertheless demonstrated a high level of understanding of VFM and have proposed various measures to ensure VFM during implementation. Use of community-based and commercial contracting is expected to secure savings of up to 110% over procurement through government systems. Use of local labour and materials, together with robust design and close involvement of communities is planned to secure best chances of sustaining facilities and reducing risks of rapid depreciation. The team also expects the programme will play an important role in highlighting inefficiencies within government procurement and works processes. Securing resources for repair and maintenance can only be addressed so far through efforts to instil strong community ownership of school infrastructure. These efforts will need to be complemented by adequate allocations of non-salary budget in the future.

Priority Districts
This component was not operational at the time of the review and therefore no assessment of value for money was possible. TAMO has put forward proposals for a revised component. Any revisions will need to revisit the anticipated benefits from this component and how they impact on the original VFM estimations in the business case.
Annex 4: Risk Matrix (* new risk)

Sr. No	Risks	Mitigation Strategies	Inherent Probability/ Impact	Revised Probability/ Impact
1	Reduced political will for education reform	DFID will address this risk by ensuring that politicians from all parties, as well as the media, are fully briefed on the importance of education to the development and security of Punjab, and the role PESP II will play. This work will be carried out through the TEP programme, and regular briefings at senior level. / Update: / Not enough progress was noted in terms of taking all politicians from all political parties and media on board. DFID team should utilise Alif Ailaan campaign to build and consolidate consensus around education reforms. / DFID is also actively engaging senior political and bureaucratic figures to ensure that the continued rotation of key civil servants is reduced. / Update: / On-going. Roadmap has helped a great deal to reduce turnover of key civil servants / The team will also continue to build strong linkages with position leaders from across the political spectrum through the Education and Governance advisers based in Lahore. / On-going / New Mitigation Strategy: / DFID along with TAMO and Roadmap teams will continue to actively engage senior political and bureaucratic figures to ensure their effective buy-in on key decisions related to this programme and to encourage reform initiatives that are inclusive and consultative so that they become routines in government departments.	L/H	L/H
2	Complexity and Coordination *	DFID team will improve internal coordination by delineating clearer roles and responsibilities between different team members including cross-cutting advisers and their level of engagement on respective work streams. / DFID team will seek to streamline without losing ambition and ensure efficiency ways of working. The new delivery plan approach should present opportunities to streamline and focus on key priorities. / TAMO’s workplan to reflect a strong focus on supporting DFID in the management of the PESP II programme and in helping to bring the different programme components together. / DFID to work with the School Education Department to explore the potential for a PESP II Steering Committee.		L/H
3	Opposition to reform on the basis of vested interests	The team has reduced the risk probability of opposition to reforms from “moderate” to “low” due to the on-going political and bureaucratic commitment and the fact that all stakeholders including teachers have been supportive of reforms so far. There have been some court cases against rationalisation policy/transfers but SED has managed to progress the reform in spite of these challenges. / DFID will address this risk using a range of strategies. These will include piloting controversial measures before widespread implementation, supporting the development of stronger school councils to exert upward accountability, participatory involvement of all stakeholders in design and implementation of interventions, and ensuring that the programme is based on a thorough understanding of political economy to inform its interventions. / Update: / Mitigating strategy remains relevant but the review team did not find much progress on DFID’s support for strengthening of school councils / Teachers Unions will be kept involved in design and implementation of reform to ensure their interests are properly represented and taken care of with an aim to cultivate ownership of reforms. / Update: / The strategy remains relevant but the strategy requires a defined mechanism to engage teachers unions / Publishers and journalists will be kept abreast of on-going discussion related to education reforms and the overall benefit these changes will bring to the province. In addition, PESP II will benefit from public messages being communicated through the TEP programme. / Update: / The strategy remains relevant but progress is yet to be made to effectively utilise public messaging and campaigning through the TEP programme. This is currently being explored.	M/M	L/M
4	Fiduciary and corruption risks	DFID will address this risk in three principal ways. The first two are designed to reduce fiduciary and corruption risks for the long term, while the third focuses on design decisions. / The Roadmap process will continue to address a range of issues connected to fiduciary and corruption risks, including teacher attendance, merit-based appointments and teacher transfers. / Update: / The strategy is operational. / PESP II in collaboration with SNG Programme will provide technical assistance to GoPb to support better public financial management especially in areas of procurement, budget expenditure, anti-corruption, and pay roll audit. DFID has already prepared a draft plan on mitigation of financial risk. The PESP II TA team in conjunction with SNG will continue to work with Government of Punjab for maintaining political and bureaucratic ownership around public financial management reforms. / Update: / The strategy is operational and the work is on-going. / PESP II has been designed with this risk in mind. For example, the school infrastructure component will be implemented outside the GoPb procurement and management systems, while loans made under the access to finance programme will be subject to stringent criteria. / Update: / The strategy is relevant but work under both streams has not started yet / PESP II will use external audit (through Auditor General of Pakistan) and third party audit mechanisms to verify utilisation of DFID funds for intended purposes. / Update: / On course. / New Strategy added by the Review Team: / PESP II will work with PEF to reduce the risk of fraud and corruption in redemption of vouchers by commissioning a forensic audit. The findings will be used for improving internal controls in PEF for validation and redemption of vouchers. / The DFID team should seek support from TAMO and use the Delivery Plan structure to assist in the follow up of audit findings.	M/H	M/H
5	Insufficient capacity to implement the programme at provincial level	DFID will address this risk through the programme’s TA assistance to GoPb to encourage politicians and officials to build on progress towards developing flexible, merit-based management of the education system (for example, open recruitment practices and more transparent transfer/postings). / Update: / On-course. / DFID will work with the GoPb to encourage the PMIU to be a centre for long term sustainability and capacity building – exploring opportunities for salary incentives as required. / Update: / No progress or action was noted on this strategy. / New strategy added by the review team: / DFID will work through TA to ensure that institutional capacity building is undertaken in all entities and levels within the education system of Punjab.	L/M	L/M
6	Insufficient capacity to implement the programme at district and sub-district level	Mitigation of this risk will be managed partially through the steps taken at programme level to build capacity, support PFM reforms and reduce fiduciary and corruption risks. / Update: / On-going. / In addition, TA for PESP II will include building the capacity of officials at district and sub- district level. There will be a particular focus on capacity building in LPDs. / Update: / On-going. New strategies added by the review teams: / TAMO will work through their divisional representatives for building the capacities of officials at district and sub- district level. There will be a particular focus on capacity building in LPDs. / For improving district level management in the wake of local government elections PESP II will also work more closely with SNG.	M/M	H/M
7	Conditions in low cost private schools pose a reputational risk to DFID	Mitigation of this risk will be managed by attaching conditions to DFID’s financial aid to PEF-run programmes, and to loans made as part of the access to finance programme. / Update: / The review team did not find any conditions that are attached to DFID’s financial aid to PEF-run programmes or any mechanism through which this can be implemented. / DFID has undertaken research which demonstrates that PEF schools are profitable and will be working with PEF to roll out a better employment model for teachers addressing the question of minimum wage. / Update: / No progress has been made on developing and rolling out an employment model however the cost drivers within PEF schools and their social implications should be investigated more fully before taking this decision.	H/M	H/H
8	The private sector does not respond to incentives to establish schools in under-served areas	Mitigation of this risk will be managed by attaching conditions to DFID’s financial aid to PEF, and to loans made as part of the access to finance programme. / Update: The review team did not find any evidence and mechanism of attaching and implementing conditions to DFID’s financial aid to PEF. Conditions will focus on ensuring that private entrepreneurs expand or open their operations in under-served areas, with a focus on LPDs. DFID will pilot and monitor a range of approaches (for example, the development of incentive packages) to encourage entrepreneurs to focus in those areas where more schools are most clearly needed. / Update: The strategy will only be relevant if DFID decides to go ahead with access to finance component of the programme.	M/H	M/H
9	Scholarships programme attracts negative press in Pakistan and the UK	DFID will address this risk in three principal ways. First, DFID will commission regular evaluation of the private and societal returns of the programme and ensure course correction. / Update: / Evaluation is still to be carried out Second, DFID will work on a proactive communications strategy. This will focus on publishing case studies of success stories, working through TEP, focusing on increasing parental demand for education, awareness of private and societal returns, working with LUMS to propagate the importance of scholarship beneficiaries as role models/ambassadors in their communities and their impact on raising the educational aspirations of poor girls and boys. / Update: on going / Third, DFID will seek to work with LUMS to demonstrate the targeting approach of this programme produces value for money.	L/M	L/M
10	Poor economic conditions limit job opportunities and restrict the fiscal space needed for sector reform	DFID will address this risk by monitoring closely the economic situation in Punjab and Pakistan, and taking appropriate action. The team will develop close links between PESP II and other DFID-funded programmes on pro-poor growth. / Update: / There are some questions raised through this review regarding targeting and VFM that need to be addressed. / DFID will provide support for the IMF programme through the stability and growth programme. As part of this programme DFID will continue to advocate for increased spend on social sectors, including education. / Update: / On going.	M/M	M/M
11	Delivery risk re TAMO *	DFID to agree a costed workplan with TAMO. / TAMO to consider balancing a relatively heavy senior management structure with more technical resource to deliver the work streams. / TAMO to clarify the roles and accountability chain within their senior management structure to DFID with a view to streamlining decision making processes and costs.	M/M	M/M