Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Punjab Education Support Programme II (PESP II)
Programme Value: £420.5 million		Review Date: 20 February 2017
Programme Code: 202697	Start Date: 22/02/2013	End Date: 31/03/2019

Summary of Programme Performance
Year	2013/14	2014/15	2015/16	2016/17
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The PESP II programme has made good progress on the majority of recommendations since the last annual review in January 2016 and has scored an A in this annual review overall.

Key Areas of Progress in this Review Period

- With leadership coming from the Chief Minister’s Education Roadmap there is stronger performance management, leadership and accountability at provincial, district and school levels across the province. This has had a positive impact on school data collection, analysis and use at district and provincial levels.
- There has been good progress on enrolling marginalised groups (including out-of-school children (OOSC), girls, children in remote areas, and those from poor families) into primary, secondary and higher education.
- Technical assistance (TA) to key government and non-government stakeholders implementing activities under PESP II has resulted in some improvements in their effectiveness.
- There is evidence that PESP II is improving teaching and learning (particularly in Urdu and mathematics) in the province.
- There has been a significant improvement in the accuracy of school level data. There is evidence that district officials and school councils have been meeting to discuss utilisation of budgets, quality of construction works and progress on education outcomes.
- Over the last year, improvements have been made to textbooks, teacher guides, teacher training, assessment and examination procedures.
- The majority of basic school facilities in the province are fully functioning, although more focus needs to be placed on improving the functionality of electricity in three districts.
- Progress has been made on the construction of new classrooms and toilets.
- TA teams have responded well to the DFID review of TA and are making improvements.

Key Learning during this Review Period

- The government’s transition to using District Education Authorities (DEAs) needs to be managed smoothly to ensure adequate school monitoring and ongoing improvements.
- The processes around the release and utilisation of funding from the Finance Department to the School Education Department (SED) and onwards to school councils and other organisations (e.g. the Punjab Education Foundation (PEF)) need to be improved to enable timely and effective implementation of planned education activities.
- The role of the Directorate of Staff Development (DSD) and approach to teacher training could be made more effective (particularly in relation to the use of new textbooks and English language).
- As the rate of construction increases, more focus needs to be placed on ensuring facilities are meeting the needs of school communities and can be adequately maintained.
- To achieve the Chief Minister’s 2018 Education Roadmap goals, interventions and TA need to focus on targeted activities that will accelerate progress in enrolment, retention and learning outcomes for less privileged groups in the lowest-performing districts.
- More effective management by DFID of TA to the SED and a closer working relationship on technical solutions will improve the quality and value for money of TA.
- There have been challenges around enrolling target numbers of children with disabilities into mainstream schools. Learning from this component is being captured and used to inform its redesign to achieve better impact and value for money.

Summary of recommendations for the next year

Outputs
1. DFID, with the support of TA, to monitor the risks associated with the roll-out of DEAs closely to ensure that the momentum and progress of reform are not adversely affected.
2. Technical Assistance and Management Organisation (TAMO) to ensure effective application of the new textbook development and review guidelines as Punjab Curriculum and Textbook Board (PCTB) continues to review and revise textbooks itself for other subjects and grades.
3. SED, DFID and TAMO to explore options for introducing regular formative assessments to provide feedback to schools and teachers in specific areas of learning, along with support/materials to improve teaching and learning outcomes.
4. Punjab Examinations Commission (PEC) to strengthen its research and analysis wing and develop guidelines, standard operating procedures, and training for the conduct of exams where these are missing. TAMO to provide additional support in analysis, reporting, dissemination, and use of test results.
5. TAMO to support SED to review teacher continuous professional development and training, including the future role of DSD.
6. IMC (the contractor for school construction) to present maintenance plans and evidence of school council/student/teacher training to DFID to demonstrate how maintenance will be provided.
7. PEF to improve its strategy for targeting the enrolment of OOSC in priority districts.
8. TAMO to step up TA to PEF for strengthening monitoring and evaluation and mitigating risks.
9. DFID and TAMO to support Special Education Department (SpED) to redesign the inclusive education component.
10. Roadmap team to engage at an early stage with DFID for technical support and quality assurance on key education solutions as part of the problem solving process.
11. SED, DFID and Roadmap team to ensure coherence between delivering the 2018 Roadmap goals and planned reforms and interventions. The upcoming SED, DFID, TAMO and Roadmap team strategy workshop provides the first step to ensure improved coherence.
12. TAMO to expedite any pending activities and where necessary adjust the timing of key deliverables to align with the government’s planning and budgeting cycle and processes.
13. TAMO to step up technical assistance to the full range of SED departments to strengthen their medium to long-term strategies and plans, build institutional capacity, and improve coordination to support delivery of goals.

Programme management
1. DFID to ensure all audit reports are received on time and issues addressed efficiently (including follow-up on the two outstanding issues in the Auditor General’s 2014/15 report).
2. DFID and TAMO to work with the Programme Monitoring and Implementation Unit (PMIU)/SED/Finance Department to understand the reasons for and remove the delays to the transfer of funds to Punjab Education Endowment Fund (PEEF) and PEF.
3. TAMO and DFID to align and strengthen risk management frameworks, processes, and mitigation measures to enable greater consistency in tracking, reporting and addressing risks.
4. DFID to clarify the delivery model for PESP II in relation to revisions to TAMO and Roadmap contracts by March 2017.
5. DFID to begin a formal Key Supplier Management (KSM) process with IMC in Pakistan by June 2017, and hold IMC to account for time slippages, cost increases, quality, safety, supply chains standards and accessibility.
6. IMC to step up the pace of construction, ensure potential delays are highlighted on a monthly basis to DFID and the third-party verification firm, improve accuracy and transparency of forecasted outputs and expenditure. IMC to ensure visibility of project costs at unit rate level, and a rate comparison benchmark.
7. DFID to undertake a review of IMC’s TA schedule to identify TA savings which can be re-allocated to the capital fund, allowing more classrooms to be built.
8. TAMO and DFID to align and strengthen risk management frameworks, processes and mitigation measures to enable greater consistency in tracking, reporting and addressing risks.
9. DFID to ensure partners collect data disaggregated by sex and disability and have clear approaches to addressing equity and inclusion.

List of Acronyms

AEO	Assistant Education Officer
ASER / ASI / BRAC	Annual Status of Education Report / Adam Smith International / Bangladesh Rural Advancement Committee
CCSI / CEO	Community Committees for School Infrastructure / Chief Executive Officer
CM	Chief Minister (Punjab)
CPD	Continuous Professional Development
CSO	Civil Society Organization
CTSC	Cluster Training and Support Centre
CWD / DC / DCO	Children with Disabilities / Deputy Commissioners / District Coordination Officer
DDEO	Deputy District Education Officer
DEA / DEO	District Education Authority / District Education Officer
DFC	Divisional Field Coordinator
DFID	Department for International Development (UK)
DLI	Disbursement Linked Indicator
DMO / DPA / DRC	District Monitoring Officials / Development Partnership Arrangement / District Review Committee
DSD	Directorate of Staff Development
DTE	District Teacher Educator
EDO	Executive District Officer
EVS	Education Voucher Scheme
FAS	Foundation Assisted Schools
GDP	Gross Domestic Product
GET	Ghazali Education Trust
GoPb	Government of Punjab
GRCC	Government Reform Coordination Cell
HDI	Human Development Index (UN)
HR	Human Resource
HRMIS / IMC Worldwide	Human Resource Management Information System / International Management Consultants Worldwide
INGO / KSM	International Non-Governmental Organisations / Key Supplier Management
KESP / LCPS	Khyber Pakhtunkhwa Education Sector Programme / Low Cost Private Schools
LND	Literacy and Numeracy Drive
LUMS	Lahore University of Management Sciences
MEA	Monitoring and Evaluation Assistant
MIS	Management Information System
MTBF	Medium Term Budgetary Framework
MVF	Mentoring Visit Form
NOP	National Outreach Programme
NSB	Non-Salary Budget
NSP	New School Programme
OOSC / OPM	Out-of-school children / Oxford Policy Management
PCTB	Punjab Curriculum and Textbook Board
PC-1	Planning Commission - 1
PD	Professional Development
PEC / PEEF	Punjab Examinations Commission / Punjab Education Endowment Fund
PEF	Punjab Education Foundation
PESP II	Punjab Education Sector Programme II
PFM	Public Financial Management
PKR / PMIU	Pakistani Rupees / Programme Monitoring and Implementation Unit
PMS	Performance Management System
PPA / PPBP	Partnership Principles Assessment / Parho Punjab, Barho Punjab (Learn Punjab, Prosper Punjab)
PR	Participation Rate
PRAP	Portfolio Risk Assurance Programme
Pre-DRC	Pre-District Review Committee
PSLM	Pakistan Social and Living Standard Measurement
PwC / RAF	PricewaterhouseCoopers (Auditors) / Results and Activities Framework
Rs / QAT	Pakistani Rupees / Quality Assurance Test
RISE	Research on Improving Systems of Education
SBAP	School Based Action Plan
SBS	Sector Budget Support
SC / SCWG	School Council / School Council Working Group
SED	School Education Department
SLO	Student Learning Outcomes
SMU	Special Monitoring Unit
SNG	Sub-National Governance
SOP	Standard Operating Procedure
SpED / SPO	Special Education Department / Strengthening Participatory Organization
SRO / STR / TA / TACE	Senior Responsible Owner (DFID) / Student/Teacher Ratio / Technical Assistance / Technical Assistance for Construction and Engineering
TAMO	Technical Assistance and Management Organization
TCF	The Citizens Foundation
TOR	Terms of Reference
TPI	Transparency for People Initiative
TPV	Third Party Validation
UNICEF	United Nations Children’s Fund
VfM / WB	Value for Money / World Bank

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/

Outline of programme
The PESP II programme supports the Government of Punjab (GoPb) to transform education outcomes and reform the delivery of education in Punjab. The outcome of the programme is: more children in school, staying longer, and learning more.

The budget is £420.5 million from June 2013 to March 2019 and 51% has been spent to date. The budget for the current 2016-2020 spending round is £251 million. The programme combines a mix of delivery mechanisms including sector budget support, financial aid, and technical assistance to the GoPb and includes the following components:

1. Sector budget support to School Education Department (SED) to improve access to and quality of education in government schools (£170.2 million).
2. School reconstruction and rehabilitation to build additional classrooms in existing government schools and provide a limited number of missing facilities such as boundary walls, washrooms, electricity, and water and sanitation. This is managed through the Humqadam project, implemented by IMC Worldwide (£104 million).
3. Financial aid to Punjab Education Foundation (PEF) to improve access to and quality of Punjab’s low fee private school sector through an Education Voucher Scheme (EVS), New Schools Programme (NSP), and Foundation Assisted Schools (FAS) programme (£68.6 million).
4. Targeted support to PEF to tackle social exclusion and inequality by identifying and enrolling OOSC in the 11 lowest-performing priority districts in Punjab (£10.8 million).
5. Support to SpED for an inclusive education programme to provide children with mild disabilities with formal schooling opportunities (£7 million) in mainstream government and PEF schools.
6. Support to the Punjab Education Endowment Fund (PEEF) to provide scholarships for talented female secondary school students from poor households in the 11 priority districts to study at intermediate level; and for male and female students at intermediate level to study at tertiary level (£10.9 million).
7. Support to the LUMS National Outreach Programme (NOP). A scholarship programme for talented male and female students from poor households to study at a leading university and become role models to build aspirations among people from disadvantaged areas (£7.3 million).
8. A TA component to deliver the programme and manage key components through TAMO - comprising Adam Smith International (ASI) and McKinsey - providing support to the GoPb, the Chief Minister’s Education Roadmap process and other partners in the PESP II programme (£39.7 million).
9. A programme performance evaluation component (£2.5 million). This component was revised in 2016 and is currently under procurement.

A component which focused on improving the availability of access to finance for low fee private schools was on hold from 2015 and was closed in 2016. TAMO and DFID conducted analysis which suggested low fee private school owners would invest loans in infrastructure improvements to increase enrolment and profits, rather than in the quality of teaching and student learning, and as support to low fee private schools and infrastructure improvements were being implemented through other components DFID decided that continuing this component would be poor value for money. The £9 million budget allocated to this component will be reallocated within the programme.

The education context in Punjab
Punjab is Pakistan’s most populous province with approximately 100 million people (around 56% of the country’s population). It has the largest number of OOSC in Pakistan aged 5 to16 years (estimated in 2014 to be 13 million, of which 6.8 million are girls[1]) and the highest number of children with low learning levels in Pakistan. The 2015 Annual Status of Education Report (ASER) for Pakistan found that in Punjab girls remain marginalised, particularly the poor and those affected by disabilities. Only 48% of the poorest girls are in school, compared to 68% of the poorest boys. Children with moderate to severe disabilities are also the least likely to have ever been enrolled in school.
[1] Alif Ailaan (2014) 25 Million Broken Promises: The Crisis of Pakistan’s Out-of-School Children (Islamabad)

Despite these challenges there is strong political will and engagement to improve education in Punjab. The Chief Minister (CM) leads the reform agenda and his Education Roadmap, supported by the PESP II programme, provides the high-level political engagement and accountability to drive progress through SED. The Roadmap’s goals for 2018 are:

- Enrolment and access: 95% minimum participation rate for 5 to 9 year olds;
- Teaching quality: 75% score on six-monthly assessment;
- Schools and teachers: 36,000 new classrooms, 46,000 new teachers, 100% functioning facilities in schools; and
- Public private cooperation: 2.6 million students enrolled by PEF schools for 2018.

The priorities of the GoPb and DFID are closely aligned and PESP II provides additional support to the government to meet its ambitious targets. Support through PESP II, particularly the TA component, has also enabled DFID to influence the government’s education reform agenda.

Expected results
The UK’s support to the GoPb has a significant impact on driving reform, improving enrolment and increasing learning outcomes. PESP II is forecast to support 911,310 children (47% female, 53% male) to 2019. This is 47% of DFID Pakistan’s overall education results and eight percent of DFID’s global education results of 11 million children supported to gain a decent education. In addition, all government school children (6 million primary, 4 million secondary) and PEF school children (around 2.6 million expected for 2018) benefit from UK support in Punjab. This is the result of improvements in access to education, quality, and learning from education sector reform.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The outcome of the PESP II programme is: more children in school, staying longer and learning more. This outcome is on-track to be met by the end of the programme.
Indicator No.	Indicator(s)	Milestones 2016/17	Progress
Outcome Indicator 1	Participation rate for primary school aged population (ages 5-9) / Participation rate for primary school aged population (ages 5-9) in 11 priority districts	Punjab average: / Girls: 89.5% / Boys: 92.5%	Milestone met / Punjab average: / Girls: 89.7%, Boys: 91.3% / Priority districts: / Girls: 81.9%, Boys 85.5% / (Nielson survey data as of December 2015)
Outcome Indicator 2	Participation rate for secondary school aged population (ages 10-16) / Participation rate for secondary school aged population (ages 10-16) in 11 priority districts	Punjab average: / Girls: 82% / Boys: 86%	Milestone partially met / Punjab average: / Girls: 82%, Boys: 85% / Priority districts: / Girls: 69.6%, Boys: 77.5% / (Nielson survey data as of December 2015)
Outcome Indicator 3	Student learning outcomes: / % students achieving specific Student Learning Outcomes (SLOs) - Average scores by subject for March and September six-monthly assessments and PEC Class 5 scores (in Urdu, English and Maths) disaggregated by Government and PEF Schools	Percentage of Grade 3 students that achieve specific SLOs for each subject English, Mathematics and Urdu / Mathematics: 68% / English: 62% / Urdu: 59%	Milestone partially met / Gov / Math Gov English Gov / Urdu PEF Math PEF English PEF Urdu / Sept 2015 60% 59% 53% 73% 71% 76% / Feb 2016 71% 59% 60% 83% 69% 80% / Sept 2016 63% 57% 59% 74% 67% 76% / (6-monthly assessment results - first test of academic year in Sept, second test at end of academic year in Feb)
Outcome Indicator 4	Student attendance	91% attendance rate maintained every month (91% boys schools; 91% girls schools)	Milestone met / 91.4% attendance rate (93% boys schools; 92% girls schools)[2] / (PMIU data - rolling average over the last 12 school months between Sept 2015 and Nov 2016)
[2] PMIU is the only sourced used to measure attendance rates in Punjab, and they do not collect sex-disaggregated data. Data is only collected for students enrolled in boys’ or girls’ schools, but this is only 75% accurate as are often female students in boys’ schools or male students in girls’ schools, particularly at primary level. DFID is working with PMIU to improve sex-disaggregation

Overall output score and description

Overall the programme outputs scored an A: Met expectations
Output	Score	Impact Weight	Summary
1. Stronger leadership and accountability	A	15%	Progress met expectations for this year, apart from in frequency of monitoring visits to schools.
2. Better teacher performance and better teaching	A	25%	Progress met expectations for this year, apart from in frequency of district teacher education visits.
3. High-quality infrastructure	A	15%	Progress met expectations for this year, apart from in functionality of electricity in schools in three districts.
4. Improved access to schools, especially in priority districts	A	25%	Progress met expectations for this year, apart from in enrolment of target numbers of children with disabilities into mainstream schools.
5. Top political leadership engaged on education reform agenda in the Punjab	A	10%	Progress met expectations for this year.
6. High-quality technical assistance to government stakeholders that builds sustainable systems and processes	B	10%	Progress did not meet expectations for this year, in the areas of quality and timeliness of technical assistance products and programme delivery, system/institutional strengthening and capacity-building.

Summary of recommendations for the next year

Outputs
1. DFID, with the support of TA, to monitor the risks associated with the roll-out of DEAs closely to ensure that the momentum and progress of reform are not adversely affected.
2. TAMO to ensure effective application of the new textbook development and review guidelines as PCTB continues to review and revise textbooks itself for other subjects and grades.
3. SED, DFID and TAMO to explore options for introducing regular formative assessments to provide feedback to schools and teachers in specific areas of learning, along with support/materials to improve teaching and learning outcomes.
4. Punjab Examinations Commission (PEC) to strengthen its research and analysis wing and develop guidelines, standard operating procedures, and training for the conduct of exams where these are missing. TAMO to provide additional support in analysis, reporting, dissemination and use of test results.
5. TAMO to support SED to review teacher continuous professional development and training including the future role of Directorate of Staff Development (DSD).
6. IMC to present maintenance plans and evidence of school council/student/teacher training to DFID to demonstrate how maintenance will be provided.
7. PEF to improve its strategy for targeting the enrolment of OOSC in priority districts.
8. TAMO to step up TA to PEF for strengthening monitoring and evaluation and mitigating risks.
9. DFID and TAMO to support SpED to redesign the inclusive education component.
10. Roadmap team to engage at an early stage with DFID for technical support and quality assurance on key education solutions as part of the problem-solving process.
11. SED, DFID and Roadmap team should ensure coherence between delivering the 2018 Roadmap goals and planned reforms and interventions. The upcoming SED, DFID, TAMO and Roadmap team strategy workshop provides the first step to ensure improved coherence.
12. TAMO to expedite any pending activities, and where necessary adjust the timing of key deliverables to align with the government’s planning and budgeting cycle and processes.
13. TAMO to step up TA to the full range of SED departments to strengthen their medium to long-term strategies and plans, build institutional capacity, and improve coordination to support delivery of goals.

Programme management
1. DFID to ensure all audit reports are received on time and issues addressed efficiently (including follow-up on the two outstanding issues in the Auditor General’s 2013/14 report).
2. DFID and TAMO to work with the PMIU/SED/Finance Department to understand the reasons for and remove the delays in transfer of funds to PEEF and PEF.
3. TAMO and DFID to align and strengthen risk management frameworks, processes and mitigation measures to enable greater consistency in tracking, reporting, and addressing risks.
4. DFID to clarify the delivery model for PESP II in relation to revisions to TAMO and Roadmap contracts by March 2017.
5. DFID to begin a formal KSM process with IMC Worldwide in Pakistan by June 2017 and hold IMC to account for time slippages, cost increases, quality, safety, and accessibility.
6. IMC to step up the pace of construction, ensure potential delays are highlighted on a monthly basis to DFID and the third-party verification firm, improve accuracy and transparency of forecast outputs and expenditure. IMC to ensure visibility of project costs at unit rate level, and a rate comparison benchmark.
7. DFID to undertake a review of IMC’s TA schedule to identify TA savings which can be re-allocated to the capital fund, allowing more classrooms to be built.
8. DFID to ensure partners collect data disaggregated by sex and disability and have clear approaches to addressing equity and inclusion issues.

Has the logframe been updated since the last review?
Yes. The previous annual review recommended revising the PESP II logframe. After a series of consultations between DFID and key partners, changes to indicators, goals and targets were agreed by the DFID Senior Responsible Owner (SRO) for PESP II on 28 October 2016. The logframe was also aligned with the Results and Areas Framework (RAF) against which sector budget support payments are made. These changes have reduced ambiguity and enabled more effective assessment of progress. Key changes made to the logframe:

- Output 1: Obtaining time-series data on the margin of error around the frequency of Monitoring Evaluation Assistant (MEA) visits and clarifying the baseline and milestones for school visits.
- Output 2: Clarifying milestones for printing teaching and learning materials; removing milestone for school expansion; clarifying means of verification for PEC exams; measuring breakdown of authorised/unauthorised teacher absences; adding student-teacher ratio indicator.
- Output 3: Clarifying that the milestone aims for all districts to reach 95% functionality across all facilities; including additional indicators to measure progress with school construction.
- Output 4: Improving PEF enrolment data reporting and gender breakdown; incorporating Lahore University of Management Sciences (LUMS) and PEEF indicators into Output 4; revising LUMS and PEEF targets in line with forecasts.
- New Outputs 5 (Roadmap) and 6 (TAMO) were also added to enable more effective assessment of progress under these components.
- Impact weighting for outputs two and four were slightly reduced (5% each) to accommodate the additional two outputs
- Risk ratings were updated to align with DFID’s new Risk Management Framework ratings

## C: DETAILED OUTPUT SCORING

Output Title	Strong leadership and accountability
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		N (updated to align with DFID risk framework)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone 2016/17	Progress
1.1 Number of districts with performance management system (PMS) in place and in use	Teacher and student attendance improved in five low-performing districts	A: Milestone met / Taking December 2015 as a baseline, student and teacher attendance improved in all 5 low-performing districts (except for Sialkot where teacher attendance fell during the year, although it stayed above 90%) (PMIU data) / PMS initiative expanded to all 36 districts including regular Pre-District Review Committee (DRC) and DRC meetings.
1.2 Frequency of MEA visits and reliability of data collected	90% school visit rate maintained every month in every district / Data verified (for sufficient robustness and quality). The monthly variation between audit data (from District Field Coordinator (DFC) spot checks or Third-Party Validations) and collected MEA data should be within +/- 10 % for each district	B: Milestone moderately not met / 92.6% of schools covered by MEA visits (12 monthly rolling average to December 2016). However, visit rate fell below the 90% target in some districts in some months (including due to MEA strike in August 2016). / Tablet-based real-time data collection rolled out in 36 districts. Variation between 2016 DFC audit data and collected MEA data within +/- 10% for 3 indicators in 215 schools[3] assessed: / Student attendance: 3.6% variance / Teacher presence: 0.6% variance / Functioning facilities: 4.1% variance
1.3 Functional Primary School Councils as measured by PMIU census data (released on 31 Oct) / -Regular meetings held / -Actual utilisation of funds	10% average Non Salary Budget (NSB) utilisation rate by Dec 2016 (end of 2nd quarter of financial year), and a 42% average NSB utilisation by June 2017 / Meetings held: 70% of school council meetings held on a monthly basis.	A: Milestone met / Fund utilisation: 30% of released funds were utilised by December 2016, and SED is on-track to utilise a minimum of 42% of the NSB budget by June 2017[4] (PMIU data) / School council meetings: 70% of schools holding council meetings on a monthly basis
[3] Technical Assistance for PESP II Quarterly Report Sept-Nov 2016, p.23
[4] Source: PMIU Quarter 2 Budget Execution Reports

Key Points
This output supports key functions of the SED to manage the education system better and increase government accountability to improve the quality of education in Punjab. The achievements under this output are primarily supported by sector budget support (SBS) to the GoPb and the Chief Minister’s (CM’s) Education Roadmap. In 2014 DFID and the GoPb agreed a Results and Activities Framework (RAF) aligned with DFID’s business case and the CM’s 2018 goals, with yearly results targets linked to DFID’s disbursement of SBS. The RAF for year two of the PESP II programme (July 2015-July 2016) linked disbursement to achievement of results in teaching and learning, performance management, textbook development, leadership and accountability and public financial management (PFM). The partnership with government through SBS helps to maintain high-level political commitment and the momentum needed for reform. Progress under this output over the last year has met expectations.

Output Indicator 1.1: A - Milestone met
This indicator tracks improvements in student and teacher attendance in the five lowest-performing districts in the province through use of a PMS. The milestone for this year has been met. PMIU data shows that between December 2015 and December 2016, student and teacher attendance rates improved in all of the five lowest-performing districts, apart from in Sialkot, where teacher attendance fell by 0.35%, although it stayed above the 90% target[5]. Across the lowest-performing districts, student attendance improved by an average of 2 percentage points (87.1% in 2015 to 89.1 % in 2016) and teacher attendance improved by over 1 percentage point (91.4% in 2015 to 92.5% in 2016). These improvements have been attributed to regular pre-DRC and DRC meetings as part of the PMS at district level, where granular data for each school are discussed and corrective measures taken if required.
[5] The 5 lowest performing districts on student attendance are: Bhakkar, D.G. Khan, Narowal, Rahimyar Khan, and Rajanpur. The 5 lowest performing districts on teacher presence are: Bahawalnagar, Gujranwala, Narowal, Rahimyar Khan, and Sialkot.

During 2016, the PMS was institutionalized in all 36 districts. The pre-DRCs now put up school-level information on various indicators (e.g. teacher and student attendance, non-functional facilities) and help education managers take informed decisions before matters are brought to the notice of the District Coordination Officer in DRC meetings. The indicators under review have been expanded to include scores from the literacy and numeracy drive (LND) tests. The system was reported to be working well and provides a systematic approach to reviewing performance at all levels of the education system. TAMO’s District Field Coordinators (DFCs) play a key role in building the capacity of district officials to organise these meetings and use the data to inform decisions (e.g. helping develop agendas and presentations for meetings using monthly PMIU data packs). TAMO now needs to focus on ensuring that these skills are transferred to district officials.

A Human Resource Management Information System (HRMIS) pilot has been completed in two districts: Hafizabad and Sheikupura. The pilot involves the automation of information on transfers, postings, promotions and disciplinary proceedings. The HRMIS provides a management tool to the Executive Districts Officers (EDO)/Chief Executive Officer (CEO) of DEAs to manage teachers. While this looks like a good technical initiative, it is not clear if it will address the challenges of managing teacher transfers and postings. Thus far the initiative has had limited success due to limited capacity of the partner (Transparency for People Initiative), effort required to transition data on the number of schools, teachers and non-teaching staff from the current manual system, and limited ownership by the SED. There is an opportunity to learn from a similar initiative in the Khyber Pakhtunkhwa Education Sector Programme (KESP).

The GoPb has provided official notification of the establishment of DEAs for all 36 Districts. The EDOs have been made acting CEOs of these authorities with Deputy Commissioners (DCO replaced by DC) as administrators until the elected/nominated political leadership of the DEA is in place. The establishment of DEAs is both an opportunity and a risk. DFID’s Sub-National Governance (SNG) programme and TAMO have worked together for a smooth transition, and this needs to continue, along with further collaboration with the Roadmap team and Chief Minister’s Special Monitoring Unit (SMU), the independent government monitoring body helping the CM to track progress against the 2018 education goals and coordinate reforms across Punjab. DFID needs to monitor the roll-out of DEAs closely to manage the risks associated with this reform, particularly in relation to financial management.

Output Indicator 1.2: B - Milestone moderately not met
This indicator tracks the percentage of schools visited by Monitoring and Evaluation Assistants (MEAs) and the reliability of the data collected. This milestone has not been met, but only by a moderate margin. In 2016, although over 90% of schools were visited by MEAs overall, this percentage fell below the target rate in certain months and for certain districts[6]. This variation is attributed to seasonal issues when MEAs have to perform additional administrative duties for the government (e.g. extra monitoring of flood relief, crop harvest, and religious occasions). Another reason for this variance was a strike by MEAs in August about salaries, which led to MEAs only attending around 30% of schools on average. This issue has been resolved. MEAs now use a tablet-based data system to collect monthly data from schools and to conduct the monthly Literacy and Numeracy Drive (LND) test. The logframe milestone sets a +/-10% threshold for the margin of error between the original MEA data and the DFC spot-check, as a proxy for data quality. In 2016, DFC audit data showed that the margin of error was lower than 5% for student attendance, teachers’ attendance and non-functioning facilities. TAMO audited data on MEA visits in three pilot districts and found this to be 100% accurate. The PMIU is putting additional quality checks in place, such as refining the tablet monitoring application, to increase randomisation of MEA visits. MEAs already rotate across school clusters to avoid repeat visits to the same schools. These additional checks should reduce the risk of collusion between MEAs and teachers caused by advance warning of visits.
[6] The percentage of schools covered by MEA visits was on average lower than 90% in January, February, May, August and December. The percentage of schools covered by MEA visits was lower than 90% on average for several in districts including Bahawalpur, Bhakkar, Bahawalnagar, Faisalabad, Gujrat, Gujranwala, Layyah, Lodhran, Muzaffargarh, Rajanpur, Rawalpindi, Sheikupura

Output Indicator 1.3: A - Milestone met
This indicator tracks the effectiveness of school councils by measuring the frequency and regularity of meetings and utilisation of NSB funds which they control. The milestone for this year has been met. The NSB initiative started as a pilot in 2013/14 in nine districts, and was expanded to all 36 districts from the start of the 2015/16 financial year. Under the initiative, school councils receive a dedicated amount, based on school needs, to cover non-salary expenses. The additional NSB is helping school councils to hire additional teaching assistants to improve learning, provide additional spaces and furniture for students, and cover operational expenses like stationery and utilities. The latest PMIU data available (February 2017) reveals a budget utilisation of 30% of the Rs.3.5 billion funds released during the first eight months of the financial year, against a target of 42% by June 2017. Utilisation is on-track; it normally starts low and increases after eight to nine months. The issue of slow budget release and utilisation is being addressed through provincial-level discussions with the Secretary SED and their team around quarterly Budget Execution Reports, and in pre-DRC meetings between the EDO and district officials. TAMO has conducted a Third Party Verification to review the NSB release and utilisation process and the results will be used to streamline the NSB process.

According to data from TAMO, in 2016, 70% of schools councils met on a monthly basis, achieving this year’s target. Allocation of NSB funds at the school level means school councils meet regularly to discuss spending plans. The percentage of school councils meeting frequently could be improved by more timely release of allocated funds. Feedback from participants indicates that NSB allocation has made the process more inclusive and useful for parents and other stakeholders and increased their engagement. The establishment of DEAs needs close monitoring with regards to NSB budget utilisation. Currently there is a lack of clarity on new channels for funds transfer and reporting.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations of Annual Review 2015-16	Progress
TAMO should assess the benefits of the pre-DRC meetings, preferably through a third party. The impact of new business processes needs to be properly analysed, along with the political economy of teacher transfers and postings before the system is rolled out to other districts	The TAMO team conducted a review of the pre-DRC meetings. Following consultation with the SED, TAMO agreed to train the DFCs to pilot an overhaul of pre-DRC meetings in nine districts. A revised and improved pre-DRC process which increases focus on improvements in low-performing markaz, support and training for Assistance Education Officers (AEOs), and greater accountability for EDOs and AEOs, is now being scaled-up across the province.
The quality of PMIU data should continue to be monitored closely and spot-check findings used to continuously improve data quality	TAMO has continued to work with PMIU to improve data quality by highlighting districts where there are insufficient MEAs (e.g. Rajanpur), conducting spot checks using DFCs, and feeding data back to PMIU for training and corrective action; as well as initiating a formal process for audits by senior district monitoring officials (DMOs). In addition, TAMO is conducting a pilot to randomise MEA visits (currently in two districts), and adding new indicators to highlight additional areas that could be addressed to improve schools in Punjab (e.g. a metric for sufficiency of facilities, such as number of students per functioning toilet)
TAMO and DFID to ensure dedicated resources to support the roll-out of DEAs following the elections of local bodies, ensuring clarity on roles and responsibilities among Chief Minister’s SMU, Roadmap teams, TAMO and SED, through clear transition planning	TAMO is working closely with SED to ensure transition from the existing structures to DEAs is smooth. TAMO’s Public Financial Management and Policy Adviser is a member of an SED committee established to oversee transition to DEAs. A detailed transition plan, with timelines and responsibilities, has been prepared by TAMO and will be implemented over the next six months. The necessary legal framework (rules of business, financial rules etc) will also be developed alongside transition guidelines.

Recommendations
- TAMO to analyse the new business processes (HRMIS) initiative around teacher management and apply learning from the KESP programme by June 2017.
- DFID, with the support of TAMO and the Roadmap team, should closely monitor the risks associated with the roll-out of DEAs to ensure that the momentum and progress of reform is not adversely affected.
DFID and TAMO with the support of PMIU/SED/Finance Department should review financial management processes and agree clear timelines for release and utilisation of NSB and ensure that at least 70% of NSB is utilised within the financial year.

Output Title	Better teacher performance and better teaching
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N (updated to align with DFID risk framework)	Impact weighting % revised since last AR?	Y (previously 30% - Impact weighting changed to accommodate new outputs)

Indicator(s)	Milestone 2016/17	Progress
2.1 New teaching and learning materials developed in line with new curriculum	TAMO supports PCTB in the development of Grade 4 and 5 textbooks, textbooks and teaching guides are with the printers by December 2016 (for 2017/18)	A: Milestone met / TAMO supported PCTB to develop Grade 4 and 5 textbooks and teacher guides. Grade 4 textbooks and teacher guides are with the printers. Printing of Grade 5 textbooks and teacher guides has been halted; these will be printed in time for the academic year 2018/19.
2.2 Six-monthly learning assessment system in place and data used	Independent student assessment conducted on six-monthly basis, ensuring robustness and reliability (Grade 3)	A: Milestone met / Six-monthly assessment conducted in March and September 2016. 9,167 students tested overall (5,184 in 222 government schools; 3,983 in 126 PEF schools)
2.3 Improved integrity of PEC exams, with reduced cheating and leakage and improved test design and content quality	PEC exams administered incorporating learning from 2015 examinations, and with improved quality of marking	A: Milestone met / 2016 PEC exam conducted with significant improvements in the test conduct and marking, including: improved marking rubrics and better marking process; irregularities minimised.
2.4 Quality and delivery of teacher training and mentoring	Maintain District Teacher Educator (DTE) attendance at 92% / 75% average score of students in six monthly assessment	B: Milestone moderately not met / DTE visit rate: 85.9% (based on 12-month rolling average to Dec 2016) / Average % of correct answers by Grade 3 students across all subjects: 60% in Sept 2016, up from 57% in Sept 2015. 84% on LND in Oct 2016.
2.5 Teacher attendance rates in government schools, with breakdown of authorised and unauthorised absence	93%	A: Milestone met / 93.5% teacher attendance rate based on rolling average from January to December 2016.
2.6 % of stand-alone primary public schools with a student-teacher ratio of less than or equal to 1:35	Baseline to be measured in December 2016 and targets to be decided accordingly	A: Milestone met / Baseline established as 45.5% (Nov 2016 PMIU data). Incremental performance will be first reported in 2017.

Key Points
This output focuses on key components of the GoPb’s quality reform agenda supported by TAMO and the Chief Minister’s Education Roadmap. TAMO, the Roadmap team and the SED work to improve teaching and learning through different interventions, including: reviewing and streamlining the primary school curriculum; developing high-quality English, Urdu and mathematics textbooks for Grades One to Five; developing integrated teacher guides and ensuring their effective use; improving teacher training and mentoring and developing high-quality student learning assessments aligned with the curriculum. Progress under this output over the past year has met expectations, although one milestone was moderately not met.

Output Indicator 2.1: A – Milestone met
The milestone for this year has been met. TAMO has supported the Punjab Curriculum and Textbook Board (PCTB) to develop high-quality, inclusive and gender-responsive English, Urdu and mathematics textbooks and teacher guides for Grades Four and Five. PCTB has now completed its revision of English, Urdu, and mathematics textbooks and teacher guides for Grades One to Five. The new Grade One to Three textbooks and teacher guides are already being used in schools across the province. Grade Four textbooks and teacher guides will be introduced in schools at the beginning of the academic year starting April 2017 and teacher training on these new books is planned during the course of the next academic year (April 2017-March 2018). The printing of Grade Five textbooks and teacher guides has been delayed due to a legal challenge relating to printing contracts. These books will now be introduced in schools in the following academic year starting in April 2018. New Grade Five textbooks will be piloted in selected schools to assess their quality and make any further improvements, if necessary, in time for the next academic year.

A recent study conducted by TAMO to evaluate the effectiveness of quality interventions in teaching and learning shows positive overall responses on the textbooks and curriculum, related to content and pedagogy, although responses related to structure were mostly neutral, indicating room for further improvement. The study also shows positive feedback from teachers regarding content, structure, pedagogy and medium of instruction (Urdu) of teacher guides. The new teacher guides are well-designed and fully integrated with the curriculum and textbooks. Use of teacher guides is limited, particularly in multi-grade classrooms. This may be due to gaps in teachers’ training on the use of teacher guides, or the lack of a conducive environment for delivering structured lessons in overcrowded and multi-grade classrooms. Use of teacher guides could be enhanced through better communication on their purpose, improved teacher training, and relevant guidance for multi-grade teaching.

Improvements have been made in the textbook development process for Grade Four and Five textbooks based on lessons learnt over the last two years. Textbook revisions included ensuring content was more inclusive of minority religions, women and girls. PCTB’s capacity for curriculum and textbook development has improved by virtue of close engagement in the process of curriculum and textbook revision with TAMO. TAMO has further strengthened capacity within PCTB by providing detailed guidelines on the textbook development process, including content development, manuscript review, textbook selection and procurement. If used appropriately, these guidelines can ensure that PCTB continues to introduce high-quality, inclusive and gender-responsive textbooks, provided there is strong oversight to ensure that the process remains on-track. TAMO is currently working with PCTB to review Grade Six-Ten SLOs. TAMO should continue to provide institutional strengthening support to PCTB for it to develop new textbooks, to apply the minimum quality standards agreed at the Inter-Provincial Ministers’ Meeting and to review guidelines as PCTB continues to revise textbooks for other subjects and grades in line with the national curriculum.

Output Indicator 2.2: A – Milestone met
This indicator tracks the frequency and reliability of the Grade Three student learning assessment used to report progress against the Chief Minister’s 2018 goals on learning. The milestone for this year has been met. The Roadmap team continues to support SED to conduct six-monthly student learning assessments in Urdu, English and mathematics. The assessment tests SLOs from pre-primary (Katchi) to Grade Two.

The reliability of the six-monthly assessment results is ensured through strong invigilation, monitoring and multiple checks at each stage of test administration. This includes external invigilation of all government schools; ensuring secrecy of papers; producing multiple versions of papers to minimize chances of leakage and cheating and to obtain a wider set of data points; and external marking. The roles of the external firms supporting invigilation and monitoring of the test were expanded in September 2016 to further enhance reliability of the test. In September, 100% of schools which were not externally invigilated were monitored through a third party firm, compared to 25% previously. Test papers were delivered to the central office (Lahore) and delivered onwards to schools by a third party firm, rather than papers previously being delivered through school monitoring staff (MEAs).

The combined score across all three subject areas continued to improve in government schools – there was an improvement of three percentage points between September 2015 and 2016. A higher proportion of students scored in the high marks range (> 67% correct answers). Government schools are closing the performance gap with low fee private schools. Compared to 2015, Urdu and mathematics results in government schools have improved, while English results for both government and PEF schools are flat or slightly declining. More formative use of six-monthly assessment results is necessary to drive improvements in learning. Specific subject related feedback should be provided to schools and teachers along with support/materials to improve teaching and learning.

Output Indicator 2.3: A – Milestone met
This indicator tracks improvement in examinations. The milestone for this year has been met. Punjab Examinations Commission (PEC) is engaged in an ongoing multi-year reform process to improve the content and conduct of its examinations and to establish a reliable assessment of student learning achievement for the end of primary (Grade Five) and middle school (Grade Eight). PEC has made considerable improvements in test conduct and marking. 2015 reform efforts have improved examination quality, administration, marking processes, and measures to reduce misconduct. Irregularities in the 2016 PEC exams were minimised to 2.78% (Third Party Verification reports) down from 5% in the 2015 examination. Other key improvements include introduction of on-line management systems, external monitors, marking centres adopting syndicated marking methods, and PEC monitoring them in districts and a better re-marking process with a larger sample to improve representation of the population to strengthen the reliability of findings.

PEC is also working on further improvements to test design, with support from TAMO, focusing on question development and test construction. Compared to 2015, question development was more rigorous, with broader field testing and experienced question writers; test construction procedures were clearly defined; and subject officers effectively implemented them while designing exam papers and comparing difficulty levels across versions. More effort also needs to be put into strengthening PEC’s research and analysis wing to provide more in-depth analysis of exam results along with actionable recommendations to improve teaching and learning outcomes. This is an area that TAMO should focus on, providing additional support in analysis, reporting, dissemination, and use of test results.

Output Indicator 2.4: B – Milestone not met
This indicator tracks the quality and delivery of the continuous professional development (CPD) of teachers by DSD including support for teachers provided through District Teacher Educators (DTEs). This year’s milestone for DTE attendance has not been met. There are approximately 1,000 DTE vacancies which SED does not plan to fill, and this diminished workforce means DTEs could not cover the target percentage of schools. 85.9% of schools were visited by a DTE against a target of 92% (January to December average). Student performance on the six-monthly assessment is a proxy measure for training quality. This was set as the 75% Roadmap target for March 2018 and there has been some progress towards this, as described for Outcome Three.

The role of DTEs has changed over the last year and continues to evolve. DTEs are now engaged in SED’s quality drive, which means they spend two consecutive days at two schools to provide intensive coaching to teachers, in addition to their routine visits to schools. The SED is phasing out the DTE role and replacing it with the Assistant Education Officer (AEO) role by March 2017. The logframe will need revising to reflect this reform.

Output Indicator 2.5: A - Milestone met
This indicator tracks teacher attendance rates in government schools. This year’s milestone has been moderately exceeded. Teacher attendance was above 93% in most months, with the 12 month rolling average also showing a consistent upward trend. Based on a rolling average from Jan to Dec 2016 the overall teacher attendance rate is 93.5%. This has gone up from 92.7 % last year. Average teacher presence is above 91% in all districts. Only five out of 36 districts have an average teacher presence rate lower than 93%. Authorised teacher absence (which is mainly due to teachers being on training or assigned to other duties) is 0.7%. The remaining 5.8% is unauthorised. Monthly school monitoring, along with a strong accountability regime, has led to the overall improvement in teacher attendance rates.

Output Indicator 2.6: A – Milestone met
This indicator tracks the percentage of stand-alone primary public schools with a student/teacher ratio (STR) of less than or equal to 35:1. The STR of 35 students to one teacher takes into account the fact that minimum levels of multi-grade teaching will persist in the system, despite reform efforts, and that a single teacher classroom environment can still operate effectively for smaller class sizes. This is a new indicator introduced in October 2016. A baseline of 45.5% was set in December 2016. Annual milestones and a target for this indicator will be established against the baseline.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation 2015/16 Annual Review	Progress
TAMO should provide technical expertise to DSD to strengthen the current teaching and learning model/approach that will enhance learning outcomes of children and rebalance emphasis from monitoring to actual coaching/mentoring.	Professional development days are still generally seen more as a measure of teacher capacity and are not considered adequate for teacher coaching and mentoring. TAMO is working with SED to redefine the scope and implementation arrangements for DSD’s teacher induction programme and the in-service teacher training programme. TAMO is also planning support for DSD capacity and institutional strengthening.
TAMO should continue to develop linkages between the different assessments conducted at various intervals and strengthen the feedback system, particularly with DSD, so that results are incorporated into teacher training and CPD.	TAMO has worked with DSD to align the content of the monthly DSD assessment so that it is consistent with monthly curriculum progression. The DSD assessment for Grade Three is already well-aligned with SLOs assessed in the six-monthly assessment. The monthly LND tablet-based assessment also comprises a sub-set of the basic literacy and numeracy SLOs assessed in the six-monthly assessment. Finally TAMO is working with DSD to implement process mechanisms to use the student-level data generated through the monthly assessment and feed the results back to teachers / DTEs to inform coaching and training content. TAMO plans to transition monthly assessment to PEC.
PEC should complete an institutional development plan or a needs analysis with the support of international expertise (discussions have started with Cambridge Examination and Assessment Board) through TAMO.	PEC has completed an institutional needs assessment and has defined priorities for institutional strengthening. TAMO is in the process of sourcing expertise to support PEC’s institutional development plan. TAMO is also working with external parties (Cambridge Examinations, Agha Khan University Education Network) to source assessment-specific trainings for select PEC staff as part of the institutional development plan.

Recommendations
- TAMO to ensure effective application of the new textbook development and review guidelines as PCTB continues to review and revise textbooks itself for other subjects and grades.
- SED, DFID and TAMO to explore options for introducing regular formative assessments to provide feedback to schools and teachers in specific areas of learning, along with support/materials to improve teaching and learning outcomes.
- PEC to strengthen its research and analysis wing and develop guidelines, standard operating procedures and training for the conduct of exams where these are missing. TAMO to provide additional support in analysis, reporting, dissemination and use of test results.
- TAMO to support SED to review teacher CPD and training including DSD’s future role and strategy.

Output Title	High quality school infrastructure
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Y (increased from Medium to Major to reflect need to increase pace of construction to meet end targets)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone 2016/17	Progress
3.1 Improved availability and functioning of basic school facilities (toilets, boundary wall, drinking water, electricity) in all districts	Every district has all facilities functioning >95%	B: Milestone not met / 97% of facilities functioning on average across Punjab (Dec 2015-Oct 2016 average). Three out of 36 districts do not have 95% of all facilities functioning: Rahimyar Khan, D.G. Khan and Rajanpur
3.2 Schools provided with improved infrastructure through provision of additional classrooms, washrooms and missing facilities, through Humqadam	a. New classrooms built: 550 / b. New toilet cubicles built: 270	A: Milestone met / New classrooms built: 570 / New toilet cubicles built: 310 / (January-December 2016)
3.3 School Councils (SCs) and Community Committees for School Infrastructure (CCSIs) are established and strengthened for construction supervision and school infrastructure maintenance in focused districts.	600 SCs and CCSIs (school communities) engaged and formed	A+: Milestone exceeded / 1,216 CCSIs engaged and formed
3.4 Construction supervision/site visits conducted by IMC engineers to check quality of work (infrastructure)	16,000 visits conducted by IMC engineers/supervisors	A+: Milestone exceeded / 27,275 visits conducted by IMC engineers/supervisors

Key Points
This output tracks the quantity and quality of school infrastructure in Punjab. It supports the provision of new and rehabilitated classrooms and essential facilities (classrooms, toilets, boundary walls, electricity, and water). It also supports the systems to ensure infrastructure is maintained in good condition. Progress under this output this year has met expectations, although milestone 3.1 has been narrowly missed.

Output Indicator 3.1: B - Milestone not met
This indicator tracks the provision and functionality of basic school facilities in all districts of Punjab. This year’s milestone has not been met, albeit narrowly missed. There has been continuous improvement of functioning facilities since 2011 and this trend has continued over the last year. Boundary walls, drinking water and toilets have exceeded the 95% target in all districts, with water in particular averaging 99.6% functionality. The biggest challenge has been on electricity. Three districts - Rahimyar Khan, D.G. Khan and Rajanpur - have not met the milestone target because schools lack access to electricity. SED are in the process of addressing this, with about 6,300 contracts tendered for missing facilities in ten districts.

The definition of functioning should be clarified: missing facilities are different to non-functioning or insufficient facilities and the new schemes to address missing facilities may not be addressing those which are in place, but non-functioning or insufficient (e.g. an insufficient number of toilets for the number of students enrolled). While addressing the issue of remaining missing facilities, DFID should encourage the GoPb to include universally accessible and disability-responsive school infrastructure such as good lighting, handrails and ramps. The impact of improved and more accessible infrastructure and facilities on student enrolment, retention and learning outcomes should also be analysed through the planned performance evaluation. The number of children with disabilities in government schools in Punjab is unknown owing to lack of identification and data. However, the Pakistan Annual Status of Education Report (ASER) 2015 report found that out of 60,000 children surveyed in 36 Punjab districts, 900 (1.15%) had some kind of difficulty. Of these, 75% were enrolled in schools, predominantly government-run. Under an inclusive education pilot project, the GoPb’s Special Education Department (SpED) has installed ramps, accessible washrooms and handrails in 270 mainstream government schools and 192 PEF schools. However, there is still a need to ensure schools are accessible to all, including people with disabilities.

Output Indicator 3.2: A - Milestone met
This indicator tracks the number of schools provided with improved new/rehabilitated classrooms and toilets by DFID’s contractor IMC. Construction began in 2016 and the previous annual review reported slow progress in the start-up phase. This year’s milestone of 550 classrooms and 270 toilets constructed has been met, although targets were low and pace of construction needs to significantly increase to meet end targets. Across 130 schools, 570 classrooms and 310 toilet cubicles were constructed between January and December 2016. This includes 255 classrooms and 214 toilets in 18 schools categorised as dangerous[7]. The number of classrooms forecast to be built by IMC each quarter over the previous year was overestimated. IMC’s forecasting accuracy and pace of construction have improved significantly over the last six months as the programme has become more established. Few of the classrooms planned to be built in the first six months were completed (none of the 210 planned from January to March 2016 was built, and only 26 of a planned 1,000 classrooms were built in April to June 2016). However, between July and December, 544 of the 584 classrooms forecast to be built were constructed. 143 classrooms were also reported to be completed in January 2017.
[7] ‘Dangerous schools’ are defined as the schools identified by the GoPb as having at least one existing block which is structurally dangerous. These blocks were subsequently demolished by the GoPb.

The independent third party verification (TPV) organisation, Halcrow Pakistan, reports on a sample of IMC sites to verify progress. Halcrow’s reports from both rounds of inspection at 40 different sites highlighted a need to have a detailed work plan for this programme, as well as issues with construction delays and monitoring by IMC technical teams. It is currently difficult to know when schools, packages and phases start and end construction, as targets and results have tended to be reported against different benchmarks, which means it is hard to see where slippages may have occurred. Any delays to completion of construction should be assessed to confirm whether they are due to poor performance and risk management by the contractor or IMC; or whether time extensions are legitimately needed. IMC should use their on-line management system and other tools more effectively to highlight issues which may cause delays to the forecast outputs and create more realistic output forecasts. IMC should submit its construction schedule to DFID on a monthly basis, indicating potential alterations or slippages which should be reviewed by a third party. DFID should monitor this to ensure effective risk mitigation. If corrective action needs to be taken to make up time, the TPV firm should be informed to monitor implementation of this (e.g. through double shifts or extra workdays).

A representative from the TPV firm should be present at the final inspection of as many schools as possible to verify the infrastructure quality and disability provision on behalf of DFID. This should be included in the TPV contract.

Output Indicator 3.3: A+ - Milestone exceeded
This indicator tracks the level of supervision of construction and school infrastructure maintenance by SCs and CCSIs. This year’s milestone has been exceeded. Assessment of this should be enhanced to include a qualitative dimension that measures the level of involvement, effectiveness and satisfaction amongst SCs, CCSIs and students. IMC reports conducting focus groups discussions with the community with positive results. IMC should review designs for future schools based on feedback from students, teachers, SCs and CCSIs. Issues should also be passed to the TPV firm and included in their checks, where appropriate. IMC has conducted some training for SCs and CCSIs on equipment and infrastructure care to ensure they are aware of their responsibilities for maintenance. DFID and the TPV firm should check this guidance and training have been provided to a good quality when they accept new constructions.

Output Indicator 3.4: A+ - Milestone exceeded
This indicator tracks construction supervision conducted by IMC. This year’s milestone has been exceeded. In 2016, IMC established a new database which allows analysis of progress and quality in individual school construction sites. Going forward, data on IMC visits should highlight errors identified in time, cost, quality and safety; and subsequent improvements made. There should be more visits to monitor works on sites where errors have been identified. The TPV firm completed high-quality reports in 2016 on the basis of one visit per construction site highlighting a wide range of issues such as non-compliance with design codes, quality of works and document control. To ensure due diligence and continuous improvements on-site, IMC should respond to the issues in these reports and implement an action plan based on the recommendations. This should be submitted to DFID and the TPV firm. The TPV firm’s terms of reference should be reviewed and upgraded to include follow-up and multiple visits to sites to ensure correct implementation of action plans, continuous improvement and progress on quality issues.

This logframe indicator should be replaced by a more appropriate indicator of construction quality. This could be based on non-compliance reports and subsequent rectification of issues; or the number of schools accepted by the third party as compliant with quality.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation 2015/16 Annual Review	Progress
DFID should maintain close scrutiny of the school infrastructure component to reduce risks of any further cost escalation and time delays and ensure high construction standards are met.	Scrutiny has increased over 2016. DFID receives weekly progress updates from IMC and carries out regular school visits. DFID is monitoring the scope of work and costs closely, and has hired a third party consultant for validation and to assess pace and quality of construction. Two rounds of TPV have been carried out. IMC has also implemented a management information system which provides real-time updates on progress.
Given the challenges around achieving milestones in all three indicators, DFID should raise the risk rating and take/continue corrective action relating to delivery of this component, as well as the potential reputational risk of being perceived to under-deliver for GoPb and the implied weakened (though continuing) case for the VfM of this intervention	DFID continuously reviews the delivery risks as part of the overall PESP II risk review process. DFID has put in place mitigation measures to address delivery risks around this component. A Steering Committee has been established with representatives from GoPb, IMC and DFID, to improve communication between stakeholders and protect reputational risk.
Consider further action to address missing facilities in DG Khan and Rajanpur or revise milestones to reflect that significant improvements from this point are unlikely.	This has not been addressed. However, missing facilities in DG Khan and Rajanpur have improved since 2011 and Rajanpur has shown some improvement in 2016. SED is working on providing missing facilities to ten districts (including DG Khan) through grants to sub-departments.
DFID to provide ongoing liaison and coordination support between IMC and TAMO/GoPb to avoid further delays due to duplication of planned works.	A Steering Committee has been established to improve coordination between GoPb, IMC and DFID. The Steering Committee meets quarterly to discuss issues and progress.

Recommendations
- DFID to discuss issues around electricity functionality in schools with SED and prioritise achieving the 2018 Roadmap goals in Rahimyar Khan, D. G. Khan and Rajanpur.
- DFID to review and upgrade the terms of reference for the school construction TPV before the contract is re-tendered, to enable increased monitoring and assurance of construction timeframes, cost, quality, safety, accessibility and implementation of action plans.
- IMC to present maintenance plans and evidence of school council/student/teacher training to DFID to demonstrate how maintenance will be provided.
- DFID to review milestones for the classrooms built and toilets built; indicators to reflect the rate required to complete construction on time and revise the supervision indicator to enable assessment of construction quality.
- DFID to strengthen quarterly monitoring of construction with addition of new infrastructure adviser
Output Title	Improved access to schools, especially in priority districts
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N (updated to align with DFID risk framework)	Impact weighting % revised since last AR?	Y (reduced from 30% - Impact weighting changed to accommodate new outputs)

Indicator(s)	Milestone 2016/17	Progress
4.1 Additional children enrolled in priority districts pilot	32,000 OOSC enrolled in new schools in 2 priority districts (Rahimyar Khan and Muzaffargarh)	A: Milestone met / 31,775 additional OOSC enrolled and retained in 2 priority districts[8]:
4.2 Number of children in school supported through the PEF (cumulative) i) EVS ii) NSP iii) FAS	PEF April 2017 targets: / (​i) EVS - 429,724 (236,348 Boys,193,376 Girls) / (ii) NSP - 193,788 (106,583 Boys, 87,205 Girls) / (iii) FAS - 1,726,488 (949,568 Boys, 776,920 Girls) / Total: 2,350,000 students	A: Milestone on-track to be met (based on progress April-Dec 2016) / (i) 355,211 (159,662 Girls, 195,549 Boys, (484 with disabilities) / (ii) 186,917 (81 with disabilities) / (iii) 1,608,735 (733,624 Girls, 875,111 Boys, (164 with disabilities) / Total: 2,150,863 students
4.3 Number of children supported through Punjab Inclusive Education Programme (PIEP) (cumulative)	Government schools pilot: / Teachers trained: 7,751 / Children enrolled: 9,448 (50% female) / Infrastructure improvement: 270 schools	C: Milestone not met / Teachers trained: 10,674 (48% female, 52% male) / Children enrolled: 2,116 (946 newly enrolled, 1,170 already going to school identified as having mild/moderate disabilities - 46% female, 54% male) / Infrastructure improvements: completed in 249 schools, in process in 21 schools
4.4 No of (i) tertiary level scholarships for poor and able students (boys: girls) (ii) higher secondary scholarships for poor and able girls per year.	(i) 100 (Autumn 2016) ii) 7,500 (2016/17 academic year)	A: Milestone met / (i) 109 LUMS tertiary scholarships (27% female, 73% male) / (ii) 7,250 PEEF higher secondary scholarships for girls
[8] PwC TPV report May 2016

Key Points
This output tracks support to the GoPb, PEF, civil society organisations (CSOs), PEEF and LUMS to improve equitable access to education for targeted groups. Overall, progress under this output has met expectations, although there have been challenges delivering inclusive education for children with disabilities. The impact weighting for this indicator has changed since last year to accommodate the inclusion of the new Outputs Five and Six and consolidation of equitable access activities under Output Four.

Output Indicator 4.1: A – Milestone met
This indicator tracks enrolment of OOSC through a pilot in four of Punjab’s 11 lowest-performing priority districts[9]. The milestone for this year has been met. The pilot was carried out in four districts (Rahim Yar Khan, Muzaffargarh, Bahawalpur and Bahawalnagar) from March 2015 to March 2016 to test a variety of approaches and implementation strategies for enrolling OOSC. Between January and March 2016, BRAC and Ghazali Education Trust enrolled and retained an additional 31,775 OOSC in two priority districts (Rahimyar Khan and Muzaffargarh). BRAC set up 700 schools in Rahimyar Khan, consisting of one classroom, one teacher and thirty students, and enrolled 21,000 OOSC (64% female, 36% male). GET set up 192 schools in Muzaffargarh, and enrolled 10,775 OOSC (49% female, 51% male). Data is not available for the number or proportion of children with disabilities or for children from minority backgrounds. In addition, Strengthening Participatory Organisation focused on addressing demand-side issues around access, attitude and finance in Bahawalpur and Bahawalnagar districts, working with communities to encourage families to send their children to school and providing Rs.200 per child to parents to contribute towards non-fee costs of education (e.g. uniforms, transport).
[9] Lowest-performing in terms of the number of children out of school and learning outcomes in-school children achieve

While the interventions appeared successful, a TPV study found that it was difficult to attribute demand-side enrolments to the partner. Partners had restricted leverage with schools after students were enrolled; there was limited oversight of attendance, retention and quality of education; and there were concerns around the effectiveness of student targeting. The study also found that working through PEF enabled greater government ownership, as well as local acceptance and sustainability. CSOs had limited capacity to mobilise and implement within the agreed timeframe and BRAC’s one-room school model was incompatible with PEF’s larger formal school model. PEF and TAMO lacked capacity to provide the necessary monitoring, oversight and support to schools. There was also a lack of accurate and up-to-date data on OOSC and schools. Using the learning from the pilot, DFID will work directly through PEF’s NSP and EVS to enrol an additional 150,000 OOSC across all 11 priority districts to achieve better value for money and strengthen sustainability for enrolling OOSC. DFID will also consider other options to enrol more OOSC in priority districts through CSOs and the private sector.

Output Indicator 4.2: A – Milestone met
This indicator tracks the number of children from poor households who are supported to attend government-funded low fee private schools through Punjab Education Foundation (PEF). PEF has made good progress towards its April 2017 enrolment targets (as set out in its expansion plan) and is on-track to meet enrolment targets for this April 2017. As of the end of December 2016, PEF had enrolled a cumulative total of 2,150,863 students in 6,736 schools through its EVS, NSP and FAS programmes across the 36 Punjab districts against a target of 2,350,000 children. The number of children supported through PEF has increased by around 290,000 overall since the last annual review in January 2016. PEF will need to enrol an additional 150,000 children at the start the new academic year to reach the April 2017 target. The GoPb increased its allocation to PEF from Rs. 9.8 billion for FY 2014/15 to Rs. 12 billion for FY 2016/17. This was further increased in the November 2016 Stocktake meeting by an additional Rs. 8 billion.

A key challenge for PEF’s expansion is to ensure the right schools are set up in the right places to be able to enrol and support OOSC. Although PEF has a student database which reflects movements between government and PEF schools, and between PEF schools, PEF could still do more to strengthen its focus on targeting specific groups.

Output Indicator 4.3: C – Milestone significantly missed
This indicator tracks the effectiveness of a new approach to inclusive education that enrols and supports children with mild disabilities in mainstream government and PEF schools in priority districts. This is an innovation for SpED and SED; and it is the first government programme of its kind in Pakistan. This year’s milestone was not met. In 2016, the pilot exceeded expected targets for teacher training and is on-track to meet targets for improving school infrastructure. However, targets for screening and enrolling children with mild disabilities in mainstream schools in Bahawalpur and Muzaffargarh districts were missed significantly.

7,551 children were screened for disabilities. Out of these, 946 out-of-school children with mild disabilities (44% female, 56% male) were reported by the Project Implementation Unit (PIU) to be enrolled in mainstream schools (although only 523 have been physically verified), and 1,170 in-school children were provided with additional support against a target of 9,448 children enrolled. 1,179 assistive devices (wheelchairs, crutches, hearing aids, spectacles) have been procured and 192 distributed so far. Out of the enrolled students, 78% are still in school.

Similar interventions were conducted under the PEF inclusive education voucher scheme pilot implemented in 132 low fee private schools in seven districts in Punjab.[10] An additional monthly Rs. 400 voucher was provided to schools for each child with disabilities enrolled. Teacher training on inclusive education was conducted for 268 teachers, and orientation on inclusive education was conducted for 202 school owners/headteachers. Out of 1,241 children assessed, 730 were identified as having disabilities, with 68 OOSC newly enrolled and 662 in-school children provided with additional support. At the current pace, PEF is likely to significantly missed the target of newly enrolling 5,404 children with disabilities into mainstream schools, and supporting 2,572 children with disabilities already in school by July 2018. 170 assistive devices were procured in 2015/16. In 2017 PEF plans to train an additional 346 teachers in 74 schools.
[10] Lahore, Multan, Vehari, Attock, Jhelum, Chakwal, Rawalpindi

As a result of low levels of enrolment, DFID is working with SpED and TAMO to redesign this component and increase its impact. Through TAMO DFID will commission evaluations of both pilots. DFID and TAMO will support the SpED to understand best practice and evidence around education for children with disabilities; review and strengthen their education sector plan; develop a strategy and institutional strengthening plan and design the next phase of the project. SpED has expressed strong commitment to continuing to implement inclusive education alongside existing provision in special schools.

Output Indicator 4.4: A – Milestone met
This indicator tracks support for young people from poorer households to access higher secondary and higher education. This year’s milestone targets have been met. During the 2016/17 academic year, PEEF awarded 7,250 intermediate-level scholarships to female secondary school students in the 11 priority districts in Punjab, out of an intended target of 7,500 scholarships. In autumn 2016, LUMS awarded 109 new tertiary scholarships to young people (27% female, 73% male) under the NOP scheme, which exceeded the target of 100 scholarships.

20% of PEEF scholarships are allocated to a special quota for orphans, children from minority religions, children with disabilities and children of low-paid government workers. Since 2013/14, DFID has supported a total of 33,584 PEEF scholarships for female students in the 11 Priority Districts (33,086 at intermediate and 498 at graduate level). This significantly exceeds the original end target of 28,000 scholarships to be awarded by 2018. DFID has supported 25% of PEEF scholarships awarded, and has provided 16% of scholarship disbursements since 2013/14. PEEF will award the final batch of 500 DFID-funded scholarships to graduate students in seven centres of excellence in 2017. PEEF expects to be able to award over 34,000 scholarships by the end of 2017/18 with DFID funding. Targets have been consistently exceeded as scholarship allocations are estimated based on the assumption that around 7% of students will go to boarding schools (and receive a higher amount to cover accommodation). A lower percentage of students have required boarding school as an option, resulting in more scholarships to attend day schools at lower cost. PEEF estimates that only 1% of scholarships have been cancelled owing to migration, dropout or poor performance. The CM chairs the PEEF board, and in 2016 PEEF launched the Shahbaz Sharif Merit Scholarship (SSMS) for 1,000 Master’s and Ph.D. level students.

DFID provides financial aid for high-need students at Lahore University of Management Sciences (LUMS) to undertake two years of tertiary education through the LUMS National Outreach Programme (NOP) and funding for the NOP centre. In 2016, 109 students (27% female, 73% male) categorised as high-need were awarded LUMS scholarships with DFID funding. To date, 731 high need students have been provided with DFID-funded scholarships. Currently, 448 continuing and new high-need students (73% male; 27% female) are being supported by DFID, constituting about 63% of the 706 high-need students at the university. The majority of students are from Punjab, Khyber Pakhtunkhwa and Sindh provinces, with a minority from the other geographical areas in Pakistan. TAMO has supported LUMS to make the student experience more meaningful and rewarding (e.g. conducting a four-day training for scholars on career development, life-maps of turning points which influenced their path to LUMS, and self-reflection, to enable them to act as Education Ambassadors on outreach visits to government and lower-cost private schools). TAMO also introduced an NOP internship programme, matching applicants to placements which would provide professional experience and career mentorship which they may not gain from home. Out of 50 applicants, 41 NOP students were selected for internships in development sector organisations and seven have completed their placements to date.
 Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation 2015/16 Annual Review	Progress
DFID should step up its engagement with PEF commensurate with emerging risks around capacity and scale-up and work closely with TAMO to re-energise its technical assistance to PEF.	DFID has increased its engagement with PEF over the past year, including through conducting a review through DFID Pakistan’s Portfolio Risk Assurance Programme (PRAP) which assessed PEF’s capacity. An action plan was agreed with PEF, and satisfactory progress has been made on governance, HR, procurement and asset management risks. Further work is needed to reduce risks around programme and financial management, and monitoring and evaluation. TAMO has shared all PEF’s strategies and plans with DFID, and tailored PEF’s institutional strengthening plan to be more risk-sensitive and respond to recommendations from DFID’s PRAP.
DFID should continue discussions with PEF and other GoPb stakeholders on teacher pay in PEF schools To inform these policy discussions, DFID might need to support further work in the sector to improve understanding of the possible impact of paying higher wages on labour market dynamics and the sector	This is an ongoing area of engagement for DFID with PEF. DFID has undertaken research into the teacher labour and wage markets in Punjab.
Scale up the LUMS summer coaching session and explore the possibility of a special summer coaching session specifically for DFID-funded higher secondary girls (PEEF) programme.	LUMS has scaled up its summer coaching session. A special summer coaching session specifically for PEEF female students was discussed but not set as a deliverable. However, PEEF students were encouraged to apply to the regular NOP coaching session. In 2017 LUMS plans to include 500 DFID-supported PEEF female students in the NOP summer coaching session, and have sent them application forms.
Consider whether DFID funds should only be used for those who need 100% LUMS scholarships, or whether to continue fund partial scholarships. Activities to encourage more applications from the neediest should be considered, perhaps through a reallocation of funds and a greater emphasis on outreach. These could include a foundation course to bring students up to standard, focusing on the neediest and on girls.	As a result of resource allocation and spending review discussions, DFID decided it will only fund students needing 100% scholarships for LUMS, with the grant wrapping up, on schedule, in August 2018. Over the past year, LUMS NOP centre has expanded the focus of its outreach to encourage more young women and students from northern and more remote areas to apply for its summer coaching sessions (and subsequently for NOP scholarships); and is providing more pre-entrance preparation.
Conduct a study of the economic and social returns of the LUMS and PEEF scholarships, capturing the income and non-income benefits including reasons for beneficiaries of the intermediate scholarships (PEEF) not progressing to higher education.	This was not carried out in 2016, but will be part of the wider evaluation of PESP II in 2017. In 2016, LUMS and PEEF conducted some independent studies into the economic and social returns of their scholarship programmes (covering effects on income, employment and further education). LUMS and PEEF should continue to strengthen research and evaluation in 2017, and analyse the impact of scholarships on different groups.
DFID should review LUMS NOP scholarships programme to improve its focus on gender and the most disadvantaged.	DFID reviewed LUMS’ approach to gender and the most disadvantaged within the LUMS NOP scholarship programme for this annual review. LUMS has made some improvements in attracting the most disadvantaged, but needs to continue to strengthen its outreach and support to girls and other less privileged students to have a transformational effect. DFID is working with PEEF and LUMS to provide additional coaching to girls with PEEF scholarships, to enable them to apply to LUMS for further studies.

Recommendations
- PEF to improve its strategy for targeting the enrolment of OOSC children in priority districts.
- DFID to consider options for additional work with CSOs and the private sector to enrol more OOSC, particularly in priority districts.
- TAMO to step up technical assistance to PEF for strengthening monitoring and evaluation and mitigating risks.
- DFID and TAMO to support SpED to redesign the inclusive education component.
- LUMS to continue to strengthen equitable and representative enrolment onto its NOP scholarship programme (for female students, students with disabilities and those from more remote areas).

Output Title	Top political leadership engaged on education reform agenda in the Punjab
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y (new output)	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestone 2016/17	Progress
5.1 Number and effectiveness of pre-stock take and stock take meetings	(i) 4 formal stocktake meetings (ii) Frequency of pre-stocktake meetings and routines versus plan, specifically: / 1- Quarterly pre-stocktakes with the Chief Secretary / Additional Chief Secretary / Chairman Planning & Development / 2 - Monthly review with Secretary School Education Department / 3- Monthly Roadmap update to Chief Minister, minister and senior officials on progress and key actions	A: Milestone met / 4 formal stocktake meetings have taken place with the Chief Minister, and new pre-stocktake routines have been carried out as planned. In addition to these routines a pre-stocktake meeting has been held with the Minister of Education. 3-monthly update notes since September.
5.2 Quality and use of Roadmap products	Policy documents produced for the SMU and SED with help from the Roadmap team, and in use	A: Milestone met / 4 stocktake packs; 6 deep-dive documents on priority areas; 11 weekly meetings with SED leadership; 7 best practice sharing sessions

Key Points
This is a new output added to the logframe since the 2016 annual review. It has been added to track DFID’s contribution to the Roadmap process. The purpose of the Roadmap is to maintain engagement from the most senior political and civil service leaders to drive education reform in Punjab. Progress is tracked by collecting data against 13 indicators. Quarterly Stocktake meetings chaired by the CM report progress against goals and are used to flag key decisions that are required to keep the Roadmap on track. In November 2016, 11 of the 13 indicators showed an increase against the same quarter in 2015.

Output Indicator 5.1: A – Milestone met
This indicator tracks the effectiveness of the Roadmap pre-stocktake and stocktake meetings. This year’s milestone has been met. DFID funds McKinsey to manage the Roadmap process and stocktake meetings. A separate contract has been signed with Delivery Associates for DFID support to the CM’s Special Monitoring Unit (SMU), the independent government monitoring body helping the CM to track progress of the 2018 education goals and coordinate reforms across Punjab. A review of the Roadmap in June 2016 found that the ‘roadmap has driven considerable progress over the last several years. The data underpinning the roadmap are sound and the stocktake process continues to send a strong signal that education is a priority for government.’[11] The challenge identified was the implementation of the reforms to deliver the Roadmap goals. The review noted that although there is progress against indicators, the trajectory needs to increase in some areas, notably enrolment and learning. After aligning with the CM on this perspective in the July stocktake, the Roadmap launched a set of new routines (pre-stocktakes with the Chief Secretary, weekly meetings, a monthly note to the CM , Monthly Roadmap Data Review) to drive increased government ownership and engagement in the reform effort. These worked well for the November stocktake, which the CM noted was a success, and which resulted in increased financing for PEF to increase enrolment; and renewed impetus on initiatives to improve teacher and teaching quality.
[11] Delivery Associates 2016 Punjab Education Roadmap Review Findings p3.

Output Indicator 5.2: A – Milestone met
This indicator tracks the quality and use of Roadmap products. This year’s milestone has been met. Roadmap products have had an impact on priority areas of the Roadmap: teaching quality and enrolment and access. The documents associated with the six-monthly assessment formed the basis for the government's Literacy and Numeracy Drive (LND) test. The test, and the analysis of its results, act as an independent monthly barometer of performance. The launch of the expanded LND included new SLOs, an expanded bank of questions, a new algorithm for the test and the incorporation of scores into the monthly data packs for district officials. This is a key lever for driving improvements in literacy and numeracy scores and was rolled out across the province in December 2016. An analysis of performance in English language using six monthly assessment data is being used by SED and TAMO to design new training for teachers to accelerate students’ progress in English. Roadmap documents on enrolment have resulted in the design of two enrolment pilots and the expansion of the girls’ secondary stipend programme with an increased value for the stipend. They will also be instrumental in designing the government's enrolment plan for the next academic year to achieve the 2018 goal.
Summary of responses to issues raised in previous annual reviews (where relevant):
Recommendation 2015/16 Annual Review	Progress
DFID must ensure that the Roadmap stocktakes continue to drive improvements and continued buy-in from key stakeholders	The refresh of the Stocktake goals and new routines along with the CM’s continued leadership has increased the vigour of the Roadmap process.
The plan to transition the Roadmap to the GoPb’s SMU should be implemented.	The delay in appointing a new head of the SMU means that this transition is only just beginning.

Recommendations
- DFID to work with the Roadmap team, SMU and other key GoPb stakeholders to clarify which functions will transition to the SMU and the process by which this will be achieved.
- Roadmap team to engage at an early stage with DFID for technical support and quality assurance on key education solutions as part of the problem solving process.
- SED, DFID and Roadmap team should ensure the coherence between delivering the 2018 Roadmap goals and planned reforms and interventions. The upcoming SED, DFID, TAMO and RM strategy workshop provides the first step to ensure improved coherence.
- DFID to update the PESP II logframe to ensure further alignment with Roadmap targets

Output Title	High quality technical assistance to government stakeholders that builds sustainable systems and processes
Output number per LF		6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y (new output)	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestone 2016/17	Progress
6.1 Rating of / quality and timeliness of products and programme delivery (ASI for TAMO contract)	4 - Delivery criteria being efficiently and effectively met in line with contractual and customer requirements	B: Milestone not met / 3 - Most delivery criteria being met efficiently and effectively. Few areas for improvement.
6.2 System/institutional strengthening and capacity building	4 - Delivery criteria being efficiently and effectively met in line with contractual and customer requirements	B: Milestone not met / 3 - Most delivery criteria being met efficiently and effectively. Few areas for improvement.

Key Points
This output tracks TA support provided by TAMO to the SED and SpED, GoPb and PEF. Together the two indicators provide an assessment of TA to deliver the PESP II programme and support GoPb in education programme delivery, as well as system strengthening and institutional capacity building. TAMO was assessed using the Key Supplier Management (KSM) performance review scorecard, which assesses suppliers from one to six across six performance indicators[12].
[12] KSM scoring methodology: (1) Serious delivery failure and underperformance. Immediate and major changes needed, (2) Some delivery criteria being met, however significant performance concerns and improvements needed, (3) Most delivery criteria is being met efficiently and effectively. Few areas for improvement, (4) Delivery criteria being efficiently and effectively met in line with contractual and customer requirements, (5) Proactive and innovative, delivering with superior efficiency and effectiveness above contractual expectations, (6) As score 5 and is driving industry best practice and is consistently applying this across DFID contracts.

DFID TA is currently the only TA available to the SED and provides wide-ranging support to deliver the PESP II programme and to the government to achieve reform objectives. DFID and the GoPb appreciate and recognise the value of the support provided by the TA team, and the flexibility and responsiveness of the team, but there is a general consensus that there is room for improvement across different areas of TA in PESP II. Building on the findings and recommendations of the last annual review, DFID completed a review of TAMO in November 2016 to assess how effective it has been in supporting the delivery of the programme and supporting the government and whether TA remains relevant and aligned with the GoPb and DFID’s reform objectives. TAMO responded well and effectively to the review and developed a draft strategy and management organisation plan to ensure that TA is better aligned with the emerging needs of the programme and that TAMO has a team with the necessary skills and experience to deliver high-quality TA at pace. Once the full range of improvements is implemented, a qualitative and quantitative shift in TA is anticipated.

Output Indicator 6.1: B – Milestone not met
This indicator assesses the quality and timeliness of the support that TAMO provides to the SED. This year’s milestone is not met. Coordination with the government on the TAMO work plan has improved. All key government counterparts were consulted in the finalisation of the TAMO work plan for year three. Also in year three, some workstreams have started to show better progress; for instance, the governance work stream where TAMO has provided extensive support in the development of the concept, legislation and rules for DEAs, the design of a financial management cell in SED, strengthening district performance management routines (e.g. DRCs), and monitoring budget execution. Also, the teaching and learning materials (curriculum, textbooks, teachers’ guides, teacher training modules) developed by the TAMO team are good quality and progress has remained on-track despite challenges such as litigation. Progress in some other workstreams has been slower, for instance, a DSD strategy and operational plan requested by government in early 2016. Other examples of delayed activities, expected to be completed early this year include the government’s request to develop a costed enrolment strategy; an overall assessment framework and strategy for PEC; and an overarching policy framework for the new batch of AEOs with rules and a comprehensive performance management system which will help determine the scope of AEO capacity building. Gaps in existing team capacity have also affected the quality and timeliness of programme delivery. TAMO should expedite any pending activities in year three in order to provide timely assistance to government counterparts. The timing of TAMO’s deliverables/milestones needs to be aligned with the annual cycle of important government processes, and the department’s overall planning and budgeting cycle, to deliver greater impact.

Output Indicator 6.2: B – Milestone not met
This indicator tracks TAMO’s support for system and institutional strengthening and capacity building. The milestone has not been met. The integrated support for quality led by TAMO has laid down the foundations for a good system. It focuses on improving learning outcomes, the development of quality teaching and learning materials and a range of assessment initiatives. The quantity and quality of TA provided to key government counterparts varies. Support provided to DSD and PEC in the first two years has been limited. PCTB, on the other hand, has received extensive support in the operational delivery of textbooks, teacher guides and prioritisation of curriculum. TAMO should step up its engagement with the full range of SED sub-departments and PEF to ensure that the pace and depth of TA is improved. TA activities are valued by GoPb, but are currently largely operational and reactive, rather than strategic, proactive and institutional. TAMO needs to be aligned to address the most strategic requirements of attached departments through an institutional needs assessment and prioritisation of TA support to address core institutional needs. While TAMO has provided additional capacity to GoPb, the annual review team did not find many clear examples of capacity building within government institutions more broadly. To ensure sustainability, TA should focus more on institutional strengthening support (structures, functions, systems and processes), as well as implementation support, so TAMO is building capacity and not simply replacing government capacity. A priority is for TAMO to work with relevant institutional counterparts to outline medium to long-term institutional strategies and plans for all key institutional counterparts (DSD, PEC, PCTB, PEF, and SpED), conduct a needs assessment and prioritise areas for TA. To support long-term sustainable capacity building, TAMO should explore opportunities for strengthening and making existing government systems and institutions work better, coordinate more effectively and avoid creating new structures that may be difficult to sustain beyond the life of the project.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation 2015/16 Annual Review	Progress
DFID and TAMO should ensure that that the government’s needs and DFID’s support are regularly discussed, and that the needs are properly reflected in the development of support.	TAMO Year Three work plan has been developed in consultation with relevant government departments to address reservations about supply-driven assistance. TAMO is in the process of reviewing its strategy to clearly define the future scope of TA with a clear focus on institutional strengthening. This will be finalised in close consultation with DFID and the GoPb.
TAMO should ensure that beneficiary organisations are content with the balance between generalists and technical experts in TAMO including education, equity, governance and public financial management.	Work in this area has been delayed. As a result of the DFID review in November 2016, which further reinforced recommendations made in the last Annual Review, TAMO is responding well by introducing a new team leadership and management structure and identifying and recruiting long-term technical expertise across key programme areas. TAMO has recently engaged a number of consultants to work with DSD and SpED. Recruitment of an assessment expert for PEC is still underway, which has caused delays in activities. TAMO should assign a full-time resource to work on PEF and strengthen capacity on inclusive education and equity.

Recommendations
- TAMO to expedite any pending activities, and where necessary adjust the timing of key deliverables to align with the government’s planning and budgeting cycle and processes
- TAMO to step up TA to the full range of SED departments (PEC, DSD, PCTB), SpED and PEF (in alignment with planning and budgeting processes), to strengthen their medium to long-term strategies and plans, build institutional capacity and improve coordination to support delivery of goals
- DFID and TAMO to review TA work plan to ensure that activities are strategically aligned and prioritised and aimed at strategic, institutional and system capacity-building
- TAMO to introduce evidence-based solutions, including available regional or international good practice and provide support to establish linkages/partnerships with leading global institutions

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The largest budget component of PESP II is sector budget support (SBS) provided to the Government of Punjab’s (GoPb) budget for delivery of primary and secondary education services. This financial support accounts for 40% of PESP II total programme value, with £25.5 million provided to Punjab’s education sector during the review period (Jan-Dec 2016). The level and timing of DFID’s annual disbursements depends on the GoPb’s performance against targets set in the Results and Activities Framework (RAF), which act as Disbursement Linked Indicators (DLIs) for SBS. For year two, RAF targets were set in five results areas[13]. Most of the service delivery and provision of education services is carried out at district level, with district level salaries (mostly teachers’) accounting for 71% of total sectoral expenditure in FY15/16, and 66% of budget allocations in FY16/17. The salary budget execution rate in FY15/16 was 95%, the non-salary budget execution rate was lower at 73%, and the development budget rate was 89% (with PEF comprising two-fifths of this). In FY16/17 allocations, the development budget increased to 18%, at the expense of current non-salary budget.
[13] Teaching and learning, performance management, textbooks development, strengthening PMIU and public financial management (PFM).

Direct funding to PEF, at £12 million, was the second largest expenditure for PESP II this year. This financing enables PEF to make payments to schools or provide vouchers to parents, on a per student basis. PEF’s payment per primary student is currently Rs. 550 (c. £4.25)[14]. Primary students account for 75% of pupils in PEF-supported schools. PEF payments for secondary and higher secondary students have just been revised upwards (October 2016), with the largest monthly payment being Rs. 1,500 (c. £11.50). Overall expenditure is driven by numbers of children enrolled in PEF schools. The underlying cost driver for payments is school operating costs; staffing costs account for over 70% of school revenues. DFID has engaged with stakeholders on the issue of low salaries received by teachers in low-fee private schools. The lack of long-term vacancies for teachers suggests that a market-clearing wage exists in this labour market, but DFID has encouraged PEF to develop and embed teacher certification, which would indicate teachers’ quality, and potentially raise teacher salaries.
[14] The VFM section uses an exchange rate of 1GBP = PKR 130 throughout. The PKR value of British pounds has decreased by around 20% in the latter half of 2016.

The third largest expenditure area this year was £11.5 million spent on managing and delivering school infrastructure. Previously costs had been under-estimated, with key cost drivers rising substantially. This was primarily due to changes in the proposed construction model (with the realisation that the community-led model was not feasible), so higher costs were needed for labour and building material prices. Despite rising input prices, building targets have been exceeded this year. However, this will have significant implications for unit costs and overall results.

DFID operates output-based contracts with TAMO and the Roadmap team, spending £8.5 million over the year, with payments linked to completion of planned objectives. As expected with TA support, staff fees constitute the largest cost item in their budgets. These costs are driven by staff hourly rates, the number of hours charged, and the composition of senior and junior staff. TA expenditure has been larger than initially budgeted, as the scope of the programme has evolved owing to different technical requirements to meet the increased ambition of the Chief Minister’s 2018 goals. Greater emphasis was placed on the Roadmap process and additional TA was required on several work streams including communications, district transformation, public financial management, school councils, and education quality.

DFID spent £4.1 million supporting PEEF (£2.3 million) and LUMS (£1.8 million) this year. Scholarship costs have changed little since the start of the programme and are predominantly driven by course fees and student living costs. DFID funded scholarships via PEEF cost £325 on average per scholar. LUMS scholarships cost up to £7,200 per year per student and are broken into three different categories: undergraduates on full support account for 32% of spend (students receive 100% financial support, with some receiving stipends, living and book allowances, and free hostel accommodation); undergraduates on partial support account for 27%; and graduates (tuition fees only paid) account for 28%. Management and operational costs account for over 13%. Smaller areas of spend included national outreach, research and coaching.

VfM performance compared to the original VfM proposition in the business case
The original business case proposed that VfM would be primarily achieved via PESP II’s impact on additional enrolment and improved quality of education. This expansion and improvement of education provision would produce more and better graduates who would accrue private returns - increased future expected wage earnings. The business case estimated a benefit cost ratio for the programme of 1:5. There were also greater social benefits identified, particularly through educating girls, which is strongly associated with reduced fertility, improved earning ability, child health and rates of child survival, as well as reductions in inter-generational poverty. Since then, PESP II’s scope has changed, and the estimates in the appraisal are no longer strictly comparable; particularly in the cost per student in public schools, as the business case assumed half the real annual cost that exists now. Given this underestimation, DFID financing now supports fewer students than originally planned. However, one reason for this is increased development and non-salary expenditure which should enable greater enrolment in future.

Sector budget support, influence and technical assistance
Based on an assumed Rs. 19, 200 / £148 annual per student unit cost[15], DFID will directly fund the equivalent of approximately 172,600 primary and secondary children through a year of schooling in Punjab in FY16/17 – there were 10.87 million children enrolled[16] overall, including through PEF. As SBS disbursements are linked to progress with reform, value is derived from incentivising changes that positively affect the entire education system. The extension and large increase in non-salary budget provision to all districts in Punjab has allowed schools to receive over Rs. 800,000 (£6,150) a year to cover basic needs and fund small-scale improvements and short-term staffing gaps. Previously, schools received a maximum of Rs. 20,000 (£130) a year which was far below their needs. DFID financing in 2016 will provide 1.24%[17] of the primary and secondary education FY16/17 budget. DFID’s influence through providing SBS is substantial, as demonstrated through the priority given to achievement of RAF targets.
[15] The annual unit cost per student in FY15-16 was PKR17,970 (c. £138). Calculation assumes a unit cost of PKR 19,200 in FY16-17. DFID’s share of children supported rises (and falls) with a lower (or higher) budget. . PKR 130 = £1GBP and GBP prices are quoted in current 2016 pounds. Budget allocations are similar in FY16/17, so similar unit cost assumed.
[16] This includes students of low-performing public schools outsourced to private entrepreneurs (via PEF) through the PEF’s PSSP programme
[17] Calculated as DFID’s £25.5 million support (converted at rate of PKR130 to GBP1) as percentage of SED and attached departments total allocated budget for FY 2016/17

DFID’s ability to assess the impact of SBS on institutional strengthening has improved with embedding the RAF as a key accountability framework used to track progress on priority institutional reforms and link DFID’s disbursements to achievements on key areas. DFID has exercised its right to withhold funding over the last year, delaying £7 million (25% of expected disbursement) after the first bi-annual review and still withholding £1.5 million after the final review in 2016. The RAF has defined more stretching targets for the remainder of the programme, shifting focus from process indicators (e.g. procurement and recruitment) to more stretching outcome-oriented targets such as ensuring teachers are trained on effective use of textbooks and demonstrating improvements in student and teacher attendance. The Roadmap process and its central stocktake meetings, supported by DFID, have been instrumental in driving reform and improving performance across the education sector. Teacher attendance is currently at 93.5%, well above the 90% target and a significant improvement from the 81% 2010 baseline. Student attendance has increased by 1.5% in 2016 to 91.6%. The Roadmap’s power to prioritise key areas, allocate resources and deliver greater efficiency is its key value addition, and as such the Roadmap is delivering VfM.

The desired value of TA is in supporting sustained improvements in capacity and the delivery of well-managed reforms, whilst ensuring that government feels ownership of the reform process. Currently, DFID TA is the only TA available to the SED and provides wide-ranging support. The level of TA required has expanded, given the need to support the 2018 Education Goals. This has led to a budget utilisation rate over 100% and the need for extra resource. However, the widening and deepening of scope, allied with the fact that TAMO’s initial bid represented good VfM, means we can still consider PESP II TA as good VfM. This is borne out by communications from GoPb that voiced appreciation and recognition of the value of the support provided by TA teams and their flexibility and responsiveness, although there is consensus that there is room for improvement. DFID’s recent review of TA has led to TAMO developing a draft strategy and management organisation plan to ensure TA is better aligned with emerging programme needs of the programme and a team has the necessary skills and experience to deliver high quality TA at pace.

PEF
DFID’s funding is contributing to a government-supported expansion in PEF enrolment from 1.6 million children in 2013/14 to 2.6 million for 2018. To ensure DFID funding is additional, DFID’s support is conditional on the GoPb increasing its own contributions. The government has been increasing its contribution to the PEF budget, which has allowed PEF schools (privately managed but publicly funded) to meet annual enrolment targets. There are 2.15 million students enrolled in PEF schools and the current trajectory means PEF is likely to meet its FY 16/17 target of 2.35 million. GoPb’s initial allocation of Rs. 12 billion (c. £92 million) for FY16/17 together with DFID’s scheduled financing of Rs. 2 billion meant PEF was facing a financing gap for the proposed expansion in enrolment, but this has now been reduced substantially by a restraint on primary school fees, as the original financing proposal assumed annual fee increases. DFID’s funding should support about 335,000 PEF students during FY16/17. Overall, PEF continues to be a success in increasing access to education in Punjab. Its enrolment growth rate outstrips the public sector and now accounts for 1 in every 6 students in the publicly-financed sector[18], rising from 1 in 8 since 2013/14. Advances in enrolment have been complimented with continuing growth in educational outcomes; available test scores point to greater learning in PEF schools compared to the public sector. This has been achieved with a unit cost per student (Rs. 650 per month) of less than half of the unit cost in public schools and a small fraction of the average annual expenditure[19] on a UK primary school student (over £3,000). There is still room for improvement on educational outcomes and DFID continues to stress the importance of this to all stakeholders. PEF’s value is reflected in the introduction of the new Public School Support Programme (PSSP) involving the managerial handover of low-performing public schools to PEF to improve enrolment and quality of education in Punjab in partnership with the government.
[18] This includes all public schools and PEF schools (which are privately run schools financed by public funds) at the primary and secondary education level.
[19] Rough Estimate based on IFS 2015 Schools Spending Briefing Note and previous right to information responses. Actual Spend likely to be higher once all spend of relevant authorities is included. Costs do not take into account differences in purchasing power parity.

Infrastructure
The original VfM proposition for this component was that classrooms could be built of higher quality and at lower cost than classrooms contracted through the GoPb’s own Communication and Works Department. Fiduciary risk would also be lower. Initial unit cost estimates per classroom were based on community group management of construction. The business case assumption proved unworkable and the unit cost for a classroom - between Rs. 350,000 to 450,000 - could no longer be considered valid. Based on a more traditional model (use of construction sub-contractors), the new estimates doubled to Rs. 950,000 during 2015 – remaining lower than GoPb estimates. The current per classroom estimates are Rs. 1.25 million, reflecting increases in labour and material costs. However, actual construction costs depend on school location and there have been delays in the GoPb finalising the schools in which IMC can work. Despite reduction in the number of classrooms that can be built, comparisons with GoPb infrastructure works attest to relative VfM. The latest unit cost estimates of GoPb classroom construction are around Rs. 1.8 million[20]. However, there is a need for greater clarity on government estimates, and stronger investigation into IMC’s VfM. Whilst the number of classrooms forecast to be completed has reduced significantly, the forecast level of TA required to deliver this number has only decreased slightly, and the ratio of TA per classroom has risen significantly. The reduction in site numbers (and required site visits) should allow for further reductions in TA requirements. DFID will undertake a review of IMC’s TA schedule to identify TA savings which can be re-allocated to the capital fund, so more classrooms can be built.
[20] The estimate quoted is from a Roadmap document. The actual estimate is Rs. c.2 million. We have assumed that this includes furnishing and have generously assumed a 10% reduction on this – as PESP II does not provide furnishing.

Scholarships
Expected wage earnings in Pakistan increase disproportionately for those with higher or tertiary education. LUMS graduates were found to earn around double their parents’ salary (Rs. 71,000 per month on average). Similarly, although data on the salaries of PEEF graduates was not available, the maximum annual income of a household a PEEF scholar comes from is under Rs. 25,000 (£190), suggesting that relative earnings for graduates are likely to be high. However per student costs are also higher. The trade-off is potentially more children supported at lower levels of education where individual private returns may be lower, but where the balance of economic costs and benefits to society may be more favourable. More evidence is needed to capture the effect these scholarships hope to promote, and LUMS in particular needs to continue developing its outreach to improve the equity of its programme.

Priority Districts and Inclusive Education
The Priority Districts pilot scheme to enrol OOSC through CSOs (implemented by TAMO with assistance from PEF) ended this year. DFID allocated £865,000 for the pilot, with a balance of £10 million for scale-up to the other priority districts. PEF provided CSOs with a start-up subsidy of Rs. 550 per child, and DFID provided Rs. 100 for community mobilisation and household surveys. TAMO also topped up the total budget with Rs.150,000 for community outreach and advocacy. Whilst relatively successful, following a TPV study by PwC, DFID has decided not to scale up this model. The study found the supply side intervention performed well on enrolment and could be scaled up, but showed weaknesses on the demand side and at the management level. DFID has decided to work on this objective directly with PEF, whose larger school model should bring greater value for money than the smaller-sized CSO model.

Assessment of whether the programme continues to represent value for money
PESP II continues to meet most expectations on access to education. In the review period, PESP II has covered the costs of educating around 430,000 children in Punjab (250,000 in PEF schools, 172,600 children in government schools and 7,359 scholarships). Across all components, the annual cost of educating primary and secondary students is about £96[21] - meaning a class of 30 Punjabi children is being educated for the same cost as one UK primary student. The numbers of students supported by DFID is sensitive to the depreciation of sterling, which dropped by over 20% in the latter half of the year; children are lower and unit costs higher due to this. DFID’s investment in DSD, PCTB and other agencies is helping improve the quality of education, and should enable students to gain expected private returns to education. The preceding VfM analysis suggests the majority of PESP II components are delivering solid VfM. Some components appear to have not met VfM expectations (although relative VfM has been achieved when compared to other interventions); and the infrastructure component should be scrutinised for potential VfM gains. The RAF is improving the effectiveness of budget support and driving core reforms. The robust TA review has produced new strategies that should strengthen the impact of TA, bringing synergy to the heart of the intervention.
[21] Weighted average calculation: The PKR 650 cost per month for PEF students (59% of DFID supported primary/secondary student) and the larger cost for government schools (41%).

Quality of financial management
All components are delivered through different arrangements depending on partners’ needs, and require different reporting and tracking mechanisms. The PESP II programme spend during 2016 has been broadly in line with forecasts, although adjustments are made on a quarterly/monthly basis.

Sector budget support is the largest component of the PESP II programme. Annual disbursements are made after a thorough assessment of RAF targets agreed between DFID and the GoPb. In 2016 there were two rounds of RAF assessments, one in June and one in November. Based on the first RAF assessment, DFID released £20 million to SED out of the £27 million allocated for 2016/17. This comprised £18 million based on delivery against the five result areas agreed for 2016/17, and £2 million based on progress against two outstanding areas from 2015/16. £7 million of the £27 million for 2016/17 was withheld largely due to slow progress in two areas. Following the second RAF assessment in November, DFID released a further £5.5 million out of this year’s allocation following achievement of most of the targets. DFID, SED and its allied departments have jointly reviewed and revised the RAF for the remaining years of the programme, to shift focus from process indicators to more stretching outcome-oriented targets.

DFID supports and tracks improvements in public financial management (PFM) through the RAF. Over the past year the GoPb has shown substantial improvements in PFM, including shifting to multi-year budgeting statements for 2016/17 for the first time; budget utilisation dialogue at Secretary level; and better fund allocation to school education. This enabled SED to utilise 90% of its budget allocation for 2015/16, which suggests improvements in SED’s planning and budget execution in recent years (utilisation has marginally increased from 89% in 2014/15). To strengthen financial management capacity in SED, DFID has supported the establishment of a financial management cell. DFID is funding this for the first six months and SED will take over costs from June 2017.

In November 2016 DFID released £12 million to the GoPb to allocate to PEF, out of a £18 million allocation for 2016/17. DFID plans to release another £3 million in February 2017 but is withholding the remaining £3 million due to the slow release of funds from the Finance Department; £12 million disbursed for PEF in November 2016 only arrived in late January 2017. In August 2016 DFID released £2.3 million to the government to allocate to PEEF and release of this funding by the government was also delayed. RAF assessments and previous annual reviews have highlighted the difficulties for priority sub-departments and organisations under SED, including PEF and SpED, to gain timely releases of funding. This is usually attributed to limited capacity to draw up credible expenditure plans to help secure funding.

Timely management and processing of DFID funding by GoPb is a key issue which needs to be addressed in 2017. Funding flow delays may limit PEF’s ability to deliver on its expansion plan targets as PEF needs a steady cash-flow to operate effectively and within the cycle of the academic year. PEEF has been managing the gap through their own endowment fund resources. DFID discussed the timing of release and receipt of funding with the government’s Finance Department, SED, PEF and PEEF, and there are varied interpretations of how long it takes funds to reach the recipient departments. Work is ongoing to determine the cause and unblock the slow release of funds. Over the next year, TAMO should focus on capacity-building in financial management and planning to support delivery of longer-term goals.

In 2016, DFID released £11.5 million to IMC to implement the school construction component. Payments are made monthly in-line with workplans and forecasts agreed at the beginning of the financial year. The IMC contract (currently £93 million) is also being renegotiated in line with new construction targets, increases in the cost of construction, and DFID capital development budget limitations. This year IMC has shown significant improvement in financial forecasting. As of 31 December 2016, IMC was on-track to achieve more than 95% of their forecast for fees and expenses. For capital works, IMC’s monthly spending was mostly in line with their forecast for the first two quarters, although there was a moderate underspend in the third quarter. This variance is primarily because of delays in the procurement of sub-contractors for the next round of construction, and delays in payment processing.

DFID holds direct contracts with Adam Smith International (ASI)/ McKinsey (in a consortium as TAMO) and McKinsey for support to the Chief Minister’s Education Roadmap process. Both have agreed financial procedures, which are regularly monitored through quarterly reporting. Payments are made on a quarterly basis for the Roadmap contract and bi-monthly for TAMO according to workplans and forecasts agreed at the beginning of the financial year. In 2016, DFID released £8 million to TAMO and the Roadmap team. The major challenge has been a high burn rate on the TAMO contract due to a greater ambition in targets linked to the Chief Minister’s 2018 education goals, which will result in almost full spend of the contracted budget (£17.9 million) by the end of third year of the programme. There is an urgent need to address this issue and DFID is working on options.

DFID received the Auditor General of Pakistan’s 2014/15 report on SED in March 2016, which concluded with an unqualified opinion that financial statements represented a fair representation, and expenditures had been made in accordance with legal requirements. The 2014/15 financial statement confirmed that DFID’s contribution was £46.4 million during this financial year, including payments towards SBS (£32.1 million), PEF (£12 million) and PEEF (£2.3 million); and that DFID’s funding was fully utilised. The report assesses the original eligible areas of expenditures agreed in 2013 between the World Bank, DFID and government. The audit concludes that performance of SED’s programme is satisfactory and the risk rating medium overall. Audit observations have been resolved through subsequent Departmental Accounts Committee (DAC) meetings apart from two outstanding issues around district-level use of funding which are soon to be resolved. The SED maintains the tracker for recommendations to address financial management issues highlighted in audits (such verifying student eligibility for funding, and reducing delays in transfer of funds) and provides updates on the action plan after committee meetings. However, there are two observations from the Auditor General’s 2014/15 report. An audit of IMC for 2015 was conducted by Ernst & Young and received by DFID in June 2016. This was unqualified, with no major areas for follow-up. Audit reports for PEEF and LUMS for 2015/16 are expected in early 2017.

Recommendations:
- DFID to ensure all audit reports are received on time and issues addressed efficiently (including follow-up on the two outstanding issues around district-level use of funding in the Auditor General’s 2014/15 report)
- DFID and TAMO to work with the PMIU/SED/Finance Department to understand reasons for and remove the delays in transfer of funds to PEEF and PEF.
- DFID should undertake a review of IMC’s TA schedule to identify TA savings which can be re-allocated to the capital fund, allowing more classrooms to be built.

Date of last narrative and financial report	Last annual report: August 2016 / Last quarterly report: Nov 2016
Date of last audited annual statement	March 2016

E: RISK

Overall risk rating: Moderate

Overview of programme risk
The risk to UK investment in PESP II is moderate overall. The biggest risk to the programme is that the government does not allocate sufficient funds to education departments to ensure delivery of the Chief Minister’s 2018 goals. There is a connected risk that TA provided through the programme fails to cater to the government’s needs and achievement of results and contributes to limited government ownership of programme activities. There is a risk that TAMO will be unable to bring in strong technical expertise to support other departments like DSD, PEC and SpED to deliver key reform objectives or that turnover of the heads of key organisations negatively affects programme implementation. These risks are being mitigated to an extent through close working between TAMO and SED and joint ownership of workplans. The risks have decreased over the last year as the heads of PEF, DSD and PMIU have remained stable and TAMO team positions are being reviewed and refreshed.

There are risks around PEF’s capacity, which were assessed by PwC through a review undertaken through the PRAP in 2016 which looked at their institutional strength, quality of education and ability to expand. An action plan has been agreed with PEF, and satisfactory progress has been noted in the areas of governance and management, human resource management, procurement and asset management. Further work is needed to reduce risks around education quality, programme and financial management, audit, and monitoring and evaluation. TAMO is supporting PEF to improve these areas. There is a risk that the government and PEF fail to enrol additional children identified as having mild or moderate disabilities and that remaining DFID funds allocated to the inclusive education component remain unspent. Addressing these risks has become priority areas for the DFID adviser leading on this component.

There is a risk that IMC revises down the number of classrooms which can be constructed, as a result of potential cost escalation; or that the government’s own classroom construction programme overlaps with work managed by IMC. DFID has put in place mitigating measures to address risks around the delivery of the school construction component, including a quarterly Steering Committee.

There is a risk of corruption or misuse of funds within one of the PESP II partner organisations but the use of third party verification and effective monitoring using spot checks along with technological solutions are strong mitigations.

There is a sustainability risk that the role played by the Roadmap team will not be taken over by SMU or SED during the lifetime of the programme, as there is still no clear transition plan in place to ensure this. A transition plan will be developed in 2017.

There has been considerable turnover in DFID's PESP II team; however the new team provides dedicated support to all PESP II components, and there was a robust handover to the new Senior Responsible Owner (SRO). DFID reviews and updates key risks and mitigation measures on a regular basis, through coordination meetings with partners and on the basis of TAMO’s quarterly reporting.

Outstanding actions from risk assessment:
- SED, PEF and TAMO to improve processes for recruitment and performance management, to ensure senior-level vacancies are filled, and technical and monitoring capacity is adequate
- TAMO and DFID to align and strengthen risk management frameworks, processes and mitigation measures to enable greater consistency in tracking, reporting and addressing risks

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Overall progress is on-track against targets within the expected timeframe, with the main exception of low enrolment of planned numbers of children with disabilities and the need to redesign the programme for educating children with disabilities to ensure funding allocated for this purpose is used effectively. There has also been a large reduction in the number of classrooms constructed under IMC, and an increase in the timeframe and management fees, which needs close management to ensure adequate construction takes place by the end of the programme without further cost escalation.

Performance of partnership(s)
PESP II is delivered through a wide range of partners including government departments, private sector, civil society organisations, academia, an endowment fund, and suppliers. Overall, support provided by DFID to the GoPb for SED and its allied departments has been effective due to a strong collaborative partnership which is helping the GoPb to achieve its education reform objectives. However, there are concerns around progress against funds allocated to the SpED for implementation of two inclusive education pilots. The pilots have shown low enrolment of and support to children with disabilities against projected targets. Poor performance has been attributed to weak institutional capacity within SpED and limited DFID and TA engagement and expertise during 2016. The GoPb has made good progress on education reforms against to disbursement linked indicators (DLIs) in all five areas of the RAF for year two of the PESP II programme. A new format of the RAF (devised through consultation with SED and allied departments which contribute to achievement of the targets) has been agreed for year three of the PESP II programme onwards, and demonstrates a shift from processes towards a stronger focus on results.

Regular Key Supplier Management (KSM) reviews play a key role in performance management of the output-based contract with TAMO (see Output 6). Milestones are agreed on an annual basis and refreshed each quarter. Performance is managed through regular progress reviews and a thorough assessment of milestones delivered. DFID also completed a PRAP review of TAMO in 2016. Based on the review’s recommendation, an action plan was agreed with TAMO. The major observation was around confirming the legal status of ASI in Pakistan. Following the recommendation the registration process has now been completed. Learning from previous years, the process of agreeing the year three workplan and budget was initiated well in advance, with clear timelines, and government approval and ownership. However, there have been concerns among education departments that they are not getting the TA they need from TAMO. . Going forward, the area where education departments need most help is focused support from DFID and TA which provides them with required expertise which they lack (e.g. in inclusive education for children with disabilities). DFID has increased its advisory support to these areas. TAMO is currently recruiting senior education and equity specialists to improve its technical capacity. With funding from the PESP II TA budget, DFID also recently provided £808,000 million to SED through an Externally Funded Output (EFO) with the World Bank for two years (ending December 2018) to co-fund support for specific complementary TA studies and outputs in aspects of teaching, HR management, financial and project management which are currently not covered by TAMO’s work. This will help inform both the PESP II programme and the World Bank’s $300 million PESP III programme which begins in 2017, and help to ensure a consistent approach to education reforms in the province.

The inception phase for DFID’s new contract with McKinsey to support the Education Roadmap process and the Chief Minister’s quarterly education stocktakes concluded in March 2016DFID’s Procurement and Commercial Department recently launched a review process for suppliers who are not among DFID’s top 12 suppliers (in terms of funding). This includes McKinsey. The first review was completed in November 2016 using balanced score cards. This found that McKinsey had been responsive, and had effectively supported the Roadmap process, but needed to align better with the priorities of the SED’s senior management. A new quarterly reporting framework will aim to clarify the distinction between support from TAMO versus the Roadmap (McKinsey) team.

After a challenging start, IMC has increased the pace of delivery of school infrastructure construction. Over the past year IMC has streamlined its internal controls and functions, but there is still room for further improvement. It is important for DFID to better understand IMC’s delivery chain and downstream partners (i.e. its sub-contractors) to address challenges at geographically dispersed sites. IMC should be able to improve the accuracy of its financial projections as the programme progresses, as there is greater clarity around costs once design and construction have begun. IMC needs to substantially accelerate the pace of construction to catch up with budget estimates. A full-time infrastructure adviser has joined DFID to enhance quality assurance of IMC’s work.

DFID has a strong working relationship with PEF through regular engagement at a senior level. PEF has made good progress towards achieving its 2016/17 action plan targets. DFID has decided to channel scale-up and delivery of the Priority Districts pilot component through PEF, based on third party validation conducted in May 2016 which found that working through PEF increased sustainability and government ownership. In 2016, DFID commissioned a thorough review of PEF’s capacity and systems to gain further assurance on the organisation’s ability to deliver its expansion plan. The agreed action plan aims to build PEF’s capacity in programme management, financial management, monitoring and evaluation and audit. DFID’s partnership with senior management at LUMS and PEEF has worked well, and both organisations have achieved the targets agreed for this year. DFID continues to engage with LUMS on improving its approach to addressing gender inequality issues and making outreach and targeting more equitable to enable admission of more female students who meet the merit criteria. PEEF’s strong performance is attributed to a strong team delivering the programme.

Recommendations
- DFID to work with partners to understand the impact of exchange rate on planned education results.
- DFID to clarify the delivery model for PESP II in relation to revisions to TAMO and Roadmap contracts by March 2017.
- DFID to begin a formal KSM process with IMC Worldwide in Pakistan by June 2017, and hold IMC to account for time slippages, cost increases, quality, safety, supply chains standards, and accessibility.
- IMC to step up the pace of construction, ensure potential delays are highlighted monthly to DFID and the third-party validator, improve accuracy and transparency of forecast outputs and expenditure.
- IMC to ensure visibility of project costs at unit rate level, and a rate comparison benchmark.

Asset monitoring and control
TAMO and IMC manage and monitor assets through an asset register and physical tagging. Updates on assets management are part of TAMO and IMC’s regular reporting to DFID, and the most recent updates were received and reviewed in January 2017. Assets were reported to be in place and in good condition. The annual review team looked at how assets are procured, the processes followed, and documentation of the procurement process, and spot checked the procurement process and documentation in place at TAMO. The review team also randomly selected 15 different line items for physical spot checks to verify IMC’s assets, and all assets were found to be in place and appropriately tagged. Going forward, DFID plans to conduct physical spot checks of assets on a quarterly basis.

G: CONDITIONALITY

Update on partnership principles (if relevant)
The PESP II business case states that funding is based on the Government of Pakistan’s commitment to poverty reduction, protection of human rights, strengthening public financial management and domestic accountability, as set out in the UK’s Development Partnership Arrangement (DPA) with Pakistan.

The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division at the federal level and text is shared every six months. The PPA was discussed most recently in December 2016 during our Bilateral Assistance Talks. The PPA sets out the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for: reducing poverty and achieving the Sustainable Development Goals. These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the four principles. DFID can therefore continue to plan and deliver sizeable programming on-budget. Progress towards the SDGs and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Elite capture and its influence is often cited as a concern. Recent pressures on international non-governmental organisations (INGOs) have led to a downturn on domestic accountability.

The majority of the UK’s investment in PESP II is through sector budget support (SBS) conditional on disbursement linked indicators (DLIs), direct financial aid and technical assistance to the GoPb. Progress has been enabled by the political will to reform combined with improved SED ownership and capacity. There has also been strong commitment from the Finance Department, although financial management (PFM) under PESP II could be strengthened. The GoPb is now implementing a detailed PFM reforms strategy under the leadership of the Finance Minister, through the recently finalised Provincial Finance Commission Award and with substantially increased resources for the education sector. With support from PESP II, the senior leadership in SED now regularly analyse and monitor the budget execution and take corrective actions, especially on non-salary and development budgets. Under PESP II, the SED has also established a Financial Management Cell to support budget planning and expenditure. The GoPb has also improved accountability through enacting the Rights to Information Act and establishing a Citizens’ Feedback Initiative to inform the government about service delivery issues. The government is also now using a tablet-based monitoring system to hold education managers and teachers to account.

H: MONITORING & EVALUATION

Evidence and evaluation
A number of reviews were conducted in 2016, including third party verification of the Priority Districts pilot and final impact assessments of PEEF and PEF baseline review reports. Recommendations made were mainly around strengthening monitoring and evaluation structures, systems and procedures. Measures taken in light of these recommendations include drafting an updated monitoring and evaluation strategy, providing tablets to MEAs for data capturing and work towards the creation of a consolidated database. The DFC audit of PMIU data showed remarkable improvement in the data quality after introducing tablets for data collection. In addition, DFID conducted a review of TAMO and developed a work plan which is being followed and closely monitored.

The majority of last year’s recommendations have been incorporated in the logframe. This has improved the ability to track milestones for outcomes and outputs. However, logframe assumptions should be revisited to check if they still hold true, or if others have emerged during the course of the project. For example a two-month delay in textbook printing due to litigation from private publishers was not identified as a potential external challenge. A logframe matrix which includes risk, monitoring and VfM should be updated at review points to ensure a logical connection between the three. A careful documentation of underpinning assumptions will not only benefit the current programme but also inform future similar projects. After a contract with Oxford Policy Management to conduct a formal evaluation of PESP II was terminated in January 2016 (details of which can be found in the PESP II Annual Review 2016), an evaluability study was carried out to determine which aspects of the programme should be reviewed. The tendering process has been initiated to bring a supplier on board to carry out a performance evaluation of the programme. The evaluation is expected to commence in 2017. TAMO is conducting evaluations of the two inclusive education pilots being implemented through the government SpED and PEF. These are expected to be completed in spring 2017, and used to inform design of the next phase of the government, PEF and DFID’s support to education for children with disabilities.

Monitoring progress throughout the review period
DFID conducts quarterly monitoring, risk analysis and VfM framework updates with the support of a governance adviser and economist. DFID conducts monthly progress review meetings with TAMO, in addition to RAF assessment meetings that will happen quarterly. The VfM framework in its current form is comprehensive in terms of data and serves as a detailed repository of numbers but regular analysis and a narrative need to be added to make it more actionable. Over the past year, DFID's PESP II team has been restructured to provide additional technical and programmatic support, and improve the strategic direction and oversight of the programme. Every workstream strand now has a clear lead; a lead education adviser has oversight of key strategic discussions; and the Senior Responsible Owner (SRO) provides overall leadership and linkages with the wider DFID education portfolio. DFID also frequently conducts visits to schools supported under PESP II across the districts in Punjab.

TAMO is providing technical support to SED to strengthen PMIU to become a high performance, stand-alone unit to manage data collection, ensure quality and share data with public. It has developed a monitoring and evaluation strategy for PEF and is assisting PMIU to execute this. It is imperative that this evidence base is owned, managed and used effectively across the programme, providing robust progress information. TAMO launched an Education Hotline pilot in Lahore and Bahawalpur in November 2016 to collect direct beneficiary feedback. If managed well, this initiative can provide critical information to improve the regular project management cycle.

This Annual Review was conducted by DFID Pakistan’s education team through:
1. Desk review of key background documents on the PESP II programme (December 2016). TAMO provided DFID with a narrative of progress against the logframe, supporting data, documentation and strategy documents.
2. Visit to Lahore and Chiniot 9-12 January 2017. The objective of this visit was to analyse progress made under the different components of PESP II and assess key successes and challenges. The review team met with the senior leadership within the GoPb (Secretary SED, Special Secretary SED, Secretary SpED, Finance Secretary, Directors of PCTB, DSD, PEC, SMU), as well as PEF, PEEF, LUMS, IMC, ASI and McKinsey. The review team also visited government and PEF primary, middle and secondary schools, a government special education school and LUMS.

Recommendations:
- DFID to review and update the PESP II logframe quarterly from April 2017 to reflect new assumptions and revised targets for 2017/18 and 2018/19 (including Roadmap)
- TAMO to fully operationalise the PEF Monitoring & Evaluation strategy by December 2017, ensure technical team leads conduct field visits as part of the M & E strategy, and make the Monitoring and VfM framework more analytical and actionable
- TAMO and DFID to align and strengthen risk management frameworks, processes and mitigation measures to enable greater consistency in tracking, reporting and addressing risks. DFID to ensure partners collect data disaggregated by sex and disability, and have clear approaches to addressing equity and inclusion issues