Global SME Finance Initiative

Annual Review 2015

Date Programme started: January 2012

Dates review undertaken: 27 May – 30 June, 2015

EDRM: 5065377

Abbreviations & Acronyms
AR	Annual Review
AS	IFC’s Advisory Services
CB	Credit bureau
CR	Collateral Registry
DFIs	Development Finance Institutions
EIB	European Investment Bank
E&S	Environmental and social issues
FCAS	Fragile and Conflict Affected Situations
FI	Financial institution
IFC	International Finance Corporation
IS	Investment Services
JICA	Japan International Cooperation Agency
MFI	Microfinance Institution
OFID	OPIC fund for International Development
PFI	Partner Financial Institutions
PSD	Private Sector Development or Private Sector Department (as context requires)
RSF	Risk Sharing Facility/Finance
SME	Small and Medium Enterprise

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global SME Finance Initiative
Programme Value: £75 million		Review Date: June/July 2015
Programme Code: 202935	Start Date: 28/01/2012	End Date: 30/09/2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress, lessons learnt and headline actions

General progress

As summarised below in Summary of Progress the programme has performed well in terms of reaching fragile States, the number of institutions involved and leveraging capital from other Development Finance Institutions. The main challenge relates to data –attributing the results and proving engagement with women-owned or headed businesses and obtaining jobs data. The second biggest challenge is IFC’s failure to respond to so many of last year’s Annual Review recommendations. This will be escalated within IFC’s management and the final payment withheld unless and until a plan to address them is concluded. As a result despite good performance against the indicators (with many being exceeded) which would have resulted in the technical score of an A+, the programme has been awarded an A.

Process of Review

The SME programme underwent a Mid-term Review by independent consultants Dalberg and Beecher. DFID inputted into the terms of reference for it and provided comments on the report (provided in draft to DFID on 4 June) and DFID held extensive discussions/interviews with Dalberg and IFC. This Annual Review includes the findings from the Mid-term Review, the most recent six monthly progress reports from IFC and the discussions with some of DFID country office representatives (Pakistan, Tanzania, Bangladesh, Mozambique), the Growth and Resilience Department, a DFID Results Adviser, PSD’s Economist and interviews with IFC’s regional and Headquarter staff working on the Initiative. This Annual Review was led by PSD adviser from DFID Ethiopia.

Summary of progress

- The Initiative has been very successful in reaching fragile and conflict affected situations (FCAS), particularly when compared with IFC’s standard lending reach in these countries. The Initiative now covers 27 countries (seven new ones added since last review are highlighted in bold) – Afghanistan, Pakistan, Nepal, Bangladesh, Myanmar, and India in South Asia; Burundi, Mali, Congo, Chad, Togo, Rwanda, South Sudan, Liberia, Kenya, Tanzania, Mozambique, Zambia, Malawi, Guinea, Sierra Leonne, Ghana, Nigeria, Cote d’Ivoire, Democratic Republic of Congo (DRC), and Uganda in Africa, and Haiti in the Caribbean.
- 94.000 of the SMEs supported (nearly double from last year) were in fragile countries, which is 347% of the target.
  - 72% of DFID’s funding has gone to countries where less than 25% of the small firms have access to bank loans.
  - 62% of DFID’s funding has been used in supporting Financial Institutions in Lower Income Countries
  - 63% of the Initiative is focussed on FCAS – whereas in IFC’s overall lending portfolio they make up 5%.
  - More than 60% of DFID’s funding has gone to sub-Saharan Africa.
- A large number of loans have been disbursed, with most loan numbers and amount targets exceeded - 103,427 SMEs having access to loans and the monetary value of these loans to SMEs reached £4 billion (59% more than the set target, 378% of the target for FCAS).
- Twice the target number of financial institutions have been supported - 33 in total with investment services and advisory services.
- A lot (16) projects are underway for general financial infrastructure e.g. credit bureaux, collateral registries.
- DFID has disbursed a total of nearly £64.47m (£12m this year) under this Initiative. Of this, £28.63m has been for advisory services and £35.84m for investment services projects. This was from the Private Sector Department except for £6.44m from DFID Nigeria and £2.5m by DFID Mozambique. DFID Tanzania has expressed interest in co-funding any expansion or continuation of the Programme.

Main issues or challenges faced
Attribution of results – the SME Initiative reports all loans provided by a supported Partner Financial Institution as being a result of its funding, due to the IFC and its advisers finding attribution of its results challenging. Clearly, some of these loans would have happenned without the Initiative as many of the Institutions supported were already doing SME lending and the finance from IFC is sometimes a small proportion of their overall lending portfolio. Further, there are other funders involved e.g. the Dutch and the results are not pro-rated to the donor contributions. This issue has been raised repeatedly with IFC and its advisers, including in the last Annual Review and DFID may condition any future funding on development of a methodology for a proper attribution of results.

Problem with obtaining data on gender – a key target of the Initiative was to have a large proportion of loans focussed on women-headed or women-owned businesses. Most of the Partner Financial Institutions do not have a system for tracking this and IFC did not insist on it contractually until recently, hence the data from IFC is very limited and it is impossible to work out whether gender targets have been met and whether there is the appropriate impact on women-owned/managed businesses. IFC is addressing this by conditioning new finance on tracking this data and new work e.g. Advisory services will have an increased focus on supporting women owned/managed businesses.

Jobs-created figures are very hard to obtain and are low (61,000 as at March 2015 as opposed to the target of 500,000) due to time-lags in the creation of jobs by an SME receiving a loan (an SME may make capital investments and only after sales growth increase employment materially).

The G20 Prize Technology based solutions do not appear to have been as catalytic as hoped, in particular in facilitating FCAS and Lower income country SMEs to win procurement contracts.

These issues are discussed further in relation to the specific indicator below.

Lessons learnt from the Initiative :
- Strengthening the capacity of the Financial Institutions and senior management “buy-in” to SME lending is critical to ensure project success and sustainability.
- IFC’s advocacy and championing of SME Lending within a Partner Financial Institution and raising it with financial partners was noted as Financial Institutions as pivotal and arguably as important as the funding or technical support.
- Peer learning amongst Financial Institutions was found very useful, even experiences from Asia in Africa and vice versa. Financial institutions noted the similarities of issues faced.
- Provision of advisory support alongside investment services generally has greater and more enduring impact, especially when the Partner Financial Institution aims to access new markets.
- The local political context, the efficacy of enforcement, the quality of data reported, and the capacity and awareness of Financial Institutions to adopt the reforms and uptake the financial infrastructure are key drivers of progress and success.
- There are long lead times for projects, especially financial infrastructure projects due to regulatory and often legislative changes or projects with new partners who need to undertake changes to meet IFC’s Environment and Social Governance Standards. The logframe should reflect this (targets should not be set at 50% half way through). Jobs results lag because of the lifecycle of an SME taking investment – it may take time before capital investments result in revenue increases that enable additional hiring.
- Given these lead times and start-up time and delayed results, the Mid-term Review may have been too early in some ways but given that DFID has disbursed much of its funds, in other ways it is also too late for DFID to use it to fully influence existing DFID commitments. It will however influence any expansion of the programme.
- DFID should have put more pressure on IFC to ensure DFID’s requirements were met and to be clear that it can/will withhold funding. It should done more to ensure gender tracking requirement were built into the IFC’s contracts from day one. While it raised the issue, it did not withhold finance to ensure this and IFC was late in finally tackling the issue. Similarly DFID has raised the attribution repeatedly but IFC has failed to address it.
- DFID needs to push IFC and its Mid-term Review consultants to do better broader lesson learning about sustainability of the Initiative and the advantages/disadvantages of different forms of financing and the impact on SME productivity etc.

Headline future actions
Strategic level:
- Gender Action Plan that will lay out how IFC to targeted approach for committed projects and pipeline within the Global SME Finance Facility. Action: IFC to produce a final action plan. Timing August 2015
- IFC/Dalberg to design a methodology for attribution of results related to DFID funding (not just sharing with other donors but using a counterfactual of what loans would have occurred anyway) and agree this with DFID and adjustment of/production of second set of targets accordingly. Action: IFC/Dalberg to produce a methodology Timing: December 2015
- To prioritize deploying the remaining £4.2 million in Investment Services and £6.4 million in Advisory Services funds to investments/projects that target specific key areas – especially women-owned SMEs and FCAS. Action: IFC to focus on these priority areas. Timing: Next Progress report;
- More analysis to be undertaken to (1) test the theory of change in the Business Case, in particular seeing whether there is has been an impact on the growth in size of SMEs, their productivity, profitability, return on investments made by the SME and more analysis on whether the lending by the Financial Institutions is sustainable (2) assess the impact of the Risk Sharing Facility on the DFI and Financial Institution lending Action: IFC submit report. Timing: next annual review
- Follow up on the findings and recommendation arising from the evaluation by Enclude, consultants, of technology based approaches and solutions. Action: IFC, in collaboration with Enclude, submit the action-plan and report progress to DFID and discuss. Timing. Progress report
- To base interim milestone targets for future projects on expected performance growth paths with likely growth trajectory of the Initiative's impact targets. Action. IFC to apply this for future institutions that would feed in to the logframe;
Follow up on monitoring climate change related results. Action. DFID to discuss with IFC the importance of CC as our cross-cutting theme for all our programmes (not just climate specific ones) and seek IFC’s commitment to uphold agreed targets. Timing. Next Donor meeting.
Exploit opportunities for peer to peer learning among the PFIs in the Initiative. Action. IFC will use opportunities for such learning in coordination with the SME Finance Forum. Other opportunities will also be considered. Timing. Ongoing
- Improve coordination between IFC and DFID country office teams to ensure a complementary approach across each country’s financial sector portfolio as well as synergy with lessons learning and experience shared both ways and ensuring that there is additionality and minimal overlap between donor initiatives. Action: IFC as implementing partner to engage the relevant DFID country office teams to ensure the central and country-based projects are joined-up. Timing. Ongoing
- Consider follow-on financial infrastructure projects where required. Action. IFC allocating an additional $4 million to Financial Infrastructure projects and will discuss allocation with DFID.
Operational level:
- To include covenants in agreements with Financial Institutions requiring them to provide access to data, and access to SME clients for interviews. Action: IFC has already started to include those in all new agreements and negotiation with PFIs with exciting agreements for amendment. Timing. Ongoing
- Revise logframe including (i) amendments from previous years, (ii) changes recommended as part of the MTR including NPL indicators, (iii) changes that were foreseen but not defined as a result of including new eligible countries in the initiative and (iv) increased targets as the current ones are now too modest. Action: IFC to submit a revised proposal to DFID and DFID then to review. Timing by September 30, 2015
- Review the guidelines on pricing models for AS projects to ensure they are not causing unnecessary constraints or perverse incentives.
Action: IFC to submit a note for discussion with DFID. Timing by October 2015;
Timely submission of IFC quarterly financial statements. Action. IFC to adhere to agreed submission timeline.

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3716779.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3402661.xls

Summary of Programme:

How it works – what it does
The Global SME Finance Initiative (the Initiative) was created in March 2012 with the objective of increasing access to finance for SMEs, and as a result creating new employment opportunities in some of the world’s most challenging economies. It works with the IFC and other development finance institutions (DFIs) to enable them to provide finance (investment services- IS) to banks and non-bank financial institutions such as microfinance institutions (Partner Financial Institutions – PFIs) to onlend to SMEs. Finance is provided where it would not normally be commercially viable for PFIs to lend.

In addition IFC provides advice and capacity building (Advisory Services – AS) on a cost-sharing basis to PFIs and grant finance for changes in the broader financial support infrastructure such as collateral registries or credit bureaux. The Initiative has a particular focus on women-owned-businesses and SMEs in Fragile and Conflict Affected Situations (FCAS).The geographic scope of the Initiative covered by DFID’s funding originally included 20 countries in Africa and Asia. 7 countries in were added in 2014 including Haiti which is outside those regions.

Funding
DFID seeded the Initiative with a commitment for £75m (£60m coming from Private Sector Department, £10m from DFID Nigeria and £5m from DFID Mozambique). DFID Nigeria and DFID Mozambique were unable to make their commitment by £3.56m and £2.5m, respectively. The shortfall was covered by PSD Department in March 2015. In March 2012, the IFC’s Board of Directors approved £125 million for the commercial tranche of the Facility. IFC’s contribution has now reached £386.8 million. Other DFIs have also provided funds to the Initiative including EIB (£65m), OPIC (£93.75M); European Commission (£19.5m) and JICA (£1.3m) in grant funding to the SME platform including our targeted countries. Discussions are underway with other DFIs and donors for potential investments of nearly £300m, including the Netherlands.

Main components

The Initiative has the following three components;
1. Risk sharing and investment component (£40m): It combines grant funds from donors and investments from DFIs to help the Financial Institutions scale up lending to SMEs by providing, for example:
1. Risk Sharing Facility (RSF) Guarantee to cover up to 50% of the loss suffered by the Financial Institutions in the SME lending portfolio covered under the Initiative; and
2. Direct funding lines especially in markets with liquidity constraints. This is expected to enhance risk taking by the Financial Institutions since the loans have a lower risk weighting in the banks’ own balance sheets than they would do without DFID’s contribution. The DFID grant financing alongside financing from the DFIs is expected to improve the pricing as well as terms (e.g. tenure) of the products from the DFIs to the PFIs. It is not clear if it has any impact on the final lending rates.
It is intended that IFC and other DFIs will invest a combined £325 million in the initial phase in SME finance projects with about 35 PFIs. DFID committed £40 million in potentially returnable grant funding as the Initiative’s anchor donor. The Initiative when fully funded is targeted to reach £0.9 billion - £1.2 billion from additional DFIs and £0.3 billion from donors - to further expand its geographical focus. As of June 2015, the Initiative had mobilised £25.4m of concessional funding from three other donors.

2. Advisory Services component (£32m): A complementary Technical Assistance pool to (i) support the PFIs in establishing and strengthening skills, systems, products and processes (e.g. credit risk appraisal and management) needed to scale up their SME financing portfolio and; (ii) support development and improvement in financial market infrastructure (e.g. credit bureaux and credit registries) to improve the information on credit worthiness of SMEs which can in turn bring down the risks and transactions costs in lending to SMEs. The PFIs co-finance the cost of these services. DFID is providing £32 million grant funds to this component.

3. Financing for G20 SME Finance challenge winners(£3m): This includes (i) funding for technology based solutions of the G20 SME Finance Challenge winners. DFID is providing £3m funding to three of the fourteen G-20 SME Finance Challenge Winners for scaling up technologies which may help SME finance and (ii) funding to support the development and operations of the SME Finance Forum, housed at IFC. The Forum provides an on-line knowledge gateway and discussion forums for knowledge sharing on SME finance to identify and promote best practices across countries and institutions and establish baselines.

Management by IFC
IFC does all management for a fee, which including the trust fund management, of 6.4% / £4.8 million of DFID’s contribution. Out of the total budget, £2.4 million was earmarked for Monitoring and Evaluation work. The facility was also extended to 2021 with no-cost extension approved on May 2015 to enable IFC deploys the remaining allocations on deals with the tenure of six years or more.

Fit with DFID’s Strategy
Supporting SME finance is a key part of DFID’s Economic Development Strategic Framework, in particular the pillars of catalysing capital flows and trade in frontier markets and ensuring growth is inclusive, and benefits girls and women.
- The Programme is a core contributor to:-
  - the “We Wills” commitment (part of DFID’s Departmental Results Framework -DRF) of improving access to financial services for 200,000 SME by 2019. Notwithstanding the challenges around attribution (explained earlier), a significant part of this commitment has been delivered by the programme in less than half the overall timeline.
  - the commitment in DFID’s Strategic Vision for Girls and Women to improve access to financial services for over 50,000 women headed or owned enterprises by 2019.

Expected Results by March 2021
- Provide at least £5 billion of additional commercial lending to 200,000 small businesses in target countries, at least a quarter being women-headed businesses.
- Provide one million people with employment opportunities and increased income.
- At least a quarter of these benefits will go to small businesses in fragile and conflict affected countries.
- Provide 300,000 people with employment opportunities and increased income.

Contribution to DFID’s operational plan and wider DFID objectives
Scaling up SME financing in poorer countries, is a key deliverable of the DFID Business Plan 2011-15 and the Private Sector Department’s (PSD) Operational Plan 2011-15. It is also consistent with wider UK Government objectives of encouraging enterprise development in developing countries that are facing numerous challenges, including their ability to maintain investments during global economic crises and stimulation of growth in countries emerging from conflict.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment

The Initiative has achieved the Outcome which is to increase SME financing on a commercially sustainable basis in the identified countries and segments by catalysing investments from DFIs and private sector; supporting the development of enabling financial market infrastructure; and promoting use of technology to address wider systemic constraints such as weak information infrastructure. Although projects take time reach maturity, implementation has been in full swing with nearly 90% of the budget committed. As such the programme should be on track to meet the overall 2021 targets. Progress has been made under each of the areas as described below:

Outcome Indicator 1: Number of SMEs reached with loans, of which (a) 25% to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

On track: General Lending targets have been surpassed, in some cases rather substantially. Compared to the logframe set for March 2015, 103,427 SMEs have been reached. While the target for fragile countries and markets have been substantially exceeded i.e 248% of the target, despite challenges in the local environment, the Initiative seemingly fell short on women headed or owned businesses i.e. only 4,127 (17%) reached. This is due to under reporting/lack of data as most institutions do not gather the data and IFC only recently contractually required it of them. Independent assessments were unable to ascertain that the Initiative will reach the targeted number of women by the end of the programme but the analysts were confident that the figures understate the number of women owned/managed businesses reached.

It should be noted however that IFC reports all loans made by Partner Financial Institutions, irrespective of whether there is a causal link with IFC or DFID funding. Clearly some loans would have been made in the absence of the Initiative and other donor funding needs to share the results.

Outcome Indicator 2: Monetary value of additional loans to SMEs through development of financial infrastructure and disbursed by PFIs, of which (a) 25% to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

On track but with a caveat for the gender issue: The main monetary loan targets have been surpassed as have the FCAS targets in some cases rather substantially. Compared to the logframe set for March 2015, monetary value of additional loans to SMEs was more than 1.5 times than the set target while the figures for FCAS are more than 4 times the target.

However, the results for women headed or owned businesses are only 14% of the current milestone target. Again, independent assessments were unable to ascertain definitively that the Initiative will reach the targeted value for women by the end of the programme but found that the figures were an understatement.

Outcome Indicator 3: Number of new jobs created by SMEs benefiting from the Initiative

On track: Despite data limitation given the relatively early stage of maturity of all the IS and AS projects, the resulting extrapolations about the potential job effects of the Initiative are promising. Statistically significant positive correlation was found between access to finance and employment growth, although results varied fairly significantly by country, business size and sector. Currently, it is estimated between 561,000 to 608,000 jobs have been supported as of late 2014 and between 61,000 and 65,000 jobs added/created at SMEs as a result of financing to date. If current trends continue, Dalberg, the independent evaluators estimate that between 2.5 million and 31.8 million jobs will be supported and between 600,000 and 5.8 million jobs will be added at SMEs as a result of financing by 2019.

It should be noted here however that the jobs results are extrapolations from the loan results and therefore the fact that the loan figures are not attributed means that the job figures are also overstated.

General Results Attribution Problem

Projects under the Initiative follow IFC’s corporate guidelines on results attribution for IFC’s Development Goals (IDGs)[1]. IFC acknowledges that individual attributions for the finance it provides remains a challenge. The Mid-term Review consultants concluded that the overall evidence to establish a direct causal linkage between the Initiative and the subsequent changes at the PFI level is not strong enough to make firm statements about causality. This issue is faced by many DFID programmes however and DFID needs to be able to produce some results which are more attributable to its own financing as the current set of results are potentially misleading. DFID has put forward suggestions for attribution methodologies. None are perfect but they would provide a more realistic set of results for the number of loans, volume and jobs figures. More work will be undertaken with IFC and its consultants on this.
[1] The IFC Development Goals (IDGs) are corporate-level development goals which IFC began testing in 2011. They were inspired by the Millennium Development Goals as a way to better integrate IFC’s results measurement with strategy

Aggregate Output Score and Description:
The overall composite score across the three programme outputs is estimated at A, which means the programme moderately exceeded expectation.

This reflects both the findings on the progress to date over the 12-month review period and progress trajectory against milestones for 2021, as well as a Mid-term Review by Dalberg and Beecher. There is reason to believe that the projected output results will not only be reached but exceeded, due to the lower than expected average size of DIFD funds allocated to more projects enabling higher outreach, most projects have yet to reach maturity and the non-linear and exponentially increasing results coming through are posed to outstrip already good numbers.

But the result should be taken with caution, as the logframe has not been updated at all since the the nature of the programme and pending results were better understood when implementation started, with the overall score giving a misleading sense that the programme is achieving all when it has some substantive challenges such as result on women, jobs created and attribution.

Given these issues, we would suggest downgrading the score to an A.

Lessons: Provided in the Summary Sheet
Actions: Provided in the Summary Sheet
Has the logframe been updated since the last review? No – will be updated for the next one.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Risk sharing mechanism (s) to catalyse investments from DFIs in the selected PFIs for scaling up SME financing on commercially sustainable basis in the 15 target countries, including in the high risk environments of fragile/conflict affected countries.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone1 (March 2015)	Progress (March 2015)	Score
1.1: Cumulative number of Partner Financial Institutions (PFIs) supported with risk sharing and funding mechanisms.	15 PFIs	32 PFIs	A++
1.2a: Volume of additional funding mobilized for SMEs through PFIs under the investment facility component (concessional funding).	£800m	£918m	A+
1.2b: Investment leveraged from DFIs and PFIs as a multiple of the size of the risk sharing funding from DFID.	£323m	£530m	A++
1.2c: Share of fragile countries and frontier markets in (a) and (b).[2]	(a) 4 PFIs / (b) £200m	(a) 10 PFIs / (b) £86m	A
[2] Indicator should be amended to 1.1 and 1.2a not a and b

Key Points
- More than double of PFIs/banks and non-banks financial institutions supported. The initiative has more than exceeded not only the set milestone for indicator 1.1 but also doubled the overall target of the programme. These investments were supported by DFID’s concessional funding of £33.1m with 53% on loans and 47% to RSFs;
- The Initiative meeting its target for IS portfolios in overall volume of SME loans generated. The IS portfolio is exceeding targets by 15%. Furthermore, with only 20 PFIs reporting on their portfolio growth and reports being based on loan disbursed not committed mean it is likely that these targets will have been substantially surpassed by the end of the Initiative;
- The Initiative has exceeded its target to mobilise investment from DFIs by 58%. IFC (£387m), EIB (£65m) and OFID (£98m) committed for commercial funds with additional £20 million in concessional funds in February of 2014 for Blended Finance by EIB. Discussion underway with the following - EIB to come into the 7 Ecobank transactions as well as a SocGen transaction, OFID expected to sign Framework Agreement in next month or two and Dutch expected to provide donor funding with a focus on FCAS and West Africa (expected to relieve some of the pressure on DFID’s 15% cap in that region);
- The Initiative is on track to utilise the entire amount of DFID funding by March 2016. Initiative had mandated 83% (40% for signed transactions[3] and 43% to mandated transactions) for of the DFID funding for IS investment by March 2016. Considering that the Initiative has £4.5 million in DFID funding allocated pipeline investments, it is very likely that the Initiative will commit the entire IS DFID funding by March 2016;
  [3] Once projects are mandated, DFID funds have been committed to the transaction, but have not been disbursed to PFIs
- Projects are occurring in geographies where most needed. See above.
- Less DFID funding for more. The final targets for Investment Services implied an average DFID funding per client of £2.78 million. To date, however, the average DFID funding is £1.18 million per IS client, less than half of the implied target. This smaller than expected project size on the investment side is likely a result of the care the Initiative is taking to minimize subsidy and ensure that subsidies provided do not distort markets. This indicates, a) the Initiative will reach more clients and is thus poised to have a bigger impact, and b) that the IFC’s staff has had to develop a larger pipeline to ensure that all funding can be put to use;
- Long gestational period for projects to reach maturity. On average it is taking almost a year to move from a mandate[4] (DFID commitment) to signed IFC contract and disbursement for IS projects due to approval process, delay in fulfilling all the Environmental and Social Governance requirement and Ebola in one case. This explains why 52% of IS transactions that have been mandated have not yet been signed and disbursed. However, track-record shows that the process has been speeding up in the last year;
  [4] Transactions where the client has signed the mandate letter. Typically, these projects have had their Concept Notes approved by the Blended Finance Committee (BFC), and are moving into the appraisal stage
- Investment services were intended to encourage PFIs to increase SME lending as well as target new, underserved clients. This is done by either making available additional capital in the form of loans or sharing the risk of lending to SMEs through risk sharing facilities (RSFs). For example, Advans DRC and Advans Cote d’Ivoire were capital-constrained—as indicated by the low deposits to loans ratio—and therefore took IFC loans to raise needed capital to enable them increase their SME lending portfolio. Yes Bank in India, on the other hand, had a large deposit base (deposit-to-loan ratio of 3.4). However, at the time of the investment the bank was looking to add longer term liabilities to the balance sheet. The £98 million loan provided to Yes Bank included £5.2 million in subsidy to serve women-owned SMEs and SMEs in low-income states (LIS) in India. Similarly, the RSF at SIB Cote d’Ivoire allocated 30% of the guarantee to agricultural SMEs and 25% to women-owned SMEs.
- IS projects have also helped or encouraged PFIs to further improve their institutional capacity for SME lending. While the investment services are not directly targeted at supporting improvements in capacity to serve SMEs, during the independent assessment, the IFC Investment Officers observed changes within the PFIs after the IFC’s investment was made. For example, 40% of the PFIs developed a new SME finance strategy and 60% strengthened the existing strategy. Similarly, 20% of PFIs developed new lending processes and lending products and an additional 20% strengthened the existing ones. 20% of PFIs developed new management information systems (MIS) and credit scoring systems.
- Indications that IS projects would have a larger impact if accompanied by advisory services. To date there are five projects which are actively using the Risk Sharing Facility with relatively low utilization rates (BICICI Cote d’Ivoire using 15.4% of the facility, SIB Cote d’Ivoire using 6.4%, DTB Kenya using just 3.5%, and Access Bank Nigeria 2.6%.). Reasons range from delay in fulfilling all of the IFC’s E&S requirements (four out of the five) and cost of using the RSF due to drop in interest rate. In addition, to identify new clients, introduce new products, and establish new distribution channels before registering loans on the RSF require additional expert support. However, because the PFIs would have to cover at least 50% of the cost of AS, PFIs usually take the RSF without the AS. This explains the slow uptake and maturity of the projects. The Initiative has now started to combine advisory engagement with three PFIs but this needs to be scaled up.
- Additionality of IS was unclear. Some PFIs reported strong additionality while others were mixed. The Mid Term Review findings were similar as were the findings from field visits by DFID country offices. The situation ranged from the facility loan being the primary source of capital for expansion e.g. in DRC to the Initiative also working in banks which had large existing SME lending portfolios e.g. Pakistan or it being used to target segments e.g in India.

Summary of responses to issues raised in previous annual reviews (where relevant):
- Commission scoping work to assess the need and feasibility of providing longer-term risk capital (e.g. equity and quasi-equity) to support high growth SMEs. It has been agreed this will be pursued through the scoping work for the DFID-IFC Development Capital Investment Platform – a separate proposed Business Case
- Mid-term review to assess the impact of DFID’s concessional funding on (i) enhancing the risk appetite of DFIs and PFIs; (ii) on pricing of DFIs’s investments in the PFIs; and iii) pricing of the loans to SMEs. Partially Done. The Mid Term Review has showed the increase in PFIs’ SME portfolios at a faster rate than the overall financial sector. However the growth in SME portfolio does not mean it is fully attributable to the IFC’s services. The pricing of the IS was much lower than forecasted leading to more projects. Average loan size indicates that the majority of PFIs are serving mostly small enterprises. There is however limited qualitative assessment or detail on how really DFIs’ attitudes have been affected.
- Logframe amendments (i) redefine indicator 1.2a to replace the words “ additional funding” with “additional commercial lending”; (ii) remove “and PFIs” in the statement of indicator 1.2b as the targets for this indicator reflect investment mobilised from only DFIs and (iii) the indicators to be revised with a view to focus more on capturing catalytic impact and feasibility of harnessing technology and innovation in tackling constraints to SME finance. There are several logframe amendments that need to be considered together, including (i) the above, (ii) changes recommended as part of the MTR, and (iii) changes that were foreseen but not defined as a result of including new eligible countries in the initiative. The timeline for an updated logframe is September 30th 2015

Output Title	Capacity of partner banks and Non-Banking Financial Institutions (NBFIs) strengthened through well-targeted technical assistance to partner financial institutions in risk management, product development, and improvement in of business processes, and support for development of financial market infrastructure such as credit bureau and collateral registry in the identified.
Output number per LF		2	Output Score	A Technically this is an A+ but due to wider issues with programme downgraded to A
Risk:		Medium	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / (March 2015)	Progress (March 2015)	Score
2.1a: Cumulative number of PFIs and financial infrastructure projects covered with advisory services and activities.	20 PFIs	51 PFIs including 16 financial market infrastructure projects	A++
2.1b: Cumulative number of PFIs and financial infrastructure projects supported with advisory services in the fragile countries and frontier markets	5 PFIs	25 PFIs and 8 financial market infrastructure projects.	A++
2.2a: Volume of SME loans generated by PFIs / financial infrastructure covered by advisory services plus IFC's non-concessional financing.	£1,700m	£3.1 billion	A++
New indicator: 2.3a: Percentage of PFIs reporting that the growth of their SME loan portfolio is greater than the growth of the bank's commercial loan portfolio. / Old indicator: 2.3a: Percentage of SME loans per loan officer. Target: to be confirmed	65%-75%	73%	A
New Indicator 2.3b: Percentage of PFIs reporting an improved NPL ratio at the SME portfolio level. / Old indicator 2.3b: Processing time per small and medium size loan. Target: to be confirmed	65%-75%	44%	B
2.4a: Number of Credit Bureaux (CBs) and Collateral Registries (CRs) created or significantly strengthened. / 2.4(b): Credit Bureaus: / (b1) Total number of firm inquiries / (b2) Total number of loans to firms / (b3) Total value of loans granted to firms / 2.4(c): Collateral Registries: / (c1) Number of SME loans by CRs / (c2) Value of SME loans by CRs"	(a) 14 / (b1) £0 / (b2) £0 / (b3) £0 / (c1) 30,000 / (c2) £3,094 mil	a).15 / (b1) £0 / (b2) £0 / (b3) £0 / c1) 2,270 / c2) £317 mil	B
2.5: Number of PFIs provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have neutral impact.	4	3	B

Key Points
- The Initiative has exceeded the milestone target for the number of PFIs and financial infrastructure projects supported by more than 2.5 times. The Initiative’s AS component has more than exceeded not only the set milestone for indicator 2.2(a) but also surpassed the overall milestone target of the volume of loans facilitated by a third. . Total AS project value was £53.1 million with DFID’s funding share registered at 47% of which 67% used for PFI advisory projects and 33% for financial infrastructure. In addition, there are 16 (12 operational) financial market infrastructure projects – secured transactions reforms and collateral registries and credit bureaux (CB) to support development and improvement of Credit Bureau and Collateral Registry to address systemic constraints e.g. bridge information asymmetry between banks and SME borrowers.
- The Initiative meeting its target for AS portfolios in overall volume of SME loans generated. The AS portfolio is exceeding targets by 80%. This is with only 20 PFIs reporting on their portfolio growth so far as well as based on loan disbursed not committed as such it’s likely that by the facility’s end, these targets will have been substantially surpassed;
- The Initiative is on track to utilise the entire amount of DFID funding by the end of the extended window[5]. Initiative had mandated 84% (50% for signed advisory projects with 34% allocated for umbrella projects) for of the DFID funding for AS projects by March 2015. Considering that the Initiative has £5.6 million in DFID funding allocated to high and medium probability AS projects, it is very likely that the Initiative will commit the entire AS DFID funding by March 2016. Moreover, the average size of DFID funding allocated to the signed projects to date is smaller than expected, putting the Initiative ahead of the targets set.
  [5] Six month from March 2015
- Successful crowding in under the AS. The initiative has mobilized £28.6 million from PFIs, governments, and donors - 64.4% of the total mobilised funding for AS, bringing awareness, attention, and funding to SME lending among new stakeholders. This ability to mobilize such funding not only shows the willingness of partner financial institutions to contribute their own resources to improving SME lending but also the readiness of PFIs, donors, and governments to support SME lending.
- Misleading targets for non-performing loans (NPLs). Targets set with respect to NPLs in the Initiative’s Logframe assume that all PFIs will have an existing SME portfolio with high NPL rates and that the Initiative is expected to contribute to lowering the NPL rates, however many are new to SME lending and have very low, or even 0, NPL rates at baseline. The targets will therefore need revising – see below.
- Financial infrastructure project have not yielded fruits yet. These projects have long gestation period and can start generating meaningful credit history and collateral information for financial institutions only after the Credit Bureaux and Credit Registries themselves have a robust data field .Despite reaching above the expected number of credit bureaux (CB) and collateral registries (CR) created or strengthened to facilitate the access to finance for SMEs, the number and value of SMEs loans generated was not met. That is mainly due to data being unavailable from registries etc as they only just became live.
- Low carbon and climate resilient results yet to materialise. At the moment the facility has only three climate related projects and these projects are not reporting results yet with little attention paid by IFC as ‘IFC has other blended finance and advisory platforms for climate related initiatives, so IFC stated there is relatively less need for focusing on climate facilities under this Initiative’. This needs to be discussed between DFID and IFC.
- Positive correlation between the PFIs’ pre-intervention capacity to serve SMEs and the AS from the Initiative. The independent assessment has shown that, in several PFIs, the management team was committed to serving the SME segment and willing to finance the launch of operations, but needed technical support to set up or strengthen the SME program. This was the case of Bank Alfalah in Pakistan, BancABC in Mozambique, and Gulf Bank in Kenya. Similarly, Advans DRC first received advisory services from the IFC to begin its SME operations and later qualified for a loan.
- The breadth of changes led by advisory services projects addressed the needs of the PFIs to better serve the SME segment. The processes ranged from supporting the PFI in setting up a specialized SME unit within the PFI (for nascent PFIs) to supporting the PFI with its lending distribution channels or providing non-financial services to SMEs (for mature PFIs). Advisory services clients have largely been implementing the IFC’s recommendations with qualitative feedback indicating that the support has been instrumental in increasing SME lending. In some cases, efficient approval process and good customer service has proved more important to the PFI than the offer of a lower interest rate.
- The magnitude of the change affected in each of the financial infrastructure projects is relatively large. The independent review showed a breadth of change which varied from capacity building and technical assistance to enhancing the quality of the data reported to the credit bureau (in the case of Nigeria) to developing the first ever credit bureau in the country (in the case of Myanmar). For the Secured Transactions Reforms and Collateral Registries projects, the magnitude of changes varied from updating an existing law to include movable collateral (in India) to drafting the nation’s first secured transactions law and developing the first collateral registry (in Afghanistan).

Summary of responses to issues raised in previous annual reviews (where relevant)
- IFC to prepare and discuss with DFID an action plan over the next three months to help PFIs improve their management information system to be able to better track and report gender disaggregated results. “IFC will i) engage directly with the PFIs that are unable to report on gender data and ascertain the exact challenges and constraints that inhibit individual PFIs from reporting on this data. Based on this assessment, IFC will develop a plan to target and work with a number of key PFIs that have the potential reach, willingness and commitment to track and report on gender numbers. And ii) work on an approach that the banks could apply in determining a baseline of women borrowers based on their current portfolio. This will be based on the approach IFC is currently developing to pilot in a women's markets project. IFC will use learnings from this pilot to inform its approach to work with the PFIs supported under this Initiative, especially those PFIs that have SME Finance portfolios (but not necessarily a gender focus). Periodic updates on the progress made on the approaches” This undertaking has not been followed through by IFC. See Headline Actions on the second page of this Review for the Gender Action Plan proposal.
- IFC to track and report to DFID if it costs more (and how much more) to deliver AS (and even IS) in FCAS context. We have not had any information from IFC on this.
- IFC to evaluate the various options in reallocation of funds across components and make a proposal to DFID by August 2014. No-cost extension of the Facility from March 2019 to March 2021 agreed with IFC to enable the Facility deploy the remaining allocations on deals with the typical tenor of six years or more

Output Title	Development of technology based approaches and solutions to drive SME financing and development in the identified developing countries.
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (March 2015)	Progress / (March 2015)	Score
31a: Number of banks and non bank financial institutions adopting and scaling up the use of psychometric credit scoring tool / 3.1b: Number of SME loan applications processed and approved using psychometric tool. / 3.1c: Number of banks using EFL tool / 3.1d: Time/ hrs for EFL score turn around / 3.1e: Volume lent using EFL tool.	a) 6 / b) 9,900 / c) 6 / d) under 3 hrs / e) 120,000,000	a) 22 / b) 50,254 / c) 22 / d) less than 1 hr but 95% less than 5 minutes / e) £151,562,500	A++
3.2a: Number of SMEs in fragile countries successful in winning large procurement contracts. / 3.2b: Volume of financing SMEs are provided in support of bid and delivery for large contracts. / 3.2c: Total value of procurement contracts SMEs supported to bid and deliver. / 3.2d: Value of operating LOCs guaranteed jointly by PDT and partner local banks. / 3.2e: Number of SMEs provided with credit guarantee. / 3.2f: Number of SMEs reached through credit counselling/facilitation. / 3.2g: Value or procurement contracts facilitated. 3.2 h: Number of women-owned SMEs reached through contracts facilitated.	a) 247 / b) £8.8 million / c) £44.4 million / d) £9 million / e) 72 / f) 175 / g) £44 million / h) 24	a) 622 / b) £2.19 million / c) £9.26 million / d) £2.19 million / e) 7 / f) 615 / g) £2.19 million / h) 240	B
3.3a: Number of SMEs accessing the technology driven platform to reach investors and mentors. / 3.3b: Volume of investments in SMEs made possible through the technology-driven platform. 3.3c: Number of business plans approved for investors 3.3d: Number of businesses coached/ number of businesses financed. / 3.3e: Number of women-owned businesses financed. 3.3f: Finance leveraged.	a) 100,000 / b) £14.11 million / c) 687 / d) 693 / e) 160 / f) £14.11 million	a) 21,058 / b) £12.43 million / c) 558 / d) 567 / e) 53 / f) £12.4 million	C

Key Points
- Small component but with significant contribution. This is a minor component of the Initiative in terms of share in the overall budget and contribution to the programme outcome - £3m of DFID funds. The output, however, has strategic significance as it supports piloting of new and technology-enabled approaches that may transformational impact on SME financing, especially in countries in FCAS
- Scaling up technology based solutions which can help some of the systemic constraints faced by SMEs. DFID’s funds are used to: 1) to support the operations of the G-20 SME Finance Forum and Women’s Finance Hub managed by IFC and 2) provide performance-based grants to three of the 14 G-20 SME Finance Challenge Winners to pilot innovative solutions that address key constraints to SME finance. The three challenge winners are: 1). Entrepreneur Finance Lab which is testing how and to what extent a tool based on psychometric analysis can be used by banks to predict entrepreneurial ability and risk of loan default; 2). Building Markets’ (BM) Factor Finance for Procurement (3FP) pilot that provides training and credit guarantee support to enable small businesses to bid for large value contracts to supply materials to donor-supported development projects, especially in FCAS and; (3). Bidnetwork to provide on-line mentoring and peer-to-peer investment support to SMEs.
- Nearly four times of targeted banks and NBFIs adopting and scaling up the use of psychometric credit scoring tool with nearly four times of SME loan application processed using those tools. The initiative has more than exceeded not only the set milestone for indicator 3.1 but also surpassed the overall target of the programme by 267%. Same goes for indicator 3.2 with the overall target of the programme outstripped by 52%
- EFL tools used by banks as well as time it took to turn the score around went beyond expectation. The initiative has more than exceeded not only the set milestone for indicator 3.3 but also surpassed the overall target of the programme by 267% with indicator 3.4 performing three times better than planned. The time has actually not just been below 1 hour but for 95% of the case it was done in less than five minutes. This has enabled for the volume lent using EFL tool to be go above expectation.
- Three times of the SMEs in fragile countries successfully winning large procurement contract with value of procurement contracts SMEs supported to bid and deliver being on target. However, the value of procurement contract facilitated was significantly below expectation
- Women fared better with outreach contract facilitation hitting 10 times than expected
- Yet this output is much behind the other outputs substantially not meeting expectation. Volume of financing provided to SMEs for bid and delivery of larger contracts have fallen short than expected with only 30% of finance was secured for SMEs to bid and deliver large contracts. Only 7 out of 72 SMEs provided with credit guarantee despite more than three times of the targeted SMEs (175) reached through credit counselling/ facilitation.
- Despite the targeted number SMEs accessing the technology driven platform to reach investors and mentors, volume of investments in SME’s was just below expectation.
- Not included in the Mid-Term Review. As a separate evaluation of all the challenge winners is currently being implemented, this component was not part of the MTR. Enclude, the selected evaluation firm, has recently submitted a draft findings report which is being reviewed by IFC. They presented the preliminary findings at the G29 challenge winners gathering on June 24th in London, following which Enclude is finalising the report for submission in July 2015

Summary of responses to issues raised in previous annual reviews (where relevant)
- IFC submit a plan to DFID by September 2014 detailing how IFC will commission comprehensive evaluation of the challenge winners to assess the feasibility and scalability of the models rather than development results of the pilots and through what channels they will disseminate the findings. An evaluation of all the challenge winners is taking place with the final report due in July 2015
- IFC should submit a plan to DFID by September 2014 detailing how they will to test feasibility and scalability of the underlying innovative approaches and through what channels they will disseminate the findings. Should be covered by the above report. If not, DFID will follow up.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Performance of key cost drivers
At this stage of the programme cycle the key cost drivers are as follows:

Investment Services	Advisory Services
Pipeline development and supervision	Market context
Administering the trust funds and investment vehicle	Degree of specialization for required project
Governance and approval mechanisms	Availability of consultants
Reporting and M&E.	Security issues

Data to assess performance against these cost drivers has not been provided. However, overall programme management cost for this year seems to be around 0.8% of DFID spend.

Performance against VfM metrics
The Business Case provides consideration of Value for Money under the specified components listed in the table below. As can be seen, the volume of investment leveraged from DFIs for every £ of funding from DFID was nearly double of the set target. The volume of lending to SMEs by DFIs for every £ of risk sharing capital from DFID, exceeds the target ratio of over £20, at £25.7. Figures on management costs have not yet been provided so it has not been possible to assess VfM performance against this indicator.
VfM Indicator	Milestones (March 2015)	Progress (March 2015)
Volume of investment leveraged (£) from DFIs for every £ of funding from DFID.	£8.5	£14.8
Volume of lending to SMEs by DFIs (£) for every £ of risk sharing capital from DFID.	Over £20 / £800m in new lending to SMEs in total	£25.7 / Based on £918.4m in total lending and £35.8m[6] of DFID IS capital
Management costs	Below 6.4% (£4.8m) of the overall programme cost
[6] $64m at £1=$1.65 (figures from Dalberg (2015) IFC Global SME Finance Initiative Midterm Review Annexes)

Note on indicator methodology
Indicator i) measures the ratio of DFID’s contribution to the programme to date to the total funds committed by DFIs to date. ‘Investment’ refers to programme input funding, rather than investments made by SMEs. It has not been possible to determine the extent of additionality i.e. the extent to which the other institutions would have provided funding to the programme in the absence of DFID funding.

For consistency with previous annual reviews and the logframe methodology, indicator ii) attributes all additional financing available to SMEs from the programme to DFID, even though DFID only provides a proportion of the total input costs (12%[7]). This is not a strict approach to attributing results, and is not consistent with other DFID programmes that seek to measure results where DFID is one of a number of funders. For example, the Key Performance Indicator for amount of finance mobilised under the International Climate Fund (ICF) programme follows a methodology which attributes investment mobilised according to DFID’s share of input funding. The recent note by DFID’s Chief Economist [8] advocates a similar approach when measuring finance leveraged or mobilised. The SME programme could therefore consider reviewing the methodology used and logframe indicators to provide a more credible basis for assessing leveraging that is also consistent with other DFID programmes.
[7] This is DFID’s disbursed funds to date (£64.4m) as a proportion of the total programme spend to date (£530m)
[8] Chief Economist note and ICF indicator

Efficiency
During the Mid Term Review assessment the unit cost of Investment services and Advisory Services per client was determined to be much lower than forecasted at £1.18m Vs £2.78m and £0.25m Vs £1.09m, respectively. The Mid Term Review suggested that this is likely a result of the care the Initiative is taking to minimize subsidy and ensure that subsidies provided do not distort markets for IS while for AS it is likely due to efforts to start with smaller projects as a way to build an initial relationship with a PFI and to the pricing policy becoming more rigorous with a minimum of 50% cost share. This has meant that a) the Initiative will reach more clients and is thus poised to have a bigger impact, and b) that the IFC’s staff has had to develop a larger pipeline to ensure that all funding can be put to use. The unit cost per financial infrastructure project has been close to their expected size of £0.45 million.

Category[9]	Average annual increase in SME loans per £ in subsidy
Investment Services	£170.3 per year per firm
Advisory Services	£163.8 per year per firm
IS and AS	£22.1 per year per firm
[9] The sample sizes used in the analysis were very small (6, 11 and 4 firms for the three categories respectively) and so standard deviations were large.

The Mid Term Review also assessed the increase in SME lending per year per pound invested in DFID subsidy across the various components of the programme[10] as well as the average subsidy per increase in one loan per year. The first metric shows that IS and AS had similar impacts per £ spent but the cost of increasing one loan per year was around three times higher for the AS component. The combined use of AS and IS appears to be less efficient, perhaps due to the type of firms targeted for these interventions. The qualitative response which is that combination is critical in institutions newer to SME lending or FCAS.
[10] For the advisory services component, the subsidy amount simply refers to the amount of DFID funding committed. For the investment component, the subsidy is defined as the difference between the market rates of the transaction and the rates offered with blended finance due to the initiative

Category	Average subsidy per increase in one loan per year (£)
Investment Services	£371.8
Advisory Services	£1,144.7
IS and AS	£3,500.3

The analysis also compared type of institutions and found that the increase in SME loans was much higher for banks than microfinance institutions (£169 compared with £12.4) and required fewer subsidies per increased loan, showing that the programme has been more effective when supporting banks. Similarly, efficiency was higher for interventions in non-fragile states compared with fragile states, as might be expected.

These metrics are useful for assessing value for money within the programme, and potentially for targeting in the second part of the project. Benchmarks from other SME focused programmes could also be used to compare the programme’s efficiency with different interventions.

That said, the lack of attribution distorts the figures somewhat here because if banks were already doing a lot of SME lending or would have done so in the absence of the Initiative, then the additional loan £ per subsidy may not be that high.

The Mid Term Review compared efficiency (the increase in lending per dollar invested) in seven PFI case studies in Asia and Africa show huge variance that needs further analysis to determine the drivers of this. The programme could then consider, for example, whether to focus on PFIs with higher efficiency, or to address the sources of lower efficiency. In terms of performance against budgets, figures were only included for three of the seven PFIs in the case studies, of which were performing under or at budget. More data and a wider sample would be needed to indicate budget performance across the portfolio.

PFI	Increase in annual SME lending portfolio per £ in subsidy	Performance against budget
Bank Alfalah Pakistan	£384	2.1% under
BancABC Mozambique	£3	8.8% under
FCMB Nigeria	£161	On budget
Gulf African Bank Kenya	£46	N/A
Access Bank Liberia	£2	N/A
Advans DRC	£17	N/A
Yes Bank India	£52	N/A

Does the project continue to represent value for money?
The programme still represents good value for money based on the criteria set in the business case. These criteria are that the benchmark for poor VfM will be if two or more Outcome level indicators fall short of targets by more than 30% at the Mid Term Assessment. As can be seen below, overall results against the first two outcome indicators at this point (Milestone 4, Year 4 – financial end 2014-15) are +3% and +59% above their respective targets. For the third outcome indicator (Number of new jobs created by SMEs benefiting from the Initiative), if the number of jobs ‘supported’ by SMEs is used to measure progress then the target of 0.5m jobs would have been exceeded by 14%. If, however, figures on jobs ‘added’ 61,000 are used as a measure, assuming this to be a more accurate measure of jobs ‘created’ then current results would be well below the target.

Outcome indicators	Milestones (March 2015)	Progress (March 2015)
1. Number of SMEs reached with loans, of which / (a) 25% to women headed or owned businesses, and / (b) 25% in the fragile countries and frontier markets	100,000 of which / a) 25,000 women owned SMEs / b) 25,000 SMEs in fragile countries and frontier markets	103,427 (+3%) / 4,127 (-83%) / 86,994 (+248%)
2. Monetary value of additional loans to SMEs through development of financial infrastructure and disbursed by PFIs, of which / (a) 25% to women headed or owned businesses, and / (b) 25% in the fragile countries and frontier markets	£2.5bn / (a) £620m / (b) £620m	£3.98bn (+59%) / £87.1m (-86%) / £2.96bn (+378%)
3. Number of new jobs created by SMEs benefiting from the Initiative	Baseline (TBC[11]) + 0.5m	568,000 jobs supported by December 2014 (+14%) / 61,000 jobs added at SMEs due to the financing (-88%)
[11] Baseline for those firms is embedded in the survey data. Going forward, IFC will have baselines for projects including already a few projects where IFC expanded appraisals

Quality of financial management
To date, a total of 53% of the annual budget and 86% of the total programme budget have been spent. The reason for the low spend this year was due to £10.53m reallocation to next year budget to be paid after the mid-term review with a recommendation on how it would be disbursed. Experiences of other SME programmes, and as the Evaluation Cooperation Group’s (ECG) Good Practice Standards for the Evaluation of Private Sector Investment Operations further supports, suggest that the correspondence between programme budgets spend and results are not linear. It takes time to scale up programs at the IFC, the PFI, and the SME level with outcomes accruing slowly at first, and then accelerate as projects mature.
Unaudited financial statements for the World Bank trust fund relating to DFID’s contribution to Advisory Services are not submitted regularly to DFID as they could be. DFID has access to some online information on the World Bank portal but this does not show the most up to date information on spent and uncommitted funds. Therefore we require IFC to send DFID quarterly financial statements under our Administration Agreement. These are key for us to be able to work out that we are not financing in advance of need and comply with UK Government accounting management requirements. These can arrive quite late. For example in July 2015 DFID received the September 2014 statement only after chasing.

Date of last narrative financial report	Unaudited financial statement for the World Bank trust fund relating to DFID’s contribution to the Advisory Services in June 2014 (EDRM number 4846479) and February 2015 (4911967)
Date of last audited annual statement	Access on line for the unaudited financial statements for the WB’s TF (071850) for Advisory Services. / Unaudited financial statement for the trust fund relating to DFID’s contribution to the Investment Services for Quarter ending June 2014 received in July 2014 (4575250) and Quarter ending December 2014 received in February 2015 (4883543) and Quarter ending March 2015 received in July 2015 (5031267And Quarter ending September 2014, received on 13 July 2015.

E: RISK
Overall risk rating: Medium

Overview of programme risk: The SME Finance Initiative has a Risk Matrix with mitigation strategy in place (Annex 1). The review assesses that the Initiative continues to be in the medium risk and high impact category.
Impact	Probability
		Low	Medium	High
	Low
	Medium	1, 8, 10
	High		2, 3, 4, 5, 6, 7,9

However, during an internal audit review of the Private Sector Department in June 2015, seven issues with risk ratings were flagged up and listed below. Actions proposed below and in the risk registry will be monitored as per the timeline set out.
Internal audit report findings and recommendations (paraphrased rather than verbatim)		Rating	DFID’s action forward / To note – dates are revised from initial proposals to/from Internal Audit to reflect most recent situation.
1	Risk management / Project risk – IFC carries out due-diligence of all projects and their partners as a part of its Integrity Due Diligence standards. DFID relies on IFC’s policies and operational procedures for the risk assessments. IFC needs to report to DFID as to how the standards are applied in practice in order that DFID has a clear understanding of the risk involved. / Risk register – The programme does not have a risk register and of the ten risks identified in the business case the delivery plan captures only three. / Fraud and corruption – There is no consideration of fraud and corruption risk at programme, portfolio or project level		Project Risk: DFID to engage with IFC and request and review the current methodologies IFC use for risk management. By July 2015 / Risk Register DFID team will develop a risk register which will be incorporated within the Delivery Plan and therefore subject to quarterly review. By August 2015 initially and reviewed quarterly / Fraud and Corruption: IFC to provide assurance as to how it includes fraud and corruption risk in its implementation and due diligence. By August 2015
2	Investment risks / Anchor funding – Risk that DFID funds, as anchor donor, are spent without a verifiable output to measure success is to an extent crystallised funds could potentially represent a sunk cost. / Pricing structure – Risk that DFID is over-exposed in comparison with other donors and that IFC is unable to leverage further capital. There is also the risk of loss on investment as contributors’ funds in the investment component do not require a positive return on investment, although this was not the original intention of DFID’s contributions to the Initiative.		Anchor Funding: This review looks at many of the issues which Internal Audit raised. DFID to review the results of the MTR before making the final disbursements (£10.5m in all, although £4.2m for Investments). By Sep 2015 / Pricing structure: IFC to provide evidence of compliance with the risk sharing criteria in the AAs. By December 2015
3	Financial risk / ODA reflows – It remains unclear as to how DFID propose to budget for these potential reflows. The BC provides that the protocols to manage reflow will be agreed between IFC and DFID after the MTR in 2015. This action needs to be prioritised given that any reflow will have negative ODA implications. .		ODA reflows – IFC and DFID to agree a protocol and negative ODA implications for management of and the final destination of reflows at the time of the MTR. Commence discussion on this in July 2015 with a view to firm up options by end of 2015.r.
4	Delivery chain and programme due diligence / Due diligence of IFC – The BC governing this Initiative pre-dates DFID’s Due Diligence Framework. Assurance on fiduciary and other risks is provided solely through the Multilateral Aid Review process which is not very detailed. / Downstream partners and delivery chain – DFID is relying solely on IFC’s operational systems and procedures to assess and monitor risks down the delivery chain.		Due Diligence of IFC: DFID to continue to liaise with the International Financial Institutions Team (IFID) in DFID about Institutional Review. The team plans to undertake Due diligence of IFC as a part of the development of the BC for the DFID-IFC Dev Cap programme. By November 2015 / Downstream Partners and Delivery Chain: DFID programme team has already started utilising DFID Advisers in Country Offices to validate and gather more information about the operation of the projects in their country. This practice will continue and the programme team will make field visits to the extent possible under the available staff resources and travel budget. Ongoing from July 2015 (onwards)
5	VFM and capacity / Delivery plan – The BC has a VfM matrix which needs to be better integrated in to the the Delivery Plan.		VFM in logframe: DFID to use the Delivery Plan to monitor VFM (ongoing) as well as work with IFC on how best to incorporate VFM outputs in the logframe By Sept 2015
6	Operational framework / Maintenance of Quest – Full programme documentation was not maintained and up to date on Quest including final copies of the framework agreement and executed documents. / Amendments –The amended administration agreements make reference to the original intended structure. This is a control risk and there is a concern that documents are not updated on a timely basis.		Maintenance of Quest: PSD to review Quest documentation as recommended. By June 2015 / Amendments: To record the operational changes outside of the agreement. By June /July 2015
7	Investment oversight. / Selection criteria – DFID not seek assurance that the changes to the criteria included within due diligence assessments for Partner Financial Institutions (PFI) are being approved by the Donor Steering Committee. / Geographic scope – The needs assessment has not been updated since the administration agreements were executed. / SME definition – Through the IFC’s ability to identify a definition of SME during the assessment of each project there is a risk that investments could be made into businesses that do not meet the criteria under the DFID log frame. / Products and projects – PSD relies upon the programme project approval processes being followed and does not obtain assurance that this is carried out.		Selection Criteria: Confirmation on IFC adherence to Investment selection originally criteria submitted to DFID or explanation of changes. DFID is following up on this issue. Action end September 2015. / Needs Assessment: The relevance of the programme design was assessed as a part of the AR process and the MTR consultants have assessed the relevance as well sustainability of the programme deliverables. / Investment Approval Processes: IFC to provide assurance with evidence about how the investment criteria set in the BC are applied in the investment approval process. Ongoing - to be included as part of IFC’s half-yearly progress reports.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Financial disbursement has been broadly on target and as per the protocol set out in DFID’s administrative arrangements with IFC with 86% of DFID’s disbursed and remaining due after mid-term review is finalised and actions coming from the review agreed. DFID agreed with IFC in May 2015 to provide a no-cost extension to the Programme up to March 2021 with a view to deploying the remaining allocations on deals with the tenure of six years or more.

Performance of partnership (s)
This is an IFC-run programme to which DFID is an anchor investor. The Initiative does not involve any new legal entity or structure. There is one more new funder since last year OPIC along with existing funders, IFC, EIB EC and JICA with the possibility of Government of Netherlands coming in. The initiative is seen by IFC as a “blended finance” initiative. DFID’s £40m to the investment component has been provided as a grant to an IFC Trust Fund, with the expectation that much of it will be used to finance ‘concessionality’, or first loss guarantees. But some of it is potentially returnable.

Investment decisions are taken by the IFC Board, after recommendation by the IFC blended finance committee. IFC’s own incentives work well to deliver DFID’s objectives. It wants to use DFID money only where absolutely necessary to ensure lending or achieve additional developmental benefits, so as not to distort the market for its commercial operations. DFID gets to comment on the investment proposal through (UKDel) seat on IFC Board.

Strategic direction and management oversight is provided by a Donor Steering Committee that so far consists of DFID and IFC that meets quarterly. There is more frequent engagement between the relevant PSD and IFC staff at the operational level. The relationship has operated well, although there have been periods where agreement has taken some time to reach as the issues have been detailed, difficult and not easy to resolve (for example adjustments to the terms of the Initiative, M&E arrangements, financial forecasts etc). Overall, the relationship between DFID and IFC is positive, although in-country coordination between IFC and DFID Country Offices is far from efficient as already explained elsewhere and this has been flagged several times by DFID.

Asset monitoring and control
The review was not able to scrutinise the financial and asset management aspects of the programme by IFC except by relying IFC’s internal quality assurance structure and reports. PSD receives six monthly operations/progress reports. It also receives financial statements and high level information about pipeline of activities along with IFC’s call of funds which provide assurance over the use of programme assets and the implementation of projects.

G: CONDITIONALITY
Not applicable – delivered through IFC. PSD does not provide any funding directly to Financial Institutions or partner governments.
H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
An independent mid-term review was undertaken by Dalberg Global Development Advisors and the Beecher Analytics Group with draft report submitted to DFID in June 2015. They were contracted by IFC in June 2014 to evaluate the Initiative’s impact vis-à-vis the Initiative’s theory of change and expected results and DFID provided input into the Terms of Reference. They i) designed methods for the midterm and end term performance review, ii) pilot test data collection and iii) implemented the midterm performance review.

The Midterm Review was commissioned more than two years before what will be the true mid-point of the initiative. At the time of the review, 11 out of 16 IS (loans), 15 out of 16 IS ( RSF), 18 out of 35 AS and 15 out of 16 financial infrastructure have yet to start reporting. As a result, it concentrated heavily on leading indicators of impact and focuses as much on defining methodologies for assessment as it does on assessing the Initiative to date. For example, the review was unable to fully assess whether the Initiative is on track to meet targets of reaching firms owned or managed by women or jobs created due to the Initiative. In addition, the review has failed to report on the attribution of the results to the programme as well as to DFID despite DFID insistence on this being in the Terms of Reference. Furthermore, the Review concluded that the overall evidence to establish a direct causal linkage between the IFC’s intervention and the subsequent changes at the PFI level was not strong enough to make firm statements about causality. DFID is currently under discussion with IFC about attribution and developing a methodology for it.

Monitoring progress throughout the review period
All projects under the Initiative are subject to IFC’s governance and M&E standards. Projects under this Initiative are subject to the same SME results framework and reporting requirements as applicable to all other advisory and investments services projects of IFC. Results data for projects funded through this Initiative are collected and reported through the IFC’s Results Measurement Network (RMN). Data for this Initiative go through three stages of IFC’s internal data control and assurance by:-
1. IFC’s in-country staff leading on the project who provides quality assurance for the data collected and reported by a PFI;
2. RMN staff for the relevant region; and
3. A senior staff of IFC’s Development Impact Department based in the HQ.
The data is finally reviewed by IFC’s external quality assurer of impacts and results, namely Ernst Young.

IFC undertakes supervision missions to projects and continue to do so over the life of the Initiative so that IFC’s project M&E team can verify their results and can engage their clients to get a better understanding of how the PFI's clients have been impacted by this Initiative. Going forward IFC has said it will implement the following steps:
- include M&E/data reporting clauses in the legal agreements with PFIs, as it is essential for IFC staff to have a legal basis for requesting data
- integrate M&E into project cycles so that questions are being asked at appropriate times in the project cycle, not too early or too late.
- maintain an M&E specialist for the programme to work with regional staff and clients on ongoing M&E, which will also support an ongoing learning agenda
- continue to communicate with staff and management about the critical nature of the M&E programme and specific demands on staff and clients going forward.

Dalberg and Beecher have also developed a methodology to track and estimate the Initiative’s impact on job creation. It will pick up to 10 Initiative-funded projects which will be subject to in-depth studies (seven undertaken during the mid-term review) and 2 projects that will be subject to experimental design. This work will be informed by and supplemented with work conducted by the World Bank’s Development Economics Department and IFC’s Let’s Work program. The DFID programme team will continue to provide direction to the consultants to ensure that the evaluation addresses key questions important for DFID, including issues around validation of data, attribution of results, impact on behaviour of the PFIS as well the DFIs, measurement of the impact on jobs etc. PSD is also in discussion with IFC how the mid-term review and further evaluation work can examine the wider impact of IFC’s advisory services on PFIs – i.e. how IFC is building capacity, increasing risk appetite etc.

The majority of the £2.4m M&E budget is earmarked for the mid-term and post evaluation of the Initiative and measurement of impact on jobs. Part of it will be used to contribute towards the learning agenda (e.g. in-depth case studies) to determine the link between SME finance and jobs. The M&E budget also pays for staff costs of an M&E Specialist working on the Initiative full time as part of the coordination unit, and proportional share in cost of IFC’s M&E Specialists who dedicate more than 10% part of their time to the Initiative.

Review Process
- DFID staff engages regularly with IFC with progress report submitted every six months to monitor its effectiveness.
- The annual review was led by PSD advisor from DFID Ethiopia with field visits undertaken by DFID PSD Advisers in Tanzania, Pakistan, Bangladesh, Mozambique. Inputs from other parts of DFID, particularly those that have SME-related programmes and/or policy responsibilities were incorporated. The review is based on six monthly progress reports from IFC, and interview with IFC’s regional and Head Quarter staffs responsible for management and implementation of the Initiative and draft report and interview with Dalberg who undertook the Mid-term performance review.
List of Documents
- Business Case as approved by SoS in January 2012.
- Latest draft Annual Progress Report from IFC (May 2015)
- Latest available results data reported by IFC against the logframe indicators.
- Presentation by IFC at the last Donor Steering Committee Meeting on May 2015.
- Last year’s DFID Annual Review Report June 2014
- Draft Mid-Term Performance Review – Dalberg 08 June 2015
- Documents relating to Trust Fund arrangements with IFC