Annual Review - Summary Sheet

Title: Support to the World Bank project ‘Enabling the Business of Agriculture’
Programme Value: £3,000,000		Review Date: 04/11/2015
Programme Code: 204123	Start Date: 18/11/2013	End Date: 31/08/2016

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
This is the second annual review of the Enabling the Business of Agriculture project (EBA), a 3-year programme commencing in 2013.

The EBA team have successfully completed the second phase of the project drawing on expertise across two departments in the World Bank – the Agriculture Global Practice and the Global Indicators Group in the Development Economics Vice Presidency (DEC). The programme is broken up into two components: (i) development of regulatory indicators relevant for the agriculture sector and (ii) development of more policy and practice focused metrics that provide a deep dive assessment of the enabling environment in agriculture.

On the first component, data collection has scaled up from 10 to 40 countries, meeting the 2015 target in the logframe. These data have been coded to build indicators for six core topic areas (seed, fertilisers, transport, mechanisation, access to markets, and finance). Two categories of indicators have been developed - legal indicators and time/motion indicators – which draw on the development of a scoring methodology. The EBA project team have identified three additional topic areas where indicators can be developed at a later date: livestock, ICT and water. Indicators for the land topic area are being developed following a more in-depth consultation. Both gender and environmental sustainability have started to be integrated into the relevant topic areas during the last year. The programme’s second report is due for launch in December 2015.

On the second component, the EBA team have made progress in developing a suitable approach to this set of variables – market metrics (MM), however, this approach is not yet finalised. The work in progress methodology builds on work during year one, which recognises the difficulties in collecting comparable and objective data. To assist with this task, a Technical Advisory Committee (TAC) has been established with representation from across the World Bank Group. This group will focus on ensuring that the EBA indicators and MM are relevant, formally providing the necessary counsel to ensure that they inform policy dialogue, analysis and decision-making.

After concerns in the first year surrounding insufficient communication about the project, the EBA team have proactively sought opportunities to engage with stakeholders globally. These include engagement with government representatives, private sector players, CSOs, trade associations and contributors to the project’s development.

Overall, feedback from interviews with stakeholders – members of the multidonor trust fund, CSO representatives and DFID country offices - have indicated satisfaction with the technical rigour, discipline and responsiveness of the EBA project team. However, concerns remain over the limited timeframe of the pilot phase; the eventual buy-in of the EBA indicators; the integration of gender and environment as topic areas; and the accessibility of the EBA website and first year report.

Summary of recommendations for the next year
1. Ensure the release of the 2015 EBA materials and data are more consumable, public-facing and accessible to a wide range of stakeholders, including policy makers by January 2016
2. Work with the EBA team to scope out what the second phase of the programme should entail by March 2016.
3. Assess the extent to which gender and environment are integrated in the year two report and ensure a strong focus for year 3. Create a plan of action by February 2016 if necessary.
4. Reduce the number of countries the EBA team collect data on from 80 to 60. A scale up from 40 to 80 has been noted as being too ambitious and could impact on the timeliness of both these indicators and the development of the MM.
5. Work with the EBA team to ensure the pilot countries are aligned with DFID priorities and are focusing on the most pertinent issues for smallholder agriculture and agribusiness development. We will follow up with the EBA team, early 2016 to assess progress. indicators and the development of the MM.
A. Introduction and Context

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

Outline of the programme:
The Enabling the Business of Agriculture project (EBA) was initiated in 2013 following a call by the G8 on the World Bank “to develop options for generating a Doing Business in Agriculture Index.” The project supports Global Goal 2 of ending hunger, achieving food security, improving nutrition, and promoting sustainable agriculture. The project continues to support DFID’s current strategic framework for economic development as well as DFID’s recently published policy framework on agriculture.

The primary objective of the EBA is to incentivize policy makers to streamline regulations and policies that can contribute to a more enabling environment for agriculture and agribusiness. By measuring regulations, policies and infrastructure that affect the emergence and sustainability of agriculture-related businesses, the project aims to provide policy-makers with an evidence-backed tool that can be used to cultivate an environment in which agribusiness can thrive. By incorporating deep-dive analyses into this tool, the indicators will benefit from the added breadth and context-specific evidence not currently covered in regulatory indicators.

The EBA is funded through a multi-donor trust fund to which The Department for International Development (DFID) are contributing £3mn over 3 years. DFID’s burden share is 21%. Other donors include USAID, DANIDA, the Bill and Melinda Gates Foundation and the Dutch Ministry of Foreign Affairs. The EBA is housed in the World Bank Group, benefiting from expertise from the Agriculture Global Practice and the Global Indicators and Analysis department (GIA) at DEC, with over ten years of experience of implementing the Doing Business project.

The EBA has two main components: (i) Regulatory indicators and (ii) Deep-Dive policy and practice assessments, now known as Market Metrics (MMs)

1. Regulatory indicators: these indicators focus on the laws and regulations that are the most important for agricultural productivity in countries around the world – developed and developing. The indicators will be consistent and comparable across economies, enabling benchmarking to take place.
2. Market Metrics (MMs) multi-country studies: these metrics will examine a broader range of factors affecting agricultural productivity, market access, and the policy environment for agriculture. MMs will bring new benchmarks to the attention of policymakers and will provide a number of important new metrics to better enable policy-makers to establish their country's position in relation to their neighbours and countries at a similar stage of agricultural development.

Taken together, these two components will develop indicators in six core topics: mechanisation, accessing financial services, strengthening seed systems, improving fertiliser supply, transporting and selling agricultural goods. Due to the sensitivities around the regulatory environment for and implementation of laws for registering agricultural land, this topic areas is undergoing further testing and consultation, led by the World Bank’s Lead Economist covering land.

Three further topics were identified for initial testing during the project’s first year: contracting agricultural production, electrifying rural areas and connecting farmers to information. Comparable data for contract farming across the spectrum of countries the EBA analyses were not available, meaning it was dropped from the second year report. Rural electrification was also dropped given the minimal value addition compared to the coverage under the Doing Business Indicators of access to energy. Connecting farmers to information, or ICT (information communication technology) has been taken forward. For year two of project implementation, four further topics have been explored: water and livestock, with gender and environmental sustainability assessed across the other indicators.

The EBA indicators are being developed over three years, starting with a pilot phase of data collection in 10 countries in 2013, scaling up to 40 countries in year 2 and 60 countries in year 3. The chosen countries, both in the developing and developed world, represent a range of geographic regions at different stages of agricultural development. In addition, 14 out of the 40 countries selected in year 2 are countries with which DFID works directly.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The overarching outcome of the EBA is that it becomes a key policy tool to leverage indicator-informed regulatory reforms, which enable the emergence of a stronger commercial agriculture sector. Two out of the four outcome level indicators (see below) have milestones for each of the three years of the pilot project. For the remaining two indicators, results are only expected in the final year.

On the first indicator (countries' understanding of impact of agribusiness enabling environment is enhanced by dissemination of EBA reports), the outreach and dissemination strategy has been finalised and informally shared with CSOs. After the launch of the external EBA website (http://eba.worldbank.org) in December 2013, the website has now received 12,851 visits, a 328% increase over the last year, surpassing the 50% target in the logframe. Media clips have been produced but not yet used as media clips no longer represent a target area in the EBA’s outreach strategy. A recommendation for year three, based on interviews with donors contributing to the trust fund is the need for a more consumable, public-facing and accessible website to help with future uptake of the EBA indicators. On this basis DFID will:

Ensure the release of the 2015 EBA materials and data are more consumable, public-facing and accessible to a wide range of stakeholders, including policy makers by January 2016

On the second indicator (number of countries actively using the EBA indicators to inform policy improvements), there have been discussions with 8 countries on EBA indicator use: Ethiopia, Guatemala, Rwanda, Spain, Sudan, Tanzania, Uganda and Vietnam, exceeding the 2015 target of 4 countries. In efforts to further engage with stakeholders, The EBA project team have taken the following actions:

Engaged with a number of government officials in several target countries including Tanzania, Cambodia, Bolivia, Niger, Burma and Nicaragua, throughout data collection. In these efforts, the project was presented, comments were exchanged and information collected.

Targeted meetings were arranged with the governments of two pilot countries to share the results of EBA’s pilot experience – namely, Rwanda (meeting with Minister of Agriculture) and Guatemala (meeting with Minister of Agriculture and President of the Parliamentary Committee for Agriculture).

Started preparing a number of meetings, workshops and/or dissemination events to engage governments around the launch of the second year EBA report, such as Vietnam, Ethiopia, Guatemala, Sudan and Nicaragua.

Held discussions to establish partnerships with African institutions for training regional resources in the use and application of EBA indicators. However, EBA’s capacity building work will not be launched until the project’s third report is released. This will allow for the development of the programme’s indicators and metrics in a coherent and usable format, before embarking on programmes that build local capacity on its use.

Despite this progress, interviews with donors contributing into the trust fund and CSO stressed the continued need to have meaningful in-country dialogue with governments, the private sector and wider civil society groups about the purpose and vision of the EBA project to encourage future uptake of the indicators.

Overall output score and description
The overall output score after the second year of the project is A.

On the first output, the EBA has met expectations. In addition to meeting the target of 40 countries, an additional three topics – livestock, ICT, and water have been identified since last year, bringing the total to 10 indicator/indicator areas. Gender and environmental sustainability have been looked at across relevant topic areas as opposed to individual indicators areas.

There have been three separate outreach events, one more than targeted in the logframe: an EBA Masterclass at the World Bank’s Annual Conference on Land & Poverty; and two stakeholder engagement events in Tanzania and Guatemala. The second year report, entitled the EBA 2016 Report, is due to be launched in December 2015.

On the second output – market metrics - metrics are under development in 10 topic areas (secure property rights on land, access to finance, access to seeds, access to fertilizer, water, mechanization, ICT, access to transport, livestock, access to markets), 1 more than the 2015 target in the logframe. Data collection will begin in November 2015 in a set of pilot countries. Rather than a second year report, all reporting on these metrics will be integrated into EBA’s third year report. In consultation with donors, the team have focused on delivering the first output during the second year. This has delayed progress on the second output. The EBA team do however remain committed to developing this area evidenced by the establishment of a cross World Bank Group Technical Advisory Committee (TAC) that will provide guidance on the MM.

Key lessons
There are four main lessons learnt from the second year of the project:

Data collection across 40 countries: how to strategically combine desk research, remote data collection and country visits to gather the volume of data needed. This included the development of a network of contributors and contacts to help identify, obtain and confirm the required data.

How to aggregate the data for indicator development: the EBA team have developed a methodology to code and aggregate data within the different topic areas to formulate evidence-based indicators. This approach will be further advanced and applied in year 3.

Metrics beyond regulation: the EBA team have developed a better understanding of other metrics that relate to countries’ regulations but go beyond them to examine policies, implementation, practices, outcomes and/or market conditions. A final selection of this category of data is being determined, with the support of a Technical Advisory Committee put in place for this purpose. The methodological approach to collect these metrics will be developed in year 3.

The benefits of stakeholder engagement: stakeholder consultations in target countries, with the support of World Bank country offices and DFID Tanzania, helped garner interest and support for the programme, which in many cases generated key contacts, facilitated data collection and established a foundation for ongoing interaction.

Key actions
Based on the findings of the EBA team during the second year, there are three action points:

- The EBA team engaged with a range of stakeholders (see annex ii), to raise awareness of the project; collect and consider feedback; and provide additional data.
- The EBA team has identified, probed and refined indicator areas for three additional topic areas: livestock, ICT and water. Both gender and environmental sustainability have started to be integrated.
- Market metrics are being developed consecutive to formulating regulatory indicators and in year 3 will be collected and reported for a handful of countries.

As the project comes to the end of the three-year pilot phase, the EBA have started thinking through what phase II of the programme could look like, building on the lessons learnt and evidence collected during this first phase. DFID will:

Work with the EBA team to scope out what the second phase of the programme should entail by March 2016.

Has the logframe been updated since the last review?
Following the recommendations from last year’s annual review, additional topic areas were added to output one (livestock, ICT, gender and environmental sustainability). As discussed at the June 2015 donor meeting, rural electrification was removed owing to the similarities, and therefore low value addition, with the Doing Business indicator on access to energy.

Indicators for output two have remained the same. While it was recommended that these be updated in the last annual review, the project has delayed developing an approach to the market metrics. The team have prioritised the development of the first set of indicators following consultation with the donors contributing to the project in November 2014.
## C: DETAILED OUTPUT SCORING

Output Title	Development and roll-out of Doing Business in Agriculture methodology
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of DBA indicators developed	9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) ICT, (9) and Mechanisation. / Gender and environmental sustainability integrated across relevant indicators	Indicators have been developed for six areas: seeds, fertilisers, mechanisation, transport, finance, and markets. Indicators for the land topic area are being developed following a more in-depth consultation, led by the World Bank lead economist on land. Additional data and indicator areas are being developed for livestock, water and ICT. Separate indicators are not being developed for gender and environmental sustainability. These areas will be integrated across relevant topic areas.
1.2 Number of countries in which DBA is rolled out	40 countries	40 countries
1.3 Number of DBA reports produced.	2nd year report	Second year report (called EBA 2016 Report, to be launched in Dec 2015)
1.4 Number of workshops, seminars, conferences organised or co-organised	At least 2 events	3 events

Key Points
By the end of the second year, the EBA team successfully completed the project’s second phase with a scale up of data collection in 40 countries. Ten topics have been identified (6 core topics plus land, which is being developed following a more in-depth consultation, and 3 new topics: livestock, water and ICT, one more than stated in the original business case (with the addition of livestock and ICT)). Rural electrification was dropped owing to the similarities with the Doing Business indicators. Gender and environmental sustainability are being integrated across relevant topic areas.

The second year report is due for launch in Dec 2015. The report will present data and indicators for 40 countries. The report will look at benchmarking and will summarise the main findings across the different topic areas. Feedback from donors contributing to the trust fund about the first year report indicated that while being a thorough report, more effort is needed to make the annual progress reports more consumable and accessible in order that the project becomes part of policy dialogue. In this vein, the second year report will be much shorter and focus on headline results. The website has also been updated. Visitors can now compare data using interactive tools, much like the Doing Business website.

Summary of responses to issues raised in previous annual reviews
The previous annual review recommended that access to information technology (ICT); livestock, gender and environment were added to the list of topic areas to cover in year two. The EBA have informed donors that gender and environment, given their cross-cutting nature, are being integrated into other topic areas. Data were collected on environmental sustainability during year 2, particularly as it relates to seed (protection of genetic biodiversity) and water. Rather than collecting specific data on gender-related issues, a number of especially sensitive topics – such as land tenure, mobile banking for financial access and water use rights – have been examined through a gender and environmental sustainability lens. Brief sections of the report will feature early findings. Specific areas within these topics will be targeted and additional data collected during the programme’s third year. While scoring these topics is still being evaluated, many data will be drawn into the overall analysis and benchmarking of countries, and results published in the next report.

Until the second year report has been finalised it is difficult to determine how well gender and environment have been considered, and whether there is room for a stronger focus. This is an area DFID will follow up on, following the release of the report. Should the issues of gender and environmental sustainability be deemed weak, we will develop an action plan with the EBA team and the donor group to ensure there are properly considered and integrated in year 3.

Recommendations
1. Assess the extent to which gender and environment are integrated in the year two report and ensure a strong focus for year 3. Create a plan of action by February 2016 if necessary.
2. Reduce the number of countries the EBA team collect data on from 80 to 60. A scale up from 40 to 80 has been noted as being too ambitious and could impact on the timeliness of both these indicators and the development of the MM.

Output Title	Development of Deep Dive multi-country studies
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of DD indicators developed	9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization	Metrics are under development in 10 topic areas: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization (10) ICT
2.2 Number of DD reports produced	2nd Year Report	All reporting on these metrics will be integrated into EBA’s third year report.

Key Points
Metrics are under development in ten topics areas, one more than targeted in the logframe. Data collection is due to start shortly, at the beginning of November, 2015, in a set of pilot countries and reported on in year 3. These pilot countries will be selected in consultation with the donor group. While there has been progress the delays in developing this approach mean this output score B, moderately below expectations.

In year 2, the EBA team have worked towards developing a more suitable approach for this set of variables, however this is not yet finalised. In February 2014, a document proposing an approach for year three, and containing an analysis of the subject as well as a summary of the EBA’s pilot year experience with the MMs was presented to the donors. A decision was taken to prioritise the development of the regulatory indicators for the EBA 2016 Report. In the meantime, the MM and the required methodology are being further refined.

A Technical Advisory Committee (TAC) has been established to help inform this process. It will have a central role in discussing and determining the set of market metrics that the EBA team will focus on. In addition, the EBA team are developing research on the linkages between regulations and agriculture transformation. The research will pull together existing literature on how countries move across different stages of agricultural development. It will study the linkages between policies, regulations and other critical factors with the development of the agribusiness industry. This will help inform the usefulness of both the MM and the regulatory indicators.

Summary of responses to issues raised in previous annual reviews
The EBA team and the wider World Bank Group remain committed to this part of the programme, evidenced by the establishment of the TAC and the research into linkages between regulations, agriculture development and economic transformation. The log frame has not been updated owing to a delay in moving forward on this area.

Recommendations
Progress on the MM in year three is critical for the overall success and buy-in of this project for policy makers and agents of the agriculture sector. We will:

Work with the EBA team to ensure the pilot countries are aligned with DFID priorities and are focusing on the most pertinent issues for smallholder agriculture and agribusiness development. We will follow up with the EBA team, early 2016 to assess progress.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Two drivers of vfm were identified in the EBA business case: (i) the design and development of indicators (economic efficiency) and (ii) the take up and impact of DBA and DD indicators in the decision making of policymakers in developing countries (economic effectiveness).

VfM performance compared to the original VfM proposition in the business case
Economic efficiency
The business case identified three indicators to assess the value achieved in input purchasing (economy) and how these are converted to outputs (efficiency):

Proportion of total costs allocated to value-adding operations: operations (research, indicator development, data collection) are EBA’s key value-added operations and resources here should be maximised. Over the life of the project (3 years), the cost of management, consultants, staff and travel and accommodation needed for field work will constitute 80% of total costs. By the end of year two, the project has spent two thirds of the total allocated budget for operations, making the project on track to use the full amount by the end of year three.

Cost per report produced: EBA will produce three synthesis reports (analysing data from 10, 40 and then 60 countries). Expectation will be that consultant and travel costs will increase only slightly over time, given an adequate data collection model using remote data gathering and local consultants, reflecting an accelerated expansion of EBA into 60 countries by year 3. The total cost per report produced is USD $132,000, which includes preparation, editing, formatting, translating and printing, in addition to staff time, web-format reporting, and distribution of reports. When compared to the Doing Business report which costs $425,000 (and has over double the number of copies printed and mailed), the cost for the EBA report represents good value for money.

Communication costs: outreach events to facilitate country consultations and obtain policymakers’ buy-in are critical to EBA’s longer-term success. In recognition of this, the budget allocated to communication activities has increased from 5% in year one to 12% in year two. Annex ii) provides details of the year 2 communication activities, which reflect this scale-up.

Economic effectiveness
Measures to track EBA’s effectiveness include:
- Instances where EBA research and reports have been used by countries to inform policy improvements.
- Evidence of wider EBA uptake and use of credible methodology, measured by media citations, website visitors, journal and article references.
- Number of regulatory reforms undertaken using the EBA indicators.
- Process of agreeing to reform, which is consultative and time and cost-effective.
- Wider impact of policy changes that are assessed in a time and cost-effective manner.

It is still too early to assess the overall impact of the programme, specifically the uptake of reforms and regulations. The increasing number of hits to the website and a more targeted 2015 report should help increase awareness of the project – to both policy makers and people affected by any regulatory changes.

Assessment of whether the programme continues to represent value for money
Additional financing was granted to the EBA team from USAID to develop an outreach strategy, following concerns raised in year one. This has helped focus the EBA team on the overall impact of the project. The EBA team have built up a data collection methodology, which has meant the team have kept within the original budget for the pilot project. Under the current assessment, this project still represents value for money.

Quality of financial management
DFID’s £500,000 contribution for this financial year has been disbursed, and the next disbursement of £500,000 is due to be disbursed in March 2016. Neither the current approved budget nor the forecasting profile is expected to change over the next financial year. The World Bank’s next annual audit is due to be released 6 months following the end of the Bank’s fiscal year.

Date of last narrative financial report	September 2015
Date of last audited annual statement	n/a

E: RISK

Overall risk rating: Medium

What are the risks and how these will be managed?
Two main types of risks were highlighted in the business case: (i) the purpose and methodology of EBA is not well understood; and (ii) the programme cannot achieve buy-in among policymakers and key users. The risks, mitigation strategies and updates on any progress made and changes in context are provided in the table below.

Overview of programme risk

Risk identified in business case	Risk rating	How will risk be managed?	Annual Review Update
Methodology
Confusion over what the indicators do and don’t measure.	Medium	EBA to continually communicate the range and limits of the data.	The EBA team has communicated the range and limits of the data through the 2014 pilot report, the EBA website and engagement/dissemination meetings. There is also a description in the upcoming 2016 report, due for launch in December 2015.
Regulatory indicators and MM are not well integrated. The programme narrowly focuses on legal and regulatory indicators.	High	Brand/position the regulatory and MM as one core product with two separate but complementary components working in a synergistic way.	MM are currently being identified and set up for piloting in FY2016. / Careful selection of MM is taking place, ensuring coherence with regulatory indicators. The formation of a Technical Advisory Committee will also help ensure relevance and integration of regulatory indicators and non-regulatory metrics
Significant variations between the regulatory frameworks for different agricultural commodities limit the comparability of EBA indicators.	Medium-Low	Indicators will use a standardised case study to allow comparison across different countries.	A standardised case methodology has been developed and applied during the last 2 years.
Indicators produced are not considered to be rigorous and evidence-based.	Medium-Low	A broad group of stakeholders (including researchers, target users, subject-matter experts) should be consulted and their advice should inform indicator selection and subsequent refinements.	Data points used to build indicators are backed up by documented laws and regulations, and verified by target country governments and World Bank country offices. Technical and operational experts are consulted to ensure the relevance of the indicators and data points, and a broader set of stakeholders engaged.
Countries selected are not aligned to programme objectives.	Low	The World Bank will consult donors on the country selection process. A geographically diverse set of countries at different stages of agricultural growth will be selected to allow for sub-comparisons.	Countries were selected in consultation with donors and World Bank agricultural operations experts. Geographical, income-level and agricultural transformation diversity, as well as relevance to programme objectives, was considered and ensured for country selection
Insufficient resources to take forward the MM indicators	Medium	Ensure a robust approach is adopted and integrated into the overall vision of the project.	EBA has been developing a proposed approach for piloting a set of MM in a small number of countries, with the budget and resources set currently available to the project. This can be expanded and scaled up later.
Insufficient attention given to gender and environmental sustainability	Medium	Integration across relevant topic areas such as land, financial access and water	Gender and environmental sustainability to be integrated into the 2015 report.
Take-up and Buy-In
Lack of government buy-in	Medium	Governments of countries in which EBA will be rolled out must be informed and consulted.	Several engagement opportunities have been developed with governments. / In year 2, EBA met with the Minister of Agriculture of Rwanda and Guatemala to discuss EBA developments. / The EBA team and World Bank country office specialists have also held a number of meetings and discussions on EBA with several country government representatives in Ethiopia, Vietnam, Spain and Tanzania, amongst others. In addition, a number of meetings/workshops are currently being arranged for after the second year 2016 Report is launched.
Programme activities do not lead to regulatory changes.	Medium	EBA should continuously assess opportunities to affect changes in the regulatory environment related to the project’s interventions.	A dissemination strategy and corresponding arrangements are being developed to follow up the second year report. This includes meetings/workshops in at least 3 regions and presenting the EBA at several key conferences.
Pressure over regulatory indicators and country rankings lead to a pushback on the EBA.	Medium	EBA should carefully consider pros and cons before proceeding with country rankings.	In EBA’s communication and engagement efforts, it has been clarified that for the time being rankings are not being considered as a mechanism. For the second year report, a scoring and colour coding mechanism will be implemented, which allows for benchmarking without doing rankings.
Unintended consequences	Medium	The programme will devise a way to model the expected policy responses from the indicators to ensure against negative outcomes.	Research on the regulatory environment and links to agriculture transformation should help inform the sequencing and impacts of these types of indicators.
Governments narrowly target their reform efforts to trigger the time and motion indicators only.	Medium	EBA should encourage a broad reform discussion as opposed to narrow indicator-focussed reforms.	Beyond time and motion indicators, legal indicators have been developed and scored for the second year report, thus offering a broader approach to the regulatory framework. MMs are being identified and will be collected in the next cycle of data collection, to broaden the reform discussion around the enabling environment
The process of agreeing to policy changes is not sufficiently inclusive and consultative at country-level.	Medium	The programme should pay attention to not only encouraging policy reforms, but how they have been achieved.	The EBA team has increased their outreach activities, ensuring a wider range of stakeholders are involved in the process.
Programme is not sufficiently proactive to engage stakeholders.	Medium-Low	Specific actions including a strategic outreach plan should be a central component of the programme.	A stakeholder engagement plan has been implemented over the last year, which has included dialogue meetings, participation at topic specific conferences, communication strategy and online discussions (further details in annex ii))

Outstanding actions from risk assessment
The majority of risks to the project’s ability to deliver results remain relevant. However, a number of risks have had their risk rating downgraded to low or medium-low. “Insufficient resources to take forward the MM indicators” and “insufficient attention paid to gender and environmental sustainability” have been added as risks for the forthcoming year.

A particular risk highlighted by interviews with donors contributing into the trust fund, and related to the second set of risks, is the future uptake of EBA indicators and their ability to bring about reform. To help mitigate this risk the EBA project team have taken a number of steps, which address the EBA’s long term impact. These include:

Dissemination activity: around the release of the second year report. This will focus on policy dialogue to ensure the data and findings of the report start generating impact.

Research into and the development of a matrix that allows for more relevant benchmarking. The matrix will help explain how countries move across different stages of transformation. It will study the linkages between policies, regulations and other critical factors with the development of the agribusiness industry. Particular attention will be given to the correlation between the matrix developed and the new dataset generated by EBA. These correlations and EBA data will be cross-referenced to existing literature and discussed with well-acknowledged experts contributing to new or on-going research efforts.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The EBA team have delivered against their milestones. These are slightly out of sync with the original business case owing to a delay in starting operations in the first year. The new project cycle means reports will be finalised by the end of the calendar year, rather than in the summer. The second report is therefore on track to be publicly available in December, 2015.

Performance of partnerships
The EBA team have remained responsive to the donors in the multidonor trust fund. They have kept donors up-to-date on progress and informed the group on proposed changes as well as the process to make decisions. The multidonor trust fund has met face-to-face once in year 2 in June 2015 and had one phone call. There has also been regular email correspondence allowing for more real time communication between the EBA team and the donor group.

Both the head of the Agriculture Global Practice (the World Bank) and the head of the Global Indicators Group (IFC) have attended the donor meetings.

Asset monitoring and control
Not applicable

G: CONDITIONALITY

It was not deemed relevant to use the partnership principles for management and monitoring when the programme was approved.

H: MONITORING & EVALUATION

Evidence and evaluation
As set out in DFID’s business case, the EBA is due for a mid-term evaluation following the release of the second year report. DFID will work with the EBA team and the donors in the multidonor trust fund to ensure the evaluation helps inform:

- the likelihood of the programme having an impact on countries’ regulatory environment;
- how best to integrate gender and environmental sustainability;
- the poverty impact of the reforms covered under the EBA; and
- areas to focus on for a second phase of the EBA.

Monitoring progress throughout the review period
The EBA monitoring and evaluation follows World Bank standards and requirements for project implementation. Two key steps highlight this process:

Concept Note approval – at the beginning of each year of project implementation, a concept note and work programme for the year is developed, reviewed and approved to determine deliverables and ensure alignment to project goals.

Decision Making – review and approval of the project deliverables, in this case the yearly report, ensuring that the proposed goals are met.

For this annual review, all of the donors contributing to the project were consulted and their views on the project gathered. The donor group has been working effectively, consulting on a number of issues and actively feeding into the project.

Views were also gathered from civil society representatives based in the UK and DFID Tanzania.

Annex i) LIST OF ACRONYMS

AES: Agricultural and Environment Services (AES) department in the World Bank Group
AR: annual review
CSO: Civil Society Organisations
DANIDA; Danish International Development Agency
DB: Doing Business
DBA: Doing Business in Agriculture
DBI: Doing Business Indicators
DD: Deep Dives
DEC: Development Economics Vice Presidency
DFID: Department for International Development
EBA: Enabling the Business of Agriculture
FY: financial year
GIA: Global Indicators and Analysis department in the World Bank Group
ICT: Information and Communications Technology
MM: Market Metrics
TAC: Technical Advisory Committee
USAID: The United States Agency for International Development
WBG: World Bank Group

Annex ii) EBA stakeholder consultations/engagments, 2014-2015

National Dialogues
Date	Location	Details
Dec 2014	London	Stakeholder Engagement. The EBA team met with over 30 individuals, comprised of the international CSO community, private sector supporters and targeted government representatives, to receive feedback on the EBA first year progress report.
March 2015	Vietnam	Vietnam Stakeholder Engagement. In small one-one-one meetings, the EBA team met with six representatives from Vietnamese think tanks and development partners during the team’s data collection mission.
March 2015	Burkina Faso	Burkina Faso Stakeholder Engagement. The EBA team met with 8 civil society stakeholders in a dialogue session during its data collection mission to learn about the most pressing agricultural issues in Burkina Faso
March 2015	Burundi	Burundi Stakeholder Engagement. The EBA team met with 7 representatives from Burundian farmers associations in Bujumbura. In the meeting, the farmers spoke about land access, legal status of farmers’ cooperatives and other pending issues in Burundi.
March 2015	Tanzania	Tanzania Stakeholder Engagement. The EBA team conducted a dialogue with 20 civil society, private sector and development partners in Dar es Salaam to receive feedback on the current EBA indicators and dataset.
April 2015	Guatemala	Guatemala Stakeholder Engagement. The EBA team met with 23 stakeholders—including a number of current and past contributors—in Guatemala to update them on EBA project status since EBA’s last mission to the country and listen to input on additional data points EBA could cover.
Regional and Global Convening
March 2015		EBA Masterclass at the Land & Poverty Conference. The EBA land topics team held a session at the World Bank’s Annual Conference on Land & Poverty with 8 attendees. The MasterClass reviewed the current methodological framework of the EBA project and then delved into the land topic in detail, highlighting the methodological constraints of data collection and surveys in trying to understand a country’s regulatory and institutional framework for the land sector.
March 2015		NEPAD’s CAADP Partnership Platform. An EBA team member attended CAADP‘s annual partnership meeting in order to network with civil society, governments, and the private sector. EBA specifically engaged the CAADP Non-State Actors Forum, which led to a number of introductions of potential stakeholders and partners.
May 2015		International Seed Federation Congress. EBA Team members of the seed topic attended an international meeting in Krakow to present on the seed topic and recruit additional contributors and input for the seed.
June 2015		International Food and Agribusiness Management Association (IFAMA) conference. The EBA team attended IFAMA’s annual convening in St. Paul, Minnesota in order to network with contributors and new stakeholders.
June 2015		Global Animal Health Conference. A member of EBA’s livestock topic team attended this conference, which brought together individuals from regulatory agencies, industry, academia and international organizations to discuss solutions to promote efficiency and effectiveness in veterinary product registration and introduction into the market. The conference focused on developing countries and on how to enable the widest availability of high quality, safe and efficacious products with an emphasis on Africa. It was a great networking opportunity to collect data, engage stakeholder, and recruit additional contributors.
August 2015		World Water Week. The EBA Water Team Leader attended the World Water Week in Stockholm in order learn from the world renowned event about key issues confronting the water sector, so as to further develop the “access to water” topic. Attendance was also an opportunity to network with the range of participants, with whom EBA can build relationships on technical issues and to invite them to be partners in contributing to research at the country level
Online & Telephonic Roundtables
Feb 2015		Global CSO Telephonic Roundtable. The EBA team joined the World Bank’s monthly global CSO telephonic roundtable. In the call, the team announced our drive for survey contributors and took questions related to current indicators and methodology.
Targeted Government Outreach
March 2015	Rwanda	The EBA team met with ministerial and civil servants in Kigali to discuss EBA and its application and utilization in Rwanda.
April 2015	Guatemala	The EBA team met with policymakers in Guatemala City in order to review the implications of the 2015 report for Guatemala and update them on the status of the EBA project since the team’s last visit in late 2013.
Listening/Learning Tours
March 2015	Tanzania	Meeting with Kizapara Agricultural Marketing Primary Cooperative - On Tuesday March 24, members of the EBA team met with leaders and representatives of the Kizapara AMPCO, located about 2 hours southwest of Dar es Salaam. In speaking with members of the cooperative, the team learned about the issues they face including scalability, access to markets, water supply, and financing.
		Meeting with Ms. Fatuma Kihambwe – Following the meeting with the cooperative, the EBA team traveled down the road to listen to Ms. Kihambwe who grows cassava, pineapples and cashew nuts on five acres. In speaking with her, Ms. Kihambwe could potentially benefit from joining a cooperative, but it would need to be worth her time and financial resources. The EBA team’s exploration of regulatory and policies related to financial inclusion and accessing markets have relevance for farmers like her.
		Visit with Ms. Fatma Riyami at Naturipe Kilimanjaro Ltd. - In order to learn more about the issues agri-processors experience, the EBA team spent some time with the Founder and CEO of Naturipe Kilimanjaro, Mrs. Fatma Riyami, at her office in central Dar es Salaam. Profiled by the World Bank’s infoDev initiative, Naturipe is a family-managed business and sells a number of food products in Tanzania and for export to the Middle East. Ms. Riyami spoke to us about her company and its business plan, including its challenges in growing a family business.
Communication channels
Electronic Updates. The EBA team has worked to begin communicating more often and more directly to its external stakeholders and contributors. To enable this, the team has consolidated a contact list in order to manage these communications better. These communications have been sent out via direct emails from EBA management and in the World Bank’s global civil society newsletters.
LinkedIn. The EBA team has established a LinkedIn group as a tool to manage and better engage current and future survey contributors. It is a platform for sharing updates on the EBA project along with general news and trends in the global agriculture sector. The group currently has 198 members with plans to recruit more contributors as EBA prepares for new stages of external engagement.
Website. The EBA website is a core component for EBA’s communications. Under the Stakeholder Engagement Plan, minor changes have been made to clarify language for recruiting survey contributors. More extensive changes have been proposed that include a set of “How to Engage” pages for sharing feedback and input to the EBA project. These pages would also have a calendar of upcoming events and moments for when stakeholders and external partners can contribute to the project.