## DelPHE Logframe Rev Aug 2012
PROJECT NAME | Development Partnerships in Higher Education (DelPHE) |  |  |  |  | AS AT | 2013-06-30
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013
Higher Education Institutions (HEIs) acting as catalysts for poverty reduction and sustainable development. | Progress towards meeting MDG1 in DFID's Priority countries. | Planned | 2007 | 50% of DFID Priority countries on target to meet MDG1 | 60% of DFID Priority countries on target to meet MDG1 | 70% of DFID Priority countries on target to meet MDG1
|  | Achieved |  | No milestone for 2011, but milestone for 2012 is 60% of DFID priority countries on target to meet MDG1. | No milestone for 20131, but milestone for 2012 is 70% of DFID priority countries on target to meet MDG1. | Base on avaliable data - Not achieved. The DFID Annual Report and Accounts 2012-13 indicates that MDG1 Target 1 - those living on less than $1.25 a day - has more than halved since 1990, but the other two MDG1 targets are lagging behind. Of the 28 DFID priority countries listed only 7 (25%) are flagged green (on target to achieve MDG1 target 1), 1 amber (slighly off-track). 4 red (off-track), and 16 (57%) grey (insufficient data avaiable to be able judge). Clearly this a very ambitious target and difficult to measure. The impact indciator target milestones will need to be revised for any future HEI links projects.
Source
Internal DFID reporting; compiled by FCPD each year.
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013
Planned
Achieved
Source
OUTCOME | Outcome, Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Strengthened capacity of Higher Education Institutions (HEI's) to contribute towards the Millennium Development Goals (MDG's) and promote science and technology related knowledge and skills, in DFID’s priority countries. | Number of MDG-related research outputs from partnerships influencing local, regional or national policy. | Planned | 0 | 5 examples | minimum 15 examples | minimum 20 examples | i) All indicators are based on the assumption that there will be 200 partnerships over 5 years.
|  | Achieved |  | No milestone for 2011. 2012 milestone is a minimum of 15 examples. | 11 | 14
Source
|  |  | (i) End of project reports. |  |  |  | (ii) Partnerships enable a constructive contribution to national policy dialogue.
(ii) DFID Annual Review & BC annual management report
(iii) Case studies.
(iv) External evaluation of DelPHE.
| Outcome, Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | (iii) Continuation of BC Collaborative funding.
| Increased number of departments performing internationally recognised research, in support of the MDGs and science & technology. | Planned | 0 | 5 examples | 100 examples | 120 examples
|  | Achieved |  | No milestone for 2011. 2012 milestone Is 100 examples. | 157 | 157 | (iv) Partner institutions & UK HEIs continue to cover the cost of staff time & other indirect staff costs.
Source
(i) End of year / end of project reports;
|  | (ii) Documented reports from overseas stakeholders and international agencies; |  |  |  |  | (v) Partnerships are 'demand led' and sufficiently relevant to local needs.
(iii) Research papers published in national & international journals
|  | (iv) DFID annual review & BC annual management report; |  |  |  |  | (vi) Partnerships add new perspectives and bring the specialised expertise needed for effective research.
(v) Case studies;
(vi) External evaluation of DelPHE.
| Outcome, Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013
| Partnerships developed through DelPHE funding are sustained or intend to be sustained at least 1 year after completion of DelPHE funding. | Planned | 0 | 0 | 0 | Minimum of 60 partnerships | (vii) HEI programmes and professional development benefit significantly from international interaction.
|  | Achieved |  |  |  | 114
Source
|  | (i) End of year / end of project reports detail new networks & partnerships created. |  |  |  |  | (viii) Partnership outcomes contribute towards achieving the MDGs.
(ii) DFID Annual Review & BC annual management report.
|  | (iii) Case Studies. |  |  |  |  | (ix) Partnerships enable a constructive contribution to local/regional / national policy dialogue through provision of relevant new research.
(iv) External evaluation of DelPHE.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 15000000 |  | N/A | N/A | 15000000 | 100%
INPUTS (HR) | DFID (FTEs)
0.2 of Policy Officer & 0.05 of an Education Adviser
OUTCOME 1 | Outcome 1, Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Significant joint research | Number of partnerships publishing research papers in journals. | Planned | 0 | 25 examples | 110 examples | 120 examples | (i) Political, environmental, infrastructural and other factors allow projects to flourish.
|  | Achieved |  | 100 | 136 | 139
Source
(i) End of project report.
|  | (ii) BC annual management report. |  |  |  |  | (ii) Clear mechanisms in place for monitoring & evaluating partnerships.
(iii) Case studies.
(iv) External evaluation of DelPHE.
| Outcome 1, Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | (iii) Continued engagement of UK and partner HEI's.
| Additional funds attracted from Governments or International donors as a result of DelPHE partnership either during or following completion. | Planned | 0 | 2 examples | 25 examples | 30 examples
|  | Achieved |  | 5 | 63 | 63
|  | Source |  |  |  |  | (iv) Staff and students are able to participate in DelPHE activities.
(i) End of project report.
(ii) BC annual management report.
(iii) Case studies.
(iv) External evaluation of DelPHE.
IMPACT WEIGHTING (%) | Outcome 1, Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
15% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
LOW
OUTCOME 2 | Outcome 2, Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Strengthened portfolio of MDG and science and technology programmes and courses in partner institutions. | New & revised courses developed at graduate and post-graduate levels in support of the MDGs and science & technology development | Planned | 0 | 50 examples | 75 examples | 100 examples | (i) Political, environmental, infrastructural and other factors allow projects to flourish.
|  | Achieved |  | 50 | 161 | 165
11300
(i) End of project reports.
|  | (ii) BC annual management report & external facing reports. |  |  |  |  | (ii) Clear mechanisms in place for monitoring & evaluating partnerships.
(iii) Case studies.
(iv) Feedback & institutional reports from participating HE institutions.
|  | (v) External evaluation of DelPHE. |  |  |  |  | (iii) Continued engagement of UK and partner HEIs.
| Outcome 2, Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
|  | Planned |  |  |  |  | (iv) Staff and students are able to participate in DelPHE activities.
Achieved
Source
(v) New and revised courses are relevant to country need.
IMPACT WEIGHTING (%) | Outcpme 2, Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
LOW
OUTCOME 3 | Outcome 3, Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Increased staff and student capacity in partner HEIs | Numbers of staff and students benefitting from DelPHE professional development opportunities and courses | Planned | 0 | 200 individuals | 7,500 individuals | 10,000 individuals | (i) Political, environmental, infrastructural and other factors allow projects flourish.
|  | Achieved |  | 11300 | 28835 | 37613
Source
(i) End of project reports.
|  | (ii) BC annual management report & external facing reports. |  |  |  |  | (ii) Clear mechanisms in place for monitoring & evaluating partnerships.
(iii) Case studies.
(iv) Testimonials & feedback from individual DelPHE participants.
|  | (iv) External evaluation of DelPHE. |  |  |  |  | (ii) Clear mechanisms in place for monitoring & evaluating partnerships.
| Outcome 3, Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Staff, students and other DelPHE beneficiaries provide positive feedback on how being involved in DelPHE has enhanced their knowledge and skills and future opportunities | Planned | 0 | 20 examples | 35 examples | 50 examples
|  | Achieved |  | 20 | 73 | 73 | (iii) Continued engagement of UK and partner HEIs
Source
(i) End of project reports.
|  | (ii) BC annual management report & external facing reports. |  |  |  |  | (iv) Staff and students are able to participate in DelPHE activities.
(iii) Case studies.
(iv) Testimonials & feedback from individual DelPHE participants.
(iv) External evaluation of DelPHE
IMPACT WEIGHTING (%) | Outcome3, Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
LOW
OUTCOME 4 | Outcome 4, Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Increased support for gender parity in HEIs contributing to the gender MDG | Number of project team members are women | Planned | 0 | 25% of participants are women | 45% of participants are women | 45% of participants are women | (i) Equal rights and gender issues accepted & championed at highest levels.
|  | Achieved |  | 47% | 39% | 37%
Source
|  | (i) End of year / end of project reports. |  |  |  |  | (ii) Numbers of women employed by HE institutions is at an appropriate level.
(ii) BC annual management report.
(iii) External evaluation of DelPHE
| Outcome 4, Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | (iii) Female staff are able to participate in DelPHE related activities.
| Number of women taking part in research, courses & benefitting from DelPHE related activities | Planned | 0 | 25% of participants are women | 45% of participants are women | 45% of participants are women
|  | Achieved |  | 56% | 43% | 41%
Source
(i) End of year / end of project reports.
(ii) BC annual management report.
(iii) External evaluation of DelPHE
IMPACT WEIGHTING (%) | Outcome 4, Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
MEDIUM
OUTCOME 5 | Outcome 5, Indicator 5.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Improved national and international networking between partner HEI's. | Number of partnerships contributing to information, research and best practice sharing through participation in conferences and associated events at national, regional and international level. | Planned | 0 | 30 examples | 40 examples | 50 examples | (i) Political, environmental, infrastructural and other factors allow projects to be sustained and flourish.
|  | Achieved |  | 30 | 115 | 115
Source
(i) End of project reports.
|  | (ii) Case studies. |  |  |  |  | (ii) Continued engagement of UK and partner HEIs beyond DelPHE funding.
(iii) DFID annual review & BC annual management report.
(iv) External evaluation of DelPHE
| Outcome 5, Indicator 5.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | (iii) Availability of appropriate national & regional conferences.
Planned
Achieved
|  | Source |  |  |  |  | (iv) Individuals are able to secure funding and have time to participate on appropriate events.
IMPACT WEIGHTING (%) | Outcome 5, Indicator 5.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
15% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
MEDIUM
OUTCOME 6 | Outcome 6, Indicator 6.1 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013 | Assumptions
Improved institutional management and administration of partner HEIs. | Southern partner institutions are managing partnership finances to agreed criteria and in accordance with programme guidelines' | Planned | 0 | 100 partnerships | A minimum of 75% of partnerships. | A minimum of 75% of partnerships. | (i) Political, environmental, infrastructural and other factors allow projects to be sustained and flourish.
|  | Achieved |  | No milestone for 2011 but 2012 milestone is 140 partnerships. | 78% | 78%
Source
(i) End of year / end of project reports.
|  | (ii) BC annual management report. |  |  |  |  | (ii) Clear mechanisms in place for monitoring & evaluating partnerships;
(iii) External evaluation of DelPHE
| Outcome 6, Indicator 6.2 |  | Baseline | Milestone 1 | Milestone 2 | Target Date 31 March 2013
| Projects satisfactorily completed & submitting reports/supporting documentation within agreed timeframes. | Planned | 0 | 100 partnerships | 150 partnerships | 180 partnerships | (iii) Continued engagement of UK and partner HE institutions;
|  | Achieved |  | No milestone for 2011 but the 2012 milestone is 150 partnerships. | 178 | 171
Source
(i) End of year / end of project reports.
(ii) BC annual management report.
(iii) External evaluation of DelPHE
IMPACT WEIGHTING (%) | Outcome 6, Indicator 6.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
10% |  | Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | [5 empty] | RISK RATING
MEDIUM