Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Food and Agriculture Organization (FAO): Core Assessed Contribution 2016-17
Programme Value: £ 34,181,203.16m		Review Date: Jan 2017 (updated May 2017)
Programme Code: 204147-101	Start Date: Jan 2016	End Date: Dec 2017

Summary of Programme Performance
Year	2016
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review
The last review of FAO was the project completion review (PCR June 2016) for the UK core assessed contribution to FAO in the 2014-2015 biennium. FAO had met or exceeded 91 percent of its output targets in 2015 and scored A. This review considers FAO’s progress in 2016. The review relies on FAO’s Mid-Term Review Synthesis Report 2016 (MTR) which reports on FAO’s progress during 2016 with implementing the approved Programme of Work and Budget 2016-17 (PWB). According to the MTR, 43 (86%) of the 50 Strategic Objective Output targets for the year were fully achieved, while 7 (14%) were partially achieved. Although the targets are mainly focused on 2017, progress is well advanced with 32 (64%) indicators showing at least 50% achievement against 2017 targets. Because the MTR was published two months after the first edition of this AR, this (May 2017) version has been updated to confirm the results that were anticipated in the January 2017 version.

The main recommendations from the June 2016 PCR were:

- Increase transparency and publish all documentation in line with IATI standards by the end of 2016. Progress: Ongoing. FAO management joined IATI in April 2016 and has agreed to publish disbursement information that meets IATI standards in April 2017.
- Build on progress in HR management and assessing staff performance. Progress: Ongoing. The Finance Committee (FC) has analysed FAO HR management in November 2016 and “commended the Secretariat on the achievements made in human resources management, including in the areas of recruitment and development of employees, improved gender representation, and increased efficiency in HR processes and procedures”.
- Enhance efficiency through its programmes, continuing to report on savings made and train staff to embed a culture of value for money across the Organisation. Progress: Ongoing. FAO has informally reported that it will achieve the savings it has planned in the Programme of Work and Budget 2016/17.
- Improve mainstreaming of Gender across all FAO programmes and activities. Progress: Ongoing. FAO’s Programme Implementation Report notes that FAO has met or is on track to meet most of its gender-related targets for 2014-2015. The 2016 MDR recognised that FAO has scaled up its effort to integrate gender as a cross-cutting issue in its Strategic Framework, with particular focus on closing the gender gaps in agriculture and empowering rural women, it also notes that progress will require stronger leadership from senior management. FAO Programme Committee (PC) requested an evaluation on FAO work on Gender to be released in 2019.
- Develop a corporate strategy on Climate Change by the end of 2016 to ensure more systematic approach. Progress: Ongoing. FAO will finalise a Climate Change Strategy in consultation with its governing bodies during 2017.
- Strengthen results reporting, with clear baselines and stretching targets for the next biennium programme of work and budget (PWB) to be agreed in 2017. Progress: Ongoing. FAO governing bodies will start the discussion on the PWB 2018/19 in March 2017.

DFID’s Multilateral Development Review (MDR) was published on 1 December 2016. It noted that FAO has turned its performance around between 2011 and 2015 and rated FAO as "good", on a four-step scale of weak, adequate, good, or very good. The MDR made a number of suggestions to improve FAO performance. These were discussed with FAO’s senior management in a Strategic Dialogue Meeting with DFID’s Director General for Policy and Global Programmes on 30 November 2016. The following priorities were agreed for inclusion in a performance agreement between FAO and the UK (and are reflected in the recommendations of this review, below):

- Improvements in collaboration:
- Improvements in transparency
- Improvements in risk management and resilience
- Improvements in nutrition
- Leaving no one behind
- Improvements in results management and reporting

Summary of recommendations for the next year
1. DFID and FAO should agree indicators and targets for improvements in the agreed priority areas and include these in a finalised performance agreement for the 2017 to 2020 period.
2. DFID should review and update this annual review once FAO’s MTR report is available. This was done in May 2017 and this is the updated AR.
3. DFID should review FAO’s revised strategic results framework when it is presented to the programme committee to ensure that it includes improved results targets in priority areas
4. DFID should consider aligning the annual review process with FAO’s results reporting timetable for the next biennium (2018-19).
5. The implementation of the Performance Management System (PEMS) is welcome. FAO should continue to monitor its implementation and report on this to its Finance Committee. FAO could consider setting performance targets for the PEMS.
6. FAO should consider how to increase the transparency of its reporting on Human Resources (HR) management performance.
7. The Finance Committee recommended that FAO further improve communications between management and staff representative bodies. DFID should monitor the follow up to this recommendation.
8. DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI by April 2017 in our performance agreement. DFID (UKREP) to urge FAO to include this commitment in its revised results framework and monitor progress with this.
9. DFID (UKREP) to continue to encourage FAO to enhance efficiency through its programmes, continuing to report on savings made and train staff to “embed a culture of value for money”.
10. DFID (UKREP) to monitor FAO progress in improving project management and procurement and use meetings of the governing bodies to press for progress.
11. DFID (UKREP) should continue to monitor the implementation of FAO’s Enterprise Risk Management (ERM) and its corporate risk log when this is published; DFID (UKREP) should review and update its own risk assessment when the corporate risk log is published. DFID and FAO should consider including key progress milestones in a performance agreement with FAO e.g. completion of FAO’s statement of internal control by end 2017.
12. DFID (UKREP) to monitor the implementation of the recommendations from FAO’s evaluation of its evaluation function and use meetings of the governing bodies to press for progress.
13. DFID (UKREP) should review the annual reviews prepared by the DFID country offices providing voluntary / bilateral funding to FAO. DFID (UKREP) should offer them the opportunity to provide feedback for inclusion in both the next review of DFID’s assessed contribution to FAO and our next annual strategic dialogue meeting with FAO.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	N/A
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204147/documents

The programme is the UK’s core assessed biennial (2016-17) contribution to FAO of approximately £17.5m; the total contribution for the biennium is approximately £35 - 37 million (depending on exchange rate costs). This represents 5.18% of the total assessed budget funded by all Member States. This does not include the additional voluntary contributions from CHASE, Policy Division and DFID country offices for specific projects, including FAO’s emergency response work. These are covered by separate business cases and reviews. Up to July 2016, DFID had provided approximately £9.3 million in voluntary contributions to support FAO programmes.

FAO is the UN’s specialised agency for food and agriculture. In 2012, FAO launched a process of “transformational change” reorienting the strategic direction of the Organization, institutional strengthening and pursuing greater efficiency and value-for-money. FAO identified five strategic objectives and a sixth functional objective were approved by member states. These represent the apex of FAO’s strategic results framework. They are:

1. Contribute to the eradication of hunger, food insecurity and malnutrition
2. Increase and improve the provision of goods and services from agriculture, forestry and fisheries in a sustainable manner
3. Reduce rural poverty
4. Enable more inclusive and efficient agricultural and food systems
5. Increase the resilience of livelihoods to threats and crises
6. Technical quality, knowledge and services

In November 2016, FAO proposed revisions to its strategic results framework out outcome level and below (the strategic objectives will not change) to align it more closely with the Sustainable Development Goals. FAO also outlined its Medium Term Plan for 2018-21. These were reviewed by FAO’s Programme Committee and ultimate approval for them will be sought from the FAO Conference in July 2017. The reviewed strategic framework will also strengthen FAO’s ability to monitor progress with cross-cutting themes including gender, governance, nutrition and climate change.

In December 2016, the FAO Council approved further, budget neutral, changes to FAO organisational structure to enable FAO to:

- Create a new department of Climate, Land, Water and Biodiversity (CL) headed by an Assistant Director-General reporting to the Deputy Director-General (Climate and Natural Resources)
- Appoint a new Deputy Director-General, responsible for Programmes
- Create a new Office of Chief Statistician to deal with SDGs monitoring and reporting.

The UK assessed contribution (like those of other member states) supports FAO’s Regular (assessed) Budget, which provides a minimum guaranteed amount of resources that can be committed for priority activities agreed upon by member countries in the governing bodies. It is complemented by significant voluntary (earmarked) contributions to support the achievement of FAO’s Strategic Objectives. FAO’s assessed or Regular Budget supports core functions of the organisation. Approximately 75% is spent on the technical and support staff who develop and oversee the range of tools, expert advice and standard-setting that underpin FAO’s work on food, agriculture and rural poverty in developing countries. The assessed budget also covers central administrative functions, such as Human Resources, Information Technology and security.

The UK Support has therefore contributed to FAO’s core functions, which are:

a) Facilitate and support countries in the development and implementation of normative and standard-setting instruments such as international agreements, codes of conduct, technical standards and others.
b) Assemble, analyse, monitor and improve access to data and information, in areas related to FAO’s mandate.
c) Facilitate, promote and support policy dialogue at global, regional and country levels.
d) Advise and support capacity development at country and regional level to prepare, implement, monitor and evaluate evidence-based policies, investments and programmes.
e) Advise and support activities that assemble, disseminate and improve the uptake of knowledge, technologies and good practices in the areas of FAO’s mandate.
f) Facilitate partnerships for food security and nutrition, agriculture and rural development between governments, development partners, civil society and the private sector.
g) Advocate and communicate at national, regional and global levels in areas of FAO’s mandate.

Examples of core-funded technical work and tools that are being produced during the 2016-2017 biennium, and to which the UK’s assessed contribution is therefore contributing, are:

- Food and agriculture statistical norms and standards, and the compilation, validation, analysis and dissemination of data through FAOSTAT (Corporate Database for Substantive Statistical Data) and related databases such as GLOBEFISH
- Information System on Food and Nutrition Security (with WFP)
- Global Information and Early Warning System
- Desert Locust Information System
- Animal Health Information System platform
- State of the World publications on Agriculture (annual), Food Insecurity (annual), Fisheries and Aquaculture (biennial), and Forestry (biennial).
- FAO food price index
- Global Forest Resources Assessment, and annual yearbooks on forest products, pulp and paper capacity
- Internationally agreed standards for plant health, through the IPPC. A significant tool supporting standard setting is the International Phytosanitary Portal
- Food safety and quality standards, through the Codex Alimentarius Commission (with WHO). This includes scientific advice provided through joint expert meetings on pesticide residues; food additives; and microbiological risk assessment
- OECD-FAO Agricultural Outlook (jointly with OECD).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

This Annual Review was produced by DFID UK Rep Rome in January 2017 and updated in May 2017. FAO’s reporting cycle does not coincide with DFID programme cycle, so this Annual Review has been updated to confirm the results that were anticipated in January and published in March with the publication of FAO’s Mid Term Review (MTR) 2016. Only progress on Outputs is monitored on an annual basis and reported in the MTR. Monitoring and reporting at the Strategic Objective and Outcome level takes place at the end of the biennium and reported in the Programme Implementation Report (PIR), which will be realeased in the first half of 2018. This review also relies on: the documents FAO management has presented to its governing bodies; the deliberations of those bodies; on external evaluations and assessments; and on informal exchanges with FAO management.

Annual outcome assessment
At outcome level, the DFID core (assessed) funding for FAO aims to support effective delivery of high-quality services to developing countries in support of their plans to achieve food security and sustainable agricultural development. Like other normative UN agencies, FAO’s outcome-level objectives focus largely on changes at government level, and FAO’s results framework makes clear that responsibility for delivery falls both to governments and to FAO.

FAO reports against outcome-level indicators every two years in a Programme Implementation Report (PIR) which is published five months after the end of the biennium. While monitoring and reporting on Strategic Objectives and Outcomes is released only every biennium, the MTR 2016 provides progress on Outputs, which are monitored on an annual basis. FAO’s work in 2016 was guided by the Programme of Work and Budget 2016-17 approved by the Conference in July 2015 and Adjustments approved by the Council in December 2015. The Programme Implementation Report for the 2016-17 biennium will be published in spring 2018.

Overall output score and description
The FAO strategic results framework includes the outcomes needed to achieve each Strategic Objective, and the outputs need to attain each outcome. The framework includes indicators that measure progress at each level of the results chain. Performance targets (results) are determined by priorities at national and regional level. These provide the basis for assessing and reporting how FAO’s actions contribute to changes at national, regional and global level. This review assesses progress with a subset of these outputs which have been selected from FAO’s strategic results framework on the basis of UK priorities and included in the logical framework for the UK’s assessed contribution to FAO.

FAO monitors progress with outputs on an annual basis by indicators and targets published in the Strategic Results Framework. At the end of 2016, 43 (86%) of the 50 Output targets for the year were fully achieved (thus “on track”), while 7 (14%) were partially achieved. This is a stronger test than used in the previous biennium, where the rating “on track” was given if the target was 75% met or better, in view of the more rigorous target setting process in 2016-17. Although the target setting was focused on 2017, achievement against 2017 targets is well advanced with 32 (64%) indicators showing at least 50% achievement against 2017 targets

Output Number	Output title	Output Score	Output Impact weighting (%)
1	FAO delivers at country level, in line with DFID strategic priorities	A+	50%
2	Continued HR Reform	A	20%
3	Accountability and transparency to governing bodies	B	20%
4	Value for money	A	10%

Key lessons

DFID’s MDR assessment of FAO found that FAO has demonstrated a commitment to increasing its focus on results since introducing its first results frameworks in 2012. However, FAO itself acknowledges that the process of transition to the new reporting framework led to a number of targets against indicators being set too low due to the fact that detailed country level planning occurred after the targets were set (FAO also judged that a few indicators were too optimistic).

As FAO’s strategic results framework is reviewed for the 2018 to 2021 period, DFID should use this opportunity to encourage FAO to improve its results reporting, particularly on UK priority areas such as transparency, anti-microbial resistance, nutrition, gender and climate change.

Key actions and recommendations

DFID and FAO should agree indicators and targets for improvements in priority areas and include these in a finalised performance agreement for the 2017 to 2020 period.

DFID should review and update this annual review once FAO’s MTR report is available in March 2017.

DFID should review FAO’s revised strategic results framework and use interventions in FAO governing body meetings to ensure that UK priorities, including antimicrobial resistance, nutrition, gender and transparency are addressed in FAO’s programme of work and budget and reported on

Has the logframe been updated since the last review?
Yes, the logframe is an update of the logframe that DFID used to monitor the UK’s core assessed contribution to FAO during the 2014-2015 biennium. It has been updated to align with revisions to FAO’s 2016/17 strategic results framework and to reflect UK priorities:

- Output 1 has been updated to reflect the UK priorities, including food security and nutrition, climate change, gender, work in fragile states and economic empowerment;
- Output 2 reflects an increased emphasis has been placed in HR management;
- Output 3 reflects an increased emphasis on transparency and accountability to governing bodies; and
- Output 4 assesses value for money is assessed.

Risk ratings for output 1 remain low based on FAO’s performance in the past biennium, but are assessed as medium for outputs 2, 3 and 4.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	FAO delivers results at country level, in line with DFID strategic priorities
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	50%
Risk revised since last AR?		This is the first annual review	Impact weighting % revised since last AR?	This is the first annual review

Indicator(s)	Milestones	Progress
1.1 Food Security and Nutrition: Number of countries with improved governance and coordination mechanisms for eradicating hunger, food insecurity and malnutrition (FAO Indicator 1.2.A)	FAO’s end 2016 target is 20 / FAO’s end 2017 cumulative target is 39	25 - Milestones moderately exceeded expectation. In the domain of governance, coordination mechanisms and partnerships for food security and nutrition, good progress made at global and regional levels during 2016 is translating into progress at country level, where FAO is supporting governments and other stakeholders to increase dialogue and collaboration, embrace normative and standard setting instruments for their implementation, and raise political commitment to ensure the creation of a more enabling policy and institutional environment for the right to food. Progress in this area of work is good, with new countries reporting results in particular in Latin America. / Progress is measured on an incremental basis using indicators that assess the change in terms of the effective and regular participation of relevant stakeholders in: / • Formal policy dialogue and coordination on food security and nutrition policies such as in: Angola, Cape Verde, Guinea Bissau, Sudan, Zimbabwe, Timor-Leste, Kyrgyzstan, Antigua and Barbuda, Costa Rica, El Salvador, Guatemala and Guyana; and / • Less formal policy dialogue and programme coordination discussions such as in: Mali, Afghanistan, Papua New Guinea, Colombia, Ecuador, Honduras, Mexico and Saint Vincent and the Grenadines.
1.2 Climate Change: Number of countries supported by FAO that report progress in mainstreaming food security and agriculture into Climate Change policies and processes.(FAO’s KPI 6.6.A)	FAO’s 2017 cumultative target is 30	20 - FAO will report on its progress in mainstreaming Climate Change in Sustainable Food and Agriculture for the first time in the March 2017 MTR. This will be based on FAO representatives reporting results of work carried out at country level. The indicator will be improved based on experience with its measurement.
1.3 Gender: Number of the gender mainstreaming minimum standards and women-specific targeted interventions adopted (FAO KPI 6.3.A)	FAO’s 2017 cumultative target is 10	12 - The target set for the biennium 2016 – 2017 has already been exceeded. / FAO reports on the adoption of the 15 gender mainstreaming standards set out in its Gender Equality Policy. These standards were designed to be compatible and complementary to the UN-SWAP standards which FAO reports on an annual basis. / The different divisions within FAO report annually against their progress with the standards. By the end of 2016, 12 standards out of 15 were achieved across FAO. This is an improvement compared to the 2014-15 biennium.
1.4 Work in fragile states: Number of countries that have improved their commitment and capacity for disaster and crisis risk management for agriculture, food and nutrition in the form of policies, legislation and institutional systems. (FAO Output 5.1.A)	FAO’s end 2016 target is 14 / FAO’s end 2017 cumulative target is 47	27 - Milestones substantially exceeded expectation. FAO reports that 27 countries and 3 regional institutions have formulated strategies/plans for risk reduction and crisis management as a result of FAO’s support in 2016.
1.5 Economic Empowerment: Number of countries with an improved set of policies, institutions and interventions aiming to generate decent rural employment, including for women and the youth (FAO Outcome 3.2.A)	FAO’s end 2016 target is 6 / FAO’s end 2017 cumulative target is 20	6 - Milestones met expectation. FAO reports that work to support agricultural rural development policies and strategies to integrate Decent Rural Employment principles is on track and results in Ethiopia, Guinea-Bissau, Mali, Senegal, Tunisia, and Uganda meet FAO’s 2016 target.

Key Points

Overall, progress with the indicators for this outcome has moderately exceeded expectations and in the case of indicators 1.1, 1.3 and 1.4, has exceeded the targets set for end 2017. This assessment was based on FAO’s Mid-Term Review (MTR) which was published in March 2017 and reports on FAO’s progress with these indicators.

Indicator 1.2 on Climate will be improved and refined by FAO and we will consider replacing it in the next reporting period. In particular, as FAO has developed a Climate Change Strategy in 2016, we would expect to see it integrated in the next Programme of Work and Budget.

Although MTR reports that it has exceeded its gender target for 2016 (indicator 1.3), DFID’s Multilateral Development Review found that it was too early to assess if there has been an improvement in FAO’s focus on girls and women in its policies, investment choices and partnerships. FAO has committed include an annex to be dedicated to gender in future Strategic Objective evaluations. FAO’s office of evaluation will also release an evaluation of FAO’s work on gender for consideration by the Conference in 2019.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2016 MDR noted FAO’s increasing focus on results since introducing its first results frameworks at the time of the first 2011 MAR. During the 2014-15 biennium FAO revised its results framework to cover all funding sources. FAO now has the tools in place for results
Measurement, indicators have been improved and most have baselines. The MDR also notes that this is work in progress and that progress in measuring results at country level has been variable.

Recommendations

DFID should review and update this annual review once FAO’s MTR report is available in March 2017. This AR was updated in May 2017.

DFID should review FAO’s revised strategic results framework and use interventions in FAO governing body meetings to ensure that UK priorities, including antimicrobial resistance, nutrition, gender and transparency are addressed in FAO’s programme of work and budget and reported on rigorously.

DFID should consider aligning the AR process with FAO’s results reporting timetable for the next biennium (2018-19).

Output Title	Continued HR Reform
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		This is the first annual review	Impact weighting % revised since last AR?	This is the first annual review

Indicator(s)	Milestones	Progress
2.1The Performance Management Policy and System (PEMS) is implemented and rolled out	The performance evaluation and management system is implemented	Milestone met expectation-The implementation of the revamped policy on Performance Evaluation and Management System (PEMS), which was launched in February 2016, is proceeding well
2.2Time required to recruit staff (FAO’s KPI 11.1.A)	120 days	120 - Milestone met expectation- / FAO’s Office of Human Resources (OHR) reports that the time taken to recruit staff in 2016 was 120 days. This is based on a review of the recruitment processes for Professional and General Service Staff.
2.3Vacancy rates drop in technical and non technical areas	21% (Baseline)	Milestone met expectation-The total vacancy rate on PWB posts was 17.4% in 2016.

Key Points

To assess this output, we relied: on FAO’s report on Human Resources Management to its Finance Committee in November 2016 (FC 164/7); on the Draft Independent assessment of FAO’s technical capacity, released in January 2017 (to be finalised in March 2017); and on informal reporting from FAO senior management. Although we cannot independently verify FAO reporting, the member states that sit on the Finance Committee scrutinise it carefully. Overall FAO has met expectations for this output. Will encourage FAO to increase the transparency of their HR management to better enable us to verify progress.

- 2.1. FAO’s HR Management Report noted that FAO’s performance management system (PEMS) has been simplified and improved in 2016. FAO reports that the main changes include an improved online system, simpler and better quality work plans, emphasis on more timely, higher quality feedback and a move from a 4-point to a 5-point rating scale. The report also notes that the PEMS has been reviewed in internal management discussions and in consultations with the Staff Representative Bodies. For example, it the previous 4 point scale had led to difficulties by managers to rate the performance of staff without a central point for satisfactory performance.
- 2.2 The November 2016 HR Management Report did not report on the time taken to recruit staff in 2016 so we asked FAO management to provide a progress update. This confirmed that the 120 day target had been met. This is the same target as in 2015 despite the acceleration in the recruitment of professional posts noted in FAO’s HR management report. That report also noted that improvements to the recruitment of professional level staff included more transparency, more direct involvement of recruiting units, and faster recruitment than before. Members of the Finance Committee queried this and suggested that more authority for recruitment should be delegated.
- For ouput target 2.3, FAO management confirmed that this target had been met. FAO management has confirmed that the high target vacancy rate is a cost saving strategy and that vacant posts enable the organization to retain a more flexible use of resources, given that 75% of FAO’s regular budget goes on staff. FAO Management has said that they will aim for a 15% vacancy rate moving forward. This has led to a significant increase (33 percent) in the use of Non Staff Human Resources in the biennium.
- As mentioned above, the HR Management Report also noted that FAO’s recruitment of professional positions was accelerated in 2016, leading to a decrease of vacant posts. It also noted that a roster of qualified candidates for General Service positions has been established and is updated periodically. The Finance Committee interrogated this report in their meeting in November and asked FAO for more information on seniority of the professional staff appointed.
- The HR Management Report also showed that FAO has increased its use of Non staff Human Resources (NSHR or consultants), usually on short term contracts, to fill administrative positions. This highlights the challenges that a high vacancy rate poses to the organisation. The Finance Committee suggested that FAO use non-staff human resources more efficiently.
Summary of responses to issues raised in previous annual reviews (where relevant)
DFID’s June 2016 PCR recommended that FAO ‘Build on progress in HR management and assessing staff performance’. The November 2016 HR report shows that FAO has done this.

The 2016 MDR notes that FAO has transformed HR from a transactional function into a more strategic business partner, aligned with supporting the delivery of FAO’s Objectives. A 2015 External Auditor Report noted “significant achievements” by the Office of Human Resources that should “provide traction in the implementation of the FAO Human Resource Strategy”. Nonetheless, the MDR also found that HR is still perceived as too HQ-centric and bureaucratic and that “In some cases, there is also a perception of lack of transparency and consistency”

Recommendations

The implementation of the Performance Evaluation Management System (PEMS) is welcome. FAO should continue to monitor its implementation and report on this to its Finance Committee. FAO could consider setting performance targets for the PEMS.

FAO should consider how to increase the transparency of its reporting on HR performance.

The Finance Committee recommended that FAO improves communications between management and staff representative bodies. DFID should monitor the follow up to this recommendation.

Output Title	Accountability and transparency to governing bodies
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		This is the first annual review	Impact weighting % revised since last AR?	This is the first annual review

Indicator(s)	Milestones	Progress
3.1Implementation of governing body decisions within prescribed deadlines (FAO’s KPI 10.1.B)	90%	Milestone met expectation- 90% / The Key Performance Indicator regarding the implementation of FAO Governing Body decisions is formulated by calculating the number of Council decisions fully implemented or initiated within the prescribed deadlines. The implementation of decisions is monitored and reported on through a standing item on the Council agenda at four sessions during the biennium, for which a background document is submitted to the Council for discussion and decision.
3.2 Percentage of recommendations where the agreed management response has been completed by the due date (FAO’s KPI 10.2.A)	95%	Milestone did not met expectation- 84% / This figure relates to both audit and evaluation recommendations. FAO will separate reporting on progress with the different types of recommendation in its results framework for the 2018-2019 Programme of Work and Budget (PWB).

Key Points

- Overall FAO moderately did not meet expectations for this output.
- To assess this output, we relied on the MTR results reporting from FAO’s management and on DFID’s MDR assessment of FAO’s transparency which was discussed with senior management in December 2016.
FAO management reports that it has met the expectation for Indicator 3.1, while it did not met the expectation for Indicator 3.2.

Summary of responses to issues raised in previous annual reviews (where relevant)
DFID’s June 2016 PCR recommended that FAO ‘Increase transparency and publish documentation in line with IATI standards by the end of 2016’. FAO did not meet this target but has committed to publishing disbursement information with IATI by April 2017.

The 2016 MDR notes that FAO is strong on promoting global data and statistics for food and agriculture, in line with its normative role and supports promotion of open data and access to information. However, the MDR also underlines that FAO does not publish project information systematically and recommends that FAO to publish its documentation with IATI.

Recommendations
FAO should consider how to increase the transparency of its reporting on HR performance.

DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI by April 2017 in our performance agreement. DFID (UKREP) to urge FAO to include this commitment in monitor progress in its revised results framework and monitor progress with this.
Output Title	Value for Money
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		This is the first annual review	Impact weighting % revised since last AR?	This is the first annual review

Indicator(s)	Milestones	Progress
4.1 Per cent of savings and efficiency gains planned in the 2016/2017 PWB realized	100%	100%

Key Points
This output target has been met. To assess this output, we relied on MTR results reporting from FAO’s management and on DFID’s MDR assessment of FAO’s VFM. FAO’s output results for 2016 is included in FAO Mid Term Review 2016.

FAO management confirmed that 100% of efficiency savings planned in the 2016/2017 Programme of Work and Budget (PWB) have been achieved and that USD 14.2 million have been reallocated to eight higher priority areas of work.

Further savings will become increasingly difficult to identify, as approximately 75% of FAO’s core budget goes on staff costs over which it has very little control (like other UN agencies, FAO is obliged to comply with regulations stipulated by the International Civil Service Commission in New York).

FAO is active in reducing staff costs where possible by limiting expenses in relation to duty travel and maintaining a high vacancy rate. FAO is also experimenting new ways to drive down costs and has carried forward the total closure of its premises during the 2016 Christmas week, which resulted in USD 1 million savings.

Summary of responses to issues raised in previous annual reviews (where relevant) DFID’s June 2016 PCR recommended that FAO ‘Enhance efficiency through its programmes, continuing to report on savings made and train staff to embed a culture of value for money’. As set out above, FAO has reported the savings it has made.

The 2016 MDR recognises that FAO Director-General has endeavoured to instil a stronger culture of value for money in the Organisation, achieving efficiency gains and savings of US$108.2 million over four years from the 2012-13 biennium to 2014-15. Like the PCR, the MDR also finds there is work to do in training staff to properly embed a culture of value for money (VFM). The MDR reports on feedback from country level which finds that technical staff can interpret rules in terms of the cheapest option rather than seeking the bid that will deliver the best outcomes per unit cost. FAO launched a corporate capacity building programme in 2015 to strengthen project management in regional, sub-regional and country offices – as well as in HQ-based technical departments.

Recommendations
1. DFID (UKREP) to continue to encourage FAO to enhance efficiency through its programmes, continuing to report on savings made and train staff to embed a culture of value for money.
2. DFID (UKREP) should monitor FAO progress in improving project management and procurement.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
FAO’s key cost driver and main asset is its staff, which accounts for 74% of the FAO 2016-17 net appropriation budget (as reported in FAO’s Programme of Work and Budget (PWB) 2016-17). FAO staff costs are linked to those agreed in the UN common system and FAO management has limited options for controlling them. The most significant components are salaries, medical costs and benefits, such as education grants and home leave. 70% of cost increases in FAO’s Programme of Work and Budget for 2016/2017 are accounted for by increases in these costs (as reported in an information note for the 2015 FAO Conference). FAO has taken steps to reduce benefits where possible and is an active member of an inter-agency after-service health insurance (ASHI) to decrease liabilities for its retired staff. The 2016 MDR notes that efficiency gains of around US$6.5 million have been achieved through changing travel arrangements and more use of videoconferencing facilities.

As reported under output 4, FAO’s Programme of Work and Budget (PWB) for 2016-17 planned efficiency gains and savings of US$14.2 million which FAO reports that it has achieved. These will enable reprioritisation of FAO work while preventing growth in FAO’s Regular Budget. In December 2016, FAO Council approved a restructuring of FAO management structure, on a budget neutral basis, which aims to improve FAO’s programme delivery further. The Council decision reflected assurances from FAO management that it had achieved further efficiencies of USD 4.5 million for this restructuring which will enable reinvestment in technical work through the conversion of some 46 administrative positions to technical and programme positions in priority areas.

Exchange rates are another key cost driver. FAO requires that its member states make their assessed contributions in both US Dollars (USD) and Euros (EUR) to minimise financial risks to FAO from exchange rate fluctuations. Nevertheless, FAO still faces the risk of unfavourable exchange rates increasing the costs of its operations in countries which do not use USD or EUR and for operations which are funded from voluntary contributions in other currencies.

FAO has started to strenghten its regional and national dimension following the guidance of its governing bodies. During the biennium 2016/17, FAO has allocated 59.3% of its regular budget to its work at HQ and global level, while 41.6% is destined to decentralized offices in Africa, Asia and Pacific, Europe and Central Asia, Latin America and the Caribbean and Near East. The number of staff posts are almost equally split between HQ and decentralized offices. It is too early to assess what impact this has had on FAO’s effectiveness. The actions proposed in recommendation 13 will support an assessment of this in future.

VfM performance compared to the original VfM proposition in the business case
The assessed contribution to FAO that is the subject of this review is exempted from the requirement for a business case because it is a mandatory requirement for the UK membership of FAO. The level of the UK contribution is determined as 5.18% of FAO’s core budget for the 2016/17 biennium. The percentage that each country is required to pay is determined by the UN centrally on the basis of the size of each country’s economy.

Assessment of whether the programme represented value for money
The requirement to pay the UK assessed contribution in USD and EUR means that the cost of this in GBP varies and is increasing because of weakening of the GBP:USD and GPB:EUR exchange rates. The 2016 forecast amount for the UK contribution was £16.5 million but when paid the actual UK contribution was £17,681,203.16. Similarly for the UK contribution in 2017, the forecast amount is £16.5m, however, current exchange rates suggest this will cost approximately £20.5 million

Despite the increasing cost (to the UK), the value for money of this programme is likely to have been maintained or increased because of recent improvements in the economy, efficiency and effectiveness of FAO (reflected in the 2016 MDR assessment). These include:

- Cost-containment measures, including reduction of posts, more efficient procurement at headquarters, reduced travel and accommodation expenditure by FAO staff, and other measures, such as the establishment of the Shared Services Centre in Budapest and its two regional hubs in Bangkok and Santiago to create more cost-effective centers in delivering the more transactional aspects of HR.
- Efficiencies achieved through delivering outputs with a reduced budget, whilst maintaining the programme level agreed in the Programme of Work and Budget endorsed by FAO Conference to increase efficiency further, particularly at country level, improvements in procurement processes should be explored.
- Rollout and implementation of FAO’s new results framework designed to support the measurement and monitoring of FAO’s effectiveness.

Quality of financial management during programme
The report on the financial position of the organisation, presented to the Finance Committee in November 2016 notes that FAO is steadily improving the quality of its financial management, and its investment style continues to be prudent and low risk. The Finance Department at Headquarters has been strengthened, and some financial posts have been moved to regional and country offices to increase capacity. Financial training is being provided to all FAO Country Representatives and the implementation of the Global Resource Management System allows FAO Headquarters, for the first time, to have a comprehensive overview of financial expenditure, commitments and staffing.

Date of last narrative financial report	November 2016
Date of last audited annual statement	October 2016 (covering 2015 accounts)

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
The project completion report (PCR) of DFID’s assessed contribution to FAO in 2014-15 and the 2016 MDR reported that FAO had made progress in strengthening risk management, including through the introduction of Enterprise Risk Management (ERM) to ensure that risk management is applied systematically. The approval by FAO’s Finance Committee of its Internal Controls Framework (ICF) was an important achievement in 2016. Nonetheless, implementation of the ERM is work in progress and FAO’s completion of a statement of internal control at the end of 2017 will be a key milestone.

As part of FAO’s internal controls, annual reports from the Inspector General and the Audit Committee are published and scrutinised by FAO’s Finance Committee. The report of FAO’s external auditor is appended to FAO’s audited accounts which are presented to FAO’s biennial Conference of member states. FAO also publishes a management report on progress with External Audit recommendations. This and the annual report of the IG include a synthesis of audits undertaken and an assessment of progress in addressing their recommendations.

FAO’s Office of the Inspector General (OIG) undertakes internal audits of FAO’s work with the aim of ensuring that all high risks of the Organization, as captured in an OIG’s risk register, are independently reviewed over a defined cycle, currently three biennia, taking into account the oversight coverage of the Office of Evaluation and the External Auditor. The May 2016 annual report of the Inspector General summarises the results of OIG’s audits and investigation work during 2015. It recognizes positive measures undertaken in 2015 as part of FAO’s ongoing organisational reforms. At the same time, the report notes that there remain important challenges “that are essential for the Organization’s transformation to be sustained and greater efficiencies achieved.” The report identifies 27 outstanding recommendations made by the OIG to mitigate high risks. Of these, 10 have been outstanding since 2013 or before.

The FAO Audit Committee 2016 annual report found that despite progress in 2015, FAO’s ERM “remains at a low maturity level”. The Committee stressed the importance of FAO management completing a top down assessment of corporate risks and the timely adoption of the corporate risk log as required in ERM policy. FAO management informally confirmed this was done in late 2016 and that the revised corporate risk log will to be published in February 2017. This will support risk based audit planning.

The FAO management reported on its progress in implementing outstanding external audit recommendations in November 2016. The report stated that 15 ‘fundamental’ or ‘significant’ recommendations were outstanding. This assessment was scrutinised by the Finance Committee which asked for the External Auditor’s view on this assessment. The external auditor plans to validate (or otherwise) progress with each recommendation in his 2016 year end audit.

FAO continues to make progress in managing its risk and this should ultimately decrease the level of risk facing FAO. Nonetheless, there is much further to go and at this stage, this review assesses that FAO’s risk remains medium as assessed in earlier DFID assessments.

DFID (UKREP) should continue to monitor the implementation of FAO’s ERM and its corporate risk log when this is published; DFID (UKREP) should review and update its own risk assessment when the corporate risk log is published. DFID and FAO should consider including key progress milestones in a performance agreement with FAO e.g. completion of FAO’s statement of assurance by end 2017.

Outstanding actions from risk assessment:
DFID’s risk assessment identifies risks: to the implementation of FAO’s organisational reform agenda as the DG nears the end of his second and final term in June 2019; to FAO’s ability to deliver results at country level if national governments do not prioritise FAO recommendations; and to FAO’s financial stability both from currency exchange fluctuations and from the impact of potential fraud.

Outstanding actions for DFID are predominantly at country level where this and other reviews have recommended that DFID country offices should assess how effectively FAO’s corporate systems, monitoring, financial management, oversight and capacity building for local partners are being implemented by the FAO country offices that they are funding directly. Recommendation 13 (see monitoring section) will support these actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Overall, FAO is on track in the delivery of its output targets. FAO’s MTR, published in March 2017, confirmed that 43 (86%) of the 50 Output targets for the year were fully achieved (thus “on track”), while 7 (14%) were partially achieved

Performance of partnership (s)
According to the MDR, FAO generally develops strong partnerships and works in a participatory manner with partners, particularly at country level. The 2016 MDR also recommended FAO to strengthen its collaboration with other UN organisations, and particularly with IFAD and WFP, both based in Rome. In November 2016, the three Rome Based Agencies, FAO, IFAD and WFP, issued a joint paper on collaboration. This was welcomed by member states as a step in the right direction. Member states have called for annual joint progress reports to their governing bodies. Key areas for collaboration are consulting on work plans at country level, and coordinating work on nutrition and climate change. UKREP will closely monitor the implementation of the commitments made in the paper.

The UK-FAO partnership remains strong. FAO continues to respond positively to numerous programme and information requests. UKRep Rome has good contact with the senior management team and across the Organisation and has recently organised a high level strategic dialogue with FAO senior management. As an outcome of this dialogue, DFID and FAO have agreed to negotiate a performance agreement, which should be finalised by mid-2017.

Asset monitoring and control
FAO undertakes its own monitoring and control, which are reviewed in audit reports.

G: CONDITIONALITY (½ page)
Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
FAO’s Office of Evaluation is independent and reports to the membership through FAO’s Programme Committee as well as to FAO management. Evaluations in FAO assess activities, projects, programmes, strategies and policies and are published in the Office of Evaluation website. Thematic and strategic evaluations are submitted to the Programme and other Committees and to FAO’s Council. Evaluations are often conducted in response to requests by the Programme Committee and the results are presented systematically to FAO governing bodies. In total, 39 Evaluations were published in 2016. Management responses are submitted to the Committee, together with reports on implementation of recommendations.

A 2016 evaluation of FAO’s evaluation function reported that FAO’s Office of Evaluation (OED) had made significant progress during the last biennium but that there remains scope for improvement both in learning and accountability. The timing of OED’s evaluations and recommendations limit their overall utility. The evaluation notes that in some cases evaluations were done too early or too late; there have been delays in the evaluation process (e.g. time taken to agree on the ToRs, timing of interactions with concerned parties, and with reporting). These issues limit FAO’s access to an important source of learning and improvement.

FAO’s management has provided a response to the findings of the evaluation, welcoming the recommendations and ensuring they will be carefully considered, including in developing a plan for decentralized evaluation.

DFID (UKREP) to monitor the follow up and implementation of the recommendations from FAO’s evaluation of its evaluation function and use meetings of the governing bodies to press for progress.

Monitoring progress throughout the review period
UKRep Rome monitors FAO’s performance through scrutiny of FAO management reporting. UK Rep Rome uses UK and EU interventions in FAO governing bodies to discuss and press for further progress. UK Rep Rome also meets with FAO’s senior staff overseeing policy, administration, finance and human resources on a regular basis and uses these meetings to monitor and discuss progress.

This Annual Review was completed by DFID UK Rep Rome in January 2017 and updated in May 2017, following the publication of FAO’s Mid-Term Review of progress in 2016. This review has relied on: the MTR and other documents FAO management has presented to its governing bodies; the deliberations of those bodies; on external evaluations and assessments; and on informal exchanges with FAO management. We are grateful to FAO management for providing us with a preview of their 2016 MTR results and their contributions to this review.

As noted throughout this review, DFID’s 2016 MDR assessed FAO performance up to the end of 2015. The MDR findings were discussed with FAO’s senior management in a Strategic Dialogue Meeting with DFID’s Director General for Policy and Global Programmes on 30 November 2016.

UKRep also engages with DFID country offices and policy staff at headquarters, advising on due diligence issues, policies and FAO processes, and helping resolve any problems that arise. These exchanges also facilitate UKRep’s overview of FAO’s performance at country level, however this could be done more systematically and this review recommends:

DFID (UKREP) reviews the Annual Reviews prepared by DFID country offices providing voluntary / bilateral funding to FAO and offers them the opportunity to provide feedback for inclusion in both the next review of DFID’s assessed contribution to FAO and our next annual strategic dialogue meeting with FAO.

The FAO strategic results framework 2014-17 guides the planning and monitoring of Organization’s work. In addition to the annual monitoring and reporting exercises (MTR and PIR), during 2016 FAO designed and implemented a corporate e-Operational Monitoring Dashboard as part of establishing a “single version of the truth” for FAO data. The dashboard delivers timely and reliable information to managers (but not member states) across all FAO offices on operations under their respective areas of responsibility in a format that facilitates analysis of work, allowing timely detection of issues and initiation of pertinent adaptive actions.

Sources
- Conference documents, particularly the Programme Implementation Report 2014-15; C 2017/8
- Council documents, particularly the Reviewed Strategic Framework and Outline of Medium Term Plan 2018-2021; CL 155/3
- Programme and Finance Committees documents, including Human Resources Management ; FC 164/7 and Mid Term Review Synthesis Report 2016
- Financial highlights paper to FC
- Informal exchanges with FAO management
- Report on Financial Position of Organization
- Reporting on external/internal audit recommendations
- Multi-Year Programme of Work
- DFID Annual Review 2014 and Project Completion Report on FAO Core Assessed Contribution 2014-15;
- DFID Multilateral Development Review 2016
- Informal membership seminars and presentations from FAO management, including on results reporting.
- Independent assessment of FAO’s technical capacity
- Independent evaluations

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process