Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	September – November 2015

Title: Enabling Better Delivery of Aid in Somalia
Programme Code: 202827	Start Date: 1st November 2011	End Date: 30th September 2015

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	A	A	B	A
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	£11,993,000
Extensions/ amendments	No-cost extension approved on 18th December 2014, for extension to 30th September 2015
Log-frame revisions (with dates)	April 2015
Total programme spend	£11,983,187 to date

Follow up actions required following closure

Most of the components of this project will continue under different funding models, either from the UN Multi Donor Trust Fund or DFID’s humanitarian programme. Only the NGO Consortium and Aid Coordination Unit is seeking further funding. DFID should continue to work to put these institutions on a more sustainable footing or aid their closure.

In December 2014, the Humanitarian Team (HT) signed a three year MoU with OCHA for continued support under the Multi-Year Humanitarian Programme (MYHP), and will continue to monitor OCHA’s deliverables under the new grant.

DFID support to Food Security and Nutrition Analysis Unit (FSNAU) is continuing under the MYHP through a three-year MoU signed in December 2014. The Humanitarian Team will continue to monitor FSNAU’s deliverables. FSNAU aims to ensure a broad range of stakeholders have access to appropriate food, nutrition and livelihood security information, enabling them to respond to emergencies and plan for development.

Support to the NGO Safety Programme is continuing under the MYHP through a new accountable grant for 2 years. The Humanitarian Team will continue to monitor NGO Safety Programme (NSP) deliverables and performance.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717472.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4851848.xlsx

Outline of programme and what it has achieved

This programme was a set of interventions to make the targeting and delivery of aid to Somalia more effective. It did this in two ways. Firstly by supporting stronger use of evidence, management of risk, planning and co-ordination in implementing development assistance and in the humanitarian response and secondly, by enabling greater access for aid workers in Somalia through the provision of improved safety and security.

The context in which the programme was developed is not entirely reflected in the baseline measures. The 2011 famine had highlighted the lack of coordination and the high risk of aid diversion in Somalia. There were high levels of distrust among humanitarian partners. There were few development actors, and limited or no engagement from the UN and World Bank outside of humanitarian support, yet increased appetite to provide support which originated from the 11th September 2001 terrorist attack in the US.

The context in 2015 is very different. Coordination has vastly improved as a result of the New Deal and the humanitarian cluster system and there is a better grip of how to manage fiduciary risk in an unusually challenging environment which depends on local NGOs for delivery.

Key achievements are:

Overall, this programme enabled the UN to play a key role in enabling the increased development and humanitarian assistance to Somalia.

The Risk Management Unit’s risk assessments and training have resulted in greater scrutiny of development partners and been a tool to weed out corrupt NGOs and promote those with robust fiduciary systems in place. The contractor information management system now covers 3505 contracts, totalling over US$4 billion. The awareness of risk and how to manage it among development actors in Somalia is high.

The Resident Coordinator’s Office (RCO) has played a useful role in reaching agreement with the government on UN-wide issues. In particular in Puntland, it helped to lobby for engagement on the New Deal. It has had success in improving coordination of UN agencies, particularly in standing-up the UN multi-partner trust fund (with attendant joint programmes and ensuring a single strategic framework among all the UN agencies ( including the political mission).

The Aid Coordination Unit (ACU) in the Federal Government of Somalia has been critical to the success of the New Deal in Somalia. It has been instrumental in setting up the aid architecture around the New Deal and providing a channel for the government for effective engagement with donors.

Food Security and Nutrition Analysis Unit (FSNAU) has consistently produced informative and technical reports, covering food, nutrition, markets, harvests, and vulnerabilities which are relied upon by key humanitarian players providing support in these areas. There is evidence that they have been used to inform decision making and improved the knowledge base for those decisions allowing for more effective interventions.

The effective functioning of the UNDSS has supported development partners over the last four years. There has been confidence in their security protocols and operations allowing greater engagement with the Federal Government in Mogadishu and increasingly in the regions.

OCHA plays a central and critical role in the humanitarian response in Somalia. It has been hard to separate support under this programme to wider DFID support under the Common Humanitarian Fund (CHF) but, as a result of this funding, OCHA’s systems are more robust and its monitoring and evaluation has reached a very good standard.

## B PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The outcome is ‘Aid to Somalia is more effectively targeted and delivered’. There is substantial qualitative evidence that the programme’s package of interventions have been central to the delivery of aid in Somalia over the last four years benefitting UN agencies, and humanitarian and development NGOs by tackling the key barriers to delivery: security; managing fiduciary risk; coordination; and evidence. It is arguable that funding would have come from elsewhere for the essential components of the project if DFID had not funded them but it is highly likely there would have been significant delay and this would have impacted on the speed in which the international community could respond to positive developments in Somalia by providing more effective aid.

There are three indicators –
% of population in need reached with humanitarian assistance in areas of greatest need.

Level of adherence to New Deal principles: Governance structures to support the priorities in the New Deal Compact are functioning well. There are regular Somalia Development and Reconstruction Facility executive meetings (SDRF) and each year there has been one ministerial High Level Partnership Forum (HLPF) which bring together donors and government in the partnership envisaged in the New Deal. Under this, the Peace and Statebuilding Working Groups (PSG WGs) bring together government official and key donors at the technical level to coordinate assistance on a regular basis.

Aid flow to Somalia mapped and consolidated: The Aid Coordination Unit has conducted an aid mapping exercise which has been used to identify gaps.

We therefore conclude that the project has met its outcome. It has achieved its outputs and overarching objective.

One key issue was whether DFID could begin seed-funding these functions and then withdraw when the time was right. This has been an ongoing tension in the programme and some components of the programme have had to be extended. Yet concerted effort over the last 18 months has had results. In October 2015, the Somalia Development and Reconstruction Facility (SDRF) approved the UN Multi-Partner Trust Fund’s (UNMPTF) proposal to support an aid enabling facility to enhance UN-provided security, risk management and coordination services. This achievement is important in determining the success of the intervention. This was in response to DFID pushing for a more sustainable, long-term replacement for aid enablers support for the last few years and it became intrinsic to whether the programme achieved its objectives to improve sustainably the aid environment.

Output Score and Description

Output 1: Stronger use of evidence, management of risk, planning and coordination in implementing development assistance. Score: A

This output has been achieved. There have been prominent advances in risk management in the aid community in Somalia as whole as a result of the RMU. Taking collectively the components supporting the RCO, the ACU and NGO Consortium added up to a big push to improve coordination in Somalia. Coordination in 2015 is vastly improved upon compared to 2011 but, despite anecdotal evidence, it is difficult to directly attribute this improvement on this programme. Planning of development assistance has significantly improved as a result of Somalia’s New Deal Compact, which can in part be attributed to this programme because it funded an aid effectiveness adviser in the RCO who played a pivotal role in setting up New Deal governance structures. The ACU has also moved forward on the mapping of development assistance which is relevant.

Output 2: Stronger use of evidence, management of risk, planning and coordination in implementing humanitarian assistance. Score: A

This output has been achieved. The RMU has had an impact on raising the level of risk management in the humanitatarian agencies as well as development agencies and OCHA in particular has engaged. FSNAU has consistently produced informative and technical reports, covering food, nutrition, markets, harvests, and vulnerabilities. Feedback on these reports has been generally positive. OCHA’s lead on coordination has been welcomed by donors, with policies and processes enhanced through coordination meetings in Mogadishu – for example, during the Somalia Country Appeal Process. OCHA also provides ad hoc briefings, maps and documents to the international community. 421 organisations engage with the Food Security Cluster Cluster coordinated by the World Fund Programme. There are 13 meeting locations across Somalia, ensuring coordination and accessibility, in stark contrast to the 2011 famine when there was little coherency in the aid community’s response.

Output 3: Greater access for aid workers in Somalia through the provision of improved safety and security. Score: A

This output has been achieved. The NGO Safety Programme has had a significant impact on opening up access to NGOs and ensuring their employees’ safety. It has been a free, professional and respected service which has therefore been universally taken up. It is clear that without it the number of NGOs working in Somalia would have been affected although we cannot say to what extent. The UNDSS has also competently performed its security functions supporting all the UN agencies and donors largely thanks to DFID funding. The issue here is whether these functions would have been equally effective without DFID funding, because funding would have had to be found from elsewhere, and whether DFID funding allowed others to shirk their responsibility. It is hard to assess the counterfactual but it is likely at a minimum there would have been a delay or breaks in the security services and they may have been offered on a reduced scale if DFID had not taken responsibility. This would have affected the level and, more likely, quality of development assistance available in Somalia. DFID has also ensured the services will continue.

Lessons and how these have been shared

The key lesson is that in extreme cases DFID may need to fund a programme such as this in a fragile context where it takes on a disproportionate burden share of costs in order to speed up delivery options and effectiveness. The justification is that it has a critical impact unlocking key support for Somalia from others with a relatively small amount of money. However there must be a fully worked up and agreed exit strategy with implementing partners who must know that funding will stop in a given time and so other funding streams must be urgently found. It might be that DFID reduces funding in stages overtime. DFID should develop coherent policies on funding aid enablers, and on burden sharing including on developing funding models that facilitate withdrawal. In the case of this programme, there was a positively disproportionate impact whereby, for a relatively small amount of money, DFID funding had a transformational impact on the aid environment in Somalia.

If DFID is going to take on a highly disproportionate burden share for aid enablers, it needs to ensure this is well understood and communicated to other donors, both to ensure they recognise the need to share the burden and to earn DFID greater leverage in the donor community that such funding deserves.

It is important to consider the possible repercussions on local NGOs in an environment where there is a heightened awareness of fraud. Poor communications on why funding has been refused by a UN agency or high profile donor, which may be entirely unrelated to fiduciary risk, can have serious negative repercussions for that institution and create an environment of suspicion and fear. It is especially important that there is transparency on funding decisions in this context.

In a programme that has diverse elements and a wide range of implementing partners, it is important to consider how they fit together, where they might complement each other and to pull out any synergies. It is possible that one funder of this sort of collection of interventions could greatly enhance the individual components by linking up the delivery partners and focussing on how they impact each other.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Stronger use of evidence, management of risk, planning and coordination in implementing development assistance
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Coherence of programming across the UN	Number of Joint Programmes: 6	8 under way, 3 in MPTF pipeline
Analysis influences programming across the UN	Number of agencies to have received training on the programming implications of improved analysis: 180	Unclear / (The indicator is confusing since it mentions ‘180 agencies’ – since then this has changed – there are two trainings: One is the FAO study and the other is an RMB-type workshop that RCO is organizing for agencies by the end of the year. The previous head of RCO was not available to comment)
Risk Management in the UN system	Agencies with an ERM: 22	RMU reports that all 23 agencies currently have an ERM (though with varying levels of effectiveness)

Key Points

UN Risk Management Unit (RMU) – Scoring: A+

The UN’s RMU has over time proved invaluable in raising the importance of effective risk management for both UN agencies and latterly NGOs. Its assessment of the fiduciary risks of potential contractors was cited as especially useful. It continues to provide a public good to a wide variety of partners, through its risk assessments, advice on risk handling and training, and appears to have had an impact on risk management across all partners in Somalia. For example, its online risk management training tool is free and accessible to all globally, reaching more partners, whilst its forthcoming civil service tracking system will help partners to identify duplication. Since 2014, it has engaged more regularly with NGOs and civil society, including via feedback surveys, training (which has now been offered beyond UN partner NGOs), and support writing project documents. The RMU is also supporting OCHA to implement a policy of deferred prosecutions. There is now demand for the Somalia RMU model from other UN operations.

However although there is clear evidence of greater awareness of risk management, it has been hard to calibrate to what extent the collective management of risk has actually improved beyond anecdotal evidence. The RMU is primarily associated with fiduciary risks, especially fraud and the diversion of aid although more recently it has been trying to broaden this out. On the plus side, this has improved the operational environment for all donors who have greater assurance. A possibly negative repercussion, is that some, mainly local, NGOs who failed UN OCHA’s capacity assessments of partners in 2013 were unfairly viewed suspiciously due to OCHA’s relationship with the RMU. This caused resentment in the NGO community.

The sustainability of the RMU’s funding and staffing vacancies have been identified as issues. The RMU acknowledges that – since it does not receive core funding from UN Headquarters – it must seek more sustainable funding arrangements. It will now be funded by the UN MDTF.

UN Resident Coordinator’s Office (RCO) – Scoring: B

DFID funding initially enabled the RCO to staff its office in Somaliland, which, given Somaliland’s status, was necessary. Political sensitivity prevented the UN from engaging with Somaliland from Nairobi or Mogadishu. Funding was later extended to the office in Puntland and across all the Somali RCOs offices. The RCO did help ensure that Somaliland and Puntland were in the New Deal to some extent when the New Deal in Puntland in particular appeared to be unravelling and Somaliland was suspicious of the process. We found that the RCO has been able to play a coordinating role, including with the FGS to reduce the duplication of aid reporting. There are examples of where it helped coordinate the delivery of aid in Puntland and brokered FGS-Puntland relations ahead of the New Deal Compact. It also took on issues that were important for all UN agencies and negotiated outcomes with the Somaliland or Puntland Administrations for example of the use of the airports. In Somaliland, it delivered work on media freedom by creating space for journalists.

The problem for the review team was that the role of the RCO was hard to verify with some conflicting views on its usefulness. Its areas of work were often under the radar given the need to show that it was not overshadowing the individual UN agencies it was representing. However engagement with the FGS’s Ministry of Planning and in Somaliland has been patchy. Under-staffing and visibility have also been an issue. There is a question about whether the Development Partners’ Forum will become active again, and some have questioned the usefulness of the risk management database.

The RCO has improved its performance in the last year, being more responsive and putting in place risk management strategies and an operations manual for the multi-partner trust fund. There is now an NGO liaison officer based in the RCO, and the RCO has worked with the NGO Consortium to highlight protection issues to the FGS. The coordinators also seem to play a useful role in the cluster meetings. We learnt that training on results-based management is being developed.

On financial burden sharing, the RCO acknowledges that it did not focus on attracting donors beyond DFID for a long time, and the continuity of funding has been highlighted as a weakness. Some argue that the RCO should first and foremost coordinate the UN, and therefore if it is valued, it should primarily receive funding from UN core contributions or from UN agencies. The RCO has now secured funding from the EU, Sweden, Norway and Denmark for its own joint programme on aid enablers (the UNMDTF), to cover both RCO and UNDSS. Whilst it can be harder to mobilise funding for the RCO (given its coordinating role with less tangible outcomes), the RCO and RMU have now merged and are looking to share resources.

It is important to note that the logframe was developed with the previous Head of the RCO, who left to join the UN ebola team in Sierra Leone and was not available for this PCR.

Programme Analysis & Support Component – Scoring: C

As noted in previous Annual Reviews, this component underperformed in part due to the RCO’s lack of capacity to mange programme activities effectively. Funds were assigned to a feasibility study for irrigation water management in the Middle and Lower Shabelle regions. However, this has yet to be delivered by the FAO, although after intensive engagement from DFID the study has now been conducted and the report is due in November 2015. The DFID Programme Team agreed with the RCO to re-direct funds to other activities, including support for the Garowe RCO Office and the FGS Aid Coordination Unit, the feedback on both of which has been broadly positive.

UN Results Adviser – Scoring: A

The Results Adviser was placed in the RCO’s office to help improve coordination, creating a Risk Working Group for UN agencies to coordinate with each other, and later training on understanding DFID’s systems e.g. the theory of change. The adviser developed the monitoring framework and process for the Integrated Strategic Plan of the UN country team and helped deliver two rounds of monitoring and lessons learned for the UN’s senior management group. The adviser has increased awareness of the importance of and options around third party monitoring by working with the UN M&E working group, RMU and the larger UN agencies such as UNDP and UNICEF.

The adviser convenes and facilities the Statistics and Monitoring and Evaluation Working Groups, and has proposed new terms of reference to empower staff in these fora. However, challenges for the adviser include ensuring consistency in approaches to monitoring and evaluation, particularly as they can only advise rather than direct individual UN agencies. During the course of the programme, the advser’s role and objectives have had to evolve as the UN priorities and capacities have shifted but there needed to be a clearer understanding of the adviser’s objectives and deliverables. In terms of value for money, there is a question about whether the post could be localised, although it would then be more difficult to build the DFID-UN links and improve each organisation’s knowledge base of the other. (The Head of the RCO has since informed DFID Somalia that this post will be done by additional staff time secured from UN Headquarters.)

Aid Effectiveness – Scoring: A

The Aid Coordination Unit (ACU) in the FGS has played a central role in the New Deal and in the engagement of the Federal Government with the donor community. The UK is recognised as being the first donor to support the ACU, before the EU, Sweden, Denmark and others also provided funding. The ACU confirms that UK funding came at the right time. UK backing has enabled it to support the FGS in advance of the High-Level Partnership Forum conferences, and to establish the SDRF in 2013 and also the PSG Working Groups (WGs). The ACU ensures that the regions are included in these fora – Puntland now has an ACU contact point, as do Jubaland, ISWA and Benadir. Aid coordination has improved between the FGS and donors, and Somali ministers are held responsible for the effectiveness of the PSG WGs. This year the ACU was able to coordinate and liaise for the FGS on the National Consultative Forum on the 2016 electoral process, for which it has been praised, including by President Hassan Sheikh Mohamud. Ensuring an inclusive, credible electoral process in 2016 is a top UK priority.

The ACU has held a number of donor briefings, including at the British High Commission in Nairobi, on progress and the challenges it faces. It has undertaken an aid mapping exercise, with the support of the World Bank and UN to improve donor coordination. Its updates and financial reports to donors have been good. The ACU hopes to continue beyond the lifespan of the New Deal Compact, but has raised concerns that it will not have the funds to do so from early 2016, and cannot identify areas of work to be cut to save on costs.

This component also funded an aid effectiveness adviser to the FGS. She was initially part of the RCO and then worked between the RCO and UNSOM New Deal teams, providing technical assistance to the ACU. She played an essential role on the New Deal by supporting the development of the Compact, helping to set up New Deal structures including UN basket funds, and playing a central role supporting reporting, for example for the High Level Partnership Forum in Copenhagen in 2014.

NGO Consortium – Scoring: B

The NGO Consortium has proved important as a coordinating and advocacy body for NGOs – for example, ahead of the High-Level Partnership Forum in Copenhagen in 2014 and New Deal Conference in Brussels in 2013. It acts as a central voice for NGOs, and its meetings in Nairobi, Mogadishu, Hargeisa and Puntland have been well-attended by international NGOs. It has developed clear civil society positions to feed into conferences. The Consortium also arranged for an NGO Liaison Officer to be placed in the RMU. It has published operational guidelines for Somalia and Somaliland, and has also developed NGO policy positions on protection and remittances. It enables NGOs to identify and work around funding gaps, and to receive risk information. Gender has not been a strong thematic issue for the Consortium, but it has been highlighted in policy papers.

The ongoing issue is that the Consortium has been based in Nairobi and has very low participation from Somali NGOs. This has meant there have been questions about its legitimacy. The Consortium’s presence in Mogadishu is being re-established, and it recognises that it needs to strengthen its presence in Kismayo and Baidoa, whilst also supporting the capacity-building of local NGOs to build trusting relationships with the FGS – which can only be achieved by maintaining a presence on the ground. These examples have begun to enhance the Consortium’s legitimacy as an NGO coordinating body.

DFID has been funding the NGO Consortium for a shorter period than other components, and not for the full life cycle of this programme. DFID’s multi-year approach to funding has enabled the NGO Consortium to undertake long-term planning. They have been asked by donors, including DFID, to ensure the sustainability of their finances and to diversify their funding arrangements. Their funding strategy concluded that membership fees would need to be increased, for which INGOs understood the reasoning. The Consortium is now examining its funding strategy, and is keen for DFID to continue funding it because it risks facing a funding crisis.

The Consortium undertook strategy and evaluation exercises in late 2014, involving stakeholders in the process. The Consortium’s challenge now will be to remain useful and relevant. Some report that the Consortium is under-staffed. It is important to note that a number of recipients were unaware that DFID was funding the Consortium.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 Annual Review recommendations	Progress
If considering potential future funding for the Risk Management Unit, DFID should work with other donors (on the basis of the RMU’s proposed approach for 2015-2017) to ensure funding is conditional on a number of key factors that would incentivise improved performance, including: improved and more detailed financial reporting (with a prescriptive template and reporting timetable included in any new MoU); introduction of a new M&E framework, on which DFID monitoring should be based, with at least one major tranche linked to the completion of an independent mid-term review; more effective project governance structures, with tranche disbursement conditional on (a) project boards being held according to a fixed timetable set out in the MoU and (b) more regular risk management fora to seek feedback from wider stakeholders, in particular NGOs.	This has been noted by DFID. The RMU is engaging on a more frequent basis with NGOs through risk management and information management fora and feedback surveys. Since the arrival of the new Head of the RMU, reporting has improved significantly, and it now provides timely and quality reporting to DFID. A DFID colleague used to sit on the RMU Board, which began to meet more frequently.
DFID Somalia should also consider whether a small performance tranche linked to the achievement of full senior staffing complement would be effective in encouraging more effective recruitment (on which any other improvement is dependent). Any submission or business case for additional funding should include a review of the value-for-money of UNOPS project management, currently funded through a management fee of 13%.	This has been noted by DFID for any future funding.
Given the poor performance of the Programme Analysis & Support component, DFID Somalia should consider re-allocating any remaining funds to better performing components for the remainder of the project.	Completed. Funds were reallocated to the Garowe RCO Office, the RMU (UNOPS), and the FGS Aid Coordination Unit.
The RMU itself should work to diversify funding sources, and include within its next 3 year strategic plan an in-depth evaluation of the impact of the RMU, both to advertise important progress but also to enable learning.	In progress. The RMU agrees that it needs to diversify its funding sources, and did not do so in previous years of this project. It has secured funding from the EU, Sweden, Norway and Denmark for its own aid enablers project.
If considering future funding for the UN Resident Coordinator’s Office, DFID Somalia should: ensure greater burden share with other donors; and more clearly set out what the RCO offices are intended to achieve and how that could be measured.	This has been noted by DFID.
The RCO office needs to step up plans to diversify funding sources, by explaining clearly to the international community what services provided by the RCO would be in jeopardy if DFID funding ends as planned.	In progress, with the approval of the new UN MPTF Aid Enablers programme.
If considering future funding for the Aid Effectiveness, DFID Somalia should consider how to achieve greater burden share with other donors.	As above. This has been noted by DFID.

Recommendations for future programmes

In any future programmes DFID should:

- Consider how to achieve a greater burden share with other donors, and in particular those donors that benefit most from collective public goods contributing their fair share. A funding exit strategy for DFID should also be agreed formally and in writing. (SDG donors have since agreed to take a twin-track approach, in funding the new UN MPTF Aid Enablers programme in the short-medium term, whilst also collectively lobbying the UN to increase its core contributions to Somalia in the medium-long term.)
- Ensure that its contributions are not used solely to fund the core tasks of UN organisations (this should come from UN core contributions).
- Ensure that there is greater project governance and improved financial reporting, in line with DFID requirements, and maintain regular face-to-face communications with recipients and partners to stay on top of issues such as financial management and staffing.
- Ensure that the logframe remains relevant as a monitoring and evaluation tool.
- Ensure that all project components maintain visible and active communications to promote DFID’s financial support.
- Work out specialist project management arrangements carefully in advance when they are many different DFID stakeholders affected by the programme.

These recommendations apply to all three outputs of this programme.

Output Title	Stronger use of evidence, management of risk, planning and coordination in the humanitarian response
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of interventions in relevant clusters responding to emergencies utilising FSNAU information	70%	Anecdotal reporting suggests this has been achieved, although no assessment has been conducted to provide any definitive evidence
% of CERF and CHF allocations that are made towards highest priority projects; % of ERF project allocations that are made in accordance with agreed criteria	CERF 100% / CHF 90%	Pooled funds contributed US$76.8 million to Somalia operation making up 17% of funds received by the 2014 HRP. This included $55.4 million from CHF and $21.4 million from CERF (underfunded $20 million, Rapid response $1.44 million). The majority of the funds were allocated to highest priority projects.
Level of satisfaction expressed by key stakeholders (government, donors, humanitarian actors) with UN OCHA coordination leadership	Nairobi 80% (against a milestone target of 90% for Nairobi)	As per results from the 2014 OCHA Somalia’s Partner Survey.

Key Points

Food Security and Nutrition Analysis Unit (FSNAU) – Scoring: A

DFID funding has supported FSNAU to continue its work to fill a gap in the data and analysis of food security. FSNAU has consistently produced informative and technical reports every 6 months, covering food, nutrition, markets, harvests, and vulnerabilities. Feedback on these reports has been generally positive – for example, the FSNAU post-harvest briefings. The technical reports have been useful for NGO planning and targeting, and are regularly quoted by the recipients. For example, following FSNAU’s press release of the late rains in May 2014, DFID and humanitarian actors met to re-programme funds to respond. As a result of FSNAU’s analysis of the upcoming El-Nino, the UN developed a response plan, while the Food Security Cluster utilises data generated by FSNAU. FSNAU’s early warning learning and analysis ensures that information is relayed to partners, with data drawn from a wide variety of sources across Somalia.

Results are communicated openly through press briefings, and are archived on a dedicated open website. Additionally, donor visibility has been more prominent than in other areas of this programme, with donor logos displayed on core products.

Challenges have remained around the timeliness and reliability of the data being provided – for example, the 2011 famine was well underway before a report was issued that then led to action. The reports have been criticised as too technical and overwhelming recipients with data. FSNAU recognises the need to develop how its information is packaged, including making the information more accessible given their technical nature. Despite encouragement from DFID, FSNAU has continued to focus on producing its technical reports and not on building the capacity of the Somali authorities to begin to carry out its own assessments.

OCHA Somalia – Scoring: A

DFID funding has helped to support the OCHA secretariat, including coordination, staffing, and monitoring and evaluation. It has been welcomed by donors, with policies and processes enhanced through coordination meetings in Mogadishu – for example, during the Somalia Country Appeal Process. OCHA also provides ad hoc briefings, maps and documents, to the international community. OCHA’s engagement with the FGS in Mogadishu has improved in quality and quantity, and it has broadened the number of agency partners to 97 in 2015. NGOs have benefitted from OCHA’s specialist technical reviews. OCHA is refining its remote monitoring tools, including third party monitoring. OCHA’s partnership with DFID has been positive.

However communication at the outset was not as coordinated as it should have been – for example, with the exact nature of OCHA’s coordinating role not clearly defined, and civil society not included as much as NGOs would have wished. The regularity of NGO attendance at OCHA’s briefings have been mixed. Some NGOs felt OCHA’s focus was on managing the Common Humanitarian Fund (CHF) not on coordination. The general view on OCHA’s performance on coordination was coloured by OCHA’s capacity assessments required to apply for CHF funding, which was not working as it was intended (to broaden the number of implementing partners). The last assessment of NGOs was in 2013 due to procurement delays in finding a new assessor. Only NGOs who passed the assessment then have been able to receive funding under. OCHA states that many NGOs did pass their capacity assessments, and that additional assessments would be undertaken to re-test the NGOs that did not pass. These assessments were comprehensive, and necessary to identify high-risk NGOs.

Another issue is that we believe OCHA’s coordination was halted for around a year, and meetings were more focussed in Nairobi rather than in Somalia according to some partners but this has been contested. Recruitment of staff with the right skillset has also been a challenge. Whilst their general reports have been useful, it has been a challenge for DFID to obtain DFID-specific reporting.

World Food Programme – Scoring: A

WFP has used DFID funding for information management and reporting, capacity-building, analysis, advocacy, and contingency planning. WFP has provided bulletins of how the Food Security Cluster has performed. 421 organisations engage with the Cluster, and there are 13 meeting locations across Somalia, ensuring coordination and accessibility, in stark contrast to the 2011 famine when there was little coherency in the aid community’s response. Decisions in the Cluster have been informed by data on the ground from FSNAU and FUSENET, and as a result aid reaches 2.5 million Somalis per month. During Al-Shabaab’s ban of humanitarian agencies in 2012, NGOs were able to redirect resources to those that were not banned, demonstrating the collective potential (and diversity) of the Cluster. Additionally, WFP having developed guidance on thematic issues, to assist local NGOs and others to interpret FSNAU’s data and what the Cluster is recommending.

Some NGOs informed the PCR team that they received little monitoring benefits from the Food Security Cluster database, despite contributing to the database. It has become more relevant recently, but requires users to input data regularly. There is clearly more work to do but we judge that this component adequately met its objectives.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 Annual Review recommendations	Progress
Given the vital information and analysis role that FSNAU plays in the context of Somalia, there is a strong need for continuing FSNAU’s activities into the foreseeable future.	DFID recognises the vital data and analysis that FSNAU provides to the aid community, and funding will continue under DFID Somalia’s humanitarian programme.
FSNAU needs to speed up implementation of government institutional capacity development.	Some progress. FSNAU is training FGS staff and building institutional capacity – for example, through its collaboration with local universities and establishing new units throughout Somalia but there is little evidence of results.
FSNAU needs to strengthen and broaden existing technical partnerships	Some progress. FSNAU liaises with and provides data to organisations including WFP and the Food Security Cluster / Inter-Cluster Working Group.
FSNAU needs to broaden its donor base and diversity its funding sources.	Unclear. DFID should follow up on this point before committing to future funding.

Recommendations for future programmes

OCHA should investigate means of raising its visibility and ensuring that its risk/capacity assessments for NGOs are explained clearly.

Output Title	Greater access for aid workers in Somalia through the provision of improved safety and security
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of UN and INGO aid workers covered by emergency medical response services	2,400	2000 workers covered during the period of DFID funding
Number of aid workers provided with security information	1,500	1,170 persons on NSP mailing list (by 15/10/2014)*. / 1,213 persons on NSP mailing list (by 12/06/2015). / 311 aid workers trained in individual security training; 55 in country director & security focal points (SFP) training. / A total of 1,273 aid workers from January 2012 - March 2015 in individual safety training, and 104 as Country Directors & SFP. / *This information may have been further distributed, thus reaching a wider range of personnel, but the review assumes the indicator is intended to measure primary recipients.
% of NGOs operating in Somalia satisfied with the support they receive from the NGO Safety Programme (NSP)	60%	Daily reports: 76% NGOs consider them good or very good. / Bi-weekly briefings: 73% NGOs consider them good or very good. / Ad-hoc briefings: 79% NGOs consider them good or very good. / Emergency response: 69% of the NGOs who have used the service consider it good or very good. / Source: NSP Satisfaction Survey, March 2014 / The External Evaluation (March 2015) does not disaggregate by service, but states: “Approximately 90% of NGOs declared NSP services improved their security and had an influence on their decision making and operations”.

Key Points

UNDSS – Scoring: A

DFID funding has supported two broad activities for UNDSS – the provision of 4 Medical Emergency Response Teams (MERTs), and the expansion of UNDSS into Mogadishu and latterly to other locations in South Central (Kismayo, Baidoa, Beletweyne, Dolow and Dhobley). It is clear from feedback during PCR meetings that, without these MERTS and the platform, many UN and non-UN agencies (including UK Government agencies) could not operate in Somalia. For example, donors rely on UNDSS vehicles for transportation in Puntland, although there is a question over which organisations are prioritised for the use of vehicles. UNDSS is working with the RMU to share information and examine integrated risk profiles.

However, there have been genuine concerns about UNDSS’ engagement with DFID on its financial management and business planning. It confirms that it does not receive much funding from UN core contributions for operational activities, and costs rise exponentially in Somalia. Additionally, others have commented that UNDSS does not provide specific, tailored security advice to NGOs, but this is provided by the NSP, which updates on a real-time basis.

NGO Safety Programme – Scoring: A+

The NSP has been widely praised, and is seen as imperative for the security of NGO staff in Somalia. Their security training is free and accessible, with 450 NGO staff trained each year. Many NGOs would not have the capacity or funds to undertake private or self-training if the NSP did not exist. The training is flexible and alternates between Hargeisa and Nairobi. Attendants provide useful and positive feedback to the NSP, and the course is reorientated based on the comments. The security training is more democratic if provided to NGOs free of charge; otherwise there would have to be criteria about which NGOs to charge although it is clear some NGOs would have been able to cover the costs. The NSP distributes daily bulletins of security updates from the ground in Somalia, which help to corroborate reports of insecurity, and which donors and the UN can also access. The majority of their work involves providing specific, tailored advice and guidance to NGOs.

NGOs also heavily rely on the NSP’s security updates and the bi-weekly briefings. There has been concern over the suspension of training by the Kenyan Police, on which there has been no progress since June 2015. It is unclear when the training will resume in Nairobi.

As with the NGO Consortium, some of the recipients of the NSP told the PCR Team that they were unaware of DFID’s involvement and funding, despite it being an active and visible project. A new set of indicators have been agreed for the NSP. They agree that they could do more to focus on gender-related issues in their activities. The NSP works for the NGOs, but DFID could have obtained more reports from them. The NGOs can access areas of Somalia that DFID cannot. Some partners on the ground do not have access to the regular meetings, and those wishing to take part in the safety programme have to be affiliated to an NGO to learn about the opportunities. In the absence of the NSP, it is not clear that another donor would have provided funding for training, and so the number of NGO staff receiving HEIST training is higher than it would otherwise have been.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 Annual Review recommendations	Progress
A new set of indicators to be agreed with NSP.	Completed in September 2015.
PCR expected from NSP following up on recommendations.	Not completed.
If considering continued funding for the Somalia NGO Consortium, DFID Somalia should if at all possible ensure it is provided for a longer term period to increase predictability and lessen administrative burden.	This has been noted by DFID, although funding is not being continued.
Notwithstanding its plans not to continue funding for UNDSS after the end of this programme, DFID Somalia should encourage and support improvements to UNDSS financial management and planning, in order to help them finance their operations and continue to provide a platform on which international aid agencies can operate in Somalia.	This has been noted by DFID, although information on UNDSS’ financial management and business planning has not yet been received. / DFID Somalia worked hard to encourage UNDSS to improve its financial management and planning. The former DFID Head of Office and Ambassador wrote a joint letter to UNDSS, and there then followed a number of meetings with them. DFID Somalia worked with donors and the UN to push the development and funding of the UN MPTF Aid Enablers programme, which will guarantee funding for the short-medium term.
UNDSS itself needs to urgently improve its financial management and business planning systems, in order to be able to provide confidence to donors that it can manage funds effectively and transparently.	Unclear – specific information from UNDSS on this has not been received at the time of writing.
For NSP, demand for Hostile Environment Individual Safety Training (HEIST) had a slight drop in demand. Follow up with the NGOs concerned indicates this is as a result of reaching a critical mass of already trained staff. DFID Somalia should follow-up with NSP to decide whether to use funding to provide alternative training courses attracting higher demand.	This has been noted by DFID. However, when the PCR Team raised this with NSP they said that they used feedback from each participant of the security training to improve and reorientate the training, rather than provide bespoke training.

Recommendations for future programmes

In any future programmes DFID should:

- Ensure that it obtains more information from the NSP, who can access the areas of Somalia that DFID cannot.
- Ensure that a greater number of Somali NGOs are represented in both the NGO Consortium and the NGO Safety Programme.
- Work with both the NGO Consortium and NSP to ensure that thematic issues are highlighted sufficiently in their reports and training e.g. gender issues.
- Work closely with UNDSS to help improve its financial management and business planning, in order to help them finance their operations and continue to provide a platform on which international aid agencies can operate in Somalia, and to be able to provide confidence to donors that it can manage funds effectively and transparently.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key cost drivers have varied across the different components, although DFID funding has supported staffing costs in all the projects. However, until it was updated in April 2015, the logframe had become out of date and was no longer effective as a monitoring and evaluation tool, and no value for money analysis has been undertaken on this programme despite recommendations in all three Annual Reviews that this takes place. This means that there is little data on which to assess key costs drivers or performance. In part, this is due to the lack of financial reporting from UN agencies in line with DFID’s requirements, and should be addressed in any future funding arrangements as there will always a constraint on what UN agencies will provide. DFID Somalia later introduced 6-monthly Risk, Results and VfM meetings with ART on this programme, which greatly improved the monitoring of VfM, risk and reporting of results.

The NSP confirm that it has few outgoings beyond staff, bills and the training they provide, as they are centralised in Nairobi and do not sub-contract.

Funds have been spent on the activities to which they were assigned, although there have been a number of areas where financial performance was not up to DFID’s standards and the DFID Programme Team took action to rectify this. For example, the “Programme Analysis & Support Component” underperformed, and it was agreed (without consulting and seeking the requisite agreement from DFID) that funds would be redirected to a feasibility study for irrigation water management (yet to be delivered by the RCO). Other funds were re-directed to support the Garowe RCO Office, the FGS ACU and the NGO Consortium.

VfM performance compared to the original VfM proposition in the business case

The VfM proposition in the Business Case was based on the assumption of a number of benefits for each component. The evidence for these is assessed in Annex 1, where the extent that the benefit was achieved is rated as High, Medium or Low. On this basis the VfM of each component may be summarised as follows:

Core Support to Somaliland RCO: Medium delivery of benefits: Provision of leadership on key issues and Improved coordination between UN agencies. Low delivery of benefits: Facilitation of donor access (reducing transaction costs); Improved coordination across the donor community; Provision of on the ground intelligence; Reduced transaction costs for the Somaliland administration; Reduced transaction costs for UN agencies

UN Risk Management: High delivery of Benefits: Better UN programming and Reduced fiduciary risk

Analysis and Programme: Low delivery of benefits: Improved quality and effectiveness of UN programming; and Improved harmonisation of the development, humanitarian and political aspects of the UN’s work.

Aid Effectiveness: High delivery of benefits Improved commitment to agreed aid effectiveness principle; Improved commitment to agreed aid effectiveness principle; Reduced duplication and fragmentation of aid; and Improved wider donor coordination. Low delivery of benefits: Increased transparency and accountability in the UN system and Improved cost-effectiveness within the UN

Results and Statistics Manager: High delivery of benefit Improved UN accountability. Medium delivery of benefit Improved UN programming

Support to FSNAU: Medium delivery of benefit Lives saved and livelihoods protected. Low delivery of Benefit Stronger Somali institutions and partners

Support to UN OCHA: Medium delivery of benefits Lives saved and livelihoods protected and Duplication and waste within the humanitarian response.

Support to UN DSS Medical Emergency Response Teams: High delivery of benefit Improved safety and security for all donor staff operating in Somalia. Medium delivery of benefit: Increased deployment of aid staff on the ground.

Support to UN DSS to help improve security for UN staff operating in Mogadishu: High delivery of benefits Improved security for UN staff operating in Mogadishu and Increased deployment of UN staff on the ground in Mogadishu

Support to NGO Safety Programme: High delivery of benefits: Improved safety and security for NGO staff operating in Somalia; Increased deployment of NGO staff on the ground; and Reduced NGO operational costs

The highest performing components were therefore UN Risk Management, Aid Effectiveness, Support to UN DSS to help improve security and Support to NGO Safety Programme

Assessment of whether the programme represented value for money

Broadly, it is clear that the programme represented good value for money for DFID; it achieved what it was intended to do within the budget.

Results: As a result of this programme, there is overall improved coordination and efficiency in UN agencies and the aid community operating in Somalia, and greater access for NGOs and all partners operating on the ground. The counter-factual is hard to measure with a programme of this nature, but recipients of DFID funding have commented time and again that, in the absence of DFID support – for example, to the NGO Safety Programme or UNDSS MERTs – they simply could not maintain a presence in Somalia. It is also clear that there have been a number of additional, sustainable benefits as a result of this programme. For example, the FSNAU’s technical data has been valuable for the Food Security Cluster’s planning and targeting, and OCHA is deepening its coordination with UNSOM and UNSOA.

Costs: The budget was spent largely as planned. Overall DFID’s funding has been proportionate to the needs of the recipients and we judge had an impact greater than the level of funding. Partners have welcomed DFID’s leadership and multi-year approach to humanitarian programming, which has allowed them to plan more effectively. In the absence of this programme, both humanitarian and development operations in Somalia would be affected, leading to poorer VfM of aid in general in Somalia. However, DFID has taken on a disproportionate burden share vis-à-vis other donors operating in Somalia. In the case of the NSP, DFID’s financial burden share stands at 24% - this has increased, not as a result of additional DFID funding, but as a result of decreased funding from other donors. Efficiency savings have been found by offering all NGOs training rather than individually charging them. There was an indication that the RCO received more funding than it needed at one stage but the funding level was adjusted in response.

Sustainability: Sustainability has been an issue but, as a result of DFID lobbying efforts throughout the lifespan of this programme, partners are now actively diversifying their funding sources, and will be aided by the advent of the UN MPTF Aid Enablers programme. For example, NSP confirm that they have another 2½ years’ worth of funding confirmed, including from ECHO and Switzerland, while the NGO Consortium increased its membership fees in response to donor requests that it establishes more sustainable funding arrangements. It is also re-evaluating its funding strategy. The RCO has sought funding from a greater number of donors for its own joint programme for aid enablers, including the EU, Sweden, Norway and Denmark, and is also investigating options for receiving more core funding from UN Headquarters.

VfM practices: Because financial reports have not always been up to DFID standards (despite regular DFID engagement with partners on this issue), it is difficult for the PCR Team to assess vfm practice in detail. There is the additional problem of a varied approach from the raneg of implementing partners. It is clear that vfm practices were tracked and judged to be adequate for the main components.

Quality of financial management during programme

As mentioned above, the quality of financial management across the programme has been variable. For example, the NGO Consortium has provided all financial reports requested of them, whereas financial management under some other components has not been upto current DFID standards, in particular UNDSS, despite DFID advice. Some recipients were funded in advance, and others were paid in arrears. For the UN components, funding was against pre-commitments and not in advance of need. For all other components (under Accountable Grants), funding was provided against activities already undertaken.

All funds to the UNDP including additional funding to the ACU have been spent. Around £ 2,340has been set aside to pay for the costs of undertaking this PCR.

Financial profile	2011/12	2012/13	2013/14	2014/15	2015/16	Total
Intial budget projection	2.7	3.2	3.3	2.7	0.0	12.0
Actual spend	2.7	3.0	3.3	2.9	0.1	12.0

Since 2014, where major issues have arisen, the DFID Programme Team worked hard with partners to take action to rectify them, and significantly strengthened all aspects of programme and financial management – they ensured Annual Review recommendations were followed up; put in place a Delivery Plan; introduced six-monthly Risk, Results and VfM meetings; ensured financial and narrative reports were received and analysed in a timely manner; followed up on issues of quality and accuracy, e.g. insisted on more detailed financial reporting; ensured funds allocated to the irrigation study were spent as stipulated; monitored ARIES financial information to ensure the accuracy of information; and conducted independent audits. Two major reviews were done of the programme by the DFID Programme Team, and submissions on improvements to management arrangements were written to the Head of Office each time for approval.

It will be important in future programmes of this nature that a consistent DFID programme team maintains strong oversight of financial issues, working closely with recipients, and also that more prescriptive agreements are in place to match DFID’s reporting standards.

Date of last narrative financial report	Various according to partner
Date of last audited annual statement	FSNAU, NSP and UNDP for the year ending 2014

E: RISK (½ page)

Quality of risk management over the life of the programme
Risks were sufficiently managed, with this improving towards the end of the project with the development of a programme-wide risk table and a greater focus on risk, especially the sustainability risk which represented a good level of risk management. It is evident that risk was regularly discussed with partners and risks managed to a greater degree, which was partly due to the work on the RMU. Due diligence checks were undertaken on new implementing partners after DFID guidelines on due diligence came into effect, but this left out most agencies implementing the project.

The key risks identified in the original Business Case and comments on the status:

Risk	Status
Worsening security /continued deterioration in humanitarian situation creates an unacceptable safety risk for some components, e.g. FSNAU, UNOCHA, MERTs	This risk was not realised and hence components within this programme were able to meet their set objectives
Efforts to strengthen coordination are undermined by a lack of commitment from UN agencies operating in Somalia.	UN Agencies in Somalia appreciate the role the RCO has been able to play eg in coordinating the FGS to reduce the duplication of aid reporting, facilitating the delivery of aid in Puntland and the brokering of FGS-Puntland relations ahead of the New Deal Compact.

This programme had a component to improve risk management across all projects in Somalia in the RMU so, in a sense, risk management was central to the programme. Each component had an element of risk management but risks were not monitored systematically over the life of the programme. This was partly because of irregular programme management before 2014, changes to management arrangements, and the lack of a coherent structure to the way the different interventions were managed, with the Cabinet team managing some components and the Humanitarian team managing others. It means that some of the issues that the programme faced may have been captured earlier.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The NGO Consortium received a no-cost extension in November 2014, to 30th September 2015.

A no-cost extension was agreed for the UNDP component, which was behind track due to recruitment issues and a lack of capacity. There then followed a costed extension for an additional £35,000 (for the ACU), but no further time extension.

Performance of partnership (s)

The performance of partners has been varied, but has improved as the DFID programme team have strived to build and maintain positive working relationships with implementing partners, although this has not always been easy. Despite a rocky start with some, amid DFID’s concerns about financial management and reporting, relationships have improved significantly, and they have sought and achieved a higher quality of programme management.

Asset disposal and value obtained by DFID

DFID has undertaken asset spot checks through the life of the programme.IBCTI was hired earlier in this year to verify the assets’ statuses (the reports are saved on Questnumbers 5090689 and 5090672).A process is underway with UNDP and the NGO Consortium to assess which DFID assets (including armoured vehicles and computers) will be retained by them for development activities, and which will be returned to DFID.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The PCR Team noted how, increasingly, technical data and evidence is being used by partners to support more effective targeting of aid delivery across Somalia. For example, FSNAU’s technical data assists the WFP and Food Security Cluster in their planning exercises.

The RMU’s risk management database uses information fed in by partners and NGOs to improve the quality of its risk management and aid coordination. The RCO/RMU is also developing results-based management training which will assist NGOs to focus on results and outcomes/outputs. The NSP undertook an evaluation by an external consultant in March 2015, and seeks feedback from all participants of its training programme. It will be sending its own PCR to DFID containing further quantitative data. The NGO Consortium undertook an evaluation in late 2014 involving stakeholders.

No other components have planned evaluations. As the 2014 Annual Review noted, there is no articulated theory of change for the programme, or for the individual components. Use of evidence to support implementation has not been consistent across the components. It is important to note, however, that DFID guidance was followed when the programme was designed and approved.

Monitoring progress throughout the programme

In part due to the changeover of the DFID Project Team, it is not clear that the programme received sufficient monitoring throughout its lifespan. This could have been rectified through a consistent DFID Project Team and stronger project governance structures at an earlier stage.

As noted above, the logframe was only updated in April 2015, despite significant changes to project context and objectives, and no explicit value for money analysis has been undertaken on this programme despite recommendations in all three Annual Reviews that this takes place. This means that there is little evidence with which to evaluate VfM of this programme or individual components sufficiently. During the final year, this project was included in DFID Somalia’s six-monthly reviews of VfM, risk and results, which provides reassurance that these issues were adequately addressed in the final stages of the project.

This PCR was conducted primarily from 21st-25th September 2015 in Nairobi (with subsequent follow-up throughout October-November 2015 in London), through face-to-face meetings and phone calls to programme partners and recipients, and also through a review of the project documentation to date. It was undertaken by the Somalia Unit’s Head of Political and Economic Team and DFID’s Country Liaison Officer for Somalia, whom are independent of the programme and the DFID Somalia Programme Team but have in-depth knowledge of the context in Somalia.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process

Annex 1 VFM Aid Enablers
Core Support to Somaliland RCO
Benefit	Rating	Evidence	Lessons
Provision of leadership on key issues in the relationship between donors and the Somaliland administration. In this role for example the RCO has recently led the dialogue about NGO legislation that if implemented would significantly undermine the delivery and impact of humanitarian and development assistance.	Medium	The RCO took on issues that were important for all UN agencies and negotiated outcomes with the Somaliland or Puntland Administrations for example of the use of the airports and security requirements. In Somaliland, it delivered work on media freedom by creating space for journalists.	Results were hard to quantify. The RCO’s areas of work were often under the radar given the need to show that it was not overshadowing the individual UN agencies it was representing. / Visibility was therefore a problem and meant many were not aware of RCO’s activities making it harder to verify results. / When the key benefits are coordination and reduction of transaction costs, more work must be done to determine a baseline and how improvements will be demonstrated at the beginning of the project.
Improved coordination between UN agencies that ensures the UN works coherently addresses key issues collectively and speaks with one voice.	Medium	We found that the RCO has been able to play a coordinating role, including with the FGS to reduce the duplication of aid reporting. There are examples of where it helped coordinate the delivery of aid in Puntland and brokered FGS-Puntland relations ahead of the New Deal Compact.
Improved coordination across the donor community including through the Somaliland partners forum and a complementary role if a permanent UK presence were to be established in the future.	Low	Development Partners’ Forum was useful but has not been operational for some time.
Facilitation of donor access (reducing transaction costs), including through the provision of support in facilitating missions and security.	Low	There was some evidence for facilitation of donor access because of the benefits for the wider donor community on its engagement on common issues for UN agencies (such as media reporting and security). However most of the added value of the RCO was directed at UN agencies.
Provision of on the ground intelligence both for the UN and bi-lateral donor agencies that facilitates strategic planning.	Low	There was no evidence that this benefit was realised.
Reduced transaction costs for the Somaliland administration in dealing with the UN system by the provision of a single point of contact and by the creation of space for UN sector programmes to be discussed and reviewed in a single forum.	Low	Engagement with the FGS’s Ministry of Planning and in Somaliland has been patchy. The review team were not able to speak to the Somaliland Authorities but anecdotal evidence was that the Administration does not credit the RCO office with reducing transaction costs.
Reduced transaction costs for UN agencies by sharing information and resources that helps avoid duplication across the UN and by promoting joint missions that minimise individual agency’s costs.	Low	There were limited results in the area of transaction costs. Most partners felt that better coordination had increased transaction costs in terms of the demands on them and there was limited enthusiasm for the benefits.
UN Risk Management
Better UN programming as a result of the adoption of risk management approaches that systematically take into account programmatic and institutional risks (the objective is that all UN Somalia agencies, funds and programmes as well as the UN’s largest implementing partners have adopted a common risk management approach by end of 2014).	High	The UN’s RMU has had a significant impact on risk management for both UN agencies and latterly NGOs and there is now a common, recognised ‘good practice’ approach to risk across the donor community in Somalia. / It continues to provide a public good to a wide variety of partners, through its risk assessments, advice on risk handling and training, and appears to have had an impact on risk management across all partners in Somalia.	The value for money of this intervention is high. Despite this the sustainability of the RMU’s funding and staffing vacancies have been issues. There could be more effective ways of using evidence of impact to secure funding.
Reduced fiduciary risk in UN programmes (including through the development of a transparent contractor information management system).	High	The RMU’s assessment of the fiduciary risks of potential contractors was cited as especially useful.
Analysis and Programme
Improved quality and effectiveness of UN programming through research and analysis of key issues that can inform common UN approaches. These issues will include conflict-sensitive programming, environmental protection, the implications of emerging administrations and approaches to counter-piracy.	Low	This component underperformed in part due to the RCO’s lack of capacity to mange programme activities effectively.	It is important to capture and respond, including by closing down, underperforming components.
Improved harmonisation of the development, humanitarian and political aspects of the UN’s work.	Low	There was no evidence for this benefit.
Aid Effectiveness
Increased transparency and accountability in the UN system including through the use of the development assistance database and the production of reports on aid flows and the UN’s performance.	Low	Limited evidence that this programme contributed to results in this area.	Sustainability is an issue in this area. Improvements in aid effectiveness are not embedded but the FGS is reluctant to fund these areas of work when budgets are so constrained.
Improved commitment to agreed aid effectiveness principles in the wider international community in Somalia. The unit will promote a Somali lead on aid management and aid effectiveness and help Somalia to monitor compliance with, e.g. adherence to the Fragile States Principles in Somalia.	High	The Aid Coordination Unit (ACU) in the FGS has played a central role in the New Deal and in the engagement of the Federal Government with the donor community. UK support has enabled it to support the FGS in advance of the High-Level Partnership Forum conferences, and to establish the SDRF in 2013 and also the PSG Working Groups (WGs).
Reduced duplication and fragmentation of aid. The unit will in particular promote the development and implementation of agreed sector policies in areas such as health, infrastructure trade policy etc.	High	The ACU has undertaken an aid mapping exercise, with the support of the World Bank and UN to improve donor coordination. Its updates and financial reports to donors have been good.
Improved cost-effectiveness within the UN. The unit will support the provision and use of common services to promote better value.	Low	Limited evidence of cost effectiveness.
Improved wider donor coordination. The unit will support the RCO in the secretariat function it now performs for CISS ExCom (bringing together the UN, the World Bank, other donors and NGOs).	High	An aid effectiveness adviser to the FGS was initially part of the RCO and then worked between the RCO and UNSOM New Deal teams, providing technical assistance to the ACU. She played an essential role on the New Deal by supporting the development of the Compact, helping to set up New Deal structures including UN basket funds, and playing a central role supporting reporting, for example for the High Level Partnership Forum in Copenhagen in 2014.
Results and Statistics Manager
Improved UN programming through better use of evidence and focus on results.	Medium	The Results Adviser was placed in the RCO’s office to help improve coordination, creating a Risk Working Group for UN agencies to coordinate with each other, and later training on understanding DFID’s systems e.g. the theory of change. The adviser convenes and facilities the Statistics and Monitoring and Evaluation Working Groups, and has proposed new terms of reference to empower staff in these fora.	During the course of the programme, the advser’s role and objectives have had to evolve as the UN priorities and capacities have shifted but there needed to be a clearer understanding of the adviser’s objectives and deliverables
Improved UN accountability through better monitoring and evaluation.	High	The adviser developed the monitoring framework and process for the Integrated Strategic Plan of the UN country team and helped deliver two rounds of monitoring and lessons learned for the UN’s senior management group. The adviser has increased awareness of the importance of and options around third party monitoring by working with the UN M&E working group, RMU and the larger UN agencies such as UNDP and UNICEF.
Support to FSNAU
Lives saved and livelihoods protected as a result of timely and high quality information and analysis on the humanitarian situation.	Medium	FSNAU has consistently produced informative and technical reports every 6 months, covering food, nutrition, markets, harvests, and vulnerabilities. Feedback on these reports has been generally positive – for example, the FSNAU post-harvest briefings. The technical reports have been useful for NGO planning and targeting, and are regularly quoted by the recipients. For example, following FSNAU’s press release of the late rains in May 2014, DFID and humanitarian actors met to re-programme funds to respond. As a result of FSNAU’s analysis of the upcoming El-Nino, the UN developed a response plan, while the Food Security Cluster utilises data generated by FSNAU. FSNAU’s early warning learning and analysis ensures that information is relayed to partners, with data drawn from a wide variety of sources across Somalia.	There was little actual incentive for FSNAU to build Somali capacity and they were not the right agency to do this.
Stronger Somali institutions and partners with improved capacity for food security, livelihoods, and nutrition monitoring, assessment and analysis.	Low	Despite encouragement from DFID, FSNAU has continued to focus on producing its technical reports and not on building the capacity of the Somali authorities to begin to carry out its own assessments.
Support to UN OCHA
Lives saved and livelihoods protected through improved coordination and better analysis to inform resource prioritisation and gap identification and by advocacy on the protection of civilians and international humanitarian law.	Medium	Policies and processes have been enhanced through coordination meetings in Mogadishu – for example, during the Somalia Country Appeal Process. OCHA also provides ad hoc briefings, maps and documents, to the international community. OCHA’s engagement with the FGS in Mogadishu has improved in quality and quantity. This has improved coordination, gap analysis,	DFID is also funding OCHA’s management of the Common Humanitarian Fund (CHF). Some NGOs felt OCHA’s focus was on managing the Common Humanitarian Fund (CHF) not on coordination. Ensuring priorities of all projects implemented by one agency is a challenge that needs to be carefully considered.
Duplication and waste within the humanitarian response reduced by effective coordination and prioritisation.	Low	NGOs have benefitted from OCHA’s specialist technical reviews. OCHA is refining its remote monitoring tools, including third party monitoring However the exact nature of OCHA’s coordinating role not clearly defined, and civil society not included as much as NGOs would have wished.
Support to UN DSS Medical Emergency Response Teams
Improved safety and security for all donor staff operating in Somalia through the provision of emergency medical and evacuation facilities. This is currently benefitting over 1500 UN, NGO, and donor international staff on the ground (there is no reliable data on number of local staff covered).	High	It is clear that without MERTS, most UN and non-UN agencies (including UK Government agencies) could not operate in Somalia.	DFID had limited leverage over the UNDSS given its critical role. In other words, it did not have to listen to DFID despite initial concern from DFID over its financial management and business planning.
Increased deployment of aid staff on the ground helps improve implementation of development assistance and the humanitarian response.	Medium	The has been increased deployment of aid staff which has been dependent on UN DSS MERT but it is difficult to determine how much DSS MERT was a key factor.
Support to UN DSS to help improve security for UN staff operating in Mogadishu
Improved security for UN staff operating in Mogadishu especially through the creation of locations with enhanced physical security and the use of armoured vehicles for movement.	High	It is clear that, without the security platform provided by UN DSS, many UN and non-UN agencies (including UK Government agencies) could not operate in Somalia. For example, donors rely on UNDSS vehicles for transportation in Puntland, although there is a question over which organisations are prioritised for the use of vehicles. UNDSS is working with the RMU to share information and examine integrated risk profiles.	Given the centrality of these services to the donor community, DFID needs to ensure it has an exit strategy to bring in other donors gradually or ideally switch to UN central funding from the beginning of the project.
Increased deployment of UN staff on the ground in Mogadishu expands and improves the humanitarian response and key development activities.	High
Support to NGO Safety Programme
Improved safety and security for NGO staff operating in Somalia through the provision of security advice, training and operational support.	High	The NSP was almost universally praised, and is seen as imperative for the security of NGO staff in Somalia. 450 NGO staff are trained each year and NGOs rely on the NSP’s security updates and the bi-weekly briefings.	Many recipients of the NSP were unaware of DFID’s involvement and funding, despite it being an active and visible project. When funding a public good, DFID does need to address how it will fully benefit from the good will this creates.
Increased deployment of NGO staff on the ground helps improve implementation of development assistance and the humanitarian response.	High	Greater number of NGO staff accessing security training has increased deployment and helped improve implementation of assistance. For example, specialist staff, such as M&E experts, have been able to carry out field work whereas in the absence of the support, the security costs could have been prohibitive.
Reduced NGO operational costs by pooling information and training costs and by being able to predict and manage potential crisis situations	High	The security training is free and accessible. Many NGOs would not have the capacity or funds to undertake private or self-training if the NSP did not exist. The NSP encourages cooperation on security reducing individual operational costs to NGOs.