Annual Review - Summary Sheet
Title: Improving the Quality of General Education in Ethiopia
Programme Value: £130 million		Review Date: February 2017 / Review Period: April 2016 – Feb 2017
Programme Code: 203396	Start Date: 18 October 2013	End Date: July 7 2018

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

Main Acronyms Used
CDID	Curriculum Development and Implementation Directorate
CEICT / CPD / DLIS	MoE Centre for Education and ICT / Continuous Professional Development / Disbursement Linked Indicators
EMIS	Education Management Information System
ECCE	Early Childhood Care and Education
ESDP	Education Sector Development Programme
ETWG	Education Technical Working Group
GEQIP / IFR	General Education Quality Improvement Programme / Interim Financial Report
GoE	Government of Ethiopia
JISM	GEQIP Joint Implementation Support Mission
MDTF	Multi Donor Trust Fund
MoE	Ministry of Education
MoFEC / NLA	Ministry of Finance and Economic Cooperation / National Learning Assessment ( NLA)
QESSP	Quality Education Strategic Support Programme
PTAs / REB	Parent Teacher Associations / Regional Education Bureaus
SIP / WASH / WB	School Improvement Programme / Water, Sanitation and Hygiene / World Bank

Summary of progress and lessons learnt since last review
The Ethiopian General Education Quality Improvement Programme Phase II (GEQIP II) was approved by DFID in October 2013 to support the Government of Ethiopia’s (GoE’s) general education sector. It is a four-year (January 2014 - July 2018), £130 million programme with the bulk of funding (£120 million) going through a World Bank managed Multi-Donor Trust Fund (MDTF) and the remaining £10 million to technical assistance to support research and evidence building, capacity building and technical assistance to the MoE. To date, DFID has disbursed £122.4 million of its total contribution to the programme.
The project scored an A in its last review, and this was largely due to good performance in the international procurement of textbooks and the timely distribution of grants to schools. The recommendations focused on getting a better understanding of the effective use of textbooks, using the inspection process to drive up quality, and looking at ways to sustain the school grants beyond the life of the programme. There has been improvement on several fronts since the last review. These include: very good progress on the number of schools inspected, teachers upgrading that led to increased numbers of teachers with appropriate qualifications for the levels they teach, and increased evidence of good and participatory school improvement planning. However, there are several areas where progress was slower than anticipated even though the overall score remained the same as last year. The review team recognises that the civil unrest last year combined with the drought has, to some extent, contributed to this slower pace of delivery, with some schools in Oromiya affected by periods of closure.

It is worth noting that the GoE and development partners, including DFID, have worked closely over the past year to mitigate the unforeseen implications of the drought and the unrest in a timely manner. The GoE initiated its own actions and was responsive to the situation, taking measures to complement the smooth implementation of GEQIP. Notable actions include, in the current academic year, an US$8.9million investment in school feeding, WASH and other education-related expenses to ensure 1.24 million children in severely-affected drought communities remained in school. The GoE also established command posts at the beginning of the academic year in the MoE to acquire real-time information on registration and attendance rates, tracked the extent to which the unrest affected the education system and took timely measures. The success of these interventions – and lessons learned – will support plans to mitigate the risk of the current drought.

The outcome of GEQIP is intended to be improved learning conditions and institutional capacity for enhanced learning outcomes. While there has been good progress with respect to strengthening school funding and management, there has been a lack of information on how these inputs are impacting on learning in the classroom. The recent agreement to use school inspection results to track teacher’s knowledge, lesson planning, teaching practices and assessment practices may help to address this gap, although it was unclear to the review team how the inspection results relate to individual teacher performance.
The progress against the various output areas of GEQIP is summarised below;
1. In terms of improving curriculum, textbooks and inspection, international textbook procurement and distribution has continued to exceed expectations, with cost savings being used to purchase supplementary readers for the first time in Ethiopia’s history. However, the lack of accurate data on delivery and utilisation at school level is a major gap and poses risks that books are not reaching the intended beneficiaries. An independent assessment on textbook-student ratio by regions, subject and grade level, textbook utilisation and distribution of textbook has been initiated to tackle this challenge. While the programme has continued to help the inspection of schools to bed down with 94% of schools now inspected, the potential benefits of the inspection process are not being fully realised because the alignment with other aspects of the programme such as the School Improvement Programme (SIP) is not yet robust.
2. Strengthening teacher training is tracked by support to the upgrading of teachers. To date, over 90,000 teachers have been upgraded, but there is limited information on the impact of upgrading on teaching and learning. In addition, despite examinations that are prerequisite for licensing being undertaken and tools and guidelines being put in place, the actual licensing has not been carried out. According to the mid- year project review paper, one of the factors in addressing the gender balance in schools is through increasing the number of female school principals. However the data on testing and assessment of new and existing teachers during the Ethiopian School Calendar of 2005-2007 showed that out of 1098 secondary school principals, only 51 female principals passed the written exams. The progress on the indicator for upgrading the female principals is to be documented in the next annual review as the target for 2016/2017 is greater by one percent compared with the 8% baseline.
3. The school improvement programme has successfully institutionalised participatory school level planning processes and provided funds to schools to support operating costs. Augmented grants for special needs are helping to create learning environments conducive to marginalised learners. Commendable progress has also been made in using school grants to create conducive environment for female learners and supporting schools in emerging regions. However, there were delays in getting funds down to schools at the beginning of the last school year, partly because the work plan was not signed off and partly because of the unrest. This has compromised efficient delivery of school improvement plans. The issue of longer term sustainability of school grants still needs to be resolved.
4. Strengthening management and administration has been hampered by the fact that the annual statistical abstract was late in being published. There have also been reports that there is not enough programme management capacity to deliver such a complex programme. While QESSP has been able to provide some support to the Ministry it is not sufficient to meet the level of need.
5. Improved use of ICT to improve the quality of education was to include piloting e-cloud infrastructure in 300 schools and selected universities. This component has been extremely delayed as the contract had to be terminated soon after signing when MoE obtained indications of fraud in the legal document submission. Although this demonstrates the government’s capacity and dedication to detect and tackle procurement malpractices, it has negatively compromised timely delivery of the programme. The contract has now been retendered and the Bank has given its no objection for the selection of a new supplier. With only 18 months left in the new contract, it is urgent that the contract is awarded and signed as soon as possible.
6. There are some challenges with programme co-ordination and monitoring and evaluation. A planned comprehensive evaluation of GEQIP II (with baseline, midline and end line) has still not been launched and there are concerns that when it is commissioned it will be too late to provide lessons for future programme design. Reservations were also expressed about the capacity of the World Bank and Ministry of Education to effectively coordinate such a complex programme. However, fruitful dialogue has already taken place between the Bank and development partners funding GEQIP and the Bank has put in place measures to address effective spend of remaining programme funds, and better communication and monitoring structures.
The overall risk rating remains moderate, although there are increased risks around the textbook and ICT components (related to procurement) and the timeliness of the comprehensive and independent evaluation of GEQIP to inform the next phase of the Quality Improvement Program.
 Recommendations
The three key recommendations for the programme are:
1. Follow up the assessment of textbook utilisation and distribution and identify blockages for further action in the project implementation period.
2. Ensure teacher effectiveness together with stronger school leadership is prioritised during the remaining implementation period and in the next phase of GEQIP in order to have real impact on classroom performance.
3. Check that quality assurance undertakings (such as inspection, licensing exams, NLA) are followed by remedial actions (such as school improvement, CPD and curriculum revision), during the remaining project implementation period.
Other recommendations include:
- Prepare MoE, World Bank and GEQIP partners for a gradual shift from UK financial aid allocation to a greater focus on technical assistance, including delivery approach, over the next 3 years.
- Use the monthly ETWG meetings with senior MoE officials as well as the quarterly GEQIP steering committee meetings agreed between the World Bank and the MoE to discuss GEQIP progress and bottlenecks.
- Ensure the World Bank completes the comprehensive evaluation of GEQIP with the MoE to provide strong lessons for next GEQIP phase.
- Finalise with the Local Donor Group, GPE and World Bank the mechanism for channelling the additional $30 million of GPE financing based on Disbursement Linked Indicators (DLIs) to GEQIP II.
- Ensure QESSP effectively supports programme implementation over the remainder of the project, including implementation of a delivery approach.
- Review gender and disability tracking in the logframe.
- Agree a mechanism for accelerating progress on next year’s EMIS report and implementation of the EMIS improvement action plan.
- Review risks to reflect procurement challenges and the continuing capacity of the World Bank and MoE to effectively manage the programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/

Outline of the programme
The Government of Ethiopia (GoE) launched the General Education Quality Improvement Programme (GEQIP) in 2009. GEQIP is an eight-year programme to help implement the fourth and the fifth Education Sector Development Programme (ESDP IV and V). GEQIP was designed to create the conditions for improved learning outcomes in primary and secondary education.
The UK contributed £95 million to the first phase GEQIP I (2009 – 2013) through a World Bank Multi Donner Trust Fund (MDTF). GEQIP I resources, along with government and other donor’s contributions, focused on:
- Introducing school grants to support school-based development;
- Supplying 88 million high quality textbooks and teachers’ guides alongside a revised curriculum;
- A pre-service and in-service Teacher Development Programme (TDP); and
- Capacity building for Management and Planning (MAP) at all levels of the sector.
DFID is providing £120 million to GEQIP II (2013 – 2018) through a World Bank managed MDTF. The second phase continues to focus on the provision of inputs to improve conditions for learning in primary and secondary schools. Additional priorities include school inspection, teacher licencing, education technology and more recently support to Early Childhood Care and Education (ECCE). Increasing equitable access is also a focus of the programme with specific targets for girls and boys, special support to emerging regions, and the provision of additional support for those with disabilities
In addition, DFID is providing £10 million of complementary technical support through the Quality Education Strategic Support Programme (QESSP). The British Council is managing these funds with the objective of improving evidence-based programming and supporting capacity building. Focal areas for QESSP II include sector strategic planning (for example the development of a 10 year Education Roadmap), communications, and monitoring and evaluation.
The new education sector programme, ESDP V, was launched in 2015. The policy base remains much the same as under ESDP IV, but the new sector plan involves a more concentrated focus on a few, selected policy priorities, for example: capacity development for improved management; improved teacher quality; school improvement planning and quality assurance; developing core foundation skills including an expansion of Early Childhood Care and Education; and reducing high primary drop-out and repetition rates. GEQIP II is well-aligned with these priorities.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome of GEQIP II is ‘Improved learning conditions and institutional capacity for enhanced learning outcomes’. This is currently measured by four indicators.

Teacher effectiveness measured as an index of average scores of school inspection standards on teacher’s knowledge, lesson planning, teaching practices and assessment practices.	Not meeting expectations
% of schools using at least half of their school grants allocation for the SIP teaching and learning domain (April 2017 milestone 80%)	Exceeding expectations
% of Parent Teacher Associations (PTAs) positively involved in the management of school grants (April 2017 milestone 85%)	Exceeding expectations
Procurement and delivery of E-cloud infrastructure ( 1 if it is delivery 0 if not – note that there is no milestone for April 2017)	On track for meeting expectations in 2018

The original proposed measure of the extent to which teachers ask questions in class is not being used. The June 2016 GEQIP mid-term review agreed that instead the results of inspection visits should be used. A baseline has been established using the inspection data which shows that in 96% of schools teachers are not working to the required standard. There are plans to inspect 50% of Level 1and 2 schools between now and 2018 which should provide some limited data on teacher effectiveness although too late to provide any feedback to the project on its impact.
Reports from regions and field visit observations in various regions indicate that more than 90% of the schools utilised more than 50% of the school grant budget allocation for the teaching learning activities[1]. In addition, the 2016 SIP evaluation report found that 85% of surveyed schools had identified their needs through a participatory planning process and in 97% of schools visited; plans had been signed off by PTAs. There was consistent feedback from the field visits that the planning process at school level helped to mobilise additional resources for school improvement efforts. The major concern around school grants is how they can be sustained given they are entirely funded by donors
[1] Ministry of Education Annual Progress/ Performance Report from July 8 - July7 2016 Schools in Ethiopia are assessed by inspectors on a 26 point scale and scored as follows in terms of the overall standards 1= Very Bad Standard 2= Below Standard 3= Standard 4= Above Standard

The contract for the e-cloud ICT infrastructure was awarded for the winning firm in 2016, but the contract had been terminated soon after signing as MoE obtained indications of fraud in the legal document submission. The contract was no longer valid and as a result a revised bid document was approved by the
Bank for re- tendering. The World Bank provided no-objection to award the contract to the selected bidder for the provision of e-cloud infrastructure in February, which includes detailed implementation time line. Given only 18 months are left of the project timeline, the MoE urgently needs to sign a contract with the winning bidder, closely follow up implementation and ensure successful completion.

Overall output score and description

Output	Impact weighting	Score
Improved curriculum, textbooks and inspection	15%	A
Strengthened teacher training programme	15%	B
Improved school improvement programme including provision of school grant	30%	A
Strengthened education management and administration	13%	B
Maximising the impact of GEQIP II through strategic supports from the Quality Education Strategic support programme (QESSP)	12%	A
Improved use of ICT to enhance the quality of education	5%	A
Improved co-ordination, monitoring and evaluation	10%	B

Key lessons

GEQIP is a large complex programme and needs sufficient management capacity to ensure effective coordination of inputs to maximise the outcome and impact.

Providing TA via QESSP has been effective, but it needs to be more tightly tied to the GEQIP programme development objectives and its delivery accelerated.

Even a small shift in resources such as the 1% of school grant funding for special needs can have significant impact at school level.

There was not enough capacity to effectively conduct large scale procurement such as the ICT equipment and this should have been factored into the programme design and prioritised in the inception stage

The GoE has taken commendable actions in expanding school feeding and providing support for the drought-affected communities that has contributed to reducing its negative consequences on GEQIP delivery. However, it is important to develop contingency plans as part of a project inception for unanticipated events such as the political unrest and drought last year as these could have serious knock-on effects for programme delivery.

Rigorous monitoring and evaluation has not been given enough attention and this has led to significant gaps in understanding the impact of inputs at school level, and risks that supplies such as textbooks could be misappropriated.

Key actions
See recommendations in the summary

Has the logframe been updated since the last review?
The logframe was updated based on recommendations from the 2015 review. The changes are:

Output 2 – ABE indicator was dropped as GEQIP is not funding upgrading of ABE facilitators
Output 4 – was revised to focus on leadership training and the dissemination of the Statistical Abstract.
Output 5 – this is a new output focused on tracking the impact of QESSP
Output 6 – the weighting was reduced to 5%

It is not recommended to further change indicators in the logframe at this stage. However, the logframe should be reviewed in terms of tracking of gender and disability and reflect DFID’s contribution in strengthening teacher training in a more holistic manner.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved curriculum, textbooks and inspection
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Ratio of number of students to number of subject books distributed to students	1:0.9	Output moderately did not meet expectation: - Desk review of the Mode’s CDID shows a 1:1 ratio. Field visits to schools during the AR suggest the ratio is around 1:2 with substantial variation and the JISM field visit to SNNPR also found the same. A formative evaluation on curriculum implementation shows shortage of textbooks in some schools but not the exact ratio. The most reliable source of information for this is the MoE’s desk review which shows a 1:1 ratio. / (Score: B)
Number of textbooks and teacher's guides (based on new curriculum) distributed to schools (cumulative)	68million	Output met expectation : - As of January 31, 2017, about 69 million copies of Grades 1-12 reprints (37 million copies) and Grades 1-8 mother tongue textbooks and teachers’ guides (32 million copies) have been delivered to schools. / (Indicator Score: A )
% of schools inspected each year	100%	Output met expectations: - Overall more than 94% of schools have been inspected, and plans are now underway for re-inspection of schools at Level 1 and 2. Moreover, out of the 44 Level 1 and 2 schools planned for joint re-inspection by the woredas and the Federal School Inspection Directorate, 24 (more than 50%) are already re-inspected. / (Indicator Score: A)

Key Points

There have been substantial savings in the textbook component and these have been used to sign further textbook contracts, including for 60 million copies of supplementary learning materials. The procurement of audio-book readers, unfamiliar to Curriculum Development Implementation Directorate (CDID), is under discussion.

The need for independent assessment of textbook utilisation and distribution has been recognised and initiated by the MoE. This will provide evidence on whether textbooks are being delivered to schools in a 1:1 ratio and also on the use of textbooks. There are also cases where students do not bring books to school even if they have received them because of worries about losing them. The assessment will clarify this and recommend ways for a more effective utilisation of textbooks at classroom level.

There has been impressive progress in instituting an inspection department in the Ministry although the fact that 89% of schools are either level 1 or 2 is a concern. Efforts to link inspection results to school improvement planning are underway. This includes the development of an integration guideline for inspection and school improvement. Information on the inspection levels of the schools across all regions has been communicated to senior officials at a nationwide education conference and a political commitment to work towards improving inspection levels has been adopted by the respective regional councils. Yet, inspections seem to over-emphasise inputs such as supply of trained teachers over outcomes such as learning achievement. There are also no clear plans in place for responding to inspection findings and no incentives or sanctions for schools that do not move up to the next level when they are re-inspected.

Summary of responses to issues raised in previous annual reviews (where relevant)

The inspection rating of schools is now being used as an indicator of education quality and an index has been developed from this to measure teacher effectiveness. The distribution and effective use of textbooks has not been tracked in the reporting year but it is already initiated and will be part of the M&E undertakings in the current year.
Recommendations

Adjust the indicator and milestone for textbook procurement and distribution to reflect the additional books that are currently being procured.

Make a decision now on whether the Ministry’s request for teaching materials for all 36,000 O classes (pre-primary) should be supported under the textbook component.

Use the planned textbook survey to establish the extent to which textbooks purchased under GEQIP I and II have reached schools and are being utilised by students in classrooms.

Work with the Ministry to review the institutional links between inspection, SIP and teacher training and make recommendations for how inspection can better drive performance improvement, including clarifying the role of REBs in the school improvement process.

Raise the risk rating to high because of the lack of data on textbook distribution and use.

Output Title	Strengthened teacher training programme
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
No. of teachers upgraded from certificate to diploma and from diploma to degree (cumulative)	from certificate to diploma: 68,000 (cumulative) / from diploma to degree: 28,000 / (cumulative)	Output moderately did not meet expectation: - According to the Joint Sector Review, 20,517 (12,485 male & 8,032 female) have graduated this year from certificate to diploma making a cumulative total of 63,325 and 16,753 (13,090 male & 3,663 female) have graduated from diploma to degree making a cumulative total of 26,652. This is a very good progress given the disruption last year. (See Key Points bullet 6 below). Moreover, an additional 65035 (40115 male & 24920 female) are enrolled in the 2008 academic year (Ethiopian calendar) in the summer diploma to degree upgrading programme. / (Indicator score: B )
No. of teachers licensed (cumulative) )	2,500 primary teachers / 800 secondary teachers 500 school leaders licensed	Outputs moderately did not meet expectation: - The actual handing over of licensing certificates did not happen. However, to date, 5,149 (4,535 male and 615 female) have scored the pass mark on subject examinations and become qualified for portfolio assessment. Guidelines and tools for the portfolio assessment have been put in place. Moreover, 3,927 new graduates (exempted from portfolio assessment) have passed the subject examinations and become qualified for licensing and are awaiting award of certificates. / (Indicator score: B )

Key Points
- Availability of qualified teachers is one of the most important inputs for quality education. The upgrading intervention has led to an increase of qualified teachers from 51.7% (2010/11) to 82.85 (2015/16) and pupil per qualified teacher ratio from 1:107 (2010/11) to 1:57 (2015/16).
- Two nationwide studies, namely the National Teacher Demand and Supply Gap Analysis and Comprehensive Review of Teacher and School Leader Training Practices, were commissioned through QESSP. While the former has resulted in valuable information about the current and future demands of the sector, the latter has generated recommendations to improve quality and complementarity of the training programmes. The recommendations are agreed by the MoE, REBs and teacher training providers and have provided valuable input for the on-going revision of the teacher development blue print of the country.
- QESSP has funded an assessment of the impact of the teacher upgrading programme in the Tigray and Alternative Basic Education (ABE) training for 1100 ABE facilitators in Afar and Somali regions. The impact assessment provides insights into how future similar programmes can be developed. The ABE facilitators training has also enabled children in the two emerging regions to attend quality ABE provision.
- A national conference to examine teacher recruitment, training, deployment and management has been initiated through QESSP and the plan is finalised.
- There is a lot of upgrading being supported which is mainly focused on increasing teacher qualifications. There is as yet no evidence on whether this impacts on teaching and learning.
- About 69, 800 pre-service teacher trainees are enrolled in the 37 colleges across the country. There is no indicator in the DFID log frame on pre-service training and this would appear to be a major gap and underestimated DFIDs contribution to teacher development across the country.
- Recently, the process of teachers licensing and relicensing has been substantially revised and this is why there has been no actual licensing undertaken so far. However, considerable progress has been undertaken in the subject testing, which is a prerequisite and forms 80% of the licensing process.
- The majority of teachers who have sat a written examination as part of the licensing programme have failed even though many have recently been upgraded. There appears to be a disconnect between the licensing exercise and the upgrading programme and lack of clarity on what will happen to teachers who fail to get a licence once the system is fully introduced. However, the subject examination results are analysed and shared with the Teacher Development Programme (TDP) directorate to inform CPD plans for the sector.

Summary of responses to issues raised in previous annual reviews (where relevant)

Neither the teacher development impact study planned through GEQIP II nor the closer monitoring of universities has taken place. These are less likely to happen within the remaining implementation time of GEQIP II. However, a number of studies concerning teacher training in Ethiopia, namely, Analysis of Teacher Demand and Supply of the General Education Sector; the Current Status of Ethiopian Secondary School Teacher Education Programme and Teacher Training practices with a focus on pre-primary and primary in-service teacher training were commissioned through QESSP. The findings and recommendations have been communicated to relevant stakeholders to challenge and improve approaches for teachers’ development during the rest of the GEQIP II implementation time as well as policy and practice concerning teacher education in the future. The performance assessment for licensing has been replaced with a portfolio assessment. The ABE indicator was dropped from the logframe but no indicator of teacher performance was included.

Recommendations

- Ensure that the comprehensive evaluation systematically captures the impact of GEQIP support provided to teacher training and makes clear recommendations for how GoE should proceed with efforts to upskill teachers
- Review the plans for licensing in order to better understand how it is working and seek stronger and more concrete alignment with other components such as inspection and TDP.
- Follow up with the WB on why the TDP impact study was not undertaken.

Output Title	Improved school improvement programme, including provision of school grant
Output number per LF		3	Output Score	A
Risk:		Medium:	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% of schools receiving school grants in October every year	80%	Output moderately did not meet expectation: - There was a delay in disbursing school grants from MoFEC partly because of the civil unrest and partly because the work plan took time to agree. As of January 2017, 96% of schools had received school grants / (Indicator Score: B)
% schools receiving training on the alignment of inspection results to SIP	ToT training for the four emerging regions by MoE on the alignment of inspection results to SIP, to be cascaded to 20% of schools	Outputs moderately exceeded expectation: - A ToT on evidence based planning and decision making was conducted for 400 REB, zonal and woreda education experts and selected school principals, in which 100 of them are from emerging regions. The content includes using inspection results to inform School Improvement Plans. According to the GEQIP coordinator in the MoE, 30-40% of the trainees have cascaded training to school-level. / (Indicator Score: A + )

Key Points
- The second indicator was introduced after the last AR as the previous indicator (Liked to SIP training) was not stretching enough
- The importance of school grants arriving in advance of the beginning of the school year was flagged in order to aid school-level planning. In relation to this, MoFEC emphasised the need to get the annual work plan signed off in a timely manner. The civil unrest also likely contributed to the late disbursement of grants.
- The school grant survey is an extremely useful tool for tracking how grants are being disbursed and utilised at school level – the plan for a follow up survey is welcomed.
- The allocation of 1% of the grant to Special Education Needs (now raised to 4%) although small in scale appears to be incentivising schools to identify, create access and make provision for this target group. The additional allocation for the emerging regions is also creating opportunities for the poverty-affected communities to tackle the unique challenges they face, due to remoteness, in a more focused manner.
- School grant allocated for 0 classes has provided the most-needed resources to expand pre-primary enrolments.
- There is a need to make sure all schools have the updated guidelines and are oriented in the use of grants for special needs education.
- School grants are largely used to fund operating costs such as stationery and have been fully integrated into school budgets. There are major risks to school level financing because these grants are currently 100% donor funded. This point was raised in the last AR.
- Field visits undertaken by a DFID team reveals school grants have been utilised to create a more conducive learning environment for girls including advancing awareness and creating facilities for menstrual hygiene management and establish safe spaces for girls which has led to reduced absenteeism, improved self-esteem, and enhanced learning performance as compared to their male counterparts.

Summary of responses to issues raised in previous annual reviews (where relevant)
The main recommendation was to work with DFID economists and other donors to begin discussions on a future transition to government funding of the school grants and increased GoE financing in the education sector. The Bank indicated that it was not possible to tackle this in the current programme. However, increased amount of matched funding by the government including textbooks and school grants has been considered in the next phase of GEQIP which is currently under design and negotiation. An increased amount of information on inclusive education needs has been made available in the education statistical abstract compared with the previous years. A decision to extend GEQIP grants to 0 classes ( pre-primary) has been made and schools are utilising grants to set-up pre-primary classes. This has been verified from recent field visits to pre-primary classrooms.
Recommendations
Consider whether Special Education Needs can be tracked over the remaining life of the programme and whether the upcoming school grant evaluation sufficiently analyses the impact of additional school grants on improving learning achievement of students with special needs, girls and learners in the marginalised communities.
- Plan for the transition from GEQIP II from partner to government funding of school level running costs.
- Make sure the Annual Workplan is signed off in good time to allow for the disbursement of funds through MoFEC.

Output Title	Strengthened education management and administration
Output number per LF		4	Output Score	B
Risk:		Medium:	Impact weighting (%):	13%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
No. of school leaders received school leadership training (cumulative)	2,943 (20% female)	Output moderately did not meet expectation: According to the Joint Sector Review, 2,702 are enrolled in the current year. There is no information on % of females. 1,693 are already trained so this indicator is likely to be met / Indicator score: B
Timely dissemination of Education Statistics Annual Abstract by early October following the school year	October	Outputs moderately did not meet expectation: The National Educational Statistical Abstract was not dissiminated in October. However, the draft was shared with partners in December and is validated at the time of writing this report. This is a commendable improvement as compared to the previous year in which the draft was circulated in July. A considerable number of regional abstracts have also been made available in October. / Indicator score: B

Key Points
- The first and second indicators were changed based on the recommendations of the last Annual Review.
- We have assumed that the first indicator is tracking the post graduate Diploma in School Leadership training. This is in line with the World Bank results framework. The target there is to train 1600 over the next two years.

- The EMIS report is again delayed with the abstract distributed in December and validated at the time of writing this report. While this is an improvement on last year, it is still a major obstacle to effective planning.
- An action plan to strengthen EMIS is developed through QESSP. The study has identified mechanisms to improve timeliness, accuracy and reliability of educational data and the required investment to realise this.
Summary of responses to issues raised in previous annual reviews (where relevant)
The recommendations from the last review focused on refreshing the indicators and placing more emphasis on QESSP. These recommendations have been followed up on and there is now a new output focused on QESSP.

Recommendation
- Clarify what is being tracked under the school leadership indicator and consider using the comprehensive evaluation to assess the impact of this training
- Urgently act to get the Abstract finalised and published.
- Work with the MoE and development partners’ to implement the EMIS strengthening plan which is commissioned via QESSP

Output Title	Maximising the impact of GEQIP II through strategic supports from the Quality Education Strategic support programme (QESSP)
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
No of capacity building proposals supported by QESSP (cumulative)	12	Output met expectation: 2 proposals completed, 10 ongoing and 1 planned / (Indicator score A )
number of researches conducted/ innovative and relevant interventions identified, designed, implemented by the REBs and MoE , lesson learned, research findings disseminated to the relevant stakeholders (cumulative)	10	Output moderately did not meet expectations : 6 researches conducted and disseminated, with 7 more ongoing and one planned / (Indicator score B)

Key Points
- There was positive feedback on the contribution that QESSP had made to supporting procurement capacity in the Ministry to enable World Bank procurement guidelines to be followed.
- Over the past year, QESSP was reshaped to be impact-oriented and strategically aligned to GEQIP components. This has helped to focus the support provided. Clear milestones to be delivered through QESSP were developed and the workplan has been updated accordingly.
- At Federal level, focus has been on capacity building, knowledge management, and policy development. In terms of capacity development, QESSP has supported institutional strengthening in the Federal Ministry with restructuring agreed and lines of accountability clearer. QESSP has also been supporting knowledge management in the Ministry and there is now a clear plan for this. Support for ESDP V and a roadmap for improving EMIS were among the notable policy development contributions.
- Regions have been brought on board and QESSP-funded work is happening everywhere except Dire Dawa.
- QESSP financing was used to lay the foundation to accelerate delivery in the education context in Ethiopia. The senior leadership in the education sector requested and embraced the approach based on ruthless prioritisation and a focus on learning outcomes. A scoping study to implement a delivery unit with region-specific costed implementation plans was developed and an agreement was reached to use QESSP funding for the initial implementation of the plan.
- The late start of QESSP means that evidence is coming in just as GEQIP II is winding down
- Despite the commendable progress over the past year, QESSP is reportedly pulled in too many directions and still needs a more strategic focus

Summary of responses to issues raised in previous annual reviews (where relevant)
QESSP has not supported the development of a strategic approach to planning for leadership training and management. QESSP has been included as a separate output area and its impact weighting is increased since the last review.

Recommendations
Agree with MoE and the British Council how to align QESSP with a delivery approach to ensure that GEQIP II priorities are achieved.

Output Title	Improved use of ICT to enhance the quality of education
Output number per LF		6	Output Score	A
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Conducting a survey of ICT in education knowledge and capacity for the participating (pilot) secondary schools and universities	Detailed concept note and survey tools developed	Output met expectations – according to the JISM, CEICT has developed a detailed concept note and survey tools for conducting a baseline of ICT in education knowledge and capacity in participating secondary schools and universities. / (Indicator score: A)

Key Points

In support of GEQIP’s plan to pilot an e-cloud enabled ICT provision in 300 secondary schools, the ICT focal points from these schools were trained on ICT for education through QESSP.

The ICT survey needs to be conducted as soon as possible in order to set targets for improving capacity and practices and introduce relevant ICT-based content within GEQIP II period.

This component has been extremely slow and, consequently, less than 1% of its $34.67m budget has been spent to date. This is because fraud was detected in the e-cloud system procurement process. Although this has led to delays in setting up ICT systems, it has demonstrated the governments robust financial management and capability of tackling procurement malpractices.

The World Bank provided no-objection to award the contract to the selected bidder for the provision of e-cloud infrastructure in February. Given only 18 months is left for the project timeline, the MoE urgently needs to sign a contract with the winning bidder, then prepare a detailed implementation and monitoring plan for its successful completion. (See page V, paragraph 3) for the main reasons for the e-cloud system procurement delay.

Summary of responses to issues raised in previous annual reviews (where relevant)
The AR notes that the situational analysis was due to be conducted in April 2015 and that it was critical the study fed into policy development to ensure ICT improves teaching and learning in schools. The study has still not taken place almost a year later. The 2015 AR also notes that the component is not developing strategically and its impact should be reduced to 5%.

 Recommendations
Urgently discuss with the World Bank whether the e-cloud contract should be terminated and budget re-allocated to other components as there is a high risk that it will not be delivered before the end of the project. If a firm decision to pursue the procurement is made, closely follow up timely delivery of the intervention with in the project timeline.

Raise the risk rating for this component to high

Output Title	Improved co-ordination, monitoring and evaluation
Output number per LF		7	Output Score	B
Risk:		Medium	Impact weighting (%):	10 %
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
% Implementing Agencies (IAs) providing timely inputs to GEQIP annual planning exercise and GEQIP six monthly reports	70% with good quality	Output moderately did not meet expectation: - According to the GEQIP Coordination office in the MoE, IAs are attending the bi-annual planning and re-planning meetings and about 90% of them have submitted their reports to the GEQIP coordination office using a standard format. However, there continue to be problems with the quality of reporting from IAs leading to delays in finalising and approving work plans. / Indicator score: B
Evidence base on impact of reforms aimed at improving the quality of education	Comprehensive evaluation ToR finalised	Outputs Meeting expectations: -ToRs are finalised and no objection has been given by the World Bank / Indicator score A:

Key Points
According to the JISM, overall there is adequate staffing at federal level to support the planning and coordination of the project, with the exception of procurement and contract management. Despite additional capacity being offered through mobilising QESSP funded consultants, there still exists a capacity gap in this area.

- The annual plan for 2016/17 was reported to have been agreed late because of problems with quality.
- The JISM also reports that while it is encouraging that a single reporting template for GEQIP2 performance has been developed and distributed to all implementing agencies through training, it is crucial that the project reports include more in-depth analysis on how the component activities and its progress contribute to delivering GEQIP2 results.
- 24 consultants are being supported by GEQIP in emerging regions to strengthen capacity, but there were some questions over the precise contribution to GEQIP implementation
- Plans are on track for the comprehensive evaluation although it is still not contracted with only 18 months left in the project.
- A survey of textbook utilisation is planned for June 2017 and this is to be welcomed. It is crucial that this study also captures issues in textbook distribution down to school level.

Summary of responses to issues raised in previous annual reviews
The last AR recommended that reviews and reports should 1) identify bottlenecks and identify the ways to overcome them and 2) build on key evaluative studies. There was limited evidence of action against either of these recommendations led by the MoE, apart from the National Learning Assessment (NLA) and some researches commissioned through QESSP,

Recommendations
- Ensure that the planned comprehensive review generates robust lessons for programme implementation and detailed planning of GEQIP 3.
- Further Align QESSP with GEQIP II delivery in order to accelerate progress
- Translate JISM recommendations to concrete action plans, rigorously follow up delivery of the plans and use quarterly GEQIP steering committee meetings to discuss progress and bottlenecks of programme implementation
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers for GEQIP II, as set out in the Business Case are:

- Cost of school grants
- Unit costs of textbooks
- Unit cost of enhanced pre-service training for primary and secondary teachers
- Unit cost of upgrading teachers qualification (in-service training)
- Cost of Information and Communication Technology (ICT) infrastructure in secondary schools

As highlighted below, school grants continued to be the key cost driver accounting for 62.31% of total spend, followed by In-service teachers training (11.6%), teaching and learning materials (10.9%) and pre-service teacher development programme (8.2%). Reflecting the delay in the procurement of ICT, the spending for this component is close to zero with significant implications for the efforts to improve learning conditions at schools. It is worth noting the increase in the expenditure shares of these key components compared to the estimated costs over the entire life of the project.

Cost driver	Estimated cost over the life of the project	% from the total project cost	Total spend as at 30 September 2016	% from total spend
School grant	US$ 249 million	45%	US$135.78 million	62.3%
Teaching and learning materials	US$ 104.3 million	19%	US$23.79 million	10.9%
Pre-service teacher training	US$ 19.7 million	3.6%	US$ 17.83 million	8.22%
In-service teachers training	USD$ 29.8 million	5.4%	US$ 25.17 million	11.6%
A national ICT infrastructure Improvement	USD$ 28.4 million	5.2%	US$0.001 million	0.0005%

For the QESSP component, the key cost drivers of the programme are capacity building grants (34%), fees for international and local advisors/consultants (33%), programme operations including the deliverology work (19%).

Key Cost Drivers of QESSP

VfM performance compared to the original VfM proposition in the business case

Compared to the Business Case proposition, the GEQIP programme has shown mixed performance on VfM: improvements on the economy and cost-effectiveness side and under-performance on efficiency and some effectiveness indicators.

Average cost per textbook (a measure of Economy):
Greater saving on text book procurement: As per information from the World Bank and the MoE, 69 million textbooks of different subjects and grades have been successfully procured and delivered to schools and/or Regional Education Bureaus. The procurement process brought about $25 million (£20 million) in savings, a remarkable gain for the country. Accordingly, further 60 million text books and supplementary books are under procurement. The average price of textbook purchased was $0.58 (£0.46) significantly lower than the average unit price highlighted in the Business Case (£1/text book) and the unit cost during GEQIP1 programme (£0.70/text book). It is lower compared to sub-Saharan African countries (Tanzania £1.5, Kenya £2.43).

Total cost per primary teacher trained (a measure of cost-effectiveness):
The investment in teacher upgrading is undermined by the significant teacher turnover: The WB Education Sector Financing Review gives the annual per full-time student cost at a College of Teacher Education (CTE) in 2012 of £354 which is well below the £475 assumed in the business case. As per GEQIP2 interim financial report (IFR) for the first quarter of 2016/17, a total of US$ 25.2 million has been spent on in-service training so far. Dividing this by the cumulative 90,194 teachers, which benefited from the in-service training programme, gives a unit cost per trainer of £221.5 which is still below the £475 assumed in the business case. Yet, there are questions on the VfM of the investment in teacher training given the high staff turnover at schools estimated at 17,000 in 2015/16.

Average price of computer labs installed and operational in secondary schools (a measure of Economy):
Potential savings in the contracting of computer labs at schools: The contract for installing 2 labs each in 300 schools and 10 universities, plus national infrastructure for supporting this, is expected to cost £17.1 million. This could be considered as a cost per lab of £27,650, significantly lower than the unit cost of £31,300 considered in the GEQIP2 PAD.

Cost per primary pupil educated (a measure of Cost-Effectiveness):
Reasonable cost per pupil: The WB Education Sector Financing Review shows a unit cost of £13 in 2012/13. This is below the £20 assumed in the business case for primary pupils and that in similar African states, e.g. £42 in Tanzania. Estimates based on GoE general education spend in 2015/16 revealed a unit cost of £17 for primary (excluding admin costs) and £32 for secondary (including admin costs).

Procurement processes completed on time (a measure of Efficiency):
Underperformance on this measure of efficiency: ICT procurement is still behind schedule and this has contributed to the observed underspend in the first quarter of 2016/17. The 18 months taken for the main ICB textbook procurement was a major cause of the project underspend in 2014/15, albeit in keeping with international norms for such contracts.

Receipt of school grants - speed of delivery by system (a measure of Efficiency):
Underperformance on this measure of efficiency: Normally, the school grant is expected to be disbursed to the schools in October each year to allow them sufficient time to implement the school improvement programme (SIP). However, the review team learned of a delay of two months in the transfer of school grant to the regions/schools mainly associated with the delayed approval of the GEQIP Annual Plan. With the exception of Somali region, school grants had reportedly reached 96% of schools by January 2016, including small schools and Alternative Basic Education Centres (ABEs). In Somali region affected by the drought (with delays in opening of schools), the grants reached only 48.1% of schools. The Regional Education Bureau is planning how to utilise the budget in the remaining months of the fiscal year.

Independent evaluation on the school improvement programme (SIP)/school grant (SG)carried out in June 2016 revealed that all (100%) of the school management group and teachers covered by the study confirmed that 50% of the grant is used for teaching-learning domain of school improvement programme as indicated in school grant guideline. In addition, the evaluation highlighted that the SIP/SG is highly recognised by all study participants, irrespective of their affiliation, as an important intervention to make schools as better places for students to learn. It is filling essential gaps in the provision of education [and more importantly in the effort to improve the quality of primary and secondary education in Ethiopia].

Text book utilisation rate (a measure of Effectiveness):
There is a lack of data on whether textbooks are being effectively used at schools. As per information from the MoE, the ministry is tracking the books and their utilisation through regular school level visits and through the Joint Review missions. The Ministry’s supervision mission found instances where text books assigned to one woreda were stored in another woreda. Action was taken to redistribute the books based on such findings. Also, there is evidence that students do not bring books to school even if they have received them because of worries about losing them. A text book survey to understand distribution and utilisation is planned for next year.

Teacher effectiveness in terms of knowledge, lesson planning, teaching methods (a measure of Effectiveness):
More effort still needed to improve teacher effectiveness: Teacher effectiveness is measured as an index of average scores of inspection standards on teacher’s knowledge, lesson planning, teaching practices, and assessment practices. Based on the 2013/14-2014/15 inspection findings, the average percentage scores of this index was 45.9% for Level 1 schools and 59.6% for Level 2 schools. This value was updated using the full inspection data from 2013/14-2015/16, which includes detailed data from 34,126 schools. The results show that for Level 1 schools, the average percentage score of the index was 45.4% while for Level 2 schools the value was 59.3%.

VfM Performance of QESSP is summarised below:

Economy: The average fee paid by QESSP is one of the key VfM indicators on the economy side. Currently, QESSP is paying a fee rate of £650 for international consultants and £321 for local consultants. This seems reasonable to attract qualified and experienced advisors to deliver quality TA to the FMoE and Regional Education Beuros. The average fee rate of QESSP is as per the contract and is in line with the average fee rate paid by other DFID Ethiopia programmes. It would have been helpful if these fee rates could be disaggregated in to long-term and short term to make meaningful comparison with other programmes. Furthermore, it would be useful if the QESSP team could work out a strategy to reduce fee rates by head-hunting of qualified and experienced educational experts and consultants in country.

During the review year, QESSP managed to generate savings worth £88 thousand through a number of cost saving initiatives.. It provided the services of an International Programme Director at no cost to DFID; provided the services of a full time project officer at no cost to DFID; successfully negotiated on daily fee rate and days of input with the firm employed to undertake the scoping study on accelerated service delivery in the education sector without compromising the overall quality of service. British Council used the same fee rate set 2 years ago for a recently approved new position despite obvious increases due to inflation and rising cost of living; and looked for cost sharing with other development partners (UNICEF). It would be useful if information is provided by the QESSP team on how the savings have been utilised. Moreover, declaring the profit margins gained from the various inputs would lead to further transparency and a more informed analysis on the VFM. Hence, it would be useful for the QESSP team to do so.

Efficiency: The pace of delivery as well as fund utilisation performance of QESSP has improved since the last annual review. Currently, of the expected six main activities, QESSP is implementing 6 compared to 4 during the last Annual Review. However, the M&E framework has not progressed as expected and lack of proactive risk management system is affecting timely delivery of planned outputs.

Current spend is three times higher compared with the same period last year. The significant improvement in spend is largely due to better awareness of the project and its ways of working. Total spend in the reporting period is £1,047,613. This represents 73% of the spend target for the period (£1,389,083).

There has been strong emphasis on building local capacity in QESSP activities. The long-term advisors provided training and on-going support to MoE staff in strategic planning, aligning plans and organisational structures to sector priorities and specific areas such as branding, design and contract administration.

Cost per output: In 2016, QESSP provided capacity building grants to a number of Regional Education Bureaus. The capacity building grant to Somali REB helped to provide training to 749 existing ABE facilitators who had capacity gaps. Given the total spend of £117,850 for the training, the cost per participant was £157, which seems reasonable. Also, the capacity building grant provided to BG REB helped to provide training to 400 indigenous people community representatives and school leaders at an average cost per participant of £117, which again seems reasonable.

The spend per participant per day for the annual education conference (£42) and for the quarterly education review meeting (£49) were also reasonable. Although the total costs for research works differs by the nature of the research project, the scope of the research work and geographical coverage (National, regional and Institutional), cost per research ranged between £43k (for regional) and £134k (for national). Although comparison across other research works is difficult, the spend per research seems in the lower to middle category.

Particular	Cost per output
Cost per ABE facilitators trained (Somali)	£157
Cost per indigenous people, community representatives and school leaders trained (Benishangul Gumuz)	£139
Cost per research (regional scope)	£43,333
Cost per research (national scope)	£134,220
Cost per participant per day in the annual education conference	£41
Cost per participant per day in the general education quarterly review meeting	£49

Effectiveness: Although it is difficult to measure the actual impact of TA programmes, the QESSP programme has been working to support the development of the MoE’s and REBs’ capability in:
- Evidence-based policy formulation and analysis
- Design and management of change/reform in order to enhance organisational effectiveness and efficiency
- Programme implementation and co-ordination.
Over the last year QESSP has been on the right path towards this goal as it has now been strategically aligned around the GEQIP components and helped in the delivery of the following.

- Harnessing the effective use of data for policy reform and improving service delivery is a critical intervention supported by QESSP. To this effect, QESSP organised a workshop on deliverology for over 75 key education leaders across the three sub sectors of the education system. The workshop helped to raise level of awareness and to gauge interest in improving implementation capacity through adopting a delivery unit approach.
- Additional key achievements under effectiveness include:
  - A revised national school standard prepared ( pending a national workshop to syndicate and disseminate);
  - A revised national pastoralist education strategy prepared (pending validation);
  - A detailed report on the status of out of school children and an agreed 12 month joint government and donor action plan prepared;
  - An independent appraisal of the Education Sector Development Plan V (ESDP V) in support of Ethiopia’s request for additional funding from GPE was undertaken; and
  - A comprehensive and costed Monitoring & Evaluation (M&E) plan prepared.
There was positive feedback from the MoE on the contribution that QESSP had made to supporting procurement capacity in the Ministry to enable World Bank procurement guidelines to be followed. While acknowledging those positive signs of effectiveness, there is further need for QESSP to focus more on enhancing policy dialogue and pushing the swift implementation of the deliverology approach in the MOE. It should enhance closer working with the World Bank and the GEQIP teams at various levels to improve the effective implementation of the planned GEQIP activities.

Assessment of whether the programme continues to represent value for money

 As highlighted above, the VfM performance of GEQIP II was mixed: improvements on the economy and cost-Effectiveness side and under performance on the efficiency and some effectiveness indicators. The key underperformance areas on the VfM side include delayed release of school grant, huge lag in ICT procurement, increased teacher turnover and inability to determine text book utilisation rate at schools. Despite this, however, GEQIP II continues to be relevant to the Ethiopian Education system as it continues to help improve and transform school environments important for better learning outcomes. The procurement and delivery of text books at such a scale would not be possible without GEQIP investments. The massive upgrading of teachers can contribute to better learning, although we do not yet have evidence on the impact of such upgrading on learning outcomes. Considering this, the huge cost savings associated with bulk procurement, the reasonable cost per pupil, etc, we still consider GEQIP investment as VfM.

Looking forward, the VfM performance of the programme depends on how effectively the procured text books are used for teaching learning at schools, the ability of school grants to procure quality inputs at low cost and the concrete impact of the teacher development programmes in improving learning outcomes.

As highlighted above the QESSP component continues to deliver VfM considering the reasonable fee rates, the cost savings generated, the improved pace of delivery as well as better fund utilisation performance, the cost per output and the capacity building contributions so far. There is greater potential for delivering more VfM if QESSP team develops a strategy to reduce fee rates using local inputs as much as possible and focuses more on enhancing policy dialogue and pushing the swift implementation of the deliverology approach in the MOE.

Quality of financial management
DFID’s financial management of disbursements to the GEQIP II programme is based on its MoU agreement with the Government of Ethiopia (GoE) and the administrative agreement with the Word Bank, for WB managed Multi-donor Trust Fund (MDTF). Payment to the contracted suppliers is based on signed contracts, with disbursements following timely submission of quality-approved milestone deliverables. The table below shows the programme’s performance on overall spending against budgets and for each active programme components for the period April 2016 to March 2017.

Component Code	Component Description	Total Programme Budget	Total Spend against Budget to Date	% Spend Against Total Budget	Budget Allocated / Apr. 2016 – Mar. / 2017	Total Spend (Invoiced) / Apr. 2016 – Mar. / 2017	Annual Performance
		2012 - 2018	March 2017	March / 2017
		A	B	B/A	C	D	(D/C)
203396 - 101	Procurement of services	0.13	0.13	100%	0	0	0
203396 - 103	Strategic technical support to the Education Sector in Ethiopia (QESSP)	9.8	3.2	32.65%	2.8	2.7	96%
203396 - 104	Programme Monitoring & Evaluation	0.14	0.07	50%	0.074	0.073	99%
203396 - 106 / & / 203396 - 102	Support to the GoE GEQIP II Programme	119.8	119.0	99.3%	43	43	100%
	Total	130	122.4	94 %	45.9	45.8	99.8%

Programme budget and spending, April 2016 - March 2017, in millions & GBP (£)
The programme finance is managed through AMP and ARIES, in line with DFID smart rules. The programme achieved excellent financial management ensuring no significant payment forecast variance during the review period. The overall programme budget management performance in terms of planned budget and actual expenditure for the review period is high, 99.8 percent.
The World Bank (WB) has a well-established grant and financial management (FM) system for the GEQIP MDTF it manages. Disbursement to the GoE from the MDTF is on the bases of annual costed work and procurement plan. Other strict payment conditions are utilised including the quarterly IFR and annual audit statement. The GoE submits the quarterly IFRs ( spell out ) to WB and donors and expenditure is reviewed in accordance with the plan. The latest 2016 (2008 EFY) annual independent audit (unqualified audit opinion) and the quarterly IFRs have monitored the appropriate management & utilisation of the GEQPI II funding for the review period. Both the audit report and the IFRs found no record of fraud and noted that the programme financial management is in accordance with the FM arrangement set out in the Project Implementation Manual (PIM) and is compliant with the government public financial management (PFM) rules, national laws and regulations. There have been no reports of aid diversion or incidents of fraud and corruption during the report period except the MoE’s identifications of indications of fraud in the legal document submission immediately after the contract was awarded for the pilot e-cloud infrastructure set-up. This was proof of the government’s capacity and dedication in detecting and tackling procurement malpractices before they become a stumbling block.

The audit report further confirmed that all programme external financing had been used in accordance with the conditions of the relevant financing agreements, with due attention to economy and efficiency, and only for the purposes for which the financing was provided. An action plan has been agreed between the WB and the GoE to address the internal control weaknesses identified by the audit.

Timely disbursement of funds from MDTF to the GoE /MoFEC has been a challenge for the programme. The late annual work plan and budget approval process by the WB is one of the reasons for late disbursement which resulted in a delay in release of funds to MoFEC and school grants. This has made timely utilisation challenging and created a surplus of funding at the end of the year.

Recommendation:

For the future, the WB & MoFEC need to be more proactive and ensure the annual work plan and budget approval process is finalised before the granting year. Moreover, timely disbursement of funds to regions and schools would help to better align MDTF disbursement schedule with programme expenditure plans and to smooth programme implementation.

Payment to the QESSP component of the program is made on the basis of the milestone payment schedule agreed in the contract. A clear date for quarterly milestone deliverables agreed with the supplier and payment is effected once quarterly reports are reviewed and approved by the SRO.

Date of last narrative financial report	GEQIP II Interim Financial Report (IFR) for second Quarter ended January 09,2017 submitted to the WB on March 24/2017
Date of last audited annual statement	April 2017. .

## E: RISK
Overall risk rating: Medium

Overview of programme risk

The political unrest last year impacted on schools in some regions – in Oromiya, for example, schools were reported to have been closed for the best part of a year. A dip in the secondary examination results in 2016 was put down to this. The stakeholders consulted for this review indicated that the risk of a re-occurrence was relatively low. However, the impact of drought and disease internally and conflict in neighbouring countries, which is happening more regularly, requires a crisis response plan and resources to handle both internally displaced people and refugees. This should be embedded more in the Ministry of Education sector plans and within the next phase of GEQIP to reduce the need for parallel emergency responses.

Timely procurement of ICT infrastructure and additional textbooks are major risks as the project enters its final 18 months of implementation. While QESSP has provided some support for procurement this may not be sufficient. There should be a thorough discussion and follow up with partners on the progress of the ICT infrastructure procurement. The government has demonstrated its capability of detecting areas with high potential for fraud, hence the risk of procurement related fraud remains very low.

There is also a risk that the comprehensive evaluation will not be carried out in time to deliver any lesson learning either for programme implementation or for the design of DFID’s next programme. This will need to be carefully managed and lessons learnt from other researches and studies need to be integrated into the planning of the next phase of the nation-wide quality improvement programme.

So far, the tremendous oversight and engagement of community on the usage of school grants has reduced the potential risk of their misuse. Beneficiary feedback strategies on school grants and other relevant components of the programme will be applied to further foster grassroots’ ownership and checks and balances practices on expenditure. The risk on procurement also remains low as the government has demonstrated its commitment by detecting areas with high potential for fraud. However an independent review of procurement systems in the Ministry, for example by DFID’s Ethiopia Portfolio Assurance Programme (EPAP), would provide further assurance.
Outstanding actions from risk assessment
The risks of the ICT, textbook and evaluation components have all been raised to high.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
Both GEQIP and QESSP have a predetermined project start and end dates. One of the major components of the project, E-cloud procurement is delayed for valid reasons. Efforts have been made to accelerate the procurement process and ensure the delivery of the relevant output within the project span of time.
Performance of partnership (s)
Overall the performance of partnerships appears to be satisfactory. The GoE through the MoFEC and MoE have maintained their political commitment to improving quality of education through GEQIP. The Planning and Resource Mobilisation Directorate continues to lead on the coordination of the programme and managed to act on several of processes. Progress on identifying additional staff for capacity building in financial management and procurement has also been made.

Contributions by financing partners have been good. All partners have maintained their commitments. UNICEF has also joined the partnership with £1million.

Formal partnerships and contacts have been maintained through the QESSP II Steering Committee, chaired by the Minister. Financing from QESSP has been utilised to undertake a scoping study and develop implementation plans for a new initiative “a delivery approach” as a means of reform and accelerated delivery for the Ethiopian Education System.
Asset monitoring and control
All GEQIP II assets are governed by the Ethiopia’s public finical management systems. The QESSP II Fund manager has a well-organised assets register system. All assets from the project so far have been captured by the assets register system and DFID conducts asset spot checks and annual asset inspections and review documents related to the assets. The spot check focuses on the system, procedures and practices of handling assets procured through DFID funding. Accordingly, the monitoring for the review period was conducted on the contracted organisation, i.e. the British Council that executes the Education Program together with the Government of Ethiopia (GoE). Most of the assets were purchased for the project office in order to execute its functions. It has already been noted in the prior monitoring visits that the British Council has good practice in registering and monitoring of the assets. On this particular monitoring exercise, DFID ensured that the assets that were purchased for the downstream partners have been handled properly.
Procurement Management

The programme successfully completed major procurements of textbook, motorcycles, IT equipment and vehicles worth about USD $37.4million. However, delays have been noted. The 2016 joint monitoring mission report and Procurement Management Assessment rated the project’s procurement performance as moderately satisfactory. The mission report has also noted that since July 2016 a total of USD $25 million savings were generated from the procurement and delivery of text books.

The main challenges for the programme’s effective and efficient procurement management have been the lack of experienced procurement and contract administration staff, and delays in procurement and contract implementation processes. In view of the large volume of procurement managed, there is a need to enhance procurement and contract management capacity. The QESSP component is providing capacity building support to the FMoE by providing short-term procurement consultants. These additional staff are helping to ensure the required textbooks are procured on time and delivered to schools where they are critically needed.

A clear plan of action to address the main challenges in procurement, including delays in textbook procurement and distribution, has been agreed. Other robust control and scrutiny mechanisms include; the ‘no objection’ or bid document review and approval requirement from the World Bank (WB) for the different procurement thresholds; annual procurement plan reviews and approval by the WB; an independent procurement audit; and the strict requirement for all procurements by the FMoE to follow the WB procurement procedure and the programme procurement management manual. The identification of fraud in the IT procurement demonstrates the systems are working.

G: CONDITIONALITY

Update on partnership principles (if relevant)

DFID has judged that the provision of DFID’s funding to this programme should be dependent to the Partnership Principles. The partnership assessment undertaken in May 2016 reveals the Government of Ethiopia remains committed to the partnership principles and makes it eligible to receive sector financial aid. However, there exists a concern particularly in relation to some civil and political rights.

To inform the disbursement in December 2016, DFID Ethiopia conducted a Programme Level PPA. The Programme Level PPA judged it remains appropriate to continue to use aligned financial aid in Ethiopia’s education sector to deliver results for poor people. The Government has shown strong commitment to improving education services and there was sufficient evidence of their commitment to the partnership principles to allow DFID’s disbursement to the Multi Donor Trust Fund.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme has generated limited robust independent evidence on its effectiveness. As noted above, a planned comprehensive evaluation is only now being contracted so there is as yet no baseline data to inform partners about the impact of the programme at classroom level. It will be important for the comprehensive evaluation to be contracted and learn lessons for the successor to GEQIP II which could also inform the design of DFID’s next business case for the programme succeeding GEQIP II . One of the lessons to consider for future programme design is whether key evaluations should be independently contracted.
Two other evaluations are planned for this year. One will examine the distribution and utilisation of textbooks, and the other will re-evaluate the impact of school improvement planning and school grants. The first of these will be crucial in generating data about the extent to which textbooks are being used in schools to improve teaching and learning, and to identify bottlenecks in distribution.
An evaluation of school improvement planning and school grant management was produced in June 2016. This was helpful in identifying progress and bottlenecks. It was unclear to what extent findings had been taken up by the project.
The scoping mission contracted for end of last year to look at possible areas for a new business case, also provide some useful triangulation on the achievements and challenges of GEQIP 2.

Action : Consider action to influence implementation strategy of future programmes.

Monitoring progress throughout the review period
A Mid Term Review was conducted by the World Bank in July 2016 and all project components were reviewed and recommendations made to government and partners. A number of these related to restructuring the results framework as it was reported that there was a lack of clarity on indicators and a lack of effective monitoring mechanisms, especially at classroom level. The review team did not see the progress report produced by the MoE for the mid-term review.
Action : Translate recommendations from the JISR to actions and follow up in the quarterly steering committee and monthly ETWG meetings.
DFID took part in a Joint Implementation Support mission in February 2017. The mission reported modest progress against the PDO indicators. The mission visited SNNPR, Tigray and Afar. DFID staff reported that the Joint Implementation missions need to be more strategic with bottlenecks to progress picked up in regular meetings.
GEQIP partners interviewed indicated that there was no regular platform for dialogue with government and the World Bank on GEQIP II implementation. One of the recommendations of this AR is to institute quarterly meetings to discuss progress.
The late publication of the Annual Abstract continues to hamper policy making as does the fact that information on learning achievement is only available every four years.