Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: The Malawi Family Planning Programme
Programme Value: £25.2m		Review Date: 25 Feb 2015
Programme Code: 202656	Start Date:14 Dec 2011	End Date: 30 March 2018

Summary of Programme Performance
Year	2013	2014
Programme Score	A+	A
Risk Rating	L/M	M/H

Summary of progress and lessons learnt since last review

This annual review (AR) of the Malawi Family Planning Programme (MFPP) covers the period January to December 2014

The AR has assessed the MFPP performance for this period as A. However, this score obscures some issues with the programme which need addressing rapidly.

2014 has been a challenging year for the MFPP as budget reprogramming following a reduced overall DFID Malawi budget meant the main delivery partner, BLM, experienced a cut in its budget for 2014 from £3.2m. to £2.28m. The budget for 2015 was concomitantly increased. BLM warned that there will be unrecoverable results losses because of the pattern of re-programming. BLM exceeded their revised milestones for 2014 and their delivery model appears to be a sound one.

Despite this achievement, this AR has highlighted significant concerns with financial management at BLM which have remained consistent across time and reporting mechanisms which are generally weak despite some observed improvements in the last half of 2014. Consequently, senior management oversight should be strengthened as recommended in the 2014 DDA..

Summary of recommendations for 2015

Strategic
- DFID Malawi should review detailed evidence and data from BLM and assess the pattern of delivery to target groups. While there is evidence to demonstrate that BLM are hitting milestones the data is not disaggregated sufficiently to assess whether hard to reach groups are able to access the organisation’s services or whether anecdotal evidence about compromised reach is justified (hence apparent contradictions in information). Should the evidence show that insufficient young people and rural inhabitants are being reached, BLM should suggest remedial approaches.
- DFID should continue leading the organisation of meetings between stakeholders to discuss alignment of activities to ensure that beneficiaries get the best service across the country. From 2012, DFID had a leading role in prepeartion for the2012 Family Planning summit. From 2014 DFID brought together partners funding BLM to discuss alignment of support to BLM. DFID should be more proactive in the RH TWG where partners in the family planning SRH sector hold wider discussions that may yield greater benefits.
- DFID should provide early information about budget reprogramming wherever possible. DFID should ask BLM for more information about the impact of budget reprogramming on results, bearing in mind that the reported results often exceed the revised targets. BLM have indicated that the figures in 2014 are partly a ‘function of programming’ and that they expect the upward trend in CYP results to fall back to approximately 10% a year. However, further information would be appropriate to ensure that DFID fully understands its investment.

Programme and management
- The impact of the DSA should continue to be monitored by DFID particularly as it may affect training provision by BLM.
- BLM should be encouraged in further efforts to reach the hard-to-reach. DFID should also consider embedding information from BLM’s work with girls aged 10-14 years in order to increase understanding of provision of services to the young.
- DFID should ensure that appropriate links are made with other DFID programmes especially where programme efficiency is concerned (e.g. MSHP/CSMT; Keeping Girls in School). Connections between programmes can also yield improved VfM for DFID.
- BLM should be encouraged to share the results of their cost per CYP exercise, the results of which are due in the first quarter of 2015.
- The log frame should be reviewed and separate recommendations can be found within this report. These recommendations include a review of milestones which may, in some cases, have been set at too low a level.

VfM and financial performance recommendations
- BLM’s financial management capacity is a matter of concern – high level meetings should take place between DFID, BLM and MSI. This is important on a number of levels but not least because of the level of BLM’s dependency on DFID. BLM’s pilot sustainability plans are to be welcomed in this context.
- BLM’s exit plan for the VSP has not been submitted as arranged – DFID should follow this up promptly.
- BLM should be encouraged to disclose further information about: a. the way in which money from clinic services is transferred to reserves and subsequently used; and, b. exchange rate gains and losses. Impacts of the GBP/MKW exchange rate should be monitored as these have implications for the cost per CYPs reported by BLM.
- DFID should confirm that the sub-contraction of delivery services by IHS to Cargo Management Logistics is as originally planned when IHS were contracted.
- Lessons from the discontinuation of the voucher programme should be disseminated across the office, to other voucher-based programmes in DFID, and to MSI.
- DFID and partners should enhance their understanding of costs and cost drivers as this will improve VfM practices. DFID VFM training slides could be shared with BLM and DFID’s economists could consider offering a workshop for BLM. A workshop should ensure that the relevant people from BLM can all attend.

Communications and Engagement
DFID should conduct a programme delivery workshop to include UNFPA and BLM, and possibly UNICEF. Both BLM and UNFPA should improve their reporting standards.
- DFID to continue providing formal feedback to partner organisations after an annual review, in writing and face to face, detailing assessment of progress, quality of reporting, issues for resolution and recommendations. This could link into DFID’s plan for a common approach to partner reporting.
- DFID Head of Office to meet the new head of UNFPA to raise DFID’s expectation in relation to standards of reporting expected from UNFPA

Research and evidence
DFID should ensure the research funding component in the programme is utilised to support FP research There is an opportunity to support key research projects with BLM and these should be explored. It is important that this programme is situated within a broad understanding of family planning and fertility in the sector.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Section A: Introduction and context

Outline of the programme

The Malawi Family Planning Programme (MFPP) aims to increase the coverage and use of effective family planning (FP) in Malawi over five years (2011-2016), particularly among the rural population, the poorest and young women. The programme was set up in response to the levels of poverty experienced in Malawi, and health related challenges to development which impacted on Malawi’s predicted failure to meet three of the MDGs. In addition to which, family planning services were poor in a context of high maternal mortality, high total fertility and high abortion rates.

The total budget for the programme is £25.2 million. Some £19 million is used for FP service delivery through Banja La Mtsogolo (BLM) – a non-profit provider of sexual and reproductive health care services in Malawi. A further £6 million was provided to the United Nations Population Fund (UNFPA) to procure contractive commodities on behalf of the Government of Malawi (GoM) for use by BLM in their service delivery work. £200,000 was set aside for monitoring and evaluation and there are plans to use this for research in 2015 if DFID Malawi confirms its decision not to evaluate this programme.

At impact level it is expected that the MFPP will contribute to reducing maternal mortality, the total fertility rate and the HIV prevalence rate. This would further contribute to Malawi’s progress towards achieving MDG 5 (Improvement of maternal health), and MDG 6 (combat HIV/AIDS, malaria and other diseases). However, the focus of this programme is reproductive health as other programmes addressing these diseases.

The planned outcome is the increased use of effective family planning methods, especially by the young, the rural population and the poorest. The outcome is supported by five outputs; use of family planning; FP awareness, knowledge and access; strengthened policy, planning and implementation; improved cost effectiveness; and, effective procurement and provision of commodities. The first four outputs focus on delivery by BLM and the fifth measures the work of UNFPA.

Originally the MFPP was expected to enable an additional:
- 3.6 million Couple Years of Protection (CYPs)[1]
  [1] CYP is an estimated measure of protection from pregnancy by contraceptive methods in a one-year period. Different methods of contraception provide different measures of CYP (see https://mariestopes.org)
- 1.27 million fewer pregnancies
- 180,000 fewer abortions (mostly unsafe)
- 4,460 fewer maternal deaths; and
- Save 888,000 Disability Adjusted Life Years (DALYs)

However, following re-programming in 2014 the results were revised to enable an additional:
- 3.47 million CYPs;
- 1.23 million fewer pregnancies;
- 180,000 fewer abortions (most unsafe); and
- 4,500 fewer maternal deaths; and save 889,000 DALYs.
Some results remained at their original level as it is expected that ground lost in 2014 will be made up in 2015 with the reprogramming of monies into 2015.

The total results can be broken down to those attributable to the BLM component and those attributable to the UNFPA component:

BLM Component	UNFPA component
2,831,270 CYPs	646,000 CYPs
1,000,000 fewer pregnancies	229,000 fewer pregnancies
148,000 fewer abortions	32,000 fewer abortions
3,700 fewer maternal deaths	800 fewer maternal deaths
729,000 DALYs saved	160,000 DALYs saved

Running parallel to this work, and reported in the same log frame as the MFPP, is another FP programme (Programme of Work II)and also implemented by BLM which is due to close in 2015. This annual review does not cover this second programme.

The MFPP was previously reviewed in 2013 and scored an A+.

BLM operating model
BLM has been providing sexual and reproductive health services in Malawi since 1987 and has is a partner in the Marie Stopes International Global Partnership. The organisation has 31 centres across Malawi which offer services to women, men and adolescents. These centres are supplemented by clinical outreach team which work in 460 further areas across Malawi. There are three approaches to outreach:
- An extension service to rural Ministry of Health centres which do not normally have the staff or equipment.
- A mobile initiative using tents (Tent Outreach Clinic Initiative or TOCI).
- Use of other structures such as a school or health post (Community Outreach Clinic Initiative or COCI).

The outreach model is important as it enables BLM to provide services to the hardest-to-reach. There are challenges to providing a mobile service and these include seasonality-based uptake associated with agricultural cycles; road and vehicle conditions; and the weather.

BLM established the Blue Star social franchising network in 2008 which aims to provide training for the private sector. Additionally, there are other providers of family planning services in Malawi including the Ministry of Health, PSI, and private providers.

Issues in 2014/15 affecting the programme

2014/15 budget revisions
In 2014, DFID advised BLM of revisions to the budget for the MFPP. The 2014/15 budget was reduced by £1mn, from £3.2 million to, £2.0 million; the budget for 2015/16 was increased from £3.8 million to £4.8 million. BLM reported that delays by DFID in confirming the revisions impacted on results. A new log frame adjusted for the new budget was submitted by BLM in September 2014 and agreed by DFID. It is this log frame that is being used for this annual review.

Daily Subsistence Allowance
The GoM is currently resisting donors requirements that government staff are no longer provided with a DSA for training etc. This has led to the cancellation of training and events and may further impact on implementation in 2015 as BLM have targets for working with government staff.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
There are five measures at outcome level; outcome indicator 1, the contraceptive prevalence rate (CPR), was measured at baseline in 2010 and is not due to be measured until 2015.

Indicators two to four measure: unintended pregnancies averted; unsafe abortions averted; and, maternal deaths averted. The fifth and final Indicator measures the number of additional women using modern methods of family planning through DFID support (disaggregated by age: 15-19; 20+) Figures are presented below.

Indicator(s)	Milestones	Progress
2. Unintended pregnancies averted	Pregnancies averted: 186,223	Pregnancies averted: 481,819
3. Unsafe abortions averted	Abortions averted: 26,543	Abortions averted: 86,837
4. Maternal deaths averted	Deaths averted: 604	Deaths averted: 1,338
5. Number of additional women using modern methods of family planning through DFID support (disaggregated by age: 15-19*; 20+)	(15-19): 7,631 / (20+): 101,382	(15-19): 9,021 / (20+): 99,712

* BLM also provide services for 10-14 year olds

Milestones were altered following re-programming but in some cases e.g. outcome indicator 1 the original target would have also been exceeded. These figures point to a programme on track at the outcome level. Further information about achievements at this level despite budget reprogramming would be helpful and BLM should be asked to supply this information.

BLM has long term structures in place underpinning a strong and visible delivery profile which, through its three models of clinics, outreach and franchise, gives BLM a sound framework for operations and the potential for growth. BLM’s relationship with MSI means staff have access to good and improving data systems which generate reliable estimates of use.

However, significant challenges remain and these are discussed throughout the body of the report at output level. These include reaching the hardest-to-reach, inter-agency relationships and financial management. Concerns about reaching the young, the poor and the rural were voiced throughout meetings and unless significant efforts are made to enable these populations to access services there may be equity issues in the future. Additionally, there may be opportunities to link up with other cognate DFID programmes such as ‘Keeping Girls in School’ which also target the key populations in the MFPP.

Overall Output score and description

The AR has assessed the MFPP performance for this period as A. However, this score obscures some real issues with the programme which need addressing.

This annual review notes the following:
- Strong performance of the programme against output 1 (A+) – use of services. This reflects the key strength of BLM, the delivery partner on the ground.
- The lower score for output 2 (B) which measures access, awareness and knowledge of family planning and sexual and reproductive health services. This is the result of the closure of the VSP
- Good performance against output 3 in terms of policy planning and implementation. However, this is a weakly constructed output.
- The rating of ‘A’ for output 4, (strengthened programme cost-effectiveness, quality and accountability) driven by cost per CYP. However, this score is challenged by financial management issues discussed in this report and vulnerabilities in the GBP/MKW exchange rate.
- The score of ‘A’ for output 5 which measures commodity security. However, this is also a weakly constructed output, and measures only national level activities. Additionally, UNFPA have not been forthcoming with information and therefore, some assumptions have had to be made.

Key actions and lessons
DFID Malawi needs to be as clear as possible as early as possible with partners about budget re-programming. It is accepted that organisational-wide allocation round reviews can represent problems as part of the budget directive is beyond the control of the DFID Malawi office.

Communications and Engagement
- Ensure that meeting between DFID, BLM and PSI goes ahead to discuss coverage, and therefore efficiency, of FP services across Malawi.
- DFID to continue to push for regular communications, and quality reporting with UNFPA.
- DFID to follow with BLM on the usage of DFID branding on BLM website.

Financial management
- This report has highlighted issues with BLM’s financial management capacity. This is a matter of concern. DFID should take this at the highest level with MSI
- DFID should investigate sub-contraction of delivery services by IHS to Cargo Management Logistics, checking that this was part of the original arrangement.

M&E and research
- The annual review finds that it was an appropriate decision not to evaluate this programme. However, there are areas where research would be extremely useful and DFID/BLM should discuss how research monies can be most appropriately used.
- DFID could support research into an expanded understanding of fertility decline, value for money and other issues e.g. unmet need for family planning as part of the holistic understanding of trends in fertility in Malawi. The PEAKS facility could be used to evaluate whether this would be a good use of DFID monies.
- DFID Malawi should explore the potential to link up with other DFID programmes such as ‘Keeping Girls in Schools’. Such programmes are strongly aligned and have the potential to strengthen each other.

UNFPA and BLM reporting
- Reporting by BLM and UNFPA is still weak.
  - BLM should improve reporting especially in terms of narrative in order to demonstrate that they understand the trends they are reporting on can embed lessons from delivery, communications and learning. This will make them not just a more effective organisation but a more effective partner for DFID. This message has already been conveyed to BLM by the adviser for this AR.
  - UNFPA should improve reporting to ensure that, but not confined to:
    - Appropriate data is included along with data analysis e.g. on stock availability. Without such information the work of UNFPA is difficult to assess.
    - Narrative reporting is useful and clear
    - Technical information is correct - for example, data/labelling errors do not occur. The six monthly reports contained two errors: the contraceptive prevalence rate from the MDG Endline survey report was cited as 57.4% rather than the 58.6% recorded in the MDG report; and, the CYP per unit of Depo provera was reported as 4, rather than 0.25; or 1 CYP per 4 units)
  - DFID should provide UNFPA and other partners with the DFID reporting template accompanied by guidance for completion, and consider feedback in writing and in person.

Log frame
The log frame has been updated since the last annual review. Milestones in the log frame were altered in response to the budget re-programming which was a marked feature of the MFPP in 2014.

The MFPP log frame has been used as a key source of evidence for this AR (Annual Review). The adviser for this AR has also conducted a review of the log frame. This review concluded that while the underpinning logic of the log frame was sound there were weaknesses which meant that the utility of the log frame was compromised. Consequently the following alterations are recommended:

- Changes to the log frame to ensure completeness which include; cumulative/annual notation added in as appropriate against indicators; targets should be clearly identified as well as sources- with triangulation wherever possible; and, assumptions could be improved.
- A change to the construction of Indicator 3.1 is also recommended – currently this is a compound and confusing statement. Dissemination should be separated out from policy influencing and the level and nature of policy influencing should be established in advance of measurement.
- An alternative indicator may be considered to replace that for the VSP in output 2.
- DFID should review the structure of Output 4.
- Indicators 5.1 and 5.2 should be reviewed as these duplicate information.
- An additional measure should be considered for output 5 that will enable sub-national commodity stock availability to be monitored. It is accepted that this does not directly come under the control of UNFPA but it is important that the programme does have oversight of the work of CMST and an indicator in this output could be an appropriate compromise. Oversight of CMST is needed and engagement at a high level around commodity supply has been picked up in annual reviews (MHSP, Oct/Nov 2014)
- Weightings and risk levels should be reviewed. As should milestones for 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective FP and other reproductive and sexual health services used, especially by the young, the rural population and the poorest.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Couple Years of Protection (CYP) disaggregated by young (under 25) and rural (number and proportion).	MFPP Total: 242,250 / MFPP Young: 35,700 / MFPP Rural: 169,575	MFPP Total: 300,344 / MFPP Young: 75,052 / MFPP Rural: 225,292 / Achieved A++
1.2 Proportion of CYPs delivered by LAPM	MFPP: At least 80%	MFPP: 95% / Achieved A+
1.3 Client visits by service type	MFPP FP: 109,013 / MFPP other non-family planning services: 0	MFPP FP: 125,463 / MFPP other: 40,580 / Achieved A+

Key Points
This output assesses the degree to which clients are accessing BLM’s services, the nature of the client and the extent to which uptake of LAPM is occurring.

It is to be noted that:
1. These figures have been achieved despite the budget reprogramming; and
2. Concerns have been highlighted in discussions with stakeholders that the rural population and young people are not being reached. These figures do appear to contradict verbal information but the figures for the young may be biased towards an urban population, and the figures for rural biased towards older women. As a result, this AR recommends that BLM provide more detailed information about its reach.
3. This is the second year that BLM have exceeded the milestones in their log frame and DFID Malawi should re-examine the milestones for future years in the light of BLM’s performance.

Some 95% of CYPs delivered by BLM in 2014 were by LAPM. Expanding access to LAPM is aligned with national policy direction. BLM are sensitive to balancing this policy direction with providing choice to women: ensuring women are equally counselled for short-term, long-acting and permanent methods. Outreach service provision is geared towards making LAPM more available in areas where other facilities e.g. government and CHAM do not offer this service.

BLM suggest that 2014 may indicate a change in trends away from shorter-term methods to LAPM. For the organisation, 2014 was not ‘business as normal’ as staff expanded newer approaches such as more free days, more engagement with young people and new relationships, such as those with the National Youth Council and AirTel. The introduction and greater uptake of vasectomies (MSV) is also thought to be promising.

Overall this output is scored at an A+

Summary of responses to issues raised in previous annual reviews
The 2013 annual report raised the issue of preferential use of short acting methods (e.g. Depo-Provera) by women in northern areas over LAPM. The same has been observed in the other two regions. While it is clear that BLM are exceeding their target with respect to LAPM, a clinic visit to peri-urban area in Lilongwe showed that there were women in this particular clinic who preferred methods such as Depo Provera. BLM confirmed that women in rural areas were also in favour of using short acting methods. It also seems that it is older women who prefer LAPM, following the birth of what they would like to be their last child. There is unlikely to be significant shift in a year but the figures demonstrate the need for continued promotion and sensitisation along with understanding of why women continue to use short acting methods. BLM should report disaggregation in greater depth in their reports so, for example, patterns of usage of LAPM can be identified for the target groups. This is important as early work is likely to have targeted the easier to reach and such information will inform delivery patterns. It will also enable DFID to assess progress in a more comprehensive way. The roll out of the CLIC information system should enable such analysis.

Recommendations
1. BLM to continue promotion/sensitisation for LAPM should take place – but this should also be continued to be balanced with respect for women’s choices.
2. BLM should be encouraged in their work with MSV.
3. The log frame targets should be reviewed.
4. Further analysis of data will provide insight into the more significant patterns of progress – this should be reported by BLM in their bi-annual reports.

Output Title	Access, awareness and knowledge of FP and SRH services at the individual, household and community levels.
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 15-24 year olds are aware of at least three modern methods of family planning	Not applicable	A mid-term KAP survey is planned for 2015. No milestone set for 2014 Achieved: N/A
2.2 Number of voucher clients who access services through the voucher programme	12,000	7, 472 (62%) / Achieved: C
2.3 Number of BLM supported service delivery sites (BLM centres, outreach sites and Blue Star Clinics)	75	82 (109%) / Achieved: A

Key Points
While there was no KAP study planned for 2014, BLM should be encouraged to make timely preparations for the KAP study in 2015 as this will be a key piece of information about the potential long-term gains for this programme

7,472 clients accessed LARC in 2014 through the pilot voucher programme, running in BLM’s BlueStar social franchises. This is the first year that BLM reported against this indicator since taking on the programme.

A DDA in 2014 identified a potential for abuse of the voucher scheme programme (VSP) as the selection criteria of beneficiaries was unclear. While the voucher scheme was thought to be a good initiative, DFID recommended further monitoring to ensure that the beneficiary identification process was strengthened. DFID’s work was followed by a visit from MSI (BLM’s principal partner) in October 2014 The VSP was suspended to allow for a comprehensive Quality and Technical Audit of the programme. Recommendations included only permitting clinics assessed as ‘high quality’ to deliver the VSP; reviewing the criteria for the selection of providers; checking whether mobilisers were undertaking sufficient work to create demand and investing the potential use of a Behaviour Change Communications (BCC) strategy; review of the geography of provision; and a greater emphasis on targeting men.

The VSP was suspended in November 2014 and discontinued permanently in January 2015. An IAD by DFID in 2014/15 found the ‘framework of governance, risk management and control provides very limited to nil assurance over the achievement of objectives. Risks to objectives are severe (combined impact and likelihood).’ An exit plan from BLM was expected by February 13th 2015 that would also offer alternative arrangements that allow poor women in peri-urban areas, who were the target beneficiaries of the voucher scheme, to still able to access FP methods. The plan will also ensure that clients of the voucher scheme who had the FP long acting methods inserted have them removed free of charge, as per the scheme commitment.

The establishment of 82 service delivery sites associated with BLM is to be welcomed. BLM suggest that the success was due to their work with the MoH and their district counterparts to map additional outreach sites within various districts and deployed dedicated outreach and clinic outreach teams per these revised requirements. However, there are issues that may affect expansion in the future. The most pressing of these is the relationship between BLM and PSI (aligned with IPPF). PSI is funded through USAID and KfW and is essentially working in the same space as BLM, competing for the same clients. A franchise split has been agreed but this does not include directly supported clinics. Some discussions have taken place to promote schedule sharing and highlight the potential for beneficiary confusion.

Overall, this output is scored as a B

Summary of response to programme issues raised in previous annual reviews
Not applicable

Recommendations
1. DFID should follow up issues from the discontinuation of the VSP promptly.
2. BLM should make adequate early preparations for the KAP study in 2015.
3. Substantive discussions should take place as early as possible among BLM, related service providers and donors in family planning to ensure that services complement and do not duplicate each other. This will also help to allay any beneficiary confusion.
4. DFID and BLM should ensure that learning from the discontinuation of the voucher scheme is embedded across the sector.
5. DFID and BLM to consider an alternative indicator to support this output to replace that for the VSP.

Output Title	Strengthened national proficiency in SRH policy, planning and implementation
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator (s)	Milestones	Progress
3.1 Evidence of influencing policy and dissemination of impact and learning	1	2 / Achieved: A
3.2 Number of health workers trained by BLM (includes public, private and BLM providers).	220	301 (137%) / Achieved: A++
3.3 Number of public sector and CHAM sites receiving supportive supervision/ mentoring from BLM	Not applicable	Not applicable – measurement begins 2016

Key points
Output 3.1: BLM coordinated Malawi’s World Vasectomy Day in November 2014. Supporting discussion about, and uptake of, this FP method is a key strategy for BLM. BLM is working with the MoH on resourcing future training and mentoring of vasectomy providers. BLM believe that they are the only organisation working in this space in Malawi.

Two BLM presented at the International AIDS Conference in Australia in July 2014 on lessons learned in improving male involvement in SRH service demand and uptake. BLM have reported verbally, but not formally on their work in supporting access to emergency contraception by outreach workers as well.

BLM report that they participated in the following technical working groups (TWGs) at national level during the period under review: Sexual and Reproductive Health TWG, Safe Motherhood subgroup, FP subgroup, Reproductive Health Commodity Security Subgroup, HIV Prevention TWG; and, Monitoring, Evaluation and Information systems TWG. BLM also reports that it contributes information from the field, relays stock-out information, operational challenges and offers assistance to the MoH with issues raised during TWGs, such as transport/storage of commodities, staff training, and crisis response. BLM also pilots activities on behalf of MoH, such as new FP innovations (in 2014 BLM piloted communications materials and a new follow-up approach to increasing uptake of post-partum IUDs, the results of these pilots will inform MoH policy decisions). No change is reported from last year’s activities.

The information above indicates that BLM are working in more areas than formally reported on, following the recommendations below may mean that, subject to clarification, BLM score more highly in future reviews.

Output 3.2: This indicator is rated at an A+. It should be noted that progress against this indicator may be subject to challenges in 2015 as the impact of the training moratorium for government staff continues.

Overall this output is scored as an A+. Expectations were exceeded in terms of training and there is further evidence that BLM may be exceeding targets set for dissemination and influencing.

Summary of responses to issues raised in previous annual reviews
Issues raised in the 2014 annual review include:
- BLM did not meet the target for indicator 3.1 in 2013 but have met it for 2014. This is a challenging indicator because policy shift is difficult.
- Evidence of influencing and dissemination. This still needs to be improved but an enhanced methodology should help with this issue.
- Retention of staff skills. BLM report abandoning some training events in 2014 as MoH and CHAM staff resisted the Harmonized Donor DSA policy (Nov 2013). BLM has met repeatedly in 2014 with donors, INGO Forum partners, DFID Malawi, as well as meeting with RHD and CHAM leaderships to try to secure support for the BLM’s scheduled trainings. No firm commitments have been made by MOH/RHD or CHAM. The MFPP is weighted heavily in the final years of implementation towards the provision of training (2016-2018); BLM has suspended all external training until the issue can be resolved at senior GoM/DFID levels. In 2014, BLM trained and provided refreshers for its own staff as needed until all MFPP training was suspended post budget re-phasing.

Recommendations
1. Output indicator 3.1 is a compound indicator and measures two separate themes – a. policy influencing and b. dissemination of impact and learning. Policy influencing is difficult to measure per se and needs to be supported with a strong framework that allows objective impartial measurement of what is a judgement based indicator – what policy and who is creating the change. What counts as change – needs to be established a priori. Can be helpful to have an idea of where and the level at which change is targeted too – although opportunistic change should not be ruled out. This kind of indicator also needs triangulation from other sources. Additionally, as policy change tends to be a contributory activity rather than an attributionary activity this measure may be set too low as other organisations are likely to be working towards shared goals. Consequently, the methodology needs to be reviewed. It should also be noted that DFID is also moving towards more sophisticated measurement of knowledge uptake and this thinking should inform any changes.
2. The issue re DSA should be carefully monitored by DFID.
3. Milestones should be reviewed.

Output Title	Strengthened programme cost-effectiveness, quality and accountability
Output number per LF:		4	Output Score	B
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 No qualified audits and no major concerns raised through ‘spot checks’	None	2013 Audit was unqualified / Significant concerns raised about the voucher scheme – since discontinued / Achieved: C
4.2 VfM Studies (as per M&E Plan)	Not applicable	Not applicable
4.3 Cost per CYP	£6.79	£4.90 / Achieved: A+
4.4 Service delivery channels (outreach, BLM clinics and BlueStar providers) achieve minimum service quality standards	Centres: 90%; Outreach: 90%; / BlueStar 85%	Centres: 92% Outreach: 93% BlueStar: 80%* / Achieved: A
4.5 BLM achieves MSI-defined performance standards for programme management	Not applicable	Measured every two years. Next assessment: 2015.

* There are 31 centres, 564 outreach sites and 81 Blue Star social franchises

Key points
Indicator 4.1. While the 2013 audit was unqualified it was four months late. More seriously, the voucher scheme was discontinued (see Indicator 2) and the financial management issues identified by DFID via ‘spot checks’ continue. BLM acknowledge that there is an issue around financial management and these have further been recognised at a senior level in MSI. There is also a problem with asset management (see relevant section). For this reason, this indicator has been rated as a ‘C’. BLM is an important partner for DFID in Malawi and therefore, it is important that BLM is resolves this issue.

Indicator 4.2. Cost per CYP – this milestone was achieved although it is higher than the figure of £4.19 for 2013 when the equivalent milestone was £6.90[2]. However, BLM report that the strength of the GBP against the MWK is the largest driver of reduction in Cost/CYP as well as the cost efficiencies BLM has gained in coordinating with MoH/CMST to source commodities in country (though the public system), and retaining long-term clinical staff who, though they require skills refreshers and ongoing mentoring, do not require full in-service training. While the GBP/MWK exchange rate does mean savings this represents exposure for the project and this aspect of the budget should be monitored.
[2] Targets were originally set by DFID and input into the invitation to tender log frame with the note (“Baseline and projections made based on the current cost per CYP of Malawi's leading FP NGO (which is £7.50)”). After award, the baseline (2012 figure) was then adjusted to £6.95 based on updated information and the targets adjusted proportionally. Once BLM’s 2014 Cost Calculator results are fully analysed (circa Q2 2015), the targets may be revisited for the outer years of MFPP.

Indicator 4.4. Service delivery channels. The percentages for centres and outreach, while exceeding the target have fallen back from those of last year (94% and 96% respectively), although BlueStar clinics have improved from 78% in 2013. BLM also report that clinics have individual improvement plans in place.

Overall this output is scored as a B.

Summary of responses
1. Preparation of annual plan; BLM responded by submitting an annual plan as agreed.
2. DFIDM to work with HQ to share Malawi learning. DFIDM shared learning on the VSP and outreach service at the Health Advisers CPD in February 2015.

Recommendations
1. DFID should be pro-active in supporting BLM and MSI to address their on-going financial management issues within as short a time frame as possible.
2. The impacts of the GBP/MKW exchange rate should be monitored.
3. Log frame milestones and targets should be reviewed.

Output 5: UNFPA: Contraceptive commodity security improved for short-term methods (including injectables) for the public sector

Output Title	Contraceptive commodity security for short term methods (including injectables) for the public sector
Output number per LF:		4	Output Score	A
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators	Milestone 3 2014/15	Progress
5.1 Limited stock-outs of contraceptive pipeline supply for (DFID funded) UNFPA stock	i. At least 95% of each UNFPA commodity delivered on time* / ii. At least 20 months of stock available for each commodity	9/10 of original orders in 2014 arrived on time (Depo-Provera due in Aug 14 delayed); / No data available. UNFPA report ‘no gaps’ expected in 2015 / Achieved: B
	Two orders from use of extra monies arrived 2014, two due March 2015. These are excluded from this assessment.
5.2 Demonstration of effective procurement against forecast and commitment	i. 95% of the annual commitment for each commodity procured / ii. 95% of annual commitment for each commodity delivered*	100% procured (10 orders placed + 4 further emergency orders) / 9/10 commodity orders delivered / Achieved: A
5.3 Economy in procurement by UNFPA competitive unit costs demonstrated against other funders	At least 70% of UNFPA commodity prices are lower than international suppliers	UNFPA report using 2013 prices to procure commodities in 2014. / Achieved: A

*following clarification with UNFPA both these indicators measure delivery to CMST

Key points
This output measures the stable and forecastable availability of contraceptive commodities for the Malawian public sector.

Indicator 5.1/5.2 UNFPA procured in a timely fashion against the planned procurements for the fifth tranche of funding. Nine out of 10 of procurement orders arrived as forecast. There was one delay to a shipment which arrived in November 2014 rather than August 2014. UNFPA can only report that there are no gaps forecast for 2015 in commodity stocks, rather than for a 20 month period. The National Family Planning Stock Status Report – end of December 2014 (supplied by UNFPA) does have information on stock status which shows that there is stock of oral contraceptives for 105.5 months, other commodities such as Male Condoms, Depo-Provera and Jadelle have less than 20 months of stock each (12.1, 18.5 and 11.4 respectively). Hence, this indicator is graded as a ‘B’.

A change to indicator 5.2 means that detail at sub-national level has been lost and omission of LMIS data in UNFPA reports means that DFID cannot verify UNFPA’s statements of coverage. An analysis of LMIS data provided for December 2014 shows that over 80% of reporting districts experienced one or more stock outs at health facility level in the reporting month. While it was argued by CMST staff that low/stock out situations can be remedied within 24 hours by transporting stock between locations there are indications that supply is not stable. This is important as it is immediate availability to clients in health facilities that is a key part of this programme.

Further information at a sub-national level is available from the ‘National Survey on availability and accessibility of modern contraceptives and essential, life-saving maternal and reproductive health drugs in service delivery points in Malawi’ (Government of Malawi/UNFPA, Baseline Survey May 2014). This surveyed 164 Service Delivery Points (SDPs) in April 2014. This found that 86% of SDPs were offering contraception and most were offering at least three forms of family planning.

Stock status was assessed for the six months preceding the survey. Of those facilities that provided contraceptives, 55.3% (n=141) reported a stock out. Stock outs were more common in tertiary delivery points, which are probably rural facilities, compared with primary or secondary points. This implies that facilities which tend to serve the poorer are more likely to suffer from stock outs. Varied reasons for stock outs were cited in the report including delays from the main source of supply and non-availability of commodity on the market as well as failure to re-order by the facility itself.

While this survey applies to Malawi as a whole and not the DFID project, because of the inter-related nature of DFID’s programme with overall provision for the public sector, it does imply issues that may impact on DFID’s programme. (It should be noted that NGOs (including BLM) made up 2.4% of responding health facilities in this survey and therefore, care should be taken when applying results of the survey to BLM).

BLM itself notes that their relationship with CMST has improved since 2014, and their recognition as an approved service delivery point by CMST/MoH has been a ‘watershed’ as BLM can now pull directly from CMST across all their health facilities.

Indicator 5.3. UNFPA report that commodities procured in 2014 were done so through the LTA, and therefore, at 2013 prices. No further information was forthcoming.

Overall this output is rated as an A.

Summary of response to issues raised in previous annual reviews
The annual review in 2014 (for the reporting year 2013) contained two recommendations. The first was for proactive monitoring of commodities allied to timely provision of information by UNFPA to DFID. The second focussed on the need for UNFPA to improve reporting and communication with DFID
In 2014, UNFPA made a pre-emptive decision to procure further stocks of Depo-Provera without consultation with DFID, using a balance of £651,737 remaining from the monies disbursed to UNFPA by DFID. DFID expressed dissatisfaction with this approach at senior level. A similar event occurred in 2012 when UNFPA switched to Norestat without consultation. It is disappointing to see a further occurrence of this lack of communication.
Reporting is still not of high quality and expectations about quality should be firmly established with UNFPA. With the arrival of a new representative DFID has hopes that better communication channels can be established and DFID’s expectations reinforced.

Recommendations
- DFID to strongly express need for better communications with UNFPA and to recommend that UNFPA as a global flagship organisation should produce reports of a quality commensurate with its status which allow for clear tracking of its activities, description of progress and assessment of its contribution to the improvement of family planning provision in Malawi.
- DFID to investigate distribution of commodities at a sub-national level and check whether reporting against an indicator at national level is appropriate. It appears key to monitor sub-national trends as part of the programme management activities for this programme. As part of this review, indicators 5.1 and 5.2 should be reframed.
- The 2014 survey report has a number of recommendations. DFID should consider supporting UNFPA and the Government of Malawi to further explore the recommendations.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Section D Value for Money and Financial Performance
Key cost drivers and performance

The specific costs are personnel; outreach services including travel expenses and vehicles; training; equipment and supplies; accommodation; and family planning commodities and services.

Key cost drivers are:
Staff. For a second year, BLM report that inflation is impacting on staff costs. Two cost of living adjustments in staff salaries were made in 2014. However, a performance management system has been introduced which uses KPIs and bonuses and supplants the ‘thirteenth cheque’ model. Staff are reported, by management, to have responded well to this change. BLM employ more than 600 staff, most in the field, and their costs respond to this number

Outreach services including travel and vehicles: outreach services are expensive because of their reliance on costs such as staff, petrol (see below), and vehicle maintenance. The BLM fleet is ageing and procurement of new vehicles is behind schedule. BLM were questioned about the value for money of their outreach service versus a different model (e.g. setting up permanent clinics with local outreach). BLM felt that the current model still provided value for money because of its flexibility and ability to respond to need. The budget re-programming has meant that research designed to examine this issue did not take place as planned in 2014.

Petrol: This commodity remains expensive but the price is volatile. There were fuel price adjustments both upwards and downwards in 2014 as the price of fuel internationally decreased but as the Kwacha weakened against the dollar. Petrol reached M/K 856.70 a litre in 2014. As of February 2015 it is priced at M/K 696.30.

Buildings and associated commodities. BLM initiated a major restructure in 2014 which included plans for a move from Blantyre to Lilongwe. This will take place in March 2015. While rental costs are expensive in Lilongwe BLM’s vision is to buy a property as this will be more cost-effective in the long term. BLM are selling their building in Blantyre. The move will enable them to have closer contact with their partners. The restructuring has also included the creation of new posts e.g. an insurance and corporate liaison officer who will work with insurance companies. This will be a key post as the majority of BLM’s fee paying clients are using insurance and the relationship with the insurance companies will benefit BLM.

Family planning commodities and services. BLM undertook a review in 2012 which included comparisons of costs with other providers such as private clinics. As a result prices were increased and income has improved. Despite this income does not cover the costs of the clinics themselves. BLM aim to make the clinics sustainable with the proviso that they are benchmarking against government run clinics rather than private providers which can limit their prices. They will start the transition to sustainability with one clinic in each region in 2015. The current cost per CYP, at £4.90 (and discussed in more detail below) demonstrates continued value for money with respect to this service.

BLM has sought ways to understand and therefore, manage costs which should provide dividends in the future. Firstly, in 2014 BLM introduced a new cost calculator, rolled out through MSI. This will provide costs down to team levels once fully implemented. Research for this was conducted in 2014 and included field work and observational studies. This cost calculator is an Excel based tool which breaks down costs into services; service delivery channels, teams, staff, overheads and commodities. It also uses SUN based accounting information. The aim is to support improved efficiency, decision making and VfM. It can be combined with the MSI Impact calculator to perform cost-effectiveness analyses. BLM are experiencing problems with SUN and are waiting for support from an MSI provided adviser.

Secondly, BLM introduced CLIC to 19 of their 31 clinics during 2014. This is a MIS system for client records and set-up is supported by MSI London staff. It allows for client tracking over time, linking visits and services. A staff member interviewed in a clinic in Lilongwe expressed satisfaction with the system. CLIC allows MSI to track activity globally but at an aggregate level. Appropriate use of this tool will also allow for analysis of value for money.

VfM performance compared to the original VfM proposition in the business case
The MFPP Business Case was supported by an economic appraisal of the costs and benefits of the recommended option. The appraisal concluded that the programme represented excellent value for money. However, the appraisal notes that the intervention would no longer represent good value for money in the event of a major increase in service and commodity costs of if there were disappointing results in terms of the target groups benefitting from the services (young women, the rural population and the poorest).

Value for money through UNFPA procurement system/LTA. The current LTA was negotiated six months after the start of this programme and will expire in 2016. UNFPA rely on the LTA to demonstrate value for money procurement. It was not possible to get UNFPA to provide further information over and above the statement that they were currently procuring at 2013 prices. This experience reflects statements in the original business case which commented on UNFPA’s lack of transparency in reporting. It is noted that UNFPA has not improved in this respect.

Value for money through CMST. Issues with CMST have been noted and DFID contracted a private warehouse and distribution company (IHS) which, in principle, should have supported value for money by reducing stock-outs and distribution costs. However, IHS report sub-contracting to a further company and this should be investigated promptly by DFID, especially as this has implications for other programmes. BLM’s new ability to warehouse stocks should improve distribution and stock management, generating value for money for the programme and the organisation.

Reach to target groups. Anecdotal evidence indicates that the programme is not yet reaching the hardest to reach – the costs of reaching this group may result in an increase in overall programme costs, and costs per CYP. However, this does not mean that the programme will no longer be value for money. DFID should work with BLM to forecast costs against reach.

Duplication of work. BLM is aware of the potential for duplication of their work and has previously agreed with PSI and respective donors a geographical division to work. However, it is important that such partnership agreements are revisited and updated to ensure VfM.

CYPs. The reported costs per CYP for the year under review stand at £4.90, some 28% lower than the milestone. This is a good result for the programme. Work from the Guttmacher Institute in 2014 (using 2013 data)[3], describes, at a national level, the continuing unmet need for contraception, information and concludes that ‘the current level [in 2013] of contraceptive use already provides a net saving of $16.6 million (6.1 billion Malawi kwachas) annually to Malawi’s health system … The bottom line is that every additional US$1.00 spent on contraceptive services will save the health system US$2.20 in maternal and new-born care’. However, the exchange rate driver behind the costs per CYP is noted at output 4.
[3] ‘Benefits of Meeting the Contraceptive Needs of Malawian Women’, 2014, http://www.guttmacher.org/pubs/IB-Malawi.html

Assessment of VfM
Overall, this programme represents value for money, with the noted provisos.

Quality of financial management
Issues around the financial management regime in BLM have been noted in this annual review. It is important that these continue to be monitored closely and with MSI if appropriate. The potential for fraud and corruption in BLM was rated as high in the risk register for 2014 while the risk for mismanagement of the voucher scheme was rated as medium.

Audited financial statements from BLM were reviewed by DFID in October 2014. It was noted that financial statements were not qualified; and, that accounts were only signed in July 2014, four months after the statutory deadline. Issues identified in the audited accounts included asset management (discussed elsewhere) and the accumulation of outstanding debts from 2012 which were not recovered as recommended during 2013. The auditor described as these issues as ‘control weaknesses’ in their covering letter.

Recommendation – that there is better understanding of costs and cost-drivers in this programme by the key partners. Currently BLM are demonstrating confusion between costs and cost-drivers which may impact on their ability to achieve value for money from the DFID sponsored programme.

DDA
A Due Diligence Assessment (Level 1) was undertaken on BLM during 2014, together with the Royal Norwegian Embassy. The DDA observed: a gap with respect to the key position of internal auditor; weak reporting of results and finances, although it assessed the financial systems as appropriate to need.
.

Date of last narrative financial report	February 2015 – for Q4, 2014
Date of last audited annual statement	2013 Audit: signed off 31st July 2013 by BLM

E: RISK (½ page)

Overall risk rating: Low/Medium/High

The original risk was Low/Medium. This AR suggests moving this to Medium/High

Overview of programme risk

The nature of the risk for the MFPP has shifted since the last annual review when the risk was rated at ‘Low/Medium’[4]. This AR suggests that the risk level should be increased to Medium/High.
[4] It should be noted that the risk register was derived from a risk register produced by BLM.

There are regular reviews of risk strategy documents at both BLM and DFID Malawi. DFID last reviewed the risk register in 2014 and of the twelve items listed, one was rated as Green/Green; five as Amber/Amber; three as Amber/Red or Red/Amber; and, three as Red/Red, Of the three items rated Red/Red, that for two (weak communications by UNFPA impacting on strategic decision, and the impact of budget revisions by DFID in 2014) were thought to be reducing in significance and a third (fraud and corruption) remained at the same level. This AR thinks that this pattern should be adjusted slightly and the risk direction for UNFPA communications rated as static rather than declining.

However, risk of voucher mismanagement was rated as Amber/Amber following the DFID walk through but was subsequently closed.

DFID Malawi should consider reviewing the risk level for the following reasons
1. Poor confidence in the level of financial management at BLM. This risk prompts the ‘high’ rating.
2. The need to increase work in targeting the poorest, the rural population and young women. This risk prompts the ‘medium’ rating as it has implications for the achievement of equity and social inclusion objectives.

UNFPA’s ability to deliver remains at a low/medium rating as this work is fully concentrated at procurement. UNFPA’s conceptualisation of the organisation as one focused on procurement for the Malawian Health sector is a narrow one which excludes the potential for greater co-operative work with donors and a reduced impact across the country. The work by DFID and BLM to improve distribution mechanisms is welcomed but may need greater oversight.

Outstanding actions from risk assessment

The risk register should be revised and used more proactively to monitor risks. The risk register contains descriptive information about the risks but does not support appropriate mitigation activities – as a result it should be subject to an overhaul.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Overall, the delivery of the MFPP is on track. BLM have a strong delivery structure and have delivered good results even in a year where their funding was cut significantly for that year. Expected results were reduced in the log frame as a result of the budget re-programming and BLM frequently exceeded these revised targets. However, this AR has identified significant contextual concerns. BLM note that ‘cashgate’ has prompted a review of the nature of their funding base and they are looking at expanding the diversity of their funding.

Performance of partnership (s)

DFID has the following two key partners in the MFPP; BLM and UNFPA. BLM was, as discussed, subject to budget reprogramming which created concern within BLM. UNFPA were not affected by the re-programming and have delivered to the letter, if not the spirit, of their aspect of this project. BLM report that their relationship with CSMT improved during 2014. DFID should continue to work on relationships with both key partners.

Asset monitoring and control

DFID has concerns about BLM’s asset monitoring approach. A backlog of asset issues has developed with implications for assessments of depreciation. There is also an issue with the systems BLM use. This was picked up in the audit for 2013. The organisation is currently tendering out for technical assistance.

There has been a delay in the procurement of vehicles for BLM associated with this project. These delays have their origin in DFID Malawi’s need, subsequent to the original design for the MFPP, to tender for the Reproductive Health Framework. As the procurement of vehicles fell within the framework the process fell behind the original timeline. Further, DFID needed to procure within the Department’s own procurement guidelines, rather than through MSI as requested. The sub-contractor was also subject to delays prompted by vehicle availability. The vehicles arrived in Malawi in January 2015 and are currently being processed.

During budget reallocations in 2014, as part of the mitigation response, discussions looked at the possibility of staggering the procurement of vehicles over 2014 and 2015 as part of the mitigation response. BLM/MSI declined to follow up on this route highlighting the need for total number of vehicles required for them to be fully operational; additionally, the vehicles in use at the time were not roadworthy, had increased maintenance costs and represented a hazard to staff. The vehicles will remain DFID assets until the decision is made whether to pass over to BLM at the end of the project or to reassign.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The partnership principles support DFID’s decision-making process about the provision of development assistance within a country where there is an aid partnership. An assessment of a partner government’s commitment to the principles influences DFID’s working relationship with a government. Although all funding through Malawi government systems was suspended in late 2013 there was no direct relationship to the MFPP because funding is provided to the two key partners and there is no financial aid to or through, government systems. However, there are implications for the wider system and relationships e.g. because UNFPA discuss contraception commodity requirements with the GoM; and because there is a relationship with the Royal Norwegian Embassy as they and DFID are Joint Financing Agreement Partners to the wider work of BLM. These implications should be monitored.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evidence: Following a brief review no evidence has been found that to challenge the evidence of need for family planning provision in Malawi. Monies for a potential evaluation were set aside in the original programme budget but DFIDM made the decision not to evaluate. This AR concurs with this decision and suggests that the planned monies could be effectively used in key research areas instead. Further data disaggregation would inform a more sophisticated understanding of the delivery reach of the programme.

Theory of change and assumptions: The theory of change in the original business case is outline in nature only and assumptions in the log frame are minimal. This AR has therefore, not assed these aspects of the design process but recommends that, as the programme now extends to 2018 the theory of change could be updated and that the identification of assumptions would strengthen programme comprehension.

BLM: BLM have a strong monitoring system which will be further improved once the CLIC system has been rolled out across the country. The organisation has a core M&E team and assesses data quality on a quarterly basis using information from randomly selected clinics. Data query and logic checks are built into their systems. Data collection is supplemented by mystery client exercises which check for areas such as finance, confidentiality and respect. Exit interviews are also conducted. BLM holds monthly project review meetings to examine trends, issues and patterns e.g. a recent spike in female condoms. BLM are moving to follow MSI’s lead in developing ‘real-time’ data systems and analysis.

The AID Assurance Report on VSP Monitoring and Reporting found that much of BLM’s anti-fraud strategy is reliant on a Management Information Database that was intended to be fully functional by mid-2014. As of October 2014 this was not in place and this limits the amount of effective monitoring and reporting that can take place.

Monitoring progress throughout the review period
Information and evidence to inform performance against indicators has been drawn from the following sources:

- DFID Assurance Review (IAD) of Malawi Support to Family Planning Programme, January 2015
- DFID and BLM Risk Ratings
- The Malawi Family Planning Programme Business Case, 2011
- MDG Endline survey report
- MFPP Log Frames
- Malawi Health Sector Support Programme (MHSP), October-November 2014
- MFPP Annual Review, Jan-Feb 2014
- Support to Family Planning – UNFPA- Commodity Procurement Annual Review, December, 2012
- National Family Planning Stock Status Report End of December 2014 (Supplied by UNFPA)
- Family Planning 2015 Commodity forecast and gap analysis (HTSS Pharmaceuticals) (Supplied by UNFPA)
- Malawi Family Planning Programme MSI/BLM Quarterly Progress Report (July-Sept 2014)
- Malawi Family Planning Programme MSI/BLM Jan-June 2014 Biannual progress report.
- End line KAP survey , submitted to BLM, Dec 2013 (Dr B Ngwira)
- Benefits of Meeting the Contraceptive Needs of Malawian Women’, 2014, http://www.guttmacher.org/pubs/IB-Malawi.html
- Increased access to quality contraceptive commodities in Malawi (UNFPA Third Party Procurement), reporting period: January to June 2014 and July to December 2014
- Banja La Mtsogolo Due Diligence Assessment, 2014 and the BLM Feedback and comments
- Banja La Mtsogolo Financial statements for the year ended 31 December 2013 Report to Management

Additionally:
- Meetings and email exchanges with staff members from: UNFPA, BLM, USAID
- DFID staff
- Field visits (one clinic and one outreach centre) and informal discussions with service users and staff

Acronyms

BLM	Banja La Mtsogolo
CHAM	Christian Health Association of Malawi
CLIC	Client Information Centre
CMST	Central Medical Stores Trust
COCI	Community Outreach Clinic Initiative
CPR	Contraceptive prevalence rate - the percentage of women who are currently using, or whose sexual partner is currently using, at least one method of contraception
CYP	An estimated measure of protection from pregnancy by contraceptive methods in a one-year period. Different methods of contraception provide different measures of CYP (see https://mariestopes.org)
DSA	Daily Subsistence Allowance
FP	Family Planning
GoM	Government of Malawi
HIS	Delivery contractor to CMST
KAP study	Knowledge, attitude and practice(s) study
KfW	German government-owned development bank, based in Frankfurt
LAPM/RC	Long Acting Permanent Methods
LMIS	Logistics management information system
LTA	Long Term Agreement
MDG	Millennium Development Goal
MoH	Ministry of Health
MFPP	Malawi Family Planning Programme
MSHP	Malawi Health Sector Support Programme
MSI	Marie Stopes International
MSV	Marie Stopes Vasectomy
SDP	Service Delivery Point
SRH	Sexual and reproductive health
TOCI	Tent Outreach Clinic Initiative
UNFPA	United Nations Population Fund
VSP	Voucher Scheme Programme

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process