Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building Empowerment and Accountability in Malawi (BEAM)
Programme Value: £24,957,729		Review Date: 31/03/2017
Programme Code: 200469	Start Date: 7/12/2010	End Date: 30/04/2018

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016
Programme Score	NA	A	A+	A+	A	A
Civil Society Governance fund			A	A++	A+	A
PFM			B	B	A	B
Risk Rating	NA	Medium	Medium	Medium	Medium	High

Summary of progress and lessons learnt since last review

This Annual Review covers the 6th year of operation of the Building Empowerment and Accountability in Malawi (BEAM) programme. As a portfolio programme BEAM has moved from featuring 14 components in its original design to the remaining two - the Tilitonse civil society governance fund and support to Public Financial Management (PFM) reform through the World Bank’s PFM Multi-donor Trust Fund (MDTF).
Performance of the Tilitonse related outputs has been relatively strong. The Tilitonse Independent Impact Evaluation report (IIEA, 2016) concludes that the working relationship between government, CSOs and citizens has been strengthened as a result of the programme. The evaluation highlights numerous examples of strong interaction between CSO’s and district councils enhancing transparency of use of local and constituency development funds. National policies have also been effectively influenced, for example, Centre for Human Rights Education, Advice and Assistance (CHREAA) on prisoner rights, Norwegian Church Aid (NCA) on mining issues, National Media Institute for Southern Africa (NAMISA) on the Access to Information Bill, Centre for Multiparty Democracy (CMD) on the Local Government Amendment Bill, and Danish Church Aid (DCA) on national-level advocacy to review fiscal policy.

The evaluation, whilst highlighting areas of success, also concluded that the overarching results are more a collection, rather than a coherent aggregation, of different interventions designed to complement each other. The evaluation recommended that future strategy should promote linkages between local initiatives and national level processes. The evaluation concluded that impact is likely to be greater where there is traction for change, and where support is clustered around a particular issue or problem, addressing different parts of the policy-making / implementation cycle.

There have been some notable improvements in public finance management, from a low base, but implementation of the Integrated Finance Management Information System ( IFMIS) component is still slow. This element of the programme remains a high risk intervention for DFID.

Summary of recommendations for the next year

DFID to amend the BEAM logframe to reflect that PFM will be the only remaining component for the remainder of the programme once funding to Tilitonse ends in September 2017.

Tilitonse Secretariat to prioritise documentation of lessons learned and sharing and dissemination of results as the programme draws to a close.

Tilitonse Secretariat to develop a clear close-out plan and close-out risk matrix in order to ensure that all the key factors and risks have been identified and properly managed around DFID’s funding coming to an end in September 2017.

Tilitonse Board to ensure there is a robust transition arrangement should be in place between the Tilitonse programme and the new local foundation with clear milestones and timelines.

DFID to work closely with the World Bank (WB) and Government of Malawi (GoM) to ensure that the contract for the new IFMIS system has clear results-based payment milestones and that there are robust mechanisms for quality assuring delivery.

DFID to assess whether it should continue support to the PFM agenda post April-2018 and if so what form this should take.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-200469/
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4429218.xlsx

Outline of the programme

The Building Empowerment and Accountability in Malawi (BEAM) is a £24,957,729 programme which was launched under a Programme Memorandum in December, 2010. It has been extended from its original completion date of June 2016 to April 2018. The extension was done to cover a £4.5 million two-year contract extension with DAI/HTSPE which implements the Tilitonse component to provide sufficient time for Tilitonse to be established as an independent Malawian foundation and to extend the closing date of the Financial Reporting and Oversight Improvement Project (FROIP) under the World Bank Multi-Donor Trust Fund (MDTF) until April, 2018 to increase WB oversight of the remaining Integrated Financial Management Information System ( IFMIS) procurement process.
[note] The PFM MDTF end date was extended until October, 2018 in line with the FROIP April, 2018 end date.

BEAM combines work on the ’demand side’ of governance - supporting citizen and community based projects that promote better information, monitoring and influencing of Government policies and programmes – with work on the ‘supply side’ – supporting selected Government or quasi-Government institutions to improve service-delivery and increase transparency and accountability.

The expected impact of the programme is ‘more accountable, responsive and inclusive governance in Malawi able to support progress on off-track MDGs’. Its outputs are:

1. Civil society fund strengthens local organisations’ ability to promote access to information and monitor and influence policy
2. Government public financial management policies, procedures and practice strengthened
3. Capacity of National Integrity System assessed and civil society and Anti-corruption Bureau (ACB) capacity strengthened (not assessed in this review as activities completed in 2014)
4. Civil society community based monitoring strengthened (not assessed in this review as the Kalondolondo project closed in March 2016)

The governance and political context has changed several times since the launch of BEAM in 2010. In its first year, the programme operated in an environment of sharply declining governance with President Bingu Wa Mutharika’s government increasingly limiting the independence of accountability institutions and restricting the ability of citizens to exercise rights and freedoms. This changed with Bingu Wa Mutharika’s sudden death in April 2012 and transfer of power to Vice President Joyce Banda. As Head of State, Banda moved quickly to address concerns around economic management, political governance and human rights. Increased space for civil society and more freedom for the media to speak out returned, and relative stability ensued. However, during 2013 Banda’s leadership was increasingly being questioned and her position was weakened by the revelation of grand scale fraud and corruption involving public finances, popularly known as Cash-gate. The Peter Mutharika government which came to power following the May, 2014 tripartite elections made a strong commitment to Public Sector Reform, including reforming the public finances and following through on Cash-gate corruption issues. Public sector reform initiatives started on a high note with clear political will and direction as seen by the appointment of a Public Sector Reform Commission which was led by the country’s Vice President, Dr Saulos Chilima. Implementation of core civil service and public financial management reforms however has been slow. Corruption indicators across the board have declined and the recent publication of the Corruption Perception Survey (2016) shows Malawi slipping by 8 places from 112 to 120 with a score of 31, creating a difficult environment within which to make progress on improving accountability of public resources. The recent scandal around the procurement of maize by Agricultural Development and Marketing Corporation (ADMARC), a parastatal organisation funded by government is an illustration of entrenched and deep-rooted corruption in Malawi.

BEAM is a portfolio programme which originally brought together a total of 14 planned components. Some components were in-design at its approval stage, some were short extensions to existing projects, and others were still to be fully defined. Throughout, BEAM has had to adapt to the changing circumstances while staying committed to achieving the overall impact of the programme. By the start of the current annual review period, the BEAM portfolio had been rationalised to concentrate on its two remaining components:

Component	Description	Contributing to output	Operational dates
Tilitonse	A multi-donor Civil Society Governance Fund (Tilitonse) combined with an Independent Impact Evaluation Agent (IIEA) which completed its work in October, 2016. The fund aims to strengthen civil engagement to support efforts to achieve greater public accountability for service delivery and faster progress on development outcomes while at the same time contributing to the institutional development of civil society organisations (CSOs). This is a £19,654,267 programme with a DFID contribution of £13,617,857.	1	23/02/2011 – 30/09/2017
Public Financial & Economic Management (PFM) Reform	Contribution to a World Bank managed PFM Multi-donor Trust Fund (MDTF) supporting the Malawi Government’s Public Financial and Economic Management (PFEM) Reform Plan. As of June 2016, contributions received by the PFM MDTF totalled $16.5 million. DFID’s contribution is £5,174,000 ($8.1 million). DFID also supported a forensic audit into the Cashgate scandal with follow up interventions supporting investigations and prosecutions through a total contribution of £1,251,664.	2	01/07/2011 – 30/04/2018

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome for BEAM is “Greater citizen voice and participation in governance with improved management of public resources”. Three indicators of this outcome are based on the Tilitonse programme and one on PFM. The Tilitonse Independent Impact Evaluation (IIEA) released in September 2016, shows that there is strong evidence of achieving the outcome of voice and participation especially the inclusion of marginalised groups such as the youth, women and girls. Progress has remained slow on public financial management. The implementation of the new IFMIS system will not be completed within the project timeframe, in spite of the extension to April 2018.

The table below sets out the four indicators that measure this outcome based on results from the two remaining BEAM components.

		Milestone 2016	Result 2016
1	Improved scores in relevant Public Expenditure and Financial Accountability (PEFA) indicators	Current PEFA assessments completed for key indicators (revisions to PEFA framework in Feb '16 mean these are non-comparable to previous targets)	PI - 23.4: C- / PI - 25.3: C / PI - 26.3: C / PI - 29.2: C / PI - 30.2: C / As of March 2016
2	Number of documented cases of influence at national and decentralised levels on government and non-government actors achieved by BEAM programme partners (Tilitonse)	1330	992 Based on Grant Management Information System (GMIS)
3	Number of people supported to have choice and control over their own development and hold government to account	250,000 (Cumulative)	970,086 (cumulative)
4	Quality of cooperative activity (Tilitonse) / Extent to which cases demonstrate a strategic approach to partnerships / % of funded project respondents that say they have a ‘strong’ working relationship with Government officials / # of cases that demonstrate improved collaboration between CSO/citizens, government stakeholder and/or private sector actors	1/4 of cases – at least 5 out of the 19 cases) / 27.5%(Thematic call) / ¼ of cases (Over a quarter of cases demonstrate improved collaboration due to Tilitonse (at least 5 out of 19 cases))	9 out of 19 cases / 75% (Open Call Endline) / 50% (Thematic call Endline) / Data not collected by IIEA
[note] A score of C reflects the basic level of performance for each indicator and dimension, consistent with good international practices. A score of D means that the feature being measured is present at less than the basic level of performance or is absent altogether, or that there is insufficient information to score the dimension. It’s not possible to make any generalised statements as to how A, B and C scores should be interpreted in terms of overall strength of PFM. An A score obviously represents stronger performance against the specified criteria, however whether this means stronger PFM performance as a whole requires an understanding of how this narrowly defined criteria interacts with the broader systems.
[note] Source: WB staff informal estimates, FROIP Results Framework

Outcome indicator 1:-moderately did not meet expectation. Changes in the PEFA methodology in 2016 mean that the PEFA indicators initially identified to track results are no longer valid. The World Bank produced a new results framework for the project in 2016 (5681433) reflecting these revisions and also focusing on PEFA dimensions rather than PEFA indicators to enhance relevance. The table below presents progress against these in March 2016, based on informal assessments by Bank staff – a full PEFA has not been conducted since 2011. Due to the methodology revisions, the March 2016 values are not directly comparable to the Baseline.

Indicator	Baseline (June 2011)	Current (March 2016)
PEFA PI-23.4 (former PI-18) – Effectiveness of payroll controls	B+	C
PEFA PI-25.3 (former PI-20) – Internal controls on non-salary expenditure	C+	C
PEFA PI-26.3 (former PI-21) – Effectiveness of internal audit	D+	C
PEFA PI-29.2 (former PI-25) – Accounting,recording and reporting	C+	C
PEFA PI-30.2 (former PI-26) – Characteristics of External Audit	D+	C

Outcome indicator 2:- moderately did not meet expectation. The Tilitonse GMIS data shows 992 documented cases of influence out of the set target of 1330 for the review year. This fails to meet the target by 338. However, the Tilitonse Independent Impact Evaluation report (IIEA, 2016) shows stronger evidence of performance at this level. Out of the 12 CSO case studies which were conducted, 11 of the grantees (91.6%) aimed to empower citizens to engage with government with the ultimate objective of influencing government to respond to citizens’ issues. There is evidence of more positive engagement between citizens and government and how citizens have influenced government decisions. There is clear evidence of this in the following case studies: CCODE, CU, CHREAA, WfP, DCT. Tilitonse grantees have contributed to mediation between government and citizens and increased opportunities for citizens and government to come together. Citizens have increasingly engaged government in discussions about their issues and the WfP project has useful examples of this. In areas where CCODE has implemented its work, citizens’ problems have been made more visible to government and this has stimulated government’s response to citizens’ needs. Further evidence is obtained from the IIEA evaluation (page 43, par.103) which shows that SWET’s use of radio listening clubs influenced services, putting pressure on government to respond to citizens’ demands.

Outcome indicator 3:- For the review year, Tilitonse reported 970,086 (cumulative) people informed about their rights which surpasses the target of 250,000 of the DFID DRF indicator. Additionally, the Independent Impact Evaluation report (IIEA, 2016, p.34; par.80) shows that a large number of citizens have received information from Tilitonse grantees. In 10 CSO case studies (SWET, CCODE, WfP, NCA, DCA, DCT, CHREAA, NAMISA, CMD, CU), there is evidence that citizens received information from grantees and this has resulted in citizens being able to better understand and claim their rights. Further, the impact evaluation reports that in all six CBO case studies (COVISODE, ECOBO, FOCCAD, St Jude’s, NAYORG, and ECOYA), citizens stated that they had acquired more knowledge of rights and responsibilities from their engagement with Tilitonse grantees. COVISODE was singled out as providing strong evidence of this awareness as three citizen groups, project staff, one CSO stakeholder and one government stakeholder all mentioned citizens’ increased awareness of the responsibilities of local governments. Based on GMIS data and the Independent Impact Evaluation, it is judged that this indicator substantially exceeded expectation.

Outcome indicator 4:- substantially exceeded expectation. On sub-indicator 1 (Extent to which cases demonstrate a strategic approach to partnerships), the GMIS data shows 9 out of 19 cases demonstrating strategic approach to partnership and this surpasses the target by 4. On sub-indicator 2 (% of funded project respondents that say they have a ‘strong’ working relationship with Government officials), the Independent Impact Evaluation ( page 41, par.95) shows that 75% (Open Call Endline study ) and 50% (Thematic Call Endline study) of funded projects where respondents said they have a ‘strong’ working relationship with Government officials, and 71% (Open Call 2 Endline study) showing improved collaboration between CSO/citizens, government stakeholder and/or private sector actors. Specific projects interventions where these have happened include Action Aid, the Association of Early Childhood Development in Malawi, Maziko Radio Station, Southern African AIDS Trust, Care Malawi, Centre for Legal Assistance, World Vision, CCODE, Oxfam Malawi, Theatre for a Change, WUSC, SWET, MIJ, Malawi Human Rights Resource Centre (MHRRC), and NCA. In these projects, the marginalised groups (i.e. youth, women, prison inmates) have been included in all key processes and interventions. On sub-indicator 3, no data was collected by IIEA and this has not been rated.

Overall output score and description

The output score of the programme is A on the basis that:
- Output 1 with an impact weighting of 60% scored A
- Output 2 with an impact weighting of 40% scored B

Output 1: Output 1 ‘Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy’ scored A.

The achievement of the milestone for Output indicator 1.1 substantially surpassed expectation with GMIS data recording 282 information products being produced. The IIEA case studies noted that 83% of CSOs and all the 6 CBOs showing information dissemination that has raised citizen awareness about rights and entitlements. For Output indicator 1.2, a total of 2,269,886 people have been informed about their rights to public services, slightly less than the planned milestone of 2,500,000. However, the IIEA case studies show that in 83% of the case studies citizens received information and this was also the case with all the 6 CBO case studies. Output indicator 1.3 was not monitored but information is reported from another indicator monitored by Tilitonse, “Number of dialogue initiatives aimed at influencing service delivery behaviour policies, strategies and resource allocations”. The reason indicator 1.3 is no longer being measured is due to the fact that the open calls had been phased out and the DFID BEAM logframe was not updated to reflect this change. Since Tilitonse has reported on the new indicator, the annual review has used the data to rate the new indicator. The new indicator has substantially surpassed the milestone achieving 5,988 representations to duty bearers against a milestone of 800. For Output indictor 1.4, Tilitonse recorded that a total of 32 innovative practices developed by Tilitonse grantees were adopted by other CSOs or agencies outside Tilitonse, against a milestone of 30. This indicator was not monitored by the IIEA.

Output 2:- There have been some notable achievements in 2016 in PFM areas supported by the Financial Reporting and Oversight Improvement Project (FROIP) under the World Bank MDTF: including the timely preparation of financial reports and preparation of outstanding audit reports on the financial statements FY 2012/13 to date. However, progress on procuring and implementing a new IFMIS system, the largest single expenditure item under the project, has been slow. In addition actions to strengthen the integration of the existing IFMIS system have not been undertaken and progress in strengthening internal and external audit has fallen short of targets.

Key lessons

Collaborative work-Thematic call: One of the key aspects of the Tilitonse Thematic Call was the promotion of CSOs working together at local and national level. In the three Thematic Call case studies conducted by the Independent Impact Evaluation Agency and as observed during the field visit as part of the AR, grantees were conducting activities at both local and national level, and there were various examples of achievements at these levels. However, there was relatively little evidence that local and national activities were ‘joined up’ towards higher level strategic goals – rather, the local and national components seemed relatively separate and generally involved different actors. This is a challenge for the Tilitonse programme as it evolves into becoming a new Foundation.

The impact of CBOs needs further learning: The last BEAM Annual Review noted that the Tilitonse shift to funding more community based organisations (CBOs) from a focus on national CSOs/ NGOs was successful at the local level with examples of tangible results in improving service delivery at service centres. The Annual Review argued that local organisations’ performance compared positively to that of national Civil Society Organisations (CSOs) with much greater experience and capacity. However, the Independent Impact Evaluation (IIEA report, page 55, par.142) makes an interesting observation which this Annual Review wants to carry forward. The learning is that there is an issue of magnitude which makes the impacts of CBO and CSO grantees inherently difficult to compare. CBO grants are generally tens of thousands of pounds and run for a year in one locality, while the other grant rounds were hundreds of thousands of pounds running for more than one year and across more than one location. The IIEA analysis shows that it has yet to be proven that the CBO interventions (and the initial changes) have led to ongoing changes in local government responsiveness. The Tilitonse programme needs to understand this further in its ongoing monitoring and evaluation work to get a deeper analysis of the impact that the CBOs are making. If well understood, this will help the new local foundation to strike the right balance between supporting national CSOs and localised community organisations.

Traditional Capacity building vs a Mentorship approach: The shift from traditional capacity building to a mentorship approach was introduced later in the implementation of the Tilitonse programme. Both the field reports and findings of the Independent Impact Evaluation (IIEA) show that the mentorship approach in the latter years of Tilitonse have been more effective in building capacity. This learning needs to be transferred to the Tilitonse Local Foundation to ensure an early adoption of the approach and possibly the crop of mentors as well who will have built better expertise and familiarity with grantees working at various levels.

Balance between CSO organisational development and building citizen / government capability: Tilitonse focused its capacity building interventions around sound financial and project management of its grantees. While this is important for donor accountability, the lesson is that much more support is needed to build ‘ways of working’ i.e. facilitation of processes, thinking and acting politically, partnering in strategic ways, forming alliances. This has been noted in various reviews and reinforced through the Independent Impact Evaluation (IIEA). As the current programme comes to a close this year, the local foundation needs to take this on board and ensure a good strategy is in place to support partners to work politically and build coalitions.

Sufficient focus on policy implementation: Notable successes of Tilitonse relate more to policy-making processes (at the national level) or solutions to local problems (community-level), with weaker evidence of the effectiveness of routine monitoring of existing policy commitments. Although most grants will be winding up by July 2017, some more focus on this aspect is needed to ensure that the policy commitments get implemented.

Commitment to Public Financial Management (PFM) reform: There has been an improvement in high-level commitment to improving Public Financial Management during 2016 particularly around compliance in financial and audit reporting. This has been reflected in an uptick in the pace of project implementation. Some of this progress however is likely attributable to the new World Bank Development Policy Operation which included PFM improvements as conditions to be met before disbursement. The bulk of the PFM project is now focused on procurement of a new IFMIS system (i.e. a technical and therefore a partial solution). The political and human dimensions that are inherent to the weaknesses in public financial management controls need more attention. While the current IFMIS is outdated, its replacement is only part of the solution. A more coordinated and problem-driven approach by donors should be considered when thinking of any successor to the FROIP project.

Key actions and recommendations

Future civil society foundation

The Tilitonse Local Foundation should identify all the key learning and organisational needs that the current Tilitonse programme can provide support to. It should further draw its plans and time lines clearly so that there is a seamless transition between the Tilitonse programme and the Local foundation.

Tilitonse

Tilitonse programme should identify all the key risks related to programme closure and mitigation strategies to ensure that these risks are properly managed and controlled.

Tilitonse should revise its budgets for the remaining period and agree on a revised contract amendment with DFID to ensure the financial position and forecast of the programme is clear and accurate.

Tilitonse should continue to document results and compile case studies that can highlight results especially during the two year extension period leading to closure of the programme.

Tilitonse should deal with all the outstanding financial management issues with its grantees to avoid run-over cases after the closure of the programme in September, 2017.
Public Financial Management

The MDTF donors should carefully manage the risks associated with the IFMIS procurement. The GoM and the WB should continue their efforts to strengthen oversight and monitoring of the remaining procurement process and should ensure that the contract has clear results-based payment milestones.

DFID should continue to drive forwards dialogue around the risks relating to the project timeframe and develop mitigation measures with GoM, the WB and other PFM donors. This risk should be carefully monitored to ensure it remains within our risk appetite.

By the end of 2017 DFID should have developed a plan for its support to PFM beyond April 2018, whether this is direct or embedded within a broader public sector reform agenda.

Programme management issues

After closure of the Tilitonse programme, the BEAM log frame should be revised to reflect the remaining PFM activities and results.

Learning for future programming (Tilitonse)
- DFID to learn from the challenges associated with reporting in a portfolio approach log frame in future programming and consider alternative ways of capturing complexity of results.
- The Tilitonse grant windows funded many different grantees to do many different things, dispersed widely by policy reform area, sector, level of government, size of intervention and so on. This design meant that at the end of Tilitonse, the overarching results are more a collection of examples than a coherent aggregation of different interventions designed to complement each other. For the future, there should be linkages between potential local initiatives and national level processes. The Impact evaluation shows that impact is likely to be greater where there is traction for change, and where support is clustered around a particular issues or problems, addressing different parts of the policy-making / implementation cycle.

The Tilitonse programme has been helping partners to carryout political economy analysis as an exercise in itself without sufficient application of that analysis to working differently. There was lack of ongoing practical mentoring that deals with the political economy as a ‘live issue’. For the future, the Tilitonse local foundation should focus much more effort on strategic and political ‘ways of working’, with less focus on building CSOs and more on building the capability of citizens and civil society.

 Has the log frame been updated since the last review?

The BEAM log frame was updated in November 2016 to reflect changes to the programme context as a result of closing of the Kalondolondo component of the BEAM programme, completion of the Independent Impact Evaluation Report in September, 2016 and review of the Tilitonse logframe. The changes are recorded in Quest document number 4136499. By omission, Tilitonse specific indicators were not revised at this time, as had been recommended by the previous annual review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy (Tilitonse)
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone for 2016	Progress
1.1 # of information products developed in funded projects	250	282
1.2 # of people informed through funded projects about their rights to public services	1,000,000 men / 1,500,000 women / 2,500,000 Total	2,269,886
1.3 # of representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery / (Not monitored by Tilitonse since 2016 and instead the indicator below is one being monitored) / “Number of dialogue initiatives aimed at influencing service delivery behaviour policies, strategies and resource allocations”.	800	5,988
1.4 # of practices and issues promoted by CSO grant partners that are adopted by other CSOs and development actors	30	32

Key Points

Indicator 1.1 is about informational materials produced by Tilitonse grantees to disseminate key messages on rights and entitlements. For 2016, achievement of this indicator exceeded expectations. The GMIS data shows that 282 information products were produced surpassing the target by 32. The Independent Impact Evaluation (IIEA report page 34, par. 80) provides qualitative analysis and noted that in 10 of the 12 CSO case studies, (83%) (SWET, CCODE, WfP, NCA, DCA, DCT, CHREAA, NAMISA, CMD, CU), there was evidence that citizens received information from grantees which resulted in citizens being able to better understand their rights. Furthermore, in all six CBO case studies (COVISODE, ECOBO, FOCCAD, St Jude’s, NAYORG, and ECOYA), citizens – including young people and people with disabilities – stated that they had acquired more knowledge of rights and responsibilities from their engagement with Tilitonse grantees. In two cases (COVISODE, ECOBO), this has enabled them to engage with government. In COVISODE, evidence was particularly strong as three citizen groups, project staff, one CSO stakeholder and one government stakeholder all mentioned citizens’ increased awareness of the responsibilities of local governments. A female citizen reported: “We are [now] able to arrange meetings and engage with the chief and the committee for information from the district.” Information was disseminated through products such as radio recordings (e.g. DCT), radio jingles, leaflets, posters, manuals and various clothing materials. However, low literacy and education levels were seen as barriers to citizens’ increased understanding of information in some cases (NCA, CMD, CU, CCODE).

The number of people informed about their rights (Indicator 1.2) did not meet the target according to GMIS data. Cumulatively, a total of 2,269,886 people have been informed about their rights to services (this combines national as well as Community data through work of CBOs which was not included in previous reviews). This fails to meet the target by 230,114. However, the Independent Impact Evaluation report (IIEA, 2016, p.34, par.80) shows that many members of the general public have received information from Tilitonse grantees. For example, in 10 out of 12 CSO case studies (SWET, CCODE, WfP, NCA, DCA, DCT, CHREAA, NAMISA, CMD, CU), there is evidence that citizens received information from grantees and this has resulted in citizens being able to better understand and claim their rights. Additionally, the impact evaluation reports that in all six CBO case studies (COVISODE, ECOBO, FOCCAD, St Jude’s, NAYORG, and ECOYA), citizens stated that they had acquired more knowledge of rights and responsibilities from their engagement with Tilitonse grantees.

Indicator 1.3 measures the number of representations to government officials through formal social accountability tools such as score cards. These approaches were largely used by larger CSOs. However, with the phasing out of most of the open calls, it is more relevant to refer to CBO interventions focusing on community meetings rather than formal accountability tools and captured under another indicator in the Tilitonse logframe which measures the “Number of dialogue initiatives aimed at influencing service delivery behaviour policies, strategies and resource allocations”. Based on CBOs and CSOs interventions, the GMIS data shows 5,988 representations were made under this indicator and this surpasses the target substantially. The Independent Impact Evaluation Report (IIEA, page 35, par. 81) captures performance of CSOs and shows there were five cases out of twelve (CHREAA, CMD, NAMISA, NCA, DCA) where evidence is strongest of the grantees taking an important role in collaborating with – and in most cases leading – CSO and government stakeholders in influencing relevant policies at a national level. These include: CHREAA on prisoner rights, NCA on mining issues, NAMISA on the Access to Information Bill, CMD on the Local Government Amendment Bill, and DCA on national-level advocacy to review fiscal policy.

Indicator 1.4 measures innovative practices shared by Tilitonse grantees. The Independent Impact Evaluation did not monitor this indicator. The GMIS data shows that a cumulative total of 32 practices were shared by Tilitonse grantees which surpass the set target by 2. One of the cases recorded relates to a newly funded CBO (NECOSS) working with hospital personnel, the police and community members to track drug management at target health centres. This has enhanced collaboration between Health Advisory Committee and HFAC at district level. This initiative has been adopted by other organisations focusing on drug monitoring. The field findings show that there are other good examples of innovative practices that have been shared in the year which have not been observed by the secretariat. One of them is the use of radio listening clubs and phone messaging on monitoring development issues especially Local Development Funds (LDF), Constituency Development Fund (CDF) and District Development Fund (DDF). Development Communications Trust (DCT) uses Radios and Phone messaging to communicate issues from the communities to government officials and politicians in Phalombe. This initiative is now being shared with CCJP who work with DCT in the same area under the Oxfam support. World Vision has been an advocate of Community Voice and Action (CVA), a social accountability approach that promotes engagement between communities and government. This has been tried in Zomba with various communities and it has been applauded as a crucial tool and approach to bring community issues closer to those who matter. This approach has been widely adopted by other organisations and communities as was noted in Nkhatabay in Mankhambira area where communities are using this approach after learning it from communities in Zomba where World Vision is also operating.

Tilitonse has a current grants portfolio of over 80 grantees, 44 of whom are CBOs approved under the second CBO call. With this, capacity challenges increased for the CBOs most of which need basic facilities and operational systems. In response to this, the Tilitonse Board approved a new Capacity Action Plan to address these gaps and consolidate the programme strategy by deploying additional and better skilled mentors. The secretariat also increased staff capacity with the employment of four Programme Officers approved by the Board under the extension phase to provide further support to the CBOs.

As Tilitonse will be evolving into a Foundation in September 2017, most of the grantee projects will be phasing out in June, 2017 with a few remaining to close in July. The close out is a high risk period in both programmatic and financial terms. Being aware of this, Tilitonse strengthened its monitoring and overall management of its grants to ensure early detection and remedy of any issues of concern in the implementation of projects by its partners. The recent revelation of potential conflict of interest in the secretariat has increased the Board and DAI’s vigilance against any attempts of fraud in the running of the secretariat functions.

Learning between grantees has continued to increase. In the year, Tilitonse organized a number of learning events including a regional best practice workshop for grant partners under all funding windows in October 2016. The workshop was attended by 112 participants from Community Based Organizations, local NGOs, international NGOs, and faith based organizations, all funded under Tilitonse. This provided a platform for all grant partners to share best practices and lessons learned from the approaches used during project implementation, technical and financial reporting and networking among other things. Tilitonse was also invited to be an organizing partner of a learning conference organized by USAID-funded ‘Supporting the Efforts of Partners’ (STEPS) Programme that took place in June 2016. Tilitonse assisted with the development of the workshop programme, rationale, methodology, and identification of local experts in different fields to make presentations during the workshop. Tilitonse delivered a presentation on exit/phasing out strategies using Tilitonse Fund as a case study and the processes being followed in the establishment of the Foundation. The presentation provided an opportunity for Tilitonse to share its experiences, achievements, and lessons learnt working in the governance sector with the wider civil society and other donors.

A number of Case Studies and best practices were compiled to consolidate and showcase the gains the Fund has made to the governance sector in Malawi. During the reporting period, the Secretariat together with DAI and the Ministry of Information’s Malawi News Agency embarked on case study documentation process covering four selected Tilitonse funded projects implemented by the Malawi Human Rights Commission, Nkhadze Alive Youth Organization (NAYORG), the Development Communications Trust and Foundation for Community and Capacity Development (FOCCAD). The exercise was aimed at capturing significant change/success stories from the selected funded projects in visual and written form (feature stories and video documentaries) that highlights key project results, activities, successes, challenges and impact of the Programme. These documented cases were shared in the national newspapers and the video documentaries were aired on the national TV, MBC. In addition, an external consultant was engaged to assist with documenting further case studies and briefing notes from the Programme for processing into different information products for wider sharing.

Summary of responses to issues raised in previous annual reviews

The last annual review made a number of key recommendations which have been dealt with in this implementation year.

The 2015 Annual review recommended that Tilitonse should increase dissemination and communication of results, case-studies and lessons learned. This should include improving the website and ensuring that all case-studies, project briefs, grantee profiles are linked from the GMIS to the website for public access. In addressing this recommendation, the website was redesigned to make documents more accessible and the site more interactive. More documents were uploaded on the website to ensure efficiency in information sharing. The website was visited by 4,645 users (59.3% were new whilst 40.7% were re-visits) and the web pages were viewed 26,310 times during the reporting period. The Programme has also transitioned from using the manually-designed newsletter to an online version as the former was found to be limiting in terms of provision of information since different attachments could not be integrated into the document. DAI, the managing Agency supported the secretariat to ably transition from manual with technical support from its headquarters. The current version of the newsletter accords the Programme an opportunity to provide more information through links to other document sources, reports and publications. Recipients of the newsletter included all grant partners and sub-grantees, development partners, Board Members and close to 100 newsletter subscribers from the website.

The Tilitonse programme has intensified its monitoring and evaluation activities and introduced a performance tracker which flags potential non-performing projects. Tilitonse has also embarked on case study documentation where at least 10 case studies will be compiled and shared with various stakeholders at the end of the programme. This is in additional to the independent impact evaluation.

Tilitonse has carried out various lessons sharing and learning sessions and will continue doing so especially in the close down period of the programme. The website has also been upgraded and improved to host a lot of lessons learning documentation that have been compiled in the life of the programme.

- The local foundation board will develop its strategic plan and based on this, a clear capacity building plan will be developed to address various capacity issues including the technical governance capacity.
- The Tilitonse logframe was not revised on time and this led to the BEAM logframe being revised without affecting the aspects related to the Tilitonse logframe.

Recommendations

The Tilitonse Local Foundation should identify all the key learning and organisational needs that it wants support on from the current Tilitonse programme. It should further draw its plans and time lines clearly so that there is a seamless transition between the Tilitonse programme and the Local foundation.

Tilitonse programme should identify all the key risks related to programme closure and mitigation strategies to ensure that these risks and properly managed and controlled.

Tilitonse should revise its budgets for the remaining period and agree on a revised contract amendment with DFID to ensure the financial position and forecast of the programme is clear and accurate.

Tilitonse should continue to document results and compile case studies that can highlight results especially during the two year extension period leading to closure of the programme.

Tilitonse should deal with all the outstanding financial management issues with its grantees to avoid run-over cases after the closure of the programme in September, 2017.

Output Title	Government public financial management policies, accountability, procedures and practice strengthened
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Independence of the National Audit Office	Backlog of annual audited statements cleared 2012-2015. Public Audit Bill approved by parliament. / (Dec 2016)	Partially achieved: / The 2014/15 and 2015/16 Audit Reports were completed. This brings audited annual statements up to date (from 2012/13). / The Public Audit Bill has not yet been approved. It is currently at committee stage. However, it should be noted that approval is a political process, which the project does not have direct control over.
2.2 Quality and timeliness of in-year budget reports	Consolidated 2015/16 financial statements are submitted for external audit by end of October 2016. / (Dec 2016)	Achieved.
2.3 IFMIS roll-out and update	IFMIS procurement contract given no-objection by the World Bank. Integration between current IFMIS and the payroll achieved. / (Dec 2016)	Not achieved. / As of end-Dec 2016 the World Bank had provided a no-objection for the Government to move on to the next stage of the procurement process – the live demonstration by the preferred supplier. Once this has been completed satisfactorily the contract negotiation process will begin. It will therefore be some time before the final contract is given a no-objection by the World Bank. / The Government have not yet completed the interface between the current IFMIS and the payroll.

Key Points

External Audit and the Independence of the National Audit Office
Legislative proposals that would increase the independence for the NAO have been developed and are at committee stage in parliament.

Proposed amendments seek to address the political, financial and administrative angles of NAO independence. The project engaged PwC to provide technical advice and guidance on international best practice to ensure National Audit Institutions are more independent. DFID and other donors have engaged significantly with political and technical stakeholders such as members of the Public Accounts Committee and Senior Civil Servants to ensure the final Bill meets international standards and to move the legislative process forward.

The Auditor General has submitted audit opinions for the FY 2012/13 – 2015/16 financial statements to the Treasury. This represents significant progress since last year when the audit opinions for the FY2012/13, 2013/14 and 2014/15 financial statements were outstanding as of January 2016. As of February 2017, the Auditor General is up to date on auditing financial statements, reflecting the significant investments in capacity building under FROIP, however the 2015/16 audited statement was submitted to the Treasury after the December 31st statutory deadline.

Quality and timeliness of financial reporting:

The FY 2015/16 financial report was submitted by the Accountant General to the Auditor General prior to the 31st October 2016 statutory deadline. This is the first time since FY 2011 this has been achieved. The quarterly financial statements have been prepared and audited up until March 2016.

IFMIS roll-out and update

Progress on the procurement of the new IFMIS has been slow. The project end date was changed from June 2016 to April 2018 to enable more time for the IFMIS procurement. In 2016 the GoM successfully completed the bid evaluation and has received a no-objection from the World Bank to proceed to the next stage of procurement: the live demonstration. There are still a number of steps before implementation can begin and any further delays to the procurement process will squeeze the already tight implementation window. There is a significant risk that the implementation of the new IFMIS will not be completed prior to the project end date (see section E for full discussion).
[note] In anticipation of this DFID approved a no cost extension of the BEAM project in June 2016 in order to cover the full FROIP duration.

Achievements under the project include improvements in the security of the IFMIS system and the implementation of the government wide area network. However, the GoM has not yet implemented a number of actions targeted at enhancing the effectiveness of the current IFMIS system, including the integration of the IFMIS and HRMIS and the integration of central and local government IFMIS.

Overall performance of FROIP

Throughout 2016 WB progress reports (Mar 2016, Jun 2016, Oct/ Nov 2016) rated the progress towards achievement of the project objective and overall project implementation as ‘moderately satisfactory’. An improvement in financial reporting was noted during the second half of 2016 and the focus now needs to be on keeping up the momentum on PFM reforms built up in 2016.

Summary of responses to issues raised in previous annual reviews

The previous review noted the absence of M&E framework for the project. This remains the case. The Bank provided no objection for the recruitment of an M&E specialist in 2015, however the GoM has remained reluctant to engage support and in late 2016 the Bank brought in its own M&E specialist to develop an M&E framework for the project. This has not yet been shared with donors. DFID continues to push for greater transparency in results and use of funding. No annual workplan has yet been shared for 2017.

- The logframe was revised to include relevant targets for 2016 and April-2018, taking into account the no-cost extension.
- DFID have continued to push for enhanced donor coordination around PFM. The GoM has made an effort in 2016 to reinvigorate both the broader PFM donor-government coordination structures as well as FROIP specific governance arrangements. By promoting greater dialogue it is hoped that this can help to mitigate some of the risks outstanding around the project. In addition, donors have monthly PFM donor meetings where key issues are discussed.

Recommendations

By the end of April 2017, the World Bank should finalise the monitoring framework and annual workplan for 2017.

The MDTF donors should carefully manage the risks associated with the IFMIS procurement. The GoM and the WB should continue to strengthen oversight and monitoring of the remaining procurement process. The World Bank should prepare and agree with trust fund donors and the government a risk matrix with mitigating actions for the IFMIS implementation by April 2017. This should be jointly assessed by trust fund donors and the World Bank on a monthly basis.

Recognising the recent initiative taken by the GoM, DFID should continue to push for constructive dialogue between the GoM and donors on PFM issues and specifically on the risks relating to IFMIS implementation in formal Government of Malawi structures.

By the end of 2017 DFID should have developed a plan for its support to PFM beyond April 2018, whether this is direct or embedded within a broader public sector reform agenda.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for the programme were grants disbursed under the Tilitonse Project (Support to Civil Society Governace Fund – Component 200469-110) and consultancies for strengthening anti-corruption fight under the Public Finance Management Component (200469-117). Given reallocation of additional resources away from other budget lines, the IFMIS procurement now amounts to 51% (from an originally 28%) of the FROIP project.

In terms of grants, Tilitonse Secretariat continued to monitor grant performance through quarterly monitoring visits. The Audit and Finance Committee of the Board has met 4 times as required to provide oversight function on Finance Management at the secretariat broadly. Particular attention was on Grants as it forms the key cost driver. It was observed during the field visits that 5 of the 7 Grant Partners visited kept their financial records well and a review of the financial documents showed that supporting documents were complete and filed accordingly. This can be attributed to the monitoring visits and financial management mentorship which the Tilitonse programme has provided to the grantees.

VfM performance compared to the original VfM proposition in the business case

The BEAM programme was designed and approved prior to the introduction of the business case format and therefore has no established VfM indicators. However, efforts are being taken to ensure that VfM is achieved in programme delivery, as demonstrated below.

Assessment of whether the programme continues to represent value for money

Tilitonse

Economy – Generally, economic delivery of the programme is considered fair. It was observed, however, that procurement of capital assets, especially IT equipment, by Tilitonse downstream partners did not consider economic benefits. It was observed that supplier selection decisions were based on price by selecting the cheapest supplier and not considered specifications. It was further observed that this was due to lack of procurement technical capacity of the downstream partners, especially CBOs. Downstream partners whose risk rating increased were suspended and funded on reimbursement basis upon resolution of risk factors.

Efficiency – An average of 26% of the programme costs were used for overhead costs. This percentage is inclusive of capacity building costs for Tilitonse Grant Partners through the mentorship programme. This is considered fair considering the high level skills of the programme delivery staff at the secretariat and mentors. Further, delivery of the programme through community-based organisations reduced the administration costs at the downstream partner level as most of the personnel work on voluntary basis.
Exchange gains have been monitored on monthly basis among the donors and Tilitonse grant partners. The Grant Partners were advised to reprogramme the exchange gains which had a positive impact on the delivery of programme outputs.

Effectiveness – A new MoU in November 2015 meant renewed cooperation between the donors and a new contract was signed with DAI to continue with Tilitonse. Savings of £172k were achieved through this negotiation with the service provider providing 120 days of pro-bono technical and back-stopping support. As the lead donor for Tilitonse, DFID is leveraging funds worth £5.8 million from other donors with its £13.6m investment. The fund manager was recruited using the OJEU process with financial criteria increased to emphasise the desire to see good value for money, and the competitive grant making process allows the fund to ‘test the market’ and select those partners that are best placed to deliver results and value for money.
[note] Irish Aid contributes EUR 2,550,000  and the Royal Norwegian Embassy NOK 46,000

Overall, Tilitonse is assessed as delivering good value for money. About 75% of the programme budget has been spent on programme delivery through grants to downstream partners. The programme realised savings of up to £172k through contract renegotiation with DAI, the supplier delivering the programme, through the project cost extension. Close monitoring of grants has resulted in effective risk management which has prevented loss of funds through fraud and corruption.

PFM MDTF

Economy / Efficiency – The IFMIS procurement process is ongoing, however a number of risk mitigation measures have been put in place to drive VFM in procurement. The IFMIS procurement process is being overseen and quality assured by the World Bank on the basis of International Competitive Bidding, following the World Bank procurement rules. The value-for-money of the procurement will ultimately depend on the strength of the contract and the GoM’s ability to effectively implement a new IFMIS. To help to ensure this the WB will scrutinise the contract from a technical and commercial perspective and a precondition for a no objection on the IFMIS contract is the presence of a dedicated GoM IFMIS implementation unit.

DFID was the first donor to contribute to the PFM MDTF and has helped mobilise approximately £8 million from other donors. The GoM has committed to cover any funding shortfall in the procurement of the new IFMIS (currently estimated at USD 3 million).
[note] The EU contributes EUR 7m, Germany EUR 0.4m, Irish Aid EUR 0.5m and the Norwegian Embassy NOK 15m.

Effectiveness – Whilst the initial business case focused on upgrading the existing IFMIS, it was decided in 2014 that it would be better VFM to procure a new IFMIS given the existing systems’ inadequate technical specifications and lack of support services. In addition, weaknesses in the control environment and business processes relating to the existing IFMIS made Cashgate possible and a new IFMIS offers the chance to review these and re-set attitudes towards IFMIS. Continued efforts to strengthen the control environment around IFMIS are essential if the new system is to deliver VFM by improving financial management, reporting and oversight.

Currently FROIP is considered to be good VFM, in spite of the significant risks. In addition to the processes described above to deliver VFM in IFMIS procurement, discussions are ongoing to ensure a robust plan is in place to support IFMIS implementation beyond April 2018.

Quality of financial management

Financial management continued to be of high quality. During the year under review, the programme budget was £1,932,745.50. Of this budget, £1,864,296.45 has been spent representing a 3.6% variance (Table 1). The variance is mainly due to agreed changes in the payment schedule for the Impact Assessment of Cash-gate response.

Table 1: BEAM 2016/17 Finance Report
Component	Approved Budget	Spend	Balance	Variance
Total	£1,946,745.50	£1,877,246.18	£69,499.32	3.6%
200469-102	£1.00	£0.00	£1.00	100.00%
200469-103	-£0.02	£0.00	-£0.02	100.00%
200469-110	£1,648,076.25	£1,641,959.92	£6,116.33	0.37%
200469-114	£41,483.78	£41,483.78	£0.00	0.00%
200469-115	£0.00	-£28,471.06	£28,471.06	#DIV/0!
200469-117	£257,184.49	£222,273.54	£34,910.95	13.57%

Cumulatively, the programme is underspent by 9.5%, an improvement from 17% reported during the 2015/16 AR. Table 2 shows cumulative expenditure for the programme.

Table 2: BEAM cumulative expenditure
Component Code	Component	Approved Total Budget (£)	Cumulative Expenditure (£)	Balance (£)	Variance
200469-101	Appraisal and Design	93,039.53	93,039.53	-	0.0%
200469-102	Support to Local Government Elections	1.00	-	1.00	100.0%
200469-103	Civic & Voter Education for Local Government Elections	410,000.00	410,000.00	-	0.0%
200469-104	Monitoring and Evaluation	3,702.83	3,702.83	-	0.0%
200469-105	Support to Good Governance Fund projects	67,713.85	67,713.84	0.01	0.0%
200469-106	Accountable Grant to Story Workshop	130,792.00	130,792.00	-	0.0%
200469-107	Accountable Grant to Malawi Economic Justice Network	95,642.55	95,642.55	-	0.0%
200469-108	Accountable Grant to Centre for Human Rights Education, Advice and Assistance (CHREAA)	53,420.15	53,420.15	-	0.0%
200469-109	Accountable Grant to Malawi Union for the Blind	48,111.95	48,111.95	-	0.0%
200469-110	Support to Civil Society Governance Funds	13,224,312.85	11,755,093.98	1,469,218.87	11.1%
200469-111	Support to Anti-Corruption Bureau	550,000.00	550,000.00	-	0.0%
200469-112	Advisory and management support	3.00	-	3.00	100.0%
200469-113	Anti-Corruption Accountable Grant for National Intergrity System	421,503.50	421,503.50	-	0.0%
200469-114	Independent Impact Evaluation Agency	395,249.61	395,249.61	-	0.0%
200469-115	Community Based Monitoring	2,244,345.00	2,215,873.94	28,471.06	1.3%
200469-116	National Audit Office	43,000.00	43,000.00	-	0.0%
200469-117	Public Financial Management Trust Fund	7,229,699.33	6,356,000.16	873,699.17	12.1%
Total		25,010,537.15	22,639,144.04	2,371,393.11	9.5%

 An average forecaster variance of 6% was registered. This is attributed to constant engagement with the delivery partners on accurate forecasting. Tilitonse programme submitted monthly financial reports and forecast which were adequately reviewed. The programme achieved an ODA target with spend by December 2016 at 94.6%. Spot checks conducted at the Anti-Corruption Bureau (ACB) and Tilitonse Grant partners showed that programme assets are well stocked and managed.

Through constant monitoring of grants, no new ineligible costs were reported. However, £3,652.70 was recovered from a total of £12,733.29 which was reported as ineligible costs from Tilitonse Programme grant partners in previous years.

DFID has received an assurance from the WB that an amount equal to or greater than the DFID contribution to the PFM MDTF will be paid out directly from the World Bank’s account in Washington DC to suppliers. This will cover IFMIS procurement. In this way DFID has distanced itself from the project expenditure being executed by the GoM. The GoM managed account has an outstanding mis-procurement, consisting of consignment of Desktop computers and printers procured in 2013 under worth $519,142.32. The WB issued a letter of demand in July 2016 for refunds and an invoice for the full value to the GoM through the Secretary to Treasury. The period for repayment elapsed in August 2016 and the GoM has been urged to rectify the situation as a matter of urgency.

Date of last narrative financial report	Tilitonse: February - Quarterly report for Oct-Dec 2016, / WB MDTF: 30 June 2016.
Date of last audited annual statement	Tilitonse: 31st March 2016 / WB MDTF: June 2016

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

During the review period the overall risk level for BEAM has remained unchanged, however, there has been changes within individual components and some risks have materialised and become issues the team is now managing.

In terms of the civil society components, there has been the risk of closing space for civil society as tensions grow between Government and CSOs. This has become a real issue with the development of a new NGO Policy which is being seen as a tool for government to suppress civil society operations in Malawi. DFID with other donors have provided feedback to the NGO Board identifying key areas of concern and proposing significant changes. The Tilitonse programme has supported the National Advocacy Platform and CONGOMA to coordinate civil society response to the draft policy and proposing areas that need further discussions and changes. DFID and other development partners will continue to monitor this closely and play a key role in ensuring the policy is suitable for civil society operations in Malawi.

Fraud and corruption risks in Malawi are significant. Where fraud concerns cases have emerged, these have been followed up closely by the BEAM programme managers and DFID’s Counter Fraud and Whistleblowing Unit in the UK. Since the last annual review, Tilitonse programme has reported new frauds which are being effectively managed at both the secretariat and downstream partner levels. Lawyers have been engaged to pursue any case of fraud and claim back all funds involved in such cases. The Tilitonse board is on top of these issues and has been strict and uncompromising on tackling fraud.

The future of Tilitonse and its transition to a Foundation was a commonly agreed upon goal for the donors. The Tilitonse project has been extended until 2017 to provide time to establish the new foundation. However, there are considerable risks associated with this process that need to be carefully managed. There is a considerable risk of loss of DFID investment if the learning, evidence, processes, procedures and systems that have been established (with considerable effort and expense) under Tilitonse is not taking forward into the Foundation.

Risks pertaining to the procurement of the new IFMIS under FROIP

There are major risks surrounding: (1) the quality of the procurement process and broader implementation plans and (2) the completion of the procurement within the allocated timeframe. The quality of the procurement process is being prioritised over the speed. Many of the weaknesses in the current IFMIS stemmed from weaknesses in the procurement process and a number of mitigating measures have been put in place to avoid repeating this mistake. The contract for the new IFMIS will be scrutinised by the WB from a commercial and technical perspective. It will have clear results based payment milestones and the WB will quality assure delivery prior to payment. PFM donors are pushing for an independent third party to also review delivery.

Prior to giving a no objection to the final contract the World Bank will review the preparedness of the GoM to implement the new IFMIS. Crucial in this regard is a dedicated, fully-staffed IFMIS team to support roll out of the new system up to April 2018 and beyond. The GoM has committed itself to funding any shortfall in the budget for the new IFMIS implementation.

DFID are actively engaging with the WB, other trust fund donors and the GoM to mitigate the risks around the tight timeframe. Over the past three months a number of dialogues have taken place to generate a shared understanding of the risks and to put in place plans for ensuring successful implementation beyond the April 2018 cut-off for current donor support. As well as considering donor engagement post April 2018, attention is being given to the GoM’s own plans and resourcing. The option of extending the project is not on the table. The WB and GoM still believe that implementation is possible within the timeframe and the need for a further extension in the absence of clear extenuating circumstances would raise major questions about the GoM’s commitment to and readiness for a new IFMIS.

In December 2016 the resident World Bank technical expert acting as the task team leader for FROIP left the WBG. The WB has arranged temporary cover from the Senior Financial Management Specialist resident in Zambia and is recruiting a permanent replacement. DFID are monitoring the situation closely and have flagged our concerns to WB management to ensure that the WB maintains an adequate level of oversight. To mitigate this risk even further, DFID are exploring with the WB around the possibility of providing dedicated international IFMIS technical assistance to be embedded in the Ministry of Finance.

Outstanding actions from risk assessment

- DFID to continuously monitor government and civil society relations and use influence to protect against closing space for civil society. The situation should be carefully monitored given the current context.
- The Tilitonse board should continue to manage fraud risks tightly and ensure that all outstanding cases are concluded before the programme draws to a close.

DFID to remain continuously engaged with the Government of Malawi on strengthening Public Financial Management. Based on the extension that was granted, DFID has requested that implementation be on the basis of Payment by Results or other verifiable stages of completion.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe: Most programme components have delivered on time except for the procurement of IFMIS at the Ministry of Finance and legislative reviews, including independence of the Auditor General’s office and Audit/Financial reporting at the MoF. This has been affected by the Malawi Government’s slow procurement process and a change in the preferred supply of the system. However, through the World Bank, technical support has been provided to the ministry to ensure no further delays are encountered.

Performance of partnership (s): Partnerships with the Royal Norwegian Embassy (RNE) and Irish Aid in the Tilitonse programme have worked well. The programme has benefitted from the expertise of these partners to effectively delivery the programme outputs. Through the quarterly Board Meetings with DFID, Delivery Parters have provided oversight on Financial Management, Grants Management and Monitoring and Evaluation and Research. Committee meetings have included a closer monitoring of risks. The Programme Manager and Democratic Governance Advisor have been representing DFID at these meetings. Internally, programme risks have been monitored through monthly programme meetings and the programme risk register has been kept up to date. This has resulted in the programme management to shape their grant monitoring process and recover ineligible expenses. In addition, the two DPs agreed to exhaust their contributions and defer part of DFID’s contribution to 2017/18 in order to allow DFID respond to the humanitarian crisis. The World Bank has provided adequate support to the Ministry of Finance and Economic Development in reviewing procurement processes for Integrated Financial Management Information System (IFMIS).

DAI as a management agent of the Tilitonse programme has performed relatively well although some concerns have emerged over the years. One of the areas of the strong areas of DAI has been around financial controls and risk management. The strong monitoring system and anti-fraud policies helped to reduce cases of fraud in the programme. Where fraud happened, the programme was able to respond quickly and decisively and most funds lost to fraud were recovered. Concerns have been around the lack of support from the UK to help the staff in the secretariat handle highly technical issues such as the theory of change, PEA and capacity building for civil society. DAI staff in UK haven’t demonstrated that support to local staff as a result most of the work has been done through consultants which in the ended provided an expensive arrangement.

The Government has shown greater commitment in 2016 to implementing reforms and coordinating with donors. The GoM is producing a rolling action plan to guide the PFM reform agenda and attempts are being made to reinvigorate PFM governance structures. In 2016, the Secretary to the Treasury (ST) took a direct interest in the new IFMIS procurement; however a change of ST in February 2017 creates a risk around the continued buy-in to this process. The WB-donor partnership on the trust fund has worked moderately well in 2016. In response to donor concerns the WB have organised a series of meetings to troubleshoot issues with various WB staff. The result has been clear actions on the part of the Bank to address concerns raised.

Asset monitoring and control: Spot checks were provided to selected Tilitonse partners and ACB. It was observed that partners are managing programme assets effectively through asset registers. All assets procured through the programme were recorded on asset registers and were physically verified to be available.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

In November 2013, DFID froze all funding through the Government of Malawi’s system and there is currently no financial aid provided through any of the BEAM components. However, support has continued to some quasi-state institutions such as Malawi Human Rights Commission and the Malawi Council of the Handicapped and similar institutions through enhanced control measures including opening of dedicated accounts for the projects. The World Bank has formally agreed that no DFID funds will be disbursed through GoM accounts, even though the PFM MDTF arrangements in principle allow this. On this basis, the use of the Partnership Principles does not apply in the detailed management and monitoring of any part of the BEAM programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is no evaluation planned for the BEAM programme as a whole, largely because the numerous components included in BEAM since its inception would make it challenging to provide a single, coherent assessment of achievement. An impact evaluation was contracted for the Tilitonse Fund and was carried out on an on-going basis for the first phase of the programme by the Independent Impact Evaluation Agent (ITAD). The Impact Evaluation was completed in September, 2016 and approved by SEQAS. The two year extension to the Tilitonse fund does not include an extension to the contract of the Independent Impact Evaluation Agent (ITAD). To cover the gap, the board has approved an internal monitoring and evaluation plan which includes carrying out various case studies and documentation of results by the Tilitonse secretariat. Monitoring of individual projects has intensified with a results tracker that sends early warning of underperforming projects.

A World Bank mid-term review was carried out in September 2015, followed by a supervision mission in March 2016, an IFMIS supervision mission in June 2016, and a FROIP implementation support visit in Oct/Nov 2016 all of which have helped inform this annual review. In December 2016 a WB M&E expert visited Malawi to help the GoM develop an M&E framework for the project, although this is yet to be finalised.

Monitoring progress throughout the review period

This annual review was led by the DFID Malawi Democratic Governance Advisor, in collaboration with members of the DFID Malawi Governance and Security team and input from the BEAM programme partners. In addition to reviewing reports and documentation, as part of the review process team members visited a number of Tilitonse project sites in the north, centre and southern parts of the country during mid of January, 2017. Interviews were also held with key stakeholders (see table below). The review was peer -reviewed by the DFID Malawi peer review team and quality assured by the Governance Team Leader before being submitted to the DFID Malawi Head of Office. Programme delivery partners were consulted on a draft of the review for fact-checking purposes.

We have received feedback from a variety of stakeholders and beneficiaries.

Majority of the grantees visited talked about the mentorship support having made a great difference in their overall organisational capacity building. They felt the mentorship approach is one of the best innovations under the Tilitonse programme. However, a partner in Mchinji (CISE) expressed concern that they do not receive a clear programme of mentorship such that at the time of the visit, it was not clear when the mentors would be visiting the organisation.

Beneficiaries at local levels have appreciated how Tilitonse projects have brought different actors together to resolve common problems. A community in Phalombe where DCT and CCJP Blantyre Diocese are working under the Oxfam project said that they have been greatly empowered to hold district officials and politicians to account on development projects. Before the Tilitonse supported projects, district officials and politicians in the area did not explain how they were using LDF, CDF and DDF. They said having been empowered through the project they have followed up on a number of projects that stalled including a police unit where they found cement was stolen by the ward councillor who was at that out on bail after police arrested him following pressure from the community.

Tilitonse Project site visits

Organisation	Status	Location	Project
DCT/ CCJP (Oxfam subpartners)	NGOs/INGO	Phalombe	Enhancing Community Capacity in Tracking Development Resources and Results an Local Level.
CISE	CBO	Mchinji	Civic Engagement to Reduce Girls’ Drop out in Kamwendo and Boma zones
Kanyerere Youth Organisation	CBO	Rumphi	Promotion of Transparency Through Community Voice
Kamphenda Community Organisation	CBO	Rumphi	Strengthening Citizen Engagement in Development Activities
World Vision	INGO	Nkhata-bay	Education Governance in Sanga ADP
DCA/APW	INGO/NGO	Neno	Citizen Action in Local Governance Accountability

Acronyms used

ACB	Anti-corruption Bureau
CBOs	Community Based Organisations
CCJP	Catholic Commission for Justice and Peace
CCODE	Centre for Community Organisation and Development
CHREEA	Centre for Human Rights, Education, Advice and Assistance
CISE	Community Initiative for Social Empowerment
CMD	Centre for Multi-party Democracy
COVISODE	Common Vision for Social Development
CSOs	Civil Society Organisations
CU	Concern Universal
CVA	Citizen Voice and Action
DCA	Dan Church Aid
DCT	Development Communications Trust
DDF	District Development Fund
ECOBO	Enukweni Community-Based Organisation
ECOYA	Environmental Concerned Youth Association
FOCCAD	Foundation for Community and Capacity Development
FROIP	Financial Reporting and Oversight Improvement Project
GMIS	Grants Management Information System
GoM	Government of Malawi
HFAC	Health Finance Advisory Committees
IIEA	Independent Impact Evaluation Agent
LDF	Local Development Fund
MHRRC	Malawi Human Rights Resource Centre
MIJ	Malawi Institute of Journalism
MoF	Ministry of Finance
NAMISA	National Media Institute for Southern Africa
NAO	National Audit Office
NAYORG	Nkhadze Alive Youth Organisation
NCA	Norwegian Church Aid
NGOs Non-Governmental Organisations
PFM	Public Finance Management
RLCs	Radio Listening Clubs
RNE	Royal Norwegian Embassy
SEQAS	Specialist Evaluation and Quality Assurance Service
SWET	Story Workshop Education Trust
VFM	Value for Money
WB	World Bank
WfP	Water for People
WUSC World University Service of Canada

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process