Annual Review - Summary Sheet

Title: Institutional Strengthening of the Electoral Process (ISEP)
Programme Value: £6.3 million		Review Date: January, 2015
Programme Code: 203567	Start Date: February, 2013	End Date: March 2017

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A+
Risk Rating

Summary of progress and lessons learnt since last review

Delivery of the programme is on track and elections were successfully delivered and declared free, fair and credible by both local and international observers. ISEP made significant contributions to the success of these elections through the £3.1 million support to the UNDP Multi-donor Basket Fund which provided all sensitive elections materials and technical support to the Malawi Electoral Commission (MEC). The Issue-Based Civic Voter Education (CVE) was fully supported by this programme through the £2.4 million support to NDI. For the first time in Malawi’s elections, CVE looked beyond providing voter information for the elections to advocating for improved governance. Through issue-based CVE, Malawians were able to identify and prioritize local service delivery needs; understand formal and informal political processes that control how development and service delivery projects are allocated; and engage with and evaluate candidate positions on campaign promises in the context of local priorities. The £0.6million support to a joint DFID-UNDP Political Parties project helped political parties to strengthen inter-party dialogue, develop party policies and manifestos and use these as platforms for engagement with voters. DFID Malawi’s Policing Improvement Programme - which achieved an output score of A in its 2014 annual review - added value to ISEP though its Public Order Management component by contributing to build the capacity of the Malawi Police Service to manage public gatherings in the run up to, during and after the elections.

Key lessons relate to how best to support the MEC as the electoral management body to ensure that there are no last minute surprises in the delivery of elections. The last minute logistic challenges MEC faced would have marred the outcome of the electoral results if it were not for the role Civil Society Organisations, the diplomatic community and the UNDP led Basket Fund played in helping MEC to make pragmatic decisions and extend the voting period in constituencies and centres which experienced delayed delivery of voting materials. Coordination amongst donors supporting CVE activities also proved to be a critical issue and lessons have been learned with regard to effective coordination and coverage of districts and constituencies. Bilateral arrangements in supporting civil society organisations to carry out CVE were noted to be a serious problem as it was not easy to know which organisations were already funded by other donors and where they were working. The Political Parties Bill has shown that there are no shortcuts to issues of legislation and innovative ways to manoeuvre the bureaucratic hurdles have to be adopted.

Summary of recommendations for the next year

- The programme should adopt an electoral cycle approach for the issue-based CVE to sustain citizen interaction with elected officials.
- DFID should consider a cost extension of the CVE component of the programme which comes to an end in March, 2015 to facilitate continued engagement between voters and elected officials to ensure that campaign promises are fulfilled;
- The programme should further revise the Logframe to ensure that results relating to the CVE component are updated;
- The programme should support clear coordination of electoral reforms so that these are not dealt with in piecemeal by different stakeholders

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203567/
DevTracker Link to Log frame:

Outline of the programme

The capacity of the Malawi government and key electoral actors to deliver credible elections is still weak. Since the dawn of multiparty democracy in 1994, the Government of Malawi (GoM) has been unable to fully fund its elections due to inadequate resources and overstretched national budgets. The financial and technical capacity of the MEC to implement all its elections activities is inadequate resulting in reliance on donor support. Political Parties in Malawi are not fully established and operate with fragmented party structures and weakened intra and inter party democratic values. The Civil Society establishment lacks the financial and technical resources to play an effective role in ensuring free and credible elections. Malawi’s political system is dominated by patronage which has a negative influence on the behaviour of both voters and political agents. Patronage undermines accountability of politicians to the people and leaves the electoral system open to the influence of money, vote-buying, sectarian campaigning and other attempts to subvert the process. It is also a major cause of corruption as elected representatives often take office saddled with debt and view an election victory as an opportunity to enrich themselves.

The UK is committed to support Malawi to deliver its elections which are a necessary ingredient for its democracy. We aim to provide up to £6.3 million between February 2013 and March 2017 to support long-term institutional strengthening of the electoral process in Malawi as outlined in the DFID Malawi Operational Plan. £6.1 million of this is supporting the lead-up to the 2014 Presidential, Parliamentary and Local Government Elections, the actual elections and their immediate aftermath. Post-election support (2015/16 onwards) will be subject to the results of a post-election strategic review and the new UK HMG spending round.

The UK is delivering this support through:

Electoral-cycle support to the Malawi Electoral Commission (MEC) (£3.1 million): This support is delivered via a multi-donor basket fund managed by UNDP to support MEC to procure electoral materials such as ballot boxes, computers and ballot papers, provide human resource and technical support to MEC such as costs associated with elections temporary staff, Technical Assistants and IT equipment.

Issue-based Civic and Voter Education project (£2.4 million): This support is through an Accountable Grant to NDI to support issue-based CVE focused on the development of issue-based platforms and materials by CSOs that engage citizens around the electoral process and strengthen the relationship between citizens and government and promoting confidence in election result through statistically sound domestic election observation.

Electoral-cycle support for Political Parties (£0.6): The support is provided through DFID-UNDP joint funding to the Centre for Multiparty Democracy (CMD), an organisation run by the Political Parties to provide a forum for discussion and conflict resolution as well as a channel to provide multi-party support to strengthen Political Parties and the Political Party system.

Rapid Response fund to support unforeseen needs (£0.2): This was designed to meet important and critical needs as they arise in the electoral process up to 2014. These needs were not defined but expected to include material, technical or financial needs of the various actors within the election process.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is “2014 Elections are credible and free with public debate informing voter choices and electoral cycle support sustaining capacity in electoral process”. The outcome is measured by the following indicators: i) People who trust the Malawi Electoral Commission, ii) Majority verdict on the freeness and credibility of Malawi 2014 Elections, iii) Percentage of agreed Strategic Plan activities achieved on schedule. Based on aggregate score of the annual outcome indicators, the performance of the programme at outcome level has been A+. The 2014 Afrobarometer survey results – collected two months before Election Day - have indicated that 57% of the people have trust in the Malawi Electoral Commission and this surpasses the 55% target set for December, 2014 (Ref. http://www.afrobarometer.org/files/documents/press_release/mlw_r6_press_release2_trust_20Aug14.pdf ). Following the 20th May, 2014 elections, both international and local observers found the elections to be free and credible (Ref. Quest Number 4600758: (EU Elections Observer Mission Report), Quest Number 4600761: (SADC Elections Observer Mission Statement) and Quest Number 4600762: (Commonwealth Observer Group Interim Statement). The UNDP basket fund Quarter 2 (April-June, 2014) report shows that MEC already achieved 75% of its planned Strategic Plan activities and this meets the annual target of 75% as set out in the ISEP Logframe.

Overall output score and description

The output score of the programme is ‘A+’ on the basis that output 1, 2, and 3 with impact weighting of 50%, 10% and 20% respectively (which totals to 80%) recorded an equal rating of A+. Output 4 with an impact weighting of 20% scored ‘A++’. It is justifiable, therefore, to rate the overall output score as A+.

Output 1 scored A+: Achievement of milestone for output indictor 1.1 surpassed the set target by 20%. MEC achieved all its critical path activities leading to elections day and the post elections thereby posting a 100% achievement rate against 80% as originally planned. In terms of output indicator 1.2, MEC managed to enter into formal agreements with 107 Civil Society organisations and service providers to offer CVE, signed MoUs with all key government departments to support elections delivery as exemplified by the supply of vehicles and drivers from various ministries and departments, the Police and Military for security of voting materials and the voting process, including provision of helicopters and boats. Output indicator 1.3 focussed on reducing null and void votes. For the first time in its elections history, Malawi recorded the lowest null and void votes in all the three elections. From 4.6% in 2009 elections, the number of null and void votes in the 2014 elections reduced beyond expectation to 2.35% for local government elections, 1.43% for MPs and 1% for presidential races. This was unexpected and beats the 3.5% target set in the Logframe.

Output 2 scored A+: The milestone for indicator 2.1 substantially exceeded expectations with a 137.5% achievement rate. 11 political parties, 8 of which are CMD members, revised their party constitutions before elections day. CMD engaged a consultant who assessed political party constitutions and found that they generally align with the Political Parties draft legislation. Further to this, 5 political parties developed policy documents. 12 parties summarised their manifestoes for newspaper inserts. 15,000 copies of Chichewa and 10,000 copies of English brochures were produced for each of the political parties. 40,000 copies of newspaper inserts were produced and carried in major weekend papers.
The milestone for indicator 2.2 was fully met. Multi-party Liaison Committees (MPLCs) were reactivated in all 12 districts covered by CMD and were all active in the run up to elections. In the post elections period, Rumphi and Nsanje are the most active MPLCs holding a series of post elections meetings whereas Mzimba, Nkhatabay, Lilongwe and Dowa are less active and are yet to hold their post elections meetings. MPLCs helped to reduce tensions especially at the peak of election campaigns. MPLC activity in Thyolo where violence led to the death of a Police Officer sets a good case study of how MPLCs resolved electoral disputes. The milestone for indicator 2.3 was achieved well ahead of time in June, 2013 and therefore there was no milestone for 2014.
Example of manifestos supported by ISEP

Output 3 scored A+: The target for Indicator 3.1 was surpassed by 3 grants. The target was to award grants to 12 National Organisations and 19 Community-Based Organisations to carry out issue-based CVE in 28 districts. However, the programme awarded 3 more grants in the post elections period to promote citizen interaction and hold officials to account on their campaign promises. Achievement of the milestone for indicator 3.2 surpassed the target by a very wide margin. Due to demand for community candidate debates, the programme supported more debates and meetings than expected and this resulted into 711 meetings and debates being conducted which surpassed the annual target of 145 by a margin of 566. Achievement of the milestone for indicator 3.3 also surpassed the target. The plan was to conduct 16 parliamentary and 1 presidential debates. However due to demand and the focus on issue campaigns, the programme supported 186 parliamentary and 3 presidential debates. For the first time in Malawi’s elections history, there was more focus on issue-based campaigns and the following Feature Story is an example of the role Issue-Based CVE played in these elections: “Civic and Voter Education Produce New Hope for Road” (https://www.ndi.org/Malawi-CVE-story).

Output 4 scored A++: The milestone for indicator 4.1 was fully met. 800 Parallel Voter Tabulation (PVT) observers (740 men and 60 women) and 56 district observers were identified by March, and trained and deployed by May 2014. Their training included the voting and counting procedures, how to complete the checklist, and how to transmit data and report critical incidents to the data centre. The milestone for indicator 4.2 was fully met as 99% of the Observers transmitted data to the PVT Centre. Achievement of the milestone for indicator 4.3 surpassed target. By June 2014, MESN had released 10 press statements describing the PVT against a target of 2. These statements included descriptions of the PVT process prior to elections day, the conduct of the election, and verification of the official presidential results. The statements were published in the local daily papers as well as online media.

Key lessons
- The central lesson in the programme is that CVE should adopt an electoral cycle approach rather than be an event in the electoral process. The programme faced overwhelming demand for CVE in many constituencies but was unable to meet this demand due to the limited time to implement before the elections. With an electoral cycle approach, it will be more feasible to reach various communities with appropriate CVE messages.
- Electoral reforms need clear leadership. However, in the Malawi context, lack of leadership has derailed the electoral reforms as MEC has been looking to CSOs to lead the process when in effect the MEC should have lead the process for some of the key reforms. This shows that an early agreement on stakeholders’ role plays a very important role in coherently addressing the needed reforms.

Key actions
- DFID should consider identifying additional resources to support the Issue-based CVE cost extension. This will require spelling-out clear additional activities and timelines and delivery mechanisms. DFID needs to work NDI to achieve this and make a proposal.
- The logframe will be revised based on agreed results under the no cost extension if this is approved.
- The programme will support proper coordination of stakeholders to ensure that the reforms have clear leadership, specific timelines and expected results.

Has the logframe been updated since the last review?
The logframe was updated following observations made in the 2014 Annual Review. It will also be updated in April, 2015 following the completion of the CVE component of the programme.

Recommendations
- We recommend that the programme should turn CVE into an electoral cycle activity and allow for communities to engage with officials in the post elections period. This calls for a cost extension of the CVE component of the programme.
- DFID should consider a cost extension of the CVE component of the programme which comes to an end in March, 2015 to facilitate continued engagement between voters and elected officials to ensure that campaign promises are fulfilled;
- The programme should further revise the Logframe to ensure that results relating to the CVE component are updated;
- The programme should support clear coordination of electoral reforms so that these are not dealt with in piecemeal by different stakeholders.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Capacity of MEC to deliver elections and advocate for electoral reform increased
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones for 2014	Progress
1.1 Percentage of milestones of the electoral calendar achieved on schedule.	80%	100% by elections date. UNDP reports show that MEC had achieved all its key electoral activities by the voting day.
1.2 Progress in MEC using formalized/codified inter-institutional arrangements	MoUs or similar instruments are elaborated and signed with other government ministries	100%. By elections day MEC had signed codes of conduct and and MoUs for inter-intuitional arrangements with CSOs, Political Parties, Media, Electoral Officials, police, MDF and government departments involved in electoral work.
1.3 Percentage of null and void ballots.	3.5%	Null and void votes in presidential elections was just over 1%. Null and void votes in parliamentary races was 1.43%. Those of Local government were 2.35%. This surpasses the target by a wide margin.

Key Points
Achievement of the milestone for output indictor 1.1 surpassed the set target by 20%. MEC achieved all its critical path activities leading to elections day and the post elections thereby posting a 100% achievement rate. Although MEC faced logistical challenges on elections day where there was a delay in deployment of elections materials in some centres in Blantyre and Lilongwe, this was not attributable to failure to meet its electoral calendar. What went wrong was that MEC could not allocate adequate vehicles to deliver materials to centres in the city trusting that vehicles would be easily found on the eve of elections. This did not work and a few centres in the city had no electoral materials by the time voting started. This caused panic and riots in some of the centres. However, overall, about 99% of centres had received all the materials they needed and voting progressed smoothly. For the centre which did not have materials by the time voting started, MEC was advised to extend voting hours and in isolated cases where voting was disturbed due to riots, MEC reprinted voting materials and voting was conducted over the 3 day extension. For the future, MEC should be assisted with more vehicles and logistical experts to ensure that deployment of materials is complete before voting day. MEC should also change its recruitment criteria for poll workers to ensure that competent people are hired for the job. This will deal away with the errors on results sheets which were the basis for candidates disputing the outcome of the elections and calling for a recount. .

The achievement of the milestone for output indicator 1.2 surpassed expectation. By elections day, MEC had signed MoUs with all key stakeholders and government departments which included Malawi Defence Forces (MDF), Malawi Police Services (MPS), government departments, CSOs, Electoral Staff, Political Parties, UN Women and both local and international observers.

The milestone for output 1.3 was achieved with MEC surpassing the target of Null and Void votes by a wide margin. The percentage of Null and Void votes was set at 3.5% but this was reduce down to 2.35% for local government elections, 1.43% for MPs and 1% for presidential races. This is a significant record and beats most of elections in the Southern Africa region. While there were significant successes, the logistical capacity of MEC was a serious concern as materials in some few centres did not arrive in time for voting. This led to voters in some centres to riot and burn electoral materials.

Summary of responses to issues raised in previous annual reviews
The 2014 Annual Review recommended that MEC should re-submit the legal reform proposal on shortening the voting hours. This is now being considered alongside the on-going broad range of reforms.

Recommendations: The programme should support electoral reforms to ensure that critical issues relating to delivery of elections have been resolved.

Output Title	Capacity of Political Parties to develop issues-based electoral platforms, increase party democracy and promote reforms of the party system increased
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Member political parties’ constitutions aligned with the revised political parties act	60% of member political parties’ constitutions are harmonised with the revised PPRRA	137.5%. (11 political parties, 8 of which are CMD members) revised their party constitutions before elections day.
2.2 Number of districts where Multiparty Liaison Committees are reactivated	12 districts	100%. MPLCs were reactivated in all districts covered by CMD and were all active in the run up to elections. Rumphi and Nsanje are currently the most active MPLCs holding a series of meetings after elections and Mzimba, Nkhatabay, Lilongwe and Dowas are less active and are yet to hold their meetings after elections.
2.3 # of member political parties signing up the National code of conduct for political parties	8	All political parties who contested in elections signed the MEC code of conduct in June 2013.

Key Points
The milestone for indicator 2.1 substantially exceeded expectation with a 137.5% achievement11 political parties (8 of which are CMD members) revised their party constitutions before elections day. Further to this, five parties developed policy documents. 12 parties summarised their manifestoes for newspaper inserts. 15,000 copies of Chichewa and 10,000 copies of English brochures were produced for each of the political parties. 40,000 copies of newspaper inserts were produced and carried in major weekend papers.

The milestone for indicator 2.2 substantially exceeded expectation. MPLCs were reactivated in all districts covered by CMD and were all active in the run up to the elections. Rumphi and Nsanje are currently the most active MPLCs holding a series of post elections meetings and Mzimba, Nkhatabay, Lilongwe and Dowa are less active and are yet to hold their post elections meetings.

The milestone for indicator 2.3 was achieved well ahead of time in June, 2013 and therefore there was no milestone for 2014.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2014 Annual Review recommended that CMD should speed up passing the Political Parties Bill. The Political Parties Bill has not yet been enacted and there is hope that with the New Parliament in place which seems to be eager to pass it, the bill may be enacted in 2015.

Recommendations
CMD should use the Legal Affairs Committee and Private Members Bill to table the bill in Parliament.

Output Title	CSOs better able to deliver issue-based civic and voter education programmes and stimulate public debate
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2014	Progress
3.1 Number of local organizations participating in program and providing CVE.	31	31 organisations continue to be funded and participate in CVE. 3 more organisations were awarded grants in the post elections period.
3.2 Number of townhall /issue-based public information campaigns completed by civil society partners	145: Partner activities, including candidate-community meetings, community debates on issues, creation of candidate and community manifestos, dissemination of voter education materials, radio programming and theatre	711 partner activities including candidate-community meetings, community debates on issues, creation of candidate and community manifestos, and dissemination of voter education materials, radio programming and theatre were conducted.
3.3 Number of candidates debates conducted	16: Parliamentary and/or local candidate debates organized. 1 National Presidential debate organised	186 parliamentary and debates were organized by ISEP partners and this surpassed the milestone by a very wide margin. / 3 National presidential debates were organized and aired and this surpassed the original milestone of 1 debate.

Key Points
The target for Indicator 3.1 was surpassed by 3 grants. The programme awarded grants to 31 organisations prior to elections to implement Issue-Based CVE and 3 more grants in the post elections period to promote citizen interaction hold officials to account on their campaign promises. Achievement of the milestone for indicator 3.2 surpassed the target by a very high margin. Due to demand for community candidate debates, the programme supported more debates and meetings than expected and this resulted into 711 meetings and debates being conducted which surpassed the annual target of 145 by a margin of 566. Achievement of the milestone for indicator 3.3 also surpassed the target. The plan was to conduct 16 parliamentary and 1 presidential debates. However due to demand and the focus on issue campaigns, the programme supported 186 parliamentary and 3 presidential debates. NDI Feature Story: Civic and Voter Education Produce New Hope for Road (https://www.ndi.org/Malawi-CVE-story)
Presidential candidates’ debates

Summary of responses to issues raised in previous annual reviews (where relevant):
None

Recommendations: We recommend revision of the output and recasting results to include continued engagement between voters and elected officials to ensure campaign promises are implemented. This means the CVE component should have a cost extension.

Output Title	Civil society better able to monitor 2014 elections and speak out against cases of electoral malpractice
Output number per LF		4	Output Score	A++
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2014	Progress
4.1. Number of citizen observers trained on how to conduct a PVT (disaggregated by sex and age).	800, number of PVT Observers, 56 district observers	800 PVT observers (740 men and 60 women) and 56 district observers were deployed. This represents 100% achievement rate.
4.2 Percentage of observers that transmit data to a central information center, including the vote count from randomly sampled polling stations on election day	99.1% observers deployed successfully transmit their data on election day	99% of observers transmitted data
4.3 Number of public statements that civil society partners issue using PVT analysis;	2: number of statements issued. / 2: number of press conferences	10 press statements and 2 reports / 4 press conferences

Key Points
The milestone for indicator 4.1 was fully met. 800 PVT observers (740 men and 60 women) and 56 district observers were identified by March, and trained and deployed by May 2014. Their training included the voting and counting procedures, how to complete the checklist, and how to transmit data and report critical incidents to the data centre. The milestone for indicator 4.2 was fully met as 99% of the Observers transmitted data to the PVT Centre. Achievement of the milestone for indicator 4.3 surpassed the target. By June 2014, MESN had released 10 press statements for the general public describing the PVT process. These statements included descriptions of the PVT process prior to elections day, the conduct of the election, and verification of the official presidential results. The statements were published in the local daily papers as well as online media.

The PVT was used to allay fears of rigging that escalated due to delays in announcing results. Electoral stakeholders used the PVT statistically analysed results to compare with official results and it proved that elections were not stolen. This helped to calm down fears of rigging and led to acceptance of the outcome of elections. The A++ rating reflects how, in the difficult aftermath of the elections when the results were being contested, the delivery of PVT became a game changer which facilitated the acceptance of the officially declared election outcome by both the public and those running for office.

Summary of responses to issues raised in previous annual reviews (where relevant)
None.

Recommendations
The PVT should continue to be discussed during the electoral reforms and be adopted as one of the key areas that can enhance credibility of electoral results. Legal framework enabling PVT should be put into place

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

During the period under review the key cost drivers in the programme were:
- The fall of the Malawi kwacha
- Rising fuel costs for all programme partners
- International procurement of sensitive elections materials such as ballot papers
- Adjustment of honoraria for temporary elections staff
- Registration of voters and production of voters roll

VfM performance compared to the original VfM proposition in the business case

The ISEP Business Case (BC) proposed key measures of VfM for elections and the assessment points to a very positive outcome:

Cost of elections per voter: The BC proposed that the unit cost per voter for the May 2014 elections will not be more than an average of $5.08 (based on a research study in 34 countries in the World) [1]. The 2014 elections achieved a cost per voter of $5.1. This is within the expected costs and shows that the costs were contained and VfM was achieved.
[1] Lopez-Pintor, J. and Fischer, J., (2005) “Cost of Registration and Elections (CORE) Project”, IEFS

Cost of post-election violence: The BC also proposed to measure VfM by the economic cost of violence. Where there has been post-elections violence, economic growth has usually slowed. In Kenya for example, between 2004 and 2007, the country had registered growth rates of between 5.1 and 7.1%. However following elections violence, in 2008, the rate of growth was just 1.7% (and 2.6% in 2009). For Malawi, elections were free and credible with no major incidences of violence. The 2014 growth rate was 6.1% and this is expected to slightly rise to 6.2% in 2015 (http://www.africaneconomicoutlook.org/en/countries/southern-africa/malawi/). The peaceful nature of the elections which this programme has contributed to in no small measure, has helped to keep the economy stable. In principle the programme has achieved VfM.

Cost savings due to early tender and competitive bidding: This programme contributed £3.1million to the UNDP basket fund. The basket funds were used largely for international procurement. Through early tendering and using UNDP procurement procedures, the basket fund was able to save almost £1.5million in international procurement.

Use of donor harmonised rates: Donor harmonised rates were applied to all field trips for project partners except in one case where a waiver was obtained. This was to facilitate the deployment of elections observers whose job was deemed risky and therefore slightly higher rates were used for their allowances and honoraria.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money. The team scrutinizes partner financial reports and does not make disbursements until it is fully satisfied with financial and narrative reports and work plans submitted. Coordination of activities and adherence to donor harmonized rates has supported the achievement of value for money.

Quality of financial management
Generally financial management for ISEP has been good. The programme improved the financial oversight of implementing partners by reviewing financial reports from all its partners and comparing the progress against the narrative progress reports. Each partner is being audited annually. Audit reports are discussed and improvements are agreed with clear action plans.

Date of last narrative financial report	NDI: 30/09/2014 / UNDP/CMD: 30/09/2014 / UNDP: 30/09/2014
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Low/Medium/High
The programme entered the review period with an overall risk rating of medium. Coming to the end of the review period, with the elections delivered, this risk has reduced to low.

Overview of programme risk
Currently there are 6 active risks of which 3 are political, 2 fraud and corruption, 1 partner delivery and 1 reputational. The general rating is medium. We have rated one risk as high which is an “external risk” related to Federalism and electoral system debates. Soon after elections in May, 2014, some quarters of the society including MPs from two opposition parties in parliament started to call for a Federal System of Government. Since then Federalism debates have taken centre stage. This, we fear, may derail the focus on needed electoral reforms which ISEP is supporting jointly with other donor programmes. Related to this is a medium risk which about political party inter-party cooperation breaking down within the process of electoral reforms. This if it happens, it will have the effect of stalling electoral reforms and closing the door to the possibility of these reforms being passed in parliament if they get submitted at all.

Outstanding actions from risk assessment
The programme reviewed its risks in November, 2014 and retired 9 of the 16 risks. The 9 risks were directly related to elections day and were retired following the successful elections held on 20th May, 2014. During the revision, we added two new risks, i) Lack of direction and leadership to implement electoral reforms to address the range of problems that affected the electoral process for the 2014 elections and ii) Federalism and electoral system debates affecting the direction of needed electoral reforms. We are closing monitoring and re-assessing these and the other four risks ensuring that the programme is not affected in any negative way.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Generally, the programme is on track to deliver all planned work and results. The programme adopted an electoral cycle approach and will still be live till March, 2017. The different components of the programme have different end dates. The Issue-Based CVE component which is being implemented by NDI and was supposed to close on 31st December, 2014 has been extended to March 31, 2015. This extension was duly approved by the Head of Office and was necessary to allow for NDI to properly close new sub-grants which were awarded after the elections with the aim of enhancing citizen interaction with elected officials. The extension was also necessary due to the change in the evaluation approach which took time to be agreed.

Performance of partnership (s)
All partners have performed well. UNDP who leads on the Basket Fund to which ISEP contributes £3.1million acted effectively to ensure that all sensitive electoral materials were delivered on time for the elections. Through its procurement systems, materials were delivered three weeks before elections and this was highly commendable. CMD which is a partner for the Political Parties component, performed well especially in supporting political parties to develop their party policies and manifestos which were summarised and publicised in key newspapers. NDI, which implements the CVE component, was outstanding in the way they implemented the PVT. The PVT proved very vital in allaying fears of rigging as stakeholders were able to verify the outcome of the elections through PVT statistically computed results.

Asset monitoring and control
DFID conducts assets checks on partners regularly and gets updates through management meetings and asset registers which partners send to DFID every year. DFID approves procurement of new assets through formal requests which are followed by consultations and discussions to obtain clear justification for additional assets. Disposal of assets is also negotiated and approved by DFID. The last assets check was in February, 2014 and the next is expected at the end of the project in March, 2015.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

While we supported Malawi’s tripartite elections, DFID support did not go through government systems or any of its departments or institutions. The support to MEC was exclusively through UNDP systems and largely involved international procurement of electoral materials. Partnership Principles were not originally used in the ISEP Business Case and since DFID is not providing any financial aid, the use of the Partnership Principles does not apply in the detailed management and monitoring of the ISEP.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The BC suggested two evaluations, one after the 2014 elections to assess outcome level results, and one after the end of the programme to assess outcome and impact level results. That changed with the the evaluation appraisal done after approval of the BC which proved that an evaluation is not needed for the entire programme. However, because of its new approach, the Issue-Based CVE implemented by NDI would benefit from evaluation and this is being done now with results expected at the end of January. The purpose of this evaluation is to “check whether voting patterns changed significantly from previous trends (national presidential and parliamentary) and identify factors that contributed to this change”. Generally, evidence for some of the indicators has been drawn from various sources including Afrobarometer surveys and the Moi Ibrahim foundation.

So far new evidence has been gathered from the 2014 Afrobarometer results which show that 57% of the public trust Malawi Electoral Commission and this is against the projected 55% according to the Logframe. The Null and Void votes have been computed from MEC’s own elections results record and show that Null and Void votes have significantly reduced. Both local and international observers have already declared Malawi elections free and credible (Ref. Quest Number 4600758: (EU Elections Observer Mission Report), Quest Number 4600761: (SADC Elections Observer Mission Statement). Quest Number 4600762: (Commonwealth Observer Group Interim Statement).

Monitoring progress throughout the review period
Progress is being monitored regularly through quarterly progress and financial reports. Management meetings are also held which focus on progress and how finances are being used. Reports and information from meetings are checked and verified through field visits which are done over the year. The field visits provide an opportunity for the DFID team to hear real stories about the progress being made and direct feedback from beneficiaries. Examples of feedback from beneficiaries include:

From political party presidential candidates: Those who participated in the debates have recognized the importance of the debates to their campaigns. Lazarus Chakwera, a popular candidate from the MCP and leader of the opposition following the elections, commented that he “was happy to witness history in the making and was proud to be part of the history.” Helen Singh, a candidate from one of the less popular parties, noted, “the debates helped me to get the votes I never dreamt I would get. For sure, many people did not know me but the debates sold me and I got a considerable number of votes.”

Village Development Committee Chair in Chingale Zomba: “Initially we were unaware that we have the power to summon our MP or councillor to question them on campaign promises, but now we feel so empowered and understand that elected officials are pretty much like our servants…they are not our boss like we thought, we have all the power to hold them accountable, our plans are to continue engaging them throughout their term of offices to ensure the priority issues identified are followed through.”

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process