## Sheet1
PROJECT NAME | SAFERWORLD PPA: EXTENSION PERIOD 2014-2016
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Target
A reduction in violent conflict and insecurity in Saferworld (SW) target countries | No. of communities targeted by SW in which people report reduced levels of insecurity (and a description of the characteristics, size and relevance of these communities) | Planned | High levels and perceptions of insecurity in SW target countries. | Evidence of reduced insecurity (from security perception surveys, focus groups, crime statistics, media reports etc as available) in 3 target communities | Evidence of reduced insecurity (from security perception surveys, focus groups, crime statistics, media reports etc as available) in a total of 8 target communities
Achieved
Source
Existing (and planned) participatory conflict analyses and security perception surveys; crime statistics; media reports.
OUTCOME | Outcome Indicator 1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumptions
Individuals and communities, civil society, authorities and external actors strengthen their approaches and capacities for preventing violent conflict, building peace and addressing the needs of conflict-affected (or at risk) communities, (in accordance with Saferworld's organisational change model - see annex), in Bangladesh, Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sudan, South Sudan, Uganda, Yemen | Number and description of community action groups that have the skills, confidence and capacity to take collaborative action to counter threats to security and build peaceful communities (see notes below) | Planned | This is a revised, improved indicator so we do not have an exact baseline for this indicator. Between March 2011 and March 2013, 29 community groups were formed. During this period we did not specifically measure their skills, confidence and capacity to take collborative action to counter threats to security and build peaceful communities. | 25 (additional) groups have skills, confidence and capacity to take collaborative action. | A total of 30 groups over the two years. | Overall assumptions: Context in SW’s target regions and countries does not deteriorate to the point where policies and practices cannot be developed or sustained. Sufficient will and capacity among stakeholders to develop conflict and security policies and practices. In many cases, developing this will and capacity is an integral element of SW's programming. There is sufficient political space and opportunity for CSOs to engage on conflict and security issues without facing undue risk National authorities have a sufficient level of political will and openness to change upon which SW can build, and are not overcome by contradictory interests such as corruption, political advancement etc Local authorities are able to work in collaboration with communities on peace and security issues (ie. they are not prevented from doing so by national policies or institutional mandates) SW maintains sufficient operational capacity to deal with the operational and security challenges encountered in SW target areas SW target areas remain a sufficiently high priority to the extent that support and interest for working in them is not diminished by developments in other areas (such as a renewed focus on Afghanistan, developments in the Middle East/North Africa, etc.)
Achieved
Source
Community security actions plans; agendas and minutes from meetings of community groups and local authorities; focus groups and interviews with community members and authorities; interviews with SW staff; SW and partners' conflict analysis and baseline surveys; national / local crime and violence statistics (where available); independent project evaluations
| Outcome Indicator 2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
| Number and description of civil society organisations (CSOs) that have increased capacity to influence authorities and hold them to account | Planned | Between March 2011 and March 2013, 9 CSOs increased their capacity to influence authorities and hold them to account | 10 additional CSOs have increased capacity to influence authorities and hold them to account | A total of 15 CSOs over the two years
Achieved
Source
Civil society capacity assessments; CSO strategies and CSO outputs and activities such as research papers, policy analysis, and advocacy ; focus groups and interviews with civil society representatives; interviews with SW staff; SW project documents; independent project evaluations
| Outcome Indicator 3 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
| Number and description of authorities who develop new and/or significantly improved practices, approaches and/or policies that directly respond to and mitigate conflict (see notes below) | Planned | Between March 2011 and March 2013, 13 authorities developed new/significantly improved practice/ approaches / policies | 15 additional authorities develop or significantly strengthen their practices, approaches and / or policies | A total of 20 authorities over the two years
Achieved
Source
Policies, strategies, guidelines and practices of governments and other relevant institutions; interviews and focus groups with officials; interviews with SW staff; project documents; independent project evaluations
| Outcome Indicator 4 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
| Number and description of external actors (including donors and multilateral agencies) who take up SW (and partners') recommendations on policy and practice in conflict-affected states | Planned | Between March 2011 and March 2013, 27 external actors took up SW and partners' recommendations on policy and practice in conflict-affected states | 16 additional external actors take up SW and partners' recommendations | A total of 28 external actors over the two years
Achieved
Source
Policies, strategies and official policy pronouncements of governments, donor agencies and multilateral institutions; interviews with representatives of governments and multilateral agencies; interviews with SW staff; SW project documents;independent project evaluations
| Outcome Indicator 5 |  | Baseline | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
| Number and description of Saferworld country programmes that have begun to include gender perspectives in their planning (including conflict analysis), and in doing so increase the potential for their interventions to impact positively on gender mainstreaming and gender-based violence | Planned | Some strong on the ground projects with a gender focus, particularly MENA and Nepal | Gender-sensitise our own programming across the board to take into account gendered causes and consequences of conflict and violence | Evidence base built around gender as a driver of conflict and violence and how peacebuilding interventions can address it
Achieved
Source
Guidance for gender-sensitive conflict analysis produced; Context-specific evidence and analysis on whether and where gender acts as a driver of conflict to be used to conduct advocacy with relevant actors; Evidence of how to effectively prevent and respond to gender-based violence through community-security programming; Saferworld country strategic plans; SW and partners' conflict analysis and baseline surveys; independent project evaluations
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumption
SW and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities (Y2011-2014 in Caucasus, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan; 2014-2016 in Bangladesh, Caucasus, Kyrgyzstan/Tajikistan, Nepal, South Sudan and Yemen) | Number of action-oriented community groups formed (and continually supported) by members of conflict-affected communities - with SW support - through which communities can identify their security related needs and priorities, and develop a shared purpose and vision for change (see notes below) | Planned | Between March 2011 and March 2013, 29 community groups were formed | 15 additional action-oriented community groups formed | A total of 20 groups formed over the two years | Members of conflict-affected communities are willing to form groups through which to identify their security and justice needs and develop a shared vision for change; getting to this stage will in some cases require careful relationship-building and negotiation, if community members perceive each other to be contributors to local insecurity and conflict Communities are willing to meet, and discuss working with, local authorities to address peace and security issues - in some areas developing this willingness may require significant investment if local authorities are (or are perceived to be) a contributor to local insecurity and conflict Local authorities are willing to meet, and discuss working in collaboration with, communities on peace and security issues (ie. they are not prevented from doing so by national policy) Where such willingness exists on both sides, communities and local authorities consider peace and security issues a high priority which needs to be dealt with collaboratively The conflict and security context in target countries and communities does not deteriorate to the point where it becomes impossible to engage meaningfully with communities or authorities
Achieved
Source
Community groups' terms of reference / documents of establishment; minutes and attendance lists from meetings of community groups; interviews with members of community groups and SW staff; independent project evaluations
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
25% | Number of groups that successfully implement community security action plans, in dialogue with authorities, with support from SW and partners | Planned | Between March 2011 and March 2013, 25 groups successfully implemented plans, in dialogue with authorities | 30 additional groups successfully implement plans | An overall total of 33 groups have successfully implement plans over the two years
Achieved
|  | Source |  |  |  | RISK RATING
|  | Minutes and attendance lists from meetings of community groups and local authorities; interviews with members of community groups and local authorities and with SW staff; independent project evaluations |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumptions
In Bangladesh, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sudan, South Sudan and Yemen, local civil society organisations receive support from SW to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts. | Number of local CSOs that receive targeted and tailor-made high-quality training / capacity-building from SW on how to effectively advocate for improved approaches and / or greater accountability from authorities and policymakers, building on the view of their constituents (in Kyrgyzstan/Tajikistan, Kenya, Kosovo, Somalia, Sudan and Yemen) | Planned | Between March 2011 and March 2013, 11 CSOs received high-quality training / capacity building from SW on a range of areas including advocacy (the previous indicator covered all types of training / capacity building, whereas this revised indicator has been refined to focus on a particular aspect of SW's work). This indicator previously focused on Kyrgyzstan/Tajikistan, Uganda and Yemen, so these are the countries captured under this baseline. | High quality, tailor-made training / capacity-building provided to 23 additional CSOs | Total of 34 CSOs have received training / capacity building over the two years. | SW can identify a sufficient number of CSO partners in target areas who perceive a need to prioritise working on conflict and security issues Training and capacity-building of CSOs on conflict and security issues is not considered too political or threatening by national and local authorities There is sufficient political space and opportunity for CSOs to engage on issues on conflict and security issues without facing undue risk National and international governments and multilateral agencies are willing and have the opportunity to engage in meaningful dialogue with CSOs - this will in part be dependent on political will but also on project planning cycles and the existence and promotion of consultation processes
Achieved
Source
Training materials and curricula; capacity-building needs assessments and plans; reports of training workshops and capacity-building processes (including participant evaluation forms); interviews with members of CSOs and with SW staff
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
25% | Number of local CSOs that receive training and mentoring from SW on how to support communities to identify and address their conflict / security related needs and problems (in Bangladesh, Kyrgyzstan/Tajikistan, Nepal, Pakistan, South Sudan and Yemen) | Planned | Between March 2011 and March 2013, 9 CSOs received high-quality training and mentoring of this kind from SW | 20 additional CSOs have received training and mentoring from SW | A total of 21 CSOs over the two years
Achieved
|  | Source |  |  |  | RISK RATING
|  | Minutes of meetings and other fora through which CSOs contribute to policy processes; CSO policy briefings / recommendations provided to policy-makers; CSO activity reports; interviews with CSOs and policy-makers and with SW staff; independent project evaluations |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumptions
National and/or subnational authorities receive support from SW and partners to assist them in developing effective policies and practical approaches for building peace, justice and security | Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the national level, in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen) | Planned | Between March 2011 and March 2013, 11 authorities received quality technical input and/or support from SW. This was in Kenya, Kosovo, Nepal and South Sudan (the countries previously included under this indicator, which did not distinguish between national and subnational authorities). | SW has provided quality technical input and/or support to 6 additional authorities at the national level | A total of 11 authorities at national level over the two years | Governments in Bangladesh, Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen initiate and commit to relevant policy processes related to conflict and insecurity, which SW perceives as having at least a reasonable potential to effectively address key issues in their country and with which SW is willing and able to engage with and seek to improve. Governments and institutions request, or willingly agree to, SW technical support in the area of policy development and in terms of developing their practical approaches to addressing conflict and insecurity SW is able to gain sufficient access to, and response from, governments and institutions to enable meaningful engagement on the review of policies and practices The context in these countries does not deteriorate to the point that policy processes are unravelled or institutions cease to function meaningfully
Achieved
Source
Written SW analysis, policy recommendations and technical submissions; MoUs between SW and institutions; minutes and reports of meetings between SW and policy-makers; interviews with policy-makers and SW staff; independent project evaluations
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
20% | Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the sub-national level in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Bangladesh, Caucasus, Kenya, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen) | Planned | Between March 2011 and March 2013, 11 authorities received quality technical input and/or support from SW. This was in Kenya, Kosovo, Nepal and South Sudan (the countries previously included under this indicator, which did not distinguish between national and subnational authorities). | SW has provided quality technical input and/or support to 14 additional authorities at the subnational level | A total of 18 authorities at subnational level over the two years
Achieved
|  | Source |  |  |  | RISK RATING
|  | Written SW analysis, recommendations and technical briefs; MoUs between SW and institutions; reports of training workshops and other meetings through which technical advice and support is provided; interviews and surveys with staff from targeted institutions (incl. post-hoc feedback) and with SW staff; independent project evaluations |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumptions
External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries | Number and quality of research papers and policy briefings / reports published or electronically circulated by SW and disseminated to external actors | Planned | Between March 2011 and March 2013 SW published and/or electronically circulated 136 research papers and policy briefings / reports | 42 additional briefings, papers / reports have been published or electronically circulated | A total of 86 briefings, papers / reports over the two years | SW is able to conduct participatory research and analysis, as a basis for its policy briefings and papers, in the countries where we work. This is dependent on the context in these countries and the political space for NGOs and local partners to undertake local-level and participatory research and consultation with communities. External actors continue to request, or enthusiastically respond to suggestions regarding, SW training and capacity-building on engagement in fragile and conflict-affected countries
Achieved
Source
SW research papers, policy briefings and reports; SW website and publications list; SW dissemination lists; interviews with SW staff and with recipients of SW papers / briefings / reports
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
20% | Number of external actors (disaggregated by gender) receiving relevant, high quality training from SW, or participate in relevant and productive SW-facilitated seminars / roundtables, on engagement in fragile and conflict-affected countries | Planned | Between March 2011 and March 2013, 1,824 external actors have received training from SW or participated in SW-facilitated seminars / roundtables on engagement in fragile and conflict-affected states | 1,850 additional external actors have received training or participated in SW-facilitated seminars / roundtables | A total of 1,900 external actors over the two years
Achieved
|  | Source |  |  |  | RISK RATING
|  | Training materials and curricula; reports of training workshops; participants lists and participant evaluation forms (incl. post hoc evaluations and feedback, 3 - 6 months after event); interviews with trainees and with SW staff; independent project evaluations which include an assessment of relevance and quality of trainings and roundtables |  |  |  | Low
| Output Indicator 4.3 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
| Number and quality of products (including briefings and submissions) provided to the UK Government by SW, which build on evidence and lessons learned from SW programme implementation | Planned | Between March 2011 and March 2013, SW has provided 9 products building on evidence and lessons learned from SW programme implementation to the UK Government | The UK Government has received 6 additional products building on evidence and lessons learnt from SW's programming | The UK Government has received a total of 13 products over the two years
Achieved
Source
SW documents and evaluations; SW products and briefings produced over the programme period for DfID; DfID staff interviews; independent project evaluations
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016) | Assumptions
SW incorporates new elements into its MEL system including an Outcome Mapping, Monitoring and Harvesting approach and trials a more systematised beneficiary feedback mechanism | Number of teams collecting and reviewing outcomes on a quarterly basis | Planned | SW has a Programming and Monitoring Framework, and is rolling out an Outcome Mapping, Monitoring and Harvesting approach across the organisation. This is allowing SW to learn from and adapt its programming approaches, and contributing to understanding how to evaluate influencing. | 50% of SW teams are collecting and reviewing outcomes on a quarterly basis | SW has an integrated approach to harvesting outcomes and testing them through review and evaluations 100% of SW teams are collecting and reviewing outcomes on a quarterly basis | SW is able to access relevant data to enable robust M&E and reporting, and is not prevented from doing so by serious deteriorations in the conflict context in target countries or by insurmountable difficulties in collecting necessary data from national and local authorities and institutions in the countries where SW wiorks SW's donors continue to support the development of M&E capacities and systems DFID continues to recognise the importance of adopting an approach to M&E which promotes and enables genuine learning and supports application of this learning at local and community level, and which places a strong emphasis on incorporating beneficiary perspectives of what constitutes success in their particular context
Achieved
|  | Source |  |  |  | RISK RATING
|  | SW M&E tools, policies and framework; outcome reports; SW reports against the logframe; SW lessons learned documents and evaluations |  |  |  | Low
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline - based on achievements during 2011-13 | Milestone 1 (achievements to date, March 2014 - March 2015) | Target (overall achievements March 2014 - March 2016)
10% | The number of partners and community action groups that participate in setting outcomes for their work and provide feedback on the changes they are seeing as a result of working with Saferworld. | Planned | SW is currently trialling this approach in Nepal, Yemen, South Sudan and Bangladesh. | At least 12 community action groups are participating in setting outcomes for their work, monitoring them and reporting on them. | Based on experiences to date in trial communities, SW reviews its beneficiary feedback approach, learning from the challenges in implementing it, and adjusts it for further roll out.
Achieved
Source
Partner and community evaluations of community action plans; participatory M&E tools; outcome reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Notes:
Outcome indicator 1: 'Collaborative action' refers to action that is undertaken by members of the community working together and - in most cases - working with security providers and / or other local officials; in some cases it also refers to a number of communities coming together to solve a shared problem that they have jointly identified, including communities divided by conflict.
Outcome indicator 3: The specific types of improvement that are needed to policies, practices and approaches are determined and monitored at the programme level, and depend on the context and existing weaknesses. SW is looking for evidence of factors such as strong provisions for accountability, involvement of the public in determining the content of policy or nature of practice, effective implementation of commitments, and relevance to context and needs.
Output indicator 1.1: 'Action-oriented community groups' refers to groups - comprising community representatives and in most cases working with security providers and / or other local officials - that are identifying problems faced by the community and taking concrete action to address them.