Type of Review: Annual Review

Project Title: Transparency International Programme Partnership Arrangement (PPA)

Date started: 01 April 2012	Date review undertaken: 30 June 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK, through the Department for International Development (DFID), is investing in a 3 year Programme Partnership Arrangement (PPA) with Transparency International between 2011 and 2014. An investment of £3,374,344 for each year has been agreed (£2,670, 269 per year for the general PPA and £704,075 for the CHASE PPA). This type of strategic investment can leverage much greater impact than traditional project funding by playing a key role in shaping how Transparency International uses its non-DFID resources.

What are the expected results?
The results that investment in the general PPA is expected to deliver are: / Evidence developed on corruption issues / Citizens supported to address corruption and promote integrity by increasing the number of Advocacy and Legal Advice Centres globally, from 60 to 75. This is also supported by increasing the number of Development Integrity Pacts (DIPs) between organisations of disadvantaged citizens and public institutions charged with the delivery of public goods and services from 61 to 105 / Positively influencing external stakeholders keeping the number of press statements annually at 50 statements. Influence will also be made by increasing the number and description of TI documents with recommendations on Anti-Corruption practise and policy annually. / Strengthening the capacity of the TI movement by increasing the number of cooperative projects within the movement coordinated by TI-S with a minimum target of 30 projects. 90 TI-S National Chapters globally will be trained in corruption and integrity issues. / It should be noted that TI-S are currently gathering additional baseline, milestone and impact data which will set out agreed quantifiable targets and clear indicators to measure progress. / Through the CHASE PPA, TI-Defence and Security Programme (DSP) expects to: / Support nine countries to develop defence integrity or counter-corruption programmes, with a particular focus on conflict or unstable environments / Influence at least 25 states and five national defence industry umbrella organisations to support the inclusion of an anti-corruption mechanism in the UN Arms Trade Treaty (ATT) / Deliver six practical tools to enable governments, companies and at least twenty civil society organisations to address defence and security corruption / Support international organisations such as the UN, AU, EU, World Bank and NATO to deliver six defence integrity or counter-corruption initiatives. (Reported on under Outcome 4 and Output 4 in the Annual Review Self-Assessment provided by TI-DSP but no details covered here in this joint CHASE – CSD Annual Review document.)

What is the context in which UK support is provided?
Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / To achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral and multi-pronged approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs and following a robust selection process and implementation of a Resource Allocation Model, partners were identified for a 3 year PPA which began in April 2011.

## Section A: Detailed Output Scoring

General PPA - Output 1: To develop evidence on corruption issues
Output 1 score and performance description: / B Outputs moderately did not meet expectation
Progress against expected results: / Indicator 1: research publications produced by TI-S received significant uptake by the public but also by the target groups directly. However due to prioritizing comprehensive and high-impact research outputs in the reporting year, TI-S has not met the milestone for the first indicator. / Indicator 2: provided support on a wide range of publications produced by national chapters. Training, technical assistance, development the methodology, along with methodological and quality control are among the core functions of TI. Did not meet milestone for the second indicator. This is explained by the fact that a range of reports which were planned to be finalised between April and December 2012 were already published in the first quarter of 2012 / Indicator 1.1 Number and description of TI-S research publications / Baseline 11 (2010) / Milestone 2011/12 2012/13 2013/14 / 11 11 11 / Achieved 11 9 / Variance 0 -2 / Disaggregated data* N/A N/A / *– expand number of rows if needed / Indicator 1.2 No and description of TI National Chapter research publications supported by TI-S / Baseline 25 / Milestone 2011/12 2012/13 2013/14 / 25 25 25 / Achieved 62 18 / Variance +37 -7 / Disaggregated data* N/A / *– expand number of rows if needed / Recommendations: / Reduce the 2013/14 milestone for indicator 1 from 11 to 10. / 2013/14 milestone for indicator 2 to remain unchanged / Impact Weighting (%): / 25% / Revised since last Annual Review? / No / Risk: / No / Revised since last Annual Review? No

General PPA - Output 2: To support citizens to address corruption and promote integrity
Output 2 score and performance description: / B – moderately did not meet expectations
Progress against expected results: / One milestone has been met, but the other failed to meet the milestone by more than 50%. / Significant achievements were made in supporting people around the world to access simple and viable solutions that would help them to be both informed about their options when faced with corruption, and to be able to report it. However only 38 Development Pacts confirmed. / Indicator 2.1 Number of Advocacy and Legal Advice Centres globally / Baseline 60 (January 2011) / Milestone 2011/12 2012/13 2013/14 / 65 70 75 / Achieved 71 88 / Variance +6 +18 / Disaggregated data* / *– expand number of rows if needed / Indicator 2.2 Number of Development Pacts globally / Baseline 61 (21.03.2011) / Milestone 2011/12 2012/13 2013/14 / 75 (March 2012) 90 (March 2013 105 (March 2014) / Achieved 80 38 confirmed / Variance +5 52 / Disaggregated data* 27 Bangladesh, 11 Uganda / *– expand number of rows if needed / Recommendations: / TI proposing to replace indicators. This is being reviewed by DFID. / Impact Weighting (%): / 25% / Revised since last Annual Review? / No / Risk: / Low / Revised since last Annual Review? / No

General PPA - Output 3: To reach out to and influence external stakeholders
Output 3 score and performance description: / ‘A+’ - moderately exceeded expectations
Progress against expected results: / First indicator exceeded by 364%. TI’s recommendations continue to gain traction by media, policy makers and the wider public. In this reporting year they have become better at using new media tools to reach wider audiences. / Indicator 3.1 Number of page views of the TI Space for Transparency Blog / Baseline 94,077 (2010) / Milestone 2011/12 2012/13 2013/14 / 150.000 (2011) 165,000 (2012) 181,000 (2013) / Achieved 175.539 600,096 / Variance 25.539 435,096 / Disaggregated data* / *– expand number of rows if needed / Indicator 3.2 Number and description of TI document with recommendations on Anti-Corruption practise and policy annually / Baseline 14 (1.4.2010 – 31.3.2011) / Milestone 2011/12 2012/13 2013/14 / 14 14 14 / Achieved 16 14 / Variance +2 0 / Disaggregated data* / *– expand number of rows if needed / Recommendations: / Increase the 2013/14 milestone for first indicator to 500,000, particularly as this year’s milestone was exceeded by 364%. / Need to up-date the logframe with the actual milestones for second indicator for years one, two and three and the achieved figure for the 2012/13 milestone. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

General PPA - Output 4: To strengthen the capacity of the TI movement
Output 4 score and performance description: / ‘A++’ - substantially exceeded expectations
Progress against expected results: / TI has continued to expand activities supporting the capacity development of Chapters. A Small Grant Programme, partly funded by PPA support, has continued to serve as an effective channel for strengthening Chapter capacity, and has supported 27 Chapter-specific and 8 horizontal learning initiatives. In the reporting period, TI focused its support under Output 4 in the areas of capacity assessment, strategic planning and financial sustainability. / Indicator 1.1 Number of capacity development activities implemented by TI Chapters with Secretariat support / Baseline 10 (2010) / Milestone 2011/12 2012/13 2013/14 / 15 (March 2012) 20 (March 2013) Minimum 25 (March 14) / Achieved 17 43 / Variance +2 +23 / Disaggregated data / Recommendations: to increase the 2013/14 milestone. / Indicator 4.1 Number of trainings organised by TI-S for Chapters / Baseline 25 / Milestone 2011/12 2012/13 2013/14 / 25 25 25 / Achieved 26 34 / Variance +1 +9 / Disaggregated data / Impact Weighting (%): / 25% / Revised since last Annual Review? / No / Risk: / Low / Revised since last Annual Review? / No

CHASE PPA – Output 1: Conduct high level governmental workshops and events addressing Defence and Security Reform best practice and initiatives worldwide, including in Southeast-Asia, Africa, and wherever in the world governments express an interest.
Output 1 score and performance description: / A+ Outputs moderately exceeded expectation / Progress against expected results: / Narrative on progress / Indicator 1.1 / External engagements are a key element of TI-DSP’s strategy. The number of engagements last year was 199, exceeding the milestone by a total of 99. This year, we had an additional 119 engagements, excluding intra-Transparency International engagements, phone conferences and international TI-DSP strategy meetings. / Indicator 1.2 / As indicated in last year’s report, a training course scheduled for this reporting period was delivered in the previous year. Therefore, building integrity courses were not given in Afghanistan this year. / Assessment of overall progress towards indicator / Indicator 1.1 / TI-DSP is well on its way to meeting the target for this indicator. The number of engagements has exceeded the target for this year by 53. Engagements, including face-to-face meetings and through attending workshops and events, are significant for sharing TI-DSP’s expertise in defence and security corruption, keeping the agenda in different defence establishments and increasing the capacity of in-country partners for anti-corruption reform. / Indicator 1.2 / The target for this indicator was fully achieved in the first year. TI-DSP has evaluated the impact of its training course in Afghanistan, and has made the report available on-line for partners seeking to implement similar training courses in the future.
Assessment of performance of output and progress against expected results
Indicator 1.1 Number of overall TI-DSP engagements (invitations, meetings). / Baseline 80 / Milestone 2011/12 2012/13 2013/14 / 100 265 335 / Achieved 199 318 / Variance +99 +53 / Disaggregated data* While TI-DSP does disaggregate date for e.g. training and capacity building (see below), this is much less applicable to the majority of TI-DSP indicators. / *– expand number of rows if needed / Indicator 1.2 Number of ANSF senior officers and officials course participants. / Baseline 60 (in 2010) / Milestone 2011/12 2012/13 2013/14 / 90 132 132 / Achieved 132 132 / Variance +42 0 / Disaggregated data* Of the Afghan ethnic groups represented in or impact report, the respondents included 17 Tajiks, 10 Pusthuns, 2 Sadaats, and 2 Hazaras.21 / Recommendations on amendments to output or indicator / Indicator 1.1 / For this indicator, TI-DSP proposes to revise the milestone upward to 370 for next year. / Indicator 1.2 / There are no recommendations on amendments to this indicator. / DFID comments: Based on the available data, DFID agrees with TI Defence and Security Programme (DSP)’s proposed score of A+ for Output 1. It is noted however that the milestones are highly quantitative. It would have been helpful if the self-assessment report could have provided more qualitative analysis in the narrative sections for this output. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

CHASE PPA - Output 2: Reach out and influence the defence industry and governments worldwide to address more responsible arms trade and transfers, with improved controls against corruption, industry standards and codes of conduct.
Output 2 score and performance description: / A++ Outputs substantially exceeded expectation / Progress against expected results: / Narrative on progress / Indicator 2.1 / In the first quarter of the previous year, TI-DSP engaged senior government officials from Togo, Chile, Indonesia and the Philippines to convince them of the need for and the practicality of an anti-corruption mechanism in the UN Arms Trade Treaty (ATT). In the second quarter, TI-DSP engaged delegates from Congo, Cote D’Ivoire, Palau, and the Netherlands. TI-DSP was also an active participant in the last round of negotiations in March 2013 (March 18 to March 28). The ATT was subsequently adopted in April 2013 with strong anti-corruption mechanisms. / Indicator 2.2 / The number of regional and national defence industry umbrella organisations TI-DSP worked with in the previous year was 5. In this reporting year, the number has reached 7 with the addition of the Korean Defence Procurement Acquisition Program (DAPA) and the French Groupement des industries Françaises Aéronautiques et Spatiales (GIFAS). / TI-DSP’s engagement with DAPA has resulted in the latter pushing for applying TI-DSP’s anti-corruption tools to assess Korean defence companies. In addition, they intend to second people to the TI-DSP office in London. / TI-DSP has also engaged GIFAS in the previous year. Meetings are scheduled to take place in the next reporting period. / Assessment of overall progress towards indicator / Indicator 2.1 / The ATT was adopted by an overwhelming majority of States by the UN General Assembly on April 2nd. It contains three strong anti-corruption provisions. Therefore, the target for this indicator for the entire three-year period has been achieved in the second year. This was mainly due to the coordinated effort made by progressive governments and civil society organisations. / Indicator 2.2 / The target for this indicator for the three-year period was achieved in the first year. This year, TI-DSP worked with two more industry umbrella organisations, exceeding the target by 2 points. The reason for this overachievement is the launch of the Defence Companies Anti-Corruption Report that prompted follow-up discussions.
Assessment of performance of output and progress against expected results
Indicator 2.1 Cumulative number and description of states TI-DSP engages (including via regional organisations) to convince them of the need for and practicality of an anti-corruption mechanism in the UN Arms Trade Treaty (ATT). / Baseline 20 (as of February 2011) / Milestone 2011/12 2012/13 2013/14 / 50 70 A-C in an ATT / Achieved 75 82 / Variance +25 +12 / Disaggregated data* / *– expand number of rows if needed / Indicator 2.2 Number of regional and national defence industry umbrella organisations TI-DSP works with increases. / Baseline 2 / Milestone 2011/12 2012/13 2013/14 / 3 4 5 / Achieved 5 7 / Variance +2 +3 / Disaggregated data* / Recommendations on amendments to output or indicator / Indicator 2.1 / Alongside its partners in the Control Arms coalition, TI is calling on states to see the treaty as a starting point to set new international standards. / Indicator 2.2 / TI-DSP proposes to revise the target upward to 9 for next year. / DFID comments: Based on the available data, DFID agrees with TI Defence and Security Programme (DSP)’s proposed score of A++ for Output 2. It is noted however that the milestones are highly quantitative. It would have been helpful if the self-assessment report could have provided more qualitative analysis in the narrative sections for this output. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

CHASE PPA - Output 3: Produce practical tools that can be directly applied by civil society, governments, and the defence industry so that they are better able to address defence and security corruption and have increased capacity to do so.
Output 3 score and performance description: / A+ Outputs moderately exceeded expectation / Progress against expected results: / Narrative on progress / Indicator 3.1 / In the first quarter of FY 2012, the Building Integrity and Reducing Corruption in Defence and Security: 20 practical reforms Handbook was translated into Spanish. In the second quarter of 2012, three training modules were developed: the Security Sector Reform training module, the Police Anti-Corruption Training module, and a Senior Mission Leader’s Training Module. / In the third quarter of FY 2012, TI-DSP published its Defence Companies Anti-Corruption Index and the Police Anti-Corruption Report which include a company questioner and a police anti-corruption typology respectively that can be used for anti-corruption reform. In the fourth quarter of 2012, the Government Defence Anti-Corruption Index that includes a government questioner was launched, and the TI-DSP Police Report was translated into Spanish. Furthermore, TI-DSP published two training evaluation reports: one on the impact of the Building Integrity and Reducing Corruption (BI/AC) training in general and the other on the training course offered to Afghan senior officials in particular. / Indicator 3.2 / In this reporting period, TI-DSP trained six experts: Adam Foldes, Steve Foster, Lt Gen (ret) Daniel Opande, Michael May, Col. Yuriy Repilo and Lt. Colonel Serhiy Tarasov. / Indicator 3.3 / TI-DSP engaged 26 civil society organisations this year, primarily in the process of developing the Government Defence Anti-Corruption Index. / Indicator 3.4 / In the third quarter of 2012 two reports were published: (1) Defence Companies Anti-Corruption Index, and (2) Arresting corruption in the police. In the same period, two more reports were written: (3) Overview of political economy and contracting in Afghanistan: A case study in Kandahar and (4) Training the military and defence and security officials in understanding and preventing corruption. In the fourth quarter of 2012, the Government Index was launched, and the TI-DSP police report was translated into Spanish. Furthermore, TI-DSP published two reports on the impact of its training in general and in Afghanistan in particular. / Assessment of overall progress towards indicator / Indicator 3.1 / TI-DSP has produced numerous tools for defence and security anti-corruption reform. The milestones for both years have been exceeded. TI-DSP has surpassed the target for this indicator for the whole three-year period by 5 points already. The reason is that defence and security anti-corruption is a niche sector; not many organisations are involved. Therefore, TI-DSP has to constantly produce tools and build the capacity of other actors, bringing them on-board the fight against corruption in the sector. / Indicator 3.2 / Six experts were trained and made available to civil society, industry and governments in this reporting period. The total number of experts has now reached 25, exceeding the milestone by 5 points. TI-DSP is on track for meeting the target for this indicator. / Indicator 3.3 / TI-DSP exceeded the target by 26 points for this reporting period. This was mainly due to the high number of TI National Chapters engaged through a targeted exercise on the Government Defence Anti-corruption Index. The level of engagement of National Chapter is currently levelling off. / Indicator 3.4 / The milestone for this indicator was exceeded by 4 points. This is because TI-DSP hired a Communications and Publications Support Officer in the previous year, enabling the dissemination of tools and publications more widely with reduced cost.
Assessment of performance of output and progress against expected results
Indicator 3.1 Cumulative number of new practical tools developed by TI-DSP to address defence and security corruption. / Baseline 1 / Milestone 2011/12 2012/13 2013/14 / 2 8 (increased from previous milestone of 4) 9 (increased from previous milestone of 6) / Achieved 4 14 / Variance +2 +6 / Disaggregated data* / *– expand number of rows if needed / Indicator 3.2 Number of TI-DSP trained experts available to civil society, industry, and governments. / Baseline 10 / Milestone 2011/12 2012/13 2013/14 / 15 20 30 / Achieved 19 25 / Variance +4 +5 / Disaggregated data* / Indicator 3.3 Number of civil society organisations engaged by TI-DSP to build their capability in tackling defence and security corruption / Baseline 10 / Milesone 2011/12 2012/13 2013/14 / 15 58 (increased from the previous milestone of 20) 58 (increased from the previous milestone of 25) / Achieved 58 84 / Variance +43 +26 (revise to +90) / Disaggregated data* / Indicator 3.4 Cumulative number of new TI-DSP publications. / Baseline 2 / Milestone 2011/12 2012/13 2013/14 / 3 15 (increased from 3) 20 (increased from 3) / Achieved 10 19 / Variance +7 +4 / Disaggregated data* / Recommendations on amendments to output or indicator / Indicator 3.1 / TI proposes to revise the milestone upward to 18. / Indicator 3.2 / There are no recommendations on amendments for this indicator. / Indicator 3.3 / TI proposes to revise the milestone upward to 90. / Indicator 3.4 / TI proposes to revise the milestone upward to 25. / DFID comments: TI-DSP had suggested a score of A++ for Output 3. Based on the data made available in the self-assessment report, DFID questioned this score. Whilst the milestone may have been met in numerical terms, there is very little narrative surrounding the qualitative impact of the programme. Additional supporting evidence has since been provided by TI-DSP in response to DFID feedback on the TI-DSP self-assessment report. DFID recommends in future that TI-DSP ensure that it provides sufficient detail in its narrative reporting to ensure that its achievements are reflected effectively. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / General PPA – Yes / Chase PPA - Yes / 1.2 Overall Output Score and Description: / General PPA – A / Chase PPA – A+ / 1.3 Direct feedback from beneficiaries / General PPA / TI have some interesting examples of beneficiary feedback through a number of relevant tools, particularly the database used by ALACs. The ALAC database also collects information on clients’ satisfaction with the ALAC service and data from in-depth surveys with sample clients which is typically used by ALACs to assess the quality of the services provided and ultimately reach more people. / CHASE PPA / TI-DSP, like a number of other organisations under the DFID CHASE PPA funding mechanism, is working towards institutional change. While this work has a very direct impact on the everyday lives of citizens (ultimate beneficiaries), TI-DSP is less directly engaged with its ultimate beneficiaries than those organisations working in service delivery or humanitarian relief. Nevertheless, TI-DSP maintains close contact with its proximate and intermediate beneficiaries, which include governments, companies, TI chapters and other civil society organisations, industry associations and media. / TI-DSP continues to maintain a close link to its proximate and intermediate beneficiaries throughout the entire programme cycle, from programme design to implementation and M&E. Beneficiary feedback was sought through a wide range of tools including: online surveys, in-depth interviews (both in person and over the phone), direct observation, case studies (Afghan training report), and feedback gathered from media (number of and the various events that TI-DSP staff attended or organised (e.g. MEKANIC (Monitoring, Evaluation, Knowledge, Affirmation, Building Effective Networks, Influencing and Theory of Change) TI-DSP’s quarterly systematic process to maximise learning from their work.) / Beneficiary feedback for training – case studies and in-depth interviews / Two evaluation reports - the purpose of these two studies (one was a case study) was to follow up on the impact of TI-DSP Building Integrity course, delivered in partnership with NATO. The surveys sought to see whether the training had resulted in changes in participants’ understanding of defence corruption and how, if at all, it helped them in their work and in initiating change themselves. Of the over 600 participants that have been on the course so far, TI-DSP contacted 89 former alumni from ten countries, who attended one of the eight past courses between July 2008 and May 2011. Of the 89 former course participants contacted, 37 were successfully interviewed by phone. The participants were selected randomly, while trying to ensure geographical representativeness. / The survey found that the course had a very positive impact on participants engaged or initiating anti-corruption actions. It enabled about a quarter of participants to undertake noteworthy actions on building integrity. / Beneficiary feedback for GI – online survey / After the GI launch in January 2013, TI-DSP conducted an online survey to assess: 1) the quality of TI-DSP's support for the chapter in terms of preparing for the launch, and their accessibility during the launch period; and 2) the chapter's capacity to work on defence and security issues, and their readiness to deal with media and government enquiries. TI-DSP conducted a survey of all 82 TI chapters involved in the development and launch of the GI. The survey was conducted in a first stage by email, with follow-up by phone. Of the 82 chapters, 52 provided more or less comprehensive answers and provided scores (from 0 to 5) for our two questions. / TI-DSPs average score on the first question was 4.2, with no chapter giving DSP a score below 4 (rating was 0-5). / Direct involvement of beneficiaries and direct observation / Beneficiaries’ feedback was captured and documented through TI-DSP’s ‘scrapbook’ system. / Media monitoring / As media outlets are among TI-DSP’s intermediate beneficiaries, help to carry TI-DSP’s message forward to a wide range of audiences, the team monitored the media use of its research findings. / 1.4 Summary of overall progress / General PPA / Overall, there is evidence in some of the indicators at both outcome and output level of TI exceeding original milestone targets. Examples of progress: / Accelerated engagement with citizens through ICT tools and social media. / TRAC report was an example where limited investments led to strong impact. / Strong statement on the state of corruption in the developed world in the European National Integrity Project. / Some evidence of systemic impact e.g. the Peru Social Investment Programmes and the Kosovo laws on political financing. / However there is a need for more evidence. / CHASE PPA / There is evidence of good progress at both output and outcome level with TI-DSP exceeding the original milestone targets. DFID would however like to see more detail in future in the narrative of TI-DSP’s reporting in order for achievements and TI-DSP’s contribution to these to be reflected more effectively. / Particular highlights of TI-DSP’s achievements in Year 2 include: / Highlight 1: The Defence Companies Anti-Corruption Index (CI) and the Government Defence Anti-Corruption Index (GI) / In October 2012 and January 2013 TI-DSP launched two major indices to assess corruption risks within the defence sector and provide all major stakeholders with a benchmarking tool to assess progress over time. A report was produced to assess the initial impact, indicating that the indices contribute to an open dialogue and even policy changes. / TI-DSP have had follow up engagements with 47 defence companies, and 14 made changes to their systems based on this. There is pressure from other governments to include them in the next GI. / The impact on TI National Chapters has also been great: 47 did some of the research, and 31 took advocacy positions at the time of the launches. Media coverage was excellent with more than 400 articles, 163 in the international press. / Highlight 2: The United Nations Arms Trade Treaty (ATT) / TI-DSP very much welcomes the historic adoption of the ATT. It is the result of years of work by concerned countries, its diplomats and TI’s partners in civil society. It is also the result of TI-DSP’s own work with governments (and DFID in particular), investors and the defence industry. TI-DSP is calling on states to see the treaty as a starting point to set new international standards. / Three sections in the ATT will help states to address corruption risks at the various stages of an arms transfer, including as part of the strictest level of arms export assessment criteria, alongside international humanitarian law and human rights law, in Article 7.1.b.iv. / Highlight 3: Engaging the Afghan Security Forces and the international military on developing guidance for corruption prevention in stabilisation operations / One of TI-DSPs key innovations was to bring their constructive and preventive approach to Afghanistan. TI-DSP has worked with the Afghan MOD, MOI, ANA and ANP to run high level corruption prevention courses and has been advising them on how to reorganise themselves for better anti-corruption effects. They have been briefing deploying ISAF troops, including about which interventions risk making the problem worse. They have led a review of ISAF anti-corruption activity (particularly “Shafafiyat”) and their proposed new strategy has been adopted. This work has led to a large body of new knowledge about how to tackle corruption in stabilisation operations, which TI-DSP are currently developing into guidance. / 1.5 Key challenges / General PPA / Victims and witnesses of corruption coming forward need protection. / Increasing number of Chapters of TI finding it difficult to operate freely. / Important legislation is under pressure (e.g. Foreign Corrupt Practices Act) / CHASE PPA / The key challenges to the work of TI-DSP remain largely similar to those identified last year. / There are three main risks: (1) That TI-DSP chooses countries where corruption is so deeply entrenched that it is impossible to make visible progress. (2) That TI-DSP spreads itself too thinly, and (3) The physical risk to the lives of the team. This is particularly relevant in conflict states such as Afghanistan and Yemen. / These risks continue to be relevant and to be adequately addressed through (1) evaluating target countries with internal and external actors before planning any intervention; (2) preparing multiple year plans; (3) travelling as safely as possible, e.g. with NATO / the UK military in Afghanistan, having adequate travel insurances and working closely with those on the ground where TI-DSP intervenes, increasing in-country capacity and sustainability. / 1.6 Annual Outcome Assessment / General PPA / There is evidence in some of the indicators at both outcome and output level of TI exceeding original milestone targets so there is an indication that they will meet the overall objectives of the programme in year 3. However there is a need for more evidence to back this up. / CHASE PPA / TI-DSP has made good progress at the outcome level and indications are that they will meet the overall objectives of the programme in Year 3. However, DFID has raised some points to note surrounding the level of qualitative information provided. Specific comments have been provided against the individual outcomes below. / Details of progress against Outcomes is as follows: / Outcome 1: Defence or security reform initiatives underway and publicised in a variety of governments, especially those in developing countries, and in conflict or unstable environments. / Indicator 1 Cumulative number and description of new countries with defence integrity or counter-corruption programmes. / Baseline 0 new countries in 2011 / Milestone 2011/12 2012/13 2013/14 / 3 6 9 / Achieved 3 7 / Variance 0 +1 / Indicator 2 Volume (articles) of public reporting on defence and security anti-corruption reform. / Baseline 30 in 2010 / Milestone 2011/12 2012/13 2013/14 / 40 75 (increased from previous milestone of 50) 95 (increased from previous milestone of 50) / Achieved 55 107 / Variance +15 +32 / Narrative on progress / Indicator 1 / In the previous reporting year Greece, Peru and Norway had initiated, and to varying degrees implemented anti-corruption reforms in their defence and security establishments. / This year Thailand, Honduras, South Korea and Uganda have initiated defence and security anti-corruption reforms. Since the first quarter of 2012-13, all three branches of Thailand’s defence establishment have been tasked with creating their own anti-corruption plans. Consequently, the Royal Thai Navy visited TI-DSP seeking assistance in June. / In Honduras, TI-DSP is represented in the Multinational Committee of the Alliance for Peace and Justice, a coalition of civil society organisations critically engaging the government for police anti-corruption reform in one of the most corrupt nations in the world. In this reporting period, the Alliance successfully lobbied the President, the President of Congress and the National Security Advisory Council on several anti-corruption reform measures, including purging corrupt elements in the police force. / Another reform was initiated by the Defence Acquisition Programme Administration (DAPA) of the South Korean government. The DAPA has initiated a process of assessing 97 Korean defence companies against the Company Index questionnaire developed by TI-DSP, with the view to putting substantive improvements in place. It also intends to use TI-DSP’s defence and security corruption risk typology, translate TI-DSP’s 20 Practical Reforms Handbook and second staff to TI-DSP’s office in London. / In Uganda, TI-DSP undertook a thorough police corruption risks assessment in July 2012 at the request of Transparency International-Uganda. The findings were endorsed by the Inspector General of Police who has requested TI-DSP to implement a Police anti-corruption training and public awareness raising project to reduce corruption in the Ugandan Police Force. The project is envisaged to reduce this high level of corruption when implemented. / Indicator 2 / In the previous reporting period, 55 articles (baseline plus 45) were published. This year, the number has reached 107, including stories from Argentina, Canada, China, Czech Republic, Greece, India, Italy, Russia, Singapore, Thailand, UK, and US. These articles as well as short summaries for each are available upon request. / Assessment of overall progress towards target / TI-DSP has exceeded the milestones set for both indicators for this year and is well on its way to achieving the targets for next year. The reasons for this overachievement include purposive engagement with a number of Transparency International National Chapters (TI-NCs), the high-level of interest generated by the Government Defence Anti-Corruption Index and the Defence Companies Anti-Corruption Index, and the use of Senior Advisors with extensive contacts in many countries around the world. / Recommendations on amendments / Indicator 1 / No recommendations on amendments. / Indicator 2 / TI-DSP proposes to revise the milestone upwards to 125. / DFID comments: Outcome 1, Indicators 1 and 2 are both quantitative and do not capture any qualitative measures. DFID would recommend going forward that TI-DSP try to capture programme quality in its reporting and the extent to which the articles influenced key interlocutors and how this contributes to delivering results at the outcome level in the supportive narrative. / Outcome 2: International arms transfers are conducted more responsibly, with improved controls against corruption. / Indicator 1 Number and description of States whose position on the inclusion of an anti-corruption mechanism in a UN Arms Trade Treaty (ATT) has been informed through engagement with and influenced by TI-DSP. / Baseline 10 as of February 2011 / Milestone 2011/12 2012/13 2013/14 / 15 45 Anti-corruption mechanism in the final ATT (2012/2013) / Achieved 41 61 / Variance +26 +16 This was achieved on April 2nd 2013. / Indicator 2 / (replaced by Indicator 3) Industry membership of the international Forum on Business Ethical Conduct for the Aerospace and Defence Industry (IFBEC) and description of defence industry associations or defence companies whose membership bid has been facilitated by TI-DSP. / Baseline 2 members as of February 2011 / Milestone 2011/12 2012/13 2013/14 / 3 members (umbrella organisations) N/A (membership now open to companies) N/A / Achieved 2 +7 (companies) / Variance -1 +7 / Indicator 3 Number of defence companies making improvements to their ethics and compliance system at least partially in response to engagement with TI-DSP. / Baseline 0 / Milestone 2011/12 2012/13 2013/14 / 0 10 25 / Achieved 3 18 / Variance +3 +8 / Narrative on progress / Indicator 1 / The ATT was adopted by an overwhelming majority of States by the General Assembly on April 2nd. Three sections in the ATT will help states to address the corruption risks at the various stages of an arms transfer, including as part of the strictest level of criteria, alongside international humanitarian law and human rights law. / Indicator 2 / In October 2012, The International Forum for Business and Ethical Conduct (IFBEC) meeting was attended by representatives from Chinese, Japanese, Brazilian and Canadian defence industries who indicated interest to be actively involved in the future. TI-DSP was invited as a keynote speaker to this meeting. Seven defence companies subsequently became members. Membership to IFBEC is now open to individual defence companies rather than just umbrella defence associations. / TI-DSP have made a suggestion (accepted by DFID) to replace this indicator with one that more directly captures TI-DSP’s direct impact on companies. / Indicator 3 / Eighteen companies have notified TI-DSP that they are making improvements to their anti-corruption systems or provided further internal information to reflect how they are increasingly tackling corruption. These include BAE Systems, Day & Zimmermann, DCNS, FLIR, General Electric, Israel Aerospace Industries, Israel Military Industries, Jacobs Engineering, Lockheed Martin, MTU Aero Engines, Patria, QinetiQ, Rafael Advanded Defense Systems, Rockwell Collins, Rheinmetall, Saab, Thales, and United Technologies. / Assessment of overall progress towards target / Indicator 1 / Through concerted effort made by governments, international organisations, companies and civil society, the target for this indicator has been fully achieved in the second year. Alongside its partners in the Control Arms coalition, TI-DSP is calling on states to see the treaty as a starting point to set new international standards. / Indicator 2 / As noted above, seven defence industries have signed up for membership to the IFBEC. However, as this indicator is only tentative (as can be seen from the agreed revised log frame), report is made against the first and third indicators for this review. / Indicator 3 / TI-DSP is well on its way to meeting the target for this indicator. It has exceeded this year’s milestone by 8. The reason for this overachievement is the launch of the Defence Companies Anti-Corruption Index that prompted follow-up discussions and systems improvement. / Recommendations on amendments / There are no recommendations on amendments for these indicators. / DFID comments: For Outcome 2 Indicators 1 and 3, it could be clearer from the narrative how the actions/activities of TI-DSP informed and influenced states and defence companies. Whilst DFID recognises that the work of TI-DSP alone could not be expected to deliver the identified outcomes, a deeper, more analytical narrative of the contribution of TI-DSP would be helpful in future reporting against this outcome – i.e. to what extent can TI-DSP’s contribution be linked to the outcomes? / Outcome 3: Civil society organisations, governments, and companies are better able to counter corruption with practical tools that they can directly apply and have increased capacity to do so. / Indicator Number and description of practical tools developed by TI-DSP to address defence and security corruption that are used by civil society organisations, governments, and/or companies. / Baseline 1 as of February 2011 / Milestone 2011/12 2012/13 2013/14 / 2 8 (increased from previous milestone of 4) 9 (increased from previous milestone of 6) / Achieved 4 14 / Variance +2 +6 / Indicator Number and description of civil society organisations reporting capability in tackling defence and security corruption. / Baseline 5 as of February 2011 / Milestone 2011/12 2012/13 2013/14 / 10 15 20 / Achieved 12 19 / Variance +2 +4 / Narrative on progress / Indicator 1 / In year 1, three new tools were developed for use by governments, defence companies and civil society organisations: the Defence Budget Transparency Report, which included a questionnaire tool for civil society and others; the Offsets Due Diligence Guidance; and the Third Line of Defence Report which included a template for designing auditing systems. These practical tools were and continue to be applied and commented on, for example, by TI national chapters and by SIPRI. / In the first quarter of FY 2012, the Building Integrity and Reducing Corruption in Defence and Security: 20 practical reforms Handbook was translated into Spanish for use by TI Chapters in the Latin America region. / In the second quarter of 2012, three training modules were developed and used to train practitioners. These include the Security Sector Reform training module used in various national and continental training centres in Africa; Police Anti-Corruption Training module, used to train members of the Independent Police Oversight Committee (IPOC) in Kenya, and a Senior Mission Leader’s Training Module used in courses at the Southern African Development Community’s Regional Peacekeeping Training Centre. / In the third quarter of FY 2012, TI-DSP published its Defence Companies Anti-Corruption Index, which is being used by many companies and governments as discussed above, as well as the Police Anti-Corruption Report which includes a police anti-corruption typology that can be used as a tool by governments, international organisations and civil society groups for police anti-corruption reform. / In the fourth quarter of 2012, the Government Defence Anti-Corruption Index was launched and used by 26 civil society organisations in various countries as an advocacy tool. The TI-DSP Police Report was translated into Spanish to aid TI Chapters in Latin America in their effort to reduce corruption in police. The Chapters have established a Regional Security Expert Group, which has benefited from the police report and the police corruption typology in the report produced by TI-DSP. Furthermore, TI-DSP published two training evaluation reports; one on the impact of the Building Integrity and Reducing Corruption (BI/AC) training in general and the other on the training course offered to Afghan police officers . / Indicator 2 / The launch of the Index encouraged 22 TI chapters and other NGOs to conduct activities to press for accountability and raise awareness of defence corruption in their countries: Taiwan, Lebanon, India, Kuwait, Georgia, Palestine, Bahrain, Czech Republic, Kenya, Chile, Serbia, Malaysia, South Korea, Mexico, Colombia, Croatia, and Russia. / TI Taiwan hosted a global media launch of the index, including high-level meetings with government officials, and a workshop with 4 TI chapters (Malaysia, Indonesia, Japan, and South Korea). Despite a challenging environment in Indonesia, following the launch Executive Director Dedi Heryadi told TI-DSP “the good thing is that the media is proactive, and openly discussing a new, sensitive issue.” / A regional launch and civil society workshop were also hosted by LTA (TI Lebanon), jointly with the Lebanese Army, which gained significant media attention in the region. AMAN (TI Palestine) countered a major attack by the government on the report, and independently and successfully turned the attention into a project that includes developing an anti-corruption plan with the MOI and the creation of a civil society forum to oversee and monitor the sector. / There were also 5 national events that raised awareness of the issue and highlighted findings and next steps. / Four non-TI NGOs used the index for advocacy activities: the Institute for Security Studies, South Africa; Integrity Watch Afghanistan; the Geneva Centre for the Democratic Control of the Armed Forces’ Tunisia office; Belgrade Centre for Security Policy (with TI Serbia). / Assessment of overall progress towards target / TI-DSP has to-date produced numerous tools for defence and security anti-corruption reform. The milestone for the first indicator has been surpassed by 6 points. The milestone for the second indicator has also been exceeded by 4 points. The reason for this overachievement is that defence and security anti-corruption is a niche sector; not many organisations are involved in it. Therefore, TI-DSP has to constantly produce tools and build the capacity of other actors, bringing them on-board the fight against corruption in the sector. / Recommendations on amendments / Indicator 1 / TI-DSP proposes to revise the target upward to 18. / Indicator 2 / TI-DSP proposes to revise the target upward to 25. / DFID comments: The reporting provided on this Outcome provides better quality evidence, clearly setting out TI-DSP achievements. DFID would welcome more information on how TI intends to monitor and evaluate the impact of these guidance notes, training modules etc. on learning, behaviour and organisations results over the longer term.

2. Costs and timescale
Is the project on-track against financial forecasts: / Yes, annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. Allocations for year 3 will be allocated in the same way with no variance expected. / Key cost drivers / General PPA / The main cost drivers for the financial year 2012 were: / Staff Costs 39.3% / Partnerships (mainly transfers to Chapters) 28.3% / Travel and Workshops 11.7% / External support/advice (honoraria) 11.6% / Other 9.1% / TI has demonstrated its cost drivers at a high level; this could be strengthened by linking these costs more explicitly to activities and outputs. It's good to see that TI is tracking support costs. It would be interesting to review the performance of these over time. We welcome the fact that TI is incorporating value for money into the organisation’s M&E. / CHASE PPA / The principal cost drivers are the following: / Senior experts / TI-DSP’s way of working is to pair up a young professional with a highly experienced senior person in each of the areas where in which they work. TI-DSP attract these senior experts by the high quality of their work, the high political levels at which they work, and the very evident impact that TI-DSP is having. This would be prohibitively expensive if TI-DSP were to pay anywhere near market rates, which range from GBP 1000 per day for public sector work to £2000 for private sector work for individuals with such experience. TI-DSP’s rate is significantly lower. This does not inhibit applications from such impressive people to work with us because they enjoy it and TI-DSP value them very highly. / Cost-centred work planning / It is common to have an initial pilot or testing phase for TI-DSP projects. Then, only if progress is made and the activity is deemed to be a worthwhile use of resources, substantial resources are further invested. An example of this approach for the current reporting year was the two-staged research process for the “Arresting Corruption in the Police report”. / Budgeting and cost control / Throughout the second year of PPA funding, TI-DSP continued to be meticulous in using grant money as prudently as possible. / TI-DSP works with annual budgets that were re-assessed on a quarterly basis, and updated accordingly. TI-DSP had minimal administrative costs and as a part of Transparency International UK (TI-UK) shared the use of accounting systems and auditors with the domestic UK team to reduce costs. TI-DSP continued to require the Programme Director’s or Programme Manager’s approval of all expenses over £50. / Auditing is done by professional auditors, and a qualified accountant oversees the accounts every month. TI-DSP also has a meticulous budgeting and forecasting system. Audited accounts are available on the TI-UK and TI-DSP websites. Financial management is done thoroughly, on a monthly basis, checking and separately approving every spend item for approval before payment. As part of TI-UK, TI-DSP’s financial accounts are audited by external auditors in accordance with United Kingdom Generally Accepted Accounting Practice applicable to smaller entities and the Companies Act 2006. / Is the project on-track against original timescale: / The project is on track against the original timescale.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / General PPA / Unfortunately there is little substantive information on how evidence really drives forward the design of programmes, activities and results. / TI is using baseline studies as a key input for programme adjustment, management and learning. The programme baseline, for example, has been used to set the 2013 annual targets. The exercise to collect baseline data has led to an increased understanding of the relevant M&E indicators and processes, particularly around identifying the contribution of the TI-S to Chapter activities. In 2013, TI has successfully begun to monitor its annual plan quarterly. Being clearer on targets for the year and allowing for quarterly assessments of progress increases value for money. / CHASE PPA / The involvement of TI-DSP’s beneficiaries throughout the entire project cycle allowed TI-DSP to adjust their research design and implementation and thus make it more useful and relevant to them. This was particularly relevant for their flagship publications, the Government Defence Anti-Corruption Index and the Defence Companies Anti-Corruption Index. / Discussions at MEKANIC identified challenges regarding a log frame indicator focusing on TI-DSP and defence company progress. The indicator was subsequently replaced in co-ordination with DFID CHASE. / For the Defence Companies Anti-Corruption Index, MEKANIC led a number of adjustments for the second edition, namely: / More demanding questions – whistleblowing questions will have more details and the political environment will be more nuanced. / Adjustment in the scoring of the questions to better reflect what companies have or do not have in place to prevent corruption. / In addition to the above programmatic lessons, a number of operational challenges, lessons and opportunities for improvement were identified through our quarterly reviews of TI-DSP’s log frame. One relates to the challenge of measurement of its advocacy initiatives. While serious efforts were undertaken in 2012/13 to appropriately capture the impact (e.g.: stakeholder mapping and analysis), opportunities to improve their monitoring and measurement approaches were identified. / 3.2 Where an evaluation is planned what progress has been made? / The PPAs as a whole are served by an umbrella evaluation strategy, the first of its kind for DFID, which encompasses the Global Poverty Action Fund. This strategy examines progress at fund and at individual, organisational level. Following the announcement of the extension to the PPA fund in 2013, the evaluation strategy is being reviewed and, in addition to the individual progress reviews (IPRs) and meta evaluation that took place in 2012, further evaluative activities are being scoped out for 2014/2015 and 2016/17. This scoping process is taking place in consultation with the on-going funded organisations and the revised strategy will be ready in Quarter 4 of Financial Year 2013/14. The aim is to provide timely, fund level evaluation information for the design of future strategic funding modalities in 2014/15 ahead of the fund completion in 2016, followed by evaluative learning on the outcomes and impact of strategic funding for organisations and the fund as a whole in 2016/17.

4. Risk
Output Risk Rating: / General PPA: Low / CHASE PPA: Medium / Assessment of the risk level / General PPA / Implementation of the risk management process has continued during the year with the development of the individual “Risk Register and Management Tool” for each department at TI. These provide for the identification of risks and controls in place, as well as their assessment (probability and impact) and treatment (action plan). The Risk Management Committee continues to meet regularly and reports to the Audit Committee of the TI Board of Directors. / Security and safety risks to anti-corruption fighters increase with TI becoming more bold in its messaging. TI has started an initiative to improve whistleblowing legislation globally, funded through core support. / There is a real risk to TI that its unrestricted income from bilateral donors decreases in the coming years. As a response they have continued to invest in diversifying our donor base . / CHASE PPA / The key challenges to the work of TI-DSP remain largely similar to those identified last year. / There are three main risks: (1) That TI-DSP chooses countries where corruption is so deeply entrenched that it is impossible to make visible progress. (2) That TI-DSP spreads itself too thinly, and (3) The physical risk to the lives of the team. This is particularly relevant in conflict states such as Afghanistan and Yemen. / These risks continue to be relevant and to be adequately addressed through (1) evaluating target countries with internal and external actors before planning any intervention; (2) preparing multiple year plans; (3) travelling as safely as possible, e.g. with NATO / the UK military in Afghanistan, having adequate travel insurances and working closely with those on the ground where TI-DSP intervenes, increasing in-country capacity and sustainability. / Risk of funds not being used as intended / TI underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. / In addition for the CHASE PPA: As part of a broader HMG initiative – DFID has a new risk management policy in place which requires new projects, in support of the security and justice sector to undertake a human rights risk assessment following a standard procedure. This policy, the Overseas Justice and Security Assistance Guidance (OSJA) seeks to balance risks against the positive impact that security and justice programming can have on the realisation of human rights. DFID will be contacting PPA partners individually to brief them in more detail about OSJA and how we can work together to apply it to each programme. This will include the TI-DSP PPA. / Climate and Environment Risk / No issues were raised for the attention and action of TI as a result of the 2011 Environmental Screening process.

5. Value for Money
5.1 Performance on VfM measures / General PPA / TI’s procurement guidelines require competitive bidding for procurement of goods or services over EUR 5,000. This includes consultancies, travels, publications and other activities, and ensures economy of cost for the input needed. TI’s travel policy further requires that all staff travel economy class, and ensure that accommodation is reasonably priced, while taking safety and country costs into account. / TI tracks the costs of the support departments, including finance, human resources, office management and information technology. These departments provide the necessary support for the organisation to continue functioning effectively, and are monitored and controlled on a systematic basis. / TI tracks Value for Money for specific interventions: / The average cost of producing a TI Helpdesk answer is less than EURO 2,000. Should such answers be produced by external research consultants, costs would almost certainly have been much higher. / In this reporting year, a new financial manual was adopted, providing clear guidance on achieving value for money in procurement. The financial manual also provides clarity on other financial procedures, including processing of invoices, travel guidelines and others. / Improved M&E system also allows TI to assess value for money. / CHASE PPA / Key management processes and resource allocation decisions made at each stage of the implementation process result in the efficient delivery of higher value inputs, activities, outputs and ultimately outcomes and impact. Internal management processes reflect how TI-DSP uses the DFID PPA funding to ensure that value is maximised from every £1 spent throughout the life of the grant. At a detailed level, we track unit costs of printing – TI-DSP’s largest single external expense. / Practices that enable TI-DSP to get better value for money include the following: / Senior experts work at a fraction of the market rate. This means TI-DSP can have several times as much impact as they would otherwise have. / Similarly, TI-DSP’s senior experts are well aware of how much they are trying to do on a limited budget. So when they travel for other reasons, not connected to TI-DSP, they ‘piggy-back’ TI-DSP’s work on and only charge the marginal additional cost. Interventions on this basis include Zimbabwe, Ethiopia, USA, South Africa, Botswana, Ghana, and Sweden. This cuts the travel cost to TI-DSP of a five day trip by approximately 90%. / Tracking the unit printing costs, and getting quotes for a whole year’s worth of printing, has enabled a reduction of some 25% on the cost that TI-DSP were paying 2 years ago. / TI-UK is based at Community Action Network (CAN) Mezzanine. CAN Mezzanine works to clear environmental policies, which include cleaning being 100% eco-friendly; collecting refuse for recycling including all paper products, glass, plastic, toner cartridges and steel and aluminium cans; and using a PIR lighting system, which is movement sensitive reducing energy waste. / Transparency International UK has a relatively small environmental impact, and a policy designed to minimise their environmental footprint. The target is 100% compliance in the areas of energy use, travel, procurement, and waste recycling. TI-UK operates in compliance with all relevant environmental legislation, trains, educates and informs its employees, interns and consultants about environmental issues that may affect their work, and makes them aware of the policies in place. This includes printing in particular, which is sourced from environmentally-friendly printers (e.g. those with ISO 14001 accreditation). All paper must be FSC-certified, recycled or from sustainable sources. / The extractive industries face particularly high environmental risks. TI-DSP has been working with TI’s EU Office in Brussels to make sure that, as recently debated in the European Parliament, there is an explicit requirement for extractive companies to disclose payments to government security forces relating to their specific industry activities. This would reveal the extent to which some state security forces are acting as private paramilitaries, or at least the extent to which they are dependent on funding from extractive companies. TI-DSP has recommended to the UK Committees on Arms Export Controls that where these government security forces are the end-user named in an arms export licence, it should be verified whether the security forces do receive any payments from extractive companies, and whether these payments are disclosed to the public, before the arms export license is issued. / TI-DSP make heavy and innovative use of research students who are keen to do their thesis or dissertation on a subject that we propose. For this, TI-DSP publish a long list of research topics on our website, which attracts them. This year TI-DSP are doing research projects with multiple students tackling one topic: for example they have had 4 students at LSE on contractual corruption in Kandahar, and currently have 20 students at George Washington University in the USA on the impact of scandals on legislation. / For the reporting year, the use of senior advisors continued to be an excellent VfM resource for TI-DSP. The advisors that TI-DSP used were high profile individuals, e.g. retired ambassadors and former generals), strongly committed to TI‐DSP’s work and willing to work for fees that were well below market‐rates. They are existing staff members as distinct from external consultants hired via a firm, thus avoiding unnecessary overheads. Given their backgrounds, they were often able to obtain high level access without difficulty and to use their time effectively to provide a high degree of value‐added with minimal transaction costs. Money spent on their work yielded a high return in terms of VfM. Further, beneficiaries were very impressed by their knowledge and understanding of their needs. / The use of the TI chapters in the development and launches of the Government Index also represented an excellent value for money in this reporting period. / 5.2 Commercial Improvement and Value for Money / General PPA / Kept support costs down (at around 13% of total costs) and in some areas even managed reductions, in spite of the significant increase in operations during the past few years. / To control the cost of procuring external consultants and other services, TI increasingly contracts pro-bono and in-kind support from commercial enterprises. For example, the number of international law firms providing pro-bono support to TI increased from 2 in 2011 to 14 in 2012. / Receive EUR 10,000 worth of free advertising per month from Google along with a discount from Dow Jones on our Factiva subscription. / CHASE PPA / Where possible, TI-DSP collects a number of quotes before committing to a supplier. Their largest single expense is for publications, and they compete this on an annual ‘bulk basis’ with print companies. The same is true for sophisticated and yet easy accessible and user-friendly web tools. / A lot of TI-DSP work relies on face-to-face contact. Foreign trips will often include 12-14 hours of meetings per day to make most of the time abroad. TI-DSP relies almost entirely on budget airlines and search for the best possible hotel deals. TI-DSP also makes sure to fly at times when flights are cheapest. In addition, strategic meetings with overseas colleagues are frequently conducted via Skype or as telephone call conferences. Further, TI-DSP senior experts are often travelling for other reasons; when doing so, they try to introduce TI-DSP’s work in their agendas as much as possible. This means they can get to many countries that TI-DSP otherwise do not have the budget to get to. / 5.3 Role of project partners / CHASE PPA / The Independent Progress Review that Channel Research produced in mid-2012 very much highlights TI-DSP’s partnerships. / TI-DSP is well aware that working in isolation is less effective, and that developing advocacy campaigns and capacity building initiatives in collaboration with like-minded organizations increases not only their sustainability but also the visibility and reputation of TI-DSP worldwide. Recognizing this, during the reporting period, TI-DSP has continued to seek to develop its partnership base and thus reach a wider base of beneficiaries. The PPA funds have been instrumental in providing the means for patience that was necessary for TI-DSP to build these trusting and long-lasting relationships and achieve long lasting results. / For this reporting period, new partnership examples include the following: / Based on TI-DSP’s engagement in 2011-2013, the Norwegian Ministry of Foreign Affairs have set up a new Centre for Defence Integrity Studies, to work with less developed country Defence Ministries. This is important, as they have a long term perspective and their own secure funding. This is a good example of TI-DSP working to see other initiatives set up that extend the work that they are doing. / TI-DSP is partnering with the ‘Associacion para una Sociedad Mas Justa in Honduras to develop more effective ways that civil society can have an impact on corrupt police forces / TI-DSP has also partnered with the Independent Kenyan Police Oversight Authority with a similar objective. / TI-DSP is working in partnership with UNDP and the African Union to develop tools for tackling corruption and governance in the armed forces of West Africa / Also on this topic, TI-DSP is developing a partnership with the Institute for Security Studies in South Africa to develop a capability to improve Defence Ministries and Armed Forces in West Africa. / Partnership with multiple NGOs for the ATT through the Control Arms coalition. / TI-DSP is partnering with numerous individual TI Chapters to work together in their countries and to apply for other grants to work on defence and security corruption in their country. Examples include Lebanon, Hungary, Georgia, and Kenya. / TI-DSP’s on-going partnership with NATO through the “Building Integrity” Programme is leading to several new partnerships. This high level partnership has led in 2012 to a new spin-off initiative focusing on the combating defence and security corruption for countries in the Western Balkans, in partnership with the Defence Ministries of Sooth Eastern Europe (SEEDM). TI-DSP’s experts are providing the main anti-corruption expertise in this project. / Does the project still represent Value for Money : Yes / If not, what action will you take? N/A

6. Conditionality
Update on specific conditions / N/A

7. Conclusions and actions
General PPA / The programme is progressing reasonably well. TI has been investing in Monitoring and Evaluation (M&E) and there are some signs that this is going well. However, we do recognise that it is a long process and that there is further work to be done, particularly in producing sound evidence. TI focuses mainly on policy and advocacy, which is understandable given the nature of TI. There is a need for more information on how this work impacts and benefits poor people. / CHASE PPA / The programme has made good progress during Year 2. DFID acknowledges the skill of TI-DSP’s approaches and the impressive results achieved given the sensitivity of the work and the complexity of many of the contexts in which it works. As mentioned already in relation to reporting against outputs and outcomes, DFID would like to see progress in future on the level of detail provided in reporting on achievements – in particular as relates to the qualitative information provided. / DFID welcomes the level of ambition in terms of revising targets upwards in the log frame. DFID recommends that TI-DSP work with DFID to add clarity to their Theory of Change. / DFID welcomes TI-DSP’s efforts to develop their work on learning. In Year 3, DFID would recommend that TI-DSP work with CHASE to determine if it is possible to monitor and evaluate the processes and factors which determine the level to which TI-DSP is able to successfully influence the actions, behaviours etc. of supply and demand side actors in order to tackle corruption. Whilst it is recognised that research into M&E of ‘influence’ is a new field of study, DFID feels that TI-DSP’s work may offer opportunities for testing out such an approach which will be of benefit not only for TI-DSP’s PPA but also for broader learning with DFID and amongst other PPA partners. / Next steps include: / TI-DSP to follow up on log frame changes required for Year 3; / DFID and TI-DSP to review TI-DSP’s Theory of Change to improve clarity and coherence; / DFID to follow up with TI-DSP on how to approach OSJA implementation; / DFID to follow up with TI-DSP on possible approaches to M&E of influencing; / TI-DSP to follow up with DFID on any further information to be published for IATI.

8. Review Process
Transparency International submitted self-assessment annual reports of their progress and performance against both the General PPA and the CHASE PPA log frames during this second year of PPA funding. DFID reviewed these annual reports and provided feedback to Transparency International on both strengths and weaknesses. The feedback incorporated comments from a range of officials in relevant country and policy teams.