Type of Review: Annual Review

Project Title: Preventing Violence against Women and Girls Scaling up Country Support

Date started:	April 2013 Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The purpose of the programme is to support the scaling up of the quality and quantity of UK programming to prevent violence against women and girls (VAWG). / The programme aims to achieve this through a combination of approaches: / A Helpdesk of experts to respond to short term queries or to undertake more detailed country assignments on VAWG related programming; / A series of Guidance Notes through the DFID VAWG team and Helpdesk teams of experts; / A Community of Practice to support VAWG programming and dissemination of best practice / An evaluation of DFID’s VAWG programmes to capture impact, including beneficiaries at country level. / As set out in DFID’s violence against women and girls pillar strategy (annex 1), this programme is part of a broader effort to scale up DFID’s work on violence against women and girls in at least 15 countries as well as provide access to justice for 10 Million women by 2015. It complements a related Research and Innovation Fund which seeks to establish which approaches are most effective in preventing violence against women and girls.

What are the expected results?
The programme goal, to which UK support will contribute, is as follows: / The UK government contributes to a reduction in the prevalence of violence against women and girls in priority countries / It will achieve this through the outcome of effective, relevant and coordinated violence against women and girls programming in UK priority countries reaching 100% more beneficiaries than by the start of the programme. The estimated baseline for beneficiary numbers at the start of the programme was 470,000. / It will achieve this through delivering the following: / Guidance, tools and specialist knowledge to help UK Government staff develop, evaluate and improve their global violence against women and girls programmes. / Violence against women and girls Community of Practice aimed at improving information sharing and best practice across the UK Government on violence against women programming. / a dedicated resource for evaluating the UK’s violence against women and girls programmes to capture impact and learn lessons on ‘what works’ in preventing violence against women and girls.

What is the context in which UK support is provided?
The Global Impact of Violence against Women and Girls / Violence against women and girls is the most widespread form of abuse worldwide. Inequalities between men and women perpetuate the abuse. Intimate partner violence (IPV) is the most prevalent form of violence against women and girls, perpetrated by and/or supported by family members. Globally, at least one in three women is beaten or sexually abused by an intimate partner in her lifetime[1] / Tackling violence against women and girls is closely linked to achieving other development outcomes. It is a barrier to efforts to reach the Millennium Development Goals (MDGs) and has been dubbed ‘the missing MDG[2]. It is a particular barrier to progress on girls and women’s educational attainments[3], prevents them from being economically active and undermines their ability to choose the timing and number of children[4] (the other three pillars of DFID’s Strategic Vision for Girls and Women). / The economic costs of interpersonal violence affect societies at all levels, not just victims and perpetrators. The World Health Organisation has argued that violence against women and girls is an urgent public health priority, with huge economic costs, including the direct costs to health, legal, police and other services. It notes that in many poor communities, relatively few women may seek help from formal services but the overall costs are substantial because of the high prevalence of violence[1]. / Violence against women and girls has also been linked to women’s and girl’s agency[5] and their ability to make effective choices and to transform those choices into positive outcomes for their well-being, access to economic opportunities, nutritional status, physical mobility, access to services and social capital. This impacts on their ability to exit poverty and ultimately (given the prevalence of violence against women and girls), national growth. / Violence against women and girls is, therefore, the most widespread form of systematic abuse worldwide, yet despite some efforts to tackle it there is no evidence that levels of violence against women and girls are decreasing. / DFID: Significant commitments to tackle violence against women and girls / There are a number of international agreements which frame UK Government’s response to violence against women and girls. These include the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW), The UN Declaration on the Elimination of Violence against Women, The Beijing Declaration and Platform for Action; UN Security Council Resolution 1325 on Women, Peace and Security, and to a lesser extent the Millennium Declaration and Millennium Development Goals. / Given the strong development case for tackling VAWG and the UK’s international commitments, DFID’s Business Plan (2011-2015) identifies violence against women and girls as a priority and commits DFID to pilot new and innovative approaches to prevent it. DFID’s recently refreshed Strategic Vision for Girls and Women, published in November 2013, builds on the Business Plan and sets out four pillars for action, one of which is to “Prevent violence against women and girls”. Since October 2011 the Violence Against Women and Girls team within the Conflict, Humanitarian and Security Department (CHASE) has held the lead for the violence against women and girls pillar within DFID’s Strategic Vision for Women and Girls. / DFID’s response to violence against women is also set out in the UK National Action Plan on Violence against Women, which commits DFID to a number of actions including: / Help 10 million women access justice through the courts, police, and legal assistance. / Scale up new and innovative programmes in at least 15 of the world’s poorest countries. / In addition, DFID’s work on violence against women and girls contributes to delivery of the UK’s National Action Plan on UNSCR 1325 on Women, Peace and Security, and cross-Whitehall frameworks including the UK’s Building Stability Overseas Strategy (BSOS) and the analytical tool used to support BSOS and the Joint Assessment of Conflict and Instability. / The Violence against Women and Girls Theory of Change (ToC) gives DFID an overarching framework in which to map, evaluate, and inform the development of programme interventions across the contexts in which DFID works (see Theory of Change ‘How To’ note for more detailed information). / DFID’s country programmes cut across the four themes set out in the violence against women and girls Theory of Change, with most programmes including work on more than one theme. The four themes are: / Empower women and girls / Change Social Norms / Build Political Will and Institutional Capacity / Provide Comprehensive Services / UK Government: scaling up efforts to reach more women and girls / Preventing violence against women and girls is a relatively new area of development, with a lack of rigorous evidence on ‘what works’ in preventing violence against women. More evidence is needed, globally, to support the development of effective programming, monitoring and evaluation systems and Value for Money approaches. / DFID is aiming to address this issue through investing in high quality research through its £25m Research and Innovation Fund (RIF), launched in January 2014. The Country Support programme complements the RIF through supporting DFID country offices, and the broader UK effort, to scale up work on violence against women and girls. It will provide the evidence, know-how and monitoring frameworks to ensure that the programmes reach the maximum number of women and girls. It will also help further strengthen the evidence base for this notoriously difficult and under-developed research area so that lessons can be fed into future programmes.
[1] United Nations General Assembly (2006) Secretary-General’s in-depth study on all forms of violence against women. UN. New York. http://www.un.org/womenwatch/daw/vaw/SGstudyvaw.htm#more.
[2] UN Women, Virtual Knowledge Centre to End Violence against Women and Girls; Factsheet: Violence against women and the MDGs.
[3] UNIFEM (2010b); Vivid Economics (2011) DFID Presentation of Evidence on Increasing the Impact of Development through Gender Equality.; Pinheiro, Independent Expert for the UNSG’s study on violence against children. World Report on violence against children.UNSG’s Study on Violence against children. 2006
[4] Turquet, Watt, and Sharman (2008), Hit or Miss? Women’s rights and the MDGs, ActionAid UK; S Fried (2007), Women won’t wait campaign; show us the money: is violence against women on the HIV/AIDS donor agenda? ActionAid
[5] World Bank (2012), ‘World Development Report’

## Section A: Detailed Output Scoring

Output 1: Guidance, tools and specialist support helping UK staff develop, monitor and evaluate their country and regional VAWG programmes
Output 1 score and Performance description: / The call down contract for the VAWG Helpdesk was signed in April 2013 and manages a roster of 80 VAWG professionals who are drawn from Social Development Direct and its Alliance Partners; (IRC, Womankind, IDS, and ActionAid). Therefore this review is taking place before the Helpdesk has been operational for a full year. Social Development Direct also has a network including VAWG, social development and gender professionals of over 200 individuals where other niche skills can be sourced as needed. Other organisations that have expressed interest to join the roster include Care International. / The VAWG Helpdesk is able to provide 2 key services: / A call down contract service. This allows country offices to access technical advice and support via a roster of 80 VAWG professionals across a range of sectors. The Helpdesk assembles teams as required to support DFID country offices to deliver a range of outputs, including: / Context and situational analysis and research / Programme design and business case material / Programme reviews / Implementation support and advice / Monitoring and evaluation / A query service: rapid desk research (queries) is a service offered to DFID and other HMG staff working on VAWG policy and programming. The service draws on VAWG researchers and experts to respond to a range of technical queries. DFID and HMG clients can contact the VAWG Helpdesk by email or phone with specific queries articulated in the form of one key question (this service is funded by the programme). / The VAWG Helpdesk has also created an internal process manual to quickly source teams from the roster and expert pool for Technical Assistance in order to meet DFID rapid response time lines. The most qualified individuals are put forward to DFID after being assessed against a list of criteria to ensure that the most suitable professionals are presented for the assignment and the DFID client makes the final decision. The VAWG Helpdesk has an Expert Pool of 18 senior VAWG professionals. We have a list of criteria for adding people to our expert pool, which are reviewed and approved by the team leader before proposing CVs to DFID. / A further component of the contract with the VAWG Helpdesk is the provision of guidance material. Guidance material aims to provide in-depth information, evidence and analysis that can support DFID in a range of topics related to VAWG programming. The material should give DFID programme managers and advisors tools and guidance on how to design, implement, monitor and evaluate VAWG programmes. / A further component designed to monitor and evaluate country and regional VAWG programmes is currently under procurement and should be up and running by the summer of 2014. / Finally the programme also has a Community of Practice component that has been established, and is managed in-house by the DFID VAWG team. This is a distribution list of staff working on and interested in VAWG, used to inform those working on VAWG of key policy or evidence developments, to consult them on development of guidance and to raise awareness of VAWG issues.
Progress against expected results: / Indicator 1.1: Call Down Contract for roster of experts to give ‘hands on’ help on VAWG programming in-country available to and utilised by UK staff. / Baseline 2013: Basic Support and initial guidance offered from VAWG Team. / Milestone Year 1 (April 2014) 5 DFID Country Offices Country Offices report call down contract effective and relevant for their Violence against Women and Girls programming and policy engagement. / Actual February 2014: Milestone not met: although several pieces of work in pipeline / The Call Down Contract is operating well and has delivered or is in the process of delivering 3 pieces of work for DFID country offices (DFID Rwanda, DFID DRC and DFID Afghanistan). A further 2 pieces of work from country offices (DFID Nepal and DFID Ghana) were initiated as a result of the Help Desk and the availability of the roster of experts and are being taken forward outside the call down contract as they were outside the scope of the contracted services. / The scope of the contract includes in-country assignments (paid for by the Country Office) of up to a maximum of 4 weeks with additional time for follow up work in the UK. / A further 3 assignments are in the pipleline awaiting final Terms of Reference (DFID humanitarian programmes in Syria and the Philippines and DFID Ghana). So the volume of demand is nearly as the indicator anticipated, but there have been some issues over the effectiveness and relevance of the work as well as confusion over whether certain pieces of work can be done under this contract. / Feedback from country offices who have used this resource has been mixed. Some have reported that the work was effective and relevant for VAWG programming, but in some cases, the work did not meet all expectations. Examples include: / Rwanda - Assignment to develop a Business Case (BC) and ToR for VAWG programming – The Helpdesk provided a good team with great technical expertise and good flexibility which was appreciated by the office. However the team did not possess a great deal of experience on DFID Business Cases. The office was confident that they would be able to complete the BC on the basis of the advice they had received. The assignment is still ongoing. / Afghanistan – there were mixed views on this report. Feedback suggests that a good job was done in exploring the strategic context (including drivers of violence) and proposing a strategy and theory of change which was used in the design of DFID’s approach. However, there were several areas of the assignment TORs the consultants failed to address, including providing a monitoring and evaluation framework and a framework to influence donors. Overall it was felt that the report didn’t go far enough and much of what was presented was already known. To an extent this was due to poor sharing of information with the consultants prior to the in-country work. / At the end of the assignment the VAWG team undertook a review and key lessons have been captured and shared with will all parties. / Summary: Overall this milestone has not been met, partly based on the numbers of assignments completed, but also due to the mixed feedback on the quality of support. As this Output is demand led it is beyond the control of the implementing partners. The effectiveness and relevance of the work carried out also has room for improvement and lessons have been learnt from the Afghanistan assignment by all parties and the relevant processes reviewed. / Indicator 1.2: Helpdesk on VAWG programming for UK staff established and operational in UK. / Baseline 2013: Basic Support and Guidance offered by VAWG Pillar Staff. / Milestone Year 1 (April 2014) 15 requests for support from UK staff satisfied. / Actual February 2014: Indicator exceeded. / The milestone for this output has been exceeded, both in quantity of queries dealt with and in the satisfaction rating from those who used the service. / Key evidence provided by the helpdesk includes: / 27 helpdesk queries completed to date. / The average satisfaction score to date is 4.8 out of 5. / The Helpdesk is responding to a range of queries from across DFID including: Humanitarian Response Group, Conflict Humanitarian and Security Department, Gender Team, Nutrition Advisor, DFID Zambia, DFID Nepal, DFID Afghanistan and the Africa Directorate. / There is evidence that the reports received are helping DFID staff to scale up their programming (4 out of 7 staff surveyed agreed with this) but reports are also being used to influence other partners at country level, potentially having a wider impact. For example, the DFID Zambia advisor shared the report with GBV partners in-country. The nutrition advisor circulated the query on VAWG and nutrition to the DFID humanitarian network and the nutrition network and received very positive responses. Reports are also available on the VAWG Themesite. / There is also good evidence that the Helpdesk service is well known. All of the survey respondents who had not accessed the helpdesk services (5 out of 12 respondents) were aware of it but they were either: unsure how to access it, had gone elsewhere, aren’t working on VAWG or haven’t needed any support. At least 2 are planning to use it in the near future. Additional qualitative data from in depth interviews with 5 country offices carried out for this review, supports this evidence with all being aware of the resource and planning to use it if they hadn’t already. / Summary: Overall the milestone has been exceeded both in the number of queries dealt with and by the satisfaction of the end user. Evidence suggests there is good awareness of the helpdesk service and the service is having a positive impact on policy and programming and is being shared across teams. / Indicator 1.3: 12 Guidance Notes (4 p.a.) on best practice in VAWG programming produced and disseminated. / Baseline 2013: No guidance notes / Milestone Year 1 (April 2014) 4 guidance notes produced and disseminated. / Actual February 2014: Milestone not yet met: 3 guidance notes commissioned, 2 completed / This service is demand-led i.e. the VAWG Helpdesk responds to requests from the DFID VAWG Team for new guidance. So far, the Helpdesk has responded to all requests and delivered the draft and final guidance notes within the agreed timeframe. To date DFID have commissioned 3 guidance notes, 2 of which have been delivered. These are: / ‘Briefing Paper on Prevention and Response to VAWG in Emergencies’ and; / ‘Responding to VAWG in Security & Justice Programmes’. / The VAWG Helpdesk is now developing a new DFID Guidance Note on “Addressing VAWG through Education Programming”, which is due to be submitted to DFID in April 2014. / The Guidance Note indicator was perhaps over ambitious in that it did not fully account for the time needed from the DFID VAWG Team to drive this work. The VAWG team put a strong emphasis on ensuring the final products were developed in consultation with country teams or programme staff to ensure that they were practically relevant. The VAWG team also wants to tailor guidance notes that are driven by demand from country offices and advisors. The team are currently undertaking further consultation as part of this review to identify priorities areas for the guidance notes as well as preferences for format etc. / It may be worth reviewing the indicator for future years to assess whether plans are realistic for this demand led service. The milestones should also be reviewed as they are currently focused on quantity and not quality, with no measure of effectiveness or user satisfaction. / Evidence on the quality and uptake of the guidance notes was collected as part of the review. Anonymous surveys on wider country support, including guidance notes were disseminated to all DFID country offices, with 10 responses received. / These showed that: / 8 respondents had accessed 1 or more of the guidance notes; / All 8 found the guidance useful. / Interviews with 5 DFID country offices were also conducted for more in depth feedback to assess the quality of the guidance provided and 4 out of 5 had made use of the guidance and found it to be very helpful, in particular for business case development. The office that hadn’t made use of them gave time pressures and an over-abundance of guidance in the round as the reason. The current format is user friendly and all who had used them were happy with it, with 1 feeling that an interactive resource would be useful. The importance of engaging country offices in the development of the guidance was emphasised as was the benefit of having a VC based learning session for each note disseminated. This feedback is reflected in the recommendation section of this review. / Summary: Overall this milestone has not been met due to the number of notes produced, and this is due entirely to the DFID demand side. However, the overall aim of this component is being met with evidence demonstrating that the guidance notes that have been produced are considered a useful resource, anecdotal evidence also suggests that they are used by other partners as well. Going forward, the VAWG team should continue to take a demand-led approach to developing guidance notes, focusing on quality and relevance, rather than simply volume of notes. / Indicator 1.4: VAWG Community or Practice (CoP) has large and diverse membership and is active in improving information sharing and best practice across UK on VAWG issues. / Baseline 2013: VAWG CoP has 60 Members / Milestone Year 1 (April 2014): VAWG CoP has 100 active members. / Actual February 2014: Milestone has been met. / The VAWG Community of Practice (CoP) has 96 members within DFID and there is also a parallel group of approximately 10 cross Government colleagues that can’t be part of a DFID distribution list but with whom we share information and details of events. This brings the total to over 100 members and this number continues to grow. / The Community of Practice has largely been used to inform those working on VAWG of key policy or evidence developments, to consult them on development of guidance and to raise awareness of VAWG issues. For example around 30 people attended the recent learning event on what works on prevention for VAWG from DFID UK, FCO and DFID country offices. / This indicator is DFID driven and to date the VAWG team have taken action to expand the CoP by raising awareness of it through, for example attendance of the advisory Continuous Professional Development (CPD) conferences in Africa and Asia in November 2013, and presentations on the team’s work to other, UK based staff including in other Government Departments. / It may be worth reviewing the indicator for future years to assess whether the milestones are appropriate as currently these only focus on increasing membership. We should also assess how useful the CoP is to its members. / The feedback received via anonymous surveys on wider country support, including the CoP, showed that / 8 respondents were members of the Community of Practice and all 8 find it useful. / There was also feedback in the survey on suggestions for improvements to the Community of Practice and from the interviews with 5 DFID country offices. This included strong support for the Community of Practice to share evidence digests and policy updates, including a request for country offices to be kept more up to date on international VAWG related events such as CSW to enable them to engage with their in-country partners. There was also some interest in newsletters and appetite for more discussion on VAWG topics and sharing good practice across country offices. This feedback is reflected in the recommendation section of this review. / Going forward, the CoP will become even more important as a means of securing buy-in and disseminating the results of DFID’s Research and Innovation Fund (RiF) as it starts to generate more policy and programme relevant evidence. The VAWG team need to give more consideration to how this will be done. / Summary: Overall this milestone has been met as the total number of people who form part of the CoP, including across Government, exceed the target. Evidence shows that members find the CoP useful but there is more that it could do to share information and initiate discussion forums on VAWG. Going forward the DFID VAWG team should review this indicator for the reasons set out above and consider how to maximise links with the RiF. / Indicator 1.5: Dedicated resource for evaluation of DFID’s VAWG programming to capture impact and learn lessons on ‘what works’ in preventing VAWG. / Baseline 2013: Few ad hoc evaluations of DFID’s VAWG Programmes / Milestone Year 1 (2014): Mapping of existing and planned evaluations complete and remit of evaluation resources confirmed. / Actual February 2014: Not met / This component of the programme is currently under procurement. It is expected to be up and running by summer 2014 at the latest. The delay in starting this component is due to a change in scope of the work and the lack of resources available in the VAWG team to progress this any sooner. / Impact Weighting (%):100 / Revised since last Annual Review? N/A / Risk: Low / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? / No / 1.2 Overall Output Score and Description: / B – Outputs moderately did not meet expectation. / This programme has scored a B, as 3 out of the 5 milestones for year 1 have not been reached, although most have come very close. This is largely due to a later start than anticipated, and the fact that the period being reviewed is not a full year. It may also be due to the fact that some of the log frame targets were over-ambitious, especially given that the DFID VAWG team had reduced human resources over a period of time whilst the programme was starting up. / Overall the progress is good and the programme is performing well against the objectives. / 1.3 Direct feedback from beneficiaries / As this programme focuses on support to DFID staff, albeit to support their externally facing work to prevent and respond to violence against women and girls internationally, we have consulted every DFID Country Office as well as service users in the UK through questionnaires via Survey Monkey to help ensure independent verification of the review’s findings. We had feedback from 12 respondents to the helpdesk questionnaire and from 10 respondents to the wider support questionnaire. The information from the survey responses was supplemented by interviews with key country office staff in 5 of our offices. A summary of information from the surveys is attached at Annex A and B. Indirect beneficiaries of the programme will be those supported through increased DFID programming on VAWG issues. Output 1.5, which is currently being procured, will help the DFID team to develop a clearer methodology for assessing numbers benefitting from DFID’s increased focus on VAWG.
1.4 Summary of overall progress / Overall this programme is making progress and meeting the increasing need for advice and support from country offices as well as UK based staff to enable continued scaling up of work to tackle VAWG. / There has been good and increasing uptake of the VAWG query service, there are a number of country assignments in the pipeline, a new guidance note is being developed and membership of the CoP continues to grow. Evidence from this review suggests overall high levels of satisfaction with the support available and appetite for more advice, information and discussion on this complex priority area of work. / The mapping work that is currently being procured under this programme will give a good indication of the extent to which VAWG programming is being scaled up across DFID offices and the evaluations will enable better understanding of how effective these programmes are. / Following this review, the programme management team will consider submitting a request for a no-cost extension to be able to extend the Helpdesk service for an additional 1 or 2 years. This would ensure resources are available to provide ongoing support as this, still relatively new area, of DFID programming develops and would allow the programme to tie in with its sister programme the pioneering Violence against Women and Girls Research Innovation Fund that will focus on what works in preventing violence against women and girls and drive innovation, generate ground breaking new evidence, and support new prevention programmes on the ground.
1.5 Key challenges / The DFID VAWG team has been under-resourced for much of the year and this has affected the ability to deliver all components of the programme to schedule and to maximise awareness raising activities. / The area of work, although an important priority for DFID country offices, is complex, cross cutting and requires a lot of in-country advisory time and expert knowledge. Country offices need to be regularly reminded of the resources on offer (without being overloaded) and in many cases supported to access them. / The demand led nature of the helpdesk service means that it is difficult for them to plan expert time ahead and to ensure that support is available when needed, as DFID staff often have very quick turnaround times for short notice work. / Looking ahead it will be important to ensure that this programme complements and supports the new VAWG Research and Innovation Fund, ensuring that the support provided has a direct, positive impact on DFID’s ability to deliver effective policy and programming on VAWG.
1.6 Annual Outcome Assessment / The outputs are on track in general and are responding to demand. Evidence from the surveys suggest that they are influencing country programming. The final component, once underway should provide us with more hard evidence as to whether the programme is really resulting in more beneficiaries being reached on VAWG work.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes. / The Preventing Violence against Women and Girls Scaling up Country Support programme started in April 2013 (commissioning of guidance note on Prevention and Response to VAWG in Emergencies) with funding of £1.87m, over 3 Financial Years, split between 3 components. Current funding is due to end on 31st March 2016. / At the moment the project is demand led as only the Help Desk, Call Down Contracts and Provision of Guidance Notes elements are up and running. In this respect the programme is on track against financial forecasts with the Monitoring and Evaluation component currently under procurement. / 2.2 Key cost drivers / The programme consists of 3 components and requires partners with significant experience and expertise in prevention of VAWG as well as knowledge and experience in designing programmes and projects focussing on VAWG and monitoring and evaluation. / The key cost drivers of all 3 components are programme staff salary costs (including travel and subsistence costs), with personnel engaged in the Helpdesk and the development of supply-side products such as guidance notes and monitoring, mapping and evaluation of DFID’s VAWG programmes. / 2.3 Is the project on-track against original timescale: No / There has been slippage in the monitoring and evaluation component due to lack of DFID resources to take this forward. This component is expected to be up and running by summer 2014, therefore we will be in a position to review progress on this indicator for the next annual review. We do not expect this delay to prevent the programme from achieving its overall outcomes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project. / The evidence from the review suggests that the anticipated demand from country offices for the support provided is there and growing as awareness increases. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Low. / 4.2 Assessment of the risk level. / The risk rating remains low. No changes needed following the recent CHASE risk review exercise. Risk rating will be continually monitored.
Risk of funds not being used as intended. / The likelihood of misuse of funds is very low. A number of checks and balances are in place to prevent misuse of funds and checks with DFID advisers and programme managers in country sites monitor release of funds. The Help Desk model is demand driven with agreed remuneration and standardised charges for the various pieces of work listed in our contractual agreement. / Climate and Environment Risk. / Low: No change since original classification by Climate and Environment Adviser.

5. Value for Money
5.1 Performance on VfM measures / The rationale for setting up the VAWG Scaling up Country Support Programme was that DFID advisors and other UK Government Departments (primarily country based) working on programmes needed quicker and flexible access to good quality expertise in data, evidence, results, indicators and advice on entry points for scaling up prevention of VAWG programming.In terms of outputs, the programme provided two key services for DFID advisors: / Provision of a Helpdesk: UK Gov Depts are able to quickly access bespoke expertise on a range of programme related enquiries. This includes support with all aspects of programming e.g. gathering of evidence/data to inform a particular intervention options, establishing value for money, setting meaningful impact indicators, review of log-frames, literature reviews of previously unexplored areas etc. provision of oral briefing and written papers either virtually or following in-country visits. These outputs are delivered often to very tight deadlines. / Provision of Supply Side Products: As well as responding to helpdesk requests, the organisations involved in the programme will develop guidance, good practice guides and interactive presentations to DFID’s specification on a range of key issues including: developing robust theories of change, and innovative methods in monitoring and evaluation. / Having a centrally managed contract in place allows quick and easy access to a range of quality expertise saving time and money in sourcing and contracting. / 5.2 Commercial Improvement and Value for Money. / All parts of the Scaling up Country Support Programme, with the Helpdesk in particular, allow DFID to tap into a rich vein of specialist external knowledge. The flexibility of the Helpdesk is an advantage (providing the ability to respond over different timescales to small and large requests alike). Sometimes helpdesks can be somewhat formulaic, and this one’s flexibility makes it easier for advisers to get what they need. The programme is meeting a tangible demand and is considered good value for money. The VAWG team will look at ways to increase value for money by revisiting the contracted services on evidence gathered in this review to provide a more comprehensive service to UK Government Depts. / 5.3 Role of project partners. / At the moment the Help Desk component is fully operational with a Strategic Oversight Committee consisting of representatives of each consortium organisation and DFID’s programme management team meeting quarterly to review progress. There may be scope to widen this forum to include OGD’s or partners from the Monitoring and Evaluation component as the programme progresses. / 5.4 Does the project still represent Value for Money : Yes / From evidence gathered the programme is helping improve the quality of DFID programmes and expand the knowledge of our in house staff. It would be more expensive for each country office to obtain this knowledge and expertise on an ad hoc basis as our centrally negotiated and managed contracts will drive down and standardise costs. We will to continue to drive value for money by addressing issues such as reviewing current contractual agreements to provide a more comprehensive service and widely disseminate knowledge products. We will also work to ensure that DFID and HMG staff are aware that the helpdesk products are available across HMG to be drawn on more widely to maximise VFM. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions. N/A

7. Conclusions and actions
Recommendations from this review: / For the VAWG Helpdesk team: / The Helpdesk team should seek advice from DFID programme team immediately if request comes in that is likely to be outside scope of contract. / The Helpdesk team/expert leading a country assignment should ensure they have the necessary information from country office prior to commencing work, and should alert the DFID VAWG team immediately if there are any concerns. / Helpdesk to take reasonable steps to build experts familiarity with DFID systems and processes, including business cases. / Helpdesk team to provide input to revising and updating the programme logframe following this review to ensure that it is measuring both quantity and quality of the service and that the milestones are accurate and realistic. / Run a VC learning event for DFID offices (with the DFID VAWG team) following publication of each guidance note. / For the DFID VAWG team: / The DFID VAWG team should review the overall programme logframe in association with partners to ensure that it is measuring both quantity and quality of the service provided and that the milestones are accurate and realistic. / Helpdesk – output indicator 1 and 2: / The DFID VAWG team should review the Help Desk Service Level Agreement together with partners and DFID Procurement Group to provide a more comprehensive service following the feedback from this review. / Guidance notes – output indicator 3: / The DFID VAWG team should: / Continue to ensure that the quality of guidance materials and input from country offices is prioritised and should consider whether the quantity needs to be reduced or spread over a longer period / Continue to seek suggestions for future guidance note topics from country offices and consider having one on measuring results, as well as looking at whether the existing VAWG Theory of Change and Community Programming notes need to be updated. / Work with partners to explore avenues to introduce more interactive guidance notes at the same time as maintaining current printable PDF format. / Community of practice – output indicator 4: / The DFID VAWG team should: / Widely publicise the VAWG Themesite discussion page within the Community of Practice to encourage interactive discussions on current topical VAWG issues. / Consider organising regular learning events publicised through the Community of Practice, timed to ensure maximum participation of Country Offices. / Use the Community of Practice to share evidence digests and policy updates (including of DFID UK involvement in key international VAWG related events) / Pilot a regular newsletter to the Community of Practice and explore how to include country office updates in this and wider communications through Community of Practice. / Give more consideration to how to maximise synergies with the Research and Innovation Fund (RiF) as it starts to generate more policy and programme relevant evidence. / Wider issues / The DFID VAWG team should: / Consider identifying a lead point of contact from the team to be the primary point of contact for each country office on VAWG and to maintain proactive contact with each office / Continue to scope the demand and need from country offices for VAWG related training and explore options for meeting this need. / Consider how to improve coordination between centrally managed and country programmes on VAWG. / Identify and promote opportunities for 10% advisory support within the team to supplement the team’s resources and increase overall capacity and knowledge of VAWG within DFID.

8. Review Process
This was a desk-based review undertaken by CHASE (Victoria Clements, VAWG Deputy Team Leader, John McGinn, Deputy Programme Manager) in February 2014. We have used a combination of self-assessment by the helpdesk, backed up with feedback obtained from DFID staff as part of the helpdesk query closure management procedures. To provide some independent verification of findings, we commissioned anonymous surveys via Survey Monkey. One survey focused on the Helpdesk and one on wider country office support. Both went to DFID country offices and the former also went to UK based users of the helpdesk. There were 12 respondents to the Helpdesk survey and 10 to the wider country support survey. A summary of information from the surveys is attached at Annex A and B. The information from the survey responses was supplemented by interviews with key country office staff in 5 of our offices.