Type of Review: Annual Review

Project Title: Saferworld Programme Partnership Arrangement (PPA)

Date started:	June 2011 Date review undertaken: August 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing £5.1m over three years to Saferworld as part of DFID’s programme to fund civil society organisations – the Programme Partnership Arrangements (PPA). / Saferworld is a not-for-profit organisation that believes that everyone should be able to lead peaceful fulfilling lives, free from insecurity and violent conflict. They work towards meeting three ‘peace conditions’ vital to achieve this overall vision: / people are free from fear and insecurity / people have fair and effective paths to address their grievances / people are central to preventing conflict and building peace / A broad range of actors have a role to play in achieving these peace conditions. By positively influencing the behaviour of these actors Saferworld seek combined policy and practice change to ensure that: / Individuals and communities have the opportunity and capacity to influence effective responses to conflict and insecurity, and to promote peace / National and international civil society plays an active role in influencing authorities and building capacities for peace / National and local authorities are responsive and accountable to people’s needs and their actions help to build peace / External actors operate in a way that supports peace, including through their aid and international assistance policies and their engagement in conflict-affected and fragile contexts / Saferworld puts people at the heart of all its programmes. They work directly with communities affected by instability and conflict to articulate their safety concerns and improve their sense of security. Community security is fostered by first investing sufficient time and energy to gain the trust of local communities, and then supporting them to voice their concerns and aspirations to those in power. They achieve this through developing collaborative partnerships with local organisations. They also document lessons from their work, and the work of others, to create learning and evidence to inform policy and practice more generally: international norms and frameworks for development, peace-building and state-building provide important standards for all actors, but must be informed by the experiences of those most affected by violence and conflict. Consequently, through their programming, policy development and advocacy, they challenge national and international actors to listen to the views and priorities of those living with insecurity, while at the same time, seizing opportunities to influence and support civil society, governments and international agencies to respond in a sensitive and accountable fashion. / To note: Saferworld also has funding relationships with DFID’s Country Offices in Somalia, Kenya and Uganda. This has changed from 2011/12. Saferworld did have a research grant and co-funded projects in Kyrgyzstan and Nepal which naturally concluded. Although the number of grants has decreased, Saferworld’s relationship with DfID in both Kenya and Somalia deepened last year (with a particular focus on election security in Kenya and civil society support in Somalia), while in Uganda, the project continued as part of an on-going commitment.

What are the expected results?
Saferworld works at the intersection of conflict, security and development at both policy and programming levels, focused on 18 conflict-affected contexts across East Africa, Central and South Asia, the Caucasus, Eastern Europe and the Middle East. Their advocacy work seeks to improve international policy and programming in such contexts. They use the strategic funding provided by the PPA to: / Underpin the extensive commitment of time and energy required to influence change at the local level with communities in conflict-affected contexts – meaningful change is normally achieved through trust and significant accompaniment. / Provide space and capacity for innovation and learning, in order to better inform practice – such as piloting new approaches which are hard to undertake with project-specific funding. / Enhance their ability to link international policy work with their in-country programming – plan for higher-capacity and more flexible and appropriate responses for fragile and conflict-affected contexts. / Be responsive to emerging policy trends and unforeseen opportunities – as they relate to conflict prevention and security building. / Make investments in their staff, operational and administrative functions – to boost effectiveness and value for money. / In terms of results, the PPA is expected to deliver the following: / Impact: A reduction in violent conflict and insecurity in Saferworld (SW) target countries. / Indirect Outcome: Civil society organisations and authorities increase the impact of their contribution to preventing conflict and increasing community security. / Outcome: Individuals and communities, civil society, authorities and external actors strengthen their approaches and capacities for preventing violent conflict, building peace and addressing the needs of conflict-affected (or at risk) communities, (in accordance with Saferworld's organisational change model), in Bangladesh, Georgia/Abkhazia, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sri Lanka, South Sudan, Uganda, Yemen. Output 1: In Georgia/Abkhazia, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan, SW and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities. / Output 2: In Georgia/Abkhazia, Kosovo, Kyrgyzstan/Tajjikistan, Somalia, Uganda and Yemen, local civil society organisations receive support from SW to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts. / Output 3: In Kenya, Kosovo, Nepal and South Sudan national and local authorities receive support from SW to assist them in developing effective policies and practical approaches for building peace, justice and security. / Output 4: External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries. / Output 5: SW, in consultation with DFID, develops and applies a robust monitoring and evaluation system which enables the identification, measurement and communication of results at output and outcome level, and demonstrates contribution to impact level.

What is the context in which UK support is provided?
Support to Civil Societies to deliver DFID objectives: / Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / In order to achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs and following a robust selection process and implementation of a Resource Allocation Model, partners have been identified for a 3 year PPA to begin in April 2011. Saferworld is one of these. / International/ UK Context for Security and Justice Interventions: / Internationally, the consensus around the contribution that safety and justice can make to stability and development has also become increasingly well established. The World Development Report (2011), for example, found that insecurity ‘has become the primary development challenge of our time’ and is a major obstacle to the successful achievement of the MDGs. The New Deal, which was agreed at the 4th High Level Forum on Aid Effectiveness in Pusan, South Korea in December 2011 also recognises the importance of security and justice as key elements of peace-building and state-building strategies. / UK aid addresses the causes of poverty as well as the symptoms. Rule of law has been identified by the UK Prime Minister as part of the Golden Thread linking open economies and open societies, which is a key enabler for successful economic and social development. Security and justice are also important considerations for poor people: the 2000 World Bank report Voices of the Poor identified that security and justice are as important to poor people as hunger, employment and lack of safe drinking water. As a result, DFID has committed to scale up its support for security and justice reform in 18 countries following the Bilateral Aid Review in 2011, and the UK Government’s 2011 Building Stability Overseas Strategy (BSOS) restates and reiterates the central contribution that functioning security and justice systems can make to creating stable and open societies and economies. Furthermore, the UK recognises the positive developmental impact that targeted investments in women and girls can make. As such, the UK has committed itself to improving access to safety and justice for 10m women and girls globally by 2015. The UK’s support to Saferworld will make a substantial contribution to the achievement of improving security and justice for poor and marginalized communities in target countries.

## Section A: Detailed Output Scoring

Output 1: In Georgia/Abkhazia, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan, Saferworld and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities
Output 1 score and performance description: A++ Outputs substantially exceeded expectation
Progress against expected results: / Indicator 1.1 Number of action-oriented community groups formed by members of conflict-affected communities in Georgia/Abkhazia / Kenya / Kyrgyzstan/Tajikistan / Nepal / Pakistan / South Sudan - with Saferworld support - through which communities can identify their security related needs and priorities, and develop a shared purpose and vision for change / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / 10 groups formed SW continues support to the groups formed in Year 1, where appropriate, and an additional 10 formed A total of 26, over three years / Achieved 12 17 / Variance +2 +7 / Disaggregated data / Narrative on progress: Saferworld report that they continued to support pre-existing community action groups in Central Asia and the Caucasus, and supported the creation of new groups in Nepal (12) and Kenya (5). In South Sudan, Saferworld supported an existing Police Community Relations Committee (PCRC), to avoid duplication. The careful creation of these representative and sustainable fora is a crucial step towards results at the outcome level. An evaluation of the Central Asia programme said; ‘community stakeholders contrasted Saferworlds programme with their experiences of other externally driven projects, highlighting its approach of empowering community security working groups to identify and address their own local security needs as a unique strength of the programme’ and ‘the establishment of dedicated informal structures in the form of community security working groups has been effective, primarily through the care taken to ensure they are representative of their whole community and the intense support given to them by Saferworld and the Partner Coordinators.’ / Assessment of overall progress towards indicator: The milestone was achieved. Creation of two new groups in South Sudan was delayed by insecurity and violence between police and communities. Saferworld has not yet reached the stage of implementing a community security programme in Pakistan. / Indicator 1.2 Number of community groups in Georgia/Abkhazia, Kenya / Kyrgyzstan/Tajikistan / Nepal / Pakistan / South Sudan who have the opportunity, as a result of SW-facilitated meetings, to voice their security and justice concerns to local authorities in order to begin identifying joint solutions and plans for action / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / 8 community groups have had the opportunity to voice concerns to authorities and begin identifying joint solutions and plans for action An additional 10 An overall total of 24, over three years / Achieved 12 18 / Variance +4 +8 / Disaggregated data / Narrative on progress: Saferworld reported that they supported 18 new groups (12 in Nepal, 5 in Kenya and 1 in South Sudan) to voice their concerns to authorities and involve them in implementing action plans, while continuing this support to groups in Central Asia and the Caucasus. The approach varied in Nepal where local government and police representatives participated as official advisors to its groups (reflecting learning from a previous project). They attend every meeting of the community group, increasing trust and buy-in. In South Sudan, Saferworld’s support has built the confidence of community members to raise issues in the PCRC meetings, in which they had previously participated passively. / Assessment of overall progress towards indicator: The milestones have been exceeded. New models have been tested in Nepal and provide learning for other programmes. / Recommendations: / Indicator 1.1: Amend target to a total of 44 plans over 3 years. / Indicator 1.2: Amend target for year three a total of 40 groups over 3 years. / Comments from Review Team: Saferworld have scored themselves A++ for this output. Given the almost doubling of achievements to targets and based on available evidence, CHASE agrees that this output should be scored A++. CHASE also agrees with Saferworld that targets for year 3 should be revised upwards. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: In Georgia/Abkhazia, Kosovo, Kyrgyzstan/Tajikistan, Somalia, Uganda and Yemen, local civil society organisations receive support from Saferworld to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts.
Output 2 score and performance description: A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 2.1 Number of local CSOs in Kyrgyzstan/Tajikistan / Uganda / Yemen who receive targeted and tailor-made high-quality training / capacity-building from SW on areas such as strategic planning, advocacy, conflict analysis and monitoring and evaluation, and on the technical aspects of conflict-related issues relevant in their country / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / High quality, tailor-made training / capacity-building has been provided to 6 CSOs An additional 6 CSOs A total of 16, over three years / Achieved 4 7 / Variance -2 +1 / Disaggregated data / Narrative on progress: Saferworld reported that 10 CSOs in these countries have received training / capacity-building in this period, 7 of them ‘additional’ CSOs not reported on last year. 70 youth activists have been counted as ‘1’ for the milestone. Saferworld provides CSOs with on-going support and accompaniment, based on a capacity needs assessment. The examples below highlight on-going partnerships. / Yemen: / National Organisation for Development of Society received training on designing a community security programme and capacity-building on financial management. / Tamkeen Development Foundation received training on research and data analysis. / Partners for Democratic Change received training on research and facilitation skills, and a subsequent report demonstrated increased grasps of key concepts and methodology; / Resonate! Yemen in the youth activists programme; having delivered one advocacy training alongside Saferworld, they delivered a second independently. / 70 youth activists in Yemen received: training on conflict analysis, which received very positive feedback; advocacy training and networking events; and capacity building on financial management. / Uganda: / Saferworld trained the Uganda NGO Forum on conflict-sensitivity, and advocacy. Saferworld delivered training on applying conflict analysis during project planning, implementation and M&E. / Central Asia: / Foundation for Tolerance International, Youth Initiatives for Development (MIR) and Association of Scientific and Technical Intelligentsia of Tajikistan Partnering with Saferworld has enabled them to fill gaps in their previous knowledge on conflict-sensitivity and analysis conflict. It is ‘clear’ that they ‘would not have developed such a committed approach without the considerable institutional capacity building provided by Saferworld staff’. / Liberal Youth Alliance (Kyrgyzstan) developed a network of CSOs promoting police reform. Saferworld trained them on community-based policing, research and advocacy. / Assessment of overall progress towards indicator: Saferworld reported that it has provided quality support to a total of 10 CSOs in these countries in this period, and the milestone has been over-achieved. The target is likely to be under-achieved because the logframe counts additional CSOs trained each year. Saferworld’s model of partnership is to work with the same partners over a number of years, leading to sustainable increases in capacity. / Indicator 2.2 Number of local CSOs in Georgia/Abkhazia / Kosovo / Somalia who receive support from SW to articulate and convey the needs and views of their constituents within policy development processes. / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / A total of 5 CSOs have been supported by SW to articulate needs and views of constituents within policy development and dialogue processes An additional 3 CSOs A total of 10 CSOs, over three years / Achieved 6 3 / Variance 0 / Disaggregated data / Narrative on progress: Saferworld reported that 6 CSOs in these countries have received support to convey the views and needs of their constituents in policy-making processes, 3 of these additional this year. / Caucasus / The Institute for Democracy and the Abkhazia Community Reference Group, attended a seminar (organised by Saferworld) with the deputy Prime Minister, at which they jointly identified the need for an ombudsman, new criteria for entering government service and a liaison forum for law enforcement agencies and community members. This was a direct opportunity for communities to voice their perspectives to senior officials. / Somalia / Non State Actor Platforms in Somalia/land reflect the needs and views of ordinary Somalis within national and international policy-making processes. Platforms have sought and gathered the perspectives of local actors on pertinent issues and policy-making processes, including: / Somaliland Non State Actor Forum (SONSAF) was entrusted by the local authorities to conduct pre- & post-election consultations with local civil society and community members and consulted with around 1,000 people on their pre-election Citizen’s Dialogue. / Through a MoU with the National Election Commission, SONSAF deployed 800 election observers, consisting of all sections of civil society, providing the opportunity for members of civil society to participate in, and promote fairness and accountability in relation to, the democratisation process. / Puntland Non State Actor Association (PUNSAA) held a consultation meeting on the barriers to forming political associations attended by 66 civil society and other representatives. Participants developed an action plan, calling for the establishment of constitutional court, an inclusive media law, increased time for political associations’ registration and civic education workshops. Following the meeting, the Transitional Puntland Electoral Commission’s expressed its interest in working with PUNSAA to this end. / South Central Somalia Non State Actor Forum (SONCENSA) consulted constituents on the issue of youth and arms in Somalia following a request from the UN Disarmament Committee to hold consultations that would assess the needs of young people and make recommendations to the UN on youth disarmament. / SOSCENSA and Somali Media for Environment, Science, Health and Agriculture (SOMESHA) organised a consultation meeting with civil society representatives. Participants developed a roadmap for achieving sustainable agricultural practices as a way to increase resilience to climate change. / Kosovo / Saferworld has provided long-term support to Forum for Civic Initiatives (FIQ) to consult with the public on security issues and influence policy change. FIQ is now recognised as a central player in this regard and is part of the Government-led working group to develop a new arms controls strategy. In this period, FIQ organised a consultation process to gather public perceptions, and prepared a resulting set of recommendations, which it submitted to the working group. / Assessment of overall progress towards indicator: Saferworld is on track to meet the target. / Recommendations: / Indicator 2.1: Reduce the target to a total of 13 CSOs over three years. / Indicator 2.2: None / General Comments from Review Team: Saferworld have scored themselves A+ for this output. On first review of Saferworld’s Annual Review Self-Assessment, CHASE suggested that a score of A would be more appropriate as Indicator 2.1 was exceeded by one this year (although off target by 1 over Years 1 & 2) and Indicator 2.2 delivered what was expected. Based on discussions with Saferworld, a review of the self-assessment guidance and available evidence, the review team has however agreed to reinstate the A+ score for this indicator. Details of the discussion with Saferworld are outlined below, in the response they provided to DFID’s original feedback on their AR Self-Assessment. / Response from Saferworld: In deciding what ‘score’ to give Saferworld for this output within our self-assessment, Saferworld report that they were led by p. 16 of the guidance for completing the Annual Review Self-Assessment, according to which Saferworld were instructed to ‘answer in reference to overall output statement not individual indicators’. Saferworld therefore referred to the output statement - In Georgia/Abkhazia, Kosovo, Kyrgyzstan/Tajikistan, Somalia, Uganda and Yemen, local civil society organisations receive support from Saferworld to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts’, and felt that against this statement Saferworld had ‘moderately exceeded our expectations’ (as per a score of A+). This therefore led them toward a different, and Saferworld felt more accurate conclusion about their overall level of work and achievements in this area, than if Saferworld had answered only in accordance with their performance against the indicators and the numbers contained in the milestones. This is partly because, as noted in their report, the indicators capture increases in the numbers of organisations Saferworld are working with, whereas actually Saferworld’s model is to work with the same organisations over a period of time, creating a genuine partnership within which capacity can be substantially developed. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: In Kenya, Kosovo, Nepal and South Sudan national and local authorities receive support from SW to assist them in developing effective policies and practical approaches for building peace, justice and security
Output 3 score and performance description: A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 3.1 Number of government-led policy development processes in Kenya, Kosovo, Nepal and South Sudan to which SW provides quality technical input and support / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / SW has provided quality technical input 5 policy processes SW has continued support to the policy processes reported under Milestone 1 (where they are still underway) / An additional 5 policy processes A total of 12 policy processes, over three years / Achieved 11 8 / Variance +6 +3 / Disaggregated data / Narrative on progress: Saferworld reported that it supports the development of policies related to peace and conflict prevention in a variety of ways: / Promoting a consultative approach to policy development, within which the needs and views of civil society and the public are sought out and represented; / Supporting the capacity of local civil society to engage in and influence policy processes / Providing expert advice on the technical content of policies / Drawing on experience of supporting similar processes in other countries, taking into account varieties in context, need and capacity / Inputting experience of working at the local and community level; providing information on the situation at ground level and recommendations on appropriate models and approaches / Publishing recommendations and policy briefs / In this period, Saferworld has supported 8 policy development processes. / Kenya / Saferworld supported the Independent Electoral and Boundaries Commission IEBC and the National Police Service (NPS) to develop a draft framework for coordinating election security arrangements, draft training content on election laws, and a draft election laws handbook for security agents. These are currently in use to train the police. / Saferworld provided technical assistance to the NPS to draft a national community policing framework; the basis for a national policy on community policing. Saferworld held meetings with the NPS to identify existing gaps and opportunities, facilitated a meeting of key stakeholders at which ToRs were developed, and shared its training materials to inform new NPS materials on community policing. / Saferworld and the civil society Usulama forum are supporting the review of the NPS standing orders (SSOs), seeking to harmonise them with Adminstrative Police SOs, and apply them to the National Police Reserve (community volunteers). Saferworld plans to organise consultations and provide technical expertise to the drafting process. / Saferworld helped the Internal Accountability Unit to finalise documentation on police complaints mechanisms and ran sensitisation workshops for police officers. / Kosovo / Saferworld provided expert input to the Administrative Instruction to improve the workings of the Municipal Community Safety Councils (MCSCs). Saferworld is on the Steering Group overseeing implementation of the National Community Safety strategy. Saferworld has worked with MCSCs at the local level and used this experience to highlight current weaknesses in the practices of MCSCs but also to provide a model for how they can work effectively. / Saferworld and partner FIQ advised on the content of the new National Small Arms Control and Light Weapons Control and Collection Strategy, 2013-15. Saferworld helped to design a public consultation process on the strategy. / South Sudan / Community Security and Small Arms Control Bureau (CSSAC Bureau): having previously provided technical input to a national policy (which was passed in this period) and legislation (which is awaiting parliamentary approval), Saferworld continued work on Regulations on Small Arms Control. Saferworld advocated the need to establish a drafting committee to prepare the Small Arms and Light Weapons (SALW) regulations, provided technical advice on the content of the regulations, and facilitated drafting sessions. / Nepal / Saferworld is working with the Nepal Peace Trust Fund, providing feedback on the peacebuilding potential of proposals submitted by government ministries. Saferworld’s feedback has covered issues of inclusion, gender sensitivity, conflict sensitivity and M&E. / Assessment of overall progress towards indicator: Saferworld has exceeded the three year target. While some processes have stalled, Saferworld’s work has been particularly significant in Kenya in this period, linked to elections and ongoing police reform. / Indicator 3.2 Number of formal / informal governing institutions in Kenya / Kosovo / Nepal / South Sudan who receive quality technical support from SW to assist them in developing more participatory approaches to addressing people's security and justice needs / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / Achieved A total of 4 institutions have received technical support An additional 4 An total of 10 over three years / Variance 5 4 / Disaggregated data +1 0 / Narrative on progress: Saferworld report that it has advised a total of 8 institutions on participatory approaches; 4 of them (local government in Kenya, the CCSSAC Bureau, the MCSCs and the Village Development Committees (VDCs) are additional institutions. / Kenya / Saferworld and partners promoted enhanced co-operation between the NPS, local government and communities, in six counties at risk of election-related violence and provided small grants and technical advice for ‘rapid responses initiatives’ through which these mechanisms could react, in real time, to identified risks. This led to authorities addressing needs in a timely manner and with the active participation of civil society and community representatives. / Saferworld and Usulama supported the NPS to take a more participatory approach. They have: worked with the NPS to develop a software tool through which the public can provide feedback on their performance; co-ordinated civil society monitoring of the recruitment of senior police officials; supported the formation of community-level peace and action groups; and provided training on community policing. / South Sudan / Saferworld’s work in Kuajok is building more co-operative and open relationships between police and communities, through supporting public participation in PCRC meetings.143,144 / Saferworld’s ongoing technical support to the CSSAC Bureau has included advice on how to make the process of developing small arms legislation and regulations more participatory, encouraging the inclusion of CSO experts within the drafting process. / Kosovo / Saferworld’s input is strengthening the role that MCSCs in Kosovo play in developing and implementing participatory approaches to community safety. Saferworld’s technical input on the new Administrative Instruction to MCSCs, which enhances their mandate and capacity, drew on previous experience of working directly with MCSCs to develop and implement action plans with local communities. / The Ministry of Internal Affairs is taking a participatory approach to developing the new Small Arms Control Strategy; Saferworld advocated the need for consulting with civil society on the content of the policy and helped design the consultation process. / Nepal / The direct involvement of police officials within Saferworld and partners’ community security programme is enhancing their cooperation with communities. VDCs are taking a more participatory approach by including joint police-community initiatives within their annual plans. / Assessment of overall progress towards indicator: Saferworld is meeting its milestones. / Recommendations: / Indicator 3.1: Increase target over the three year period to 22. / Indicator 3.2: None. This indicator is problematic because the milestones measure the number of ‘additional’ institutions supported each year, whereas Saferworld’s model of working is to provide ongoing support to particular institutions over a period of time. / General Comments from the Review Team: Saferworld have scored themselves A+ for this output. Based on available evidence, CHASE agrees that this output should be scored A+. CHASE also agrees with Saferworld that targets for year 3 should not be revised upwards. However, DFID/CHASE should discuss how best to reflect depth of engagement in this indicator to capture the nature of long-term engagement with individual organisations. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries
Output 4 score and performance description: A++ Outputs substantially exceeded expectation.
Progress against expected results: / Indicator 4.1 Number and quality of research papers and policy briefings / reports published or electronically circulated by SW and disseminated to external actors / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / 12 briefings, papers / reports have been published or electronically circulated An additional 20 An additional 20 / Achieved 78 58 / Variance +66 +38 / Disaggregated data* / Narrative on progress: Saferworld report that they exceeded their target of research papers and policy briefings for 2012/13. SW received excellent feedback on the quality of these. Michael Anderson, Lead Adviser to the UK Prime Minister on Post-2015 said “Saferworld's materials were some of the best and most influential both for supporters of the peace agenda and for the sceptics”. / Assessment of overall progress towards indicator: Saferworld report they have significantly exceeded our target. / Indicator 4.2 Number of external actors receiving relevant, high quality training from SW, or participate in relevant and productive SW-facilitated seminars / roundtables, on engagement in fragile and conflict-affected countries / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / 50 people representing external actors have received training from SW, or participated in SW-facilitated seminars / roundtables An additional 50 Over 150 people, over course of three years / Achieved 53 1771 / Variance +3 +1721 / Disaggregated data / Narrative on progress: Saferworld have reported that they have exceeded their milestone of 50 people involved in Saferworld-facilitated seminars/roundtables. We have also presented at a number of high-profile international fora. / Assessment of overall progress towards indicator: Saferworld have been very successful in taking up opportunities to present Saferworld messages to external actors both through projects and through other on-going seminars and roundtables undertaken as part of our thematic work. / Indicator 4.3 Number and quality of products (including briefings and submissions) provided to the UK Government by SW, which build on evidence and lessons learned from SW programme implementation / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / The UK Government has received 3 products An additional 3 products A total of 10 products, over three years / Achieved 3 6 / Variance 0 +3 / Disaggregated data / Narrative on progress: While the majority of the reports and briefings during this period were disseminated to HMG officials, Saferworld report that they also produced outputs specifically related to UK Government policy and practice. These products focused on the Building Stability Overseas Strategy (BSOS) and upstream conflict prevention (3), the Preventing Sexual Violence Initiative and the UK National Action Plan on UNSCR 1325 on Women, Peace and Security (2) and on strengthening the UK Conflict Pool (1). FCO officials described Saferworld’s briefing on the Preventing Sexual Violence Initiative as ‘very useful’, ‘coming at the right time’ and having ‘certainly influenced the Preventing Sexual Violence Initiative team’. / Assessment of overall progress towards indicator: Saferworld exceeded the milestone. The launching of the new initiative on preventing sexual violence provided a good opportunity to input into HMG policy and practice. / Recommendations: / Indicator 4.1: Increase milestone to ‘an additional 40’ in recognition of projected continuation of engagement with a number of policy processes plus further outputs at the country level. Saferworld should also explore amending the target for this indicator to better reflect the qualitative aspect of this indicator. / Indicator 4.2: Saferworld and DFID should discuss how to accurately capture and reflect outputs in this area, including reflecting quality as well as quantity. / Indicator 4.3: Amend indicator to 5 additional products supplied to HMG in 2013/14, a total of 14 over the three years. Saferworld should also explore amending the target for this indicator to better reflect the qualitative aspect of this indicator. / General Comment from the Review Team: Saferworld have scored themselves A++ for this output. Given the production rate of policy papers and senior level independent endorsement for their quality, CHASE agrees that this output should be scored A++. There is a question as to how realistic the original milestones were given the extent to which they have been exceeded. CHASE also agrees with Saferworld that targets for year 3 should be revised upwards but need to balance and capture qualitative indicators with quantitative. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: Saferworld, in consultation with DFID, develops and applies a robust monitoring and evaluation system which enables the identification, measurement and communication of results at output and outcome level, and demonstrates contribution to impact level
Output 5 score and performance description: A Outputs met expectation
Progress against expected results: / Indicator 5.1 The quality of SW's monitoring and evaluation systems and approaches and the ability of SW to report fully and meaningfully against the indicators contained within the logframe / Baseline See logframe / Milestone 2011/12 2012/13 2013/14 / SW has established an institutional framework for M&E, including tools for capturing results at the outcome level of the logframe, and is able to report against the logframe in a meaningful and robust way. / DFID and SW have shared ideas relating to M&E and learnt from each other’s’ experiences SW has further strengthened its M&E framework and approaches, based on experience during Year 1, and is adapting its programming approaches based on lessons identified through M&E. / DFID and SW have continued to shared ideas relating to M&E and learnt from each other’s’ experiences SW has a strong M&E framework in place which has provided useful lessons for DFID and enabled SW to improve overall impact and effectiveness of its work. / Achieved See narrative on progress / Variance / Disaggregated data / Narrative on progress: Saferworld report that it has significantly strengthened its M&E, including incorporating theories of change into annual plans; quarterly reporting system; outcome monitoring which captures change, significance and contribution; participatory community security index whereby community members identify and monitor outcomes within ‘domains of change’; designing M&E component of new Karacel intranet; staff training. / Saferworld shared approaches with DFID and PPA grantees through learning groups, theory of change workshop, and discussion with CHASE lead, though potential exists for closer sharing in the next period. Saferworld and DFID also have shared ideas and learning on M&E through Saferworld support to DFID programmes in Pakistan and Nigeria. / Assessment of overall progress towards indicator: Progress in on track. / Recommendations: None / General comment from the review team: Saferworld have scored themselves an A for this output. DFID agrees with this assessment. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A+ programme moderately exceeded expectations. / 1.3 Direct feedback from beneficiaries / Within Saferworld’s community security work, they design and monitor programmes around perceptions of security and safety, and community relations with security providers. They commonly use the following methods: / Tracker perception surveys - these use standard sampling methods and FGDs and KIIs. These are repeated annually where possible, and show how wider community perceptions of security are changing (ultimate beneficiaries). / Community mapping exercises – these follow a standard approach in individual communities where we work, are public, and repeated annually (immediate beneficiaries). / These instruments typically allow SW to understand: / Level of feeling of safety: (disaggregated by sex and age and relevant geographic or ethnic differences) / Issues and problems affecting citizens’ security / Reasons behind insecurity / Results of the feeling of insecurity / Initiatives undertaken by participants to address problems / Behaviours/ perceptions of security authorities and other officials / They have used these instruments to follow trends in Kosovo, Central Asia, Caucasus, Nepal, Pakistan, Bangladesh, and Northern Uganda. Their new on-line system will eventually enable them to draw in tracker survey data to process alongside their results monitoring. / Immediate beneficiaries: Their Community security approach is based on participation by community action groups at all stages: conflict analysis, planning and design of responses, negotiation with security providers, implementation, and monitoring progress and evaluating results. Their Central Asia and Nepal programmes provide examples of how this works. / In Central Asia community groups work with local authorities to develop and implementation action plans. They participate in a structured evaluation process which includes assessment of outcomes, a sensitivity index, relationships between actors, contribution of each actor to the outcome, and an evidence box. As such, beneficiaries are at the centre of the process. / In Nepal, community groups have established a Freedom from Fear Index, built around outcomes that they themselves determine. They monitor progress against this and display monitoring information publicly, as a prompt for discussions with the broader community. / Proximate beneficiaries: The work SW does to influence national authorities is characterised, at the national level, by partnerships with particular security sector actors (such as the CSSAC Bureau in South Sudan, the Kenya Police Service, the Ministry of Internal Affairs in Kosovo). SW tends to think of these institutions as partners, and their feedback is sought at regular meetings and at the point of evaluation. / SW asks actors in the global policy community for feedback where it can and keeps records in its evidence box. They seek their views in any review or evaluation. SW’s work over 20 years on developing the momentum and content for an Arms Trade Treaty is currently the subject of an evaluative process, in which feedback is being sought from across the coalition working on the ATT, with an additional focus on ‘outcomes for money’. This will be complete by Autumn 2013. / Saferworld’s outline and examples of how they have collected beneficiary feedback to improve their work is clear and thorough and provides a learning opportunity for others working in similarly complex environments.
1.4 Summary of overall progress / Much of the approach and work conducted by Saferworld fits in extremely well with on-going policy and programme discourse in DFID on S&J and Rule of Law. The problem-centric approach to S&J is particularly welcome and the self-assessment report provides useful examples e.g. p8: example of reducing violent community relations in Kyrgyz and Tajik communities through community based problem-centric solutions (often which do not require solutions via formal S&J actors or approaches). / DFID is grateful to the Saferworld team and is pleased to endorse the A+ score of the overall programme. Looking forward, there are a number of key areas where we feel we the partnership could improve its overall level of performance: / As part of on-going learning, DFID needs to improve the way that it engages with Saferworld so as to maximise the use of learning, evidence and experiences from Saferworld’s programmes to inform future DFID policy and programming. This is especially the case given DFID’s evolving problem-centred approach to the Rule of Law. / A key issue with many reports from PPA partners is a need to better articulate in the high-level narrative on progress what the specific contribution/ role of Saferworld was in relation to the outcomes/successes. Illustrative examples include: / Outcome 1: Indirect Indicator 1. It was not clear from the narrative what specific activities/support were provided by Saferworld to deliver the outcomes. The self-assessment report noted: ‘9 CSOs supported by Saferworld have succeeded in supporting or influencing authorities to adopt new or revised policies/ approaches in this period. This period provides evidence of their skills and capacities, and the impact of Saferworld support’ (p12). What was not clear from the narrative report was how Saferworld facilitated this and what their contribution was. / Although constraints relating to the word limit of the self-assessment report are acknowledged, the report did, at times, lack some depth, analysis and evidence. An illustrative example is ‘In this period, 16 CSOs across 7 regions/ countries have demonstrated increased skills, confidence and capacity.’ / Much of the Saferworld theory of change references working with civil society organisations to build capacity and capability so that they are able to influence and persuade local and national security actors to improve their security. The PPA grant provides resources to facilitate dialogue, convene workshops/ seminars etc. This is an interesting approach to improving security through demand side channels (compare to classic supply side police reform programmes) and it is recommended that in Year 3 (and potentially beyond) Saferworld consider work with CHASE evaluation and results advisers (and others) to determine if it is possible to monitor and evaluate the processes and factors which determine the level to which demand side actors are able to successfully ‘influence’ the actions, behaviours etc of supply side security providers. Whilst it is recognized that research into M&E of ‘influence’ is a new field of study, it is felt that Saferworld’s projects may offer fertile ground for testing out such an approach which will be of benefit not only of Saferworld’s PPA but also for broader learning within DFID. / Saferworld have provided the following high-level commentary regarding their overall progress this year: / Individuals and Communities: 40 Community Security action plans were developed and 37 implemented in Nepal (12), Central Asia (12), the Caucasus (8) and Kenya (5). The process of people working together, often in communities with deep ethnic, historical or other divisions, leads to increased trust. These projects address barriers to security and development facing communities, and - through demonstrating that problems can be tangibly addressed – start to increase willingness to engage with authorities and break down feelings of isolation and apathy. / Civil Society: 16 CSOs across 6 regions / countries have demonstrated increased skills, confidence and capacity in issues of community security, conflict-sensitivity, and inclusive governance and political processes: Caucasus (2), Central Asia (3), Kosovo,(1) Somalia (3), Bangladesh (1), Uganda (3), Yemen (3). Of these, 9 are additional CSOs to last year. / Authorities: 6 institutions have developed new or strengthened approaches, policies or strategies (Kenya National Police Service (NPS), National Steering Committee on Peacebuilding and Conflict Management (NSC) and Independent Electoral and Boundaries Commission (IBEC); Government of Uganda, South Sudan CSSAC Bureau; Kosovo Ministry of Interior). Of these, 3 are ‘additional’ institutions. At least 3 institutions have started to change their practices in line with new strategies / policies / approaches: the NPS, the Municipal Community Safety Councils (MCSCs) in Kosovo, and District Local Governments in Uganda. / External Actors: Saferworld’s research, analysis, policy development and advocacy has had considerable success informing and influencing the policies and practices of external actors at international and national levels including: governments (9 - UK, US, China, Mexico, Sweden, Norway, Costa Rica, Uruguay, Palau); multilateral organisations (4 - UN, EU, OECD, G8); UN High Level Panel; civil society organisations and networks (4 - Control Arms, Beyond 2015, InterAction, Alliance for Peacebuilding) representing over 500 CSOs; and INGOs and other actors (10 – Global Witness, Christian Aid, International Alert, Crisis Action, The Elders, Social Development Direct,, Institute of Development Studies; Overseas Development Institute; Independent Commission on Aid Impact and the British Council). Out of this total of 27 actors, 22 are additional this year. / Organisational Effectiveness: Saferworld made substantial progress strengthening its systems and infrastructure for effectiveness as an organisation: new Financial System in place, devolved country programme structure, and new Planning and Monitoring Framework. / Highlights: / Signing of Global Arms Trade Treaty to regulate the transfer of weapons. Saferworld provided technical expertise to EU, UK and civil society coalitions for 20 years on this issue. / Notable expansion in the number of communities actively organising and demonstrating confidence in their ability to facilitate positive change. / Kenya – considerable impact achieved by supporting Peace and Security Task Teams in hotspots at risk of pre- and post-election conflict. The potential for serious violence to erupt was, in most cases, mitigated.
1.5 Key challenges / Saferworld reported the following challenges: / A key element to achieving impact lies with Saferworld having dedicated staff, working alongside local communities and partners. The investment required in building teams with the appropriate skills, and orienting them sufficiently in a period of rapid growth, is substantial. It is particularly challenging when securing staff for demanding environments. / Dealing with unpredictable political environments, and making provision for significant risk due to insecurity proved an additional strain on resources. / The unpredictable nature of negotiations with some donors caused unexpected financial exposure or, in the case of delayed timeframes, harmful effects on partner relations and project delivery. / Saferworld’s proactive approach to managing the challenges of the unstable security and political contexts in which they work is welcomed, as are the efforts made to respond to feedback from last year’s Annual Review.
1.6 Annual Outcome Assessment / The Saferworld PPA has exceeded expectations at the outcome level. Indications are therefore, that Saferworld is on track to meet the overall objectives of the programme in Year 3. However, as noted above, Saferworld need to better articulate in the high-level narrative on progress what the specific contribution/ role of Saferworld was in relation to the outcomes/successes. Saferworld has recommended amendments to the indicators at outcome level as a result of overachieving (and exceeding the target for the 3 years in some cases). These are the following: / Outcome Indicator 1: Increase from a total of 16 community security plans developed and a total of 9 implemented over 3 years to a total of 85 plans implemented over 3 years. / Outcome Indirect Indicator 2: Amend target from a total of 9 community security action groups to a total of 20 groups over 3 years reporting that authorities have increased their understanding of community security needs and are addressing them effectively as a result. / Outcome Indicator 2: Increase target from a total of 16 civil society organisations to a total of 22 CSOs in conflict-affected countries which have the skills, confidence and capacity to identify factors undermining peace and security and to effectively seek to address them. / Outcome Indirect Indicator 1: Increase target from a total of 10 civil society organisations to a total of 11 CSOs over three years which have supported and/or influenced authorities to revise/strengthen their policies and approaches in relation to conflict and insecurity. / Outcome Indicator 3: Increase overall number of institutions over three years to 15. This means two additional institutions develop a new policy/strategy approach next year. Increase target to 5 for the number of institutions that have changed their practices. The current target is a total of 8 new institutions which develop new of significantly improved approaches, strategies and/or policies that directly respond to and mitigate conflict and a total of 3 institutions which start to change their practices over the 3 years. / Outcome Indicator 4: Increase target from a total of at least 7 external actors to 33 external actors who take up Saferworld (and partners’ recommendations on policy and practice in conflict-affected states and in doing so increase the potential for their policies and actions to more effectively prevent conflict and build peace.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Yes, annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. Allocations for year 3 will be allocated in the same way with no variance expected. / 2.2 Key cost drivers / The cost structures of Saferworld show the following from a total spend in 2012-13 of £8.45m: / Staff costs £3.86m (46%) / Travel costs £530,000 (6%) / Accommodation and meeting hire costs £1.37m (16%) / Per diems for staff, partners and programme participants £495,000 (6%) / Consultants £437,000 (5%) / This represents some 80% of Saferworld expenditure. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / None. / 3.2 Where an evaluation is planned what progress has been made? / The PPAs as a whole are served by an umbrella evaluation strategy, the first of its kind for DFID, which encompasses the Global Poverty Action Fund. This strategy examines progress at fund and at individual, organisational level. Following the announcement of the extension to the PPA fund in 2013, the evaluation strategy is being reviewed and, in addition to the individual progress reviews (IPRs) and meta evaluation that took place in 2012, further evaluative activities are being scoped out for 2014/2015 and 2016/17. This scoping process is taking place in consultation with the on-going funded organisations and the revised strategy will be ready in Quarter 4 of Financial Year 2013/14. The aim is to provide timely, fund level evaluation information for the design of future strategic funding modalities in 2014/15 ahead of the fund completion in 2016, followed by evaluative learning on the outcomes and impact of strategic funding for organisations and the fund as a whole in 2016/17.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The level of risk has remained stable across the outputs. Saferworld reports that the PPA agreement has allowed investment in the systems to manage growth and reduce the level of associated risk. / Risk mitigation actions taken include: / Standard operating procedures and Risk Management policy: Security risk management requires an investment of resources and significantly reduces the risk should a serious incident occur. / Cost driver data: This data is available following the restructuring of SW’s accounting systems in early 2012. This was achieved by recruitment of a new Finance Manager and other investment in central functions. Progress in developing accurate financial data, along with clear financial procedures, mitigates against damaging financial misdemeanour. / The South Sudan office faced closure in early 2012-13. PPA funding allowed SW to retain core staff. The programme ended the year with income of £400,000 and a potential budgeted income of £1m for 2013-14. / As part of a broader HMG initiative – DFID has a new risk management policy in place which requires new projects, in support of the security and justice sector to undertake a human rights risk assessment following a standard procedure. This policy, the Overseas Justice and Security Assistance Guidance (OSJA) seeks to balance risks against the positive impact that security and justice programming can have on the realisation of human rights. DFID will be contacting PPA partners individually to brief them in more detail about OSJA and how we can work together to apply it to each programme. This will include the Saferworld PPA.
Risk of funds not being used as intended / On corruption: / Saferworld underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. No particular issues have been identified since. / Saferworld report that they have a new anti-bribery and anti-corruption policy for Saferworld HQ and offices is included in their handbook. This includes declarations of conflict of interest by staff. It is recommended that Saferworld submit a copy of the policy to DFID for information. / 4.4 Climate and Environment Risk / It is acknowledged that Saferworld does not undertake specific programming in C&E areas and that much of the work appears to have a negligible environmental footprint. There is no evidence in the self-assessment report of an over-arching institution-wide C&E policy. However, the report does refer to Saferworld considering environmental responsibility an important value for money issue. DFID would welcome more information on the extent to which that is more widely actioned and operationalized. DFID also notes the reference to some organisational (HQ level) greening and efforts to reduce water consumption, using sustainable materials and reducing waste. We would welcome more information on how and if this is monitored. Finally, there is recognition of international air travel being the organisation’s greatest environmental impact with a survey of the CO2 emissions per person per flight recently undertaken and plans to explore carbon offset.

5. Value for Money
5.1 Performance on VfM measures / Integral to and implicit within the judgment as to whether the PPA represents VfM is the concept of opportunity cost -- the cost in undertaking activity X instead of initiative Y. Research has shown that the headline cross-cutting findings on the cost of reducing conflict and insecurity are together large and significant – Kaufmann and Kraay (1999) find that an improvement of one point on a 6 point rule of law index is associated with between a 2.5 and 4 fold increase in per capita incomes. Thus, it can be argued that security and justice programmes represent good value for money if they (i) make an overall positive impact on security and access to justice and (ii) that impact is greater than other possible development interventions. / It is beyond the scope of this annual review to review other programmes in DFID’s portfolio to determine if they would have utilised financial resources more economically, efficiently and effectively and thus demonstrated better value for money than the Saferworld PPA. However, there is growing domestic and international consensus around the positive contribution that good quality security and justice interventions can make to economic development. For example, the Prime Minister’s Golden Thread argues that security and justice are central characteristics of open societies and open economies. Crime, conflict and violence are serious obstacles to sustainable economic development.[1] Research shows that crime and violence lower investment and employment growth, owing to the ‘signalling’ effects they have on potential investors.[2] Business executives identify the costs of crime, conflict and violence as the second most important impediment to business competitiveness in their countries.[3] Eventually, the costs of crime and violence can reach a significant share of national income. Citizen fears’ for their personal safety may also impede workers’ mobility, generating adverse impacts on labour markets, and raising the costs of doing business. For example, evidence from Colombia suggests that women who experience severe domestic violence earn 70 percent less in monthly income than do non-abused women. Translating this into macroeconomic outcomes, they estimate that violence against women led to a loss in productivity equivalent to 2.43 per cent of GDP annually. Internationally, the World Development Report (2011) found that a lack of safety ‘has become the primary development challenge of our time’ and is a major obstacle to the successful achievement of the MDGs. Furthermore, poor people themselves have articulated their desire for improved safety and justice. The 2000 World Bank report Voices of the Poor identified that security and justice are as important to poor people as hunger, employment and lack of safe drinking water. As such, it is reasonable to argue that investments in security and justice represent, on balance, good value for money if they can be shown to demonstrate positive improvements in safety and access to justice. / Saferworld argue that they cannot focus on meaningful unit cost comparatives, as it is not possible to compare countries with high differences in living standards and costs of operation. Their focus next year will be on a timesheet pilot covering 35% of staff, and new processes to compare per diems and consulting rates. / General Comments from the Review Team: The self-assessment report sets out useful approaches to managing operating costs. However, value for money goes beyond an analysis of cost drivers. It is recommended that Saferworld, with CHASE economists and policy leads, consider ways to try establishing the value for money (efficiency, effectiveness and economy) of a particular security intervention in a particular location. The World Development Report (2011) made a strong economic case for peace and security (e.g 4% of GDP lost due to violent extremism for example). The issue of value for money in security and justice interventions is one that DFID is currently working on and so potentially offers an area for shared learning, experiences etc. / 5.2 Commercial Improvement and Value for Money / Staffing: the methods used to assess and benchmark salaries are as follows: / UK/International salaries and benefits: Saferworld benchmark INGO salaries and benefits through a specialist HR consultancy firm and with People in Aid. / National salaries and benefits: benchmarking done locally with other INGOs. / Annual pay review: A cost of living increase is considered each year, and depends on funds available. / Procurement rules cover all key areas of spending including a full tender process for large purchases for values in excess of £50,000. The new policy was used for a 3 vehicle purchase in South Sudan and Saferworld’s new intranet system. / Significant cost achievements include core data analysis (possible for the first time from restructured Chart of Accounts) providing a solid base for cost driver analysis. / Saferworld and its Somalia/land partners did a cost mapping of hotels, meals, refreshments, local transport and communication) in each zone. SW have now standardised their approach. / In South Sudan, a high cost location, Saferworld: / Changed procurement of office supplies to buying in bigger bulk at a cheaper price, and to doing more regular reviews of contractors / Moved from single consultant to on-going support arrangement for IT, at a cheaper flat rate. / Framework contracts tendered for taxi/vehicle hire services and legal services, re-tendered annually at flat rates. / Arranged co-sharing offices in Wau and Kwajok. / 5.3 Role of project partners / Saferworld adopts a range of partnership approaches. These reflect the different contexts and cultures in which they operate. / Partnerships with NGOs in conflict-affected states: Saferworld have partnership agreements with over 30 organisations working in 16 countries, predominantly national NGOs. As Saferworld’s main form of partnership, they require long-term, high-input support for institutional development, and joint design and implementation of projects. / Partnerships with national authorities: Saferworld partners with national authorities, in order to influence national policies and practices (e.g. South Sudan to inform policy development on arms control; Kenya regarding police reform). Saferworld also work in partnership with European governments (UK, Netherlands, Sweden), the EU and UN. / Partnerships with peers: Saferworld has alliances with peer agencies in the UK, EU and United States to widen the expertise-base they can call upon, and extend the reach of their policy and advocacy work. These include Conciliation Resources, the PSNI and the Alliance for Peacebuilding and InterAction. / Saferworld Associate Network (SWAN): Saferworld’s network of senior professionals have 30+ years’ experience with a UK or Ugandan police force. The peer-to-peer respect they bring to the table is a great asset. / Saferworld’s partnerships range from - at one end - long-term, based on a shared vision, to project partnerships at the other – shorter term, and focused on the joint delivery of project outputs. According to an independent assessment of Saferworld’s civil society capacity-building, “partnership in Saferworld describes an organic and on-going relationship… which develops over time”. / Saferworld strengthens the capacities of its partners on technical issues, such as community security, conflict sensitivity or arms control. Saferworld ensure such knowledge is adapted to partners’ capacities and their particular context. / Saferworld provides ‘accompaniment’ characterised by regular - sometimes daily – interactions and strong personal relationships, often with an element of mentoring. This allows for support to be guided by partners’ real needs and priorities. Most of the partnerships in the first category are based on this sort of relationship. Saferworld derives essential learning about the context and culture from these partnerships. They help Saferworld to reality-check its aspirations and adapt technical discourse to local realities. / a) Effectiveness / Local actors have the legitimacy to address issues around conflict, insecurity and governance, as they are directly affected by them. Empowering these actors to become agents of change is more effective as they have deeper contextual knowledge and greater access. / b) Sustainability / Saferworld partnerships shift from one of relative dependence to increasing independence, and from initial close management by Saferworld to collaboration between equals. Saferworld’s partnerships with FIQ in Kosovo and with PeaceNet in Kenya helped them become respected independent organisations. / In Yemen Saferworld has deliberately opted to partner with less formalised groups to widen the base of civil society actors focusing on peace and security. In Georgia, Saferworld partners with two NGOs perceived to be on different sides of the political spectrum, to ensure political balance and foster trust. In the recent Central Asia Evaluation, the evaluator concludes that ‘the single most distinguishing factor in the success of the programme .. is probably Saferworld’s commitment to genuine empowerment of its partners to find their own course, and of the communities to take responsibility for their own security, while still providing intensive support and challenging them rigorously to achieve the standards Saferworld has set’. / c) Relevance / Where there are no existing organisations working on areas of security and peace-building, Saferworld supports the establishment of new organisations which become key partners (eg NSA Platforms in the three Somali regions; a CSSAC Bureau in South Sudan; Usalama Forum, Kenya). In other cases, Saferworld works with nascent groups (e.g. women activists in North Africa) or with well-established organisations that have not worked directly on the relevant issues (e.g. BRAC in Bangladesh, INSEC in Nepal). / Additionality of PPA funding for Saferworld’s partnerships / Sustained and strategic partnerships contribute more to building local capacities and empowering local actors than short-term ones. These require consistency of support over long periods. Funding that is restricted to discrete, time-bound activities allows for minimal support to partnership development. The Capacity-Builiding Audit suggests this “has profound implications for the nature of the partnerships Saferworld can pursue and challenges the ideal notion of partnership”. PPA funding for this central aspect of Saferworld’s work is invaluable for sustainability. / 5.4 Does the project still represent Value for Money : Yes – based on available data but recognise more could be done in this area to improve our understanding of the value for money of Saferworld’s PPA. / 5.5 If not, what action will you take? N/A
[1] Shelley, L. (2002). “Crime as the Defining Problem: Voices of Another Criminology.” International Annals of Criminology, 39(1), 73-88.
[2] World Bank (2005). World Development Report 2005: A Better Investment Climate for Everyone. Washington, D.C.: World Bank.
[3] World Economic Forum (2003). The Global Competitiveness Report. Geneva: World Economic Forum. See Skaperdas, S., Soares, R., Willman, A. and Millar, S.C. (2009). The Costs of Violence. World Bank Report. Washington, D.C: World Bank.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The review team appreciated the substantial effort made by Saferworld to provide a thorough response to the self-assessment review template. The feedback below reflects our assessment of the Annual Review and of progress made to date as well as any additional feedback received. We concur with Saferworld’s own self-assessment that the programme should be scored an A+ overall. Key concluding comments on the PPA: / Much of the approach and work conducted by Saferworld fits in extremely well with on-going policy and programme discourse in DFID on security and justice and Rule of Law. Of particular note is Saferworld’s close cooperation with DFID over the past year through discussions on post 2015 (Outcome 1, Indicator 4 & Output 4). Saferworld has played a lead role in the UK and international NGO/ civil society community on how to reflect conflict and violence in post 2015 discussions. / Evidence of scale up is welcomed e.g. commitment by Nepali police to open a new post in a Village Development Committee where villages had no access to the police (p.7). We also welcome the level of ambition shown by Saferworld regarding potential scale up for Year 3, e.g. suggestion to increase to a total of 85 plans under Outcome 1 in response to swift progress against this outcome in Years 1 and 2. / A general observation regarding the way in which Saferworld narrates its progress is a need to better articulate what the specific contribution/ role of Saferworld was in relation to the outcomes/successes. / Saferworld’s proactive approach to managing the challenges of the unstable security and political contexts in which it works is welcomed, as are the efforts made to respond to feedback from last year’s feedback letter. / Feedback from Saferworld and DFID country offices has indicated that the strategic nature of the Saferworld PPA grant may be creating tensions in that activities supported by the PPA might also have received discreet project funding from other donors or DFID country offices. As such, attribution and contribution analysis becomes more complex as each donor/ office seeks appropriate levels of recognition for their support. Saferworld has been transparent with CHASE about this tension. It is recognised that the PPA grant to Saferworld is a strategic grant and is not allocated to specific projects or programmes. The examples cited in the self-assessment report (in particular regarding election support in Kenya also supported through a bilateral grant from DFID Kenya) are intended to be illustrative of the type of work that Saferworld conducts globally. The tension caused between strategic and project- specific funding is not unique to Saferworld and is an issue which may need to be addressed more widely by DFID. We do not propose any changes to the logframe or examples cited in the self-assessment report at this stage. It is recommended though that, going forward, Saferworld explicitly references all sources of income both in the finance section (1.3) and as part of the narrative around specific projects cited as illustrative examples (reference on p. 37 to a blend of PPA and bilateral DFID spend is a good model which could be made more prominent). / Much of the Saferworld theory of change references working with civil society organisations to build capacity and capability so that they are able to influence and persuade local and national security actors to improve their security. It is recommended that in Year 3 (and potentially beyond) Saferworld consider working with CHASE evaluation and results advisers (and others) to determine if it is possible to monitor and evaluate the processes and factors which determine the level to which demand-side actors are able to successfully ‘influence’ the actions, behaviours etc. of supply-side security providers. Whilst it is recognized that research into M&E of ‘influence’ is a new field of study, it is felt that Saferworld’s projects may offer fertile ground for testing out such an approach which will be of benefit not only for Saferworld’s PPA but also for broader learning within DFID and amongst other PPA partners. / NEXT STEPS / Key areas for follow-up are as follows: / Further discussion with DFID on how to achieve clarity on reporting on strategic funding where overlap with other funding might occur. / DFID to follow up with Saferworld on how to approach OSJA implementation. / DFID to follow up work with Saferworld on VfM in security and justice interventions. / DFID to follow up with Saferworld on possible approaches to M&E of influencing. / Saferworld to follow up with DFID on further information to be published for IATI.

8. Review Process
This Annual Review was conducted by Peter Diston (Governance Adviser) and Siobhan Sutton (Programme and Policy manager) following the guidance note issued by DFID’s Civil Society Department. Saferworld submitted a self-assessment annual report of their progress and performance against the PPA log frame during this second year of PPA funding. DFID reviewed this annual report and provided feedback to Saferworld on both strengths and weaknesses. The feedback incorporated comments from officials in relevant country and policy teams. Due to time and resource constraints, it was not possible to conduct interviews with beneficiaries or conduct field visits to verify the claims made in the self-assessment.