Type of Review: Annual Review

Project Title: International Planned Parenthood Federation

Date started: April 2011	Date review undertaken: 31 May 12

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK, through the Department for International Development (DFID), will invest in a 3 year Programme Partnership Arrangement with IPPF between 2011 and 2014. An initial investment of £8,600,000 for 2011-12 has been agreed. Subsequent disbursements will be performance-based; as assessed through robust monitoring and evaluation mechanisms.

What are the expected results?
In 2014, IPPF will deliver 55 million SRH services in GSWACH+ focus countries (an increase from 2009 baseline of 45.8 million); / In 2014, IPPF will deliver 6.1 million couple years of protection in GSWACH+ focus countries (an increase from 2009 baseline of 4 million); / In 2014, poor and/or vulnerable people will form 80 per cent of IPPF’s clients in GSWACH+ focus countries (an expected increase from 2009 baseline of 72 per cent); / By 2014 IPPF will serve a total of 50 million clients in GSWACH+ focus countries; / By the end of 2014, all grant-receiving IPPF Member Associations will provide a package of essential, high-impact sexual and reproductive health and rights services.

What is the context in which UK support is provided?
Civil Society Organisations (CSOs) are accepted as an essential part of the global partnership to deliver the Millennium Development Goals (MDGs) and public goods. / In the UK, the Government has stressed the importance of strengthening the ‘Big Society’ and developed a ‘Compact’ to shape the relationship between government and civil society. / Civil society plays a vital role in supporting citizens to improve their lives. CSOs are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. CSOs can extend governments’ and official donors’ reach with hard to reach groups - such as disabled people, vulnerable children, female headed households and people living with HIV AIDS - and in hard to reach areas or where, for example, DFID has no programme . / DFID objectives for its work with CSOs: / Deliver goods and services effectively and efficiently; / Empower citizens in developing countries to be more effective in holding governments to account and to do things for themselves; / Enable civil society to influence national, regional and international institutions including improving aid effectiveness; / Build and maintain capacity and space for active civil society.

## Section A: Detailed Output Scoring
Output 1: Increase in access to and use of an integrated package of essential services (IPES), centred around family planning, through IPPF Member Associations (MAs), increasing knowledge, access and choice that will improve the health of women and girls, particularly poor and vulnerable people.
Output 1 score and performance description: / A++ Output substantially exceeded expectation. / Progress against expected results: / Under this PPA, IPPF has given particular priority to improving performance in 45 focus countries. This group includes 39 of the 49 countries identified by the United Nations Global Strategy for Women’s and Children’s Health (GSWACH), plus an additional six countries (Bolivia, Brazil, Guatemala, India, Peru and Sudan) where IPPF Member Associations are primarily supporting poor and vulnerable groups, and are positioned to scale up service delivery over the PPA period. This is referred to as the GSWACH + group. / IPPF have exceeded all of the 2011 milestones that were set in the Logframe for Output 1, with the exception of services that reduce recourse to unsafe abortion. This is because IPPF has revised the definitions of its service statistics module on abortion related services and does not reflect a reduction in services per se. Future milestones in the logframe have been adjusted accordingly. / Output Indicator 1.1 Milestone Achieved 2011-12 / Sexual and Reproductive Health services provided / All Clients All SRH services 44,200,000 62,955,932 / CYP 4,100,000 4,438,856 / Young People All SRH services 22,000,000 26,355,377 / All clients HIV/STI/RTI services 4,200,000 9,244,207 / Services that reduce recourse to unsafe abortion 640,000 571,976 / Long term reversible methods 3,100,000 4,106,820 / Poor, marginalised etc 72.50% 80.40% / Output Indicator 1.2 Milestone Achieved 2011-12 / Member Associations providing integrated package of essential services: / 75% (6 out of 8) 65% 82% / 100% (8 out of 8) 30% 36% / Recommendations: / IPPF expects the progress made in 2011/12 to continue throughout 2012/13 particularly with respect to the expansion of service delivery through IPES, linking SRH and HIV responses, and their focus on the poor and the marginalised in particular all adolescents and young people. / Impact Weighting (%): 40% / Revised since last Annual Review? N / Risk: LOW / Revised since last Annual Review? N

Output 2: Engaging and influencing policy mechanisms for SRH and choice at global, regional and national levels Specifically contributing to: 1) Access to family planning/SRH; 2) Initiatives that reduce recourse to unsafe abortion; 3) Comprehensive sexuality education, and child protection; 4) Integrated HIV/AIDS and SRH, including stigma reduction;5) National budget allocations for SRH.
Output 2 score and performance description: / A+ Output exceeded expectation.
Progress against expected results: / For the GSWACH+ MAs that are included in the PPA Logframe, IPPF had a successful year. In total, 32 policy or legislative changes were achieved in 2011, some 78 per cent above the 2011 milestone which aimed for 18 changes. / Output Indicator 1.2 Milestone Achieved 2011-12 / # and description of national, regional and/or global financial/policy-making committees in which IPPF’s MAs are active. Types: 1) National Development Planning/Budgeting 2) PRSP 3) MTEF 4) Swap 5) CCMs 6) Donor national level programmes 7) National Contraceptive Security Committee 170 172 / Recommendations: / IPPF state that the period to 2014 will be a vitally important period in ensuring that SRH and family planning are recognized as critical to human development, and that this is adequately represented in the post 2015 development framework. As a result, there is no adjustment to milestones at this point. / Impact Weighting (%): 40% / Revised since last Annual Review? N / Risk: LOW / Revised since last Annual Review? N

Output 3: Strengthen the economy, efficiency and effectiveness of IPPF's network.
Output 3 score and performance description: / A Output met expectation. / Progress against expected results: / IPPF has implemented performance-driven financing for all Member Associations in the Western Hemisphere region, covering approximately 10 % of core IPPF funding utilised in GSWACH+ countries, compared to the year 1 target of 5%. We expect that the system will be implemented for all remaining counties in 2013. / IPPF has re-calculated the baseline and 2010 performance, using the new conversion factors. As a result, in 2011, IPPF has calculated CYP cost as £3.27, an increase of 7.5 per cent on the baseline. As for prior years, this is an indicative estimate based on a sample of the largest GSWACH + CYP providers. / This increase in cost has been driven by a number of factors. In 2011 IPPF exceeded the target for SRH services provided to poor and vulnerable clients, by an estimated 5 million services. We know that providing services to poor and vulnerable people is typically more expensive for a range of reasons (harder to reach, cannot afford to pay for services etc), which presents an ongoing challenge to bringing down the cost per CYP. / Output Indicator 3 Milestone Achieved 2011-12 / (3.1) % of IPPF funding to MAs that is delivered through performance-driven financing 5% 10% / (3.2) # MAs that produce and use standardised activity cost data (% efficiency) Nil Nil / (3.3) Change in cost per CYP/birth averted £3.04/£10.57 £3.27/£11.36 / Recommendations: / IPPF will continue to refine their methodologies for measuring cost per CYP, recognising that there are many factors that influence this output (number of services to poor and vulnerable populations, exchange rate fluctuations, and timely availability of data). For this reporting year, milestones have been adjusted for these reasons. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: LOW / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / No. This is the first Annual Review for this Programme Partnership Arrangement. / 1.2 Overall Output Score and Description: / The overall Output score for IPPF is A+: Outputs moderately exceeded expectation. / 1.3 Direct feedback from beneficiaries / As part of their overall M&E approach, IPPF encourages all its Member Associations (MAs) to collect feedback from beneficiaries. Data from the global indicators survey shows that 98 per cent of MAs in GSWACH + countries collect client views through satisfaction surveys, exit interviews, and suggestion boxes. Currently, there are two regions working towards a more systematic approach to the collection of direct feedback from beneficiaries at the MA level. / IPPF started the ‘Changing Lives’ series 2 years ago using the rapid PEER (Participatory Ethnographic Evaluation and Research) approach. PEER is a qualitative methodology that trains project beneficiaries to conduct conversational interviews with other people in their community or social network on how they have benefited from the project. A PEER review captures the story of a project and the difference that it has made, primarily from the perspective of the people who are the beneficiaries. PEER review data are used by MAs to inform decisions about projects/programmes, and as part of final evaluations. / 1.4 Summary of overall progress / IPPF achieved strong outcomes during 2011 continuing the trend seen since 2005, and reflecting their commitment to the delivery of a broad range of sexual and reproductive health services. By the end of 2011: / IPPF averted over 1.27 million unwanted pregnancies in the GSWACH+ countries (7 per cent above the estimated milestone). 40 per cent of pregnancies averted were for young people; / IPPF averted 341,700 DALYs (disability adjusted life years) (18 per cent over the estimated milestone); / IPPF averted 388,412 unsafe abortions (2 per cent higher than the estimated milestone). / IPPF's core investments result in SRH services provision in countries with the greatest need. Worldwide, 78 per cent of IPPF's services are provided in countries defined by the UNDP Human Development Index (HDI) as having low or medium levels of human development. In the GSWACH + countries, as outlined under Output 1, in 2011, IPPF have increased their capacity to reach the most vulnerable populations, and 8 out 10 of clients were classified as poor and/or vulnerable. / 1.5 Key challenges / Contraceptive security is a major challenge: as women’s demand for contraception increases, the need for governments, donors, manufacturers and other stakeholders to supply the demand becomes increasingly critical. Supply chain systems have to function correctly (stock-outs are common) and be able to supply contraceptives that have been pre-qualified (contraceptives that have received an approval of quality and safety) and registered for use in a country. On the demand side, a range of socio-cultural factors continue to prevent people (especially young women) from accessing sexual and reproductive health services (lack of awareness, fear of stigma, etc). IPPF know these can be overcome through a combination of outreach, Comprehensive Sexuality Education, and awareness raising. However, this takes time and resources. / It is a constant struggle to maintain SRHR as a political priority and safeguard existing funding streams for SRHR. IPPF will need to continue to mobilize its committed and active supporter base to increase political priority of SRHR. This is especially important during the coming period, where the post-MDG framework is taking shape. / 1.6 Annual Outcome Assessment / This is the first annual reporting period under the Programme Partnership Arrangement (PPA); therefore it is still too early to measure impact on the overall outcome. IPPF has so far made very good progress in this first year of the PPA.

2. Costs and timescale
Is the project on-track against financial forecasts: / Yes, annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. Allocations for year 2 will be allocated in the same way with no variance expected. Funding for year 3 may be adjusted up or down based on performance; however, it will be allocated in the same way. / 2.2 Key cost drivers / IPPF has identified its main cost drivers in service delivery to be as follows: technical staff time, clinical commodities, and clinic running costs. / Is the project on-track against original timescale: / Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Through 2011, IPPF’s data collection team has identified a number of areas where they need to improve data quality. IPPF is also consistently reviewing and incorporating sector-wide data assessment criteria. These changes have been discussed with DFID Technical Reproductive Health team and have been reflected in a revised Logframe. / 3.2 Where an evaluation is planned what progress has been made? / IPPF must commission a mid term and end Independent Progress Review (IPR) as a condition of the PPA. The mid-term IPR was completed in October 2012. DFID has contracted an evaluation manager to review the IPRs submitted by each PPA holder, drawing conclusions on the performance of the individual PPA holders and the fund as a whole.

4. Risk
Output Risk Rating: / The overall output risk rating for IPPF is Low. / 4.2 Assessment of the risk level / IPPF is driving value for money (VfM) and efficiency through its global goal to double service delivery by 2015. With the scale of IPPF service delivery greater in some countries than others, there is a risk of over-dependency and focus on key service provider MAs, and possible missed opportunities in terms of investment in other countries where there is still great need for interventions. IPPF is managing this risk partly through its performance-based funding resource allocation system, by which resources are directed towards populations where need is greatest and where there is opportunity to scale-up activities to increase the impact of IPPF funds. In addition, IPPF continues to undertake significant MA capacity building activities targeting countries where a modest investment in infrastructure, management and/or systems capacity will have the greatest return in terms of scaling up interventions and results. / IPPF’s service delivery model is highly dependent on the availability of approved medical commodities in the clinics. An efficient supply and control system across the Federation is therefore, fundamental - with local country conditions often making the maintenance of supplies lines and storage conditions difficult particularly where governments have failed to deliver on commitments. This area remains a key risk for IPPF. / Risk of funds not being used as intended / IPPF underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. / 4.4 Climate and Environment Risk / Implementing voluntary family planning programmes is a key contributor to sustainable development and environmental protection. IPPF are bound by the environmental sustainability component of the MDG7 (Ensure environmental sustainability). IPPF has been integrating an emphasis on the environment within its policies. In 2010, IPPF developed a policy to set out IPPF’s position on climate change, population and sexual and reproductive health and rights, and to provide guidance on where the Federation can engage in climate change related processes.

5. Value for Money
5.1 Performance on VfM measures / IPPF recognises the importance and necessity of a value-for-money approach to programme and wider activity. They seek to do this through the three key pillars recommended by BOND: / a. Put the right systems and processes in place for managing value for money; / b. Compare value for money between alternative programme strategies and choices; / c. Use of evaluations and metrics to demonstrate value for money. / 5.2 Commercial Improvement and Value for Money / IPPF is working with Member Associations to develop greater understanding of how they improve their efficiency and effectiveness and thus drive increased value for money. Initiatives that support this include the introduction of performance based funding, workshops on clinic efficiency, the development of unit costing systems, ongoing work to improve data quality and the roll out of manual and electronic clinic management systems. / 5.3 Role of project partners / As mentioned in section 4.2, IPPF are focused on key Member Associations to meet performance targets. IPPF is driving value for money (VfM) and efficiency through its global goal to double service delivery by 2015. / 5.4 Does the project still represent Value for Money : / Yes. / If not, what action will you take? / N/A

6. Conditionality
Update on specific conditions / N/A

7. Conclusions and actions
IPPF have had a successful first year in this Programme Partnership Arrangement. / IPPF submitted a revised Logframe annotating the results achieved for this reporting year. They provided adjustments to their milestones for years two and three in August 2012.

8. Review Process
IPPF submitted a self assessment annual report of their progress and performance against the PPA log frame during the first year of PPA funding. DFID reviewed this annual report and provided feedback on both strengths and weaknesses. The feedback incorporated comments from a range of officials in relevant country and policy teams and also included input from the contracted evaluation specialists who have been commissioned to review the Independent Progress Reviews.