Type of Review: Annual Review

Project Title: Saferworld

Date started: 1 April 2012	Date review undertaken: 31 May 2012

Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK, through the Department for International Development (DFID), has invested in a 3 year Programme Partnership Arrangement with Saferworld between 2011 and 2014. An initial investment of £1,739,160 for 2011-12 has been agreed. Subsequent disbursements will be performance-based; as assessed through robust monitoring and evaluation mechanisms.

What are the expected results?
The results expected from this investment are; / In at least 10 countries, individuals and communities influence effective responses to conflict and insecurity and to promote peace / In at least 10 countries, civil society plays an active and effective role in influencing the public and authorities and building capacities for peace / In at least 6 countries, authorities are more responsive, effective and accountable to people’s needs and their actions help to build peace / At least 4 external actors operate in a way that supports peace internationally - in at least 4 countries - including through their recovery, development, political and security actions / Saferworld’s geographic priorities include the Horn and Great Lakes regions of Africa (regionally and in Kenya, Somalia/Somaliland, Sudan and Uganda); South Asia (regionally and in Bangladesh, India, Nepal, Pakistan and Sri Lanka); Central Asia (Kyrgyzstan, Tajikistan); the Caucasus (regionally and in Georgia/South Ossetia/Abkhazia); Balkans (regionally and in Bosnia, Kosovo and Moldova); and the Middle East (Yemen).

What is the context in which UK support is provided?
Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / In order to achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs and following a robust selection process and implementation of a Resource Allocation Model, partners have been identified for a 3 year PPA to begin in April 2011. Saferworld is one of these.

## Section A: Detailed Output Scoring

Output 1: In Georgia/Abkhazia, Kenya, Kyrgyzstan, Nepal, Pakistan and Sudan, Saferworld and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities.
Output 1 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: / Saferworld was expected to achieve 10 action-oriented community groups to be formed in Year 1 (with Saferworld support) by members of conflict-affected communities in Georgia/Abkhazia, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan. Through these groups communities can identify their security related needs and priorities, and develop a shared purpose and vision for change. Saferworld supported the formation of 12 such groups in Year 1 with 2 in Nepal, 4 in Kyrgyzstan / Tajikistan, 3 in South Sudan and 3 in Georgia / Abkhazia. / Saferworld was expected to achieve 8 community groups in Georgia/Abkhazia, Kenya, Kyrgyzstan, Nepal, Pakistan and South Sudan to have the opportunity to voice their security and justice concerns to local authorities. This was as a result of Saferworld-facilitated meetings in Year 1 - in order to begin identifying joint solutions and plans for action. Twelve such groups had this opportunity in Year 1 with 2 in Nepal, 4 in Kyrgyzstan / Tajikistan, 3 in South Sudan and 3 in Georgia / Abkhazia. / Recommendations: / Some of the key recommendations pointed out by Saferworld include; / Change the reference to Kyrgyzstan to Kyrgyzstan/Tajikistan throughout relevant documentation as Saferworld’s programme engages in both countries. This document refers to Kyrgyzstan/Tajikistan. / Change the reference to Sudan to South Sudan throughout relevant documentation following the creation of the new state during 2011. This document refers to South Sudan. Please note that Saferworld plans to engage in Sudan on advocacy issues. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: In Georgia/Abkhazia, Kosovo, Kyrgyzstan, Somalia, Uganda and Yemen, local civil society organisations receive support from Saferworld to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts.
Output 2 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: / Overall, Saferworld exceeded expectations under this Output. They were expected to provide high-quality training and capacity-building to 6 local CSOs in Kyrgyzstan/Tajkistan/Uganda/Yemen in Year 1, on areas such as strategic planning, advocacy, conflict analysis and monitoring and evaluation - as well as the technical aspects of conflict-related issues relevant in their country. In Year 1, Saferworld provided tailor-made training and capacity-building to a total of 4 CSOs in these countries, and a further 17 CSOs received training in a group setting. All training and capacity-building was based on needs identified through organisational capacity assessments. The tailor-made training provided include, 2 CSOs in Kyrgyzstan/Tajkistan received tailor-made training and capacity-building. The Foundation for Tolerance International in Kyrgyzstan received capacity-building support from Saferworld on research and analysis skills, participatory community security programming, and monitoring and evaluation. The Association for Scientific and Technological Intelligentsia in Tajikistan received training on conflict-sensitivity and capacity-building support to undertake participatory community security programming. / Examples of the group training include 12 CSOs in Uganda which received training on conflict-sensitive approaches to development programming in the country’s insecure Karamoja region. / As per indicator 2, Saferworld was expected to support 5 CSOs in Georgia/Abkhazia/Nepal/Somalia to articulate and convey the needs and views of their constituents within policy development processes in Year 1. Saferworld has provided this support to 6 CSOs in Year 1. / Recommendations: / DFID has suggested that this indicator is more clearly divided between CSOs that receive tailored capacity building support and those that receive training as part of groups, as these activities would be expected to have different outcomes. / Impact Weighting (%): 25 / Saferworld proposes to decrease this to 20% to compensate for the adjustment made to the weighting percentage under Output 4. They believe this provides a more proportional spread between output areas across the programme of work. However, it has been agreed with DFID to keep the impact weightings as they are, as they reflect DFID’s priorities for PPA deliverables. / Revised since last Annual Review? N / Risk: Low / Saferworld recommend revising this to ‘medium’ due to the challenging contexts in which this output is being applied. / Revised since last Annual Review? N

Output 3: In Kenya, Kosovo, Nepal and Sudan national and local authorities receive support from Saferworld to assist them in developing effective policies and practical approaches for building peace, justice and security.
Output 3 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: / Saferworld exceeded expectations. They were expected to provide quality technical input into a total of 5 policy process in Kenya/Kosovo/Nepal/South Sudan during year 1. They went on to successfully provide support to a total of 11 processes. These entailed of 3 processes un Kosovo, 2 in Nepal and 2 in South Sudan. The other four were in Kenya where according to Saferworld’s annual review; they provided expert input into the development of the National Police Services Bill (2011), National Police Service Commission Bills (2011) and the Independent Police Oversight Authority Bill (2011). They also facilitated input from a coalition of local CSOs. They provided close technical support to the Kenya National Police on the establishment of a new Internal Affairs Unit, which is designed to raise standards and accountability. / Saferworld also provided quality technical support to 5 institutions in Kenya/Kosovo/Nepal/South Sudan during year 1 which is higher than the expected total of 4. This support includes 2 institutions in Nepal, 1 in South Sudan, Kosovo and Kenya where Saferworld helped the Police Reforms Implementation Committee (PRIC) to adopt a participatory approach to police reform. / Recommendations: / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive Saferworld analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries.
Output 4 score and performance description: / A++ - Outputs substantially exceeded expectation
Progress against expected results: / Saferworld were expected to deliver publication and dissemination of (electronically or in print) 12 quality research papers/policy briefings/reports to external actors during Year 1. They exceeded this by publishing and disseminating 78 of such papers/briefings/reports. Saferworld also went on exceed expectations under indicator two by providing quality training to 53 people on engagement in fragile and conflict-affected states. 31 of these are reported to be women and 32 men. For example, 12 DFID South Sudan on staff were trained by DFID’s Conflict Advisor and Saferworld’s regional head of programme, on conflict-sensitivity. / As expected under indicator 3, Saferworld delivered 3 products building on evidence and lessons learned from Saferworld programme implementation during Year 1. One of these papers is the ‘Lessons from the People’s Peacemaking Perspectives project’. / Recommendations: / Saferworld have suggested some recommendations going into the next year. / Output Indicator 4.1, the milestones for Years 2 and 3 could be raised to 20 per year making a total of 78 papers, reports and briefings by 2014. It would be advisable to increase the milestones and target further as 78 papers have already been developed. / Output Indicator 4.2 is revised in future years to include seminars/roundtables as well as training events, since this will capture the policy dialogue and facilitation role that is a core component of Saferworld’s work and is not currently captured at output level. / Clarification of Output Indicator 4.3 to cover products provided to any branch of the UK government, rather than restricting this to DFID, as this will better enable Saferworld to demonstrate the reach and nature of its work and influence, and the way in which they seek to work at the intersection of different branches of government and promote coherent approaches. / Impact Weighting (%): 20 / Saferworld recommend increasing the impact to 25%, in light of policy advocacy work with external actors being a significant and successful part of Saferworld’s work that this revised percentage would better reflect. However, it has been agreed with DFID to keep the impact weightings as they are, as they reflect DFID’s priorities for PPA deliverables. / Revised since last Annual Review? N / Risk: Low / Saferworld recommend revising this to low/medium due to the higher likelihood of conflict in some of the countries where it works which may have an impact on risk. / Revised since last Annual Review? N

Output 5: Saferworld, in consultation with DFID, develops and applies a robust monitoring and evaluation system which enables the identification, measurement and communication of results at output and outcome level, and demonstrates contribution to impact level.
Output 5 score and performance description: / B - Outputs moderately did not meet expectation
Progress against expected results: / Saferworld was expected to have established an institutional framework for Monitoring and Evaluation (M&E) and to have and developed tools for capturing results at Outcome Level. Saferworld reports to be on track on developing their framework from their organisational change model, although it is clear that the framework is not yet fully in place. They use their country strategies as a basis. This includes elements for each area of programming such as, a conflict analysis, an actor and power analysis, a theory of change, outcome challenges and progress markers for our CSO partners. As well as advocacy targets and a security index that can be used by partners and beneficiaries in our community security work. Some of the elements that they believe to be vital for constructing an effective institutional framework include, a baselines report for their PPA funding which assesses baselines in depth across their output areas and a framework for collecting evidence against their advocacy and policy objectives, with a scalar tool and six types of evidence, which teams collect in the Saferworld Evidence Box. / Saferworld is also working on further enhancing their use of SMS technology. They are looking to develop a bespoke database system to gather data on their community security work in one centralised place. Furthermore, they are looking to develop a tender document for an online collaboration, knowledge and learning system, which will provide an online evidence collection system that teams can learn from and use to demonstrate the impact of their work. / Recommendations: / Impact Weighting (%): 10 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: / A+ Outputs moderately exceeded expectation. / 1.3 Direct feedback from beneficiaries / Because of the nature of Saferworld’s work, they have a well-developed methodology for determining where to work through tracker surveys and focus groups; mapping community security needs in the target areas with the participation of all sections of the community. Working with community reference groups / community safety forums to discuss the immediate security needs, and short-list the most important; facilitating joint planning with those reference groups to plan responses. As well as strategies for engagement with local authorities and security providers; supporting the community reference groups to present and negotiate those plans; and evaluating the success of the implementation of those plans. In each programme, data is recorded at all these stages, and reviewed regularly by programme teams.
1.4 Summary of overall progress / In year 1, Saferworld have achieved the expected results and in some areas, exceeded these expectations. At this stage, they have already began to see results at the higher Outcome level which further demonstrates the relevance on this programme, its strategic coherence, and the strength of Saferworld’s theory of change.
1.5 Key challenges / Some of the key challenges pointed out by Saferworld include, / A continuing challenge to the Somalia Non-State Actors platforms' effective engagement in policy dialogue processes is the frequently short preparation and response time allowed by international policymakers and the often incomplete responses from international policymakers to requests from the platforms for feedback. / The operating environment for NGOs, but more so for INGOs, working on security and justice issues in Nepal has become much more difficult with a closing of operational space. / The security situation in Yemen remains very volatile, with risk levels regularly fluctuating. This has an impact on the ability of the Saferworld team to travel to Yemen, to visit locations outside of Sana’a and to conduct programme activities. / In Bangladesh, the political context, including increasingly frequent hartals (general strikes), is limiting the ability of the Saferworld team and partners to implement projects because the strikes restrict movement within Dhaka and to communities. / In a number of countries where Saferworld works, such as Bangladesh, South Sudan and Nepal, there are additional challenges such as limited and infrequent electricity supplies and difficult communications with poor land and mobile telephone connections.
1.6 Annual Outcome Assessment / Based on the evidence provided on Saferworld’s annual review, we expect the PPA to achieve its Outcome. Saferworld works at four related levels, and with four different categories of actors, as indicated in their logframe and change model, and in their four outcome indicators. Their goal is to influence change at the level of individuals and communities; civil society; authorities; and external actors. Saferworld believes that change is needed at each of these four levels in order to contribute to their overall vision of a world in which people are able to lead peaceful, fulfilling lives free from insecurity and violent conflict. At the end of year 1, they can identify change at outcome level in each of these four levels, and can also begin to demonstrate how their work at each level strengthens outcomes in the other areas.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. Allocations for year 2 will be allocated in the same way with no variance expected. Funding for year 3 may be adjusted up or down based on performance; however it will be allocated in the same way. / 2.2 Key cost drivers / Saferworld is an organisation working in some 15 countries, with offices in the UK and five overseas locations. Approximately 50% of staff are in London, although this percentage is falling over time. Our key costs are: headcount; staff salary (some 50% of cost); additional staff costs (housing, education etc); consultant costs; travel; meetings and conferences; overheads. / Budgets for donors are analysed into headcount and then ‘activity cost’. Excluding the employee cost from activity cost means that this analysis is limited. Procedures are in place to ensure all costs incurred are appropriate to the location of the spending. Staffing make up half of our costs. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / N/A / 3.2 Where an evaluation is planned what progress has been made? / Monitoring and evaluation is expected to be integrated into the PPA partner’s approach to managing the funding they receive through the PPA mechanism. The onus is therefore on Saferworld to develop a Results Framework which will allow for a transparent evidence-based assessment of the results and value for money achieved through the grant they receive. As stated in the Business Case, an externally contracted Evaluation Manager was put in place to ensure that the monitoring and evaluation strategies adopted by the organisations are adequate for providing such information and to allow for an overarching fund-level evaluation to take place.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The key risks affecting the successful delivery of the expected results remain valid. Nevertheless, given changes in some of the contexts Saferworld is operating in, further or intensified mitigating actions are required. For example, in Nepal the shrinking of space for I/NGOs to work on peace and security issues means that Saferworld needs to invest more in building and strengthening relations with national level government contacts and on-going lobbying with donors on this issue. In South Sudan, an increase in inter-communal violence in some areas of Saferworld’s operation is affecting access to communities. / Saferworld is also assessing potential organisational risks of engaging in new models of doing business with for-profit organisations through consortia for large scale programmes.
Risk of funds not being used as intended / Saferworld underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. / 4.4 Climate and Environment Risk / As the Business Case states, the greatest environmental impact of Saferworld’s work comes from internal working practices (for example, use of transport and specifically air travel; paper use; energy efficiency of premises etc). All the printers it uses adhere to sound environmental principles including the use of recycled paper, FSC certification (environmentally and socially responsible forestry) and the use of vegetable inks. / Saferworld has taken steps to reduce this impact, by having a ‘light footprint’, employing people locally where possible and opening national offices where possible to limit necessary flights from the UK. This is also part of Saferworld’s on-going decentralisation objectives, which includes addressing environmental concerns and reducing our impact.

5. Value for Money
5.1 Performance on VfM measures / Saferworld has not tracked VFM savings for Year 1. For Year 2 and 3, they will track core costs and trends to ensure VfM. / The revised Chart of accounts will be a key benefit here. / Analysis of staff time will also be a key tool. / Comparative performance of each Country and the UK operation will be tested. / High level donor contract comparative performance will be produced by the management accounts. / Monthly management accounts will be the main process by which performance is monitored and KPI data will highlight trends and variances. Further quarterly analysis work will be performed on the new accounting system to assess areas for accounting structure improvements and also reporting enhancements. / Saferworld has grown significantly, in recent years doubling income. Management acknowledge that financial systems have not kept pace. In 2011-12 Saferworld undertook a review of core financial data on Sage (its accounting system) and restructured it to produce key donor reports and, for the first time, aggregated summary financial data for management. They have also reviewed all processes of input and output of data to automate where possible and improve speed of reporting. These changes are being rolled out in April 2012. / For the first time, the new system details how each employee is costed to projects. It allows the analysis for each donor of staff working on a project, and also reports for each staff member of how time has been changed in each period. The new structure disaggregates ‘partner’ and ‘Saferworld’ clearly. In 2012-13 Saferworld will refine the structure further. / Budget data production has also been reviewed with a focus on the creation of clear budgets where the core drivers can be analysed quickly. For the first time in 2012-13, budgets will be loaded into Sage. In 2012-13 we will address the challenge of producing meaningful reports of performance against budget and forecast. Both benchmarks are important and we will need to resolve the shortcoming of our Sage accounting system, which can hold only one set of benchmark figures. / 5.2 Commercial Improvement and Value for Money / There are no direct procurement aspects to this PPA. The main element of Saferworld’s financial expenditure continues to be staffing costs. / 5.3 Role of project partners / Saferworld has developed a policy paper which defines its understanding of Value for money, achievements so far on this agenda and proposes a plan of action to further improve organisational performance. This document will be shared also with project partners in order to stimulate similar discussions on value for money within their own contexts with the provision of examples from an organisation working in the same sector. / 5.4 Does the project still represent Value for Money: Yes - In reference to the value for money measures in the Appraisal case of the Business Case, the PPA with Saferworld still represents value for money. Saferworld remains a great fit with DFID’s objective and priorities as well as clarity of their vision and impact. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Overall, the PPA is progressing as planned. Since the partner’s self-assessment and feedback from CHASE, Saferworld has revised the logframe for Years 2 and 3. CHASE will continue to engage proactively with Saferworld particularly on key priorities for evidence-building in conflict, security and justice programming and policy.

8. Review Process
This desk-based review was undertaken by the CHASE programme officer. The review drew on project documentation and relevant correspondence between DFID and Saferworld since April 2011.