## IRC 2014-2016
Logframe
International Rescue Committee UK
Title: | Urban Humanitarian Crises Advocacy and Learning Partnership
Project Number: | 204273
PO Number: | 40089378
Project period: | 01 Oct 2014 - 31 Dec 2016
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | DFID-IRC Advocacy and Learning Partnership on Urban Humanitarian Crises
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Individuals, households and communities impacted by crises are safe, healthy, educated and economically empowered and, along with the cities they live in, are better able to cope with future shocks and stresses. | Humanitarian response and programming takes into account long term needs of the city, its residents and development objectives | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Humanitarian response and preparedness is mainstreamed into urban planning and governance processes | Planned
Achieved
Source
Evaluations of emergency responses in urban areas affected by crisis. Reports and policies from associations of planners and city authorities (eg UCLG)
|  |  |  | 2015-02-28 | 2015-12-01 | 2016-12-31
OUTCOME | Outcome Indicator 1 (Advocacy) |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Humanitarian and development actors have improved understanding and enhanced policy and operational commitment to respond to the challenges and opportunities presented by urban crises, to meet the immediate needs of the city and its inhabitants, foster recovery and encourage sustainable development. | The percentage of targeted stakeholder organisations that demonstrate that they recognise the need to tailor interventions to the urban context or have taken steps to improve policies or operational capacities. | Planned | Stakeholder Mapping and interviews | 75% of Group A stakeholder organisations engaging in IRC-DFID policy events or have had introductory bilateral meetings with IRC | 25% of Group A stakeholders demonstrate commitment to improving response to urban crises. 25% of Group B stakeholders engaging in IRC-DFID policy events or referencing material produced by IRC and the Urban Coordination Cell | 50% of Group A stakeholders demonstrate a change in policy and/or practice to reflect the urban context and 50% of Group B stakeholders amplifying messages that can lead to improved response to urban crises | Current trends towards increasing urban considerations in humanitarian and development funding and programming continue. Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response. Relevant actors - including local and global humanitarian and development organisations, and local and national governments - are willing to change their attitudes, policies and operational behaviour in response to advocacy messages, new evidence and tools. IRC and DFID will be able to gain access to World Humanitarian Summit Regional Consultations and Habitat III preparations. Side Events will be permitted at relevant advocacy events. Messages on urban will be heard by WHS Secretariat and incorporated into outcomes WHS report as well as Habitat III. Outcomes of WHS will result in real policy change.
|  | Achieved |  | 13 out of 17 Group A actors engaged (76%) | 53% of Group A stakeholders demonstrate commitment to improving response to urban crises. 38% of Group B stakeholders are engaging in our events or referencing to our material. | 59% of Group A stakeolders demontrsate a change in policy or practice 70% of Group B stakeholders have amplified messages
Source
Key informant interviews, reports, policies and public statements from governments, donor agencies and multilateral institutions. Requests for advice/support from partnership leads. References to policy recommendations in WHS and Habitat III preparatory documents and outcomes.
| Outcome Indicator 2 (Learning) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| The number of peer organisations report that they have an advanced understanding of the complexities associated with working in an urban environment and are considering changing their programmes based on key lessons generated by the Urban Crises Project. The number of IRC country offices that report they are taking steps to review their operations and/or are engaging with authorities in crises affected urban areas to improve response based on evidence presented through the Urban Crises Project | Planned | Peer organizations mapping and interviews | (removed pending recruitment of Learning Manager) | Baseline conducted for 4 peer organisations and 4 IRC country offices to establish initial evidence gathering based on existing programmes in urban contexts from both the IRC and peer organisations. One learning product issued. | 4 peer organisations report that they have an advanced understanding of the complexities associated with working in an urban environment and are considering changing their own urban programmes. 4 IRC country offices report that they are taking steps to review their operations and/or are engaging with authorities in crises affected urban areas to improve response.
|  | Achieved |  |  | Baseline conducted for 4 peer organisations and 6 IRC country offices. | 4 Peer organisations (Norwegian Refugee Council, World Vision, Women's Refugee Commission and Habitat for Humanity) reported advanced understanding; 6 IRC country or regional offices (Uganda, Tanzania, Burundi, Pakistan, Thailand and the Horn East Africa and Zimbawe region) reported they are taking steps or are engaging with authorities
Source
Key informant interviews, proposals and programme documents, and papers from targeted organisations and country offices.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
|  |  |  | 2015-02-28 | 2015-12-01 | 2016-12-31
OUTPUT 1 (Advocacy) | Output Indicator 1.1 (Advocacy) |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Key stakeholders are encouraged to develop, review and enhance their policies on urban contexts and better operationalise them. | Number of advocacy products produced with actionable policy recommendations that address how humanitarian, development and urban stakeholders can improve response in urban contexts and disseminated at regional and global advocacy and policy events and through online downloads. | Planned | None | 1 paper linked to Ditchley Park event | 3 papers | At least 6 advocacy products (papers, reports and briefings) have been published or electronically circulated over the course of 2 years. | IRC is able to secure side events at the right global policy fora. Targeted agencies accept our advocacy messages and evidence their willingness to change.
|  | Achieved |  | Paper produced and disseminated | 5 papers and 4 additional products. | 7 Advocacy products published or circulated.
Source
IRC-DFID advocacy products (research reports, policy briefings and discussion notes); IRC and DFID website and publication lists and dissemination lists.
| Output Indicator 1.2 (Advocacy) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of events at which evidence based advocacy messages are shared (side events, high-level panel events). | Planned | None. | 1 Ditchley Park event | 4 events. | At least 6 events where advocacy messages are shared.
|  | Achieved |  | Ditchley park event held | 7 events held. | 12 events where advocacy messages have been shared
Source
Notes from event; participant lists
IMPACT WEIGHTING (%) | Output Indicator 1.3 (Advocacy) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
65% Output 1 is focused on the advocacy component of this project and therefore on influencing change in institutional, organizational and municipal actors and decision-makers. This will result in the improved understanding and commitment the project seeks from the stakeholders and is therefore more heavily weighted. | Number of targeted stakeholders (including humanitarian, urban and development) briefed by IRC on the specificities of urban crises and key recommendations. | Planned |  | 75% of Group A organisations exposed to key messages at Ditchley Park event or through bilateral meetings with IRC. | All Ditchley Park attendees in Group A have had at least 2 follow-up meetings and 30% of Group A have sent representatives to other IRC events. Initial meetings held or other forms of institutional engagement with Group B stakeholders | Engagement maintained with all Group A organisations and follow-ups with Group B. Briefings extended to five additional high-level stakeholders (donors, international multilateral agencies or INGOs)
|  | Achieved |  | Event held, bilateral meetings held in Geneva and Washington DC. 13 out of 17 Group A stakeholders reached (76%). | All Group A stakeholders have had at least 2 follow-up meetings and 76% of them (13 out of 17) have been regularly engaged with programmes. All Group B stakeholders have been involved in meetings or institutional engagement. | Engagement maintained with all Group A and Group B stakeholders throughout the life of the project. Briefings extended to 6 additional stakeholders (Germany, Irish Aid, Royal Institute of British Architects - RIBA, Brookings Institute, Save the Children UK, ODI.)
|  | Source |  |  |  |  | RISK RATING
Medium. Risks are the lack of traction for change within the UN system and the focus of World Humanitarian Summit drawn to other thematic areas.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
|  |  |  | 2015-02-28 | 2015-12-01 | 2016-12-31
OUTPUT 2 (Learning) | Output Indicator 2.1 (Learning) |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Humanitarian and other actors supported to have greater understanding of how urban contexts are impacted by crises and how to programme effectively for the urban context. | Number of knowledge products produced on how urban contexts are impacted by crises and how to programme effectively for the urban context. | Planned | Number of knowledge products produced by those in the Urban Response Community of Practice, as identified and monitored by ALNAP's Directory of Urban Humanitarian Learning | Plan for 3 knowledge products with timings and proposed focus of each | 1 knowledge product produced. | At least 3 knowledge products produced based on evidence and lessons learnt from IRC urban programming and other non-IRC urban humanitarian and development programming over life of project. | Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response. Relevant actors - including local and global humanitarian and development organisations, and local and national governments - are receptive to new evidence and tools, and are willing to adapt policies and operational behaviour in response to these.
|  | Achieved |  |  | 1 knowledge product drafted | As of December 2016, 2 knowledge products were produced and disseminated. By December 2017, 5 knowledge products were produced and disseminated.
Source
Knowledge products, IRC monitoring of urban programme, staff interviews (IRC and other operational actors).
| Output Indicator 2.2 (Learning) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of Regional Practitioner Workshops delivered independently or jointly with IIED on how urban contexts are impacted by crises and to promote exchange of knowledge on how to programme effectively in urban areas. | Planned | None. | Plans for Regional Practitioner Workshop to be delivered jointly with IIED. | 1 Regional Practitioner Workshops delivered by IRC in collaboration with IIED. | 3 Regional Practitioner Workshops delivered by IRC or jointly with IIED.
|  | Achieved |  |  | 1 Regional Workshop held in Instanbul | 3 Regional Practitioner Workshops delivered
Source
Workshop materials, feedback forms and interviews with external actors on workshops, IRC reporting on urban programme
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
35% The learning component of this project critically feeds into the advocacy work and provides the tools for humanitarian actors to implement their improved understanding and commitment. |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium. Risk is that humanitarian space further limited in Syria region limiting scope for learning and research
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## IRC-final
Please refer to the Smart Guide for advice on completing the various fields in the log frame.
Smart Guide
PROJECT TITLE | DFID-IRC Advocacy and Learning Partnership on Urban Humanitarian Crises
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
Individuals, households and communities impacted by crises are safe, healthy, educated and economically empowered and, along with the cities they live in, are better able to cope with future shocks and stresses. | Humanitarian response and programming takes into account long term needs of the city, its residents and development objectives | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Humanitarian response and preparedness is mainstreamed into urban planning and governance processes | Planned
Achieved
Source
Evaluations of emergency responses in urban areas affected by crisis. Reports and policies from associations of planners and city authorities (eg UCLG)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Mar 17) | Milestone 2 (June 17) | Milestone 3 (Sept 17) | Target (Dec 17) | Assumptions
Urban and humanitarian stakeholders (including local governments) will increase their knowledge, technical capacity, and commitment to working in partnerships (including through providing appropriate institutional support) in order to be better able to meet the immediate needs of cities and urban residents affected by crises (including the way these shape and are shaped by gender relations), to foster recovery and sustainable development in their aftermath, and to strengthen preparedness for future events. | Global policy discussions relevant to urban crises/Alliance thematic priorities reflect key Alliance messages | Planned | New Urban Agenda contains references to humanitarian crises. New York Declaration on Refugees and Migrants references urban areas and the importance of context. IASC Principals endorsed an Urban Action Plan in May 2015 | Global Alliance priority messages are agreed/endorsed at Alliance members meeting in March. Relevant policy discussions/processes and opportunities to collectively influence during 2017 are identified. | Evidence of coordinated Alliance messaging and advocacy at ECOSOC Humanitarian Affairs Segment. Steering Group advocacy and policy influencing strategy in place | Evidence of coordinated messaging during UNGA session period. | By end 2017 relevant global policy/operational discussions (eg Global Refugee Compact and IASC Principal meetings) are sensitive to urban context and reflect relevant Alliance messages and actions. | Current trends towards increasing urban considerations in humanitarian and development policy, funding and programming continue. The Global Alliance for Urban Crises Steering Group and Secretariat operates effectively and priorities remain aligned with those of the DFID/IRC partnership. Alliance Steering Group is receptive to the efforts of IRC/DFID partnership and is active in it's advocacy role. Non-humanitarian actors recognise relevance of the urban crises agenda to their work and seek to engage with the Alliance. The Global Alliance Steering Group, IRC and DFID will be able to access and influence relevant policy discussions including ECOSOC Humanitarian Affairs Segment, UNGA discussions and processes, Global Refugee Compact discussions and processes and IASC Principals and relevant meetings. Alliance members in countries where IRC will hold workshops are willing to engage during and collaborate post workshops. Relevant actors - including local and global humanitarian and development organisations, and local and national governments - are willing to change their attitudes, policies and operational behavior in response to advocacy messages, new evidence and tools. Alliance working group members are committed and work collaboratively to develop and implement work-plans. Messages on urban crises will be heard by relevant policy makers and result in real policy change.
|  | Achieved |  | Meeting held and influencing opportunities identified | Partially met - SG members attended Segment meetings in June & SG policy and advocacy strategy is being drafted. | Partially met - Although individual Alliance members were able to advance pre agreed messages at UNGA high-level event with Brookings Institute, the Alliance itself did not convene the meeting and thus was not in a position to sign on to the letter. | Program influenced key messages including: Global Compact on Refugees, Europen Union policy, IASC meetings and World Bank policy.
Source
Key informant interviews, outreach tracker, reports, policies and public statements from governments, donors, multilateral institutions and other sources. Reference to policy recommendations in relevant processes/outcomes.
| Outcome Indicator 2 |  | Baseline | Milestone 1 (Mar 17) | Milestone 2 (June 17) | Milestone 3 (Sept 17) | Target (Dec 17)
| Cities impacted by crisis and their response actors show operational commitment to foster recovery, encourage sustainable development and future resilience for all city inhabitants. | Planned | Humanitarian response actors and local authorities in cities do not work towards common goals of long-term recovery and resilience as outlined in the Global Alliance recommendations. |  | One local authority or municipality of a city in crisis is committed to fostering recovery and resilience in the long-term evidenced by documented changes. | Two local authorities or municipalities of a city in crisis are committed to fostering recovery and resilience in the long-term evidenced by documented changes. | Two local authorities of a city in crisis are committed to fostering recovery and resilience in the long-term evidenced by documented changes.
|  | Achieved |  | One local authority (Greater Municipality of Amman) committed to fostering recovery and resilience in the long term | Exceeded - in May IRC, 100RC, and Greater Amman Municipality co-hosted Amman City Practitioner Workshop, Amman Resilience Strategy was released, 20 NGOs attended workshop and 8 commited themselves to Resilience Strategy. City of Athens also released Athens Resilience Strategy. Kampala City Practitioner workshop is in planning. | Exceeded - During the quarter, the IRC held a city practitioner workshop, which included commitments from Kampala Capital City Authroity. Also, Paris released Resilience Strategy including IRC recommendations. | As previously reported, the local authorities of Amman, Arua, Athens, Kampala, and Paris – a total of five municipalities - have expressed a commitment to fostering recovery and resilience for their displaced populations in the long-term in ways directly attributed to the Urban Crises programme.
Source
Documented plans, policies, or actions by traditional or non-traditional humanitarian actors (including local authorities) attributable to actions by the project
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
9
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (Dec 17) | Assumptions
The Global Alliance for Urban Crises is operational and effectively functioning the end of 2017 | Priority working groups supported with advice on policy and practice | Planned | No WGs established | Decision on priority working groups made | Workplans in place for at least 2 working groups | 2 working groups operational and meeting regularly | 3 WGs operational/meeting regularly | working groups align with IRC/DFID priorities. Working Group members are receptive to IRC/DFID's facilitory and supportive role in developing workplans and advocacy strategies. Alliance Steering Group (and members) is able to fundraise to ensure appropriate support is available so that that the secretariat and steering group can operate independently
|  | Achieved |  | Working groups were decided | Met - working plans in place for 2 WGs and other 2 working plans will be completed end of July. Co-leads of each working group will convene in August to form overall policy and advocacy strategy. | Exceeded - Three of the four working groups (WGs 2,3 & 4) have met regularly and finalised their work plans. WG 1 also began an informal mapping of existing tools used in urban crises from across its members, although they have not yet met. | The target milestone of 3 Alliance Working Groups operational and meeting regularly was exceeded. All 4 Alliance working groups are operational and have funding to sustain themselves through 2018.
Source
Reports from Global Alliance Steering Group and from Working Groups
| Output Indicator 1.2 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (Dec 17)
| Preliminary findings from Alliance activities and working groups are amplified by the Steering Group and informing global advocacy and policy messages | Planned | Alliance members' findings/messages incorporated in an ad hoc manner in to global advocacy and policy processes | Advocacy and Policy influencing priorities identified for Steering Group and for priority working groups in March Meeting | Working groups have established mechanism for feeding back on progress made towards priorities to Steering Group/Secretariat | Priority working groups have identified policy and advocacy messages and an advocacy/influencing strategy in place | End of programme event in partnership IIED amplifying messages from all priority working groups, the Steering Group and the Urban Crises Programme
|  | Achieved |  | Influencing priorities discussed but still not submitted | Met - mechanisms for feedback and regalular review processes established between WGs and SGs. | Met - Policy change priorities and advocacy opportunities have been identified through the working group work plans, and the draft advocacy strategy circulated by the Alliance Secretariat to the Steering Group in August. Coordinated messaging is being fostered at different levels of the Alliance. | The end of programme event was held in November 2017 and was attended by over 100 participants from academic institutions, UN and donor agencies, INGOs, state governements, and local municipal authorities.
Source
Reports from Global Alliance Steering Group; reports, policies and public statements
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (Dec 17)
| Steering Group well established, including its secretariat, and lessons from the Urban Crises Programme amplified | Planned | Steering Group newly formed with no strategy, priorities or work plans in place | Alliance strategy drafted and ToRs agreed for secretariat and Steering Group | Alliance Work plan (for secretariat and SG) agreed and in place | at least 3 steering group meetings held | Secretariat and Steering Group can function without additional support from IRC
|  | Achieved |  | Strategy drafetd and TORs agreed and attached with the report | Met - Secretariat work plan in place and weekly review process between Secretariat, IRC, and UNHabitat in place. | Partially met - Two meetings were held. A third meeting planned for August was cancelled due to the inability to reach a sufficient level of participation during the summer, when many members were on leave. | The Steering Group is now well established, following an in person meeting in Paris in October 2017, followed by two subsequent conference call meetings in November and December 2017. The meetings have provided a space to discuss a range of issues including, advocacy, fundraising, Working Group activities and renewal of the TOR for the SG itself.
|  | Source | [5 empty] | RISK RATING
|  |  | Reports from Global Alliance Steering Group and secretariat; |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
|  |  |  | March | June | September | December
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (date) | Assumptions
Global Alliance vision and priorities translated to city level where cities are affected by displacement | Number of city practitioner workshops held that involve at least 4 members that represent non-traditional humanitarian actors (professional networks, local authorities, academics) | Planned | 0 | 0 | 1 city workshop held | 2 total city workshops held | 2 total city workshops held | Workshops can be delivered within the planned timeframe and relevant case studies can be documented soon thereafter. Local authorities will be receptive to hosting or participating in workshops. Response practitioners are open and willing to participate in workshops and coordinate and/or collaborate thereafter. The IRC will not be seen as impeding on existing efforts to coordinate urban responses wherever they exist
|  | Achieved |  | Workshop planned for May in Amman | Met - 1st City Practitioner Workshop, co-hosted by IRC, IIED, 100RC, and Greater Amman Municipality held in May. Planning for workshop in Kampala in September has begun. | The IRC successfully hosted two city workshops, titled Urban Practitioner Workshops, in Amman (May 2017) and Kampala (September 2017). Each workshop was co-hosted with the local municipal authority and resulted in clear commitments under Outcome Indicator 2 for many stakholders in each city. | The IRC successfully hosted two city workshops, titled Urban Practitioner Workshops, in Amman (May 2017) and Kampala (September 2017). Each workshop was co-hosted with the local municipal authority and resulted in clear commitments under Outcome Indicator 2 for many stakholders in each city.
Source
Workshop attendance list
| Output Indicator 2.2 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (date)
| Number of case studies published and disseminated documenting at least one example of collaboration in each network | Planned | 0 | 0 | 2 case studies published and disseminated | 4 total case studies published and disseminated | 4 total case studies published and disseminated
|  | Achieved |  | The case study will be one output of the Workshop | Exceeded - three case studies were published during reporting period. | Exceeded - During the period, 2 additional case studies were prepared for in the 5th knowledge produce on Lebanon municipalities. | The IRC published or dissiminated six case studies of collaboration over the course of the grant, with an additional case study published under the programme but after the grant’s formal end date. They include case studies of humanitarian-local authority partnerhips in Amman, Athens, Kampala, Maiduguri, Paros and two in Lebanon with several municipal authorities or unions of municipalities.
Source
Written case studies published and disseminated
| Output Indicator 2.3 |  | Baseline | Milestone 1 (March 2017) | Milestone 2 (June 2017) | Milestone 3 (September 2017) | Target (date)
| Number of city-wide reports published and disseminated on collaboratively working towards recovery and resilience in response to urban crises | Planned | 0 | 0 |  | 1- shared or accessed by at least 150 users | 1- shared or accessed by at least 150 users
|  | Achieved |  | On track |  |  | The report, From Response to Resilience, details the long term plans of Amman and Kampala to address urban displacement. Publication was delayed publication in order to receive sign-off for co-publication with relevant municipalities and 100 Resilient Cities. The report was published in February 2018 and disseminated to over 150 users.
Source
City Practitioner Workshop attendance lists, case studies, City wide reports published, # of shares or access
IMPACT WEIGHTING (%)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
8
INPUTS (HR) | DFID (FTEs)

## IIED-final
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
|  |  |  | 2015-12-31 | 2016-12-31 | 2017-12-31
PROJECT TITLE | Building knowledge, skills and understanding for response to urban humanitarian crises
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Individuals, households and communities impacted by crises are safe, healthy, educated, and economically empowered and, along with the cities they live in, are better able to cope with future shocks and stresses. | Humanitarian response and programming takes into account long term needs of the city, its residents, and development objectives | Planned | literature review
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Humanitarian response and preparedness is mainstreamed into urban planning and governance processes | Planned
Achieved
Source
|  |  |  | 2015-12-31 | 2016-12-31 | 2017-12-31
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17) | Assumptions
Urban and humanitarian stakeholders (including local governments) will increase their knowledge, technical capacity, and commitment to working in partnerships (including through providing appropriate institutional support) in order to be better able to meet the immediate needs of cities and urban residents affected by crises (including the way these shape and are shaped by gender relations), to foster recovery and sustainable development in their aftermath, and to strengthen preparedness for future events. | Number of urban and humanitarian stakeholders from different sectors gaining improved knowledge, technical capacity and skills to plan for and respond to urban humanitarian crises* | Planned | Strategic steering group identify availabity of current material as insufficient for the scale of need | Target urban and humanitarian stakeholders needing capacity building for urban response and urban toolkits are identified | At least 10 urban and humanitarian stakeholders have been exposed to knowledge products, learning events and/or networking; at least 2 consultation draft toolkits developed | Strategic steering group assess availability of materials as sufficient to meet needs of urban and humanitarian stakeholders, through knowledge products, learning events and/or networking | Current trends towards increasing urban considerations in humanitarian and development funding and programming continue. Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response. Relevant actors - including local and global humanitarian and development organisations, and local and national governments - are willing to change their attitudes, policies and operational behaviour in response to advocacy messages, new evidence and tools.
| *key stakeholders will be defined once the Learning Partnership has been established | Achieved
Source
Six-monthly reports by Learning Partnership; minutes of SSG meetings
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17)
| Institutional support from local, national and international governments is visible in the form of recognition of the need to plan for recovery from humanitarian crises in development plans | Planned | Strategic steering group identify current level of knowledge and recognition of local, national and international governments as insufficient | Relevant local, national and international government bodies requiring support are identified | Engagement with at least 10 local, national and international bodies | Strategic steering group feedback identifies international processes as promoting urban concerns to a greater extent; and national and local planning processes accounting for humanitarian concerns in the target countries/cities
Achieved
Source
six-monthly reports of Learning Partnership IIED logframe tracker; minutes of SSG meetings
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2525912.34 |  |  |  | 2525912.34
INPUTS (HR) | DFID (FTEs)
1
|  |  |  | 2015-12-31 | 2016-12-31 | 2017-12-31
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17) | Assumptions
Effective practices documented, tools generated and innovative operational working methods developed by the learning consortium. | Number of tools and knowledge products co-produced by partners within the two consortia | Planned | An assessment by SSG finds current level of knowledge products available is insufficient to meet knowledge and information needs of both humanitarian and urban stakeholders | Consortia formed and workplan for production of knowledge products (of different types) and tools developed | At least 3 tools and knowledge products produced (including research papers, briefing papers, advocacy notes, guidebooks) produced by consortium members | A total of 9 tools and knowledge products (including research papers, briefing papers, advocacy notes, guidebooks) co-produced by consortia; SSG assess knowledge and information needs to be better met by existing tools and products | A pool of suitably skilled and qualified organisations and researchers exist and are able to undertake the necessary activities and documentation. Programme partners are able to identify and access the right forums to disseminate key findings and messages. Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response.
|  | Achieved |  |  |  | exceeded
Source
Six-monthly reporting by Learning Partnership; minutes of SSG meetings
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17)
| Number of learning events jointly delivered by partners within in the two consortia. | Planned | An assessment by SSG finds that there is a lack of collaboration and communication between humanitarian actors in different sectors (conflict, disaster, etc) | Workplan developed for learning events co-organised and independently organised by consortium members | At least 2 joint events held, one of which at the World Humanitarian Summit | A total of 4 events held and jointly organised by consortia; Learning Consortia lead to better communication between humanitarian sectors in urban areas as assessed by SSG and LC members
|  | Achieved |  |  |  | exceeded
Source
Six-monthly reporting by Learning Partnership; minutes of SSG meetings
IMPACT WEIGHTING (%) |  |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40 | [6 empty] | Risk rating: medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1078864.9347 |  |  |  | 1078864.9347
INPUTS (HR)
0.4
|  |  |  | 2015-12-31 | 2016-12-31 | 2017-12-31
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec '17) | Assumptions
Innovative thematic and regional research produced through a learning fund and small scale research and documentation fund. | Number of research grants allocated through the learning fund and the small-scale research fund | Planned | A pool of suitably skilled and qualified organisations and researchers are idenfitied and are able to undertake the necessary research to fill gaps in knowledge. | First round of 10 research grants allocated | Second round of 15 research grants allocation | A total of 25 research grants allocated | Programme partners are able to identify and access the right forums to disseminate key findings and messages. Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response.
|  | Achieved |  |  |  | exceeded
Source
IIED project tracking database
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec '17)
| Number of knowledge products produced from both funds and disseminated at events and through online downloads | Planned |  | 10 knowledge products in progress; accurate assessment of forums for dissemination identified (including workshops, seminars, conferences and other events) and dedicated IIED webpage created for knowledge products | 10 knowledge products complete and 15 in progress; At least 2000 total internet downloads and papers disseminated during at least 3 events | At least 25 working and briefing papers produced; At least 5000 internet downloads and products disseminated at a further 3 events
|  | Achieved |  |  |  | exceeded
Source
IIED products tracker; ALNAP download tracker
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17)
40 | Effective and relevant knowledge products are produced (including products with particular focus on needs of different groups and gender relations)* | Planned | An assessment by SSG finds gaps in ability of current knowledge products to meet knowledge and information needs of humanitarian and urban stakeholders and advocates. | A framework for assessing effectiveness and relevance of the knowledge products is produced jointly with IRC | An assesment by SSG indicates that knowledge products are relevant and being accessed by appropriate stakeholders | The products are assessed to have had a strategic impact by SSG members in global and local platforms.
| *The effectiveness of relevance of the products will be assessed through a framework jointly developed with IRC | Achieved |  |  |  | met
|  | Source |  |  |  |  | RISK RATING
|  | Minutes of SSG meetings |  |  |  |  | low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1262364.9347 |  |  |  | 1262364.9347
INPUTS (HR)
0.4
|  |  |  | 2015-12-31 | 2016-12-31 | 2017-12-31
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (Oct 17) | Assumptions
Best practices disseminated, policy changes discussed and capacity of key actors built through learning events, networking, and effective project management. | Number of different types of events organised (webinars, workshops) and number of participants atttending the events, with feedback from participants indicating that they plan to make use of workshop content in their work | Planned | IIED and IRC jointly identified types of events and potential dates and locations for these in order to reach key stakeholders | Workplan for key events of different types prepared; Target audience for events and network identified; 1 event held with at least 20 participants. | A further 2 events held including 1 at World Humanitarian summit; at least 50 people with representation from different sectors attend events and indicate that contents will be used to inform their work. | A total of 4 learning events; each attended by at least 20 people, with representation from different sectors, attend events, and indicate that contents will be used to inform their work. | Global and local humanitarian actors are willing to share their own experiences, including failures, as a means of strengthening understanding of urban humanitarian response. Relevant actors - including local and global humanitarian and development organisations, and local and national governments - are receptive to advocacy messages, new evidence and tools, and are willing to change their attitudes, policies and operational behaviour in response to these.
|  | Achieved |  |  |  | exceeded
Source
IIED logframe tracker
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17)
| Number of events at which research outputs shared | Planned | There is a need for more events at which new knowledge products and tools are delivered, and different stakeholders are brought together | Mapping of key events prepared | Research outputs shared in at least 3 events | Research outputs shared at a total of 6 events
|  | Achieved |  |  |  | exceeded
Source
IIED logframe tracker
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (Dec 17)
20 | Chances of reaching the most relevant people are maximised and information that is most useful to them is shared to them | Planned | An assessment by SSG finds key humanitarian and urban stakeholders are lacking necessary and useful information regarding response to urban humanitarian crises | Mapping of key target audiences and their information needs prepared | SSG assessment indicates that relevant contacts are utilising knowledge products | An assessment by SSG finds that events have been targeted at the most relevant actors
|  | Achieved |  |  |  | yes
|  | Source |  |  |  |  | RISK RATING
|  | Minutes of SSG meetings |  |  |  |  | low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 184682.4674 |  |  |  | 184682.4674
INPUTS (HR)
0.2

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.