Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Macroeconomic and High Level Policy Making Support Fund
Programme Value: £4.5 million		Review Date: June 2017
Programme Code:	Start Date: June 2014	End Date: March 2018

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

Introduction
The Macroeconomic and High Level Policy Making Support Fund (‘the Macro Fund’) is part of a portfolio of economic development programmes through which DFID supports the Government of Ethiopia. It was set up during the growth of DFID’s economic development portfolio, specifically to be flexible and respond to emerging needs of Government. By delivering technical assistance in key areas, such as logistics, it has forged a path for larger DFID programmes, such as the Ethiopian Investment Advisory Facility (EIAF) to take forward more substantial work. DFID’s increased focus on economic development comes at a crucial time for Ethiopia as it looks to build on the development outcomes it has achieved over the last decade and push towards a pathway of further industrialization and sustainable growth.

Performance
The macro fund has performed well this year, providing high-quality, evidence-based technical assistance to the Government of Ethiopia (GoE). Through its support to the International Growth Centre the Macro Fund has helped strengthen systems within the Ethiopian Investment Commission (EIC) to build relationships with investors and address any problems they have; this year it has also helped build a new export reporting scheme. Core funding for the Economic Policy Analysis Unit (EPAU) has enabled the unit to provide high quality analysis and policy advice to the heart of the GoE, improving the use of evidence in policymaking on some highly sensitive issues. A new project on trade logistics has provided technical assistance for scoping work on critical trade bottlenecks, enabling major improvement programmes to take place in the coming year.

Two projects have faced difficulties. Technical assistance to the National Bank of Ethiopia (NBE) has not performed as expected due to misaligned expectations and breakdown in the working relationship between the IMF and the NBE. DFID will work with the IMF, NBE and other donors to ensure that the technical work that has been delivered can be used productively in future, even if plans for the secondary market have been delayed. Planned technical assistance to the Ethiopian Maritime Affairs Authority (EMAA) was cancelled before the mission begun, due to a breakdown in the working relationship between UNDP and the EMAA. DFID staff are now working with UNDP to redesign the project; if this cannot be agreed the money will be returned to DFID.

Feedback from GoE officials indicates that the outputs of the Macro Fund are of high quality and are useful to policymaking. The Fund is reactive to recipient requests, meaning that it is strongly aligned to GoE’s priorities and needs. This has the advantage of building the GoE’s trust in DFID, and increasing the UK’s influence. However, the disadvantage of this approach is that it reduces the coherence of the Fund. Two of the projects – support to the EIC, and trade logistics – focus more on organisational capacity building and specific technical assistance than macroeconomic or high-level economic policy or analysis. This makes it harder to assess the overall performance and effectiveness of the Fund against the original outcome statement.

The macro fund is due to end in 2018. As the macro fund has laid the foundations for other technical assistance programmes on economic development (such as EIAF) the programme will not be expanded or extended. All projects currently running under the fund should come to an end. Any legacy monitoring of projects will take place through other related DFID Ethiopia programmes.

Compliance to Gender Equality Act:
We assess that there is little direct impact on gender outcomes from outputs of the macro fund. However, by supporting the Government to maintain a stable macro economy and improve economic policy making it can contribute to creating greater economic opportunities, for both women and men. Macroeconomic stability tends to expand the opportunities for women and girls at least as much as for men and boys[1].
[1] World Bank (2012) Gender equality and development, p.100.

Summary of recommendations for the next year

Recommendation 1: Given the reactive nature of the fund, it is particularly important that each new project is carefully monitored. This should include all aspects of Value for Money, including measurement of impact. This will not always be in the form of quantitative metrics, but could include regular conversations with senior GoE officials to ensure that the project remains relevant to their priorities and that the outputs are leading to greater use of evidence in decision making.

Recommendation 2: Although most of the Macro Fund outputs have no impact on gender equality, next year’s review should assess whether gender impacts were taken into account in those projects where there is a more direct connection, for example the recruitment strategy of the EIC, and in the impact on livelihoods assessment of the Berbera corridor diagnostic.

Recommendation 3: Pay careful attention to political economy risks in design and appraisal of new projects or requests for funding extensions, specifically 1) the need for a good working relationship and alignment of expectations between the GoE and providers of technical assistance, and 2) undermining of projects due to ideological policies, vested interests or renewed protests.

Action on key recommendations from the 2016 Annual review:

Recommendation 1: DFID should actively try to reduce the administrative cost of Macro Fund sub-projects. This could be done by aiming to fund projects with a larger average size and by streamlining the approval process.

This year, the Macro Fund approved three new trade logistics-related projects, costing £262,000,
£560,000 and £550,000. This means that the average size of project has indeed increased. There have also been extensions to existing projects, but these pose a much smaller administrative burden.

Recommendation 2: consider extending its support for EPAU beyond October 2016. In addition, if EPAU struggle to recruit middle management through the systems that are now in place, DFID should consider facilitating the hiring of consultants on a fixed term basis to supplement EPAU’s core staff.

A request for funding extension was received in October 2016 and a new grant was made in May2017.
It appears that the EPAU’s recruitment process was successful and therefore it is no longer in need of short-term consultants.

Recommendation 3: routinely update risk register as projects are approved to reflect the impact on overall programme level risk.

The risk register has been updated as part of the Annual Review process to reflect the risks highlighted in project proposal documents.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204803/documents/
DevTracker Link to Log frame:

What support is the UK providing?
Through the Macro Fund, the UK’s Department for International Development (DFID) is providing up to £4.5 million over four years (2014/15 to 2017/18) to strengthen the use of evidence in macroeconomic and high level economic policymaking in Ethiopia. Support is provided through a flexible and responsive mechanism that is able to mobilise international and local expertise at short notice on key macroeconomic and growth related policy challenges. Key partners and recipients of the macro fund support include the Ministry of Finance and Economic Cooperation (MoFEC), the National Planning Commission, the National Bank of Ethiopia (NBE), the Ethiopian Investment Commission and the Prime Minister’s Economic Policy and Analysis Unit (EPAU).

Why is UK support required?
Despite the strong economic growth & poverty reduction performance, Ethiopia has been witnessing signs of strain on the macro economy. Ethiopia continues to be vulnerable to inflationary pressures, a widening trade deficit and the large financing requirements of State Owned Enterprises (SOEs), particularly in energy, sugar and transportation, which has pushed up the combined deficit to close to 10% of GDP.

There is good evidence that macroeconomic instability is having a negative impact on the prospects for growth and on the poor[2]. For instance, inflation has been higher than savings interest rates for several years, creating a disincentive for savings at a time of high investment. Access to finance continues to be the most frequently cited constraint to private businesses. High inflation has also undermined competiveness and contributed to falls in export earnings. Lastly, there is strong evidence that the urban poor are disproportionately vulnerable to macroeconomic instability as they are less able to shield themselves from income and price volatility.
[2] IMF(2011), Joint (IMF-World Bank) Staff Advisory Note on Growth and Transformation Plan (GTP) (2010/11−2014/15).

What are the expected results?
The project impact is “improved macroeconomic stability and resilience” and this will be achieved through the “increased use of evidence in macroeconomic and high level economic policymaking”.

What has changed since the last Annual Review?
Widespread anti-government protests took place in the summer of 2016, partly motivated by perceived lack of economic opportunity in certain regions. Some protestors attacked foreign-owned businesses (though this was not a focus for the protests). The government has restored order, but a state of emergency persists, which creates risks for investment promotion initiatives, both from the possibility of renewed protest and from foreign investors being deterred by the state of emergency. To date we have not seen a significant impact of the state of emergency on foreign direct investment (FDI)
The macro economy has remained resilient over the last 12 months. Inflation has been relatively stable, with prices 7.1% higher than this time last year[3]. FDI has been buoyant, reaching approximately $2 billion in the first half of the Ethiopian financial year (July 2016 – January 2017). Growth is estimated to be 7.5% in 2017[4]. However, there is some concern about debt levels, which have increased rapidly over recent years threatening to pull Ethiopia into high risk of debt distress. The Government has now cut its external borrowing to respond to this risk. The UK is closely monitoring the situation.
[3] 12 month moving average inflation, May 2017. Central Statistics Agency of Ethiopia.
[4] IMF estimates. GoE estimates tend to be larger.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

There has been encouraging progress towards delivering the Macro Fund‘s objective of ‘increased use of evidence in macroeconomic and high level economic policymaking”. Funding has been used to build capacity and improve systems for evidenced-based policy making. Overall, the project is on course to deliver its desired impact by the time of project completion (May 2018). However, the specific target of ‘Ethiopia has established a secondary market for securities based on the advice of the IMF’ is very unlikely to be attained.

Outcome Indicator	Milestone	Assessment
Evidence that macro fund outputs have led to an improvement in GoE economic policy making	(i) Macroeconomic reporting from NPC is informing the decisions of the economic council	The National Planning Commission have used the template developed last year by the consultant for their quarterly report. They have produced 3 quarterly reports so far for the FY16/17, and gave very positive feedback about the template and knowledge transfer.
	(ii) Key NBE officials have established an understanding of the operations and management of the secondary market	Training and capacity building provided by the IMF long term Advisor has improved key NBE officials’ understanding of secondary markets; however, the programme has not progressed well and NBE staff are very far from being able to manage a secondary market.

Overall output score and description

A – outputs are in line with expectation. Although the specific outcome milestones for 2017 have not shown progress in line with expectation, these only reflect two projects (and one had already closed). Taking the live projects as a whole (i.e. taking into account all the outputs) there has been good progress this year, and there is evidence from feedback that the outputs have been used to improve GoE policy making.

Key lessons

Relationships are key to the effectiveness of TA: in two Macro Fund projects, relationships between the GoE and the implementers (IMF and UNDP) have broken down, which has endangered the outcome of the project. DFID should consider the GoE’s existing relationship with a potential implementing partner as a key factor when assessing new projects. It was well-understood by DFID that relationships between the IMF and Government of Ethiopia have been poor in the past. This project was seen as a way of strengthening that relationship by working towards a common objective. While the risks around the relationship were well understood, perhaps the ambition on the outcome was too high.

The Macro Fund is largely reactive (to requests from the GoE), which has its advantages, but can result in a lack of strategic focus. For example, the EIC and trade logistics projects do not relate to macroeconomic policy making, the former does not relate to policy making at all but rather to capacity building in core government operations. However, while these did not completely align with the original scope of the business case, they have been strongly complementary to other projects within the economic development portfolio and contributed towards DFID’s overall strategic objectives in Ethiopia. DFID should be explicit about the trade-offs between flexibility and focus and ensure the rationale for each project is made clear.

The experience of the long term Advisor to the NBE suggests that DFID also needs to take extra care in cases where a single external advisor is embedded in a government agency, as they can be isolated and do not necessarily have access to management chain support.

Key actions

As part of ongoing progress monitoring, and in the PCR, DFID should seek feedback from senior Ethiopian government officials, from a wide range of posts if possible, to assess whether the outputs of DFID funded assistance are truly being valued and used by the GoE.

Has the log frame been updated since the last review?

The log frame was updated at the beginning of April to reflect new project which started since the last annual review and two extensions of on-going projects:

Output 1 (IGC support to the Ethiopian Investment Commission)
Output indicator 1.1 has changed to reflect the extension of the programme. Previously was “final report received by DFID details significant progress on both the investment promotion and export promotion work stream”. Changed to “ Interim report  provides evidence of significant progress of the relationship building programme including transfer of principles of programme to industrial parks; extension of file sharing system; induction of new staff; and embedding of processes within organisation”.

Output 2 (EPAU)
As DFID support has been extended, a target for June 2018 has been added, and the target for 2017 has been converted to a milestone for the same.

Output 3 (IMF)
No change

Output 4 (ad hoc requests/usefulness)
No change

Output 5 (Trade logistics)
This is a new output, reflecting the Support to the Ethiopian Trade Logistics Sector project which was started after the previous Annual Review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective Policy support to the Ethiopian Investment Commission
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1) Delivery of technical support in investment promotion and export promotion work stream	Interim report provides evidence of significant progress of the relationship building programme including transfer of principles of programme to industrial parks; extension of file sharing system; induction of new staff; and embedding of processes within organisation.	The central objective of embedding the new relationship building scheme has been achieved very well, transfer of principles to industrial parks has begun, induction of new staff takes place on an ongoing basis, extension of the file sharing system has been delayed.
1.2) Feedback from high-level officials within the GoE.	Director General of EIC and/or PM’s advisor on industrialisation rate the support as highly valuable	The Deputy Commissioner of the EIC was very positive about the value of the support, describing it as “very effective” and “very successful”. There are plans within EIC to scale-up the relationship-building programme.

Key Points

The International Growth Centre (IGC) support to the Ethiopian Investment Commission (EIC) focuses on technical advice, building capacity and systems strengthening. The core focus of the programme is on the “relationship building programme”, which aims to improve the service to investors from the EIC. It has created systems though which issues investors face are tracked systematically by the EIC. The DFID-funded consultants have continue to strengthen and embed the relationship building programme, working with staff to improve monitoring of cases, minuting of meetings and follow up on action points. The recently recruited Deputy Commissioner has increased the frequency of team meetings in order to increase mutual support for addressing problems and speed up resolution. Feedback from a relationship building team leader indicates that the consultants’ role has been extremely helpful in facilitating solutions and improving working practices. The consultants take a capacity building approach, both formally (providing training to new recruits) and informally (helping staff to think through issues and how to deal with them). This is a sentiment shared by the Deputy Commissioner and Commissioner. There are plans to roll out the relationship building programmes to EIC’s regional centres.

As the technical assistance to the EIC enters its last year, the capacity building aspect has become more important, and the consultants report that they have been handing over more functions to permanent staff, and are searching for the most skilled new recruits to take over the ‘progress chasing’ role.

Since the last annual review, the EIC has been required to report on export behaviour by firms it assists, in line with the increased focus on exports by senior policymakers including the Prime Minister. The consultants have prepared a template for the export report, and a data collection tool for firms. This is now in the early stages of adoption, but appears to be progressing well.

The introduction of the export report has taken up much of the consultants’ time, and therefore there has been less progress on expanding the file sharing system or transferring principles to the industrial parks. Nonetheless, they have provided some consulting for the deputy commissioner for industrial parks, and will do more in the coming year.

Overall, the technical assistance has produced very tangible improvements in the EIC operating procedures, which is reflected in positive feedback from foreign firms who are being helped by the EIC.

Recommendation: Since the support to the EIC via the IGC started DFID has increased its support to the EIC via other channels e.g. the Private Enterprise Programme for Ethiopia. As the IGC work comes to the end of this phase DFID should consolidate its support to the EIC and no longer provide support via the macro fund.

Output Title	Effective implementation of the Prime Minister's Economic Policy and Analysis Unit (EPAU) work plan
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y (reduced from 40%, as new output added for trade logistics)

Indicator(s)	Milestones	Progress
2.1) Number of Policy Papers, White Papers, programme evaluations and research products produced by EPAU (per year)	15	19
2.2) Feedback from the EPAU Technical Oversight Committee and senior GoE policymakers on the quality and effectiveness of EPAU's outputs.	Strong with clear reference to quality of outputs and impact	The technical oversight committee of EPAU is not active. This indicator should be revised.

Key Points

Although the number of policy papers, White Papers, programme evaluations and research products falls short of the milestone, a wider assessment of the EPAU’s activities indicates that it is performing well. Outputs this year include:
- Completing the Validation Plan for the Large-scale Commercial Agriculture (LSCA) Strategy, and drafting the LSCA Strategy Framework
- Developing an in-house data cleaning software toolkit for trade and output statistics, which has been adopted by the World Bank for use in other African countries.
- Preparation of an export statistics report (using regularised statistics as above), including in-depth investigative pieces on focus sectors or individual firms. This will be launched soon, and subsequently form a quarterly series.
- Monitoring of grain prices in 19 major domestic markets, with monthly reporting and quarterly forecasts.
- Development of the National Logistics Capacity Building Strategy for the Ethiopian Shipping & Logistics Services Enterprise.
- Policy briefs on World Trade Organisation accession, regional agreements, & other trade topics.
- Has started consultations for Ministry of Health Transformation Plan, but work has been suspended while MoH undergoes internal re-organisation following change of Health Minister.
The EPAU has also engaged in capacity building, recruiting analysts and programme officer to fill gaps that were noted in last year’s AR, and expanding staff development & training.

The EPAU continues to enjoy a high profile within the Ethiopian government, and has been tasked with assisting on some of the GoE’s highest priorities, including export promotion, health and commercial agriculture. The development of a new LSCA strategy is a highly sensitive task, due to recent accusations of ‘land grabbing’ and forced displacement, and the selection of the EPAU to handle this reflects the confidence that the Prime Minister has in them. At the review meeting the head of the EPAU requested DFID’s help in procuring an international expert to input into the LSCA strategy, specifically recognising the need for international legitimacy for the new strategy.

Outputs and analysis produced by EPAU are often produced for the Prime Minister or senior Government ministers. It can therefore be difficult to obtain direct feedback on the quality and effectiveness of the outputs. However we can infer this from the continued demand for analysis from senior policy makers. DFID should endeavour to discuss EPAU when possible with senior ministers.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous AR recommended that DFID extend its support for the EPAU for another year: a formal request for funding extension was received in October 2016 and a new grant was made in May 2017.

The previous AR recommended that DFID support the EPAU by providing fixed-term consultants, should the EPAU’s staffing difficulties continue. However, it appears that the EPAU’s recruitment process was successful and therefore it is no longer in need of short-term consultants.

Recommendations

DFID should seek regular feedback from senior officials and other ‘customers’ of its analytical outputs, to assess whether the work of the EPAU remains relevant and of high quality.

Providing core funding to EPAU means that DFID is responding to a clearly articulated need on the part of the GoE, and wins DFID influence and trust. However, the GoE-owned nature of the programme poses some risks for DFID, both in terms of impact and the reputational risks associated with sensitive government policy.

DFID should consider closer oversight of the work of the EPAU, to increase its awareness of any issues or reputational risks.

Output Title	Effective delivery of technical assistance to the National Bank of Ethiopia on secondary debt markets
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1) Delivery of planned outputs against IMF project proposal	Long term adviser in place / Review of policy environment undertaken / Capacity building activities from NBE staff taken place - both on the job training and at least one study tour to either India, Kenya or Uganda"	Long term advisor is in place / A number of reviews have been completed. / Capacity building workshops have been delivered to NBE, and also Ministry of Finance and Economic Co-operation (MOFEC) and some commercial banks. / One exposure visit to Ghana organised for 3 senior NBE officials.
3.2) Feedback from senior NBE officials on the quality and effectiveness of the TA’s outputs.	NBE officials rate the support as highly valuable	Director of Monetary and Financial Analysis confirms that the outputs described in 3.1 have been useful; however there have been many disagreements over the scope and of the TA’s work and output has slowed down.

Key Points

This project aims to assist the National Bank of Ethiopia (NBE) to facilitate the start-up of the secondary market of Ethiopian government securities. At a strategic level, this technical assistance would help promote efficient financial market mechanisms, which would in turn support economic growth. DFID is funding the provisions of expertise, which is delivered via the International Monetary Fund (IMF).

The long term Advisor (LTA) from the IMF has been in place since September 2016. He has delivered most of the expected outputs: these include reviews of the policy environment and an action plan, which the NBE found useful. A number of outputs have been drafted, including a Fixed-income directive, a Central Securities Depositary directive, and an Operating Manual. The LTA has also organised an exposure visit to Ghana for three senior officials, including the Vice Governor of the NBE, which the Vice Governor found to be a very effective learning experience and prompted him to seek greater co-operation with MOFEC on his return to Ethiopia. The LTA’s workshops for NBE, MOFEC and commercial bank staff have also been well received.

However, this project has run into serious difficulties in the past six months, leading to a major risk that it will not deliver its aims, and that the launch of the secondary debt market will be delayed. Firstly, there has been a breakdown in trust and communication between the LTA and the relevant senior NBE officials, including the responsible Vice Governor. The LTA has not received comments on recent drafts he has submitted, including a proposal for the debt regulation unit, two directives and one guidance note. Secondly, the GoE has not yet finalised its policy on secondary debt markets, specifically which institutions will be permitted to take part when the market is launched, and this impedes finalising the relevant legal and technical documents. More broadly, lack of support and buy-in from the political level, and even from other parts of the NBE, have undermined staff morale and therefore limited the ability of the LTA to collaborate and transfer knowledge.

Overall, it is clear that the IMF and the NBE had very different expectations when the contract was first agreed, on both the role of the RA and on the policy framework for the secondary debt markets. This initial mis-alignment has, in the absence of effective mediation, led to a breakdown in the working relationship and impeded the effectiveness of the project. Given that considerable technical outputs have been delivered, in a manner which the NBE can use in future, this work has still had merit even if a secondary market is not launched at the end of it. DFID will work with the NBE, IMF and other donors to ensure that the technical work that has been produced will feed into any future developments once this particular project comes to an end.

Recommendations

In order to maximise the impact of the LTA in the time they remain in Ethiopia, remedial action is necessary. This could be:
- DFID Ethiopia can play a mediating role, convening both sides and agreeing a way forward with clearly defined tasks, responsibilities and expectations. DFID has already requested that the LTA draft a short note explaining which tasks and documents are on hold, requiring a policy decision from the GoE before they can be finalised; and/or
- A senior representative from the IMF could conduct a workshop to reach agreement on the exact role of the LTA, how they can work with NBE staff, and what the policy framework of the secondary debt market should be (though reaching agreement on the latter is very ambitious for a 1-day workshop)
If substantive progress is not possible from the above two, then a backup option would be:
For the LTA to focus on areas where agreement already exists on the usefulness of the approach, such as delivering workshops and training as needed, and writing guidance and reference documents such as the operating manual.

In addition, DFID should work with the NBE and IMF to ensure that the products that have been developed are treated as public goods and can be used as inputs for any future work in this area.

DFID-E can learn lessons for future TA projects:
More regular monitoring of projects to spot issues of concern earlier, even in cases where the supplier is a highly-regarded Development Partner.

Output Title	The macroeconomic support fund is a useful resource for GoE policy makers
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (revised from 20% to 10%)

Indicator(s)	Milestones	Progress
4.1) Ad hoc requests linked to macro-economic policy making are delivered on time and to a high quality	Based on demand	Outputs from funded projects generally produced to a high quality, e.g. diagnostic reports and project preparation from trade logistics project, / Draft directives from TA to NBE / Data cleaning toolkit from EPAU
4.2) Level of awareness and use of outputs of Macro Fund among Government and development partners	Evidence used regularly in partner discussions	The work of the EIC – including its relationship building programme – enjoys a high level of awareness amongst relevant ministers. / There is little awareness outside of a select, high-level group of policymakers of the analytical products being produced by EPAU. / There is currently little awareness or utilisation of the outputs of the TA to the NBE. / The scoping, diagnostic and proposal work by the IFC has been received by the Council of Ministers, and has led to the approval of the infrastructure for logistics project loan. / The head of the Ethiopian Maritime Affairs Authority is aware of the Berbera corridor diagnostic project, but the outputs have not yet come to the attention of ministers.
4.3) Annual number of requests from GoE officials for policy support on macro and high level economic policy advice	10	More than 10

Key Points

The Macro Fund has been used to support various projects this year. These include 3 projects concerning trade logistics, research by the Ethiopian Development Research Institute, and extensions to existing support to the National Bank of Ethiopia, EPAU and Ethiopian Investment Commission.

DFID is a trusted partner to the Government of Ethiopia and it receives regular requests for Technical Assistance and other policy-making support in the economic development space. The Macro Fund sits alongside other funds providing economic technical assistance, such as EIAF[5] and PEPE[6] – requests from GoE do not specify which fund they want support from. This makes this indicator difficult to measure. Examples of requests received recently include: Continued support to EIC (agreed); continued support to EPAU (agreed); various requests in the trade logistics area (some being delivered under this programme, others delivered under EIAF, others declined); research proposals from EDRI on 2 themes - climate change and labour markets (under consideration); feasibility studies for heavy industry (delivered under PEPE).
[5] Ethiopia Investment Advisory Facility
[6] Private Enterprise Programme for Ethiopia

Recommendations

This output includes three ‘catch-all’ indicators, but the information they cover would in some places more appropriately included in the other outputs and the outcome.
Remove indicator 4.1, amending other outputs to include an indicator on quality where relevant.

The annual number of requests is not a suitable measure of ‘demand’, as it takes no account of the size or importance of the request, and furthermore the GoE does not make requests specifically to the Macro Fund. Therefore, it would be better to change this to a qualitative assessment of whether GoE sees DFID as a trusted source of support and TA on macro and high level economic policy.

Output Title	Delivery of high quality expertise on trade logistics
Output number per LF		5	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Y (new output)	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestones	Progress
Use of DFID-funded TA in design of new World Bank programme on trade logistics	Bank project dealing with key constraints in trade logistics sector approved by board	$150 million World Bank Trade Logistics project has been approved by the board.
Delivery of high-quality support to Ethiopian Maritime Affairs Authority	Logistics Transformation Office established	Halted – the EMAA has cancelled its agreement with the delivery partner (UNDP) so this project will not proceed
Extent to which Ethiopian Government is able to take more informed decision on its policy on the Berbera corridor	Corridor diagnostic report delivered and findings presented to Joint Operating Committee (EMAA and BPA)	Summary report has been delivered.

Key Points

The DFID-funded technical assistance via the World Bank to assist in the design of a large trade logistics programme has substantially delivered the required outputs to a satisfactory quality. The TA delivered scoping missions and produced project preparation documents, such as a feasibility study for improvements to Modjo Dry Port, an ICT assessment of the Addis Ababa-Djibouti corridor, and a regulatory assessment of the Ethiopia-Djibouti transit arrangements. These were sufficient to gain approval by the Ethiopian Council of Ministers and the WB Board for a new WB lending programme which will fund improvements to the Dry Port, ICT systems and regulatory reform. Trade logistics are recognised by the GoE as a key bottleneck to export expansion, and several more priority projects will be on the agenda, such as a special logistics regime for industrial parks, and cool chain logistics for horticultural produce.

Although agreement was reached between the Ethiopian Maritime Affairs Authority (EMAA) and UNDP to provide support for the establishment of a Logistics Transformation Office, the working relationship between the two broke down and the project has been halted. This happened after DFID had disbursed funding to UNDP, but none of these funds have yet been spent. DFID staff are now working with UNDP to redesign the project; if this cannot be agreed the money will be returned to DFID.

The Berbera corridor diagnostic is being conducted by Trade Mark East Africa (TMEA). They have produced a summary report, but not yet presented their findings to the Joint Operating Committee. The evidence and recommendations they have gathered are already being used as inputs to broader trade logistics advice being provided to the Government by DFID. A sub-contractor has also produced two Political Economy reports on the implications of politics on trade in the region. DFID-Somalia confirm that the outputs so far are of a high standard. This corridor project remains promising, however there is a high level of political risk due to the need for consistent ministerial engagement, and high-level agreement between Ethiopia, Somaliland and DP World (the operator of the Berbera Port).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The programme has disbursed a total of £3.32 million in its three years of operation, roughly three-quarters of the total programme budget of £4.5 million. Of this disbursement, the key cost driver was the support provided to EPAU (35% of total programme disbursements) followed by the diagnostic work on Ethiopia’s trade logistics sector (17%) and diagnostic work on the Berbera trade corridor (also 17%). For EPAU the key cost driver is staff costs and for the NBE, EIC, and the trade logistics projects, the key cost driver is consultancy fees. This is in line with expectations of a project of this type (technical assistance), which typically allocates the majority of funding to consultancy/human resource. This is also in line with the expectations set out in the business case.

VfM performance compared to the original VfM proposition in the business case

Benchmarking of consultancy fees conducted in the previous AR indicate that, for technical assistance to the EIC and NBE, fees are comparable to averages for DFID-Ethiopia. Since then, Professor John Sutton has been providing his input to the EIC project pro bono, thereby making the project even more economical. There has been no other changes to fees for either project.

The Berbera trade corridor strand of the trade logistics project has performed well on economy, despite the added complication of two DFID country offices having to work collaboratively on cross-border affairs affecting two separate governments. The standardisation of procurement procedures and policies ensured that the processes were transparent and fair, resulting in timely and competitive procurement of sub-contractors through the TMEA framework agreement.

DFID Somalia and TMEA secretariat undertook a comparative analysis of the market rates, and used this to benchmark the Political Economy Analysis & diagnostic study delivery costing. £206,740 savings were realised through negotiation on fees and expenses, reducing the overall price from the initial offer and also reducing the number of days for some of the consultants (Trade Specialist). The work has mainly used national or regional consultants, with a focus on engaging and building local capacity. International expertise was only bought in where absolutely necessary.

Assessment of whether the programme continues to represent value for money

Overall the programme continues to be relevant to emerging macroeconomic needs of the GoE and its theory of change remains valid. Information presented in this review suggests that the programme represents value for money. Last year’s review noted that the transaction costs in terms of DFID staff time were substantial, however this year there has been a shift towards approving fewer, larger projects, thereby reducing the admin cost per project and improving the VFM.

Quality of financial management

Date of last narrative financial report	Financial report from EPAU received in May 2016, covering the period June 2015 – April 2016 (Quest: 577292); / IGC financial reporting has been in the form of invoices for payments. / We expect the financial report from IFC in June 2017 / The IMF financial report due in April 2017. This should be followed up as a priority.
Date of last audited annual statement	Audit of International Growth Centre: Received April 2016 / Audit of EPAU: Received August 2016

Disbursements under the fund almost tripled in this review period compared to last year – annual spend increased from £802,000 in 2015 to £2.03 million in 2016 as more components started. In total the programme has disbursed a total of £3.32 million to date.

Macro fund financial report from June 2016 to May 2017

Component	Total commitment (£)	Project spend June 2016 – May 2017 (review period) (£)	Overall Project spend to date (£)	Remaining Committed Balance (£)
Live Projects
Research and Analysis undertaken by Economic and Policy Analysis Unit. Ongoing	1,150,000	700,000	1,150,000	0
Support to Develop Ethiopian Investment Commission Ongoing	555,583	101,686.13	419,783.02	135,800
Technical Assistance to the National Bank of Ethiopia Ongoing	424,882		424,882	0
Capacity Strengthening for the Implementation of National Logistics Strategy Ongoing	262,000	112,500	112,500	149,500
Top of Form / Diagnostic Work on Ethiopia’s Trade Logistics Sector OngoingBottom of Form	560,000	560,000	560,000	0
Top of Form / Berbera corridor diagnostic work through DFID Somalia managed contract OngoingBottom of Form	550,000	550,000	550,000	0
Completed Projects
Macroeconomic Reporting for National Planning Commission Complete	21,295.15	10,622.00	21,295.15	0
Support to Government of Ethiopia’s Public Private Partnership Framework Complete	8,692.00		8,692.00	0
Natural Resource Management Training Complete	16,000		16,000	0
Comprehensive Evaluation of the Tax System of the Government of Ethiopia Complete	56,578		56,578	0
Total completed and live projects	3,605,030	2,034,808	3,319,730	285,300
Approved and Uncommitted Budget
Approved Budget	4,500,000
Uncommitted Budget	894,970

The total approved budget for the Macro Fund is £4.5 million. To date approximately £3.6 million has been committed and £3.32 million spent. There is approximately £894,000 uncommitted balance. Hence, the program team need to make a decision on the pipeline projects including the unutilized UNDP project fund.

EPAU delivered its financial report covering the period May 2016 – April 2017. The financial reporting is in line with agreed reporting format as per the MoU. The report highlighted that EPAU has utilized 99% of the disbursements for the period and we have not observed any anomalies in the report.

We are strictly monitoring fund utilization vis-à-vis planned outputs under each component and have not encountered any financial misuse for all work streams financed by the macro-fund. There was a theft of funds from one of the sub-contractors of the Berbera corridor work, due to an email scam. This was reported to DFID’s counter fraud unit. However DFID was not liable for this loss and therefore did not actually incur any losses.

We have received EPAU’s external audit report for the year ended 31st December 2015. The audit report is unqualified with no issues identified.

An audit report of the International Growth Centre (IGC) was received in April 2016. The result demonstrated that IGC has demonstrated an improvement in the financial management of the project compared to the previous year’s audit results. According to the audit report, the recommendations made in 2015 have been implemented. Although there were some minor recommendations and overall the audit provided assurance that DFID funds are managed in accordance with requirements.

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk:

The key risks identified in the business case and subsequent updates are:
  1. Ideologically or politically driven policymaking dominates over the use of evidence (medium probability, high impact)
  2. Economic deterioration (e.g. external shocks, slowdown in domestic demand) mean that improved macroeconomic policymaking does not translate to improved economic conditions (medium probability, medium impact)
  3. Policy decisions trigger unintended or unforeseen harmful social or environmental consequences (medium probability, medium impact)

In the past year, the outbreak of political unrest suggests a further risk should be added:
  1. Widespread protests or social unrest lead to deterioration in the business environment and deter foreign investors (low-medium probability, high impact)

In addition, the spread of projects and number of suppliers means the transaction cost on this programme are high relative to its value. This introduces a delivery risk as maintaining close oversight of all components at all times is costly. This is one reason why the programme will not be extended beyond its original timeframe .

Last year, the IMF expressed concern over the acceleration of public sector borrowing with associated risks of external debt distress and private sector crowding-out. It advised careful selection and implementation of public projects with judicious use of non-concessional external financing and greater use of public-private partnerships. This year’s Article IV consultation by the IMF has been postponed to the autumn, and there is a possibility that Ethiopia’s risk of external debt sustainability will be downgraded to ‘High’.

The current drought is expected to have a harmful impact on growth and poverty, but thanks to the large social safety net programme (which has reached 18.2m people this year[7]) the drought is not expected to cause a famine. However, the drought, debt and export challenges are not at a level to hinder the translation of improved macroeconomic policymaking into improved economic conditions in Ethiopia. The World Bank projects that Ethiopia’s GDP will grow 8.3% in 2017[8], faster than any other Low Income Country.
[7] http://www.worldbank.org/en/news/immersive-story/2017/06/07/breaking-the-cycle-of-crisis
[8] World Bank Group, “Global Economic Prospects: A Fragile Recovery” (June 2017), p.20 https://openknowledge.worldbank.org/bitstream/handle/10986/26800/9781464810244.pdf

Whilst these developments are not judged sufficient to change the overall risk ratings or the approaches to managing and mitigating risk, DFID-E should continue to monitor and discuss with Government the debt burden and export performance in its macroeconomic discussion forum.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The Macro Fund is delivering in line with planned timeframes:
The IGC accountable grant for support to the EIC was extended and payment was disbursed. This current phase includes significant plans for handover to EIC teams to enable the external support to be wound down in line with current time frames.

A request for extension of funding to the EPAU was received in October 2016 and a new grant was made in April 2017. As this funding supports ongoing activities of a government institution it is likely that external funding will be necessary to support the unit beyond the life of this project.

The IMF long term Advisor to the NBE was in place in September 2016. Production of outputs is broadly on track but due to the issues with the relationship between the NBE and the IMF DFID will assess whether the work should be stopped early.

The IFC has delivered its diagnostic report on Ethiopian trade logistics and this fed into the design of a large ($150 million) World Bank project, which has been approved.

Trade Mark East Africa have delivered most outputs for the Berbera Corridor diagnostic, although they have not yet presented findings to the joint project board. The work will be completed by Autumn 2017.
However:
UNDP support to the EMAA has been cancelled; the project is delayed indefinitely while options are explored to either redesign or recover DFID funding.

Performance of Partnerships
Due to the nature of the macrofund a large number of implementing partners are involved. Of the live projects in this review period, performance has been mixed.
- The IGC has been performing well. It has a good relationship with counterparts in the EIC and senior policy makers on the Ethiopian Investment Board.
- EPAU, TMEA and IFC/World Bank have all been performing in line with expectations.
- Although the technical outputs being produced by the IMF have been in line with expectations, the relationship with the NBE is a serious concern. IMF headquarters could have played a more active role in managing this.
- The lack of activity under the UNDP component has been disappointing. However, UNDP are now actively working with both DFID and the Government of Ethiopia to resolve this.

Asset monitoring and control

EPAU shares an updated asset register on DFID’s assets status. Following that, DFID conducted a spot check in April 2017. EPAU has demonstrated excellent asset management over the review period and they have taken necessary action on minor recommendations.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

There is no specific conditionality attached to this programme. Commitment to the Partnership Principles does not play a specific role in the management or monitoring of this programme, therefore a programme level Partnerships Principles Assessment (PPA) has not been undertaken. Our assessment is that this assessment remains valid and there are no plans to undertake a PPA in the next year.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There has been no significant change in the evidence base since the approval of the business case and therefore the theory of change remains valid. There is no evaluation plan in the current period.

Monitoring progress throughout the review period

Each component has its own monitoring and reporting requirements. Due to the nature of the work these tend to be in the form of reports. DFID-E regularly discusses performance (technical and financial) for each component with beneficiary institutions as well as with consultants delivering the work.

Annual Review Process
This annual review was conducted by an economist from DFID’s International Financial Institutions Department, based in London. It is based on document review and a week of work in Ethiopia interviewing stakeholders and DFID staff.