Business Case
Summary Sheet
Overall programme risk rating:	High
Title: Yemen’s Multisector Humanitarian Response Programme (MHRP)
Programme Summary: To improve food security and nutrition outcomes for the most vulnerable in Yemen. DFID is to provide cash and voucher assistance for food security and a multisectoral approach to the treatment and prevention of acute malnutrition through three sectors: Nutrition, WASH and Health.
Programme Value: £90 million		Country/ Region: Yemen
Programme Code:	Start Date: 1 April 2017	End Date: 31 March 2020
Overall programme risk rating:	Major
Quest Number:	5787149

Intervention Summary

Narrative summary of why UK support is needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver (1/2 page max)
This Business Case is for a total contribution of up to £90 million between 2017 and 2020. This will fund International along with National Non-Governmental Organisations (INGOs and NNGOs) operating in governorates across Yemen where the needs are greatest. The programme will respond to urgent humanitarian food insecurity and acute malnutrition. This NGO programme will complement the existing response implemented by UN and other agencies.
The activities undertaken will work to address two critical areas of need in Yemen:
1. Improving the food security for the most vulnerable, through conditional and unconditional cash and voucher assistance.
2. Treat and address the underlying causes of Acute Malnutrition through an integrated multi-sectoral approach covering: Nutrition; Water, Sanitation and Hygiene (WaSH); and Health activities.
This multi-sectoral approach allows for greater, more comprehensive results and benefits to beneficiaries, and adds a comparative advantage to working through NGOs in comparison with that of single/duel sector UN agencies.
Yemen is one of the worst humanitarian crises in the world. On 2 July, 2015 the United Nations declared a “Level 3” humanitarian emergency in Yemen[1]. Humanitarian needs continue to rise with more than 18.8 million people in need of humanitarian assistance – including 10.3 million who require immediate assistance to save or sustain their lives. More than 7 million people do not know when they will eat again. Millions risk starvation without urgent assistance. More than 8 million face acute shortages of clean water and sanitation. Over half of health facilities are not functioning. Nearly 3.3 million children and pregnant or lactating women are acutely malnourished, including 462,000 children under 5 suffering from severe acute malnutrition. This represents a 57 per cent increase since late 2015 and threatens the lives and life-long prospects of those affected. Without immediate treatment, severely acutely malnourished children are ten times more likely to die than their healthy peers and moderately acutely malnourished children are three times more likely to die.
[1] “Level 3” emergencies are defined as, “major sudden onset humanitarian crises triggered by natural disasters or conflict which require system-wide mobilization” (IASC WG paper March 2012). Five criteria are used by the IASC Principals to determine whether a level 3 response is required, namely; scale, urgency, complexity, combined national and international capacity to respond and reputational risk.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
This programme is directly linked to the UK Aid Strategy and the Single Departmental Plan which commits the UK to strengthening resilience and responses to humanitarian emergencies (Objective 2) and providing services that meet basic needs (Objective 4). In particular, this programme will address Objective 2 through a portfolio of health, water, sanitation and food security/cash transfer programmes focused on immediate, life-saving interventions, which complement other donors’ contributions. The programme will support our commitment in the Strategic Defence and Security Review to spend at least 50% of DFID’s budget in fragile states. It will comply with the International Development Act (Gender Equality) 2014; the programme will contribute to poverty reduction and the protection of the most vulnerable and will ensure the different needs of girls, women, boys and men are considered. NGO’s will confirm compliance with all relevant anti-terrorism legislation.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme will contribute to DFID’s overall Single Departmental Plan (SDP) results in the three areas of Nutrition, Sustainable Water (though not all interventions are sustainable) and Humanitarian cash transfers.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
DFID follows the UN’s lead in assessing needs and setting priorities. Funding decisions for this programme were informed primarily by the annual UN Yemen Humanitarian Response Plan (YHRP) and will continue to be guided by the YHRP over the next three years. Notwithstanding, this programme assumes that priority sectors of intervention will remain broadly unchanged in the next three years from the current 2017 YHRP. Flexibility through scenarios is built into programme to adapt to the emerging needs. Should the conflict improve the exit strategy would be via a transition to sustainable livelihoods and resilience interventions.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Cross-HMG funds are not appropriate for a humanitarian programme of this type.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
DFID Yemen’s portfolio aligns its support to the UN Humanitarian Response Plan. We support UNICEF and WFP to deliver nutrition and food programmes respectively across Yemen. The NGO response complements these UN programmes by focussing on quality delivery of humanitarian assistance in hard to reach areas where we know the UN have less access. The multi-sectoral approach allows for INGOs to have a more comprehensive targeted response than that of a single/dual UN agency. This is organised through the Inter-agency standing committee (IASC), which allows NGO partners to identify areas with highest levels of need and provide a gap analysis to target coverage. Specialised NGOs will direct their assistance to areas where the needs are most acute, where access is limited and where UN agencies’ capacity to deliver quality programmes is limited.
The UK also funds the Yemen Humanitarian Pooled Fund. This provides rapid grants for a maximum of one year to NGOs and multilaterals so that they can respond quickly to urgent needs. The direct support to NGOs through this Multisector Humanitarian Response Programme allows for longer term planning and support. It also promotes the build-up of local acceptance, local capacity and more cost-effective and longer term solutions.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
This business case takes into account that humanitarian programming in complex emergencies[2] needs to be flexible and readily adaptable to changing circumstances. Yemen remains a complex environment, buffeted by a severe conflict built on chronic food insecurity and vulnerability to natural disasters. Programming has been designed around three conflict scenarios: 1) worsens; 2) continues; and 3) improves (page 25). We have built in flexibility to adapt and/or scale up funding and activities should a scenario change related to the security situation, humanitarian need or partner’s ability to operate. We will monitor throughout the life of the programme so that activities continue to be targeted at districts and communities most in need. The programme remains flexible to respond to emergency humanitarian disasters, (eg. Cholera, flash floods, etc) so that even if new priorities emerge the outcomes of this programme will be achieved.
[2] A complex emergency is a major humanitarian crisis that is often the result of a combination of political instability, conflict and violence, social inequities and underlying poverty.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
This programme is within DFID Yemen’s risk appetite. Operating in Yemen and delivering this programme presents a major risk. Given the high return of providing life-saving humanitarian and development assistance, DFID Yemen has a high risk appetite for changes in our operating environment which we cannot control but which may affect the delivery of our programmes. However, we have a low risk tolerance for fiduciary risks and ensure that partners are aware of the requirement to report fraud or corruption immediately. We will also work with programme partners to ensure the programme minimises the risk of doing harm. We will monitor risk and compliance (including the gender equality act (2014), anti-terrorism legislation etc.) regularly, including through quarterly meetings with partners. Enhanced due diligences have been conducted with Partners, which also include assessing assurance mechanisms on downstream partners.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
Partners will be requested to use UK branding on written materials, vehicles and supplies, with exemptions granted if this is deemed an additional security threat to operating in country. Partners will provide DFID with regular communications stories on their interventions.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
As emergency humanitarian assistance this programme has not been reviewed by the Quality Assurance Unit. However, this programme has been quality assured by the Humanitarian Advisor, as well as specialists in Social Development, Conflict, Results, Finance and an Economist. DFID Yemen partners have successfully implemented a predecessor programme where they demonstrated the ability to deliver and adapt to the conflict. All partners are undergoing enhanced due diligence assessments to assess capability. Access constraints in various parts of the country will remain a risk to delivery; this is within DFID Yemen’s risk appetite.
Does the SRO and team have the capability and resources to deliver this programme?
The SRO for this programme is the Head, Yemen Humanitarian Programmes. The Humanitarian Programme Manager will be responsible for day to day operations alongside the lead Humanitarian Advisor and Programme Officer. They will scrutinise delivery and risks through reporting from partners and monitoring the project’s delivery plan. In addition the core programme team will draw on the support of cross-cutting advisers throughout the programme (especially around Annual Reviews and the PCR) to ensure the programme is well managed and achieving its intended results.

Strategic Case

Context and need for a DFID intervention
Overview
Yemen has a long history of conflict, instability and pervasive poverty. Following repeated cycles of conflict and political crises over recent decades, both poverty and inequality increased. Yemen is the poorest and the most water-scarce country in the Arab World. The country faces a range of deep-seated development challenges including state fragmentation, rapid population growth, deep-rooted gender inequality, poor provision of basic services, and a poorly managed and weak economy that is dependent on declining oil reserves. There is endemic corruption and high youth unemployment. As a result, even before the most recent conflict, which began in March 2015, the UN assessed that 16 million Yemenis were in need of some form of humanitarian assistance. Over 10 million of those did not have enough food to eat.
The situation in Yemen has worsened considerably and progressively since the onset of the latest conflict. The longer it continues, the more complicated the political and military picture is becoming. Fighting forces are fragmented, regional dynamics highly charged and despite continued messaging to all parties to the conflict that a military solution will not end the war; the high intensity of active combat is being maintained. The UN-led Peace Process continues to face blockages: the last round of talks ended in August 2016 without success, a number of cessations of hostilities have failed to provide tangible improvements, and efforts by the UN Special Envoy to agree the Communique (the updated Roadmap) have faced significant hurdles. Recent acts by both of the main parties have undermined this process, including the Houthi/Saleh announcement of their new Government of Salvation on 28 November 2016, the Houthis’ latest refusal to engage with the UN Special Envoy’s mission to Sana’a in May 2017, and an increase of military activity initiated by Government of Yemen forces.  Airstrikes across the country have continued to cause devastation, including to critical infrastructure, and to kill and maim civilians.
The economic situation in Yemen is also having a negative effect on the humanitarian situation. According to the International Monetary Fund (IMF) Yemen’s economy contracted more than any other in 2015.[3] Yemen is 90% reliant on food imports paid for by oil and gas export revenues. Since the onset of the conflict these exports have been halted and development funding into Yemen has collapsed, resulting in a rapid decline in the stock of foreign reserves Yemen needs to cover key imports and protect the currency. Such uncertainty is feeding substantial fluctuations in price and availability of food[4] and black market activity.  According to the International Labour Organisation, female employment declined by 63.6% (27,000) in Sana’a city alone between 2014 and 2015; the labour force participation rate in 2015 (36%) suggested that only a minority of workers are economically active (men and women).[5] This is low even when compared with the low average across the Arab World.[6]
[3] IMF World Economic Outlook, October 2016
[4] Market prices are regularly monitored by the World Food Programme: https://www.wfp.org/content/yemen-monthly-market-watch-2015
[5] Yemen damage and needs assesment: crisis impact on employment and labour market (ILO)
[6] The most recent ILO observation is 50.4%
Economic Insecurity
An estimated 8 million Yemenis have lost their livelihoods or are living in communities with minimal or no basic services, pushing many into dependence on humanitarian aid. Even when food is imported, Yemenis increasingly do not have the means to buy it. The economic status of 78% households in Yemen is currently worse than in the pre-crisis period. This is mainly due to the public budget deficit, which has led to a reduction in government expenditures, delayed or total unavailability of salaries for government employees since September 2016, the collapse of the social protection system, a liquidity crunch in the local currency, depreciation of the Yemeni Riyal against the US dollar and depletion of central bank reserves. The WFP Comprehensive Food Security Survey showed that in 2014, 25% of households in Yemen relied primarily on government salaries, of which 31% were food insecure.. Salaries for health facility staff, teachers and other public sector workers are paid erratically, often leaving 1.25 million state employees and their 6.9 million dependents – nearly 30 per cent of the population – without a regular income at a time of shortages and rising prices. This has had a direct impact on people’s ability to purchase food and access other life-saving services eg health. The economic meltdown has aggravated and affected food security, especially food availability and access[7].
[7] IPC revision, March 2017.
Priority humanitarian needs
Chronic political instability, compounded by chronic economic crises over the last half decade, has compromised individual and household coping capacities in Yemen. The cost and availability of food on local markets means that staple items are often inaccessible.[8] Social protection payments to the poorest 1.5 million households (unconditional cash transfers through the Yemen Social Welfare Fund) have not been made since January 2015. Healthcare services are only minimally functioning and utilities such as electricity and water no longer function in many governorates. As a result 69% of Yemenis – 18.8 million people - require some form of humanitarian assistance, making it one of the world’s most severe crises.
[8] According to Food Security Technical Secretariat (FSTS) of MoPIC and the FAO - Food Security Information Systems (FSIS) programme.
The UN and humanitarian partners on the ground have reported increasing needs over the last year. Nearly 2 million are internally displaced, while a further 180,000 are displaced in neighbouring countries. It is estimated that 460,000 refugees, asylum-seekers and vulnerable migrants need humanitarian assistance, including 278,000 registered refugees.[9] Despite escalating need and the public profile funding to Yemen’s humanitarian crisis remains low, with the 2017 UN appeal only 31% funded[10]. A High level Pledging Conference for Yemen held in Geneva on 25 April 2017 raised about $1.1 billion. While the conference has been hailed as a success in that it raised the profile of Yemen as one of the worst global crises to the international community, the pledges only represent half of the requirement and included monies already received against the YHRP. Pledges are slow in being disbursed.
[10] HRP funding status as of 30 June 2017.
Food Insecurity
The food insecurity problem in Yemen is due to a lack of disposable income and insufficient household level crop production, as opposed to food availability[11]. This effectively means that food is available in all governorates (although with differing levels and pricing) but inaccessible to vulnerable and helpless households, who depend on market purchases as their main source of food, making them very susceptible to fluctuating food prices. Agricultural production, employing more than half of the population, has declined due to insecurity, high costs, and sporadic availability of agricultural commodities. In 2016, total cereal production was estimated at 480,000 metric tons, which was about 11 per cent below the 2015 harvest and 37 per cent below the five-year average. In March 2017, wheat prices were 32 per cent higher than pre-crisis levels.
[11] Food Security Cluster – Food Availability Brief as of March 2017.
In March 2017, a revision of the Integrated Phase Classification (IPC), a five-phase scale used to describe the severity of food emergencies, estimated that 17 million Yemeni people, equivalent to 62% of the total current estimated population, were food insecure and required humanitarian assistance to save lives and protect livelihoods. 6.8 million people were severely food insecure and urgently in need of assistance. Without concrete action from parties to the conflict and the international community, Yemen faces a very real possibility of famine[12]. The scale of need exceeds the humanitarian response capacity. While millions risk starvation without urgent assistance, it is imperative that large food assistance programmes improve their targeting and are complemented by NGO programmes reaching some of the hardest to reach geographical areas. In early 2017, joint effort by the Food Security and Nutrition clusters allowed the mapping of most urgent needs in terms of food insecurity and acute malnutrition down to the district level (all 333 districts that Yemen counts). On their side, partners of the Sana’a-based Humanitarian Access Working Group (HAWG) issued maps ranking the severity of access constraints down to the district level[13]. For this programme, analysis of these maps allowed DFID Yemen and partners to appreciate main coverage gaps, indicating districts where existing programmes have limited or no reach.
[12] OCHA Humanitarian Bulletin, Issue 23, May 9, 2017.
[13] Those maps were inserted into the Yemen Humanitarian Response Plan of January 2017 and into the Periodic Monitoring Report of June 2017.
Given the conflict in Yemen, there are possible events that could cause a severe deterioration in food consumption, malnutrition, and excess mortality for much larger populations, driving outcomes in line with Famine. These include: 1) a significant decline in commercial staple food imports below requirement levels, resulting from a failure in infrastructure including a military attack on Hodeidah port or other critical access routes, or 2) a major increase in conflict levels or change in conflict location that cuts off populations from trade and humanitarian assistance for an extended period of time[14].
[14] “Declining imports into Al Hudaydah port drive concerns about future food supplies” FEWSNET March 2017.
Nutrition
There has been a 57% increase in rates of acute malnutrition since November 2015, with 3.3 million pregnant or lactating women and children now acutely malnourished. By December 2016, the Nutrition cluster estimated that 462,000 children under 5 were Severely Acutely Malnourished (SAM).[15] Without immediate treatment, severely acutely malnourished children are ten times more likely to die than their healthy peers. Moderately acutely malnourished children are three times more likely to die. In non-fatal cases, malnutrition threatens to permanently stunt affected children’s cognitive and physical development, robbing them of their full potential.
[15] Global Acute Malnutrition (GAM) rates are as high as 31% in some locations – more than twice the 15% emergency threshold.
Water, Sanitation and Hygiene (WASH)
Already the world’s seventh most water-scarce country before the current crisis, 14.5 million Yemenis need support to meet their basic water, sanitation and hygiene needs. This includes 8.2 million people who are in acute need[16]. Across the country, rural and urban water networks have reduced services or have stopped functioning altogether. This is a result of fuel shortages, inability of consumers to pay bills, water company staff not being paid and conflict related damage. Urgent support is needed to keep urban water and sanitation systems from collapsing throughout the country. Lack of access to safe water, overflowing sewage and solid waste piling up in the streets combined with increased malnutrition are contributing to a public health crisis, leading to outbreaks of cholera, dengue and scabies in 2016 and 2017.
[16] Humanitarian Needs Overview, November 2016
In the six weeks between 27 April 2017 and 7 June 2017, the World Health Organisation reported 101,820 suspected cholera cases and 791 deaths in 19 of the 22 governorates in Yemen. Children under the age of 15 years account for 46% of the cases and those aged over 60 years represent 33% of fatalities. An already weakened health system, alongside the collapse of WASH services, and lack of waste management has all exacerbated the severity of this outbreak.
Health
More than 14.8 million people do not have access to basic healthcare. The World Health Organisation reports that the current conflict has led to a depletion of health services, with more than 54% (1,900 out of 3,507) of health facilities in 16 governorates currently not functioning or only partially functioning.[17] Physical damage was endured in 274 health facilities (69 totally and 205 partially). General services and trauma management services are only available in one third of the health facilities. In September 2016, the Yemen’s Ministry of Health announced that it had run out of basic operational funds for the primary health-care system.[18] With the Ministry of Health’s capacity dwindling, basic health services have collapsed.
[17] WHO Health Resources Availability Mapping System (HeRAMS)
[18] World Health Organisation – 28 September 2016: http://www.emro.who.int/yem/yemen-news/health-services-decline-as-conflict-in-yemen-continues.html
The continuing hostilities have resulted in a growing num­ber of wounded and sick people. Prior to the escalation of the crisis hospitals struggled with a lack of funding, personnel, facili­ties and medical supplies. They are now unable to handle the influx of patients during emergencies. Health workers have been forced to relocate due to the violence, leaving 49 (out of 333) districts without a single qualified doctor. Many of those who remain have not been paid consistently in around eight months[19]. People with disabilities, including those wounded in the conflict, are unable to access physical rehabilitation services, while centres receive minimal support for rehabilitation as local providers prior­itise other health concerns. Moreover since August 2016 Sana’a airport has been closed for commercial flights, denying civilians in need of medical attention outside of Yemen the ability to leave. This has put further burden on the health system in Yemen for chronic diseases.
[19] OCHA Yemen Humanitarian Bulletin May 9, 2017.
Humanitarian Access
Access into and within Yemen is restricted, with humanitarian agencies facing constraints in reaching areas of greatest humanitarian need. Impediments to humanitarian access reported by humanitarian partners have generally fallen into three broad categories; bureaucratic impediments, interference in humanitarian operations and security constraints as a result of armed conflict. Roughly 69% of the 333 districts in the country are either fully accessible or have relatively low access constraints. Of the 31% remaining, access to 43 districts is highly constrained. The Houthi-Saleh controlled de-facto authorities at the national, governorate and local levels have a limited understanding of humanitarian principles. They impose ad hoc restrictions on the movement and activities of humanitarian organisations, and seek to influence or interfere in operations, for example by seeking to influence needs assessments and the targeting of beneficiaries, refusing entry of humanitarian supplies and demanding access to beneficiary lists. In areas such as Taiz, approvals to allow humanitarian access is ad-hoc, further restricted by intensified fighting. The security situation is volatile. Health-care facilities, such as those supported by Médecins Sans Frontières, and offices of hu­manitarian organisations have suffered direct attacks.
Restriction on humanitarian data collection and information sharing have also been intermittently introduced and rescinded. These restrictions are at times resolved through dialogue, but the time lost represents an unacceptable burden for people who desperately need assistance.

Rationale for DFID Intervention
DFID Yemen delivers against three Strategic Objectives aligned with the UK Aid Strategy:
1. Strengthening global peace, security and governance through reducing conflict and supporting a return to political negotiations, thus helping to build a more stable Yemen;
2. Strengthening resilience and response to crises by responding to urgent humanitarian and protection needs, supporting an effective international humanitarian response, and building resilience where possible;
3. Tackling extreme poverty and helping the world’s most vulnerable through protecting key institutions to help lay the foundation for post-conflict recovery.
Funding this programme will deliver primarily against the second DFID Yemen Strategic Objective. Given the scale and severity of the crisis, whilst an inter-agency response is underway in support of the UN appeal for Yemen, there is a need to scale up interventions to meet rising needs. Whilst the UK has l
The UK’s response will make a clear and unequivocal statement that the UK recognises the severity of people’s humanitarian and protection needs in Yemen and a humanitarian crisis never seen at this scale. The UN appeal only 31% funded, our support to this programme would demonstrate UK leadership and help leverage urgent funding from other donors.
Impact and outcome expected
The expected Impact of the programme is “vulnerabilities of people affected by the conflict in Yemen are identified and reduced, prioritising the most vulnerable”.
DFID aims to meet increased humanitarian needs in Yemen and proposes a flexible approach to respond to urgent needs whilst laying the ground for resilience and recovery where possible. The overall aim of DFID humanitarian interventions will be to reduce vulnerabilities of people affected by conflict and other crises (including natural disasters) in Yemen. The programme will contribute to reducing food insecurity or prevent it worsening in the targeted districts[20] in which it operates. The measures at impact level are IPC classification and Coping Strategy Index. This contributes to the overarching Theory of Change for the Yemen Humanitarian programme (page 13).
[20] Districts targeted are specified in the table included under the Appraisal Case.
The expected outcome of the programme is “critical humanitarian need is alleviated amongst conflict-affected people, ensuring more people are food secure and a reduction in acute malnutrition”. This programme will increase beneficiaries’ levels of food consumption and will improve beneficiaries’ nutrition scores.

Gender and Vulnerability
Gender Equality
In developing this business case, we have taken into account gender-related differences in the needs of those affected by the emergency situation and will work with partners to ensure appropriate responses, in compliance with the International Development (Gender Equality) Act 2014. Interventions will take into account the needs and barriers to assistance activities specifically faced by women. All partners will collect and analyse data disaggregated according to age and gender in order to provide quality analysis and evidence to inform targeted interventions.
Protection mainstreaming
The conflict has had a devastating impact on civilians, who continue to suffer the consequences of pro­tracted violence. Allegations of human rights and International Humanitarian Law (IHL) abuses are wide­spread. Civilians face tremendous threats to their well-being, and the most vulnerable struggle to survive. About 11.3 million people need assistance to protect their safety, dignity or basic rights. There are nearly 2 million internally displaced people (IDPs). About 19 per cent are living in public buildings, collective centres, or in dispersed spontaneous settlements[21]. Services at these locations are often limited, and residents face significant protection risks, including exploitation, harassment and gender-based violence. Partners funded under this programme will be asked to demonstrate how the needs of vulnerable groups (disabilities, Migrants, IDPs, Children..) and gender are considered and incorporated within their programmes. All assistance will be planned and implemented following these basic principles designed to protect the most vulnerable, which include; promote the safety, dignity and rights of affected people; avoid doing harm; and ensure equal access to assistance.
[21] Yemen Humanitarian Need Overview, November 2016
Conflict Sensitivity and Terrorism financing
We will work with partners to ensure steps are taken to address conflict sensitivity as detailed in the appraisal case. It is the policy of DFID to ensure that no UK taxpayer funds are used to support individuals or entities associated with terrorism. DFID expects Partners and all Downstream Partners to make themselves aware of, and partners to sign compliance with, the relevant counter terrorist financing legislation. Due diligence and delivery chain mapping is undertaken on all partners to reduce risk and provide further assurance over the use of UK funds.

Appraisal Case

Assessment of feasible options
This business case assesses three options for delivering a comprehensive response to food insecurity and malnutrition over the next three years. The options considered are: 1) do nothing more; 2) increase our existing support through the Yemen Humanitarian Pooled Fund, WFP, and UNICEF; and 3) support Non-Governmental Organisations. We have used a multi-criteria analysis to consider the relative benefits of the 3 options. Alongside cost, the four key criteria are scored using a scale of 0 (low) to 5 (high). When comparing options, we assume the same geographical locations and vulnerable groups are targeted, resulting in similar activities. The criteria are:
- Relevance of operation – multisector response that will contain food insecurity and the risk of acute malnutrition in areas of high risk, limited or non-existent coverage and/or difficult access, covering food security, WASH, nutrition and health activities.
- Access to affected populations and coverage – severity of access constraints and response coverage analysis by relevant clusters.
- Administrative efficiency – responsiveness and cost of overheads
- Proven delivery capability – past performance, flexibility to adapt to new or unforeseen situations and evidence of reach.

Summary Scores:
	Option 1: / Do nothing (base case)	Option 2: / Provide up to £90m further funding through the UN pooled fund, WFP, and UNICEF	Option 3: / Support to Non-Governmental Organisations
COSTS
Direct Costs	0	Up to £90 million	Up to £90 million
Other Costs	0	Additional UN administrative tiers, lower DFID management costs.	Direct implementation with 1.5 FTE DFID Management Costs
BENEFITS
Relevance of operation	0	3	5
Access to affected populations	0	4	4
Administrative efficiency	0	3	4
Proven delivery capability	0	3	4
Total Score	0	13	17

Option 1: Counterfactual: Do nothing more:
No costs or benefits are associated with this base case. Existing support in the DFID Yemen portfolio would continue, but without further UK support no additional food security and nutrition interventions would be delivered. Whilst other donors are also supporting the YHRP, needs in Yemen by far outstrip funding available[22]. These results would not be delivered without UK funds. With no additional support some of those most vulnerable would be left in a perilous situation risking lives. This scenario is deemed at odds with the UK’s humanitarian priorities and risks the UK not doing enough in the face of the scale of need, disregarding the UK national interests. It would miss the opportunity for UK to demonstrate leadership in these areas, and encourage others to do so.
[22] The Humanitarian Response Plan remains only 31% funded as of 30 June 2017.
Option 2: Increase our current support to Yemen Humanitarian Pooled Fund (YHPF), WFP and UNICEF by up to £90m
Indirect Costs: Much of the programme consists of the provision of services that would usually be provided by the government. However, given that Government of Yemen provision of key services have all but collapsed and are further deteriorating, there are no costs associated by substituting Government of Yemen service provison.
Relevance: The YHPF aims to cover priority areas of the UN Humanitarian Response Plan which currently remain unaddressed. As such, we can expect the pooled fund to continue to focus on priority needs which include food assistance, WASH, nutrition and health activities in hard to reach areas, making best use of eligible international and national NGOs as well as UN agencies. The UK sits on the YHPF advisory board and the Fund has encouraged integrated multisector projects since 2016. However, grants are awarded for a maximum of 12 months reducing recipients’ budget certainty and ability to plan ahead. WFP and UNICEF have specific focusses on both food security, and malnutrition respectively, making the intervention relevant and already supported by the UK. They are single/duel sector focused UN agencies with the ability to deliver at scale. They lack the multisector response required to offer the combined benefits those in acute need want e.g. when food alone is no longer sufficient. We therefore score this option 3.
Access to affected populations and coverage: This combination of support has good access to those in need. WFP and UNICEF deliver at scale nationwide. NGOs have the advantage of reach of hard to access communities and the ability to target and flex their response. The YHPF supports the NGOs to provide this additional access and strives to enlarge its number of local partners eligible to direct funding and therefore increase its reach. Access therefore scored a 4.
Administrative efficiency: There are potential economies of scale for UN agencies (eg procurement). However, for the acute needs in hard to reach areas, as identified in the strategic case, the agencies would not directly implement all activities. Some of the selected NGO partners set out in Option 3 would be recipients of sub-grants with the UN under Option 2. This additional delivery chain tier increases the management and administrative costs of implementation. A management cost of 4% would be £3.6m, approximately ten times the cost of a full time equivalent in DFID for three years. Neither would we have the ability to bilaterally agree the administrative costs for the implementing NGO partners, and ensure value for money and a fair cost recovery. We score this 3.
Proven delivery capability: The YHPF; An Integrated Programme to Address Malnutrition (UNICEF); and Support to WFP to provide emergency food assistance have all demonstrated an ability to deliver scoring A, A, B respectively in their last review. After delays at the onset of the crisis the YHPF has improved allocation times of grants and increased its focus on NGOs. In spite of recent progress, YHPF is still limited in the number of partners that can implement funding allocations. Often, OCHA (managing the fund) is left with only one partner present in a given district and it is rarely the case that this partner can deliver a full multisector package of emergency food security, WASH, nutrition and health activities. The short term nature of grants makes it harder for grantees to build up local acceptance along with other benefits of longer term implementation. UNICEF has remained a strong partner delivering nutrition interventions country wide and one of DFID Yemen’s larger partners. WFP has proven ability to deliver at scale but is currently working with DFID on strengthening the assurance processes it can provide. Neither UNICEF or WFP offer the multisector response this intervention requires. This scores 3.
Option 3: Provide up to £90 million to Non-Governmental Organisations
Indirect Costs: As with option 2, given that Government of Yemen provision of key services have all but collapsed and are further deteriorating, there are no costs associated by substituting Government of Yemen service provison.
Relevance of intervention: An NGO programme would be designed to address the specific needs as identified in the strategic case. The NGOs offer flexibility and can tailor their response directly according to need. They have access to hard to reach communities to ensure those in acute need are targeted. They are able to offer a multisector integrated response, a necessity for the most critically in need, ensuring the activities maximise the impact for beneficiaries. An NGO programme would not be a stand-alone programme, but complementary to the DFID Yemen humanitarian portfolio. Not only would this programme spread our risk (in a high risk environment), it also broadens our ability to strengthen, and learn from the wider range of humanitarian agencies in Yemen. Their presence in country is critical to the continued delivery of services where historic government infrastructure has now failed (eg health and water authorities). The NGOs are coordinated through the IASC cluster system. NGO representation within the Humanitarian Country Team (HCT) ensures coordination and direct dialogue with UN agencies and the UN Humanitarian Coordinator. This way, UN agencies and NGOs can identify and address coverage gaps in a way that complement the reach and impact of each other’s programmes. For relevance this scores a 5.
Access to affected populations and coverage: The NGOs have better access to hard to reach districts where severity of need is often greatest. The intervention can be targeted and more responsive to the change in need. Programming can be flexibly designed to respond to highest needs in order to maximise impact. Sectors and districts targeted at the start of this three-year programme would be selected on the basis of a countrywide coverage and gap analysis conducted by the Food Security and the Nutrition clusters. There are several reasons why these districts are not covered by the programmes implemented by the UN agencies, including lack of access, local acceptance & security, lack of reliable local partners and/or the lack of local partners able to deliver quality through the treatment of acute malnutrition or cash transfer activities. As a result this scores 4.
Administrative Efficiency: The operating environment in Yemen results in unavoidably high management and operational costs, however direct support to the NGOs removes a further tier of administrative costs incurred when the UN engage the NGOs to deliver their programmes. A UN management cost of 4% would be £3.6m, over ten times the cost needed to manage an NGO programme with a full time equivalent in DFID for three years. The assurance of longer term funding reduces the NGO’s average set up costs over the life time of the intervention and the benefits of economies of scale afforded through medium term planning. .Administrative charges will be negotiated individually, keeping costs to a minimum whilst ensuring partners are able to deliver the quality programming needed. We score this 4.
Proven delivery capability: The NGOs operate in hard to reach areas and are quicker to adapt to the changing environment. The previous DFID Yemen NGO programme scored and A in it’s last Annual Review and is currently undergoing a Project Completion Review. Through this programme NGOs proved an ability to deliver throughout the conflict. The programme partners showed great strength in adapting activities at the onset of the conflict demonstrating flexibility moving from a resilience programme to emergency response. The programme had seen some delays in scaling up due to access constraints but overall delivered good results and we score it 4.
Conclusion of Appraisal case
Option 3 scores highest and is considered the most appropriate option. It offers a favoured set of benefits: targeted multisector interventions, flexibility to quickly adapt as demonstrated through past performance; and reach to hard to access areas, complementing the existing portfolio and spreading the risk. We reject Option 2, which addresses a broader spectrum of needs, but alone would not meet DFID Yemen’s humanitarian strategy and the needs set out in the strategic case.

Theory of Change for preferred option
The overall theory of change underpinning this and other humanitarian interventions for DFID’s humanitarian response to crisis in Yemen is shown below. The inputs, processes and outputs relevant to this particular programme are highlighted in red.

Outline of the intervention
This intervention will use up top £90m direct programme funding to NGOs. DFID Front Line Delivery will fund 1.5 full time equivalents (FTE) in staff time (70% Programme management and 30% Advisory) to support the project deliver
The outputs in the programme will be delivered by NGOs and all will contribute to the Theory of Change outcome of alleviating critical humanitarian need, and the overall impact sought. The intervention will work through two primary programme components: Food security; and an integrated prevention and treatment of acute malnutrition.
1. Food security: Aimed at improving vulnerable households’ economic security through either conditional (e.g. cash for work) or unconditional cash transfers.
2. Integrated prevention and treatment of acute malnutrition: Addressing the underlying causes of acute malnutrition and treating acutely malnourished people. This requires an integrated multisector approach that will look at the provision of food security, access to primary health care, access to safe water and sanitation services and access to acute malnutrition treatment with an effective system of referral for medical complications. Selected partners must demonstrate in their proposals their ability to cover all these sector activities in the selected districts, either through;
- UK direct funding of all activities under this programme
- UK funding for a sector complementing existing NGO activities in other sectors
- UK direct funding for a sector which will complement activities from other actors (other NGOs, UN, GCC implementing charities).
Food Security:
In year one this programme it is expected to deliver over £6.9 million of unconditional cash transfers; £600k cash for work; and £300k in food vouchers reaching 188,000 beneficiaries. A similar figure (approx. £8 million) is expected to be delivered in years 2 and 3, though the modality may change depending on the situation and need.
The programme aims at improving access to food for the most vulnerable in Yemen, through well targeted cash and voucher assistance. It will continue to promote cash transfers, either unconditional or in return of some work or training on topics directly related to acute malnutrition prevention. Interventions will focus on hard-to-reach and/or marginalised communities.
Humanitarian partners have been undertaking cash and market-based interventions in Yemen since before the current crisis. The Government of Yemen’s ‘Social Welfare Fund’ (SWF), provided regular unconditional cash transfers to 1.5 million chronic poor households across the country. SWF payments were suspended at the beginning of 2015. Humanitarian partners have increasingly used cash and vouchers as an emergency response tool. Activities are guided by a “Cash Transfers and Market Monitoring Working Group” (CMWG), which covers all cash transfer-related activities implemented by the various clusters. It recommends cash transfer amounts from regular review of market prices which will be applied by DFID partners.
There is very strong evidence that cash transfer food security programmes act as a viable alternative to in-kind assistance and will meet critical food needs, reduce suffering and save lives. Cash-based interventions support local business and markets and mitigate against the risk of creating false economies. Cash gives greater choice and control over how best to meet people’s own needs, and a greater sense of dignity. The programmes are often less costly to implement than in-kind interventions[23] and can allow rapid scale up. Cash-for-work interventions can provide a valuable additional source of income, and address basic needs including food.[24] A typical example is the rehabilitation of WASH community assets or a main access road to the local market. In doing so, partners will inject cash into vulnerable households while the community will feel ownership over the rehabilitation of common assets. It is more effective than food-for-work as it provides households with flexibility to meet changing needs.
[23] ODI Report of the High Level Panel on Humanitarian Cash Transfers. September 2015
[24] http://odihpn.org/magazine/comparing-the-efficiency-effectiveness-and-impact-of-food-and-cash-for-work-interventions-lessons-from-south-sudan/
Independent Monitoring of unconditional cash transfer activities implemented under the previous programme (Humanitarian Resilience Programme 2013-17) confirmed that this transfer modality was: feasible in hard to reach areas (Hodeidah, Lahj); was the preferred transfer modality among beneficiaries, their representatives and other stakeholders; was a safe, accountable and dignified way to address food insecurity; and did not affect local markets in terms of food availability and prices’ stability. A sample of 242 beneficiaries revealed that 96% of males and 95% of females spent their unconditional cash on food. The chart below shows beneficiary expenditure. These findings back the theory that well targeted cash transfers in the current context in Yemen will be spent on food and other essential goods and services. Studies in other contexts, for example famine in Somalia in 2011 (Longley et al. 2012) and following Typhoon Haiyan in the Philippines (Cabot-Venton et al.,2015) show similar patterns of expenditure.

The modality of transfer will also be determined by the evolving situation (Scenarios see page 25 ) Catastrophic conditions will mean immediate cash injection into the most vulnerable households. A transition towards recovery will call for more sustainable solutions such as cash for work activities. Provision of in-kind food assistance cannot be excluded in the case that local markets no longer can supply food in enough quantity. The programme is designed with enough flexibility to respond to these eventualities.
Nutrition, WASH and Health
Through this programme it is expected 80,000 children and pregnant/lactating women will be screened and treated for acute malnutrition in targeted areas. Over 560,000 people will receive WASH assistance. And an expected 260,000 people will be reached with malnutrition-targeted health services.
In early May 2017, the Nutrition cluster set three asks to the donors, including the need to fund integrated responses addressing the underlying causes of acute malnutrition[25] The programme will adopt a multi-sectoral approach to the treatment and prevention of acute malnutrition. It will work with partners whose programmes span the three sectors (Health, WASH and Nutrition) in addition to, or complementing existing food security programmes which target the same high risk beneficiary caseload. The approach will complement that supported through the UNICEF programme. Partners will actively participate in the relevant clusters to ensure coordination and complementarity of approach and avoid duplication.
[25] Donor briefing on Nutrition Cluster response - Amman, 1 May.
For example, the ACTED programme builds around existing Ministry of Public Health structures in three governorates. They increase the catchment areas of the central health structures through mobile medical teams covering remote villages and communities. Mobile medical teams were trained and equipped to screen, detect and refer severe acute malnutrition cases for treatment. The new programme will add support to families of severely acutely malnourished children as well as families with acutely malnourished pregnant or lactating women identified health and nutrition staff. ACTED assistance will provide support to vulnerable households’ economic security (cash transfers) and the provision of water, sanitation and hygiene assistance. Making sure the programme targets the most in need, in a fair and dignified way,
Such integrated approach was already promoted in the 2016 UN Yemen Humanitarian Response Plan but evidence has shown that it is not easy for large mandated UN agencies (WFP, UNICEF and WHO) to join forces and jointly address most urging needs. The purpose of this programme is therefore to provide an integrated response to those districts identified (as described above) as the most in need in terms of 1) needs identified in terms of food insecurity and acute malnutrition rates, 2) limited response coverage as identified by the FSAC and Nutrition clusters and 3/ difficult access as identified by the Humanitarian Access Working Group (OCHA / NRC).
The risk of famine-like conditions exists in Yemen with the possibility that some districts or sub-districts currently in IPC 4 (Integrated Food Security and Nutrition Phase Classification) slip into IPC5, meaning famine. The IPC index is based on three indicators: crude mortality rate; global acute malnutrition; and food consumption. Description of IPC5 / famine is: "even with any humanitarian assistance, at least one in five households in the given area has an extreme lack of food and other basic needs where starvation, death and destitution are evident” [26]
[26] IPC and Famine: Using the Appropriate Terminology and Scientific Thresholds
Lack of access to basic needs means that even with food assistance acutely malnourished people, face increased risk of death from lack of access to safe drinking water or access to primary health care and medication, particularly for children under the age of 5 and pregnant or lactating women. Evidence from past famines shows that as many, or more, people die from preventable diseases as they do hunger.
Children will be screened for Severe Acute Malnutrition (SAM) and where needed enrolled into outpatient therapeutic feeding programmes (OTPs) and referred to hospitals in cases of medical complications. Children will simultaneously be treated for common childhood illnesses such as diarrhoea and acute respiratory infections. Families with SAM children will be prioritised for food security / cash transfer assistance to support successful treatment and discharge from feeding programmes and help prevent relapse. Health and nutrition service provision will be combined with local WASH interventions based on an assessment of needs. Poor water and sanitation contributes to the spread of common illnesses, while malnutrition increases susceptibility to these and vice versa. These interlinkages provide strong justification for a multisector approach.
There is a strong evidence base to support delivering health services to improve health outcomes and life expectancy.[27] Support to water and sanitation systems in Yemen contributes to saving lives through preventing public health concerns. The recent cholera outbreak in Yemen was due to contaminated water sources. Protecting water sources, and taking preventative measures such as chlorination of water, are key activities in curbing the outbreak, therefore saving lives.
[27] Witter, S. Health financing in fragile and post-conflict states: What do we know and what are the gaps? Social Science in Medicine, Dec 2012. 75:2370-2377
Partner Selection
Partners, sectors and districts (see table overleaf) were selected at the start of this programme on the basis of a “response coverage and gap analysis” conducted by the Food Security and the Nutrition clusters, highlighting areas of highest vulnerabilities combined with poor or non-existent partner coverage due to access and security issues, lack of local implementing partners and/or lack of local implementing partners able to deliver specialised quality programming such as cash transfers or treatment of acute malnutrition.
Selection of partners and priority districts at the start of MHRP programme:

Gender and vulnerabilities
Interventions under this Multisector Humanitarian Response Programme will take account of gender-related differences. Partners will seek to collect sex- and age-disaggregated data wherever possible and use it to inform and adapt programming. As part of the UK Government’s Strategy to end Violence against Women and Girls (VAWG) we are committed to ensuring that UK humanitarian aid prevents and responds to violence against women and girls. Partners will ensure that their work to mainstream protection across all sectors contributes, where possible, to proactively improve protection outcomes for the most vulnerable communities.

Examples of gender sensitive programming include: ACTED will train female beneficiaries to provide literacy classes to peers in their communities as a cash for work activity. This will allow the inclusion of women (particularly older or disabled) in conditional cash transfer activities while supporting women in the community to gain critical literacy skills; CARE will organise separate capacity-building workshops for women involved in WASH committees and similar decision-making roles in order to identify needs and progress; and Save the Children will ensure female inputs are considered by developing channels of communication for women in the community, facilitated by female members of the project team.
Conflict Sensitivity and Sustainability
Our programming will ensure that our partners have the ability to: a) understand the Yemen context they operate in; b) understand the interaction between their intervention and that context; and c) act upon this understanding in order to minimise negative impact and maximise positive impact on the conflict. We will ensure conflict sensitivity is embedded at all stages of the programming cycle. It was integrated at call for proposal stage and DFID will ensure partners integrate conflict analysis into their work, mainstream conflict sensitivity into programme management, monitor and evaluate the programme’s impact on the conflict. Reporting on this will form part of the quarterly reporting requirements, to ensure its effective implementation.
Capacity Building
As part of the call for proposal guidelines, capacity building and the inclusion on National Non-Governmental Organisations (NNGO) in consortium were encouraged as a matter of better value for money and as part of our exit strategy should the situation evolve towards early recovery. As a result at least one of the successful proposals had an NNGO within the consortium. We will also work with the Food Security partners to scope out the possibility of building in an NNGO into a Food Security consortium at a suitable point into the programme.
Likely impact on climate change and environment
Environmental degradation including water depletion and pollution, biodiversity degradation, and soil erosion pose serious threats on the livelihoods of the poor in Yemen whose survival mainly depends on access to natural resources. Climate change is expected to exacerbate these threats through increased average temperatures, less predictable rainfall, and more frequent and severe natural climate hazards including localised flooding, drought, and in coastal areas, sea level rise.
The biggest environmental issue in Yemen is water scarcity. This is a particular concern given the already stressed agriculture industry (Yemen imports most of its food[28]), the widespread food insecurity, and scarcity of water. Yemen receives little rainfall and as a result depends mainly on groundwater produced from subterranean aquifers. The most optimistic estimates predict that the groundwater reserves of Yemen’s most critical aquifers will be exhausted by 2025-2030[29]. More than a quarter of the population currently faces acute water scarcity, using less than 15 litres of water per day per person. Knock-on effects of existing resource scarcity, degradation, and climatic changes include rising food and water prices, and therefore insecurity, malnutrition, risk of disease, and increased tensions, particularly between migrant groups and host communities over resources. Lack of strong governance of natural resources could fuel social unrest, and support for a black market and insurgency.
[28] Ecker, O., Breisinger, C., McCool, C., Diao, X., Funes, J., You, L. and Yu, B. (2010) Assessing food security in Yemen: An Innovative Integrated, Cross-Sector, and Multi-Level Approach. IFPRI Discussion Paper 982. Washington, DC: International Food Policy Research Institute.
[29] http://ynccf.net/pdf/Climate_change_and_development/Yemen_Climate_Change_Study_April_8_2010.pdf
Interventions proposed by this programme are unlikely to pose high risks to the environment. That said inevitably there will be some (minor) resource use implications regarding WaSH interventions. Any risks of social tensions regarding resource use, will be factored into conflict analysis and conflict sensitivity mainstreaming. Lastly it should be noted that the effects of climate change, if not mitigated or adapted to, may erode some of the gains proposed by this intervention, for example in the area of WASH and Health.
Value for Money (VfM) assessment for intervention
Economy:
- The NGOs will aim to reduce the costs of inputs where possible whilst retaining quality and a timely response. In this effect, local purchase and cash and voucher transfers will be encouraged, wherever appropriate, in order to reduce importing and transporting costs. Best practice procurement procedures are expected from all partners.
- Direct implementation reduces the delivery chain and associated UN overheads. Savings are anticipated to significantly offset the consortia coordination costs.
- Partners have worked to build the capacity of national staff and thus reduce / keep low the number of international staff in country, whilst maintaining the level of oversight and controls. This keeps operational costs lower and maintains greater continuity.
- In all governorates and almost all districts, partners have operations in that location. Therefore, there are reduced set up costs in any of the locations.
- Partners have experience with all activities undertaken under this programme. This means that each agency already has the necessary expertise and knowledge to implement the programme, reducing delays during hiring or procurement processes.
- As established implementing agencies, each partner has developed standard administrative costs that are evaluated regularly that ensures competitive and quality project implementation. Similarly, each agency has standard operating procedures for financial, logistic and administrative monitoring which allows for swift identification of bottlenecks or duplication of work.

Efficiency
- All the NGOs have an existing Yemen response in place. This allows for economies of scope delivering multiple projects from the same resources. Running costs such as some salaries, rents, agreements with suppliers for procurement of goods, services and equipment will be shared across separately funded projects. Where possible cost sharing on warehouses and transportation between NGOs is encouraged. We will continue to push for more joined up inter agency working during this programme.
- Three year certainty allows for greater planning including the sourcing of services and goods. Eg set up costs and recruiting for a new intervention can be high, but these costs will be offset over a greater period of time.
- The inclusion of national NGOs, brings the added value of long term sustainability and increased access to the targeted areas.
- Unconditional cash transfers present a strong value for money argument in that recipients spend the cash on the goods or services that they value most..
- The cost of outputs and the ratio between direct project delivery costs and administrative costs will be monitored by DFID and the partners and efforts will be made to make savings and allocate more funding to direct project delivery.
Effectiveness:
- Effectiveness of the programme will mainly be measured through the results framework (see management case) which includes a combination of quantitative and effectiveness focused indicators. Conflict and gender sensitive indicators; protection mainstreaming standards, and Value for Money indicators will integrated into the results framework and monitored throughout the lifespan of this programme.
- The previous programme scored well over its life span indicating the programme was effective. The PCR is currently underway and lessons learnt will be taken forward in the new programme.
Annual Reviews	August 2014	August 2015	August 2016	June 2017 [PCR Due]
Programme Score	B	A	A	Tbc
Risk Rating	Medium	High	High	Tbc

- Reliably monitoring performance is difficult due to DFID not having a presence in Yemen. DFID will monitor the NGOs’ work through quarterly reports and quarterly meetings. The programme will also be subject to review by DFID Yemen’s Independent Monitoring Programme. The previous programme was reviewed in March 2016[30]. Findings were broadly positive and showed that for both partners, there were only minor data quality issues for quantitative data accuracy, and moderate issues for adherence to targeting criteria. These were immediately corrected by the partners.
  [30] British Council: Ta’zeez Independent Monitoring Report, June 2016
- March 2016 Independent Monitoring also looked at recipients’ preference of the form of support (unconditional cash, food voucher or cash for work) and concluded that unconditional cash transfers was the appropriate targeting option for assistance.
Cost Effectiveness:
The NGO project proposals are scored against a set of criteria, including VfM. NGOs have provided DFID with their costs by component. Analysis can be done on trends of cost per beneficiaries for the different interventions. These will be used to compare costs year and year, between agencies, and against other programmes in our portfolio where data is available. VFM indicators and savings achieved will be monitored as part of the formal quarterly review of the programme as well as through regular financial reporting of spend against budget. The humanitarian advisor will scrutinise qualitative evidence provided in the reports. After year 1 of the programme, overall performance on VfM will be reviewed in detail, cost drivers assessed, and the action plan amended as necessary
Equity
All project proposals are assessed against their consideration of gender and vulnerable groups as well as protection mainstreaming. Specific details are covered in the management case and progress will be monitored during the lifetime of the programme.

Commercial Case

Why is the proposed funding mechanism/form of arrangement the right one for this intervention?
In line with Smart rules, DFID Yemen will sign Accountable Grants with the four lead NGOs using the new standard Accountable Grant Agreement template. The Accountable Grant Agreements will outline the expected value and timing of planned payments, the timeline for programme reporting and will include specific clauses on anti-terrorist financing and DFID’s zero tolerance for fraud and corruption.
What assurance has been obtained on capacity and capability of organisation to deliver the programme/intervention?
Selection of implementing partners for this option was organised through a competitive call for proposals opened to all international and national NGOs. The launch including a detailed presentation of the call for proposals was organised in Amman in November 2016, with NGO partners also able to join by video-conferencing from Sana’a and Aden. A scoring matrix was designed to evaluate strengths and weaknesses of the proposals received. This process enabled us to assess the best placed NGOs to deliver based on a series of criteria including, comparative advantage of each organisation, prioritisation of intervention based on both geographical and sectoral needs, proven access, and more. The process also ensured that partners integrated cross cutting thematic issues such as gender and conflict sensitivity, as well as value for money throughout the design of their proposals. The outcome of the process has brought five new implementing partners on board (Mercy Corps (in the CARE Consortium), Acted, ADRA, YFCA and Handicap International (all under the Acted Consortium). Each new and existing partner has demonstrated a comparative advantage to strengthen the humanitarian response. The process has also allowed us to refine our programme geographically – focussing on the most in need districts.
All the NGOs have an existing Yemen response in place, and proposals were selected based on proven experience and existing presence in the governorates selected. All provided their annual audited statements. Moreover three of the four selected lead partners (Care Consortium, Save the Children and Oxfam) have successfully delivered with DFID funds in the previous iteration of the programme, which scored an A in its last Annual Review. Partners demonstrated the capacity and capability to deliver in the difficult operating environment, as corroborated by DFID Yemen’s independent monitoring programme in 2016. ACTED will be a new DFID partner which has demonstrated strong delivery in Yemen through a comprehensive proposal. ACTED is known for operating in challenging complex and protracted[31] emergencies.
[31] Protracted crises refer to situations in which a significant portion of a population is facing a heightened risk of death, disease, and breakdown of their livelihoods. While each protracted crises is distinct occurrence, there are several common characteristics which are often present: duration or longevity, conflict, weak governance or public administration, unsustainable livelihood systems and poor food security outcomes.
In February 2017, the DFID Yemen team tendered for a supplier to undertake enhanced due diligence assessments of the four lead NGO partners. This has included fieldwork in the county offices in Yemen. This will provide DFID with additional assurances on governance, fraud, risk and delivery, especially critical when DFID is unable to operate in country. The SRO for this programme will review in detail the findings of the due diligence assessments, agree whether to proceed with payments, and agree a plan of action with partners at the outset, to make any necessary improvements.

Management and delivery of outputs
DFID will hold the NGOs to account for the management and delivery of outcomes through quarterly reviews of the logframe and expenditure reports and by conducting detailed annual and end of programme reviews. The regular meetings will ensure partners manage and DFID are alerted to delivery risks such as access constraints early on and can work together on alternative arrangements. Future payments will only be made after satisfactory reporting of the previous quarter, demonstration of delivery against outputs and evidence of future plans and accurate forecasting.
Delivery chain mapping has been undertaken as part of the due diligence process to understand all stakeholders involved from DFID to the beneficiary. Most services will be delivered directly by partners or consortia members. For cash transfers, partners will use reputable and regulated private banking institutions such as Al –Kurami Microfinance Bank and Al Amal Bank to transfer cash to beneficiaries on monthly basis. Where access to central cash delivery points is a constraint for some of the beneficiaries, partners will negotiate temporary cash distribution points to be located closer to the beneficiaries (e.g. Save the Children cash transfer programme in Lahj 2016). All partners have strong working relationships with these institutions. Partners are active members of the Cash and Market monitoring working group (CMWG) and will use the recommendations of this group in the implementation of their cash and voucher activities.
Downstream Partners
Rigorous Due Diligence assessments will be conducted on the lead consortia partners. These assessments will also provide assurance that appropriate levels of due diligence have been carried out by all lead agencies in the consortia on partners and downstream organisations. Further details of the delivery chain will also be scrutinised as part of the external due diligence process. Where additional assurances are needed DFID will conduct its own assessments and work closely with the lead agency on strengthening our assurances. Action plans will be put in place for any identified weaknesses.
Care consortium
Care will work as lead partner in consortium with: Action Against Hunger (ACF); Mercy Corps; and Norwegian Refugee Council (NRC). Care will be responsible for consolidated reporting and all financial engagement. It has significant experience in leading large-scale consortia in Yemen. CARE, ACF and NRC have a history of working together as a DFID funded Consortium. Mercy Corps is a new addition and has remained one of the largest and most active international NGOs present throughout the war, implementing multisector humanitarian programmes in 8 governorates.
The added value of bringing these organisations together as a consortium is depicted by the blend of programming experiences and logistic capacities and the complementarity of sector expertise. Each partner has highly appropriate technical expertise, extensive experience in multisector humanitarian programming and strong understanding and knowledge of the local context in Yemen. Conflict analysis, risk and vulnerability analysis, needs analysis and market assessments will be shared to enable a comprehensive situation understanding that informs response.
ACTED Consortium
ACTED will work as lead partner in consortium with Yemen Family Care Association (YFCA); ADRA; and Handicap International. ACTED will be responsible for consolidated reporting and all financial engagement. Aside from ADRA these are all new partners to the Yemen Humanitarian Portfolio. Each of the selected agencies brings a unique set of experience and operational capacities and resources, which add value to the overall intervention. Furthermore, the Consortium takes advantage of the technical and operational synergies been the three organisations, which maximises the impact and value for money of all agencies interventions while providing ideal opportunities for sharing information approaches and lessons learned. Handicap International will provide impartial consulting on protection and inclusion mainstreaming. Given the additional risks of working with a National NGO, a greater level of scrutiny will be applied to the due diligence on ACTED, and their management of downstream partners.
The Consortium Coordinator will act as the programme lead with responsibility for external representation and for oversight for the entire programme. From an operational perspective, Consortium staff - Monitoring and Evaluation (M&E) Manager, Finance Officer, Compliance Manager, Security Analyst, and Liaison Officer - will have responsibility for the coordination of their functions across the entire programme ensuring that information and approaches are coordinated between agencies. The Consortium will conduct ongoing structured conflict and stakeholder analysis throughout all stages of the programme cycle.
Food Security Platform
Save and Oxfam are delivering food security interventions through cash transfers. Whilst initially we have separate agreements with both parties we expect Save the Children and Oxfam to form a consortium, potentially including a National NGO, as part of our commitment to capacity building. Any new partner brought on to the consortium platform will undergo an assurance assessment to identify capacity to deliver and risks. Oxfam have agreed to lead the consortium, and the exact operating details of this consortium will be worked up within the first 6 months of this programme. In the meantime Oxfam and Save the Children will continue to implement their activities independently, but in close coordination with each other. The future food security platform will support and work closely with the Cash Transfer and Market Monitoring working group (CMWG).
Procurement capability:
Care
CARE, as Consortium lead, will take the responsibility of managing funds guided by its documented policies related to Financial Management, Procurement, Fraud and Security. CARE has an established due diligence process in place for engaging with international non-governmental organisations which includes assurance that their procurement procedures are in line with that of Care’s. Recognising that procurements can face logistical barriers and/or can have ripple effects in the local economy (both positive and negative), CARE and its partner undertake constant analysis of prices in local markets and connectivity as part of its value for money assessment for key inputs.
ACTED
Each partner is an established agency with standard procurement procedures that ensure fair, high quality and cost efficient resources are used. INGO global procurement procedures and policies prioritise value for money, transparency, non-discrimination and business ethics. YFCA also has thorough procurement procedures that meet the high standards of the Consortium partners. For example, for amounts higher than £8,000, procurement must follow a bidding process, which not only ensures transparency, but also ensure good value for money and competition in the marketplace. Where possible and to optimise the purchase of supplies, partners prioritise procurement from local suppliers as this reduces transportation costs, but also supports local markets.
Food Security Platform
Save the Children abides by robust procurement policies, procedures and thresholds – including anti-fraud and anti-corruption procedures – designed to ensure materials are procured at a competitive price whilst supporting local markets. Some activities such as unconditional cash transfers distribution or commodity vouchers may require a national tender process, in which case a competitive bid analysis will be conducted with a multi-disciplinary team to identify the best value contractor while ensuring high quality. All procurement is undertaken locally, as this is the most economical option to source the required inputs, and based on standard procurement guidelines: competitive quotes are collected, all relevant quality standard procedures are appropriately followed at Sana’a and field office levels.
Oxfam has well defined and rigorous procurement processes that were recently reviewed by DFID as part of its Commercial Expertise Review for 2015/2016. Oxfam’s processes not only minimise costs across operations but also ensure that country programmes including Yemen are able to procure quality supplies at the right price in a timely fashion. During the project start up period the program and business support staff will develop a comprehensive procurement plan for the first year of the project. Oxfam will also purchase required items from the local market in order to minimize different cost including transportation unless the items are not available in the local markets.
DFID relationship:
DFID have built up strong working relationships with existing partners and will establish them with the new partners. These relationships have been used to drive VFM by working with partners to reduce management costs and ensure programming is high quality and focussed in the areas of greatest need. The programme team will continue to work on this relationship to drive stronger collaboration, including on supporting the mainstreaming of cross-cutting issues, and greater efficiency including through regular ‘Round Tables’ held with all partners.
Flexibility and Scenario Planning:
DFID will monitor the NGOs’ progress each quarter, and along with the annual review will revisit the delivery mechanisms, logframe, budget and performance to agree technical direction and future funding and targets for the following year.
As the trajectory of conflict in Yemen remains uncertain partners were requested to demonstrate how they would adapt their activities against three potential scenarios for Yemen over the next 3 years, including options to scale up activities. This built on internal scenario planning work conducted in mid-2016, and updated in June 2017. The three scenarios cover a failed Yemen with accompanying humanitarian catastrophe (scenario 1); on-going crisis and conflict with a severe humanitarian situation (scenario 2); and a return to political transition, albeit with ongoing humanitarian need (scenario 3). Although there is considerable variability across Yemen, we judge that we are currently in a ‘scenario 2’ situation.
This Multisector Humanitarian Response Programme is designed to be flexible. We are currently planning for partners to deliver activities planned against a ‘scenario 2’, however should the security situation, humanitarian need or partner’s ability to operate change and trigger points show a move into scenario 1 or 3 we will quickly work with partners to switch activities between scenarios.
Should the situation further deteriorate, under ‘scenario 1’ partners will be ready to respond to emergency needs with a combination of in-kind assistance and cash transfers, depending on access and security as well as the capacity of local markets to supply needed basic commodities. The focus will remain on food security and WASH/Health/Nutrition sectors.
In case of return to some form of political transition with limited state control of Yemen (scenario 3), partners will be able to transition after three months of relief assistance, with some focus on returnees, first to early recovery activities and then towards more sustainable resilience work, in line with the strategic objectives of the programme. Partners will submit a request to DFID should they wish to re-programme activities between scenarios, including an updated budget, logframe and summary of programme activities, alongside a justification supported by a robust context analysis.
Lastly this programme remains flexible to respond to emergency humanitarian disasters (eg. Cholera, flash floods) where appropriate, and where not responding would undermine the ability to achieve the principle outcomes of this programme.

Financial Case

What are the costs, how are they profiled and how will you ensure accurate forecasting?
The total programme budget is for up to £90 million. All NGOs have submitted detailed budgets and forecasts. Payments will be made quarterly dependent on progress and reporting, as well as accurate forecasting. Forecasts and regular updates are of particular importance in this programme given the challenges of access working in a conflict. Explained variances by quarter are anticipated. All payments will be made to the lead NGO. They will then disburse funds to the other partners within the consortia where relevant.
The direct costs to DFID include approximately 1.5 full time equivalent staff time split between the Head of Yemen Humanitarian Programmes, Programme Manager, Humanitarian Advisor and Programme Officer. These are within DFID Yemen’s current headcount. DFID Yemen will also fund a component to contract external support for assurance services and to undertake enhanced due diligences including fieldwork in Sana’a, as DFID Yemen are unable to visit. These costs include VAT. Anticipated costs are shown below.
Component	2017/18 / £	2018/19 / £	2019/20 / £
101 - Save	5.2 million	5.2 million	5.2 million
101 -Oxfam	5.2 million	5.2 million	5.2 million
102 - Care Consortium	11 million	11 million	11 million
103- Acted Consortium	8.6 million	8.6 million	8.6 million
104 - Third Party assurance	25,000	25,000	25,000
Total	30 million	30 million	30 million

£24 million per year has been allocated from DFID Yemen’s Resource Allocation. Initial Accountable Grant Agreements will be within this £72m cap. A smaller unallocated proportion of DFID Yemen’s budget as well as potential funds from a bid to the crisis reserve will be reviewed during this (and subsequent) years and allocated across the portfolio based on need and partners’ ability to respond (access, scale, and nature of interventions). One of the primary benefits of this programme is its adaptability and flexibility to rapidly respond as priority needs emerge. The NGOs have demonstrated the ability to scale up several times in the previous programme, in response to the emerging need. This scenario has been built into their planning. All proposals demonstrate readiness and an ability to scale up delivery if further funding becomes available. The Head of Office will agree any allocations of additional resources to this programme based on needs, affordability and proven ability to respond. At that time an Accountable Grant Addendum would be signed with the NGO partners responding. We request up to the £90m over three years be approved in this Business Case.
The programme will be managed by the Yemen Humanitarian Programme team and funded from the DFID Yemen RDEL programme budget. This programme will be ODA eligible. Sector codes the programme will be reported under are set out below.
Funding Type: Accountable Grant (111) A/C 2362
Benefiting Country: Yemen
Acted Consortium
	Input Sector	Input Sector Code	Percentage Allocation
1	Emergency Food Aid, Humanitarian	72040	40%
2	Material Relief Assistance and Services, Humanitarian	72010	60%
Care consortium
1	Emergency Food Aid, Humanitarian	72040	40%
2	Material Relief Assistance and Services, Humanitarian	72010	60%
Save
1	Emergency Food Aid, Humanitarian	72040	100%
Oxfam
1	Emergency Food Aid, Humanitarian	72040	100%
Third Party Assurance
1	Emergency Food Aid, Humanitarian	72040	51%
2	Material Relief Assistance and Services, Humanitarian	72010	49%

Direct Programme and Non-programme attributable costs (NPAC): The programme budget provides a full breakdown of direct delivery costs and programme support costs. All NPAC rates have been reviewed in detail, negotiated and agreed individually with partners, keeping costs to a minimum whilst ensuring partners are able to deliver the quality programming needed. The following rates have been agreed on: ACTED: 7%; CARE: 8%; OXFAM: 10%; SAVE: 8%. The overall administrative cost for the project over three years is: ACTED: 20%; CARE: 24%; Oxfam: 16%; Save the Children: 25%. The rates are relatively high due to the operational difficulties of working in conflict and particularly hard to reach districts. The fluctuation reflects the different nature of their interventions and locations projects are delivered in.
Payment of funds
DFID will disburse funds to the NGO leads (ACTED, Care, Save the Children and Oxfam) on a quarterly basis, as laid out in the Accountable Grant Agreements. This is an efficient and directly accountable mechanism for funding humanitarian partners. The NGOs will submit detailed financial (and narrative) reports six weeks after each quarter end including updated forecasts and workplan for the subsequent quarter. DFID Yemen will review the reports in order to ensure that expenditure and forecasts matches the request for payment as well as progress against activities. Funds will be paid when satisfied with these reports and the forecasts for future months. Payment will only be made based on need taking into account any unused funds from the prior period. As stipulated in the four Accountable Grant Agreements, any unused funds will be returned at end of programme.
The Yemen team will maintain regular contact with partners to ensure that data input as part of DFID’s monthly finance cycle is accurate and that DFID is able to identify and monitor the financial impact of any changing circumstances and emerging risks. In line with resource accounting principles, payments to the NGOs will be forecast monthly on DFID’s financial systems to reflect the timing of the activities being funded. Any assets created by the programme will be tracked through quarterly reports and disposed of according to DFID guidance. There are no further accounting considerations.
Financial management
All existing partners have strong financial systems in place and DFID have used our strong working relationships with existing partners, to build on and improve the robustness of their financial reporting. We have already done the same with new partners, in the development of their budgets and three year forecasts, and will continue to do so with all as we move forward with the programme. The greatest weakness in the previous programme was seen in optimism bias around forecasts, not always reflecting or anticipating the challenges and changes faced on the ground. We have worked with partners and their financial teams and expect better reflections going forward.
All partners provided audited statements with their proposals and will be required to submit annual audited statements which separately identify DFID funds, associated disbursements and which show unspent funds. These will be reviewed for financial anomalies or red flags by the programme manager, seeking support from a finance manager as required. Lastly, the external due diligence assessment will further review the financial systems in place, identifying key strengths as well as weaknesses where we will then work with partners to strengthen.
Assessment of financial risk and fraud
Operating in this conflict, where institutions are weak, there is inevitably a high risk of aid diversion, corruption and fraud. DFID’s policy in Yemen is to work with well-established organisations that are able to demonstrate strong systems and controls to both detect and prevent fraud. This was a key component of the proposal assessment and selection criteria. The NGOs have in place robust agency-wide policies and procedures to prevent fraud, bribery, corruption, terrorism and money laundering. The Management Case incorporates a more detailed assessment of their controls. The external Due Diligence assessment will review systems specifically around robustness of fraud prevention and should provide DFID with a satisfactory opinion that controls are robust enough to detect endemic or significant fraud. Where weaknesses are identified we will work with partners to strengthen controls.
These precautions will not remove all risk, and cases of aid diversion (from looting and bombardment) have been report in the past. As soon as NGOs become aware of an incident (including relating to partners) they will report the incident to DFID Yemen’s Programme Management Team or directly to DFID’s Counter Fraud Service within 48 hours of learning of an incident. Upon becoming aware of an incident they will fully investigate it until the matter is resolved keeping DFID up to date. Approximately half of this programme will focus on food security including cash transfers. There is no evidence that cash transfers are more or less prone to diversion than other forms of assistance. It is possible that electronic transfers could reduce corruption risks through more transparent tracking[32]. The main corruption risks for in-kind assistance relate to procurement, storage and transport (Ewins et al., 2006). DFID Yemen will use the delivery chain mapping to identify fraud enablers and risks and work with partners to manage these risks. Our third party monitoring programme, whilst not designed specifically to detect fraud, will give assurance that funds are being used appropriately. All partners are expected to use the lists included in their Accountable Grant Agreement to ensure their partners and suppliers are not included in the global sanction, watch, regulatory, or law enforcement lists.
[32] State of evidence on humanitarian cash transfers, Sarah Bailey and Paul Harvey, ODI 2015

Management Case
Management arrangements for implementing the intervention

All partners in the consortium are direct implementers. (With cash transfers these are delivered to beneficiaries through the use micro-finance suppliers. This is the same with all our partners delivering cash programmes in Yemen.
Downstream Partner Mapping (with % of total funding shown)
DFID Yemen
(100%)

CARE UK
(35%)

NRC Yemen
8.33%

ACF Yemen
8.33%

MC Yemen*
8.33%

CARE Yemen
10%

ACTED*
(30%)

ADRA Yemen
7%

Handicap International*
1%

YFCA*
9%

ACTED Yemen*
13%

SC Yemen
(17.5%)

Oxfam Yemen
(17.5%)

NNGO
Year 2&3 (tbc)
Key
* = New DFID Partner
       = National NGO
Management Structure
DFID will work through bilateral agreements with four partners to manage the overall delivery of this portfolio, two of which will manage consortia. The diagram above represents the overall flow of funds and governance structure for the delivery of the portfolio. The % demonstrates the funding flow between partners. The expectation is that over the duration of the first year of this programme Oxfam and Save will form a consortium focused on food security, with the potential inclusion of a new National NGO.
The DFID Senior Responsible Owner (SRO) is the Head of Yemen Humanitarian Programmes. The programme will be managed by the Programme Manager, Humanitarian Advisor, and Programme Officer from Amman, Jordan. Along with the SRO they will scrutinise delivery, risks and results through reporting and quarterly meetings with all partners. Monthly programme calls will be held between DFID and each lead partner. Furthermore quarterly meetings will be held in Amman between DFID and all partners, further enabling coordination and encouraging efficiencies and learning.
Risks of intervention and how will these be managed
Given the high return of providing life-saving humanitarian and development assistance, DFID Yemen has a high risk appetite at the context, delivery and operational level but a low risk appetite at the fiduciary, reputational and safeguarding level. In this programme, we mitigate risks by: working with established and impartial agencies that have a strong track record in delivering in difficult operating environments; monitoring delivery through an independent monitoring programme; and reviewing quarterly risks and our tolerance thresholds at the programme and portfolio level.
All partners (lead and downstream) have integrated risk management systems in place and will report regularly to DFID. The main risks (net – after mitigation) identified in this programme are detailed in the delivery plan and outlined below. These will be monitored and discussed on a quarterly basis with Partners and updated accordingly. They will be managed or escalated in line with DFID Yemen’s Risk Management Strategy.
Risk Description / (Net risk colour)	Mitigating Actions
Conflict restricts access by partners to programme locations / Probability: Likely / Impact: Major	deconflict field missions, convoys and fixed assets with the EHOC (Saudi-led Coalition) notification system. / The security situation is regularly monitored with updated security plans and contingency measures in place. / Conflict analysis and its implications reflected in updated management strategies and activity plans. / Partners hold regular meetings with district authorities, local council members and religious leaders to improve access and acceptance at the local level. / Work through local staff whenever possible, employing female workers as appropriate. / Engage in community mobilisation and local participation in planning and implementation of activities to increase local acceptance. / Diverting operations to other locations in an extreme case [inbuilt flexibility in programme to do this]
Conflict restricts beneficiaries to programme locations / Probability: Likely / Impact: Major	Ensure partners have strong contingency plans, including the ability to bring the delivery of assistance closer to beneficiaries, and the investment in local capacity building – to do localised delivery where needed. / To ensure that strong gender and conflict sensitive approaches are implemented, to increase equal accessibility for men, boys, women and girls, whilst ensuring the ‘do least harm’ principle is upheld. / Ensure partner have robust beneficiary complaint feedback mechanisms and respond to all complaints to strengthen accessibility for beneficiaries.
Threats to staff safety from state or non-state actors / Probability: Likely / Impact: Major	Staff evacuation plans in place and regularly updated. / Safety and security protocols to protect staff and assets are in place and followed. / Access information locally about movements/activities of various groups; Listen to the local population. / Work closely with local groups who can work as deterrent for such situations. / Regular updated security analysis. Continued close monitoring of situation jointly with other actors. Hold regular consultative meetings with the district authorities, local council members and religious leaders to maintain acceptance. Where deemed necessary restrictions on movements in cities. / In extreme situations, evacuate staff as per the organisational policy. / Coordinates for offices and accommodation provided to UN/ KSA for de-confliction.
Continued use of central bank official exchange rate, resulting in either Donor, or beneficiary loss of value. / Probability: Possible / Impact: Major	Work with the Central Bank of Yemen (CBY) to align or move towards accepting use of the market rate. / Work with other donors and UN to form a united positon on the exchange rate issue. Ideally resulting in donors being supportive for partners to seek better rates from the market. Better exchange rates negotiated through collective economies of scale. / Ensure that partners work with the Cash and Market Working Group to ensure alignment of approach for humanitarian actors. / Work with Central Bank of Yemen and legal Yemeni financial institutions to prioritise the cash needs of humanitarian partners.
Financial intermediaries lose international and local access to funds. / Probability: Possible / Impact::Major	Encourage partners to hold multiple bank accounts with multiple banks in Yemen. / Encourage partners to use more than one financial intermediary inside of Yemen to deliver payment. / DFID to remain informed of the banking sector challenges, and work with stakeholders to have sufficient plans in place. / DFID to continue lobbying the central bank to implement all measures needed to keep Yemen from being black listed by Financial Action Task Force - Middle East and North Africa (FATF MENA).
Commercial imports stop flowing into Yemen. / Probability: Possible / Impact: Major	Continue support to UNVIM who clear vessels requesting to enter Hodeida port. / Coordinate efforts and data-sharing between different reporting mechanisms (including KSRelief and Government of Yemen). / UK Special Envoy negotiations for a solution to Hodeida and for the government to pay salaries. / Work with the World Bank and Saudi Arabia to fund the International Financial Cooperation (IFC) trading facility. / Partners provide market information to the Cash and Market Working Group to build better understanding of the local markets.
Partner capacity inhibits ability to deliver programmes effectively / Probability: Unlikely / Impact: Moderate	Robust due diligences are undertaken and reviewed to ensure partner (and downstream partner) capacity is strong. / Geographical and sectoral coverage of all partners spreads this risk, to ensure in the case of one partners’ weak capacity / or access constraints, this would not impact on other agencies ability to deliver. / Reliance on local/regional expertise wherever possible. / Capacity building of partner organisations and national staff where possible. / Working together with other NGOs on areas of common interest and programming. / UK messaging to various stakeholders in Yemen and Riyadh to improve access. / Risk management spread through implementation through various NGOs.
Lack of national and local authority cooperation with project creates delays / Probability: Possible / Impact: Minor	Partners maintain close working relationships with government ministries and local authorities. / Partners work together in order to jointly pass the message to the authorities in order to facilitate the access to the beneficiaries and movement to the field; / UK support to UN action to engage with local level structures and set up regional hubs. / Partners support OCHA Access Advocacy work by sharing information on their Access Constraints with the Humanitarian Access Working Group chaired by OCHA Sana’a, in order to populate the Access Monitoring and Response Framework (AMRF) as a safe and effective joint access advocacy tool.

Fraud/Corruption/Aid diversion Risk Matrix
Risk Description / (net risk colour)	Mitigating Actions
Mismanagement of funds (fraud and corruption) by partner or downstream partners / Probability: Possible / Impact: Major	DFID work only with established partners with robust controls confirmed through Enhanced Due Diligence Assessments. / Partners receive regular communications and fraud awareness sessions from DFID. / Partners conduct partner appraisals, maintain strict financial procedures and include code of conduct policies in MOUs for all partners. / Partners undergo annual financial audits and reports shared with DFID / All partners have whistle blower policies and mechanisms for beneficiaries and others to notify of any fraud and corruption. / Partners are required (and reminded) to report any cases or suspicions of misappropriation or fraud of DFID funds. / Ensure partners are fully transparent on all their transactions into Yemeni Real (including which exchange rate is used). / Additional quarterly reporting requested from partners undertaking cash and voucher programming. / Reimbursement of funds is sought where partners’ preventative measures are not considered robust enough. / DFID Independent Monitoring Programme (British Council).
Collateral damage and diversion of supplies during storage or transportation, additional reputational risk if aid is diverted to terrorist organisation. / Probability: Likely / Impact: Moderate	Where possible partner supplies are held in decentralised and secure locations to minimise risk. / Keep up to date with security updates and sit reps to make early decisions on relocating people and assets. / Appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc are in place / Partners investigate opportunities for asset recovery of losses and assess any lessons learnt on controls. / Partner project locations and transport plans submitted to deconfliction cell in Riyadh and the Ministry of Interior in Sana’a. / Partners are required to report any cases or suspicions of aid diversion of DFID funds. / Partners have put in place effective beneficiary complaint feedback mechanisms. / Signed Accountable Grants confirm partners’ obligation to comply with UK counter-terrorism legislation.
False Beneficiaries: Ghost beneficiaries; Incorrect beneficiary identification; collusion involving cash agents/distributors/ community leaders. / Probability: possible Impact: Moderate	Robust and transparent complaints feedback mechanisms. / Accurate biometric identification methods used by partners. / Strong community engagement and beneficiary selection through diverse community leaders (not just one). / Strong post distribution monitoring and reporting of any suspected cases. / Third party monitoring confirmation.
Cash going to de-facto Government institutions, and/or terrorist organisations / Probability: Possible / Impact : Moderate	Delivery chain mapping undertaken identifying all stakeholders before reaching the beneficiary. / DFID Yemen approach followed on working alongside (de facto) government institutions. / Ensure partners conduct robust risk assessment on their partners and suppliers and transactions are made through legitimate financial institutions/intermediaries. / Partners consult the lists provided in the accountable grant agreements to ensure they are not working with blacklisted organisations. / Annual audited statements provide assurance funds are all accounted for.

How will progress and results be monitored, measured and evaluated?
There are long-standing challenges to the measurement of the impact of humanitarian assistance in Yemen. Consequently the sector focuses on monitoring the effectiveness of output delivery and outcome achievements, as opposed to overall impact on the affected population. This is common practice in a context such as Yemen where the response is primarily aimed to save lives and reduce suffering.
The primary results reporting tool for this programme will be a single logical framework (logframe) collating results from all partners. Standardised indicators have been developed for all partners. The programme logframe will track progress against measurable indicators, determined in the development of this Business Case and monitored quarterly. The completed logframe will provide the results against which the Annual Review and Project Completion Review will score the programme. The logframe will be reviewed at least annually to reflect any significant changes in the context and assumptions made.
Monitoring is driven by partner’s results based management approach to operations. It includes the collection, analysis and disaggregation (by gender, age, disability and geography) of information on activities; the results achieved; the situation for the target population including monitoring safe and equal access to assistance; and the operational context – including both intended and unintended positive and negative impacts on conflict dynamics. Monitoring and evaluation activities have been built into the design of the programme throughout. In terms of data disaggregation, results reported by partners in their quarterly reports will be disaggregated by sex, age, disability and geography, where possible.
DFID Yemen’s’ Independent Monitoring Programme (IMP)
DFID Yemen’s’ Independent Monitoring Programme provides independent assessments of the quantity, quality and targeting of results. As such, it is a key accountability and lesson learning mechanism. IMP reviewed cash transfers through Save the Children and Oxfam in the previous programme. This programme will also be subject to the DFID’s third party monitoring in Yemen, and will undergo at least one review during its lifecycle. We will identify indicators in order to verify a sample of the programme’s results.
Beneficiary Feedback
This programme operates on the belief that beneficiaries are best equipped to understand and give voice to the concerns regarding their community. Beneficiaries and communities are therefore engaged at multiple levels, and through various modalities during the implementation of the Programme and MEAL activities.
To facilitate beneficiary feedback, mitigate corruption, help address protection issues and support the application of conflict sensitivity across all of the programme, all partners have set up effective gender sensitive beneficiary complaint feedback mechanisms. Moreover their first hand monitoring of activities and direct implementation of activities at district level enable the proactive and continuous engagement with beneficiaries and local communities. Innovative uses of social media and telecommunications are also used by partners to get continuous feedback.
Partners have committed to working with us to build in direct beneficiary feedback/engagement with DFID where possible, without the risk of jeopardising the programme or putting beneficiaries and partners at risk. We will try to work with partners to build in direct engagement with beneficiaries at least once a year, feeding into the Annual Reviews.
Annual Review
In compliance with DFID Smart Rules the first annual review will be carried out 12 months after the beginning of the programme. The first annual review will track progress made on recommendations made in the project completion review of the last DFID grant to NGO’s. It will also reflect on key cross-cutting issues, including gender sensitivity and social inclusion, conflict sensitivity, protection mainstreaming and environmental impact. A project completion review will be completed by within 3 months of the project end date (March 2019).
Evaluation
No formal evaluation is currently planned for the programme. Measures outlined are sufficient to assess achievement and ensure accountability. This shall be reviewed during the programme.
## Smart Guide
## The Business Case:
- Sets out the case for a programme, adapted to suit the context
- Explain clearly and succinctly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds
- It should be as proportionate as possible. Consider using sub headings and paragraph numbers.

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment.

Refer to the considerations below, and the 10 delivery & 10 approval questions in the Smart Rules.
Intervention Summary (2 Pages)
Start with a half page maximum narrative summary of what the programme will do, ensuring you cover the points set out at the top of that section. Then use bullet points to answer the ten approval questions that follow. Do not delete the headings/questions in bold, but do delete any square brackets which provide steers about what to think about.
Strategic Case
This makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do (impact and outcome) and how with evidence. It should link to, but not repeat, the Business Plan with a clear illustration of how the programme contributes to DFID’s global and portfolio priorities. Retain the two sub-headings and provide the information required under each of them (deleting the square brackets). It is up to you where in the Strategic Case the sub-headings go. But it might make most sense at the end.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices , with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a summary VfM statement for the preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, programme team etc). It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration, ideally set out in a risk matrix, of the risks and risk appetite. It should include the envisaged approach to escalating risks and issues as well as exit and possible closure scenarios.