Annual Review - Summary Sheet
Title: Support to the Economic Recovery of Somalia (SERS)
Programme Value: £39.4 million		Review Date: July 2017
Programme Code: / GB-1-204313	Start Date: / 20/05/2014	End Date: / 20/05/2019

Summary of Programme Performance
Year	2014/15	2015/16	2016/17
Programme Score	A	A	B
Risk Rating	High	Major	Major
Summary of progress, challenges, lessons learnt and recommendations / Overall assessment / This is the third annual review of SERS. The programme scores B, with milestones on average moderately not meeting targets. The review analysis points to two main reasons for this. First, the SERS programme works on fundamental state-building and economic development agendas in Somalia. At Somalia’s present level of development, these agendas are highly complicated and making genuine, systemic, and sustainable progress is difficult, including assessments about where and when progress is possible. The review period (2016) was also a particularly difficult period, affected by the extensive drought and slowdown in the government processes during the federal elections. Second, the programme could improve focus and a clearer theory of change, in particular within the MPF. The review finds that the World Bank (WB) and the MPF are working on crucial issues, but a more focused, prioritised approach around the key reform steps would be advisable. / Summary of progress / The SERS programme is intended to support “more effective economic institutions contributing to socio-economic recovery” of Somalia. It is delivered through the World Bank managed Multi Partner (Trust) Fund (MPF) intended to run for 10 year up to 2024. / The programme, so far, has performed well in terms of mobilising funding and developing a broad portfolio of projects intended to support state-building and socio-economic recovery of Somalia. / What has gone well:- / Over the review period, it has made good progress in pockets of public sector reforms relating to civil services, public finance management, and intergovernmental transfers and enhancing financial integrity of international remittances into Somalia. / The programme has supported government institutions to become more functional by developing a new legal framework, modernising human resource development, and recruiting new qualified staffs. Through a new merit-based recruitment system, qualified and competent recruits are being placed in key positions across the government. The programme is funding part of the civil service salaries and other costs, providing financial security to the civil servants which is expected to enhance their professionalism. The programme has done particularly well in getting an increasing share of the Federal Government of Somalia’s (FGS) civil service pay bills financed by the government’s budget. This is very significant in the context of the very narrow and small revenue base of the government. / There has been good progress on the Public Finance Management (PFM) component, considered as cornerstone of all public sector reforms in the country. The programme has supported modernization of financial management by implementing the Somalia Financial Management System (SFMIS). Transparency and integrity of government systems are improving through placement of competent staffs and establishment of independent oversight structures such as the Financial Governance Committee. A good start has also been made towards tax harmonisation. / The programme’s support to the Central Bank of Somalia (CBS) has been critical in improving the financial integrity of international remittances into Somalia, thus mitigating Somalia’s risks to international financial integrity and countering terrorist financing. Specific reforms supported by the programme have contributed to the Somali Government’s successful negotiation of a Staff Monitored Program (SMP) with the International Monetary Fund (IMF). The IMF programme (the first in almost thirty years) builds on public sector reforms supported by the MPF projects. / On support to private sector development, good progress has been made through the Public Private Dialogue (PPD) process in bringing the government and private sector to engage and chart a path for advancing high priority reforms and enabling actions. The Somali Core Economic Institutions and Opportunities (SCORE) project has contracted managers for the matching grants. After a delayed start, the managers have completed the process of inviting and screening of nearly 1800 grant applications in three regions of Somalia. The MPF has also engaged directly in sectors important to the Somali economy, namely, ICT, Oil & Gas and Fisheries, and providing technical expertise to the government in formulating policies and laws to improve the policy environment of these sectors. / The Bank has successfully used the MPF to have a strategic engagement with the Somali government and development partners in supporting economic recovery and laying the foundation for debt relief. Somalia remains in arrears and hence has no access to funding from the International Development Association (IDA). / What has not gone so well:- / Delay in payment of salaries persists. There is little evidence of how the programme is leveraging its growing financial support under the Recurring Cost and Reform Finance (RCRF) project in securing political space for pushing critical public sector reforms. It is unclear, if and how the MPF makes use of sector level evidence in prioritizing the staffing and reform needs of government institutions that can have more direct and immediate impact in unlocking economic recovery and state building in Somalia. For example, it can be argued that achieving functioning public institutions in financial and revenue generating sectors can have more direct and immediate impact on driving economic recovery than paying salaries of teachers and health workers, which presently account for 6% to 7% of the MPF’s total budget and which may be justified on stabilisation grounds. / Progress on effecting intergovernmental transfers has exceeded the target, although the same has not been adequately leveraged in securing a meaningful dialogue at the political level on fiscal federalism. Revenue mobilisation efforts continue to be constrained mainly by a narrow tax base, weak institutional and administrative capacity, weak revenue intelligence, and multiplicity of taxes at the national and sub-national level, poor enforcement to existing tax laws. / Progress on some target areas of the PFM project e.g. strengthening integrity of procurement systems and audit functions across government remains patchy and deterred by a myriad of factors, including weak capacity and political will. Planned activities in these areas are stalled due to procurement delays, and a weak supplier market. Progress on providing technical assistance and capacity building support in revenue, treasury management, budget preparation, and execution has been slower than expected. / There have been delays in implementing the catalytic fund. This is in part due to the failure of the decision-making process to avoid unnecessary interference. Equally, arrangements for providing TA relating to improvements in the enabling environment are also behind schedule. A technical assistance facility, Small and Medium Enterprise Service (SMEF) has been created but has not delivered results yet because the grant-winners are not in place. / Overall score / The programme has missed 11 out of the total number of 19 output level indicators. Of the 19 indicators, eight are scored at A or above, seven at B and four indicators at C. The AR has awarded the programme a “B” based on the overall output performance. (Score calculation Annex 4). / The AR still judges the MPF as the strongest available vehicle for delivering the objectives of the SERS programme. The AR also judges that there is a strong case for DFID Somalia’s decision to seek extension of the programme. This is because the new Federal Government has shown firm commitment to driving economic recovery and public sector reforms as articulated in the May London Somalia Conference. Economic recovery in Somalia will be choked in the absence of additional funding to support reforms. / Moreover, the programme is not off-track. The fall in this year’s score comes after two successive ‘A’s in the previous two ARs. The Fund’s performance should also be interpreted in the context of its very high ambition. Success of the programme should not be judged with the same criteria DFID would use in other low-income and fragile countries. Somalia’s difficult political economy and weak institutional capacity will take longer-than-anticipated to address in unlocking economic recovery. / Challenges / The main challenges relate to:- / Theory of Change: / The programme’s theory of change underlying DFID’s log frame – narrowing down the focus and clearly defining specific intermediate steps needed to strengthen the link between the programme’s outputs and intended outcomes. The programme currently has a very broad range of projects, covering from PFM, infrastructure development, civil service reforms, private sector development, and policy and regulations in productive sectors. Further, the focus within most of the projects is very expansive and is difficult to manage. / Moreover, not every government institution/public sector reform is equally important and urgent for state-building and unlocking economic recovery. Some will have more direct and immediate impact than others will. The MPF will benefit from having a clearly defined approach to and basis for prioritisation and sequencing of reforms. / The delivery model: / Delivery through Somali country systems: Nearly 80% of the programme’s support is through Somali country systems. This is with a view to making the government institutions more capable and sustainable in managing their own development. Planning and execution of activities across several projects have faced delays because of weak administrative capacity, lack of transparent systems and procedures, and absence of well-defined oversight mechanisms within government, the very issues projects under the programme are meant to tackle and strengthen. More targeted technical support from the MPF in strengthening the government’s project management capacity can drive timely implementation of the MPF’s projects. / Reliance on external consultants: The programme relies heavily on externally hired consultants and multiplicity of contracts to plan and deliver activities in a significant number of projects. For example, the Public Finance Management Capacity Strengthening Project II has 32 contracts in total. Of this, 17 have been executed or cancelled, and the remaining 15 are at various stages of implementation. Co-ordinating and managing activities across such a large number of contracts will be challenging anywhere, and is particularly so in Somalia, where the supplier market is very weak. A large number of small contracts can theoretically help introduce competition and build a supplier market, although this has not been properly documented in the MPF to make any assessment. It also appears that building synergies across numerous contractors can be challenging with potential risks to the intended outcomes. / Procedural and management aspects: / Lack of frequent and strategic engagement with donors: Donors consider the format and frequency of the Bank’s engagements and reporting inadequate. Most of the donors have informed the Bank that they want clearer, more timely and transparent communication from the Bank about the challenges and opportunities faced by the projects, what measures and adjustments the Bank is making to tackle the challenges. The donors have also offered to engage more with the Bank and think collectively about the challenges and potential solutions. Donors feel that efforts by the Bank in this direction, so far, have been few and far between. For example, following the Bank’s six-monthly progress report in February 2017, donors provided detailed joint feedback in March, raising concerns about the MPF’s performance, management and forward look. The Bank is yet to substantively respond to the joint donor feedback. / Inadequate and delayed information from the WB: Another procedural challenge is the lack of flexibility and timely response from the Bank as articulated by the donors in the joint feedback. This is, in part, due to the Bank’s centrally mandated operating model in fragile countries and, hence, outside the control of the Country Management Unit as well as the Task Team leaders. Some delays, however, can be addressed through timely follow ups (e.g. delay in decisions on award of matching grants under the SCORE project) and through more targeted handholding e.g. support to address delays in the recipient-executed projects. There is need of more information sharing on what steps have been taken by the Bank to address delays in the recipient-executed projects. / Key lessons learnt / Establishment of procurement systems, procedures, oversight mechanisms and management capacity are essential, especially for time-critical programmes, before a host government in a fragile and conflict affected country can be expected to execute externally funded projects. The MPF’s reliance on recipient- executed projects could be more gradual and calibrated to public sector capacity. / A consultant-based delivery model may not be appropriate for a weak supplier market. The challenges of procuring, managing, and securing synergies across multiple contracts should be carefully assessed, even when a multiplicity of contracts is needed on technical grounds e.g. one or a smaller number of contracts are unable to deliver the range of expertise needed. Equally, the balance between ground-presence and remote backstopping should be carefully and periodically assessed based on considerations of the evolving needs of controlling cost, ownership, and oversight for timely delivery, and potential development outcomes. / Delivering economy-wide transformative changes is time and resource intensive, especially in countries where public sector institutions and governance capacity is weak. In such circumstances, the choice and design of interventions need to be based on detailed diagnostics with a view to identify and prioritise critical areas of reforms based on targeted outcomes as against the approach that is all encompassing. / Implementing matching grants is complex and politically difficult. It is more so, if it involves the government in decision making, especially in countries where public sector institutions, oversight mechanisms, political economy, and clan dynamics are weak. This lesson was clearly highlighted in the DANIDA evaluation (2016) of the Somaliland Business Fund (SBF). The role of matching grants in addressing job creation and investment requirements, in any fragile and conflict affected country (FCAS), should not be over-stated at the cost of neglecting critical market and public sector failures preventing and distorting private sector development. / A granular understanding of the political economy is one of important factors for success in pushing reforms. Despite good technical work by the WB in a number of planned economic policy reforms, progress in many instances is delayed due to the difficult political economy (e.g. ICT, financial sector, Oil, & gas). The MPF’s efforts in some of these reforms could have benefited from a more granular understanding of the political economy, especially the political appetite and potential drivers of reform. / Headline future actions / Strategic Level / Push towards consolidation / There are a number of developments, which offer a good opportunity for DFID to engage with the Bank. The Somali Government and the SDRF process to push for consolidation of the MPF’s projects to identify and prioritise investments that can have more and immediate impact on state-building and economic recovery. Firstly, the Bank is in the process of finalising its Systematic Country Diagnostic (SCD) and Country Partnership Framework (CPF) for Somalia. The SCD provides a solid basis for prioritisation and sequencing. Secondly, the London Conference in May has also helped identify the Somali Government’s “priority of priorities” of economic recovery from the National development Plan (2017-19). Thirdly, an anticipated gap of $11m in the MPF’s funding envelope will most likely necessitate a process of prioritisation. / DFID Somalia should consolidate and work in greater partnership with the Bank at different levels in determining the forward look of the MPF, focussing in particular on the balance of emphasis across and within the MPF’s three themes namely (i) effective and accountable government; (ii) enabling economic growth and (iii) core economic infrastructure. The Bank can use findings from the SCD and NDP to inform what investments within each theme are the most pressing for delivering on the MPF’s core objectives. / DFID Somalia to use its engagement with the SDRF to clearly define roles/responsibilities and strengthening coordination across each of the three SDRF funding windows namely the WB Multi-Partner Fund for Somalia (MPF), AfDB Somalia Infrastructure t Fund (SIF) and UN Multi Partner Trust Fund for Somalia (UNMPTF) / Develop a core Theory of Change / As a part of developing the core theory of change, DFID Somalia will need to think about its preferred balance of emphasis across the three themes of the MPF, DFID’s funding is largely “un-preferenced”. If the pooled funding mechanism fails to deliver on DFID’s strategic asks, DFID Somalia may want to rethink its position on “preferencing” as the Bank’s TF policy allows preferencing up to 50% of contribution from any donor (Timing: October 2017). / Based on the identified balance of emphasis and intended outcomes, develop the programme’s core theory of change to establish closer and more direct relationship between the programme’s outputs and intended outcomes. DFID programme management team to agree with the Bank on a process and timeline for doing more analysis to (a) test the current theory of change, in particular assessing if and to what extent the current outputs are linked to the intended outcomes, and how best the links that are missing or weak can be strengthened. (Timing: November 2017). / Refine the approach to private sector development / Engage with the Bank and IFC to reassess the MPF’s approach to private sector development, especially under the SCORE and SICRP projects. Agree on division of roles and responsibilities between the MPF and the new IFC Trust Fund, keeping in mind (a) additionality, core competence, and absorption capacity (b) tools and expertise to address critical market and public sector failures in key sectors important to the Somali economy, and (c) clearly avoiding any duplication of efforts. This should result in a clearly defined and assigned private sector development plan. (Timing: November 2017). / Strengthen political economy analysis / World Bank to develop an action plan for strengthening robust political economy analysis in their design of interventions. (Timing: October 2017). / Operational level / Revise log frame to include adjustments needed to address the core theory of change, making output and outcome statements/indicators more relevant and SMARTER whilst modifying the timeframe and level of ambitions to realistic levels. (Timing: October 2017). / Revise and develop, in consultation with the Bank, a plan for assessing and improving the programme’s Value for Money with clearly defined indicators and methodology, and responsibility for reporting against the VfM plan. (Timing: December 2017) / Given the complexity of the programme, develop options for more support to the programme task team, including from the monitoring agent especially on the RCRF II, PFM and the SCORE projects. / Agree with the World Bank on rules and frequency of engagement including greater and transparent sharing of information, and improvements needed in the format of the six-monthly progress reports. (Timing: October 2017). / DFID and the Bank continue to engage periodically for robust forecasting and monitoring of financial disbursements to avoid payment in advance of need. (ongoing) / Prepare and agree on a revised list of lead advisers in light of past and upcoming staffing changes. (Timing: September 2017) / Hold periodic (six weekly) structured internal discussions to monitor progress, identify challenges and opportunities, and agree on approach for tackling identified challenges. (ongoing).

A. Introduction and Context
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204313/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204313/documents/

Outline of the programme
The SERS programme is intended to support “more effective economic institutions contributing to the socio-economic recovery” of Somalia. The programme is delivered through the World Bank managed Multi Partner (Trust) Fund (MPF – henceforth the Fund) originally intended to run for 10 years up to 2024.
The programme has fully disbursed £39.4m (approx. $51m USD) over three years (2014-2017) to the Fund with a total value of $330m of appraised projects, which includes both total partner commitments of $219.5m, and $111m in the pipeline. The Fund is financed 100% by international donors. The Fund supports a broad portfolio of projects (Annex Two) designed around the Somali government’s economic development priorities and operates under Somalia’s aid coordination architecture, the Somalia Development and Reconstruction Facility (SDRF). It mainly supports-
- Government recurrent costs e.g. (a) recruiting and paying salaries of civil servants in delivery of core state functions and (b) building and testing country systems and capacity for budgeting and managing public funds over time.
- Better economic governance by establishing and strengthening core economic institutions (e.g. audit, procurement, and central bank), developing administrative capacity (e.g. planning, financial management, and urban planning), and policies and regulations (e.g. tax harmonisation, telecom act, and financial sector regulation).
- Enhanced public financial management for improved integrity and transparency in government spending and procurement
- Government to improve the environment for private sector development and the private sector itself to become increasingly productive
- Urban and infrastructure assessment and planning, including feasibility studies for key large infrastructure for transport, market access, trade and energy.
- Rehabilitation of small, especially local urban infrastructure projects.
What are the expected results?
SERS intends to support Somalia’s economic recovery by delivering the programmes intended outcome measured by three indicators relating to (i) enhancement in the government’s revenue collection, (ii) total number of direct jobs created under the programme, and (iii) private sector investment directly mobilised. The programme aims to deliver these outcomes by providing expert knowledge, technical expertise, capacity building, and resources to the national and sub-national governments and the private sector. Progress against the programme’s intended outcomes and outputs are set out and analysed in the following sections of this AR.
What is the context in which UK support is provided?
Somalia is emerging out of over two decades of conflict with a dysfunctional public sector and a narrowly focussed private sector captured by business elites. Public institutions for fiscal and monetary policy management, private sector regulation, tax administration, and service delivery are either non-existent or deficient and very weak. Absence of a functional state has exposed Somalia’s vulnerability to shocks e.g. the current drought. Somalia’s domestic resource base is insufficient to maintain basic administrative structure and security. Development assistance is needed to strengthen core state functions and public sector reforms, which are precursors for (a) driving economic development, and (b) creating an effective and functional sustainable government.
Management
The WB manages the fund for a fee 5% of the fund value. All MPF projects are originated, and designed mainly by the WB and are subject to approval of SDRF and the World Bank Board. The fund supports a portfolio of projects with activities implemented by the government (classified as Recipient Executed) reinforced with additional work implemented by the Bank (classified as Bank Executed).
The Bank is responsible for appraisal, implementation, review, and monitoring and reporting on all performance aspects of the MPF-financed projects. The Bank also assumes, on behalf of the donors, fiduciary responsibility for the funds spent by the MPF.
Fit with UK/DFID strategy
SERS fits well with DFID’s Economic Development Strategy. By strengthening Somalia’s economic policy, enforcement of economic laws, and resource mobilisation, SERS catalyses investment and job creation, helping Somalia and its poor people to work their way out of poverty. SERS is central to the delivery of DFID Somalia Business Plan’s (2016-20) vision of building an increasingly stable, secure, and prosperous Somalia.
## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
The programme’s outcome is “More effective core economic institutions contributing to socio-economic recovery”. There are three indicators as set out below:
Outcome	Dec 2016 Milestone	Actual	Progress
Nominal value of domestic revenue collection at federal (FG) and regional member state level (PL) ($, current prices)	FG: $120m / PL: $1m	FG: $ 113m / PL: $ 57.6m	Target missed marginally: The FGS has made some progress in increasing its revenue from sources other than customs duties since 2014. However, domestic revenue remains low at around US$113 million, with international trade taxes accounting for 68 percent of total. Given the very low and narrow tax base, it is assessed by the IMF that simple tax reforms, even within the rudimentary administrative structures could deliver substantial increase in domestic revenue. Entrenched interests, corruption, unclear federal structure and weak enforcement capacity are some of the key challenges to sustainable revenue growth. .
Total number of direct jobs created in enterprises supported by the SCORE project. / Total / Women / Youth	i)100 / ii) 30 / iii)40	0	Targets missed: The main instrument used under the Somali Core Economic Institutions and Opportunities Program (SCORE) project to achieve these outcomes has faced significant disbursement delays due to political difficulties in getting the SME Advisory Panels (SAP) functional. SAPs in each region review short lists of applicants for grants prepared by the matching grant fund manager. A proposal is being considered for a more automatic “no objections” procedure to support speedier processing and disbursement by the fund manager.
Private sector investment committed as co-payment by Catalytic fund recipients	$1,000,000	0	Target missed: This indicator is also dependent on SAP functioning, which has held up grant processing and disbursement. Progress on actual grant awards still awaits SAP review.

The programme has missed the three outcome indicators. This is in part because of the ambitious timeline and targets. Given the very difficult operating environment, outputs have taken significantly longer time than anticipated to roll out. Equally, the transmission of outputs to outcome has a longer gestation period than originally envisaged.
The MPF is into its fourth year of operation (out of original timeframe of 10 years) and has made good progress in a number of output areas. The lack of progress on two outcome indicators, namely jobs and investment, suggest challenges in the outputs’ link with the intended outcomes, including prioritisation and sequencing highlighted in the summary sections of this review. A deeper and constructive assessment of the theory of change is needed for a more comprehensive understanding of what are the most important public sector reforms for delivering the intended outcomes. We do not have outcome indicators that reflect the state and institutions building aspects of the programme. It is recommended that this will be captured in the logframe for the next phase.
Overall output score and description
The overall output score of the programme is B (Outputs moderately did not meet expectation)
	Output	Score	Weighting %
1	Strengthened fiscal and public finance management capacity	B	40%
2	Strengthened public sector management capacity	A+	20%
3	Productivity of high priority sectors enhanced	B	30%
4	MPF is effectively managed.	B	10%

The overall composite score across the four programme outputs is estimated at B, which means the programme “outputs moderately did not meet expectation.”
This reflects the findings on the progress reported by the Bank over the Annual Review period. As explained in detail in the following sections roughly 47% all output indicators have been missed; reflecting the need for a clearer TOC and more realistic log frame targets.
Has the logframe been updated since the last review? Following the last AR, the log frame was revised mainly to provide a closer narrative of the underlining theory of change, the general approach to the revision was to make sure that outcome, and output indicators are at the right levels given that output indicators are things directly within the control of the project. Output one was split to capture economic/ public finance management angle as well as wider public sector management. The revisions in the log frame are summarised in Annex three.
## C: DETAILED OUTPUT SCORING
Output Title	Strengthened fiscal and public finance management capacity
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / (Dec 2016)	Progress	Indicative score of the output indicators
1.1. % of annual civil service (non-security sector) wage bill financed by: (i) government; (ii) Recurrent cost and reform financing (RCRF)	i) 30% / ii)70%	Target exceeded: / 47% financed by government / 53% finance by RCRF (Average for 2016)	Overall: A+ / A+ / A+
1.2. Regularity of salary payments for civil service (non-security sector): / (i) average days between payments during year / (ii) # of months of civil service salary payments outstanding at the end of year	Improvement on previous year	Target not met: / 43 (Average for 2016) compared with 37 for 2015. / 4 (There had been 10 pay runs in 2016; however, 2 of the months were for salary arrears from 2015)	Overall C / C / C
1.3.Non-salary recurrent costs eligible for RCRF funding: (i) $; and (ii) % execution of annual budget (NSRC)	i) $500,000 / ii) 50%	Target not met: / $2,000 / 0.1%	Overall C / C / C
1.4. Implementation of intergovernmental transfers to regional member states: / (i) number of RMS receiving transfer; / (ii) % increase in total volume of transfers compared to previous years outturn	i) 2 (Pl and JL) / ii)10%	Target met: / 2 (PL and JL) / 616%	Overall A / A / A+
1.5. Improved capacity as evidenced by implementation of TA activities in relevant areas (revenue, treasury management, procurement etc.) FGS, member states and SL	Firms recruited to provide revenue and broader Public financial management (PFM) TA; / Satisfactory assessment of progress against work plans for the year in key areas	Target not met / There is some evidence of capacity built in systems (FMIS), procurement and PFM professionalization but in other areas procurement delays have held up capacity strengthening	Overall B

Key Points
- Indicators 1.1 and 1.2: Though Government reimbursed a higher proportion of government salaries paid, it only paid 8 months of civil service salaries in 2016, down from 10 in 2015, and with substantial delays. The WB project teams have started to work more closely with the WB macro-fiscal team and IMF counterparts to address the issue of increasing domestic revenue and prioritizing salary payments.
- DFID recently agreed to provide some additional funding (GBP 1m through an EFO) for supporting implementation of the recipient executed projects. This is to help the Bank mobilize additional expertise on the ground to support better implementation of the MPF’s client executed governance programmes, namely PFM, RCRF and Capacity Injection.
- Indicator 1.3: Reimbursing the government’s payment of non-salary recurrent cost was a reward for, and incentive to, designing and implementing best practice procurement principles, practices, and processes. Systems have been slower than expected to introduce, and budgetary allocation has proved to be more complex than initially envisaged. To address this, additional capacity has been built across Ministries and eligible payments are beginning to gain momentum.
- Indicator 1.4: Extending recurrent financing to the Federal Member States (FMSs) has been a major achievement given the stringent eligibility conditions. This is an area where good cooperation between different parts of the WB has been evidenced as well as between the WB MPF and DFID’s bilateral PREMIS programme that is supporting the FMSs on PFM. Going forward it will be good if the Bank is able to use this as an incentive to secure greater progress, especially at the political level, on the development of fiscal federalism.
- Indicator 1.5: The World Bank has experienced significant delays in procuring its TA, which has had a knock-on effect on activities on the ground. Lack of funding for the PFM programme in particular is limiting the scope of contracts for FGS revenue and PFM contracts in Somaliland.
Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommendation 1: Implementing partners for RCRF and PFM have built sufficient flexibility within their programming to address ad-hoc public system/financial management needs when they arise. This was evidenced by the former increasing its TA on non-salary recurrent cost procurement and by the latter in covering both inland and customs revenue in their inception report.
- Recommendation 2: Output indicators have been changed to better reflect what is within the implementing partner’s control.
- Recommendation 3: WB now report data on new recruits disaggregated by gender (see output 2).
Recommendations
- Some output indicators e.g. 1.1 could be made clearer by removing one of the two targets and setting milestone targets for 1.2.
- The WB team should continue to strengthen the synergies between the economic governance projects, in particular exploring how best RCRF funding and other governance projects can prioritise staffing, capacity building and TA needs of economic line ministries with a view to build stronger links between the outputs and intended outcomes of revenue mobilisation, private sector investment and jobs creation. The WB MPF team should also build better links with WB colleagues in the macro-fiscal team responsible for advising the FGS on fiscal policy. Ensuring the sum of the parts delivers real impact over and above their individual objectives engagement at the highest level of the FGS will also be required with the new government to ensure highest-level buy-in to the necessary reforms still required.
- The WB team should establish how it could support the FGS in controlling the wage bill whilst sustainably increasing its weak capacity. The rising wage bill, without a commensurate increase in revenue, poses a huge risk to the sustainable financing in the longer-term.
Output Title	Strengthened public sector management capacity
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		New Output	Impact weighting % revised since last AR?	New Output

Indicator(s)	Milestones / (Dec 2016)	Progress	Output indicator score
2.1. Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women)	(i) FGS: 50 / PL: 25 / (ii) Women: 20%	Target moderately exceeded: / FGS: 64 (12 women, 19%) PL: 60 (17 women, 28%) / Average for % women: 23.4%	Overall A+ / A++ / A+
2.2 Ministries/agencies with operational HR functions	(i) FGS: 1 / (ii) PL: 1	Target significantly exceeded: / The Capacity Injection Project (CIP) supporting 10 and 9 ministries and agencies in FGS and Puntland respectively.	Overall A++ / A++ / A++
2.3 Improved civil service management functions / [more qualitative to capture TA activities]	Code of conduct developed; / Work on pay and grading started	Target partially met: / The code of conduct is completed. All civil servants recruited under CIP must sign it. / The pay and grading work has started in Puntland and is under procurement at the FGS level.	Overall A
2.4. Transparency & Accountability: / i) # of monthly payroll reports published on the MoF Website. / ii) # of fiscal summary reports published on the MoF Website / iii) # of contracts/concessions reviewed by FGC (cumulative) / iv) # of FGC confidential assessments for which there is evidence of follow up in line with recommendations (cumulative)	12	Target met: / i) 8 payroll reports– While less than 12, this represents 100% of pay runs in 2016 / ii) 12 / iii) 20 contracts reviewed by FGC / iv) 13 assessments with evidence of follow up	Overall A / A+ / A / A+ / A

Key Points
Merit-based recruitment is increasingly becoming the norm, and the harmonized salary scale has widely been adopted. All 10 beneficiary institutions in FGS and 9 in Puntland have gone through the reorganization and change management process with the exception of the Ministry of Finance in Puntland. All have new organization structures; new staffing plans; and change management plans, which they are now implementing. Implementation of TA activities in the various beneficiary institutions continues to face delays.
- Indicator 2.2: Improved operational, financial and human resources functions, will benefit the public service as a whole from increased capacity and improved functioning of the public sector both at the federal and regional level.
- Indicator 2.4: The monthly fiscal summaries and payroll reports are published on the Ministry of Finance website and increasing transparency in civil service pay. The Financial Governance Committee (FGC) regularly scrutinizes important government procurements and contracts, providing much need oversight and transparency.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A (new output, see Output 1 for former recommendations)
Recommendations
- It is unclear how the increased recruitments are helping the national and sub-national government in strengthening public sector institutions and ministries important for strengthening policy and the enabling environment. For example, Somalia does not have a Registrar of Companies, and regulation of key economic sectors such as telecoms and electricity remains under-staffed. Administrative structures and capacity for improving and enforcing the tax laws are often cited as significant barriers to revenue mobilisation.
- Going forward, the MPF should develop a plan for prioritising staffing needs of economic ministries and agencies than can maximise impact on the programme’s intended outcomes.
- FGC continues to be part-funded by the WB (its remit ended in April 2017 but is in the process of renewal) and it should to clarify its role with respect to its oversight of FMSs’ financial governance, especially concessions and contracts.

Output Title	Productivity of high priority sectors enhanced
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes from 40%

Indicator(s)	Milestones / (Dec 2016)	Progress
3.1. Operationalisation of the Somalia Business Catalytic Fund (SBCF) and Small and Medium Enterprises Facility (SMEF): / (i) grant applications received; and / (ii) awarded, by region.	Catalytic Fund operational - reporting to break down information as per indicator	Target partially met: / Catalytic Fund Operational / Total number of first round eligible grant applications received was 1750 of which Somaliland (752), Puntland (476), and South Somalia (522). / The award of grants has not commenced.	Overall B / A / C
3.2 Number of individuals receiving: (i) subsidized Business Development Service(BDS) or advice financed by the SMEF; and (ii) subsidized technical vocational education and training(TVET) or other forms of training financed by the SMEF	SMEF operational	Target partially met: / The SME Service Facility (SMEF) was operationalized in 2016. Provision of advisory services and TVET is slow, delayed in part by delay in award of grants.	Overall B
3.3 # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative)	0	A number consulting assignments by firms have been commissioned aimed at: 1) conducting a demand-supply market analysis for financial services in Somalia; 2) reviewing the regulatory environment relating to business registrations and drafting a company law, and; 3) providing analytical foundations to underpin the envisaged FGS renegotiation of the concession contract for Mogadishu port with Albayrak	A
3.4 Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site)	Key regulations drafted for Money Transfer Businesses (Customer Registration, AML/CFT/Operational); supervision of 2 MTBs	Target exceeded: / Key regulations drafted for Money Transfer Businesses / 12 MTBs receiving on or off-site supervision by joint CBS/Trusted Agent Supervision team	Overall A+
3.5. Contribution of ICT sector to public treasury (through taxes, and license fees)	$10million contribution to domestic revenues; ICT Licensing and taxation framework established	Target significantly missed : / $5.8 million contribution to domestic revenue / Licensing and taxation framework work on hold until passage of Communications Act	Overall C
3.6 Feasibility and preliminary design studies for specific urban investments completed. / (primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa.	3 (Mogadishu, Garowe, Hargeisa)	Target met with minor delays: / Feasibility studies were completed in February 2017. The design studies have been submitted for review and will be completed in April 2017.	Overall B

Key Points
- Overall, after two years in implementation the SCORE project has not made anticipated headway in stimulating private sector investments through matching grants. The matching grant component is stuck in the difficult political economy of Somalia and clan dynamics make direct decision making difficult. . The advisory facility, SMEF, has been operationalized after significant delays, but its activities and impact are unclear.
- Despite progress in the application rounds, decisions on winning applicants and actual disbursements has not advanced for up to 5 months due to undesirable interference and procedural delays. This is worrying given the fixed cost involved in retaining the fund manager and also WBG staff and consultants working on this.
- The most advanced assignment relating to diagnostic studies is the review of the regulatory environment relating to business registrations. Assessments identified gaps in that the business registration processes and identified an enabling law and fiscal budget allocations covering human and financial resources as critical to support operations of the business registration/registrar office on a sustainable basis. However, technical follow up, technical assistance in addressing the identified gaps and solutions remains slow and patchy.
- Good progress has been made in improving the integrity and supervision of the remittance sector. In order to strengthen the regulatory framework for the Money Transfer Operator (MTO) sector, the World Bank worked with the Central Bank of Somalia (CBS) to draft and enact MTO Operating Regulations based on the recently adopted AML/CFT Law. The World Bank also provided technical assistance for the drafting of the law. The regulations include provisions for customer due diligence, recordkeeping, ongoing monitoring, reporting, internal controls, consumer protection, and risk management. The Regulations apply to all registered and licensed MTOs operating in Somalia.
- The Trusted Agent supervises all licensed MTOs alongside the CBS. Two rounds of off-site examinations were conducted in 2016, pertaining each to a different regulation. In each round, the 12 licensed MTOs were examined. There needs to further assessment of actual impact of the measures on security, financial integrity and cost, and above all the risk of potential actions by international banks affecting flow of international remittance in to Somalia. .
- The establishment of a licensing and taxation framework for the ICT Sector has suffered delays due inordinate delays in passage of the proposed IT ACT.
- After some delays, feasibility and preliminary design studies were completed in February 2017 for the rehabilitation of roads in Mogadishu, roads and bridges in Garowe and waste management in Hargeisa. Given security concerns, the project had to restructure to enable UNOPS to be hired to manage the consultants handling the feasibility studies to provide additional security support for their work in the field. This contributed in part to the project delays at the beginning of the project. Since becoming effective, the project has been largely on track in delivering the planned outputs by February 2017.
Summary of responses to issues raised in previous annual reviews (where relevant)
- The output weighting was revised downwards, and the indicator was split into two to be able to capture the implementation of Somalia Business Catalytic Fund (SBCF) and SME Service Facility (SMEF).
- The indicator target was revised to focus on qualitative progress as ICT framework was unlikely by end of 2016 but kept to align with the MPF reporting framework.
Recommendations
- Going forward it will be important to revise the output statement to more accurately capture the programme’s private sector development objectives. Also, reassess the output indicators to more accurately measure the programme’s performance on improving the enabling environment and core economic institutions.
- Activities under this output are supply-driven and removed from the Somalia needs to improve its enabling environment by addressing the market and government failures in key sectors. There should be greater link and synergies between the PPD component under the SICRP and component of SCORE targeting the enabling environment to strengthen the demand side of SCORE activities.
- Need more communication about the state of enforcement and the benefit to the MTOs and the wider sector and to what extent the technical assistance helped strengthen the regulatory framework for the MTO sector.
Output Title	MPF is effectively managed
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / (Dec 2016)	Progress
4.1. Implementation of an effective MPF wide approach to risk management [revised] / i) # of annual Risk Management Group meetings / ii) # of quarterly reports and corresponding donor briefing sessions by Monitoring Agent / iii) Evidence of risk management response to issues raised	Quarterly RMMs; TPM fully operational with reports shared and discussed; MPF risk management matrix developed	Target met : / i) 6 Risk Management Group meetings in 2016 / ii) 4 quarterly reports shared with corresponding discussions in briefing session with Monitoring Agent / iii) Risk dashboard developed and updated at each RMG meeting in collaboration with donor focal points. Evidence of follow up actions taken shared in meetings.	Overall A
4.2. Disbursement and commitment rates: / i) including RCRF; / ii) excluding RCRF	Use Annual Review to set baseline	39% at end of 2016 / 37% excluding RCRF / Targets set for 2017 (see detail below)	Overall B
4.3. Transparency and reporting on project activities / i) Aide memoires made available to donors / ii) Publicly available documents are available on the MPF website / iii) # of annual consultative meetings with donors (Fund-, sector- or project-level)	Improvements evidenced by: improved access to aide memoires, participation in meetings, access to info on websites	Target partially met: / Aid memoires now shared with donors however not for all projects e.g. RCRF / Project documents available on the MPF website / Consultative Group meetings were held in addition to project specific briefing. Y	Overall B / B / A / B
4.4. MPF portfolio is gender and conflict sensitive / i) % of projects with WB gender flag / ii) % of projects for which updated analysis provided on the application of the gender flag (analysis, design, monitoring)	Evidence that gender and conflict issues effectively considered in programme design and implementation; including reporting on % with an active gender marker and % informed by conflict analysis	Target partially met / 75% of MPF projects (updated analysis on the gender flag application provided for all RE projects in 2016) / 33% informed by formal conflict analysis	Overall B

Key Points
- Overall, the flow of information remains patchy. There has been some progress on gender flagging of the MPF projects, although it is unclear as to why not all projects could be analysed from a gender perspectives. For a highly fragile country transitioning from decades of conflict, only a third of all the MPF projects are being informed by formal conflict analysis. As has already been explained in various sections of this AR, approach and understanding of the political economy is seen as a significant weakness of the MPF, resulting in number of key reform legislations being stuck in the political process.
- Indicator 4.2: Whilst the Bank has done well in committing the existing donor contributions to identified projects, actual spend, that reflects the volume of project activities, has been slow. Correspondingly, fewer outputs have been delivered by now than originally expected. Donors have raised concerns about the slower-than-expected disbursement profiles of several MPF projects because a slow disbursement profile raises criticism of the donors paying into the WB Trust Fund in advance of needs and locking development funds that could have been allocated to more urgent priorities. The Bank has provided its assessment about the future spend trajectory (see below) which is flat beyond 2017. .
- At the end of 2016, the MPF had disbursed 39% of paid in contributions by donors. Excluding the funds committed to and disbursed by the RCRF phase II, the disbursement rate drops slightly to 37%. On the basis of this baseline, the following targets were set for disbursements going forward:
  - Disbursements as % of paid in contributions: 2017 45%; 2018 50%; 2019 50%
  - Disbursements as % of signed project grants (signed >6 months prior to end of calendar year): 2017 55%; 2018 60%; 2019 50%.
- Indicator 4.3: There have been some improvements in flow of information, although attempts at engaging donors and coordinating efforts with other relevant programmes on the ground. Evidence of follow up actions on issues discussed at the meetings remains weak. The Bank is yet to share the report of the SCORE project review conducted in March 2017 or Aide Memoire of the RCRF Annual Review in October 2016.
- Indicator 4.4: Information on if and how political economy analysis and conflict analysis are used to inform the MPF’s project design and implementation at best remains patchy. Currently, 75% of the MPF projects have a gender flag but there is not much information available on how the gender analysis is used to identify and define possible entry points for deeper engagement on gender issues.
- Conflict analysis is a formal component of only a third of MPF projects. Although the political economy analysis is an integral aspect of many of projects, evidence on effectiveness of such analysis in mitigating political economy risk to the MPF projects and its activities is not very strong, given that a number of policy initiatives, initiated with the MPF’s support, are stuck in the political and legislative process.
- The donors have constantly urged the Bank to improve coordination with programmes in the economic development space funded outside the MPF. Greater collaboration with other development programmes provides an opportunity to expand the outreach and impact of MPF programmes. Opportunities to leverage other programmes should receive greater attention in implementation and reporting. As per the quarterly report, too often MPF programmes are implemented in isolation, even when the implementation partners on the ground are simultaneously implementing related efforts through other funding sources.
Summary of responses to issues raised in previous annual reviews (where relevant)
The Aide Memoires are now being shared with the donors, the bi-annual reports are shared but not well in advance of meetings, and the report is not sufficiently comprehensive. An improvement from the last report is that a narrative brief text is now accompanying the matrixes.
Recommendations
- Revise the logframe to set clearly defined targets missing for many of the indicators.
- To continue to engage with the WB on their bi-annual reporting which needs to elaborate in more details on what lessons are being learnt and what adjustments are being made to better tackle the political economy challenges, what measures and adjustments are needed to tackle the challenges.
- The WB to explore ways to reduce any delays in the future: e.g. by providing appropriate technical assistance to government executors to establish the project management arrangements needed and or providing more hands on support to procurement procedures.
- Encourage the WB that the projects are implemented within the set timelines, providing value for money for the costs of running the project implementation units.
- It would be helpful to have some specific examples of how the MPF projects mainstream focus on reducing the gender gaps and results already achieved and/or expected.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Financial performance
To date, donors have disbursed a total of $184.19 million to the World Bank. This represents a total disbursement equivalent to 84% of initial commitments. The UK accounts for $62.34 million. More details are available in Annex Two.
DFID will monitor this balance before making further disbursements, in line with the Smart Guide on World Bank Trust Funds, to ensure that no payment in advance of need is made.
Overall actual spend on project activities remain slow at 52% of the total funds committed, although spend has picked up significantly since last year following approval of a number of larger projects e.g. Recurrent Cost and Reforms Financing (RCRF) II and Capacity Injection Project (CIP). Speed of spend in some other projects e.g. Somali Core Economic Institutions and Opportunities (SCORE) project and Information and Communication Technology (ICT) sector development remain slow and constrained by difficult political economy and concerns about potential reputational risks.
Key cost drivers and performance
The main cost drivers for the programme remain the same as last review i.e. staff costs, security, travel, and procurement. DFID Somalia and the Bank have sought to contain these costs, for example by developing a harmonised approach to pay of advisers placed within externally funded projects.
VfM performance compared to the original VfM proposition in the business case
Overall, the Fund continues to represent good VfM, despite the lower-than-anticipated delivery of the intended outcomes. The review judges that the Fund has initiated activities in a range of areas, some of which if consolidated further, hold good prospects to deliver the intended outcomes. Interventions in some other areas, e.g. stronger public finance management, revenue mobilisation, and civil services reforms will deliver economic benefits to Somalia well beyond the life of the Fund.
In addition, despite the procedural and management challenges in the Bank’s operating and delivery model, the Fund remains the strongest vehicle available in Somalia to deliver on the UK’s economic development objectives. This is because of (i) political reasons e.g. the Bank’s convening power across range of donors and its credibility with the host government and (ii) technical reasons e.g. the Bank’s management bandwidth, thought leadership and technical expertise that comes with its presence and track record of working in challenging environment. Equally, the robust fiduciary framework of the Fund as well as ability for pool funding offset the procedural challenges highlighted in this review and which will be addressed going forward.
Limited availability of reliable and timely data, which is gradually improving with the Fund’s efforts, and the expansive focus of the Fund make it challenging to do a comprehensive and meaningful assessment of the Fund’s VfM on standard lines of Economy, Efficiency and Effectiveness. However, available quantitative and qualitative information demonstrates a reasonable VfM of the Fund. For example;-
Economy:
The Fund’s management cost of roughly 6.5% is significantly lower than the management cost of other programmes.
 Efficiency
- Whilst a number of outputs are below target, efficiency in delivery of outputs measured in terms of quality and performance is mixed. For example, in components relating to civil service reforms and public finance management, outputs have helped deliver intended objectives e.g. transparency in civil service recruitment, improving share of women recruits, tax harmonisation etc. In some other areas, e.g. in the SCORE projects outputs seem less efficient by the same standard.
- The Fund’s PFM component is designed to improve transparency, competition and integrity of the government procurement processes. Select government procurements are scrutinised by the Financial Governance Committee, which is cancelling ineffective contracts (one worth $142m alone) and revising inefficient ones. The FGC will quantify their impact in this area going forward.
Effectiveness
The programme has done well in progressing the state-building agenda, which is commendable given Somalia, is starting from a very low base. The impact of the state building measures will take time to be felt on economic development and will continue well beyond the life of the MPF. The ideal measure of economy is a calculation of unit costs. However, the breadth of the Fund’s focus and its expansive activities compound the challenge of aggregating the fund’s impact and hence developing meaningful unit cost indicator to represent the fund’s portfolio, especially given the lack of meaningful comparators.
In recent conversations with the WB, they have committed to work on developing a VfM strategy for the MPF. This is work in progress and is expected to take shape over the next three months. We plan to use this Annual Review to have discussions with the Bank to improve the holistic value for money the MPF delivers for DFID’s investment.
Quality of financial management
The quality of fiduciary management by the administrator is judged to be of a high standard. The WBG’s financial policy and standards apply to spending through the Fund. Where spending is done through the Recipient Executed projects, those are subject to stringent fiduciary risk control measures designed and applied for the Fund projects. There are also wider efforts through the PFM projects under the Fund to enhance transparency and integrity of government spending.
The MPF’s slow spending rate remains a concern and is in part due to Somalia’s difficult working environment. This is being gradually addressed through improved monitoring. The Bank is planning to initiate a process of reprioritisation with a view to scale back funding to projects where absorption is slow and to reallocate funds saved to projects with greater needs. The process will involve all the donors of the MPF and the Somali Government. DFID will be a key player in this process and will engage with the Bank with a view to ensure that the UK’s strategic interests are included. To ensure there is no payment in advance of need, the DFID programme team continuously reviews the level of funds uncommitted prior to making disbursements by reviewing financial reporting and the allocation of funds as outlined on the World Bank’s donor portal.
There has been a significant downwards fluctuation in the value of the pound in 2016. However, this is a multi-donor fund with contributions coming in six different currencies, which provides some degree of hedging. But the fund is relatively more exposed to fluctuations in Euro and the GBP that account for more than 75% of the fund’s total funding. The World Bank will need to carefully manage the impact of exchange rate fluctuations of these two currencies and adjust the scale of project activities accordingly. Any decisions made in this regard will need to be agreed and approved by DFID and other donors.
Date of last narrative financial report	1st June 2017 (from the WB client connect)
Date of last audited annual statement	September 30 2016

E: RISK
Overall risk rating: Major
Overview of programme risk
The programme is assessed as “major” risk and high impact. The programme is within DFID’s risk appetite for the portfolio in Somalia and is justified by the anticipated rewards. We have consciously designed and applied checks and balances, commended by DFID’s Internal Audit Department, to manage risks within an acceptable range. The risks of international inaction in Somalia are even higher. If Somalia fails to sustain its positive transition, it could backslide into conflict and fragility.
The programme aims to deliver transformational change by establishing core economic institutions, administration, and policy and regulations, which are largely non-existent in Somalia. The programme takes an integrated approach that aims to tackle constraints relating to knowledge, capacity, finances, and infrastructure, all under one single programme. Although such an approach has been tested elsewhere (e.g. in Afghanistan), this can be risky given Somalia’s difficult political economy, absence of institutions and very low resource base.
This risk is, however, worth taking because, despite delays, the programme will most likely deliver the anticipated headline results, and it offers the best possible opportunity to tackle the economy-wide constraints. Whether or not it is successful in bringing about a transformational change will depend, amongst other things, on (a) the will and ability of the political leadership in progressing the political settlement, and (b) alignment of incentives of the private and public sector in tackling entrenched interests with a view to support Somalia’s economic reconstruction. This is harder to predict.
The programme has a number of operational risks linked to:-
- The operating environment (conflict and security)
- The difficult and complex political economy, including a fragile political settlement
- Weak institutions, capacity and integrity of the public as well as private sector
There are a number of components under the MPF, which are Bank executed, or which could be executed at the local level, bypassing government e.g. work with the private sector. The portfolio is also geographically dispersed, meaning that if the security situation deteriorates in the South, activities planned in the North could still go on as planned.
DFID revised the Risk Matrix in September 2016 to bringing it in line with the new risk approach. The risk continues to be reviewed systematically on a regular basis.
DFID is an active member of the Multi-Partner Risk Working Group that is led by the WB and the UN. This meets on a quarterly basis, and identifies high-level risks to the WB MPF, UN Fund, and now the AFDB Somalia Infrastructure Fund. In addition, it is within the mandate of the Third Party Monitoring Agent to monitor and escalate risks to the WB when they arise.
Outstanding actions from risk assessment
Overall, the risk assessment in the business case remains a good summary of the main risks faced by the programme. Risks continue to be managed in line with the Risk Matrix. There are no actions outstanding.
F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
The World Bank has made varied progress, which may be commendable in a context of political fragility, flux, and ongoing security challenges. The Bank has also done a tremendous job in designing, developing and securing necessary approvals for a range of projects that are highly relevant to the strategic objectives of the fund and economic development priorities of the Somali Government.
The overall progress in implementation of the projects and their anticipated results is slower than anticipated. Slow progress in some areas could be partly due to an optimism bias on the part of both the World Bank (WB) and partners, including the Federal Government, about what could realistically be achieved by this point.
Performance of partnership(s)
The World Bank uses the bi-annual and the annual progress report as a reporting tool to the Donors. The MPF progress report provides information and updates on the fund’s performance, results, and financial overview for the fund, along with a breakdown of disbursements, donor commitments, and subsequent contributions. WB provides a quarterly implementation status report (ISR) for individual projects; however, the ISR reports could be clearer.
The working relationship with the World Bank has been cordial and collaborative, although structured engagements with the Bank’s task team leaders and the operations manager could be more focussed, and frequent. Important Consultative Group Meetings could be planned at least a week in advance. It is recognised that the WB country team has a difficult role in managing a large number of donors with different interests who change staff frequently and should be supported in delivering in this context, with capacity constraints discussed openly with donors.
Donors have also from time to time raised concerns about delay in sharing of Aide Memoires and follow up actions on discussions at the Consultative Group meetings. The practice of involving donors in strategic and important project related meetings with the Somali Government counterparts is not consistent across the Fund’s projects, and this leads to an atmosphere of lack of trust and shared understanding of the issues and challenges. Going forward, the Bank could involve donors in strategic interactions with the government.
Asset monitoring and control
The programme assets are owned by the trust fund and it would be the responsibility of the fund administrator to ensure that they keep a record to be able to track the programme assets at any point in time and should do so by keeping an inventory. The WB follows standard procedures in terms of asset management for the MPF. The responsibility of asset verification is delegated to the Third Party Monitoring agent, who is located on the ground and have a better visibility of the assets than the Bank. The agent’s reports are shared and discussed with donors.

G: CONDITIONALITY
Update on partnership principles (if relevant)
The April 2017 update of the Partnership Principles flagged no significant change in our assessment or the way we work through partners with governments (FGS and Somaliland). DFID Somalia uses the partnership principles in consideration of how closely we work with government. We also use them to inform our choice of aid modality particularly the extent to which we align our assistance with Government strategies and plans, and use Government financial systems.
H: MONITORING & EVALUATION
Evidence and evaluation
The programme will continue to rely on annual reviews to evaluate the effectiveness of all the projects and progress towards impact, and the need for adjustments to the log frame indictors. Further projects reviews, coordinated by the World Bank, will happen to allow the opportunity to adapt in real time delivery plans and milestones to emerging opportunities and risk. These reviews will be informed by a continuous scanning of the context through regular political economy analysis and will be coordinated with updates to the risk matrix and mitigation strategies. We plan to have a joint donor review of the MPF early next year.
Monitoring progress throughout the review period
DFID directly engages with the bank through quarterly reviews and ad-hoc meetings. In addition, efforts have been made to meet with FGS and federal member state who are implementing the projects in Nairobi, and where security allows in Somalia. Systematic reporting requirements are also in place to monitor financial management, quality, progress and risks.
MPF uses a management consulting and monitoring agent to provide external third party monitoring and assurance to complement the Bank’s internal supervision of projects. The agent is directed to report on how MPF funds are executed by the Somali authorities, confirm utilization for the purposes specified in MPF grant agreements, and monitors the flow of MPF funds from the World Bank through the government systems. The monitoring agent also advises the World Bank on trends, developments, and emerging issues that relate to the MPF portfolio.
Strategic advice is provided in quarterly and other reports as well as through meetings with the Bank teams, government counterparts, and donors. The scope of their advice is driven by developments in the portfolio, and thus will grow with the MPF. The agent’s knowledge of the Somali authorities’ operations, as well as involvement in multiple MPF projects, enables them to identify, analyse, and advise on several cross-cutting issues.
Process of Review
This Annual Review (AR) was done in-house, led by the SRO and programme management team and includes detailed inputs from the Lead Advisers of the main MPF projects, including the Leader of the Governance Team in DFID Somalia. The AR also reflects development partners’ joint feedback to the Bank in March 2017 on the Bank’s most recent six-monthly progress report to the partners. The AR also reflects information gathered through the interview with the Bank’s MPF Manager, Media and Communications Consultant, and UN-WB Aid Coordinator who met DFID’s programme team for the AR on behalf the Bank’s Task Team Leaders for the MPF projects. The AR also reflects key recommendations of DFID’s Quality Assurance Unit (QAU) report on the Business Case for next phase of DFID funding to the MPF. The AR has been quality assured by the Nairobi cross-office Accountability and Results Team (ART).

Annex One: Summary of Progress against Annual Review 15/16 recommendations

Recommendations	Actions/ Progress
DFID Management:
Reviewing the log frame, with a view to achieving a better balance between quantitative and qualitative indicators that would enable it to better capture the breadth of activities supported under the MPF and directly delivered by the World Bank and contractors. Should also be linked to the programme theory of change	Already reviewed the log frame and changes have been contextualised, explained, and placed on record.
Risks continue to be systematically reviewed, recorded, and managed regularly. The next review should include a specific consideration of the IMF Staff Monitored Programme and ensure that the risk analysis is fully aligned with DFID’s new risk approach.	Ongoing. The Risk Matrix was revised in September 2016 to bringing it in line with the new risk approach.
DFID to explore with the World Bank how to increase gender sensitivity within the MPF and move to a target of 100% of projects (rather than 70%) being gender informed according to the WB’s (global) gender flag system.	On progress- MPF projects activities are reviewed and assessed by the World Bank to systematically consider and address gender inequalities in: 1) the underlying analysis, 2) in the actions proposed, and/or 3) in monitoring and evaluation arrangements. If a positive response is recorded in at least two of these three dimensions, the operation is flagged as gender-informed. Not all dimensions may be relevant for a specific project. Hence, the goal is not to see 100% application of the gender flag across the portfolio or across all three dimensions. Rather, the application of the gender flag system is designed to facilitate a thoughtful consideration of how to integrate a greater understanding of gender as appropriate, as well as to identify entry points for deeper engagement on gender issues
DFID and the World Bank should pick up the work on developing a VfM strategy for the MPF and consider if the VfM measures suggested in the Business Case can be operationalised to better measure and monitor VfM.	The team will continue our work to better capture the VfM of the SERS programme and will use the Business Case for the next phase to refresh the VfM framework for SERS. We have already had conversations with the WB on this and expect to see improved reporting on this in the six-monthly MPF Progress Reports.
Implementing Partner:
WB to monitor adherence to hiring practice and the inclusion of gender and inclusion quotas for new recruits paid for by the Fund, to support the formation of an effective and representative civil service. Data on new recruits to be disaggregated by gender.	Disaggregated by gender is being implemented. Most projects have gender targets in there results framework. E.g. SCORE, CIP, SFF LD
Reporting and Communications: The World Bank should continue to work with donors to strengthen communications about the MPF - in particular at the project level. Specific actions should include ensuring that regular missions take place on all projects. The World Bank should ensure that communication infrastructure work supports regional governments to connect with the Federal Government and each other.	Communication on mission, meeting, and reviews is now communicated on monthly bases.
Coordination: The World Bank and donor partners should explore how to further strengthen coordination to ensure that MPF projects are not duplicating other donor-funded activity and that an effective division of labour exists. For infrastructure projects, this should include pre-pipeline consultation.	Ongoing- we use the MPF donor consultative group meetings to discuss pipeline project to avoid duplication.
Flexibility and Risk Management: The World Bank should review ways to increase the flexibility and adaptability of the MPF to the evolving context and government priorities, and ways of implementing lessons learned as the international community gain experience of working with the Federal Government and in Somalia. This could include assessing cost and feasibility of increasing presence in country in order to establish more dialogue that is continuous with key actors and donor-government engagement and partnership (this is likely to be linked to longer term prospects for pre-arrears clearance, linked to good performance against the IMF SMP, creating a case for an IDA allocation).	Ongoing - All projects benefit from extensive preparation phases where task teams work with the government, the PSG working groups and other partners on project objectives and design. This includes scrutiny of the fiduciary and procurement capabilities required for each project, on which the fund flow designs and procurement plans are developed. This serves as a critical up-stream function of risk management at project level.
The World Bank could explore some of the reasons for the lengthier time lags between project approval, “effectiveness” and implementation which are contributing to the lower than planned execution rate. The WB should ensure that lessons are learned on how to reduce these in future.	Ongoing – we continue to use the MPF consultative group meetings, programme cluster meetings, and individual project briefings to raise concerns about delays; including using donor pre-meetings to share concerns and agree a joint approach/division of labour as appropriate. We also use our engagement in supervision missions and project reviews to raise concerns and push for concerted action plans to accelerate progress in key areas.
The range of active projects has increased and is now more complex in nature, the World Bank and partners should reflect on whether the delivery approach needs to be adjusted e.g. through increasing “on the ground” and “hands on” approaches to Government capacity building.	The discussion is ongoing and the Bank is also planning to initiate a process of reprioritisation of projects. All donors will be involved in the process.

Annex Two: Financial Overview for Somalia Multi Partner Fund
(Source WB Client Connect)

Table 1: Donor disbursement to the World Bank
Donor Name	Planned Contribution (USD)	Disbursed contribution (USD)	Contribution disbursed to date (%)
United Kingdom	63.86	62.34	97.62
Denmark	12.43	6.68	53.74
European Union	76.69	59.5	77.59
Italy	2.17	2.17	100.00
Norway	19.03	10.93	57.44
State- and Peace building trust	8	8	100.00
Sweden	21.85	21.85	100.00
Switzerland	8.2	8.2	100.00
United States of America	2.25	2.25	100.00
Finland	4.41	2.27	51.47
Total	218.89	184.19	84.15

Table 2: Summary of Trust Fund Activities
Grant Type	TF - Name	Grant Amount	Disbursement amount in USD	Undisbursed Commitments Amount in USD
Bank Executed	Management and Administration	7,103,621.59	3,285,154.22	3,818,467.37
Bank Executed	Supervision of Recurrent Costs and Reform Financing Project	175,901.02	172,679.02	3,222.00
Bank Executed	Somalia Capacity Injection	852,425.00	690,597.87	161,827.13
Bank Executed	Somalia Public Financial Management Reform Project	756,500.00	565,625.62	190,874.38
Bank Executed	Bank Preparation and Supervision of the Somalia Urban Operations	607,829.00	536,042.93	71,786.07
Bank Executed	Somalia ICT Sector Support	375,000.00	194,694.75	180,305.25
Bank Executed	Somalia Petroleum Sector Inclusive Development - Capacity Building and Technical Assistance	2,200,000.00	1,839,037.83	360,962.17
Bank Executed	Somalia Petroleum Sector Inclusive Development - Consultative Meetings	800,000.00	508,999.88	291,000.12
Bank Executed	Somalia Financial Governance (TA)	2,000,000.00	1,349,122.85	650,877.15
Bank Executed	Second Somalia PFM Capacity Strengthening Project	1,000,000.00	39,612.95	960,387.05
Bank Executed	Somalia Power Sector Master Plan Development Project	950,000.00	179,300.53	770,699.47
Bank Executed	Monitoring Agent - Somalia MPF	5,484,033.00	3,910,959.87	1,573,073.13
Bank Executed	Strengthening Pastoral and Agropastoral Resilience in Somalia (SPARS)	150,000.00	111,065.90	38,934.10
Bank Executed	SCORE Preparation/Supervision Grant	2,060,000.00	1,679,725.43	380,274.57
Bank Executed	Somaliland Civil Service Reform Project - BE	420,244.00	314,600.01	105,643.99
Bank Executed	Somalia Recurrent Cost & Reform Financing Project - Supervision	500,000.00	382,895.07	117,104.93
Bank Executed	SFF-LD Supervision	500,000.00	140,215.80	359,784.20
Bank Executed	Somalia Knowledge for Results	1,200,000.00	-	1,200,000.00
Bank Executed	Somalia Country Economic Memorandum	200,000.00	87,566.66	112,433.34
Bank Executed	Poverty and Distributional Analysis	1,685,000.00	183,219.16	1,501,780.84
Bank Executed	Public Expenditure Reviews	150,000.00	79,527.17	70,472.83
Bank Executed	Fiscal Federalism Analytics	150,000.00	50,484.32	99,515.68
Bank Executed	Macro-Fiscal Analysis	350,000.00	140,338.60	209,661.40
Bank Executed	Programmatic approach to Somalia ESW/TA	1,000,000.00	110,485.84	889,514.16
Recipient Executed	Somalia Recurrent Cost and Reform Financing Project	14,816,543.95	14,816,543.95	-
Recipient Executed	Information and Communication Technology Sector Support Project (Phase 2)	5,000,000.00	3,827,031.93	1,172,968.07
Recipient Executed	Public Financial Management Capacity Strengthening Project II	16,000,000.00	6,120,641.07	9,879,358.93
Recipient Executed	Somaliland Public Financial Management Capacity Strengthening Project	4,000,000.00	676,664.00	3,323,336.00
Recipient Executed	Somalia Capacity Injection Project (Recipient Executed)	10,000,000.00	4,610,356.36	5,389,643.64
Recipient Executed	Somalia Information and Communication Technology Sector Support Project - Phase 2	2,000,000.00	239,403.30	1,760,596.70
Recipient Executed	Somalia Recurrent Costs and Reform Financing Project Phase II	39,000,000.00	31,181,341.79	7,818,658.21
Recipient Executed	Somali Core Economic Institutions and Opportunities Project - Phase 1	3,300,000.00	1,091,638.83	2,208,361.17
Recipient Executed	Somali Core Economic Institutions and Opportunities Project- Phase - I	1,500,000.00	350,437.78	1,149,562.22
Recipient Executed	Somali Core Economic Institutions and Opportunities Project - Phase I (BE on Behalf of Recipient)	6,000,000.00	2,424,108.42	3,575,891.58
Recipient Executed	Somali Urban Investment Project Recipient Executed Activities in Somaliland	700,000.00	200,000.00	500,000.00
Recipient Executed	Somali Core Economic Institutions and Opportunities Project Phase I - BE on Behalf of Government	3,000,000.00	-	3,000,000.00
Recipient Executed	Somalia - Special Financing Facility for Local Development Project	6,000,000.00	770,475.40	5,229,524.60
Recipient Executed	Somaliland Urban Investment Project BE on behalf of Recipient	329,000.00	243,574.61	85,425.39
Recipient Executed	Somali Urban Investment Planning Project	1,450,000.00	607,237.42	842,762.58
Recipient Executed	Somali Urban Investment Planning Project (BE on Behalf of Recipient)	3,521,000.00	1,919,448.55	1,601,551.45
Recipient Executed	Supporting Remittance Flows to Somalia	3,134,000.00	1,083,605.35	2,050,394.65
Recipient Executed	Somaliland Civil Service Reform Project	2,500,000.00	250,000.00	2,250,000.00
		152,921,097.56	86,964,461.04	65,956,636.52

Annex Three: Log frame revisions

Summary of changes
Impact- Indicators was changed / 1.2 Real GDP growth per annum % / 1.3 Domestic revenue as a % of GDP
Outcome / Outcome indicator 2 ‘number of direct jobs created in enterprises supported by the SCORE project’. was realigned with the project plans. / Outcome indicator 3 ‘Annual increase of intergovernmental transfers to sub-national governments’ was removed and replaced with ‘Private Sector investment mobilised (committed as co-payment) by Catalytic fund recipients’. Previously output indicator 2.1
Output 1 was split in 2 new ones and output weightings changed. / Output indicator 1.1 adjusted indicator - to ‘% of annual civil service (non-security sector) wage bill financed by: (i) government; (ii) RCRF. Primary expenditure variance’ was dropped as its now more effectively monitored through IMF SMP. / Output indicator 1.2 new indicator - Regularity of salary payments for civil service (non-security sector): (i)average days between payments during year (ii) # of months of civil service salary payments outstanding at the end of year / Output indicator 1.3 new indicator: Non-salary recurrent costs eligible for RCRF funding: (i) $; and (ii) % execution of annual budget (NSRC) / Output indicator 1.4 adjusted indicator Implementation of intergovernmental transfers to regional member states: (i) number of RMS receiving transfer; (ii) % increase in total volume of transfers compared to previous years outturn’ / Output Indicator 1.5 new indicator- Improved capacity as evidenced by implementation of TA activities in relevant areas (revenue, treasury management, procurement etc.) FGS, member states and SL. Indicator included to allow DFID to make judgement in progress on implementing the more qualitative aspects of revenue and PFM reform support
Output 2 New output - Strengthened public sector management capacity / Output Indicator 2. 1 previously output indicator 1.2. / Output Indicator 2. 2 Ministries/agencies with operational HR functions / Output Indicator 2. 3 new indicator Improved civil service management functions / Output Indicator 2. 4 previously output indicator 1.3.
Output 3 – previously Output 2 / Output indicator 3.1 was revised: from ‘Private sector investment generated through co-payment by Catalytic Fund recipients’ to Operationalisation of the SBCF and SMEF (i) grant applications received; and (ii) awarded, by region / Output indicator 3.2 Number of individuals receiving: (i) subsidized BDS or advice financed by the SMEF; and (ii) subsidized TVET or other forms of training financed by the SMEF / Output indicator 3.3: # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative) / Output indicator 3.4: previously indicator 2.4 adjusted indicator Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site) / Output indicator 3.5: Previously output indicator 2.2 / Output indicator 3.6: Previously output indicator 2.3
Output 4- previously output 3 / Output indicator 4.1 was revised: from ‘Enhanced risk management framework for MPF is effectively implemented to ‘Implementation of an effective MPF wide approach to risk management’ to reflect an evolving approach to risk management. / Output indicator 4.2 new indicator: ‘Disbursement and commitment rates: (i) including RCRF; (ii) excluding RCRF / Output indicator 4.3: ‘Transparency and reporting on project activities’