Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Central African Republic Humanitarian Recovery Programme 2016-2019
Programme Value: £40,000,000		Review Date: 30 June 2017
Programme Code: 205286	Start Date: 30/06/2016	End Date: 31/03/2019

Summary of Programme Performance
Year	2017
Programme Score	A
Risk Rating	Severe

Summary of progress and lessons learnt

This is the first Annual Review of the Central African Republic Humanitarian Recovery Programme. The programme is on track to reach its key results and outcomes. It contributes to three of the Single Departmental Plan results: humanitarian (# of people reached with humanitarian assistance - food aid, cash and voucher transfers - through DFID support); water, sanitation and hygiene (# of people with sustainable access to clean water and/or sanitation through DFID support); and nutrition (# of children under 5, women (of childbearing age) and adolescent girls reached by DFID through nutrition-related interventions).

The design of the programme, and its risks and assumptions, continue to be relevant to the context in the Central African Republic (CAR), which has seen an increase in humanitarian needs in recent months. DFID’s funding portfolio in CAR addresses both urgent response and more protracted humanitarian needs, while the internal contingency facility allows DFID to meet new spikes in need. The CAR crisis and CAR refugees continue to be severely underfunded by the international community. DFID plays an appropriate role influencing the response in both these crises, in complementarity to other donors such as the United States and the EU Civil Protection and Humanitarian Aid Operations (ECHO).

Lessons learned and recommendations from the Programme Completion Review (PCR) and Annual Reviews of the previous CAR Business Case have been considered in the design of the programme, and in this Annual Review.

Summary of recommendations for the next year

- Accountability to affected populations: In line with the Grand Bargain commitment on the participation revolution and the recommendations of the Evaluation of the Inter-Agency Humanitarian Response to the Crisis in the Central African Republic[1], and building on the World Food Programme’s (WFP’s) work in Cameroon, DFID will seek to strengthen feedback and complaints mechanisms (including regarding exclusion), and encourage learning and shared analysis between partners across the response.
  [1] http://www.interagencystandingcommittee.org/system/files/print_final.pdf
- Refugee compacts: Take forward discussions with World Bank on potential engagement on refugee integration in Cameroon, and with UNHCR on the development of a viable livelihoods strategy to underpin future World Bank involvement.
- Logical framework: the overall logical framework should be simplified, and milestones should be corrected and/or updated in light of DFID’s contribution to multi-donor programmes, while maintaining more detailed indicators for each component.
- Progress on Healthcare - DFID to request MENTOR to assess the capacity of the consortium to respond to emergency healthcare needs, given the changes in the context and capacity of other healthcare actors and the fact targets have not been met.
- Food security and nutrition in refugee operations: DFID to engage with WFP on aligning strategy and targets with available resources; and to monitor the impact of the reduction in food rations and cash transfer values.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5457664.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-205286/documents

This Annual Review has been completed by members of the Sahel and West Africa, Humanitarian and Resilience team in the Africa Regional Department, and is informed by quarterly and interim reporting from partners as well as drawing on programme visits carried out in CAR and Cameroon.

Outline of programme

The CAR Humanitarian and Recovery Programme (CHURP) addresses urgent life-saving and protracted needs of conflict-affected populations in CAR and refugees in Cameroon who have fled violent conflict since December 2013. Humanitarian needs are widespread and humanitarian aid remains crucial to address urgent needs among people affected by violence and returnees, and to help stabilise livelihoods to lay the bases for a transition towards early recovery. Assistance is delivered across all sectors, with a focus on healthcare, food security and livelihoods. The programme was approved in 2016 and provides support totalling £40 million, with a further £20 million as internal contingency facility.

Agencies - CAR response	Description
Food and Agriculture Organisation (FAO)	Livelihoods assistance
International Committee of the Red-Cross (ICRC)	Emergency and protracted assistance and protection
CAR Humanitarian Fund (CHF)	Emergency multi-sector assistance
MENTOR Initiative-led consortium*	Basic healthcare
Solidarités International (SI)-led consortium**	Livelihoods and protection support
Agencies - CAR refugees
World Food Programme (WFP) Cameroon	Food and nutrition support
UN High Commissioner for Refugees (UNHCR) Cameroon	Emergency multi-sector assistance
M&E

*NGO consortium led by MENTOR Initiative providing healthcare.
**NGO consortium led by Solidarités International providing livelihoods and protection assistance. This contract was issued in May 2017 and will be reviewed in the 2018 Annual Review.

Based on progress against agreed indicators we assess that the programme is on track to achieving its outcomes.
Expected results

Outcome 1: Address essential humanitarian needs in CAR and among CAR refugees. The target is to reach 763,506 people in CAR and 205,310 refugees with DFID humanitarian assistance by June 2017.

DFID estimates that over this review period, 1,847,123 beneficiaries have been reached (1,570,163 in CAR and 276,960 in Cameroon.

DFID calculates its beneficiary reach as a proportion of funding against the overall appeal (ICRC) or against all funds received that year (CHF). By the end of 2016, DFID’s contribution to ICRC represented 11.3% against the total budget: we have therefore considered that 11.3% of beneficiaries reported in the ICRC Annual Report were DFID-attributable. In 2016, DFID’s contribution to the CHF represented 26.7% of the total budget and we have therefore calculated our beneficiary reach as a 26.7% proportion of the CHF total reported against the 2016 Annual Report. It is important to note that the CHF’s coverage is country-wide and multisector, and some beneficiaries will require assistance from more than one intervention, leading to possible double counting. We will engage with the CHF on how to minimise this. DFID’s contribution to FAO is for a project starting in January 2017 with implementation over 28 months: achievements reported cover the period from 1 January to 31 May 2017. MENTOR’s programme is being reviewed for 7 months in this Annual Review. DFID provides funding towards UNHCR and WFP’s annual appeals in Cameroon. In the case of WFP the period covered is 11 months up to 31 May 2017, with a percentage contribution of 13.9%. For UNHCR, the period covered is 2016, with a contribution of 29.9%.

Outcome 2: Better co-ordination and coherence of the humanitarian, development and UN system in CAR. The target is that the amount of EU Trust Fund and International Financial Institutions (IFI) contributions to health, nutrition, livelihoods and protection meets or exceeds Humanitarian Country Team (HCT) humanitarian allocations to these sectors by the end of the programme.

Coordination and coherence across the humanitarian, early recovery and development spectrum have improved, with closer consultation between actors. The Humanitarian Response Plan (HRP) was drafted to ensure a division of tasks with the National Plan for Recovery and Consolidation of Peace (RCPCA) developed in line with “New Deal” principles for engagement with fragile and conflict-affected states. The move to multi-year humanitarian programming with a three-year HRP was meant to enhance this coherence. The two plans were launched in November 2016, eliciting pledges of €2 billion for recovery and humanitarian support. The EU Trust Fund, known as the Bekou Fund, has so far mobilised €222 million and contributes to the three priority pillars of the RCPCA. In comparison, the HRP has so far received $120 million (30% of requirements). Further engagement is needed to make sure that pledges are translated into financial commitments, to track actual disbursements and to ensure strategies and policy choices remain adapted to the changing context and needs.

Context in which UK support is provided

CAR has been plagued by activity by armed groups, conflict, coups and failed disarmament processes throughout its post-independence period. At the peak of the 2013-15 crisis, 900,000 people were displaced within and outside the country. The number internally displaced had reduced to just over 400,000 by early 2017 before climbing back to 500,000 in May 2017. Due to conflict, insecurity and loss of agricultural inputs, agricultural production shrank considerably causing food deficits: half the population remains food insecure, though there has been a gradual improvement in the acuteness of food insecurity, and a reduction in the population in Integrated Food Security Phase Classification (IPC) Phase 4. Healthcare remains primarily delivered by Non-Governmental Organisations (NGOs).
## Cameroon hosts 259,145 registered Central African refugees in the rural regions of East, Adamawa and North, and 18,991 in urban areas. This includes an earlier wave of displacement from 2004, and newer arrivals from the recent crisis in 2013. Refugees are relatively well integrated: only 30% live in camps, across 7 sites where they continue to depend on humanitarian assistance. The remaining 70% are settled within more than 300 villages within host communities. However, more than 20% of them remain socio-economically vulnerable. The majority of refugees are of Peul ethnicity, mostly Mbororo cattle herders, although a significant number are traders of urban origin. Refugees fleeing to Cameroon spent long periods in the bush before arriving in their place of asylum: in early 2014 global acute malnutrition rates exceeded 30-40% on some sites in Cameroon and severe acute malnutrition rates of 15%. These rates have since stabilised, with GAM rates reducing from 9.6% in 2015 to 7.3% in 2016.[2] Conditions in CAR have not improved sufficiently to prompt large scale refugee returns. In addition to insecurity and trauma, illegal occupation of houses and businesses are a significant barrier to return. The CAR Refugee Response in Cameroon is severely underfunded: UNHCR is currently funded at 5% of its annual requirement while WFP funding is at 43%.
[2] UNHCR Standardised Expanded Nutrition Surveys
## DFID Funding

The UK is CAR’s third largest humanitarian donor in 2017[3]. In 2016, DFID approved a multi-year business case that is providing £40 million in assistance to CAR populations and refugees from 2016 until March 2019, with a £20 million contingency reserve remaining to address surges in needs. This is the first Annual Review under the newly approved business case.
[3] https://fts.unocha.org/countries/43/summary/2017

Within CAR, funding has been provided to 5 partners: the CAR Humanitarian Fund (CHF) and ICRC to address urgent humanitarian gaps; FAO for livelihoods recovery through support to agricultural production; and two NGO consortia to cover protracted needs - one on health (Lead: MENTOR Initiative; Members: International Medical Corps (IMC), Cordaid, Oxfam Intermón) and one on livelihoods (Lead: Solidarités International; Members: Action Contre la Faim (ACF), Danish Refugee Council (DRC)).

In Cameroon, DFID funds UNHCR and WFP for refugee support: UNHCR focuses on biometric registration, health, education, self-reliance/livelihoods, and peace building. WFP provides targeted food and cash transfers and preventative malnutrition interventions.

This Annual Review will consider all these interventions with the exception of the gap filling one off funding to Solidarités International, which was approved one year into the three-year business case, and only one month prior to this review.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

We assess that the programme is on track to achieving its outcomes, with 1,847,123 beneficiaries reached during the review period against a target of 968,816.

We are achieving our targets and continuing to reach beneficiaries based on documented needs. Strategy, risks and assumptions of the programme set out in the Business Case remain appropriate, as shown by recent developments. The CAR crisis continues to be a severe risk environment. The severe human impact of the crisis, and the risk of sliding back into a conflict characterised by an extreme level of violence on civilians, continues. We will continue to engage and influence to improve humanitarian capacity, and to enhance coherence with early recovery actors and approaches. Outside CAR, we have made significant achievements in ensuring biometric registration of refugees, and will continue to influence actors in line with the Grand Bargain: more efficient targeting and delivery mechanisms, more emphasis on self-reliance and engaging longer-term actors in integration, benefiting the host and refugee community.

Overall output score and description

This project has scored an A: although the number of beneficiaries exceeded the target, the overall score reflects weighted scoring across outputs. Outputs met expectations, with four outputs being scored an A, one output scored B and two outputs scoring an A+: the breakdown per output is provided below.

Output	Assessment	Score
1 – improve agro-pastoral production	Met expectations, with an increase in cash-based modalities compared to initial target. Due to the timing of the reporting cycle, changes in coping strategies will be reported in the next annual review.	A
2 - healthcare and protection support	Met expectations, with a significant increase in beneficiaries reached with water and sanitation infrastructure, and challenges measuring outputs for healthcare.	A
3 – nutrition in CAR	Met expectations, with significant improvements in the health consortium’s performance. FAO has not yet started nutrition activities.	A
4 – humanitarian coordination (rapid and effective decision-making)	Met expectations, with a high performing Humanitarian Fund.	A
5 – food assistance to refugees in Cameroon	Moderately did not meet expectations, as WFP revised their nutrition strategy due to underfunding, leading to a reduction in achievements.	B
6 – basic needs for refugees and support for host communities in Cameroon	Exceeded expectations, as UNHCR exceeded targets but is yet to deliver a livelihoods strategy; indicators and targets need to be refined ahead of the next review.	A+
7 – participation in donor meetings and consultations	Exceeded expectations, with a high volume of effective donor coordination.	A+

Key lessons

CAR is once more becoming a forgotten crisis, topping Norwegian Refugee Council (NRC)’s annual ranking of the world’s most neglected displacement crises in June 2017. NRC notes that “less than two years after the United Nations downgraded the humanitarian situation in CAR from its highest alert level, the humanitarian community is now discussing if it should be raised again given the sharp increase in violence and displacement. International efforts in the country have been inconsistent, with insufficient and ebbing aid.” With a multi-year strategy which combines emergency response with livelihoods recovery approaches, and an internal contingency facility, DFID’s programme was designed in a way to maintain flexibility to adapt to contextual changes within this complex crisis.

DFID field visits continue to be critical in capturing the experience of beneficiaries receiving assistance and in highlighting programme quality issues. DFID participation in donor meetings and consultations and humanitarian country teams – in country and remotely - allows DFID to engage with improving the humanitarian system ensuring appropriate burden share with other donors.

Important advances in encouraging partners to improve monitoring and procurement have been sustained. Pipeline breaks, stock-outs and delays in delivery continue to be an issue and require further monitoring by DFID. Reporting of fraud and financial losses from security related incidents by partners has improved now that they have a better understanding of DFID’s definition of fraud and our requirements. We will continue to work closely with partners to review risk management and ensure robust and appropriate mitigation strategies are in place.

Maintaining access to intervention areas continues to be an issue for many of our partners due to the challenging security situation. DFID monitoring and partners’ efforts need to continue ensuring that security management processes are effective, that contingency plans are in place in order to reduce impact when access is temporarily lost, and that appropriate risk mitigation processes are in place.

The CHF continues to maintain its high reputation. DFID will seek to analyse and document the reasons for its continued high performance.

Key actions

- Continued engagement and burden share: DFID, together with other donor representatives on the CHF Advisory Board, will engage with the CHF’s donor base to encourage other donors to resume or increase funding to the CHF, by September 2017.
- Accountability to affected populations: DFID to agree actions with each partner to reinforce feedback and complaints mechanisms, by January 2018.
- Protection: DFID to ask partners in CAR and Cameroon to demonstrate how protection and social cohesion form part of their programme approach, by December 2017.
- Partner dialogue: DFID to set up Headquarters level dialogue with UNHCR, to support in-country engagement on improving coordination and partnerships, and to track progress with the development of a livelihoods strategy to promote refugee self-reliance, in parallel with continued engagement with the World Bank as they develop their programme, by December 2017.

Has the logframe been updated since the last review?

This is the first Annual Review. The logframe will be updated by end December 2017.

## C: DETAILED OUTPUT SCORING

Output Title	The agro-pastoral production in the targeted areas is improved and reinforced
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Number of people in CAR reached through livelihood assistance / (FAO; ICRC; CHF)	250,374 / (of which FAO: 235,000; ICRC: 2,774; CHF: 12,600)	Met expectation: 245,570 / (of which FAO: 216,450 ; ICRC: 11,363; CHF: 17,757)
Number of beneficiaries receiving seed vouchers (FAO) and general food distribution, cash and vouchers / (ICRC)	27,473 / (of which FAO: 25,000; ICRC: 2,473)	Substantially exceeded expectation: 36,760 / FAO:25,000 / ICRC: 11,760
Up to 95% of project beneficiaries are not induced to resort to negative mechanisms related to food insecurity / (FAO)	73%	Did not meet expectation / FAO: n/a (not yet measured)

Key Points

The number of people reached through livelihoods assistance reached 98% of the expected target.[4] ICRC and CHF both significantly exceeded their targets whereas FAO reached 92% of its target by the end of May. Insecurity and active conflict were the main reasons for delays. The number receiving market-based approaches and direct assistance through ICRC substantially exceeded the target, with a notable increase in ICRC’s cash for work activities against their internal target for cash-based response.
[4] The food security cluster standard for household size is five members.

FAO supported 216,450 farmers (91% of the target) to access inputs for the main 2017/18 planting season. FAO’s programme has a national reach: in the 5 prefectures[5] not covered by DFID’s contribution, FAO implements complementary activities with funding from ECHO and Office of US Foreign Disaster Assistance (OFDA). With DFID funds, FAO partnered with 11 international NGOs, 32 national NGOs and other parts of the UN system to deliver 1,342 tons of food producing seed and 129,870 hoes to 43,290 households (out of a target of 48,100); a further 5,000 households received similar inputs through seed fairs. Beneficiaries included displaced households settled in temporary sites or living with host families, new returnees and host families who suffered losses to their property and assets.
[5] CAR is administratively divided into 16 prefectures and the capital city Bangui, which is an autonomous commune

FAO has made significant improvements in the timeliness of intervention thanks to shorter supply chains: 88% of seeds were procured locally and the rest in neighbouring Cameroon. This is a significant increase from previous years, where the proportion procured locally was in the region of 20% and is an indication that some parts of the country have recovered – however seed self-sufficiency is still limited to certain parts of the country. Seed quality met FAO’s minimum standards. Local seed delivery rate was 95%, while 100% of tools were delivered on time (local markets could not supply tools to FAO’s specifications). Special attention was given to the specific needs of female heads of households and to ensure access to land for the displaced. More than 40% of beneficiaries were women.

ICRC supported 12,700 households (63,000 people) affected by conflict and other violence – notably returnees and Internally Displaced People (IDPs) – with seed, tools and disease-resistant cassava cuttings to grow more food. They also received two rounds of food aid, to avoid consuming seed meant for planting or harvesting crops early. Nearly 5,700 herding households (some 28,500 people) maintained or improved the health and market value of their livestock after 59,600 animals belonging to them were vaccinated against disease. Some 1,000 breadwinners (supporting 5,000 people) covered part of their household expenses with money earned through cash-for-work projects to cultivate cassava cuttings for their communities; another 394 (supporting 1,970 people) repaired cattle corrals used during vaccination activities. More than 68,200 people living in rural and semi-urban areas had more clean water for household consumption and livelihood purposes after wells and pumps were constructed and repaired by the ICRC, and maintained by the National Society. Returnees and IDPs also received food rations (1,445 households; 7,225 people) and essential household items (52,300 people) to help them meet their immediate needs; among them, around 330 households (over 1,500 people) who had returned to their places of origin rebuilt their homes using ICRC-provided shelter materials.

The CAR Humanitarian Fund (CHF) reached 37,541 beneficiaries with a range of livelihoods assistance activities, including support in both the agriculture and livestock sectors: provision of agricultural inputs, cash/voucher transfers, cash for work, livestock vaccinations, income generating activities, training activities relating to livelihoods, and livelihoods-centred social cohesion activities.

Summary of responses to issues raised in previous programme (where relevant)

- Follow up with FAO on new pilot method of Post-Harvest Monitoring (PHM) to ensure higher response rate after 2017 harvest season: FAO’s support to the 2017/18 main agricultural campaign has just been delivered. The quality and outcomes of Post-Distribution Monitoring’s (PDMs) and PHM to be conducted in the next quarter, and monitoring of coping strategies, will form a key part of DFID’s monitoring of FAO’s performance and will be assessed under the next annual review in 2018.
- Follow up with FAO on incorporation of nutrition sensitivity in vegetable gardening activities: FAO will start these activities after the launch of the main agricultural season to ensure that beneficiaries have time to engage in these activities. See output 3 for more details.
- Follow-up for future programming with SI consortium on strategies employed to counteract poor management of IGA’s and its impact on sustainability: The AGA with SI has only been signed in May 2017. SI’s performance will be assessed under the next annual review in 2018.

Recommendations

- Accountability measures and targeting: In order to further reinforce accountability to affected populations and to improve feedback on the quality of beneficiary selection and the performance of partners, it is recommended that FAO develops a feedback and complaints mechanism across its operations.
- Coping strategies: Consider revising the indicator targets to map against expected incremental reduction in negative coping strategies and ensure the indicator is ‘SMART’.

Output Title	Affected population are reached by healthcare and protection support
Output number per LF		2	Output Score	A
Risk:		Severe	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Number of beneficiaries reached in CAR by healthcare support / (ICRC, MENTOR Initiative-led Consortium)	423,332 (of which 247,750 over the period under review) / (of which ICRC: 1,935; MENTOR Initiative-led Consortium: 421,397 - of which 245,815 over the 7 month period under review)	Significantly underachieved: 199,191 / ICRC: 8,065 / MENTOR: 191,126 over 7-months.
Health service utilisation rate per person per year / (CHF, MENTOR Initiative-led Consortium)	CHF: 1 or more per person per year / MENTOR Initiative-led Consortium: 1 per person per year	Significantly underachieved MENTOR: 0.44 / CHF: N/A (98,761 consultations) / (NB. CHF didn’t use utilisation rate as an indicator. It varies between 0.2 and 0.6 across the country.)
Number of people with improved access to water and sanitation -hard activities only / (ICRC, CHF, MENTOR Initiative-led Consortium)	ICRC: 25,048 / CHF: 6,300 / MENTOR Initiative-led Consortium: 500 per water point	Significantly exceeded expectation: 112,735 / ICRC: 89,037 / CHF: 23,198 / MENTOR: 500
Number of beneficiaries in CAR supported in the protection sector (ICRC, CHF)	N/A	Met expectation / ICRC: 1,379 / CHF: 149,696
Number of GBV survivors in CAR who access remedial services (ICRC, CHF)	N/A	Met expectation / ICRC: 30 (health) / CHF: 711 (protection)

Key Points

ICRC and the CHF significantly over-achieved against health and WASH targets, reflecting the substantial role of humanitarian actors in delivering basic services throughout the country. MENTOR Initiative did not meet its targets for access to healthcare.

ICRC delivered medical services at two hospitals, with an ICRC surgical team at the hospital in Bangui, and renewed support to the hospital in Kaga Bandoro, and provided emergency transport, including evacuations by plane for critical cases. ICRC was not able to deploy planned mobile clinics due to insecurity, hence two ICRC-supported health centres carried out a total of 53,308 consultations and 143 patients who required emergency medical attention were referred to an ICRC-supported hospital.

ICRC has surpassed targets for water and sanitation infrastructure: in the absence of another actor with the capacity to do so, ICRC carried out major infrastructure and water treatment work on the water system in Bangui. With DFID and other donors’ support, some 615,000 people in urban areas had a better supply of safe water after ICRC support. Moreover 72,700 IDPs had more clean water after the ICRC trucked it in and repaired facilities at their sites. They also had access to latrines, and learnt more about good hygiene practices.

ICRC supported victims of sexual violence at two clinics and a counselling centre where 292 survivors received psychosocial support (30 of which through DFID support). Information sessions on the consequences of violence – particularly the importance of post-exposure prophylactic treatment for victims of sexual violence within 72 hours of an assault – were provided to prevent the stigmatisation of victims and to encourage referral. Following this, 78% of the victims of sexual violence treated at ICRC-supported facilities received care within 72 hours of their assault, up from an average of 38% in the latter half of 2015. ICRC also continued to work with a local organisation that produced assistive devices for disabled people. Moreover, ICRC carried out a range of protection activities oriented towards weapons bearers, authorities and civilians.

MENTOR Initiative provided primary healthcare support to 191,126 patients. The consortium has underachieved on its target for healthcare due to significant barriers to accessing healthcare for patients over the age of five. The Consortium has reached children under 5 at 95% of the target (based on 2 consultations per year), but only 31% of over-5s based on 1 consultation per year. The aggregate achievement is 0.44 consultations per person per year, which is comparable to data provided by the CHF after consultation with the health cluster, but remains worryingly low. The CAR government’s cost recovery policy, which provides for ‘targeted’ free primary healthcare only for children under 5, pregnant and nursing women is believed to be the main barrier, in addition to physical access and insecurity. The World Bank is also pushing use of Results Based Finance (RBF) in CAR which most NGOs and international organisations consider to be much to sophisticated a financing system and management tool for the context and unlikely to have a positive impact on the level of health services.

MENTOR has provided a detailed analysis of health service utilisation across the different consortium members showing how the modality of access to health care (free access or targeted free access) is a critical factor enabling health actors to meet standard targets for health utilisation. The ability of the consortium lead to carry out such comparative analysis and propose solutions is a strength of the consortium approach.

Consortium member IMC provided treatment for survivors of Gender Based Violence (GBV), Cordaid has made medical services available, and MENTOR refers cases to local partners Danish Refugee Council and Médecins sans Frontières (MSF) for a range of support. During the review period, 12 GBV survivors requested and accessed medical care services within 72 hours. Technical teams from each of the 4 partner organizations met in March 2017 for the first Reinforcement Team visit to exchange knowledge on IEC approaches, community-based healthcare networks, and primary level support. Traveling together to field sites, MENTOR shared expertise on their Community Health Worker (CHW) package, and IMC and Cordaid provided advice to MENTOR on how to improve support to health facilities. As a result of this visit, a WASH and medical needs-based assessment of all Consortium-supported health facilities was carried out in order to identify the priority locations for Oxfam’s WASH activities. Oxfam has so far only constructed one water point, however all technical assessments are complete and infrastructure activities will take off in the next quarter.

The CAR Humanitarian Fund has surpassed healthcare targets with 11 health projects funded in 2016 for a total of $3,848,070 (the third highest cluster). Projects funded focused on primary healthcare in areas affected by conflict and displacement and supported the response to epidemics of rabies and cholera, which has greatly expanded the number of beneficiaries reached. WASH targets were surpassed reflecting the role of WASH in epidemic prevention and response (cholera response) and in displacement sites. No targets had been set for protection activities but the CHF has continued to prioritise protection work and protection mainstreaming. Access to GBV services are reported under protection; however it is likely that there is under-reporting of GBV survivors accessing medical services (clinical management of rape) without referrals for psychosocial or legal services.

Summary of responses to issues raised in previous programme (where relevant)

DFID to monitor partner efforts to analyse and improve utilisation rates and stock-outs of essential drugs under 2016-19 project:
There has been detailed follow up with the MENTOR Consortium in Bangui and in London with the CEO, Desk Officer/Acting Consortium Coordinator and Head of Finance and Grants. MENTOR is continuing to develop a consortium wide approach to improve utilisation rates, stock and supply chain management, and provides regular updates to DFID.
DFID to follow up with Cordaid and the MENTOR consortium to do a more thorough assessment of the partners’ implementation under the new programme as a follow up to the final assessment under the CAR 2014-16 programme:
DFID will continue to follow up on Cordaid’s performance and to request updates on actions taken by the consortium lead to ensure quality assurance through thorough scrutiny of reports, field visits by the Reinforcement Team, dialogue, and feedback from other actors in the field.
DFID to carry out field monitoring visit of Cordaid programme in Alindao under 2016-19 programme:
Detailed planning had been carried out to carry out this visit together with the reinforcement team in May 2017. Due to heavy fighting in the area breaking out a week before the planned monitoring visit, this was no longer feasible. DFID will endeavour to monitor Cordaid’s programme at the next possible opportunity.
DFID to monitor and follow up on the progress of setting up a technical committee to ensure a cohesive approach amongst IMC/MENTOR consortium partners under 2016-19 project:
DFID attended a consortium coordination meeting and had in-depth conversations with the Consortium Coordinator and Desk Officer. DFID will continue engagement with the committee through this programme.
DFID to follow up on protection mainstreaming in CHF funded projects:
A monitoring visit was carried out to a GBV project in Bangui. DFID will continue to engage strategically with the CHF on how to make the centrality of protection a reality in CAR.
DFID to monitor results and impact of ICRC community-based protection:
As ICRC has particular policies around monitoring of protection activities by donors, this will need to be negotiated ahead of the next monitoring visit.

Recommendations
- DFID to include the case of CAR, alongside discussions of DRC and other countries, in ongoing discussions on World Bank’s health financing policy in fragile and conflict contexts including issues of free access to healthcare and Performance Based Financing (PBF) approach.
- DFID to revise indicators around health utilisation rate and GBV services to improve measurability while recognising the barriers to achieving international standards for access to healthcare.
- DFID to request a detailed follow up of the WASH component of the MENTOR consortium to avoid delays and ensure integration with the health components.
- DFID to request MENTOR to assess the capacity of the consortium to respond to emergency healthcare needs, given the changes in the context and capacity of other healthcare actors, and consider whether a revision may be necessary given the significant increase in needs.
Output Title	DFID helps improve children's, women's and girls' nutrition in CAR
Output number per LF		3	Output Score	A
Risk:		Severe	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Number of new malnutrition cases from children under 5, adolescent girls (10-19) and women under 50 in CAR that gain access to treatment (includes SAM and MAM cases) / (MENTOR Initiative-led Consortium)	341	Significantly exceeded expectation: 529
Number of children under 5, adolescent girls (10-19) and women under 50 in CAR with improved capacity to prevent malnutrition / (FAO, MENTOR Initiative-led Consortium)	26,376 / (of which FAO: 7,500; / MENTOR-Initiative-led Consortium: 18,876)	Did not meet expectation: 20,835 / FAO: 0 (activity not yet started) / MENTOR: 20,835
Cure rate among children treated for acute malnutrition / (MENTOR Initiative-led Consortium)	Above 75%	Moderately exceeded expectation: 86%

Key Points

The DFID funded programme in CAR specifically seeks to improve the humanitarian response to the issue of undernutrition, whether as part of healthcare provision (prevention and treatment of severe acute malnutrition; access to improved water and sanitation) or though food security and livelihoods activities. Key nutrition indicators are presented here, although the activities represented are integrated within a larger programme implemented by DFID partners.

The consortium led by MENTOR Initiative has exceeded targets for treatment of severe and moderate acute malnutrition (SAM and MAM). A total of 18,754 people have been reached with information and sensitisation on nutrition, screenings were carried out, and 529 new malnutrition cases gained access to treatment in 9 facilities offering treatment (Cordaid and IMC provide services for treatment of severe acute malnutrition; MENTOR does not implement SAM case management). After an initially difficult start marred by discrepancies with data management, Cordaid has made necessary staffing changes and increased supervision capacity on nutrition. Despite a continuing issue with drop-outs (in one case linked to a one-month delay in provision of supplies to IMC-supported facilities by UNICEF), the Consortium has met and exceeded the target for cure rate among children being treated for acute malnutrition.

Focus on nutrition needs to be continually strengthened and consolidated, as nutrition is poorly mainstreamed in the national health system. In the wider humanitarian response, it is expected that ACF’s new emergency nutrition response mechanism which has just started in CAR, modelled after their work undertaken in DRC, will help to raise the profile of the nutrition crisis in CAR as well as providing better data, and a model for response.

FAO’s nutrition activities are yet to begin in earnest, as the first five months of the programme were devoted to activities towards the 2017/18 agricultural season, which is now underway. Preparatory activities have been carried out: 12 schools have been identified to host training activities on nutrition. The « nutrition training » component of the project, which aims at building capacity of households, will be launched by July 2017. During that period, trainers will be available to start trainings and farmers will have time to attend trainings. Nutrition activities are specifically targeted at families with malnourished children, poor pregnant and nursing mothers, and households suffering from undernutrition. These activities will be two-fold, with the implementation of poultry farms for food diversification, and support to develop gardening and food crop production.

Although not captured in the output indicators, it should be noted that ICRC carried out vaccinations and malnutrition screening, and provided treatment for 2,400 severely malnourished children at 5 health facilities. These children and their families (around 8,700 people) also received food rations or financial assistance.

Summary of responses to issues raised in previous programme (where relevant)
There was no standalone output on nutrition in the previous programme.

Recommendations
- DFID to follow up on FAO’s implementation of nutrition activities and measurement of outcomes.
- DFID to continue to follow up on the wider issue of access to nutrition case management across the response, including coordination between actors for prevention and case management, supply issues and achieving quality indicators.

Output Title	DFID empowers humanitarian coordination for rapid and effective decision-making
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
% of CHF funding from donors which is allocated to projects within six months	85% of overall funding received from all donors by 30 June 2016 is allocated before 31 December 2016	Moderately did not meet expectations: 77%
% of CHF projects monitored through field visits within their project duration	40% of projects monitored in 2016	Met expectations: 43%

Key Points

The CAR Humanitarian Fund made allocations totalling $24 million during the period covered by the 2016 Annual Report. This comprised two Standard Allocations covering 86% of funds, and six Emergency Reserve allocations for 14% of funds. Eleven donors, including two that were new to the Fund, contributed a total of $28 million. The Fund has been successful in maintaining its donor base: only one of the nine donors who had supported the Fund since 2008 did not contribute in 2016. Over this period (2008-2016) DFID was the fourth largest donor after the Netherlands, Sweden and Irish Aid, contributing 15.89% of funds.

The majority of funds were received in the second part of the year: only 33% of funds were received between January and June, and 30% were received in the last quarter. This issue, which affects most country based pooled funds (CBPF), leads to a significant carry-over of late funds into the following year and affects the Fund’s financial planning and how it presents its financial situation to Donors. In 2016, the CHF was able to allocate $9 million through a first Standard Allocation (SA1) in January, using the substantial carry-over of $12.7 million from 2015. Emergency Reserve (ER) funds were allocated in February, June, July and August, and a second Standard Allocation (SA2) of $11.5 million was carried out in September. One further Reserve allocation was made in December. Strategically, the timing of the allocations allowed alignment with planning and needs assessment processes, as SA1 was based on the geographical and sectoral prioritisation of the newly-launched 2016 Humanitarian Response Plan (HRP); SA1 was in line with the Periodic Monitoring Report of the HRP and the start of the humanitarian needs overview (HNO) process for 2017. The Fund maintained flexibility through the Reserve, to allocate funding for unforeseen emergencies and funding shortfalls affecting the response.

Period	Allocation	Activities	Amount (US$)
January 2016	SA1 - 2016	Humanitarian Response Plan (HRP) based activities	9,041,801
February 2016	ER1 - 2016	Emergency water assistance for IDPs in Bria	259,200
June 2016	ER2 - 2016	Humanitarian Logistics Common Services	216,000
June 2016	ER3 - 2016	Emergency response to the rabies epidemic	249,997
July 2016	ER4 - 2016	Emergency rehabilitation of infrastructure to facilitate humanitarian access	216,000
August 2016	ER5 - 2016	Emergency response to Cholera outbreak	1,511,600
September 2016	SA2 - 2016	Humanitarian Response Plan (HRP) based activities	11,658,670
December 2016	ER6 - 2016	Emergency food distribution to IDPs in Bria	1,000,010
			$24,153,278

The fund mainly supports NGOs, with only 16% being channelled to UN agencies in 2016. The proportion being directly attributed to national NGOs is low but increased from 8% in 2015 to 13% in 2016. National NGOs are more often included in sub-granting arrangements, which provides greater opportunities for capacity building, quality assurance and risk management: 35% of projects funded included sub-granting arrangements.

On due diligence and performance management, the CAR Humanitarian Fund (CHF) has built up a strong partner performance system that relies on physical verification (monitoring), thorough review of reports, financial spot checks and audits and ensures that performance is measured and taken into account in deciding on the eligibility of partners. Monitoring visits reported (43% of projects visited, above the target) are those specifically carried out by the CHF’s staff. Feedback is also gathered from OCHA and cluster personnel carrying out project or area visits, but not reported. Partners’ eligibility to apply can be suspended based on clear criteria, in which case the HF balances transparency with confidentiality. The CHF staff invest considerable time in training and capacity building, including regular ‘surgeries’ on OCHA’s grant management system, prompted by feedback from the last user survey.

The Fund continues to have a high reputation, and receives positive feedback. Positive feedback on the fund highlights its performance in meeting priority needs, transparency, gradual but consistent approach to systems building, and the checks and balances in place in terms of risk management. The CHF also makes an important contribution to the cluster system by funding NGO cluster co-lead positions which contribute to stronger monitoring and accountability through the formal coordination system, and to the Fund. Moreover, cross learning between humanitarian funds, thanks to movement of personnel and regular formal and informal exchanges between CBPFs has had a positive effect.

In 2016, 43 projects financed by the CHF required no cost extensions, and in 53% of cases the extension was accompanied by a project revision. While 75% of these requests were due to insecurity, there were also delays in implementation due to administrative and programmatic delays, or delays with procurement and supplies. This highlights the difficulties with access and a volatile security context; the need for flexibility and adaptiveness in response; as well the difficulties in maintaining staffing capacity at field level in such a difficult and insecure environment, characterised by high staff turnover.

With the decrease in humanitarian funding for the CAR crisis, there was strong demand for CHF funding. Prior to each allocation, consultations were conducted to take into account other sources of funding such as the Central Emergency Response Fund (CERF), ECHO, OFDA, the Bekou Fund but also activities funded through previous allocations. CERF funds ($11.9 million through the Rapid Response window) were coordinated by the CHF’s Humanitarian Financing Unit (HFU) and allocated in complementarity with CHF funding to support critical humanitarian needs for IDPs and refugees.

Allocation strategies took into account gender, the centrality of protection, humanitarian access and the regional context of protection. The integration of gender in the development of projects was a requirement and the CHF unit provided training on gender equality programming and the gender marker; guidance was provided to facilitate the review of projects. Against an initial target of 75% of funded projects coded 2 with the IASC Gender Marker, the Fund reached 100%. Training sessions on centrality of protection were also organised to improve the design and review of proposals.

Summary of responses to issues raised in previous programme (where relevant)
Continue monitoring that partner performance system is used and informs allocations and M&E:
In-depth meetings were held with CHF staff in Bangui to review the performance system and its use in the allocation process, ensuring due diligence, risk management as well as confidentiality.
Ensure that CHF reports to board changes in their analysis on partners’ risk levels, and other relevant points including losses and fraud:
DFID is a member of the CHF Advisory Board and receives communications on changes to eligibility of partners based on revisions to their risk and performance levels. DFID’s policy on losses and fraud was discussed with CHF staff. We will continue to engage with CHF staff to ensure robust and appropriate mitigation strategies are in place.

Recommendations
- DFID to engage on strategic issues at the Advisory Board, if possible with common positions with other donors (Sweden and Switzerland); and encourage other donors to increase their funding.
- DFID to do a lessons learning piece on the CAR CHF’s continued high performance.
- DFID to consider the weighting and nature of this output as part of the logframe review.

Output Title	Central African refugees in Cameroon access basic food assistance
Output number per LF		5	Output Score	B
Risk:		Major	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Total number of people who have received basic food assistance – general food distribution and cash-based transfers / (WFP)	136,496 / (DFID proportion at 13.9%: 18,973)	Significantly exceeded expectation: 203,195 [164,624 general food distribution+ 38,571 / (DFID proportion at 13.9%: 28,244)
Number of pregnant women and children under five who receive nutrition support aimed at treating MAM (TSFP) / (WFP)	28,900 / (DFID proportion at 13.9%: 4,017)	Significantly did not meet expectation: 16,675 / (DFID proportion at 13.9%: 2,318) / (The activity was implemented only in 2016)
Number of pregnant women and children under five who receive nutrition support aimed at preventing MAM (blanket feeding) / (WFP)	55,510 / (DFID proportion at 13.9%: 7,716)	Did not meet expectation: 39,217 / (DFID proportion at 13.9%: 5,451)

Key Points

DFID’s contribution to the World Food Programme’s 2016 appeal enabled the agency to fill some of the most critical funding gaps in 2016 for CAR refugees living in Cameroon. Assistance was targeted to the most vulnerable registered refugees in 7 official camps and 78 off-camp sites. Due to underfunding WFP had to reduce ration size and prioritise the most critical activities: in January 2017 food rations were reduced to 50% of needs in terms of calorie intake and the value of the cash transfer was reduced from $15 to $7.50 per person per month. WFP has had to make difficult choices and has put in place sound management practices to increase value for money.

WFP reached 164,624 people with food distributions and 38,571 individuals with cash transfers enabling them to purchase food in the local market. Nutrition prevention and treatment activities were successfully implemented, with a change in strategy to maximise scarce resources. Prevention and referral were ensured through blanket supplementary feeding, and training and sensitisation (900 stakeholders were trained; 23,991 women and 4,966 men participated in nutrition education sessions) The 2015 Standardised Expanded Nutrition Survey (SENS) survey conducted by UNHCR in designated sites revealed a global acute malnutrition (GAM) rate of 9.6% while the 2016 survey showed an improvement with GAM rate of 7.3% among new refugees in and out of designated sites. With the stabilisation of acute malnutrition rates, WFP shifted its strategy from treatment to prevention during the second half of 2016. A blanket supplementary feeding approach allowed WFP to address moderate acute malnutrition (MAM) treatment and facilitate detection and referral of severe acute malnutrition (SAM).

The move to digital cash transfers was appropriate given the long delivery lead times involved with in-kind commodity transport. Digital e-vouchers can be redeemed at selected retailers’ shops for specific food items. Out of the 41 participating retailers’ shops, 8 are managed by women (23 women organised in groups). Continuous efforts are put in place to increase the number of women in supply chain. Beneficiaries also received sensitisation messages in order to promote good practices in the areas of health, nutrition education, household management, and gender.

WFP monitors food security indicators and coping strategies used by beneficiaries to meet food and other livelihood needs, through post distribution monitoring and food security assessments. Trends have been largely positive, with 84.9% showing acceptable food consumption score in November 2016. However, their dependence on food assistance, poor dietary diversity, and continuous recourse to negative coping strategies confirm that the refugees remain vulnerable. Due to underfunding of the CAR refugee response and the reduction in food rations and cash transfer values, we may see a deterioration in these indicators, signalling a reversal of previous gains attributed to DFID and other donor funding.

Summary of responses to issues raised in previous programme (where relevant)

DFID to work with WFP to look at strategies for decreasing defaulter rates in the nutrition programme:
WFP has changed its strategy towards prevention rather than treatment with the implementation of blanket supplementary feeding replacing the therapeutic supplementary feeding programme (TSFP). This strategy rests on forward distribution points, thus addressing some of the access difficulties affecting attendance at therapeutic centres.
DFID to continue monitoring WFP pipeline management to ensure there are no ruptures in supplies:
To limit risks and avoid pipeline breaks, WFP has increased the capacity of its Global Commodity Management Facility for the Douala corridor to position cargo earlier, developed long-term food supply agreements with suppliers in Cameroon, and launched new tenders with transporters. WFP engages in local procurement whenever possible to reduce lead times. Supply chain breaks are further be mitigated through timely call forwards and food prepositioning in strategic locations to ensure that sufficient quantities are available in case of any delays in new food arrivals. Further expansion of Cash Based Transfers will enable a more effective response.
DFID to work with WFP to ensure M&E adequately tracks increases in negative coping mechanisms:
This continues to be an essential recommendation given underfunding, and DFID has engaged closely with WFP in this regard.

Recommendations
- DFID to continue to engage with WFP and the Cash Working Group to promote an increased uptake in cash programming, where appropriate to context.
- DFID to closely monitor the impact of the reduction in food rations and cash transfer values, in terms of food security outcomes and coping strategy indicators.
- DFID to ensure WFP’s data and expertise is used in influencing other actors (UNHCR, FAO, International Fund for Agricultural Development (IFAD), World Bank) to developed appropriate resilience and long term Livelihoods Strategy.
- DFID to encourage other donors to support refugee operations, highlighting the risk that underfunding will reverse gains made in stabilising the nutrition and food security status of CAR refugees

Output Title	Central African refugees in Cameroon see their basic needs met and communities in Cameroon are supported in hosting Central African refugees
Output number per LF		6	Output Score	A+
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Number of individuals (refugees and most vulnerable nationals) who benefit from livelihoods support activities / (UNHCR)	3,168 / (DFID proportion at 11.8%: 374)	Significantly exceeded: 8,790 / (DFID proportion at 11.8%: 1,037)
Number of persons of concern registered by biometric registration / (UNHCR)	30,554 / (DFID proportion at 29.9%: 9,136)	Significantly exceeded: 112,336 / (DFID proportion at 29.9%: 33,588)
Number of refugees who access primary healthcare services / (UNHCR)	5,092 / (DFID proportion at 1.6%: 82)	Significantly exceeded : 64,469 / (DFID proportion at 1.6%: 1,032)
Number of refugees benefitting from activities co-ordinated with local authorities of host communities / (UNHCR)	252,537 / (DFID proportion at 2.8%: 7,071)	Met: 259,145 / (DFID proportion at 2.8%: 7,256)

Key Points

In 2016 the biometric verification exercise of Central African refugees continued as the main priority under DFID funding. By the end of 2016, a total of 112,336 refugees had been verified, both in and out of sites, significantly exceeding targets. Refugees received access to health facilities in areas hosting refugees. Peaceful coexistence between refugees and host communities in the East region was another major focus for UNHCR, with 779 awareness campaigns delivered to 117,283 people covering topics such as the culture of peace, promotion of human rights, the prevention and the management of conflicts, and community development. In addition, community based radio programmes were made and peaceful coexistence messages were broadcast 192 times in key locations.

A total of 14 health facilities were rehabilitated and 38 health centres and hospitals were supported with equipment or/and supplies; 10,691 refugee children were enrolled in primary school and 10 additional classrooms were constructed and equipped in refugee sites and refugee hosting villages in the regions of the East and Adamaoua. In addition 12 classrooms and two offices in Bertoua were rehabilitated.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to follow up with UNHCR both at country level and at HQ level to ensure that they step up in terms of improved coordination and partnerships:
As in 2015-16, relations with implementing partners continue to be strained, mainly around contracting processes although this has not impeded meeting targets.
Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors:
Underfunding of the CAR refugee response continues. There remains a need for DFID to continue monitoring the situation and supporting appropriately.
DFID to discuss UNHCR’s reporting delays with CHASE and UNHCR HQ:
While there has been good progress on biometric registration, timeliness and quality of reporting needs further improvement.

Recommendations

- DFID to initiate a strategic dialogue with UNHCR at Headquarters level to support country level dialogue around the quality of partnership and reporting.
- Continue to monitor funding levels, and advocate to other donors on maintaining funding for refugees in Cameroon, given the lack of conditions for large-scale sustainable returns.
- As part of the logframe review DFID to ensure the milestones for UNHCR are correct.

Output Title	Participation in HCT and donor meetings, and contribution to EU Trust Fund and World Bank consultations
Output number per LF		7	Output Score	A+
Risk:		Severe	Impact weighting (%):	5
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	2017 Milestone	Progress
Number of HCT and donor meetings DFID participates in	1	Significantly exceeded expectation: 3 / (1 HCT, 2 donor meetings).
Percentage of EU Trust Fund and World Bank written consultations DFID contributes to	100%	Met expectation : 100%

Key Points

DFID continued to be a valued and respected partner for operational organisations, other donors and international institutions. DFID was a core team member of the World Bank’s Fragility Assessment for CAR: inputted in the desk review, took part in a fact-finding mission in CAR in March 2016, and finalised the report which was issued in April 2016. DFID also contributed written feedback on 10 World Bank policy notes that were part of the country reengagement note, in April 2016.

Following DFID’s decision in May 2016 not to partner financially with the EU Trust Fund (Bekou Fund), there have been no formal requests for written input. However, informal coordination and collaboration with the Trust Fund continues. DFID participated in the first day of an EU and Member State Joint Programming Workshop bringing together the EU Delegation, Italy, Germany, France, Switzerland and the UK. As a result of this workshop, the EU Delegation has been asked to take a lead role on health policy issues (especially access to healthcare and health governance) and requested continued DFID input on these issues, given significant DFID humanitarian funding in the health sector.

DFID participated in a humanitarian country team meeting in May 2017, at which strategies to raise the profile of the CAR crisis were discussed. Options included Member State briefing in capitals, revision of the HRP, and request for activation of a system-wide Level 3 crisis.

Further, a joint donor meeting with ECHO and Switzerland was held in May 2017, and followed up with a combined donor meeting with the Solidarites consortium which receives funding from all three donors.[6] This optimised the time of all parties concerned, and allowed an interesting discussion on future perspectives of the consortium and funding intentions, as well as agreeing on operational adjustments to the programme which may have required a revision of the project affecting more than one donor.
[6] DFID’s funding to this consortium started in May 2017 and will be due for annual review next June.

Summary of responses to issues raised in previous programme (where relevant)
This is a new output.

Recommendations
- DFID to contribute to the health policy discussion led by the EU, with a particular focus on the appropriateness of the World Bank’s performance based financing model in CAR; and strategies to increase access to healthcare.
- DFID to develop a constructive dialogue with the EU Trust Fund, contributing to better delivery against strategies for early recovery and resilience in CAR.
- DFID to try to time missions to coincide with opportunities to engage with key humanitarian coordination or early recovery policy priorities.
- DFID to consider whether this output is appropriate as part of the logframe review.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

VfM performance compared to the original VfM proposition in the business case

The Business Case followed DFID’s approach to VfM, ‘the 3Es model’ of economy, efficiency and effectiveness. It also addressed equity and the metrics of cost, speed/timeliness, and quality/appropriateness in accordance with humanitarian planning in rapid responses. The VfM assessment and cost drivers identified in the Business Case remain relevant.

Economy (spend less)

The Business Case stressed the high operational costs in CAR. The operational cost of scale-up in particular is very high given the challenges of the context.

WFP: The total value of the food commodity costs and cash-based transfers to beneficiaries is 56% of total direct operating costs.  The monthly cost per beneficiary for GFD is about US$16 which is similar to other similar contexts. WFP endeavours to make timely purchases of commodities after the harvest when prices are competitive, for example through the Global Commodity Management Facility (GCMF) and through local purchase of cereals and pulses to save on transport costs.

Efficiency (spend well)

The previous programme tried and tested the portfolio model of seven agreements, two of which in Cameroon. All but one of the partners have multi-year projects under this programme which better enables them to seek long-term economies and to increase impact through greater cooperation with local authorities, particularly in health.

On beneficiary reach for this year, the overall target was exceeded. Three partners significantly exceeded their target (ICRC, CHF and UNHCR), one partner met their target (FAO) and two partners significantly did not meet their target (MENTOR Initiative and WFP). The agreed percentages for indirect/admin costs incurred by partners for this programme average at 6%, with the maximum level agreed at 10%.

MENTOR Initiative has initiated a comparative analysis of stock and supply costs to closely monitor procurement, improve lead times for supply, and contribute to better economy and management across the consortium.

FAO: FAO was able to group its purchases across the three main donors (DFID, OFDA, ECHO) thus minimising inputs acquisition costs. All tools were purchased locally, 88% of seeds were bought in country and the remaining 12% were ordered in Cameroon. This minimises transportation costs and delivery lead times.

WFP: WFP strives to purchase the food as soon as the contribution is received and take advantage of their internal advance financing facility to speed up the procurement process, and takes advantage of locally purchased food when possible to speed up the delivery.  Food is pre-positioned in hard to access areas before the rainy season.  WFP endeavours to minimise transport costs through a dedicated list of transport providers established on the basis of performance and a competitive bidding process.

Effectiveness (spend wisely)

WFP: Almost 100% of planned beneficiaries were reached in 2016 and the intervention was appropriate to the needs of populations facing food insecurity and malnutrition. Regular monitoring ensured that food was distributed as planned and on time, and analysis of monitoring data enabled swift corrective action to solve any issues.  The WFP Beneficiaries Feedback and Complaints Mechanism (BFCM) which functions in six languages, was launched in July 2016 to enhance the accountability towards stakeholders, improve operational transparency and to give beneficiaries a voice. Roughly one year later in May 2017, the mechanism receives an average of 3,600 calls per month. The mechanism is now considered a strong tool to collect beneficiaries’ feedback and inform programme implementation.

CHF: On average, allocations from the emergency reserve were disbursed within 45 days, including the preparation phase leading up to submission for approval by the humanitarian coordinator (17 days), contract approval, signature and disbursement. There was a significant improvement between the time it took to disburse the first Standard Allocation (119 days) and the second Standard Allocation (89 days). Standard Allocations require lengthier consultation with clusters. The CHF has worked hard to analyse the data and bottlenecks, in order to improve processes and provide training to address specific issues, leading to an improvement in timelines over the course of the year.

Equity (spend fairly)

WFP use a ‘whole of caseload approach’ meaning a balance of refugees, internally displaced persons (IDPs) and local residents, and targeting based on needs. WFP ensures that food assistance activities are targeted to the most vulnerable segment of the population with special attention to single female-headed households and widowed women, which face a higher risk of food insecurity. In particular for cash-based transfers, households led by women comprised 70% of targeted households. WFP programmes are designed with consideration for protection concerns: safety issues to, from and at the site, intra-household dynamics, or barriers for persons with specific needs.

Assessment of whether the programme continues to represent value for money

Based on the above review of four dimensions of economy, efficiency, effectiveness and equity, the programme is delivering good value for money in a very difficult operating environment.

Quality of financial management

There were some concerns regarding the quality and level of detail of the first WFP and UNHCR reports and re-drafts were requested. DFID will need to see higher quality narrative and greater financial detail in their next reports. All independent audit statements that were due have been received and were ‘unqualified’. Financial reports from partners for payment that have been received have complied with our funding agreements and enabled timely disbursement of funds.

	Date of last narrative financial report	Date of last audited annual statement
FAO	1 June 2017	N/A - due by October 2017
ICRC	1 June 2017	2016 (for 2016 up to 31st Dec)
CHF	15 May 2017	N/A
WFP	27 February 2017	2 June 2017 (for 2016 up to 31st Dec)
UNHCR	14 February 2017	N/A - due by August 2017
MENTOR	15 May 2017	N/A - due in March 2018
Solidarités	N/A - due in August 2017	N/A - due in June 2018

E: RISK

Overall risk rating: Severe
CAR risk rating: Severe
Cameroon risk rating: Major

Overview of programme risk

A live comprehensive risk register has been created and will be routinely updated throughout the life of the programme. The programme is “severe” overall as the majority components of the programme are operating in CAR. For the components supporting refugees in Cameroon, where the operating environment is much less insecure, the risk rating is better described as major/moderate.

The highest risks for CAR post-mitigation relate to the security and political context, followed by procurement and logistics, which correlates with the key cost drivers identified in the value for money assessment. The level of these risks is not reducing given the deterioration over the last few months. Violent conflict has intensified with an increase in attacks on civilians and humanitarian actors as well as the UN peacekeeping force, expansion of the conflict into previously unaffected areas, and further population displacement to levels last seen in 2014. Humanitarian access and space has been affected, and recent events could further destabilise the political context in CAR.

Partners have been proactive in reporting suspected cases of fraud or loss to DFID. Since the programme started, there have been two confirmed cases during the late 2016/early 2017 upsurge in violence. These were reported to DFID within 24 hours and funds were recovered. We will continue to review partners’ risk management to ensure robust and appropriate mitigation strategies are in place.

DFID’s Humanitarian Adviser for the programme will travel more regularly to CAR to meet with partners and other donors in country over the next year. DFID is also meeting a group of UK-based international NGOs who operate in CAR on a quarterly basis which provides situational updates and coordination of policy and advocacy efforts.

A DFID Humanitarian Adviser visited partners in CAR in February and May and began follow-up on the actions from partners’ due diligence assessments, the progress on which is being tracked in the programme delivery plan. The Humanitarian Adviser based in Yaoundé has conducted two field visits in Cameroon since August 2016. The remaining due diligence recommendations are being addressed through desk-based followed-up correspondence.

MENTOR Initiative in particular has performed strongly on security and risk management. DFID has received high quality quarterly progress reports which include dedicated sections on actions being taken to address threats and opportunities to implementation from changes in the humanitarian and security context, as well as an update on the risks and mitigation measures identified in the proposal. In addition, MENTOR Initiative was pro-active in creating a quarterly security bulletin which is shared with DFID to provide detail on the security context in the areas where consortium partners are operating and information on the impact and response to any incidents.

Cameroon
The humanitarian community and the Government are closely monitoring the security situation. Larger waves of displacements are a possibility, in case of escalating conflict in neighbouring regions of CAR. Contingency plans are being developed through inter-agency planning.

WFP staff and partners are regularly sensitised on their responsibility to ensure the safety and dignity of beneficiaries. Systems are in place to ensure detection of sexual exploitation and abuse by WFP staff or partners, and staff members are required to take the on-line course on the prevention of sexual exploitation and abuse as part of the basic security in the field programme.

Outstanding actions from risk assessment

Continuous monitoring of the situation required.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The programme is broadly on track against the original timeframe. There have been some examples where partners have improved their performance from previous funding agreements. In the past the FAO have struggled with issues around timeliness, seed quality, and M&E. Progress has been made against all three aspects, thanks to concerted follow up by donors and improvements by the FAO in planning and delivery. As noted in the review the humanitarian situation in CAR is deteriorating. It will be critical for partners to ensure they sustain their delivery so they can continue to meet the needs of the CAR citizens.

The MENTOR Initiative led consortium’s activities have been affected by this upsurge in violence in two ways: initially, staff movements were suspended and activities were interrupted during the peak of violence; subsequently, there has been an increase in needs for emergency healthcare due to the higher caseload of displaced people. DFID have asked MENTOR Initiative to assess the capacity of IMC and Cordaid to carry out more emergency healthcare based on their added value and presence with regards to other actors, and what changes this would require (see Output 2).

Performance of partnership (s)

DFID has maintained a strong collaborative relationship with the partners in this programme, many of whom were funded under the previous programme. Of note:

- MENTOR Initiative were a consortium partner under the previous programme but are now the lead. DFID have been impressed by the way they have managed communication between their partners and DFID. The quality of their reporting has been noted in particular.
- The agreement with Solidarités International (SI) has only just started but their planning appears to have improved. Concerns were raised about their planning in the previous programme given the instability in the country. Recent incidents that restricted their access to Kabo and Kaga Bandoro have not yet impacted on delivery.
- The partnership with WFP Cameroon has been open and transparent. WFP Cameroon carries out a thorough review of partner capacity, experience and performance to inform partner selection. Expectations for progress reporting have been clarified, as initial reports were insufficiently detailed. WFP has been able to respond satisfactorily to request for additional information. DFID is confident of the project’s performance based on field visits.

Co-ordination with other donors has been well received; SI welcomed the opportunity to meet all three of their main donors during the DFID HA recent visit in May 2017.

There continue to be some issues with the FAO and UNHCR on their responsiveness to requests for information and timeliness of reporting needs to improve. NGOs have also continued to raise concerns about the length of the contracting process and the quality of partnership management with UNHCR.

Asset monitoring and control

This programme includes two Accountable Grant Arrangements - the MENTOR Initiative-led Consortium and the Solidarités International-led Consortium - in which DFID owns the project assets until transfer or disposal is agreed. Both partners maintain an asset register in accordance with DFID requirements and physical checks will take place where possible on DFID visits.

All partners have agreed visibility statements where applicable. Recent field visits have confirmed that FAO are branding UKAid appropriately, including through their distribution sites. WFP also adhere to the agreement with WFP food commodity packages and distribution sites being appropriately branded. DFID will review other partners branding on field visits in the year or by partners sharing photographs if DFID staff are not able to visit some areas.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation

Partners have shared with DFID good evidence informing their programmes. Such evidence includes robust monitoring and evaluation frameworks, post-distribution monitoring reports, post-harvest monitoring reports and evaluation reports. Partners have provided evidence that they have disaggregated data by sex and where most relevant, by age. There is evidence that other needs have been considered, for example by UNHCR in supporting people with specific needs – an activity expanded from the target of those with physical disabilities to older people, children at risk of school dropout and patients with medical specific needs. This programme continues to contribute to DFID’s commitments on gender equality.

The programmes have also responded to changes in the caseload and needs of people affected by the crisis in Central African Republic. Overall this programme has provided useful insights and evidence on implementing effective programming in an extremely complex and insecure setting where access remains challenging.

The theory of change remains relevant to the project design and does not require review. No external evaluation of the programme have been planned or conducted. However, MENTOR Initiative have indicated that they will be carrying out a follow-up evaluation, and will consult with DFID on methodology.

Monitoring progress throughout the review period

DFID does not have a country office in CAR. DFID’s UK based humanitarian adviser (HA) provides oversight throughout the period and UK based humanitarian advisers carried out visits to Bangui in February and May 2017. During these visits, in-depth meetings were held with each partner and with a wide range of stakeholders. During field visits to programmes in Bangui, interaction with beneficiaries revealed that the assistance provided was meeting a critical need and was appropriate in terms of quality and timeliness. No field visits were possible outside of Bangui due to security conditions in the areas where visits had been planned (Alindao and Paoua). DFID has received narrative reporting from partners on progress and issues and held calls with partners on a regular basis.

DFID engaged a Humanitarian Adviser (HA) based in Yaoundé in 2015 to provide oversight of DFID programmes in Niger, Chad and Cameroon, including the CAR refugees in Cameroon under this programme. The HA has carried out two field missions since August 2016: one to eastern Cameroon to visit WFP and UNHCR funded projects, and the other to the WFP Beneficiaries Feedback and Complaints Mechanism (BFCM) call centre in Yaoundé to get an overview of the process of receiving calls, how they are treated and acted upon. The HA reviewed progress on operations in the Far North and Eastern Cameroon with WFP every six weeks, and has held formal meetings with UNHCR every six weeks and ad hoc meetings with various staff each month.

Where possible, direct beneficiary feedback has been an important element of monitoring the programme, including with women, men, and young people, as well interaction as with key personnel at project level.
ANNEX – List of abbreviations

ACF	Action Contre le Faim
BFCM	Beneficiaries Feedback and Complaints Mechanism
BSFP	Blanket Supplementary Feeding Programme
CAR	Central African Republic
CBPF	Country-Based Pooled Funds
CBT	Cash-based transfer
CERT	Central Emergency Response Fund
CHF	CAR Humanitarian Fund
CHURP	Central African Republic Humanitarian and Recovery Programme 2016-2019
DFID	Department for International Development
DRC	Danish Refugee Council
ECHO	EU Civil Protection and Humanitarian Aid Operations
EUMS	EU Member States
FAO	Food and Agriculture Organisation
GBV	Gender-Based violence
GFD	General Food Distribution
HA	Humanitarian Adviser
HCT	Humanitarian Country Team (forum)
HFU	Humanitarian Financing Unit
HQ	Head Quarter
HRP	Humanitarian Response Plan
IDP	Internally Displaced Person/People
IFI	International Finance Institution
IASC	Inter-Agency Steering Committee
ICRC	International Committee of the Red Cross
IFAD	International Fund for Agricultural Development
IFRC	International Federation of the Red Cross and Red Crescent Societies
IHL	International Humanitarian Law
IMC	International Medical Corps
INGO	International Non-Governmental Organisation
IPC	Integrated Food Security Phase Classification
M&E	Monitoring and Evaluation
MAM	Moderate Acute Malnutrition
MINUSCA	United Nations Multidimensional Integrated Stabilisation Mission in the Central African Republic
MOU	Memorandum of Understanding
NGO	Non-governmental organisation
NRC	Norwegian Refugee Council
OCHA	Office for the Coordination of Humanitarian Activities
OFDA	Office of US Foreign Disaster Assistance
PBF	Performance-Based Financing
PCR	Programme Completion Review
PDM	Post-Distribution Monitoring
PHM	Post-Harvest Monitoring
RCPCA	National Plan for Recovery and Consolidation of Peace
SAM	Severe Acute Malnutrition
SDC	Swiss Agency for Development Cooperation
SENS	Standardised Expanded Nutrition Survey
SI	Solidarités International
SIDA	Swedish International Development Cooperation Agency
TSFP	Targeted Supplementary Feeding Programme
UNHAS	United Nations Humanitarian Air Service
USD	United States Dollars
UNHCR	United Nations High Commission for Refugees
VFM	Value For Money
WASH	Water, Sanitation and Hygiene
XAF	Central African Francs