Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Business in the Community: Private Sector Engagement Programme
Programme Value: £755,000		Review Date: 14th July 2017
Programme Code: 203417	Start Date: 15th July 2013	End Date: 15th July 2018

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	A	A+	A+	A+
Risk Rating	Low	Low	Minor	Minor

Summary of progress and lessons learnt since last review
Business in the Community (BITC) continues to perform strongly in the delivery of this project. Significant achievements this reporting year include production of the second insight paper which highlights key findings from BITC’s research in business’ engagement with disaster relief, a briefing on how its members have responded to Hurricane Matthew, launch of the Global Relief and Resilience Hub (a system which links non-government organisations and business when an emergency is alerted), and organisation of the International Disaster Relief category at the Responsible Business Awards.

The 2017 award entries have demonstrated an increasing sophistication in the way that businesses are approaching disaster relief. The entries included companies contributing to complex and political emergencies. Last year’s review recommended that BITC keep a watching brief for opportunities to explore and identify case studies and entries from private sector engagement in conflict affected settings. This year a number of award entries focussed on the needs of refugees fleeing conflict settings, including: Dr Zigs: for who use bubble toys to raise money and donations of aid for refugees, and offers play therapy for crowds of children in refugee camps; and Cisco Tactical Operations (TacOps): for its use of cybersecurity expertise to deliver protection for refugees and aid workers who are in vulnerable situations in the midst of a larger crisis.

A lesson highlighted this year is the value that DFID obtains through partnering with an organisation such as BITC which has considerable reach and access to business thorough its networks. This has enabled products to be developed, such as the guidance, research and Hub, at a much reduced financial cost through generous pro-bono support of BITC business partners. The convening power that BITC has through its membership has also played a strong role in being able to push this agenda to a wide business audience, and stimulate debate and engagement.

A challenge highlighted this year was the impact external issues, such as the decision to exit the EU, have on the priority that business is able to give to engaging in the award process. While engagement on disaster response remains high, a slight reduction in successful award nominations this year can be attributed to external events.

Summary of recommendations for the next year
DFID should think about options for continued business engagement in humanitarian and disaster relief beyond this project’s grant period

Before the 2018 awards cycle begins BITC plan to do an internal and external review of the process, marketing and engagement, in order to drive and improve the awards process.

Now that the Hub has been launched, thought should be given to ensuring that it is fully utilised, maintained, and continually improved.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

The UK is providing £755,000 over a five year period (2013 – 2018) to BITC to help improve the coordination and effectiveness of the UK private sector’s response to humanitarian emergencies.

It was recognised that as humanitarian needs continue to grow, the systematic use of the private sector in partnership with humanitarian actors will be important to help meet humanitarian demands.

At the time of the original business case, one of the goals the UK government set for improving the effectiveness of humanitarian support was making a network that supports greater partnerships within the humanitarian sector, including with businesses. In so doing, it recognised the invaluable role that the private sector has to play as a donor of both resources and expertise, and how it can operate in partnership with humanitarian actors to save lives.

There had been a growing sense within the humanitarian sector that, beyond monetary donations, there is insufficient guidance, support, and regulation to guarantee quality humanitarian support from businesses. Moreover, a lack of mutual understanding and communication between humanitarian and commercial actors meant that access to the opportunities which humanitarian-business partnerships represent had been severely inhibited.

This project was designed to help address this problem, and through it BITC have produced guidance and provided training to business in the delivery of humanitarian and emergency aid. They use their extensive networks and convening power to deliver this work – including being able to draw on their partners (including Linklaters, GPS and UPS) for office space to hold events, meeting publication costs and other pro-bono support.

Through the project, BITC also arrange and deliver the International Disaster Relief and Resilience Award category at the annual Responsible Business Awards which showcases the best efforts of business in humanitarian response over the year, and works to continually promote business engagement.

With pro-bono support provided by Pricewaterhousecoopers (PwC) the project has also developed a tool, the Global Relief and Resilience Hub (the Hub), which will alert businesses and humanitarian organisations to crises as they develop and will match what specific businesses can offer to a response in relation to the needs on the ground and the requirements of humanitarian organisations that are active there.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Progress towards the project outcome, The private sector operating in the UK demonstrates stronger engagement in disaster response at a corporate level, continues to be on a good trajectory. Figures for 2017 are yet to be finalised. However, the 2016 milestone of 37.5% of businesses showcasing International Disaster Relief (IDR) in corporate communications was exceeded at 57%.

Recent BITC research highlights the strong value that business places on disaster response; such as 84% of businesses agreeing that it is important for businesses to contribute to international disaster relief, and 86% of businesses agreeing that international disaster relief contributes to more stable and sustainable markets.

Overall output score and description
BITC continues to perform very strongly and the overall output score for this year is an A+. Most milestones were either met or exceeded.

International Disaster Relief: Business' Unique Contribution II was published in December 2016 for output indicator 1.3 and has 163 views to date, exceeding the target’s milestone.

Output indicator 2.1 was also exceeded with the Global Relief and Resilience Hub moving beyond the planned beta testing phase and being ready for launch on the 4th July.

Output milestone 2.2 ‘Collaboration "roundtable" with businesses and their partner NGO's on strategic responses to disasters’ was not quite met to time due to external factors, but remains on track to take place.

The most significant deliverables this year have been achieved: delivery of the awards ceremony, the Global Relief and Resilience Hub, and the Insight paper.

Key lessons
Developing strong case studies that tell the stories of business engagement in disaster relief can be a time consuming and labour intensive effort, requiring a lot of work and good will from companies involved. BITC have, however, highlighted that there is great value in developing good case studies which provide inspiring examples for others to follow, and help demonstrate what can be done and the value that it brings. These are frequently asked for them from businesses in presentations and learning events.

Key actions
Indicator 1.3 should be reviewed to ensure that it captures the range of activities that BITC will produce over the next reporting year.

Whilst engagement in the Responsible Business Awards was still high this year, it saw a drop in both entries and downloads this year across all categories including the International category. Before the 2018 awards cycle begins BITC plan to do an internal and external review of the process, marketing and engagement, in order to drive and improve the awards process.

Now that the Hub has been launched, thought should be given to ensuring that it is fully utilised, maintained, and continually improved.

Has the logframe been updated since the last review?
The logframe was updated following last year’s review. Previously the Impact indicator milestones were missing and the indicator was poorly defined. DFID and BITC worked to produce a measurable indictor.
As recommended in the previous review, output indicator 3.2 ‘number of face to face meetings with business targets’ was removed. The outcome indicator was revised to make it more outcome focussed, as previously it was set at the output level. Indicator 1.3 was also revised to take account of the broader range of publications that BITC produce.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 / Development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP).	2017 International Disaster Relief Awards held	The International Disaster Relief Awards are were held on the 4th July as planned.
1.2 / Numbers of best practice case studies identified	Fourth set of case studies published: June 2017 (15 new)	11 case studies from new award entries will be added to website as a part of the awards cycle. Additionally, guidance published this year includes a range of case studies.
1.3 / Publications referencing the business case for business engagement in disaster relief.	Second Insight Paper produced December 2016 with 150 views by May 2017	International Disaster Relief: Business' Unique Contribution II was published on the 6th December 2016 with 163 views to date. / In addition to this a Hurricane Matthew response with call to action was published, and a slow onset insight paper was published on the 20th June to coincide with World refugee day.
1.4 / Online guidance for business on engagement with humanitarian community on BITC website	Review and evaluate website guidance. Refresh and populate BITC website with Award winners and case studies	Updated guidance on disaster relief and resilience featuring grab sheets has been produced. / Award winners and case studies to be populated in July following the awards.

Key Points
As with previous years, the IDRP award process has been managed to a very high standard and to time. By the time the call for entries closed, 31 downloads of the application form had been made and 14 award entries, of which 11 were eligible, had been made. The entries were from a good geographical spread including: India, Italy, the UK and the US, and covered both multinational and national companies. BITC organised rounds of assessments to judge the entries, and following the assessments BITC prepared feedback for all companies who entered, based on the scores and comments of the assessors.

To promote a good level and range of entries BITC actively reached out to target companies during the call to entry period, and publicised the award through external networks including the United Nations Office for the Coordination of Humanitarian Affairs (UNOCHA), the Start Network, and the Disasters Emergencies Committee (DEC). A blog was produced for the BITC website highlighting the important and evolving role of business in international disaster relief.

While BITC has been very proactive in publicising the award, this year saw slightly fewer eligible applications which means there are fewer case studies to publish than expected. In part it is believed that external pressures, including the decision to withdraw from the EU, and individual internal pressures in some companies, impacted negatively on the space that some businesses had to engage in the award process.

BITC’s second insight paper, International Disaster Relief: Business’ Unique Contribution II, was produced to time by December 2016. By May 2017 150 views of the paper had been recorded. The paper highlights key findings including: 80% of businesses work with a global NGO or charity on disaster relief; 84% of businesses agree it is important for businesses to contribute to international disaster relief;
79% of business respondents have provided corporate cash donations to International Disaster Relief;
86% of businesses agree International Disaster Relief contributes to more stable and sustainable markets.

Revised guidance, Addressing International Disaster Relief and Resilience: Guidance for Business, was published to time in this reporting period. This publication is designed to support business in developing a strategy, including guidance on leveraging all the relevant tools at their disposal for disaster relief and resilience. Output 3 has a related deliverable on training sessions related to this guidance.

Under indicator 1.3, BITC put together a briefing on how its members have responded to Hurricane Matthew, and a slow onset insight paper and a call to action were published on the 20th June for World refugee day.

Summary of responses to issues raised in previous annual reviews (where relevant)
Previous annual reviews have recommended that BITC keep a watching brief on opportunities to explore and identify case studies and award entries from private sector engagement in conflict affected settings, while acknowledging that this is a particular challenge. This year saw a number of entries relating to this, including from EY who have been a leading business in understanding the international refugee crisis, Cisco for protection for refugees and aid workers who are in vulnerable situations, and Dr Ziggs providing play therapy to children in refugee settings.

It was recommended to keep in view the appropriateness of the terminology ‘international disaster relief’. In consultation with DFID the wider term ‘International Disaster Relief and Resilience’ has been used for this year’s award and publications to highlight the role of business in longer term preparedness as well as relief after an emergency.

It was recommended to consider rephrasing indicator 1.3 to help capture the wider range of articles produced by BITC, beyond Insight Papers. The indicator has been rephrased from ‘Insight papers articulating the business case for business engagement in disaster relief’ to ‘Publications referencing the business case for business engagement in disaster relief’. The delivery of the second Insight Paper was a significant milestone for this reporting year, however, and remained the logframe target. As BITC well exceeded this with additional relevant papers more work should be done to make sure that this indicator reflects the range of work that BITC produce.

Recommendations
Indicator 1.3 should be reviewed to ensure that it captures the range of activities that BITC will produce over the next reporting year.

Whilst engagement in the awards was still high this year, it saw a drop in both entries and downloads this year across all categories. Before the 2018 awards cycle begins BITC plan to do an internal and external review of the process, marketing and engagement, in order to drive and improve the awards process.

Output Title	Partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 / Number of new partnerships between NGOs and business established facilitated by BITC and supported by the "Matching Tool" (now called the Global Relief and Resilience Hub)	Live test (beta testing) of "Matching Tool" in 2017	Beta testing by BITC administrators has taken place and was shared with the Operations Group on the 15 June. The Hub is now available for registration and was formally launched on the 4th July ahead of schedule.
2.2 / Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business.	Collaboration roundtable with businesses and their partner NGO's on strategic responses to disasters. April 2017	A collaboration roundtable was due to take place around a soft launch of the Hub, but was delayed because of the election period as the soft launch of the Hub was not seen to be suitable during the purdah period. Dates are now being considered for September.

Key Points
The Global Relief and Resilience Hub (previously called the ‘Matching Tool’) is tool which will alert businesses and humanitarian organisations to crises as they develop and will match what specific businesses can offer to a response in relation to the needs on the ground and the requirements of humanitarian organisations that are active there. This was made available for registration on the 19th June and was formally launched on the 4th July exceeding the year’s milestone.

The initial plan was to have a collaboration round table at the time of a soft launch for the Hub in April at an event for 80-100 delegates. However, as a general election was called, and this launch would have fallen under the purdah period, it was agreed with DFID that it would not be the best time to soft-launch the Hub. Feedback from businesses also indicated that launching at that time may also have affected attendance rates. The collaboration event is now planned for September, and the target was only not met due to external factors beyond the project’s control.

In December, an event was organised to launch the guidance and research that BITC produced. This was hosted by Linklaters and included a ‘speed dating’ event between business and NGOs to facilitate collaboration and lesson learning between the organisations.

Summary of responses to issues raised in previous annual reviews (where relevant)

At the last review it was recommended to add in a milestone for this reporting year. This has been completed.

Recommendations
Now that the Hub has been launched, thought should be given to ensuring that it is fully utilised, maintained and continually improved.

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 / Capacity building for business to identify their unique contribution and better understand how it can be used.	Training for business on key aspects of the online guidance by December 2016. / Seminar/webinar series on key aspects on business unique contribution	BITC have delivered a number of training events over the reporting period following the publication of International Disaster Relief: Business' Unique Contribution II. Details are below
3.2 / Recommendations on role of business in disaster relief put forward to DFID to inform World Humanitarian Summit 2016 preparations	World Humanitarian Summit follow up workshop with business on the breadth of scope for private sector involvement in International Disaster Relief (IDR) by end of June 2017	The follow up workshop will be incorporated into the collaboration roundtable event (see output indicator 2.2) which has been moved to September.

Key Points
By the 2016 deadline, BITC engaged in a variety of relevant external fora for training on IDR. These included:
- 2 training events for business on disaster relief
- Presenting at Impact 2030, and Europe, Middle East, India and Africa (EMEIA) responsible business event.
- Participation in the International Federation of the Red Cross (IFRC) webex event
- BITC’s updated guidance on disaster relief includes a supporting webinar package and easy to digest ‘grab sheets’ with key information.

BITC have continued to follow up with businesses and humanitarian partners through webinars and on a one to one basis on the breadth of scope for private sector involvement in IDR. A webinar in January was held with 20 attendees and an additional 157 views of the recording. Speakers from UPS, Unilever, Philippine Disaster Relief Foundation and iDT labs spoke about the importance of business in IDR.

Individual companies that BITC have engaged with throughout the reporting period include: ARM, BT, Coca-Cola, Disney, Fujitsu, House of Fraser, Intercontinental Hotel Group, Intel and others. Discussions covered a range of topics to raise awareness of business’ role in international disaster relief, provide support and guidance on how to do it, and to understand the challenges and barriers that companies and humanitarian partners want to address. BITC has also engaged with humanitarian organisations including: Global Exchange, Start Network, The Business and Sustainable Development Commission and UN OCHA.

Summary of responses to issues raised in previous annual reviews (where relevant)
It was agreed that the previous indicator 3.2, ‘number of face to face meetings with business targets’, be removed from the logframe as this is part of BITC’s routine business rather than a specific deliverable to the project. This has been done.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost driver for this project are salary costs, development of guidance and awareness raising activities, production of the award category, relationship management with business, and the development of the Global Relief and Resilience Hub.

Cost drivers since the development and approval of the business case have not changed. This year will see a slight increase on the expenses relating to the Hub when it is formally launched.

VfM performance compared to the original VfM proposition in the business case

The value for money proposition in the original business case highlights BITC’s strategic position as a central source of advice and guidance for the private sector. Its wide network of members was noted as providing an opportunity to effect sector wide change in humanitarian response, improving the private sector’s coordination during humanitarian emergencies and offering the potential to improve the quality and effectiveness of their responses. Making funding agencies and NGOs more aware of private sector resources was also highlighted as something that would enable smarter funding decisions.

BITC has continued to deliver against these VFM objectives. BITC uses a well-established and maintained database of over 800 business members which includes relevant personnel to target on emergency response issues. BITC continually updates the database through discussions with existing and target business, and uses this data to target its guidance, research and events relating to emergency response. The Global Relief and Resilience Hub will develop more predictable and systematic collaboration between businesses and humanitarian agencies, and to help ensure collaboration is sustained.

Assessment of whether the programme continues to represent value for money

The programme continues to provide good value for money, particularly in relation to the depth of engagement that BITC are able to offer DFID with its business members. The positive progress noted at the outcome level, and the linkages that can be made to this project’s outputs indicate that this project is having an effective influence as was intended.

In addition to progress against the VFM proposal in the business case, BITC make good use of cost efficiency measures in delivering this work. BITC is able to access members’ resources for events and other activities including the utilisation of business venues, catering, and other business resources saving on procurement costs. Pro bono support has also been provided by BITC member companies on a number of activities including: publications, and the development of the Global Relief and Resilience Hub.

Working with an organisation like BITC with its strong network offers DFID considerably more reach across business as well as cost savings through the pro-bono support that they are able to obtain.

Quality of financial management

BITC’s annual audited accounts for the period were unqualified and clearly separated out DFID’s funding under this project. Project financial reporting is provided quarterly, in line with the grant agreement.

Date of last narrative financial report	03/05/2017
Date of last audited annual statement	23/11/2016

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk

The risk, identified in the business case, of there being insufficient interest and commitment among business and humanitarian agencies to pursue this agenda has remained low. BITC’s continued engagement on this agenda through this programme has helped mitigate against this.

A risk was identified with the Global Relief and Resilience Hub. It was noted that similar initiatives had not been successful because the systems were not sufficiently adaptable, and placed too high a burden on users to maintain information. BITC have been mitigating this risk through running simulation workshops and getting feedback from end-users. As highlighted in the recommendation section, it will be important to focus on mainlining interest and use in the Hub.

As noted in this review, external factors such as the decision to leave the EU have shown to have an impact on the space that business can give to this agenda.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project continues to deliver well against the planned timeframe. Each year of the project the award ceremony and associated call for proposals and judging is organised very strongly and to time. The Global Relief and Resilience Hub is has been delivered ahead of time.

Performance of partnership (s)

As highlighted in the value for money section, one of BITC’s major strengths is its access to private sector contacts and ability to convene and influence its members around issues. BITC has continued to work well in this regard with an average reach of 48,000 people per month visiting its website. Updates and information on international disaster relief are shared throughout the website and are also promoted to BITC’s 17,400 Twitter followers.

A webinar was held to promote the international Disaster Relief Award on 17 January, BITC arranged a launch event for members for the new International Disaster Relief (IDR) research in December.

DFID and BITC continue to hold quarterly meetings to discuss project progress.

Asset monitoring and control

There are no programme funded assets related to this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

As highlighted under output 1, over this reporting period BITC’s new research report on how businesses' approach to international disaster relief and resilience is changing was produced in December - International Disaster Relief: Business' Unique Contribution II.

Key findings from this research are:

- 80% of businesses work with a global NGO or charity on disaster relief.
- 84% of businesses agree it is important for businesses to contribute to international disaster relief.
- 79% of business respondents have provided corporate cash donations to International Disaster Relief
- 86% of businesses agree International, Disaster Relief contributes to more stable and sustainable markets.

Monitoring progress throughout the review period

BITC and DFID meet quarterly to discuss progress and any necessary course correction to the project.

This report was produced based on BITC reporting and meetings with the International Director.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process