Business Case

Summary Sheet

Title: / Support to the World Food Programme (WFP) to provide food, nutrition and livelihood assistance to the people affected by the conflict in Syria
Project Summary: / The programme will provide emergency food, nutrition and support livelihood recovery and build resilience for the most vulnerable people in Syria
Programme Value: £36million		Country/ Region: Syria
Programme Code: 300344	Start Date: 9 December 2016	End Date: 31 March 2020
Overall programme risk rating:	Severe
QUEST Number:	13644440

Intervention Summary

Narrative summary including why UK support needed:
DFID Syria will fund the World Food Programme (WFP) £36 million over 4 years to provide vulnerable Syrian families affected by ongoing conflict with life-saving food aid, greater access to nutritious food and assistance that rebuilds livelihoods and provides economic opportunities. WFP is the largest humanitarian actor delivering food assistance in Syria. DFID funding will help WFP to reach up to 5.74 million people, including women and children, each month in both government and opposition-held areas. WFP-procured food is delivered to beneficiaries from either Damascus or across the Turkish and Jordanian borders, via an extensive, experienced `network of international NGOs and local partners. To implement this programme, WFP will coordinate with other UN agencies. For example, WFP will work with the UN Children’s Fund (UNICEF) and UN Population Fund (UNFPA) to identify malnourished women and children, and provide them with supplementary feeding. WFP will continue working closely with the Food and Agriculture Organisation (FAO) to promote greater food production and availability of nutritious food. WFP is an active partner in the Whole of Syria coordination structure.

DFID funding will support WFP’s multi-donor funded Protracted Relief and Recovery Operation (PRRO) and contribute to the following each month[1]:
[1] There is overlap between beneficiaries in the different categories. Once they have been taken into account the total reach is 5.74 million people each month.
(1)	5.5 million vulnerable Syrians provided with general food assistance;
(2)	375,000 malnourished children and pregnant and lactating women provided with food assistance and food vouchers; and
(3)	840,000 people provided with livelihood support, such as training and food for participating in the rehabilitation and creation of community and public infrastructure.

Does the programme fit with UK/ DFID’s strategic architecture?
- This programme contributes to Objective 2 (strengthening resilience and support to crises) and Objective Four (helping the world’s most vulnerable) of the UK Aid Strategy
- It aligns with the National Security Strategy and Strategic Defence and Security Review 2015 which note the consequences of conflict and instability overseas for UK peace, security and prosperity.
- It complies with the International Development Act by contributing to poverty reduction and protection of the most vulnerable.
- It contributes directly to all of the DFID Syria Business Plan objectives (protection, resilience and conflict reduction).

Alignment with DFID’s Single Departmental Plan (SDP) results target?
The programme is aligned to commitment two (‘Strengthening resilience and response to crisis’) and commitment four (‘Tackling extreme poverty and helping the world’s most vulnerable). More specifically, it is expected to contribute to the SDP humanitarian assistance indicator of: Number of people supported by humanitarian assistance (food aid and cash and voucher transfers) through DFID support. The programme will make an important contribution by providing 5.5 million vulnerable people in Syria each year with food assistance. In addition, the programme will contribute to the SDP nutrition indicator of: Number of children under five, women (of childbearing age) and adolescent girls reached by DFID through nutrition-related interventions. By supporting an estimated 375,000 children and women with nutrition interventions, the programme is expected to contribute 0.8% of DFID’s 50 million target.

Coherence with the wider international community and partner government response? WFP is the UN agency mandated to provide humanitarian food assistance and co-lead the global food security cluster. Other donors to WFP in Syria include USAID, the EU and Germany. DFID multi-year funding will incentivise WFP to make progress on UN reform priorities as well as support HMG’s and the UN’s humanitarian objectives in Syria.

How does the programme relate to other UK aid within the specific sector?
This business case is part of a package of UK support designed to deal with the protracted crisis in Syria. We also plan to support a set of other UN agencies and INGOs to meet humanitarian needs, delivering specialised services or in areas where WFP has more limited coverage. DFID also provides core support to WFP, and DFID Syria will work closely with the Conflict Humanitarian and Security Department (CHASE) to drive forward DFID’s UN reform priorities through this programme.

Is there sufficient flexibility to learn and adjust to changes in the context?
WFP and DFID will monitor the context and jointly assess the need for adjustments at quarterly and annual monitoring visits to Beirut, and annual reviews.
The grant allows WFP to work flexibly and draw upon a number of delivery modalities (deliver aid from Damascus, across the border from neighbouring countries or via air operations) as well as different food assistance modalities (general food distribution, Food for Assets (FFA)/ Food for Training (/FFT) and cash/voucher interventions). This programme is part of a portfolio in which flexibility has been systematically built in through multiple implementers with broad geographical and sectoral coverage.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. This is a severe risk programme but this should be weighed against the high return of intervening to save lives. Mitigation actions include 3rd party monitoring, due diligence and quarterly reviews. The residual risk remains severe due to the conflict.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
MENAD will liaise with Communications Division to identify opportunities for announcements of this funding. Given the dangerous operating environment in Syria, WFP has been granted an exemption for use of the UK aid branding for security reasons. However, visibility for this specific programme will be pursued through other multiple channels, including social media, public statements, and other methods as appropriate, in line with DFID guidelines.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
This programme has been quality assured by DFID technical advisers (humanitarian, livelihoods, conflict and social development, monitoring, commercial, finance, value for money and risk). Given WFP’s track record, its experience in providing humanitarian food assistance and knowledge of the region, it is the right organization to deliver a programme of this size in an unstable environment. In October 2016 MENAD carried out a Due Diligence Assessment covering the 3 WFP hubs; Gaziantep, Beirut and Damascus. It concluded that WFP have adequate controls in place to deliver the programme. DFID will follow up with WFP to address recommendations.

Does the SRO and team have the capability and resources to deliver this programme?
Yes, the SRO is the A2 Head of Syria UN programmes and is supported by a Programme Manager, Humanitarian Adviser and Livelihoods Adviser. Further support comes from a wider Advisory team, conflict, social development, commercial, monitoring, finance and due diligence staff.

Strategic Case

Context
Syria is the world’s biggest and most complex crisis. The political, security and humanitarian implications of the war are not limited to Syria but have regional and global impact, with the involvement of multiple international and regional actors, and over 6 million people displaced.[2]
[2] http://www.unocha.org/syrian-arab-republic/syria-country-profile/about-crisis

As of 28 October 2016, there are 5.47 million people living in areas where humanitarian access is extremely restricted and approximately 861,000 people in besieged areas[3]. Humanitarian access is routinely denied, despite Security Council interventions, and starvation used as a weapon of war by the Syrian regime. Sexual and gender based violence (SGBV) and forced conscription are commonplace. Civilian infrastructure has been purposely targeted, seriously depleting essential services. The violence and brutality – which represent significant violations of international humanitarian law (IHL) and human rights law - have set a new and disturbing precedent internationally, and are conducted with impunity. This may be contributing to the rise of extremism and sectarian division, allowing extremist groups like Jabhat Fateh Al Sham and Daesh to expand.
[3] The number of people in besieged areas has recently increased to 861,000 following UN classification of east Aleppo city as a besieged location

The Syria crisis has affected different parts of the country in different ways. Areas controlled by the Syrian regime and Kurdish forces still have a municipal structure but are increasingly impoverished, with rampant unemployment and a high burden of internally displaced persons (IDPs). Opposition areas suffer dwindling basic services and major destruction of vital infrastructure. In areas where Daesh has established effective control, it has systematically denied basic human rights and freedoms and committed horrific attacks on civilians including children. Syria’s borders have been effectively closed for the last year, creating a situation where millions are unable to flee the violence and remain trapped inside the country.

The UK contributes to the international efforts to resolve the crisis by condemning abuses of international human rights law (IHRL) and by bringing pressure to bear on perpetrators. However, this has so far had limited impact, and negotiations have not yet generated a lasting ceasefire. The current shelling and bombing of Aleppo has killed hundreds and destroyed the city, including hospitals, schools and markets as well as cut off access to water and electricity.

Why should DFID provide additional humanitarian aid?
The rationale for this investment is three-fold. It ensures vital humanitarian needs are met, supports wider HMG objectives and contributes towards the UK’s international commitments.

Meeting humanitarian needs
Syria is the world’s largest, most complex and most urgent humanitarian crisis. Inside Syria, over 250,000 lives have been lost and 6.6 million people are estimated to be internally displaced.[4] 13.5 million people (80% of Syrians) live in poverty and are unable to meet their basic needs without humanitarian assistance.[5] More than 60% of the labour force is estimated to be unemployed.[6] Despite $4.7 billion of pledges delivered for 2016 (as of 28 October 2016), it is clear that the needs in Syria cannot be met with existing funding.
[4] The UN stopped counting this figure in 2014. UN Special Envoy Staffan de Mistura provided this estimate in a media conference on 22/4/16
[5] Syria Humanitarian Response Plan 2016
[6] IMF, June 2016, Syria Centre for Policy Research, March 2015

As of October 2016, the UN-coordinated Syria Humanitarian Response Plan (HRP) is only 37% funded. Additional support is required to provide urgently needed assistance to millions of Syrians in dire need of protection, food, water, medicine, shelter, education and livelihoods.

The human cost of the Syrian crisis
1. Over 250,000 civilians killed;
2. 6.6m people internally displaced;
3. One third of the population without food, 8.7 million need of food assistance;
4. 13.5m people (81% of the population) are in need of humanitarian assistance;
5. Four in every five Syrians now live in poverty;
6. Over 60% unemployed, 3 million lost their jobs due to the conflict;
7. Life expectancy has fallen by 20 years;
8. The Syrian economy has contracted 57% between 2010 and 2015;
9. Quadrupling of food prices from currency deflation and loss of agriculture.

Delivering broader UK objectives

The UK Aid Strategy 2015 commits the UK to responding to humanitarian emergencies as the root causes of instability and conflict. Such crises, if unaddressed, often have direct impact on the UK, for example by contributing to irregular migration, transitional crime and terrorism.

HMG’s vision for Syria – as set out in the UK’s National Security Council strategy – is that we see progress towards ending the Syria conflict through an inclusive political settlement, with Syria presenting a reduced threat to UK national security, and better meeting the needs of its own people. This is to be achieved through the realisation of political, security and resilience objectives.

DFID’s approach to Syria is fully aligned behind these objectives and is informed by analysis of possible scenarios. It has three key strands: i) protection and relief to meet the most pressing humanitarian needs; ii) resilience building to strengthen the capacity of individuals, households and communities to deal with the impact of conflict where they are, and; iii) conflict reduction/peace-building to support Syrian communities, including moderate voices, to mitigate local conflict, build dialogue, lay the foundations for a future political settlement and offer an alternative to extremist groups. This is underpinned by DFID engagement with the international system to ensure that UK and international resources are used efficiently and effectively, offer the best possible value for money and are well coordinated.

This intervention supports the delivery of all three DFID strands:
1. Protection and relief - By providing food assistance and supporting livelihoods and food production, this programme will help to reduce the risk of vulnerable Syrian households relying on negative coping strategies and exposing themselves to protection risks. These include early marriage of girls, child labour and high risk employment, such as illegal construction work and/or prostitution. Field monitors will ensure that women and other vulnerable groups are protected at distributions and will promote awareness among WFP staff, partners and communities on gender-based violence and sexual exploitation. Furthermore, WFP will promote respect for IHL and denounce the use of food by authorities and actors as a weapon of war through the deliberate blocking of aid to starve communities.
2. Building resilience –This programme will protect and restore livelihoods, improve the food security of vulnerable Syrians, revitalize local economies and strengthen resilience to ongoing and future conflict related shocks.[7] Specific activities include: protecting and promoting household livelihood security through food production, rebuilding assets, like greenhouses, and promoting income generation; strengthening local markets through economic recovery projects and; supporting institutions and building an evidence base for food and nutrition security at all levels. Livelihood activities will aim for a high level of participation by women, and will seek to sensitize men with regard to gender issues.
  [7] WFP Syria, Livelihoods and Resilience Strategy, 2015-17
3. Conflict Reduction/peacebuilding While not a direct objective of the WFP’s programme, several activities are expected to have a positive impact on mitigating local conflict and support conflict reduction and peacebuilding. Individual and households with a reliable source of income are less likely to engage in negative coping strategies, such as joining armed groups to engage actively in the conflict. By building resilience at the community level, local conflict can be mitigated and social cohesion improved. Key activities that protect beneficiaries (for example, awareness campaigns to increase knowledge of protection issues and IHL) also reduce the pressure to move internally and, subsequently, alleviate division within communities.

This programme will also contribute to improved information on and analysis of the conflict context in Syria, supporting the effectiveness of the international response to the Syria crisis.

Sustained and appropriate assistance, provided to those inside the country, may also be a factor when Syrians make the decision about whether or not to leave Syria and undertake the treacherous journey across the Mediterranean to Europe to seek safety and access basic services. As of July, around 80,000 Syrians had made this journey in 2016.[8]
[8] UNHCR as of 18/07/2016 - 33% of 241,263 in arrivals in 2016 were Syrians http://data.unhcr.org/mediterranean/regional.php

Realising international commitments and UN reform

The UK co-hosted the “Supporting Syria and the Region” conference in London, February 2016, securing $12 billion for the region for 2016 and future years. This programme (and the other Syria humanitarian Business Cases which will be submitted to Ministers over the coming months) will ensure that the UK is able to meet its own commitments made at the London Conference to spend £510 million in 2016 and £840 million for the years 2017 to 2020 on addressing the Syria crisis in the region. This 4-year commitment is aligned with the ‘Grand Bargain’ commitments made by the international community including the UK at the World Humanitarian Summit in 2016 to provide more predictable multi-year humanitarian financing and increase the use of cash transfers. WFP have committed to double their use of cash and vouchers as a means through which to provide support to food insecure populations in Syria. WFP’s ambition is fully in-line with DFID Ministers’ commitment to provide greater levels of humanitarian aid to affected populations through cash/vouchers. The benefits are multiple and include, respecting the dignity and greater choice for affected populations and better VfM.

DFID Syria will work with DFID’s Conflict Humanitarian and Security Department (CHASE) and the United Nations and Commonwealth Department (UNCD) to agree a set of effectiveness indicators with which DFID will assess WFP and drive forward DFID’s UN reform priorities. We will also work across the UK government to use of all our technical, policy and diplomatic instruments to allow our partners to deliver aid effectively and promptly to all those in need, including in besieged and hard to reach locations.

What are the food security needs in Syria?
A recent mid-term review of the Whole of Syria food security sector states that approximately 6.7 million people throughout the country are considered food insecure which means that the availability of, access to, and utilisation of food is extremely limited. In addition to those already considered food insecure, another 2.7 million people are at high risk of becoming so.[9] [10] A standard family food ration for one month now costs an average of USD160 compared with USD20 before the crisis, an eightfold increase, and more than the salary of a school teacher (USD40 per month). It is estimated that 80% of households across the country are struggling to cope with a lack of food or money to buy food, particularly in areas where income generating opportunities are now extremely limited on account of the conflict.[11] Dwindling resources mean that it is often beyond the capacity of vulnerable people to cope physically and financially with the impact of conflict and resulting displacement. The unemployment rate has risen to 54% in 2016, from 10.3% in 2011. The loss of livelihoods has eroded economic resilience.
[9] Food Security Sector Whole of Syria Mid-Year Review 2016
[10] Population in Need – data September 2016
[11] Whole of Syria Food Security Sector Mid-Year Review 2016

Syria is a semi-arid country with a fragile environment, scarce water resources and is prone to drought. A prolonged drought affected around 1.3 million people and the livelihoods of an estimated 800,000 farmers and herders from 2006 to 2010. Environmental challenges multiply the conflict-related stress faced by the agricultural sector.

Food insecurity is higher in rural settings than in urban areas which have more markets and potential income earning opportunities through greater access to jobs. However, massive displacement of food insecure IDPs to urban areas has significantly increased competition for employment opportunities.

Food insecure households cope by relying on cheaper and lower quality foods; borrowing food and depending on friends and relatives; reducing the size and number of daily meals; and reducing consumption by adults in order to prioritise food for children. Such low quality diets, combined with reduced access to health services, increase the population’s vulnerability to malnutrition and disease. The food security outlook could worsen during 2017 due to restricted trade flows, closure of border crossings, currency devaluation, high transport costs, drought and large-scale refugee returns to Syria.

How does DFID propose to address these needs?
DFID proposes funding WFP as part of a wider package of support to UN agencies, the Red Cross/Crescent and international NGOs to collectively deliver improved food security outcomes in Syria. The majority of WFP funding (80%) will support food distributions and meet immediate, life-saving needs of up to 5.5 million of the most critically food insecure families.

WFP is well placed to operate at sufficient scale and with a large enough footprint across the whole country, operating both from Damascus and the region to deliver food assistance across the border into Syria. As the co-lead for the Food Security and Livelihoods Cluster, WFP is in a position to coordinate food security assistance across Syria, thereby helping to ensure complementarity between all humanitarian partners supported by DFID. Such leadership is vital to enable coherent planning and response across the whole of Syria.

DFID is also funding several large international NGOs and the Red Cross to complement UK support on food security channelled through WFP. By working through a number of partners, the UK will be ensuring that its response is responsive to the geographical distribution of need.

Impact and outcome expected
The impact of this programme is to save lives, protect civilians, reduce suffering and build resilience, and will be achieved by alleviating the critical food needs of 5.74 million conflict affected Syrians. Figure 1 below shows the results chain for this programme. UK-attributable results will be calculated according to the percentage of the PRRO that DFID funding accounts for (at this stage the indicative DFID percentage share is 2%).

Results Chain (Figure 1)

Support to WFP to provide food, nutrition and livelihood assistance to the people affected by the conflict in Syria

OUTPUTS				OUTCOME		IMPACT
1	Provision of general food assistance to vulnerable Syrians	80%		Critical food needs alleviated among conflict affected individuals in Syria		Lives saved, civilians protected, suffering reduced and resilience built
2	Provision of in-kind food assistance and vouchers specifically designed to treat acute malnutrition among targeted children and pregnant and lactating women	10%
3	Provision of livelihood support to targeted individuals	10%

In order to achieve these changes, DFID will support the following key activities:

Emergency provision of food. Food distributions will meet immediate, life-saving needs of up to 5.5 million of the most critically food insecure families. General food distributions are widely used and are based on the assumption of continued access to target populations. Acknowledging the importance of bread in the Syrian diet, WFP will maintain its dual approach to distribtion of wheat flour – direct distribution in rural areas where families traditionally bake their own bread; and channelled through local bakeries in urban settings experiencing bread shortages. As part of its emergency response, WFP is enhancing its capacity to rapidly respond to sudden displacement. This will involve providing ready-to-eat (RTE) rations during the initial days of displacement when cooking facilities are unavailable. Due to the experience of providing food aid in Syria, and the strong evidence base that the majority of Syrians still require life-saving assistance, WFP will initially use the majority of DFID’s funding (80%) for the emergency provision of food.

Over the four years of this programme WFP will gradually replace food distributions to urban areas with cash/voucher transfers. This transition will depend on local context. Cash/vouchers are not regularly used by humanitarian organisations in Syria, mostly due to the limited capacity of downstream partners to implement. However, this is slowly changing with local authorities approving cash training and capacity building for the Syrian Arabic Red Crescent and other partners in early 2016. WFP is currently undertaking market assessments to ensure the environment inside Syria offers a safe, secure and accountable delivery mechanism for cash-based programming and that partners are able to demonstrate capacity to design, implement and monitor programmes effectively. With DFID support, WFP will work with the Cash Leaning Partnership (CaLP) in strengthening the capacity of WFP partners to effectively deliver cash and voucher programmes.

WFP has developed household vulnerability criteria to better target this transition and will make decisions based on: household size and number children; displacement status; whether the family has access to adequate shelter and a source of income; if the household is headed by a female or child; and vulnerability of household members (i.e. presence of a disabled or chronically ill child, PLW, elderly or disabled).

Ensuring WFP contributes to strengthening local markets and improving household purchasing power through Cash Based Transfers (CBT) is vital. It is also important that WFP understand the different gender needs and impacts of CBT. Tailored approaches are required to move from protecting vulnerable groups, including women and female-headed households, to empowering approaches that build resilience during both the conflict and into the longer-term. WFP is currently undertaking market assessments (including joint assessments where possible) to determine the feasibility of CBT. Improving the use and coordination of cash-based programming supports DFID and WFP Grand Bargain commitments.

In areas where cash based transfers are not feasible, E.g.due to security risks to WFP staff /partners/beneficiaries, associated with managing a cash transfer system in a volatile conflict environment, WFP will use Food for Assets (FFA) and Food for Training (FFT) to engage beneficiaries in livelihood activities. FFA will provide beneficiaries with food for participating in the rehabilitation and creation of community and public infrastructure. The FFT tool will be used for vocational training – food will be provided as an incentive to attend training. Improving household and community physical and natural assets enhances community resilience to sudden-onset shocks and removes reliance on negative coping strategies, thereby contributing to overall household food security.

Livelihood recovery and resilience building (initially 10%). Following the implementation of pilot activities in 2016, WFP will build on lessons learned and progressively implement interventions that protect and restore household and community livelihoods and food security in stable and accessible areas of Syria.[12] This includes activities that build community assets and local infrastructure (such as rehabilitation of bakeries and irrigation systems) and strengthen local capacities. Livelihood programmes will include agricultural projects in rural settings and public work programmes, through cash for work support, in urban areas hosting large numbers of IDPs. These programmes will be delivered in partnership with local implementing partners and other UN agencies (particularly FAO and UNDP). WFP will target small-medium producers and manufacturers impacted by the conflict, who have the capacity to generate employment and stimulate markets. Ensuring that WFP boosts local food supply chains, creates employment opportunities and sustains local industries is crucial.
[12] Stable areas are those that are relatively free from conflict and can be accessed by either WFP or their downstream partners

Nutrition Interventions (10%). In partnership with UNICEF, WFP will implement nutrition-specific interventions, including preventative supplementary feeding programmes to treat and avert acute malnutition and micronutrient deficiencies among children (6 months to 5 years) and pregnant and lactating women (PLW). There is a high risk of malnutrition among PLW and their children in their crucial first 1,000 days, as food prices have increased and women may not have access to fresh food. WFP will expand current support to improve dietary diversity. This will be achieved through the distribution of vouchers to PLW which can only be used to purchase fresh food items (dairy, meat, fruits and vegetables) from designated supermarkets.

A focus on protection is an integral part of all WFP programmes and is reflected in the PRRO. For example, WFP will ensure that beneficiaries can collect their food in a safe and dignified manner, and will prioritise the safety of women and the elderly. WFP will also establish systems that guarantee assistance is received by the sick and those with disabilities who may not be able to physically access distribution sites. WFP field monitors will ensure that women and other vulnerable groups are protected at distributions and will also promote awareness among WFP staff and partners and communities on protection risks, gender-based violence and sexual exploitation. WFP has a responsibility to not only reach people in need with food assistance but to also ensure that they receive it in a manner which does not expose them to harm and, if possible, contributes to their broader protection.

WFP will also implement school feeding activities and provide fortified date bars and milk to children in areas with a high prevalence of food insecurity. Currently there are 2.1 million children out of school and Syria is suffering the largest reversal of education progress ever recorded. While available evidence suggests that school feeding can improve participation in schools and test scores, this is based on analysis from low and middle-income countries. The evidence base outlining the impact of school feeding programmes in fragile or protracted conflict situations is minimal. We will target marginalised children, including those heading households and those with disabilities or chronic illness, through direct provision of food, livelihood support and nutrition interventions designed to treat and avert acute malnutition. DFID will not directly fund WFP school feeding activities. This approach is consistent with previous DFID support to WFP in Syria.

Gender Equality Act

This programme meets the requirements of the International Development Gender Equality Act 2014. DFID will continue engaging with WFP on its gender and protection strategies. Response to gender-specific needs, promotion of gender equality and consideration of opportunities to empower women and girls are mainstreamed into all WFP programming. This is in line with the WFP Global Protection Policy and WFP Regional Gender Policy 2015-2020 Implementation Strategy. Best practice in terms of gender mainstreaming and protection actions will be integrated as much as possible into programmes and WFP has a dedicated protection and gender specialist based in Syria. Data will be disaggregated by sex, age and for disability, which will allow for greater transparency (as required by both WFP and DFID’s commitment to the Grand Bargain). As this programme transitions into protracted relief and recovery activities that promote resilience building and gender equality, empowerment of women and girls will be continually assessed and encouraged.

Terrorism and Financing

UN agencies are not legally subject to UK counter terrorism legislation but DFID mandates all partners to ensure funds do not support terrorist activity. WFP has confirmed that it complies with all relevant UN anti-terrorism resolutions and sanctions. DFID will share with WFP a list of organisations and individuals that are sanctioned by the European Union to ensure that UK funds are not used to support them A clause banning the financing of any terrorist activity or individuals will be included in the project MOU, under UN Security Council Resolutions including S/RES/1269 (1999); S/RES/1368 (2001); and S/RES/1373 (2001).
## Appraisal Case

What are the feasible options that address the need set out in the Strategic Case?

In 2016 DFID Syria Team conducted a portfolio review to consider Agencies that were best able to deliver the strategic objectives outlined in the Syria Business Plan. All agencies were evaluated according to their ability to design programmes that deliver DFID’s strategic objectives and manage and monitor these programmes in line with DFID corporate requirements and tolerance regarding risks. The Strategic Case identified the large scale need for food security, nutrition and livelihoods support. In this appraisal, four options have been considered for addressing this need:

Option 1:	Do nothing
Option 2:	Provide country earmarked funding to WFP for Syria crisis
Option 3:	Provide core funding to WFP’s global activities through DFID’s Conflict, Humanitarian and Security Department (CHASE)
Option 4:	Deliver this outcome through funding NGOs/Red Cross Movement

Option 1: Do nothing (counterfactual)

The UK is one of the top five donors supporting WFP activities in Syria. Previous appeals have been underfunded, for example in 2016 WFP only secured 75% of the funds required[13]. The UK remains one of the largest contributors and without our support, it is likely that WFP PRRO will be seriously underfunded. This would result in WFP reducing its footprint across the country, the amount of food provided to those in need, and/or overall beneficiary numbers. With no support from WFP, beneficiaries may suffer from acute malnutrition, resulting in increased morbidity and mortality.
[13] According to the Financial Tracking Service (FTS) as at 9/11/16

Without the predictability of UK support, WFP would also be limited in its ability to plan for the longer-term, resulting in significant food security gaps in the overall Syrian response.

Option 2: Provide country funding to WFP for the Syria crisis as part of a wider package of support

Successful delivery of this large-scale programme, while ensuring value for money, will require significant logistical capacity and the ability to rapidly assess changing beneficiary needs, coordinate and work with a range of partners, including local NGOs, procure at scale and deliver rapidly. WFP has consistently demonstrated its capacity to operate at significant scale and provide its services in almost every area of Syria, including those classified as besieged and hard-to-reach. WFP has been at the forefront of emergency operations in Syria since 2011 and is in a very strong position to continue strengthening its own and partners’ operational capacity. WFP is already providing food to nearly 4.2 million people a month and is able to increase its reach even further in response to emerging needs and continued access. By contributing to WFP’s 2-year multi-donor PRRO as well as future appeals, DFID would be funding the UN agency mandated to provide humanitarian food assistance and co-lead the global food security cluster, logistics and emergency telecommunication sectors. WFP also actively participates in the education, nutrition and protection clusters.

This funding would be allocated directly to the WFP response in Syria but complemented by our support to other agencies and INGOs working on food security.

Option 3: Core funding to WFP through CHASE

Providing additional core funds would show a commitment to WFP as the UN agency mandated to provide humanitarian food aid and to co-lead the global food security cluster. Core funding could be delivered through the existing DFID-supported CHASE financing arrangement and be allocated in such a way that improves overall WFP Syria operations.

However, funds would not be earmarked for Syria and it would be difficult to influence where core funds are allocated by WFP. Resources would be allocated by WFP’s Strategic Resource Allocation Committee (SRAC) based on need and operational shortfalls. This option would make it more difficult to meet the Syria conference commitments.

Option 4: Deliver this outcome through funding NGOs/Red Cross Movement

DFID is separately funding a number of large international NGOs to provide more limited food aid and livelihood development across Syria. These organisations work across the border from Turkey and Jordan, and inside Syria from Damascus. DFID also supports the Red Cross/Red Crescent Movement to build the capacity of the Syrian Arabic Red Crescent (SARC) and distribute emergency relief items (including food), undertake livelihood activities and provide cash-based programming.

To implement food assistance programmes at the scale proposed by WFP, it would require INGOs and the Red Cross, many of whom work as downstream partners for WFP, to substantially increase their presence and capacity to reach the same numbers of beneficiaries. No INGO has the mandate or experience to coordinate the entire food security response in Syria and ensure comprehensive coverage to conflict-affected Syrians. Increased funding to INGOs would also increase fiduciary risks as it is DFID’s assessment that these organisations do not currently have the capacity to absorb the same levels of funding as UN agencies. There is therefore a strong rationale for INGO funding to complement rather than replace funding to WFP.

Costs and benefits
Figure 2 on the next page considers the different ways DFID could support WFP over the 2 years and subsequent Appeals.

Conclusion of Appraisal case
The preferred option is to provide country funding to WFP for the Syria crisis (Option 2). This option will deliver at the scale required in this context and will provide specific results which can be attributed to DFID’s Syria response, which is not possible under options 3 and 4. It will also support leadership of the food security sector. This will complement DFID’s support to other UN agencies with specific mandates/target groups and INGOs delivering specialised services or in areas where WFP has more limited coverage. This option is strongly aligned with the UK Aid Strategy, the Grand Bargain and DFID’s Syria Business Plan.

Figure 2: Appraisal Options

	Option 1: Do nothing	Option 2: Country specific funding to WFP for Syria crisis	Option 3: Core funding to WFP	Option 4: Deliver this outcome through funding NGOs/Red Cross Movement
Cost	£0 million	£36 million	£36 million	£36 million
Mechanism	Do nothing	Provide country specific funding to WFP to support the Syria crisis. Results can be attributable to DFID.	Additional core funding to WFP through CHASE. No guarantee that UK funds will be allocated to the Syria crisis and may be disbursed to other WFP activities or global responses.	Provide funding to a range of INGO's and Red Cross Movement working in Syria.
MENAD management time	Low: some time required to response to enquiries on why DFID is not funding WFP’s Syria response	Medium: Administration time for managing and monitoring is Deputy Programme Manager 0.3 and Humanitarian Adviser (0.4 FTE); SRO (0.1 FTE)	Medium/Low: time required to engage on Syria issues. This is estimated at 0.2 to 0.5 DPM (no SRO). It would also require management time from both CHASE and MENAD to establish modalities.	High: Deputy Programme Manager up to 0.5, Programme Officer 0.2 and Humanitarian Adviser (0.4 FTE); SRO (0.3 FTE). The transaction cost to DFID will be high due to the number of partners needed to deliver at the scale required.
Dialogue on DFID issues, (i.e. targeting and Whole of Syria approach)	None	Dialogue with WFP will be around Syria specific issues. These discussions would be aligned with wider DFID issues, such as the Grand Bargain	Dialogue would be on broad DFID issues rather than Syria specific. It is feasible that DFID could raise Syria-specific concerns. Increasing overall core funding would increase our leverage with WFP.	Dialogue with partners will be around Syria specific issues. Coordination would be difficult and time consuming.
Results	None. Humanitarian situation worsens. Without WFP, beneficiaries would lack vital food support.	Allows for Syria specific results. Increases dialogue and ability to influence on Syria specific issues.	Difficult to attribute DFID-specific Syria results. And reduced ability to influence WFP’s operations in Syria.	Allows for DFID specific results. Investment would strengthen civil society in their response but coverage in the regime held areas would be reduced.

Achieving DFID objectives	None	STRONG: MENAD has been supporting WFP inside Syria for 4 years. The Annual Review score for 2015/16 was A.	LIMITED: This modality has not been tested with CHASE and it would reduce DFID’s ability to contribute to and influence WFP’s response in Syria.	LIMITED: Very few INGO’s work out of Damascus, therefore access to Government controlled parts of country reduced.

Theory of Change (ToC) for preferred option
The theory of change is based on the argument that by WFP providing general food assistance, livelihood support and nutrition, the recipients will have improved access to sufficient quantity, quality and variety of food to cover their essential nutritional needs and become increasingly food secure. The theory of change assumes that beneficiaries will have appropriate access to health care, water, shelter and protection to allow them to biologically utilise the food they consume allowing them to attain or maintain good health. As a result, lives will be saved, civilians will be protected and resilience built. The causal linkages between outputs, outcomes and impact are listed below, as well as key assumptions at each stage.

Figure 3. Theory of Change Diagram

Strength of the Evidence Base

Food Security Support
There is very strong evidence that delivering food, livelihoods support and nutrition, will meet critical food needs, reduce suffering and save lives.[14] However, for this to happen, interventions need to take into account the dietary needs and cultural habits of the population and be directed according to communities and households specific needs. Food and food security type interventions must be fair, accountable, and transparent and gender sensitive. Distribution to women is recommended for two main reasons: first, women often have the primary role in household food management; second, because women are more likely to use food aid for nutritional purposes (as opposed to sale or exchange for other goods). WFP will draw on its extensive experience of delivering food assistance across Syria, to ensure its food security interventions comply with the above principles and approaches, in delivering the expected outcomes.
[14] E.g. ICRC Nutrition Manual for Humanitarian Action: https://www.icrc.org/eng/assets/files/other/icrc_002_0820.pdf

Cash and Vouchers and Cash for Work (CFW)
There is a significant and growing body of evidence demonstrating that cash-based interventions can act as a viable and safe alternative or complement to in-kind assistance. Cash-based interventions support local business and markets. People often prefer receiving cash as it gives them greater choice and control over how best to meet their own specific needs, and a greater sense of dignity. Vouchers provide an alternative to cash, particularly in less secure environments. However, vouchers set restrictions on the vendors with which they are used and the creation of monopolies can lead to higher prices. Vouchers may be sold for less than their value in order to access cash.

There is good evidence that CFW interventions can provide a valuable additional source of income, and address basic needs including food[15]. CFW is also more effective than food for work as it provides households with a flexible amount to meet changing needs. CFW projects normally yield very positive short and medium-term results and can lay the foundation for longer-term structural impacts. Enhanced short term welfare gains can include improved economic conditions, household food security and health, all generated by the construction of communal infrastructure facilities. Longer-term benefits can include upskilling of individuals, changes in motivational and behaviour patterns as well as increased ownership. If adequately designed, CFW programmes can also provide new skills which in some cases lead to permanent employment after the CFW activities have ceased[16].
[15] http://odihpn.org/magazine/comparing-the-efficiency-effectiveness-and-impact-of-food-and-cash-for-work-interventions-lessons-from-south-sudan/
[16] http://www.cashlearning.org/downloads/resources/evaluations/gtz-cfw-in-afghansitan-lessons-learnt.pdf

Cash transfer and voucher programmes can also make limited humanitarian resources go further. They usually cost less to implement than in-kind assistance because aid agencies do not need to transport and store relief goods.[17]
[17] ODI Report of the High Level Panel on Humanitarian Cash Transfers. September 2015

Multi-year financing – evidence on overhead costs and transaction costs: There is some evidence that operational costs may be lower under multi-year funding arrangements as agencies are able to negotiate longer term contracts with implementing partners and suppliers, at reduced costs. There is strong evidence that predictable funding can allow agencies to procure inputs such as food, with significant savings. WFP has demonstrated savings of between 23% and 33% of the cost of commodities on average. There is strong evidence that response time can be decreased by half through flexible funding, as proposed under this BC. Limited evidence suggests that this time saving can result in reduced food deficits, though there is a good deal of variation.

A 2015 CHASE review of multi-year humanitarian programmes concluded that DFID reduces process and transaction costs by supporting multi-year programmes. This leaves staff more time for meaningful engagement to monitor and adapt programmes as well as to advocate for changes and improvements with partners. The review also found that multi-year arrangements strengthen the humanitarian system in-country by providing predictable financing and a greater focus on delivery as time is freed up from the annual cycle of programme design and fundraising. This is likely to result in better preparedness and early action.

Building Resilience: The multi-year approach will enable us to increase our focus on prevention. There is clear evidence that benefit to cost ratios of investing in resilience range between $2.3 and $13.2 of benefit for every $1 spent.[18]
[18] Value For Money of multi-year approaches to humanitarian funding, Cabot-Venton, April 2013, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/204946/Cost_Effectiveness_of_Multi-year_Humanitarian_Funding_-_Final_Report.pdf , accessed June 2015

Remote Control Operations: The most successful examples of remote management involve coordination structures that are rooted in the local context, with the potential for building ongoing and sustainable local capacity in humanitarian action. Research indicates that under such arrangements, programme quality expectations may need to be adjusted down, but standards can and should be higher than they are currently. Where possible, incorporating an ‘exit strategy’ or transition planning from remote controlled operations, will assist actors to think about long term humanitarian and resilience building goals.[19]
[19] Humanitarian Outcomes, Once Removed, Lessons and challenges in remote management of humanitarian operations for insecure areas. 2010

WFP have demonstrated an ability to manage operations remotely over the last four years in the Syrian context. Please see Management Case below.

Vulnerability and Gender
This programme aims to address food security needs and provide assistance to the most vulnerable groups, including IDPs, families with children living in hard-to-reach and besieged areas, people living with disabilities, and the elderly. All activities will be informed by women’s inputs from design and implementation to evaluation. The timing and type of activities are based on negotiation/consensus to best meet family and community needs. For example, since 2015, WFP has enhanced its protection activities by improving the design of many food distribution points to make them more accessible, dignified and safe. Targeting for relief activities, including life-saving food and nutrition interventions, as well as for self-reliance assistance, are based solely on needs and account for different vulnerabilities as identified through assessments, monitoring data and engagement with beneficiaries.

WFP will include culturally appropriate livelihood activities that can be undertaken by women, ensuring they are not exposed to violence or backlash. An overall consideration of the changed role of women in the Syrian context, following nearly six years of conflict, will also inform the types of programmes that WFP provides. Many women are now the sole income earners, so programmes must consider how to ensure women’s participation given changed cultural norms, while also allowing women to undertake their daily tasks.

Provision of food assistance to both IDPs and host families will contribute to reduce social tensions and ease pressure to engage in negative coping mechanisms. Livelihood interventions targeting women and youth will be prioritised and will focus on vocational training to obtain new skills and employment opportunities. Livelihood activities will aim for a high participation of women, while simultaneously ensuring the sensitisation of men on the targeting processes. Investment in human capital will also focus specifically on women and youth. Participants will be trained and supported to enter the labour market through a start-up grant or in-kind package for small business establishment. Other areas include agriculture and farming, livestock care, food processing and preservation. These initiatives will be designed in close consultation with women and youth taking into account their abilities and preferences, as well as their other obligations. Female headed households and those with disabled members, particularly children, will also be targeted by WFP. Ensuring livelihood opportunities are provided to these particular groups is vital to prevent a spiral into harmful coping strategies.

Conflict sensitivity and Sustainability
The DFID Syria Team has developed a set of standards to assess the conflict sensitivity of partner programmes. These require partners to a) undertake ongoing and participatory conflict analysis and ensure conflict sensitive implementation; b) build downstream partners’ capacity on conflict sensitivity; c) have conflict sensitive polices in place regarding recruitment, communications and procurement; and d) monitor conflict related risks.

WFP is a signatory to the Peace Promise that was announced during the Word Humanitarian Summit in Istanbul (May 2016), which commits signatories, among other things, to conduct contextual, risk and conflict analysis regularly and ensure conflict sensitive programming. In line with these commitments, at the corporate level, WFP has a unit dedicated to Emergency and Transition Programming, which supports country offices and the regional bureaux. The unit’s guiding framework includes conflict sensitivity as a key pillar.

At the Syria level, while WFP designs their interventions on the basis of detailed needs and risk assessments, and consults beneficiaries regularly, they currently do not undertake ongoing and standardised conflict analysis. However, WFP has a Vulnerability and Analysis Mapping unit that publishes monthly market analysis and shares this with other partners. This is crucial as the impact of WFP’s intervention on markets is a key conflict sensitivity risk. WFP also employs monitoring teams which assess the impact of WFP support at both the family and community level. This is supplemented by Third Party Monitoring (TPM) data collected in areas where WFP staff have limited access. These measures and a good awareness of how potential tensions between IDPs and host community can be avoided through targeting, indicates that WFP has an adequate understanding of conflict sensitivity risks, although a more formalised approach to monitoring these should be adopted. Greater focus should also be placed on understanding the impact WFP support has on the war economy and how this risk can be managed.

We have obtained WFP’s commitment to working with us to strengthen their capacity on conflict sensitivity on the Syria response in line with conflict sensitivity standards and a plan will be developed within the first quarter of this intervention detailing how this work will be taken forward over the next six months. DFID Syria will closely monitor WFP’s performance at quarterly reviews to ensure conflict sensitivity is fully integrated into WFP’s project and risk management processes and will formally assess performance at the annual review stage.

Resilience
This programme recognises the need to strengthen the capacity and resilience of households and communities to cope with the protracted crisis in Syria by progressively moving towards a stronger livelihoods focus. Ongoing conflict in Syria is punctuated by spikes in violence that cause major displacement, damage vital infrastructure and increase the population’s vulnerability and poverty levels. Syria has lost four decades of human development gains and poverty levels have increased to 80% since the onset of the conflict. As the crisis becomes increasingly protracted, its multi-dimensional consequences are severely felt by individuals and communities throughout the country.

In line with their Vision 2020 and Livelihoods and Resilience Strategy (2016), WFP aims to protect and restore livelihoods and food security for conflict affected populations. They will do this on top of their central food security role by building linkages to other actors and activities that will promote a more resilience focussed approach. WFP will build the capacity of individuals, households and communities to withstand ongoing and future shocks and stresses arising from the conflict.

Emergency food assistance and interventions that promote livelihoods can play a crucial role in the development of absorptive and adaptive capacities.

Absorptive: Food rations and vouchers allow beneficiaries to improve their food and nutrition security and absorb the shock of food scarcity/inaccessibility without skipping or reducing meals. Furthermore, these activities discourage negative coping strategies such as selling productive assets, accumulating debt, removing children from school, child labour and others that could cause permanent and negative impacts for families over time.

Adaptive: Cash-based interventions, skills development and access to markets help households adapt their livelihood strategies to the changing context and develop new ways to earn a living. DFID recognises the role of markets in building resilience, including to avoid reliance on external aid and build local capacities and resources. Large-scale humanitarian interventions can undermine markets that have already been weakened by conflict. By looking at localisation of production and rejuvenation of local economies and activities that promote self-reliance, this risk can be mitigated and markets can be supported throughout the conflict.

Likely impact on climate change and environment
Overall, this programme should not have a significant impact on the climate or environment. However, WFP will assess the potential for any environmental impact, especially if the scale of activities that access water resources becomes substantial, as reflected in the shift towards livelihoods activities (such as urban gardening, irrigation, etc.).

WFP coordinates with key stakeholders to assess any potential environment impact of its activities and identify mitigation techniques before approval. WFP is currently reinforcing its internal capacity to enhance environmental impact analysis.

Value for Money (VfM)
This programme will deliver value for money through a combination of scale and leadership of the food security cluster. DFID Syria has improved the value for money of this programme by:
- Continuing to push WFP to reduce general food distribution and increase cash transfers.
- Declining to fund the school feeding activities in the appeal as there is little evidence of impact on the use of school feeding as a way to address school enrolment, attendance and learning, in conflict environments. Many of the most vulnerable children are not attending school.

In 2016 DFID commissioned an independent review of UN VfM processes in protracted humanitarian crisis, with a focus on the Syrian refugee crisis in Jordan and displacement in Sudan. WFP was one of the four agencies that the review considered. The review of WFP identified a number of strengths including their formal VfM framework and that they were the only agency to undertake full cost comparisons. This comprehensive analysis of unit costs allows WFP to negotiate on prices which has led to significant cost savings in the procurement of food.

In addition to these strengths, the review identified opportunities for WFP to improve its VfM processes, such as developing systems to support results-based budgeting and strengthening the link between inputs and outputs. DFID will use the review recommendations to work with WFP and introduce further improvements in the delivery of VfM. We will also use the 2015 Multilateral Aid Review (MAR) findings and work closely with CHASE and WFP to continually monitor VfM. These approaches will help drive efficiencies and effectiveness, and ensure DFID is maximising our contribution to WFP.

WFP use a combination of approaches to achieve VfM:

Economy
In recent years, several cost saving initiatives have been implemented, allowing WFP to reallocate resources to where they are needed most. For example, food supply agreements have been established for most commodities, which allows WFP to mitigate global price fluctuation effects, including for dry pulses following last year’s bad harvest, which caused significant price increases worldwide. Furthermore, WFP has ensured they have flexibility to substitute commodities; for example in 2016 red split lentils were substituted with chick peas given the large price difference of around $500 per MT. The procurement of all inputs, including goods, services and human resources, are undertaken competitively, thereby ensuring quality requirements are met for the lowest cost possible. WFP maintains a preference for local procurement, which allows WFP to pay more for items that are produced locally due to the anticipated secondary positive impact of such procurements on local economies. Local procurement is determined on an item by item basis.

WFP use tools to support evidence based decisions, such as the Import Parity Price (IPP) which is used to compare food and transport costs, and lead times for different options.

Efficiency
WFP operate at a scale which no other agency is able to accomplish in Syria and, as such, is able to provide VfM through bulk procurement. WFP has taken measures to ensure efficiencies in the two main cost drivers; food and landside transport, storage and handling (LTSH). WFP has decreased the rate of LTSH by 37 percent between 2014 and 2015, by reducing contracted rates and optimising the supply chain coordination between all relevant actors at the country office, regional and headquarters level.

WFP will progressively transition a portion of its general food assistance into the resilience component of its programme, with a focus on cash-based transfers (CBT). Cash transfers can make limited humanitarian resources go further. It usually costs less to get money to people than in-kind assistance because aid agencies do not need to transport and store relief goods.

WFP has established a joint UN field office. All costs at this hub are shared by the UN agencies. Armoured vehicles, which constitute a significant expense, are procured through three long term agreements initially set up by UNHCR. The Operations Management Team, which regroups all UN support services focal points, meets once a month and looks into issues of common concern, including areas where savings could be generated by working together.

Effectiveness
WFP has a track record of increasing food security whilst decreasing the use of negative coping strategies in the communities where it works. WFP use a number of outcome indicators to determine the effectiveness of its programming and the direct relationship between achieved outputs and their progress towards stated outcomes. DFID will work with WFP to refine these indicators throughout implementation.

General Food Assistance (GFA): Targeted outcomes for GFA focus on increasing food security and consumption scores while decreasing the prevalence of negative coping strategies. WFP uses indicators on food security, income and coping strategies to monitor delivery and determine the direct impact of WFP assistance. Through this approach WFP is not only able to determine impact but can calculate efficiency in terms of money spent versus results, thereby allowing for comparisons with alternative interventions and methodologies.

Food for Assets (FFA): WFP calculates the effects of increased access to assets and infrastructure at both household and community levels through Household Asset Scores (HAS) and Community Asset Scores (CAS). HAS and CAS indicators are used to assess the link between increased access to productive assets (e.g. arable land, irrigation, greenhouses, etc.) and ability to generate an income (e.g. income earned through increased yields) to determine long-term effectiveness.

Commercial Case

Funding Mechanism
The proposed mechanism of funding is through a Contribution Agreement under the WFP Framework Agreement (Memorandum of Understanding (MOU) agreed between DFID and WFP). Our funding contribution of £36 million over 4 years will be used exclusively to support WFP’s PRRO for Syria (with the exception of school feeding).

Partner Assurance
DFID has a long standing partnership with WFP at all levels and is active in driving greater WFP efficiency via improved VfM, leadership, transparency, and financial accountability, through CHASE institutional reform asks. In addition, the UK is a member of the WFP Executive Board, which provides the opportunity to influence the Agency and raise any concerns through either the Board or bilaterally as required.

CHASE is leading on a process of UN reforms which is aimed at driving greater efficiency from UN agencies and the humanitarian system as a whole. DFID Syria work with WFP to drive reform through:
1. The One United Nations CHASE Business Case which will push UN agencies to make progress against the Grand Bargain commitments.
2. The independent UN Financial Review of VfM in protracted crises recommendations.

The recent multilateral roundtable on procurement reform, aims to increase harmonisation and collaboration of purchasing and supply across the multilateral development and humanitarian system by bringing together agencies with similar requirements.

Each agency faces the challenge of:
- Harmonising systems and data
- Improving transparency
- Integrating supply chains
- Moving away from ‘lowest price decision making’.

The roundtable members are committed to an ambitious level of procurement reform, and to work together to identify areas for further collaboration. DFID will chair future meeting and arrange on a bi-annual basis as a Senior Executive Procurement Forum.

Procurement Approach and Capability
We assess WFP’s procurement approach and capability to be satisfactory. WFP is a significant procurer of goods and services and its procurement function has evolved significantly over recent years. For food, the general procurement policy is to purchase from pre-qualified suppliers through a competitive bidding process. Competitive bidding guarantees that the best possible prices are obtained and that the purchase is carried out in a transparent manner. For goods and services, the policy is to procure these at the most advantageous and competitive costs. WFP’s Syria Country Office has a team of CIPS (Certification of International Procurement and Supply) qualified staff responsible for local procurement of food, commodities, non-food items, contracting services, as well as quality assurance.

WFP will attempt to harness their supply chain expertise to build local capacity and stimulate economies for example providing technical support, training, and in some cases financial support and equipment. A high level of flexibility is built into the supply chain to respond to changes in the operating environment, including capacity to transition from in-kind assistance to cash-based programming. Recent innovations in procurement and supply chain management by WFP include benefits of the key supplier relationship programme, long term agreements, a commercial strategy and improvement of cost control.

Delivery Chain

WFP delivers assistance in Syria via five local WFP offices as well as cross border via a WFP office in Turkey and another in Jordan.

Currently, WFP offices work through 40 downstream partners in Syria and cross border.;
To ensure adequate capacity, WFP conducts assessments of the downstream partners they work with and shares these with sector clusters.

Given the scale of operations combined with the volatile context, there are inherent risks of operating through downstream partners. However, these are mitigated by WFP completing due diligence of all downstream partners giving them a thorough understanding of each partner’s capacity and geographical reach. Prior to the programme starting, DFID will review a list of all downstream partners and will include in the MoU a clause for WFP to notify DFID in advance of any changes to the list. DFID will require WFP to provide assurance through its due diligence on current and future downstream partners.

The three largest cost drivers across the lifespan of the programme are:
- Food, which constitutes 74% of project expenditures
- Landside transport, storage and handling, 10% of project expenditures
- Other direct operational costs, which constitute 6% of expenditures; the bulk of which is food packaging costs, which amount to 4% of project expenditures.
## Financial Case

Project budget

Figure 4: Total planned, profiled costs for the WFP Syria project
Financial Year Scenario 1:
2016/17	£0 million
2017/18	£12 million
2018/19	£12 million
2019/20	£12 million
Total	£36 million

The total cost for the programme is £36 million over 4 years.

The PRRO appeal is for $1.6 billion and will cover 2 years starting in January 2017. WFP has confirmed that $30 million has been pledged so far from other donors.

The UK has a Memorandum of Understanding with WFP that forms the basis for funding agreements. DFID will discuss allocation amounts and tranches to be disbursed with WFP for subsequent years. This will provide WFP with a predictable resource for the coming years. To ensure the UK does not pay in advance of need, we will monitor the levels of WFP’s operational reserves and may adjust the payment schedule accordingly. We will disburse funds by end of Q3 every year in line with the Appeal, which will contribute to our ODA target but also ensure there is minimal spend in Q4

WFP's financial systems and control are well established and DFID has provided £151m to WFP in Syria since 2011. Their performance to date shows that WFP are capable of delivering a large programme.

Affordability
Before MENAD make any disbursements we will ensure there are funds available. This project is RDEL & ODA eligible and the planned project costs will be profiled on DFID’s ARIES financial system following Business Case approval. Total operating costs for DFID to manage this project are already included in the workforce planning and do not represent any increase in overall expenditure.

The funds will be committed and transferred to WFP in sterling. WFP will carry the risk of currency fluctuations, including any fall in the value of sterling as well as retaining the benefits when there is an increase in the value of the pound relative to local currency.

Final funding allocations for future years will be contingent on developments on the ground, WFP performance and the level of need set out in appeals and needs assessments. Should there be any significant change to the conflict, DFID may change the planned contribution.

Assets
As this is a contribution to an Appeal any assets purchased would not be directly attributable to DFID. There will be no assets associated with any of the components of the programme.

Reporting
WFP Progress Reports are the principal means through which WFP informs DFID and other donors how contributions for a given project have been used and the results obtained. These are prepared annually and reports on the objectives of the project, the mode of implementation, the resources used and the results obtained. In addition DFID will receive quarterly progress reports from WFP, including a breakdown of key results disaggregated by geography and demography. WFP will also provide certified financial statements. DFID holds formal quarterly progress meetings and regular informal meetings with WFP – See Management Case.

Assessment of financial risk and fraud
WFP has a range of robust procedures in place to combat financial risk and fraud

  1. Fraud and aid diversion
WFP has a zero tolerance policy for fraud. WFP has an Anti-Fraud and Anti-Corruption Policy that applies to all WFP staff members and personnel, all activities and operations of WFP, including any project funded by WFP and implemented by WFP and any government agency and/or downstream partner, and all suppliers or other parties with whom WFP has a contractual arrangement. Anti-Fraud and Anti-Corruption policies are disseminated to staff. All staff members must pass an Anti-Fraud and Anti-corruption course. WFP has also adopted a Whistle-blower Protection Policy to guard against retaliation for individuals who report misconduct, provide information in good faith on wrongdoing by one or more employees, or cooperate with a duly authorized audit or investigation. In a volatile conflict situation, there is inevitably a high risk of corruption and fraud but WFP have considerable experience of working in high risk situations. Our due diligence assessment has assessed that WFP’s approach is appropriate to this context.

  1. Terrorist financing
Whilst UN agencies are not legally subject to UK counter terrorism legislation, DFID is clear that all partners must ensure funds do not support terrorist activity. DFID will share with WFP a list of organisations and individuals that are sanctioned by the European Union to ensure that UK funds are not used to support them. A clause banning the financing of any terrorist activity or individuals will be included in the project MOU. WFP has confirmed that it complies with all relevant UN anti-terrorism resolutions. DFID will continue to robustly monitor the extent to which WFP has counter terrorist financing mechanisms in place and review new downstream partners.

  1. Downstream partner payment
All downstream partners undergo a thorough due diligence review designed by WFP headquarters, which include vetting against the UN Sanctions List 1267. Once approved WFP enters into a field level agreement (FLA) with the downstream partner. All Field Level Agreements (FLAs) include a set of provisions on anti-fraud and anti-corruption, WFP’s downstream partners are subject to annual evaluations and are also monitored on monthly basis, as they are required to submit invoices and distribution reports every month. WFP’s monitoring and evaluation unit also provides feedback on the partners including those working in areas not accessible to WFP monitors. During Quarter 1 2017, there will be an external audit of WFP’s downstream partners.

Management Case

Management arrangements for implementing the intervention

  1. DFID Management

Within DFID the resources required to manage to programme would be:
- A2 UN Team Leader (10%): Senior Responsible Officer and responsible for effective delivery of the programme and compliance with the SMART Rules and other processes.
- A2 Humanitarian Adviser (30%): provide technical oversight of the programme and lead DFID Syria engagement with WFP in-country.
- B1 Deputy Programme Manager (40%): day-to-day management of the programme including monitoring and evaluation, financial management and arranging review visits and audits.
- Livelihoods Adviser (5%): provide technical input
- Specialist advice from conflict, social development, health, commercial, education advisers
- A1 UKRep Rome: facilitate the UK’s partnerships with WFP and lead on issues where direct contact is involved.

CHASE will lead on the UK’s institutional relationship with the WFP and work with the Syria Programme Hub to ensure consistency with wider UK objectives.

The essential elements of the oversight arrangements would be:
- Regular engagement between the DFID team (SRO/Deputy Programme Manager/Adviser) and the programme (i.e. the Adviser/Deputy Programme Manager typically speaks with WFP to engage on specific issues as they arise).
- Quarterly meetings between the DFID Team and WFP to discuss progress on outputs, financial performance and risks.
- Bi-annual week long visits to monitor progress at the hubs by the DPM and Humanitarian Adviser.
- WFP will provide a list of their downstream partners and some will be selected for stakeholder interviews as part of the DFID Annual Review process.
- Annual Reviews during the programme life and Project Completion Report at the end of the programme.
- DFID will develop a Programme Delivery Plan and Risk Register and regularly update over the life of the programme.
- The DFID contracted Third Party Monitors will undertake spot checks at least once year to ensure there are controls in place to deliver effectively

  1. WFP Management
WFP has been operating in Syria from the start of the conflict and has demonstrated that they have the capacity and capability to deliver this large programme. WFP have the required infrastructure to address the growing needs and are committed to the Whole of Syria approach.

The programme will be managed by the County Office based in Damascus, whose staff have in-depth knowledge of the context they operate in and are supported by both the Regional Bureau in Cairo and the Headquarters in Rome. WFP in Damascus is headed by a Country Director (D2 level) who is supported by two Deputy Country Directors (D1 and P5 respectively) and Heads of Units linked to the functional areas (Programme, Supply Chain (Logistics and Procurement), Finance, Administration, ICT, Security, HR, Communication, and Reporting). Heads of Field Offices oversee the running of the field offices and are supported by the senior managers (CD, DCDs, Head of Supply Chain) as well as the Heads of Units. The Programme Unit comprises of staff with significant experience in nutrition, vulnerability and mapping, emergency coordination, monitoring and evaluation. In addition WFP has 7 field offices, the head of each field office reports directly to the Country Director.
The Country Office in Damascus maintains a dedicated partnership unit, which manages all downstream partners. Partners are monitored on a monthly basis through invoicing and distribution reports.

WFP’s performance in the region is strong and in the 2016 annual review the programme scored an A, attributed to good leadership and coordination. WFP also use an emergency response roster that allows for quick deployment, and temporary duty assignments are also used if necessary.

Risks of intervention and how these will be managed
Within a significantly risky operating environment, WFP has consistently demonstrated that it can operate at tremendous scale and provide its services to almost every area, including besieged and hard to reach areas. But food aid at this scale in an active conflict can cause tensions and be an attractive target for armed groups and criminal elements. WFP’s mitigation actions to maintain business continuity include emergency preparedness, remote management where necessary and flexible contracts.

The risks inside Syria are severe as partners are delivering in an active conflict zone. As DFID staff are currently not able to travel to Syria there is no direct oversight of what is happening on the ground. However DFID mitigate this risk through an independent monitoring contract (see DFID monitoring sub section).

The severe risk of operating in Syria is outweighed by the high return of providing life-saving humanitarian assistance and supporting governance and service delivery that work towards longer term, post conflict recovery and development. Even if the situation in Syria improves, the context will remain fragile and underscore the need for a flexible approach that responds to operational risks by allowing partners to scale operations up or down, change location or carry out different activities.

The main risks to our portfolio are:
  1. Conflict and violence lead to greater need and hinder delivery of assistance
There is risk that the ongoing conflict and violence leads to increased displacement and greater levels of need within Syria. Operational risks associated with conflict include security risks and constrained access, both of which limit WFP’s ability to operate effectively within Syria. HMG are mitigating this through advocacy to facilitate a peaceful resolution to the conflict but this has so far had limited effectiveness. While aware of the limitations of advocacy efforts, we are also monitoring incidences of conflict and building conflict sensitivity, flexibility and scenario and contingency planning into all our programmes. The residual risk remains very high.

  1. Aid Diversion
There is a risk that procurement, distribution and delivery of humanitarian assistance is subject to diversion. We are working closely with WFP to mitigate the risk of fraud through strengthened due diligence (including Counter Terrorism legislation compliance), independent monitoring and verification of all WFP’s anti-aid diversion systems and controls. WFP are required to report all instances of aid diversion to DFID. Aid diversion risks are regularly monitored and WFP have controls in place such as not holding large stocks of supplies in vulnerable places. In cases when the risk of aid diversion is considered too high in a geographical area, WFP would stop delivering there.

  1. Closure of border crossings in Turkey and Jordan
There is a risk that the countries neighbouring Syria close their borders due to growing internal discontent with Syrian refugees and security fears. Closing borders results in the inability to deliver cross-border aid into Syria and an increase in vulnerability as displaced people become trapped at borders. We are continually monitoring this situation and mitigating the risk through advocacy and engagement with partners, donors and national governments. DFID continues to work closely with the Foreign and Commonwealth Office to consider all possible ways to improve cross border access, including through further UN Security Council resolutions. WFP have a number of contingency measures in place to mitigate possible border closures, including expanding aid from other locations, training of trainer’s programmes, online e-learning and remote support.

WFP has a proven track record of managing food aid and large-scale logistics operations in similar insecure contexts. Were any of these risks to materialise this would be outside our risk appetite and we would immediately consult Ministers to consider what action to take, including new measures to reduce the risks or suspension/closure of this programme.

The main risks to this programme are captured in the risk matrix below.

Risk category	Net Probability	Net Impact	Net Severity (probability x impact)	Mitigation measures
DELIVERY: Storage and local partner availability/capacity, unpredictability of population movements and aid	Likely	Severe	Severe	Compliance and negotiations with counterparts in relevant ministries; Advocacy for aid convoys to besieged and hard to reach areas to support NGOs efforts; partners scaling up online e-learning and remote support as well as using borders crossings from other countries such as Lebanon and Iraq; Continuous advocacy in internal donor group for food security funding and scale up DFID funds if required; Continuous and effective training and coordination.
FIDUCIARY e.g. Aid Diversion; aid items confiscated or stolen at checkpoints; remote project management of funds; downstream partner payment	Likely	Major	Major	Strengthened programme due diligence (including Counter Terrorism legislation compliance), independent monitoring and external verification of partner’s anti-aid diversion systems and controls; WFP due diligence on all prospective downstream partners
CONTEXT / Further deterioration of security conditions, staff safety and security, direct attacks against staff, premises and vehicles, inconsistent access.	Likely	Severe	Severe	Advocacy with the FCO and UN to facilitate a peaceful resolution to the conflict; building conflict sensitivity, flexibility and scenario and contingency planning into all DFID programmes; compliance and negotiations with counterpart in relevant Syrian ministries for convoys

WFP has their own risk management system in place and will use this to inform their decision making, in close collaboration with DFID. DFID will meet with WFP quarterly to discuss progress against objectives, context, needs and risk. These meetings will highlight any changes to the key risks and will consider the need for any additional mitigating actions.

Due Diligence
The Syria Due Diligence Assessment (DDA) was undertaken in October 2016. This was a desk based review.
In addition a Central Assurance Assessment was undertaken in October 2013. No pressing concerns were raised in the report. CHASE, as the WFP institutional lead, will be renewing the Central Assessment in 2017. Based on the response provided to the questionnaire, we judge that WFP have adequate controls in place to deliver the programme.

DFID judges that WFP has adequate tools and procedures in place to ensure that due diligence risks can be managed effectively. DFID will monitor WFP on progress against due diligence recommendations at quarterly reviews.

How will progress and results be monitored, measured and evaluated?
The annexed results framework, based on WFP’s plans, has been developed to assess performance of the programme each year. This framework will be reviewed by DFID each year to reflect changes in WFP plans.

Each year, DFID will take a percentage share of the results reported by WFP in their annual reports (this will be based on the percentage that our funding has covered of WFP’s total annual appeal expenditure). At this stage the indicative DFID percentage share of results is 2%.

WFP Monitoring
WFP have developed extensive corporate systems to ensure regular monitoring, reporting and evaluation of programme across WFP operations. In late 2016, DFID commissioned an external assessment of WFP M&E processes and systems, which documents WFP’s Syria Crisis Response M&E approach and includes recommendations for improvement. DFID Syria will work with WFP to ensure their M&E plan for the PRRO Appeal includes the areas identified for improvement.

The Country Office ensures that lessons are learned and are used on an ongoing basis to guide and inform programmes. Every six months, there is a formal review of the Annual Performance plan (APP); these reviews identify progress against monitoring criteria, which can be addressed in a timely manner. Information collected via WFP’s regular monitoring and evaluation exercises (including from third party monitoring), where hundreds of food distribution points are visited as well as monitoring at the household and shop levels, is shared with relevant units and used to adjust programmes accordingly. Examples include changes to the composition of the food basket, improvement in distribution mechanisms etc.

DFID Monitoring
DFID will meet with WFP quarterly to discuss and monitor the following areas: progress to date, context, needs, risk and aid diversion.

In lieu of DFID staff not being able to physically access Syria, DFID Syria has contracted an independent monitoring supplier to conduct and document a one-day field monitoring visit to each programme every year. As part of the development of this business case WFP have agreed to engage with and support our supplier in the planning and implementation of annual field monitoring visits. Field monitoring visits will be conducted by local Syrian field monitors and will seek to verify aspects of WFP’s reporting and develop DFID’s qualitative understanding of the WFP response. Conducting this field monitoring will inform programme management, improve DFID’s response over time and document that DFID is performing its accountability function. The outcome of each field monitoring visit will be a report that includes an overall Red, Amber, Green (RAG) rating of the programme, as well as individual RAG ratings against a set of standard questions. In addition, a set of recommendations for improvement will be compiled. These recommendations will be discussed, agreed and prioritised between DFID and WFP, and a regular update on the status of the recommendations will be provided to DFID.

In addition DFID will work with WFP to develop an assessment of WFPs M&E systems and processes.

Reporting
DFID will receive quarterly progress reports from WFP, including a breakdown of key results disaggregated by geography and demography. Up to 2016, WFP were providing key results to DFID disaggregated by Syrian governorate, sex and age group. As part of this business case and in line with the DFID Data Disaggregation Action Plan, DFID will negotiate with WFP the provision of results disaggregated further by Syrian district and sub-district, as well as by beneficiary group. This will ensure that DFID continues to build on the evidence base of what works in Syria, helps us to identify gaps in our response and ensures greater programme transparency.

Accountability to Beneficiaries
WFP consider their primary accountability is to their beneficiaries. As a result, WFP engages female and male beneficiaries at all stages of programme design and implementation, and operate a number of transparent, independent and effective mechanisms to facilitate beneficiary feedback, questions and complaints on an ongoing basis.
WFP has adopted several methodologies to ascertain the outcome and impact of programming inside Syria:
- In areas where direct access is possible, WFP undertakes post distribution monitoring and interviews beneficiaries to verify satisfaction with assistance received.
- Where direct access is not possible, WFP undertakes third party monitoring. Through this mechanism evidence is collected on whether WFP is targeting the right people with the right support. The use of remote data collection methods further enhances the evidence base in inaccessible areas and informs operational decisions.
- WFP conducts consultations with beneficiaries before implementing livelihood activities.
- WFP is also exploring ways to improve beneficiary feedback and accountability by improving automation of accountability systems, feedback prioritisation, and data tracing, management, and analysis. This would improve beneficiaries’ ability to communicate with WFP and improve WFP’s ability to receive, analyse and respond to beneficiary feedback. WFP’s pilot is set to start in Lebanon and will eventually be implemented in Syria.

Annual Review
An Annual Review of WFP’s programming will be carried out by the DFID Syria Programme team each year. This will be done in close consultation with CHASE so that information is exchanged between this and the review of WFP core funding.

Evaluation
There will not be a separate evaluation for this programme as it is a well-tested humanitarian intervention with a strong evidence base. The risks of carrying out an evaluation inside Syria do not outweigh the benefits the findings could provide. The DFID Syria team will continue to seek opportunities to feed into wider DFID evaluations such as CHASE’s independent review of the operational performance of humanitarian agencies.

Annex – WFP Results framework

Outputs	Weighting		Indicators		WFP monthly target

1. Provision of general in-kind food assistance to vulnerable Syrians	80%		1.1 Number of in-kind monthly full food rations distributed		5,500,000
2. Provision of in-kind food assistance and food vouchers specifically designed to treat acute malnutrition among targeted children and pregnant and lactating women	10%		2.1 Number of child beneficiaries (6-23 months) of in-kind food activities designed to treat acute malnutrition		240,000
			2.2 Number of child beneficiaries (6-59 months) of in-kind food activities designed to treat moderate acute malnutrition		45,000
			2.3 Number of PLW beneficiaries of in-kind food activities designed to treat acute malnutrition		30,000
			2.4 Number of PLW beneficiaries of food vouchers to treat acute malnutrition		60,000
3. Provision of livelihood support to targetted individuals	10%		3.1 Number of individuals benefitting from livelihoods activities		240,000
			3.2 Number of individuals benefitting from cash/vouchers for livelihoods activities		600,000