Business Case

Summary Sheet

Title: / Animal Health and Veterinary Science Specialist Advice to the DFID Research and Evidence Division’s Agriculture Research Team.
Project Purpose: / To provide Specialist Animal Health and Veterinary Science advice on a range of Animal Health Diseases in Developing Countries.
Programme Value: / Up to £104k		Country/Region: / Global
Project Code:	Start Date:1/10/2016	End Date:31/09/2018
Overall programme risk rating:	Minor
Quest Number:

Intervention Summary (1-2 pages)

The project will ensure that DFID’s Research and Evidence Division (RED) Agriculture Research Teams are able to access specialist animal health expertise to support the delivery of a portfolio of animal health projects. The aim of these programmes is firstly to support the development and deployment of new animal health products; diagnostics, therapeutics and vaccines for neglected tropical livestock disease that affect poor farmers, specifically targeting diseases and products which are unlikely to attract private investment. Secondly to generate evidence to support better policies and address the barriers that hinder new products getting into use. DFID’s current animal health research investment (2016 – 2020) has a total value of approximately £18m and animal health will continue to be a priority in the Agriculture Research team’s forward priorities.

Livestock play a critical role in the livelihoods and nutrition of the poor, particularly in DFIDs priorities countries. Animal diseases pose a major risk to livestock keepers, reducing incomes and the value of critical assets and exposing them to increased risk of disease. There is a well-established body of evidence demonstrating the impacts that animal disease can have on the livelihoods of the poor.

The animal health support will deliver specialist support over a 2 year period to project managers and Senior Responsible Owners (SRO’s) on the context and barriers to product delivery and deployment in DFID focus countries and the pipeline for research and development programmes. The project will enable RED to draw down on specialist animal health expertise not currently available in house but which is essential to ensure that the animal health projects are delivered on-time and that risks are identified and managed early.

What are the main programme activities?

The programme will provide up to 2 days per week specialist technical animal health advice to DFID advisers, senior managers and project Senior Responsible Owners, over a 2 year period. This will enable DFID to target investments, and identify and manage risks more effectively.

After this time we will reassess whether DFID should continue to draw upon external expertise or should build specialist animal health capacity in-house.

Impact – New technologies (vaccines, diagnostics, and medicines) to address livestock disease developed and deployed more quickly.

Outcome – More effective animal health research, development and delivery programmes.

Outputs – High quality advice supporting more effective and better informed decisions to ensure that DFID’s animal health research programme generates high quality research outputs.

Specific activities:

The project will support the implementation of the following projects:
- Global Alliance for Livestock Veterinary Medicines (GALVmed).
- AgResults programme. Brucellosis vaccine development
- Animal health components of the DFID-BMGF Strategic Agriculture Research Partnership.
- Animal health elements of the CGIAR research portfolio.

The specialist support delivered through the project will also provide specialist advice on the design of a programme on the role of agriculture in humanitarian contexts particularly advising on pastoralism in these contexts.

How will it contribute to the 2015 UK Aid Strategy, DFID’s Single Department Plan and the Business Plan of your part of DFID?

DFID’s current animal health research investment (2016 – 2020) has a total value of approximately £18m and animal health will continue to be a priority in the Agriculture Research team’s forward priorities. The use of this specialist technical advice will support the Agriculture Research team’s contribution to the delivery of the UK Aid strategy, particularly by promoting economic development and by building resilience of the poorest against shocks. This programme will complement the UK’s international commitments on nutrition. By reducing the impact of disease and increasing the productivity of domestic livestock the project will help contribute to DFIDs commitments on improved nutrition by increasing access and reducing the costs of animal sourced food. Small ruminants and small-scale poultry production play a particularly important role in supporting the livelihoods of women and girls and are often neglected by the pharmaceutical industry. By reducing the risks faced by livestock assets, the project will contribute to DFID gender commitments.

DFID’s animal health research programme is delivered in close collaboration with a range of external partners and have a strong track record of working closely to deliver high quality impact. Maintaining this access to specialist advice is essential in enabling DFID to identify options for co-investment and to manage risks within these programmes. Alternative approaches to sourcing specialist advice, including the option to build in-house capacity are reviewed in the Appraisal Case. The option to switch to building this capacity will be reviewed after 2 years.

Due to the limited and fluctuating requirement for in-depth specialist advice, DFID has chosen not to maintain deep technical in-house capability in a number of agriculture sub-sectors, including animal health. Animal health expertise does exist across the UK government, particularly in DEFRA, but that capacity is overstretched and it is generally focused on the diseases of livestock that affect temperate agriculture and solution that can be applied in the UK. These are generally not relevant to the diseases, production systems or broader developing country contexts that DFID focuses on.

This project will support the delivery of REDs animal health research programme, enabling DFID to draw on technical support, supporting the effectiveness and efficiency of investments, driving value for money across the diverse portfolio and significantly reducing programme risks. The project’s performance will be reviewed after 12 months and again after 2 years to assess the need for continued external technical support.

This is a low risk project; the external supplier has a strong track record of delivery over many years in the contexts which this technology will be deployed. The primary objective of the intervention is to reduce the risks to DFID of running specialist animal health R and D projects by ensuring DFID staff has access to the sort of specialist technical expertise they need to ensure that there is timely and effective decision-making, a clear focus on delivery and results and a management of programme risks. This fits with the overall risk appetite in DFID and will enable us to maintain a balanced risk profile across the programme.

Strategic Case

Livestock play a critical role in the livelihoods of many of the poorest and most vulnerable people in the world. In all of DFID focus countries, particularly those affected by conflict or at risk of conflict, livestock provide critical resource for the poor, providing a source of income for households and contributing to improved nutrition. Livestock often provide a vital source of cash income in households with few other options, helping people access services like education and health. Livestock often provide an important form of capital for some of the poorest people with limited access to financial services, particularly pastoralist populations, and can often play a vital social function in many communities and societies.

Domestic livestock in developing countries are at risk from a wide range of animal diseases, many of which have been largely neglected by the veterinary and pharmaceutical industry. The cost of livestock disease in developing countries is considerable, but it is a cost often borne by those least able to protect themselves against the risks of disease. Even where effective treatments are available, the products conventionally marketed in developed countries may be unsuitable for use among poor livestock keepers in developing countries. They may be too expensive or delivery may require technology, infrastructure or skills not available.

The poor, who often live in close proximity to their livestock, can be affected by zoonotic diseases like TB and sleeping sickness that pass from animals to humans. The burgeoning demand for livestock products in the developing world is driving massive expansion of intensive livestock production systems. These are predicted to grow for several decades. Concurrently, increased contact rates between poor people, their livestock and wildlife, climatic factors affecting the distribution of disease and weak regulatory frameworks will contribute to significant changes to health risks associated with livestock production in the developing world. The prevalence of and impact of zoonotic disease are predicted to increase as people and livestock become more closely associated in rapidly expanding cities.

The DFID Agriculture Research Team supports a number of animal health programmes (see Annex A) which aim to reduce the impact of livestock disease on poor communities in developing countries, addressing the full innovation chain from product discovery and technology scouting, through to product development and delivery. The aim of these is to target investment to address market failures that stop poor livestock keepers accessing the drugs, vaccines and diagnostics that could reduce the risks they face. Managing these projects effectively requires a detailed knowledge of both the technology and approach needed to develop new products and the contexts in which they are deployed.

Due to the limited and fluctuating requirement for in-depth specialist advice, DFID has chosen not to maintain deep technical capability in-house in a number of agriculture sub-sectors, including animal health. Animal health expertise does exist within other UK government departments, particularly in DEFRA, but that capacity is overstretched and it is generally not in the diseases, production systems or broader developing country contexts that DFID focuses on.

The project will ensure that DFID’s Research and Evidence Division (RED) Agriculture Research Teams are able to access specialist animal health expertise to support the delivery of a portfolio of animal health projects. The specialist advice will support DFID’s work in addressing important livestock diseases listed in Annex A and will specifically cover:

1. GALVmed Phase 2 and assistance with the development of Phase 3.
2. AgResults programme.
3. Animal health components of the DFID-BMGF strategic collaboration on Agriculture research programmes.
4. Animal Health elements of the CGIAR research portfolio.
5. Possible new programme on agriculture/livestock interventions in a humanitarian and fragile/conflict affected context.

The project contributes to the delivery of the UK Aid strategy, particularly by promoting economic development and by building resilience of the poorest against shocks. By reducing the impact of disease and increasing the productivity of domestic livestock the project will help contribute to DFIDs commitments on improved nutrition by increasing access and reducing the costs of animal sourced food. Small ruminants and small-scale poultry production play a particularly important role in supporting the livelihoods of women and girls and are often neglected by the pharmaceutical industry. By reducing the risks faced by livestock assets, the project will contribute to DFID gender commitments.

This programme will contribute to delivering the DFID Research Review objective to develop and deliver at scale new agriculture technology able to improve nutrition and help increase the resilience and productivity of developing country agriculture. It will do this by providing high quality technical expertise in the area of animal health, on new evidence which has been generated to explain what works and what doesn’t and working with the private sector to test new and innovative ways of providing the best animal health services in the developing country context.

Gender Equality: Livestock disease presents risk to both men and women, but generally there is a gender difference among livestock keepers. Women tend to keep livestock that are of lower economic and social value and that can be kept close to the homestead. The products developed and deployed by the RED animal health portfolio specifically address the diseases that affect the livestock kept by women, small ruminants (sheep and goats) and backyard poultry. These livestock and production systems have tended to be neglected by the livestock industry. Largely because of their poor social and economic value and because of the diffuse nature of demand for new products. This project will contribute to the development of products able to reduce the risk faced by poor women and men in developing countries.

Terrorism and financing: The risk of this is low. The contractor is an established company based in New Zealand.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case?

The criteria used for assessing each option is to firstly meet the needs of the DFID research team for specialist technical advice focused on the countries and diseases of most relevance to the projects in the portfolio. This will require experience not just of the livestock and diseases prevalent in DFIDs focus countries, but also of the developing country context that underpins the deployment of new animal health products. Secondly to provide fast and responsive advice, tailored specifically to the needs of DFIDs project cycle management and to do so in the short-term. Lastly a cost effective service able to provide value for money. Four options to provide animal health specialist advice on the team’s research portfolio are set out below.

1. Develop animal in-house health expertise through an external recruitment exercise.
2. Recruit short-term advice through the Expert Advisory Call-down Services (EACDS).
3. Run an open competitive tender exercise to contract a commercial supplier.
4. Contract Lifestock Incorporated Ltd on a call down contract.

Each of the options is described in more detail below and appraised later in the section.

Option 1 – This option would require DFID to seek a full-time animal health specialist with relevant developing country experience through an external recruitment. Once working for DFID and accredited to a relevant professional cadre they would be eligible to apply for other posts within DFID.

Option 2 – Recruit short term specialist advice through the EACDS, DFID external facility that enable DFID staff to access technical expertise not available in-house. This would enable us identify and contract a specialist on a fixed term call-down contract, with a great deal of flexibility. However this option would be relatively expensive due to high management rates.

Option 3. Run an open competitive competition to contract the work. This option would encourage competition from a wider field of expertise and potentially drive VFM outcomes.

Option 4 – Contract Lifestock Incorporated Ltd on a call down contract. Lifestock is a private company based in New Zealand with a track record of providing specialist animal health advice to international development organisations, the UN and private foundations. This option would require us to extend their existing contract for a fixed term on a call down basis, where we are only billed for work actually undertaken.

What are the costs and benefits of each feasible option?

We have assessed each option based on three criteria, firstly the ability to deliver high quality relevant technical support, secondly meeting DFIDs immediate need for a part-time call down contract for up to two days a week linked to our business needs, and thirdly value for money, meeting the first two criteria at the lowest cost.

Option 1: This would be a reasonable long-term solution to the skills gap; however DFID does not currently have any specific plans to recruit specialist animal health advisors for three reasons. Firstly the amount of animal health research does not require a full-time person, we anticipate only 2 days week of specialist support is needed. Secondly DFID generally recruits advisers with a range of core technical competencies that can deployed across the organisation to fill a range of posts in the UK and in developing countries. These posts vary greatly in their scope and although many advisers originally have a specialist background, all are currently employed in more general posts covering range of livelihoods and agriculture programmes. We could not deploy an animal health specialist to another post in DFID unless they met the general criteria for accreditation. Thirdly it is we cannot be certain that we could recruit a livestock specialist with the right mix of skills; previous general recruitment rounds have not identified any candidates with these skills even when these have been opened up across government. Lastly if a candidate were identified it would be at least 6 months before they could be recruited into post. So although this option does offer a longer term low cost solution, it does not meet either 1 or 2.

Option 2: The Expert Advisory Call-down Service has been in put in place to enable DFID advisers to access specialist short-term support in defined areas of expertise where DFID does not maintain in-depth skills. The system is set up to identify people who are able to respond to short-term demand. It can be used to meet the demand set out in the Strategic Case; however, it is principally designed to meet immediate business needs, not longer term advisory support, and as such has a relatively high over-head cost associated with short-term support. As a result this option, though technically feasible in terms of sourcing the right skills and timing, would be expensive.

Option 3: This option would encourage competition from a wider field of expertise and enable DFID to seek the best value for money. However, the cost of advertising and administering an open competition for a programme of £100k would be considerable and specialist advice timed to meet DFID’s requirements and limited to 2 days per week may not be an attractive option for a wide range of bidders. It would take some time before the contract is in place. In addition, once contracted, the successful bidder may need a substantial period of time to familiarise themselves with the relevant DFID programmes, which may delay advice on the programmes. This option potentially meets criteria 1 and 3, but in the interim we would not be able to draw on the support needed.

Option 4: The Company has an established track record of providing high quality technical support to DFID and has demonstrated specialist knowledge, experience and skills to effectively support DFID’s animal health programmes. Lifestock Inc’s familiarity with the programme portfolio and capacity to immediately engage brings cost benefits and meets criteria 2, a quick start-up linked to DFID’s business needs. By not going out to the market we potentially risk missing an opportunity to secure a better VFM outcome for DFID. However Lifestock Inc’s has over the past two years demonstrated an ability to respond to DFID’s technical support needs on a call down basis bringing overhead savings. PCD have negotiated to drive down fee rates to a rate around 30% below the benchmark rate established by the EACDS in option 2. We think therefore that this is the option that best meets all three criteria.

Analysis of the advantages and disadvantages of each option:
(scoring out of 5)

	Quality	Timing and Flexibility	Economy	Total
Option 1	2	2	4	8
Option 2	4	4	2	10
Option 3	4	2	4	10
Option 4	5	5	3	13

Conclusion:
Lifestock Inc offer best meets the demand from DFID for a rapid, high quality and responsive advisory support. Although other options offer potential savings, these are not certain. The preferred Option 4 of contracting Lifestock Incorporated Ltd on a call down contract has been assessed by RED’s embedded procurement adviser as offering good value for the UK tax payer. In addition, Lifestock Inc’s expertise can be immediately utilized without need for lengthy orientation and introduction to the projects identified as requiring specialist livestock support. They are familiar with DFID administrative procedures and RED strategic objectives.

Commercial Case

Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin?

All funding for this programme will be from the RED Agriculture Research Team’s programme budget. The proposed budget runs from financial year 2016/17 to 2018/19, complying with FCPD guidance.

What are the costs, how are they profiled and how will you ensure accurate forecasting?

The expected cost of the programme is £104k over two years. (Table below).
The cost will be calculated on 3 monthly workplans detailing expected call down services from the service provider. These will be tightly monitored over the lifetime of the project.

The forecasting of costs will be the responsibility of the DFID Deputy Programme Manager, based on estimates provided by the contractor. The accuracy of the financial profile and forecasting will be closely assessed as part of the quarterly and annual programme reviews.

What is the assessment of financial risk and fraud?

The contractor has demonstrated through their previous contract that they have strong financial management and accountability systems in place.

DFID has a zero tolerance policy on fraud, and will apply standard measures to ensure this policy is adhered to.

How will expenditure be monitored, reported and accounted for?

Monitoring and accounting of expenditure will take place using the ARIES system; standard DFID project management procedures for inspecting invoices to ensure Value for Money and compliance with agreed fees and reimbursable costs. The contractor will submit quarterly detailed expenditure summaries and quarterly forecasts of programme expenditure to DFID, all in an agreed format. The DFID Deputy Programme Manager will be responsible for monitoring all financial reports.

There are no accounting considerations arising from the project.

Financial Case

What measures can be used to monitor Value for Money for the intervention?

A number of measures will be used to monitor value for money for this programme.

Whilst our preferred option would always be to go to open competition for new programmes, we believe that it makes sense to continue with the existing supplier, Lifestock Inc Ltd in this instance.The key reason for this is the specialised nature of the programmes, and the associated need for a particular, expert skill set.

The company provides services to a range of development partners such as United Nations Food and Agriculture Organisations, the European Commission, OIE and USAID and it has over 30 years of development experience in Sub-Saharan Africa, the Near East, South and East Asia. The company’s key focus is on livestock research.

The company is already familiar with DFID administrative procedures, RED’s strategic objectives and its capacity to immediately engage brings significant cost benefits.

DFID will pay for advice on a call down basis and is not committed to disburse the full contract value if it is not needed.

The Senior Responsible Officer (SRO) and the Team Leader (TL) in the Agriculture Research team will manage the contract and partner’s performance. The SRO will be responsible for monitoring the quality of the support given.

The SRO, Deputy Programme Manager (DPM) and TL will maintain regular contact with the consultant throughout its 2 year lifetime and in particular will:

Monitor performance against the key deliverables.
- Receive and review written programme reports.
- Undertake a DFID annual review and project completion report in line with DFID requirements.
- Develop and agree a rolling workplan throughout the programme.
- assess eligibility for and make payments quarterly in arrears

Financial invoices and reports will be checked by DFID on receipt and any queries raised immediately with the contractor in order to clarify/resolve issues. Any ongoing concerns around their financial management will be acted upon and handled in accordance with DFID corporate procedures. This could involve but not necessarily be limited to referral to Procurement and Commercial Department (PCD) with a view to enforcing contractual conditions or internal audit as deemed appropriate.

Management Case

What are the Management Arrangements for implementing the intervention?
Oversight and management roles and responsibilities within DFID

This project will be funded by the Agriculture Research Team. The Senior Responsible Officer will provide management oversight working closely with the Agriculture Research Team Leader and drawing on inputs from relevant advisers, Senior Research Fellows, and other team members as appropriate.

The Deputy Programme Manager (DPM) will be responsible for the monitoring and accounting of expenditure, standard DFID project management procedures for inspecting invoices to ensure Value for Money; and compliance with agreed fees and reimbursable costs. The contractor will submit quarterly detailed expenditure summaries and quarterly forecasts of programme expenditure to DFID, all in an agreed format.

It expected that this contract will require a low level of management time.

The programme will be delivered through a contract to Lifestock Incorporated Ltd detailing a call down arrangement which will be issued and negotiated by the RED Procurement specialist team. The contract is below the EU regulation threshold and therefore is not subject to Official Journal of the European Union (OJEU) procurement procedures.

Lifestock’s skill sets can be immediately utilized without need for lengthy orientation and introduction to the projects identified as requiring specialist livestock support. They are familiar with DFID administrative procedures and RED strategic objectives.

Risk

As detailed in the Intervention Summary, the overall risk level for this programme is minor.
External Delivery risk is minor. For the past 2 years we have drawn on the services of Lifestock Incorporated Ltd for technical support who have in the past provided services to a range of development partners. Lifestock Inc Ltd has 30 years of development experience in Sub-Saharan Africa, the Near East, South and East Asia, directly relevant to the objectives of the RED animal health portfolio in terms of livestock species, diseases and context.

Delivery Risk is minor. Access to specialist livestock research expertise will enhance the capacity and capability of RED’s Agriculture Research team to successfully steer, implement and oversee the programme portfolio – and will therefore reduce operational risks to the team’s overall portfolio.

Safeguards is minor. The consultant has extensive experience in working in animal health programmes in the development county context.

Operational risk is minor. Reputational risk is minor. Drawing on specialist livestock research expertise when needed will enhance DFID’s capacity and capability in the management of livestock health programming, and will therefore reduce the potential reputational risk of overseeing specialist programming without the required expertise in-house.

Fudiciary risk is minor. Technical expertise and advice will be drawn down on ‘as needed’ basis from a call-down contract with the chosen partner ensuring that resources are targeting the immediate demand of DFID staff working or the programmes listed above Lifestock Inc Ltd, based in New Zealand, and has a strong track record of delivery, working for a wide range of development organisations including BMGF, the UN and the World Bank.

Reputational risk. There is a potential reputational risk inherent in contracting specialist expertise from an external partner; however, the Agriculture Research team has negotiated competitive rates with the chosen partner and is confident in the partner’s ability to provide high quality technical advice. The team does not currently require a full time animal health specialist as the advice is required on a add hoc basis which we estimate at approximately 2 days per week.

DFID has in place risk mitigating actions such as:

1. Financial invoices and reports will be checked by DFID on receipt and any queries raised immediately with the contractor in order to clarify/resolve issues.
2. Any ongoing concerns programme performance will be acted upon and handled in accordance with DFID corporate procedures. This could involve but not necessarily be limited to referral to Procurement and Commercial Department (PCD) with a view to enforcing contractual conditions or internal audit as deemed appropriate.

## Smart Guide
## The Business Case

- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFID global and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices, with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, project team etc). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.

Annex A

The specialist advice will support DFID’s work in addressing important livestock diseases such as:

African Animal Trypanosomiasis also known as sleeping sickness is a parasitic disease of humans and other animals. It is caused by protozoa of the species Trypanosoma brucei. There are two types that infect humans, Trypanosoma brucei gambiense and Trypanosoma brucei rhodesiense. Both are usually transmitted by the bite of an infected tsetse fly and are most common in rural areas.

Bovine tuberculosis (TB) is a chronic disease of animals caused by a bacteria called Mycobacterium bovis, (M.bovis) which is closely related to the bacteria that cause human and avian tuberculosis. This disease can affect practically all mammals, causing a general state of illness, coughing and eventual death. Bovine tuberculosis is an important disease of cattle and is a significant zoonosis (a disease of animals which can also infect humans).

Brucellosis
Brucellosis is a zoonotic disease that affects humans, cattle, small ruminants, pigs and dogs. Brucellosis in humans is usually a result of occupational exposure to infected animals, but infections can also occur from ingesting contaminated dairy products

East Coast Fever
East Coast Fever is a disease of cattle, sheep and goats caused by protozoan parasite, transmitted by ticks in Africa.

Contagious Bovine Pleuropneumonia.
Contagious Bovine Pleuropneumonia is an important respiratory disease affecting cows and other ruminants in Africa. It is caused by bacteria Mycoplasma mycoides mycoides and is endemic in Africa in areas between the Tropic of Cancer and the Tropic of Capricorn.

Newcastle disease is caused by viruses in the serotype avian paramyxovirus type 1 (APMV-1), also called Newcastle disease viruses (NDV). The viruses are members of the genus Avulavirus in the family Paramyxoviridae. APMV-1 strains are classified into three pathotypes based on their virulence in chickens. Lentogenic strains are the least virulent, mesogenic strains are moderately virulent and velogenic strains are the most virulent.

Hemorrhagic septicemia (HS) is an acute, highly fatal form of pasteurellosis that affects mainly water buffalo, cattle, and bison. It is considered the most economically important bacterial disease of water buffalo and cattle in tropical areas of Asia, particularly in Southeast Asia, where water buffalo populations are high. Disease is most devastating to smallholder farmers where husbandry and preventive practices are poor and free-range management is common. HS is also an important disease in Africa and the Middle East, with sporadic outbreaks occurring in southern Europe. Rift Valley Fever

Sheep and Goat Pox
Sheep and goat pox are contagious viral diseases of small ruminants. The disease is found in most of Africa, the Middle East and Asia.

Peste des Petits Ruminants
Peste des petits ruminants is a highly contagious viral respiratory disease of goats and sheep

African and Classical Swine Fever.
African Swine Fever is a highly contagious haemorrhagic disease of pigs, warthogs, European wild boar and American wild pigs. African Swine Fever Virus is a large DNA virus. Traditionally Sub-Saharan Africa, and more recently a wide area across Eastern Eurasia.