Business Case

Summary Sheet

Title: Reducing Poverty through Local Economic Development (LED) in the Commonwealth
Programme Summary: To support the Commonwealth Local Government Forum (CLGF) to work with and build the capacity of local government organisations to design, develop and implement Local Economic Development (LED) strategies that deliver local investment, job creation and business development and which will inform and influence national LED strategies.
Programme Value: £3,900,000		Country/ Region: The Commonwealth
Programme Code: / 204043	Start Date: August 2017	End Date: July 2020
Overall programme risk rating:	Low
Vault Number:

Intervention Summary (2 pages max)

The achievement of development goals is not solely the responsibility of central government. Local government has an important role to play and is often directly responsible for the provision of basic services such as health, water, sanitation and education and for creating the necessary conditions for economic development.

While there has been some progress in strengthening the role and capability of local government in the Commonwealth and more widely, the pace has generally been slow. Weak capacity at the local level and/or poor intergovernmental relations significantly affects local government’s ability to deliver services or to create the enabling environment for economic development.

Although some regional organisations (e.g. the Caribbean Association of Local Government Authorities) provide modest support to help address these constraints, they are generally poorly resourced and unable to provide the support needed. The Commonwealth Local Government Forum (CLGF) is well placed to deliver this support and to help disseminate and share best practice across the Commonwealth. CLGF was set up as an autonomous organisation in 1995 and is now recognised as the voice of local government in the Commonwealth. It has received endorsement at successive Commonwealth Heads of Government Meetings (CHOGM) which has helped ensure the voice of local government is being heard at the highest level.

Under an earlier £4.5m programme of DFID support[1] (October 2012-November 2016) CLGF successfully piloted a Local Economic Development (LED) approach, raised awareness and demonstrated its potential impact. CLGF and its partners are now ready to deepen and embed that approach by rolling it out at scale with local government partners in targeted countries and by sharing the lessons from that process in other Commonwealth countries. Their proposal for a new programme of support is at Annex 1.
[1] https://devtracker.dfid.gov.uk/projects/GB-1-202947/documents

DFID funding, £3.9m over the period July 2017 to July 2020, will build on that previous programme and seek to deepen and embed the local economic development approach further. CLGF will focus their efforts on six countries: Botswana, Zambia, Sri Lanka, South Africa, Swaziland and Ghana, in order to develop a robust evidence base of what works in rolling out LED strategies at scale and facilitate the sharing of best practice across the Commonwealth.

Working alongside their local partners and drawing on the skills and experience of its regional membership, CLGF will help local government organisations to develop and implement local economic strategies. CLGF will do this by coordinating and encouraging multi-stakeholder partnerships, to build capacity, skills and knowledge, to increase their capability to develop bankable projects (i.e. projects that will attract financing), to mobilise resources for LED investments and to influence the development of national strategies and programmes.

The expected results of this intervention will be increased economic opportunities, job creation and improved skills in the communities CLGF partner with. It will also produce a robust evidence base, practical case studies and best practice that can be shared across the Commonwealth through CLGF's membership and knowledge hub. CLGF will monitor and evaluate jobs created as a result of this project and test results by measuring the number of jobs created in pilot councils; as a part of this the project will look to directly create at least 1,500 jobs through the demonstration projects.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan? Yes. The support proposed directly meets the commitment in Single Departmental Plan (SDP): 2015 – 2020 to strengthen the Commonwealth’s focus on promoting democratic values and development by strengthening the voice of local government through the engagement with national policy making on LED.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results? This is a modest (£3.9m) follow on programme (2017-2020) that builds on an earlier programme (2012-2016) that tested approaches to embed local economic development in Commonwealth countries. Given the scale of the programme there is limited scope to adjust the programme to deliver significantly increased SDP results.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy? Yes. CLGF has contributed extensively to international advocacy directly, and as a founding member of the Global Taskforce of Local and Regional Governments, the official partner of the UN Major Group on Local Authorities, to ensure the role of local government in achieving global development priorities is recognised. No follow on support is envisaged. The programme will draw on CLGF’s network to share the results of the programme and encourage wider take up.

Has the programme considered working with HMG Departments and accessing cross-HMG funds? Cross-HMG funds were considered but did not offer sufficient benefit to pursue further.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes? DFID is increasing its focus on productive and sustainable urban development; for instance DFID India is already delivering a wide ranging set of interventions on urban development as part of a cross Whitehall programme with high-level buy in from the Indian government. This programme complements that focus, recognising that CLGF has strong networks across Commonwealth city mayors and sits alongside our broader funding to the Commonwealth intergovernmental organisations.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments? The programme builds on and learns lessons from an earlier pilot. In doing so it focuses on scaling up that work in fewer countries and with fewer local government organisations while continuing to develop the methodology for LED. The lessons learned in this process will be shared with the wider Commonwealth local government community.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio? Yes. The external environment, delivery and operational risks are considered minor/low. The project builds on an earlier pilot programme that both developed the approach and built strong partnerships between CLGF and local government partners, which has helped to reduce the risks associated with this new programme.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not? The programme has a strong communications focus through CLGF’s role in sharing knowledge and best practice through their local government network and in their advocacy work. As for the previous programme we expect all CLGF publications to acknowledge UK funding and use the UKAid logo.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme? This is a follow on programme building on the successful pilot programme that scored an A+ in its Project Completion Review.

Does the SRO and team have the capability and resources to deliver this programme? Yes. Pressures expected in the run up to the Commonwealth Summit are being managed by the provision of additional surge support to the team.
Strategic Case
Context
The Commonwealth is home to 2 billion people, half under the age of 30, and more than one fifth under the age of 14. Many parts of the Commonwealth face substantial development challenges: one third of the world’s poor live in Commonwealth countries, and two-thirds of those are women.

Commonwealth countries face global challenges, which affect both the poorest and people living in more advanced countries, including the UK. Global insecurity and the risk of conflict in previously stable parts of the world is rising; despite a downward trend, poverty and vulnerability remain; natural disasters are more frequent and the threat of climate change is growing more acute, the effects already being felt by many Commonwealth member states. Migration, driven in part by these factors, presents growing challenges.

Local government plays a critical role in managing the provision of health, education, water and sanitation, infrastructure and economic development. There is potential for the building or restoring of sub-national government institutions to contribute to improving state-citizen relations, empowerment and accountability and advancing state legitimacy. Global trends affecting the complexity and criticality of local government’s role include rapid rates of urbanisation and rural under-development, the occurrence of natural disasters and climate change adaptation and impact.

Service delivery at the local level remains a challenge in many countries. Local authorities often have limited resources or ability to raise adequate resources to cover the cost of service provision, an inadequate decentralisation of power, lack the requisite technical capacity, equipment and staff, and have limited capacity and skills at the local level. Increasingly, as local government’s mandate is extended in line with rising local expectations and cost-shifting by central government, these challenges are becoming more acute. External factors like urbanisation and climate change are further impacting on capacity to meet needs.

The Cardiff Consensus for Local Economic Development was adopted by the CLGF members at the 2011 Commonwealth Local Government Conference[2]. The Consensus called on governments, development agencies and other partners to support and strengthen local government's role in local economic development (LED) to help reduce poverty, and promote economic prosperity across the Commonwealth. It gives guidelines on key actions to enable local government to play its full role in LED around:
[2] http://www.clgf.org.uk/default/assets/File/CLGF_statements/2011%20Cardiff%20consensus%204pp.pdf
- providing a clear national framework for local economic development
- creating an enabling environment for LED
- local strategies to promote LED
- LED partnerships with the private sector and other partners.
The UK’s commitment to the Commonwealth and support to date
The UK is fully committed to the Commonwealth. It will host the Commonwealth Summit in April 2018 and be act as Chair-in-Office until the following Commonwealth Head of Government meeting. The Commonwealth is a unique and politically important international network, which draws on strong UK ties and provides valuable opportunities to both influence and be influenced by its other 51 other member states.

Action at the local level to develop a sustainable approach to local economic development ensures that people have the tools to improve their economic opportunities in their communities. This feeds in directly to the achievement of national and international development imperatives, including the Agenda 2010 and the Sustainable Development Goals, with a particular emphasis on SDG 8, to promote inclusive and sustainable economic growth, employment and decent work for all, and SDG 16, to promote just, peaceful and inclusive societies.

Local economic development (LED) is a central part of developmental local government. It is a process which brings together different partners in the local area to work together to harness resources for sustainable economic growth. LED is increasingly being seen as a key function of local government and a means of ensuring that local and regional authorities can address the priority needs of local citizens in a sustainable way. LED provides an enabling environment at the community level, drawing on local opportunities, partnerships and resources, to empower all people to be economically active. There is no single model for LED; approaches reflect local needs and circumstances.

Local government has a clear role in enabling sustainable economic development at local level. Local government itself can be responsible for infrastructure development, business licencing, providing core services which influence investment decisions, and business opportunities, environmental management, and ensuring a good quality of life for all. The convening power of local government means it is well placed to engage citizens, civil society, and the private sector and influence other parts of government drawing on the evidence base being developed by CLGF.

The Commonwealth Local Government Forum (CLGF)

The Commonwealth Local Government Forum (CLGF) is the Commonwealth organisation representing local government. Its membership is made up of ministries of local government, national local government associations and individual cities and councils from across the 52 countries across the Commonwealth. It was founded in 1995 and its establishment was endorsed by Commonwealth Heads of Government at their meeting in New Zealand later that year. It has received further endorsement at subsequent Commonwealth Heads of Government Meetings and in 2003 was given official recognition as an associated Commonwealth organisation of elected representatives.

CLGF Board members and those at the helm of CLGF member organisations - including ministers with responsibility for local government, local government leaders, mayors, chief councillors, senior managers and administrators - are themselves at the cutting edge of local government policy and service delivery and provide valuable input and expertise to CLGF's policies, programmes and events. CLGF associate members include leading academic institutions that provide policy and research support through the CLGF Research Advisory Group[3]. CLGF’s work focuses around three core priorities:
[3] http://www.clgf.org.uk/what-we-do/research-advisory-group/

- Strengthening local democracy
- Promoting effective local development by improving policy, governance and service delivery capacity
- Supporting cities and sustainable urbanisation

CLGF has successfully piloted a Local Economic Development (LED) approach, raised awareness, and demonstrated the potential impact of LED through an earlier £4.5m DFID programme (Support to the Commonwealth Local Government Forum 2012-2016[4]). CLGF and its partners are now ready to deepen the approach trialled in that programme by rolling it out at scale with local government partners in targeted countries and by sharing the lessons from that process in other Commonwealth countries. CLGF’s Commonwealth reach means it can rapidly share its LED methodology and the lessons and best practice learned across its membership. The proposed programme (at Annex 1) reflects the growing demand from countries which have seen the success of the initial phase and are keen to access similar support.
[4] https://devtracker.dfid.gov.uk/projects/GB-1-202947/documents

The earlier project enabled the CLGF to work with 30 councils in 9 countries across the Commonwealth to support their efforts to provide better and more responsive service delivery, through the development of LED approaches to improve the environment for doing business at the local level and create jobs. It supported capacity building at the local, national and regional levels and helped increase the dialogue between key interlocutors at all levels of government to improve policy frameworks and improve service delivery on LED. CLGF’s work on LED has resulted in a growing evidence base on the different approaches that can be taken and these have subsequently informed national policies. The previous programme met all its objectives and scored an A+ (Outputs moderately exceeded expectation) in the Project Completion Review (February 2017).

Building on the results of that programme, CLGF propose further work in selected Commonwealth countries to support the implementation of Local Economic Development approaches at scale. They will:

•	Embed the LED approach in three countries (Ghana, South Africa and Swaziland) by supporting ministries of local government and local government associations to scale up and roll out LED activity, and by strengthening their capacity and ability to access finance and leverage investment for LED; and in doing so to demonstrate how this results in economic development, investment and increased job opportunities for local communities;

•	Support the design, development and roll out of national/provincial LED strategies in Botswana, Zambia and Sri Lanka;

•	Facilitate effective engagement between national ministries of local government, Local Government Associations (LGAs) and other stakeholders to help create the environment needed for evidence based policy making that empowers local governments to deliver LED;

•	Evaluate the impact the LED approach has on the enabling environment for successful national economic development; and

•	Share the experience and good practice developed under the programme with the wider Commonwealth local government community through the CLGF network; capitalising on the Commonwealth’s shared systems, structures and language.

DFID’s investment in the programme is expected to enable CLGF to deliver this programme and support local government in developing and implementing LED policies and programmes. This is expected to create an improved environment for doing business locally that will deliver job creation, business development and poverty reduction, particularly targeting poor and disadvantaged groups.

Theory of Change

Building on the work of, and the lesson learned from, the earlier programme of support this project, delivered though and coordinated by CLGF, is expected to provide local government organisations with the skills, capabilities and support needed to design and deliver strategies that provide the enabling environment needed for local economic development and to create a series of “bankable” projects that will leverage additional investment. While the previous programme began the process of looking at these issues across 30 local communities in 9 countries, this project will, in focusing on fewer countries but in greater depth look to demonstrate replicable results by investing at scale.

The expected direct outcomes from this investment, and the resulting improved business environment, are an increase in the level of local economic activity that provides increased job opportunities. The project is also expected to help develop the evidence base and best practice materials needed to influence the development of national economic strategies and to inform others looking to replicate this approach. The outcome is expected to contribute to the impact by combining an increase in capacity at the local level with demonstrable deliverables influencing a more supportive national institutional and political framework. More supportive, and evidence based, regional policy making which protects the interests of local government will help to sustain the potential for further improvements

This programme is designed to have the following impact, outcomes and outputs[5]
[5] See also the logical framework at Annex 2

IMPACT		Improved livelihoods for Commonwealth citizens as a result of economic development.
OUTCOMES		Economic development, investment and increased job opportunities in local communities in target countries. Local economic development results in improved environment for doing business locally and more jobs created in local communities as a result of local economic development.
	OUTPUTS	(1) National/provincial local economic development (LED) strategies designed and rolled out. (2) Increased capacity to roll out and embed the CLGF LED approach; (3) increased awareness of LED potential in fragile countries; (4) CLGF/DFID acknowledged as a Commonwealth centre of local economic development learning and good practice.
	INPUTS	DFID funding £3.9m over FY 2017-2020, with high quality programme management, reporting, monitoring and evaluating. / CLGF deepen LED through technical assistance, conferences/events, tools/knowledge, programme management, regional project offices, Commonwealth-wide learning and coordination, CLGF network/Board and Executive boards, CLGF project and finance management expertise.

Gender Equality

This project recognises that overcoming barriers to women’s participation in the local economy, and addressing women’s roles as consumers, employers and employees can have a powerful impact on the lives of women. Local Economic Development can improve women’s earnings and consumption, strengthen household resilience, foster greater investments in child well-being, and enhance aspirations for the next generation of girls and women. All Commonwealth countries are committed to the Commonwealth target of at least 30% of women in public life and to SDG 5 on gender equality and empowerment. CLGF will aim to encourage a blend of gender-sensitive public and private investment to advance local development and all indicators will be disaggregated by gender to show how far the programme is enabling women in local economic development.

Terrorism and financing

CLGF shares DFID’s policy position that none of its funds be used, directly or indirectly to provide support to individuals or entities associated with terrorism. The risks of this happening through this programme are considered to be very low. The Commonwealth Local Government Forum is committed to ensuring that it has adequate controls to counter money laundering activities and terrorist financing activities, in line with the Money Laundering Regulations 2007 as amended by the Serious Crime Act 2015. In keeping with this regulation, CLGF maintain appropriate project partner/consultant screening, monitoring and related due diligence procedures that are designed to prevent the organisation from doing business with entities which engage in either money laundering practices or other illegal activity.

In relation to NGOs, public and incorporated entities, these processes extend to the individuals that control such corporations. Officers and relevant staff of CLGF are made aware of policies, procedures and processes and are mandated to adhere to them. Both written and electronic records documenting compliance with such procedures are maintained.

DFID will continue to monitor the rigour of systems and controls throughout the lifespan of this programme.

## B. Appraisal Case

The programme proposed by CLGF builds on lessons learned from earlier work funded by DFID. CLGF continues to fill a niche position internationally because it is a member of the Commonwealth family and because its membership includes both national and local government representation. It is able to offer advantages that other organisations supporting developing countries on local governance issues are unable to match, notably by:

Bringing practitioners together through practitioner to practitioner exchanges including south-south relationships and triangular south-north relationships.

Working within the Commonwealth framework where all countries, large or small, have an equal voice, and where common values, systems and experiences provide a rich opportunity to develop shared policies and common solutions to challenges. Most Commonwealth countries also share the same common law based institutional systems.

Using common principles and standards as tools for promoting local government with national and local practitioners. These include the Aberdeen Agenda which represents part of the broader Commonwealth commitment to democratic values; and the Cardiff Consensus which sets out key priorities for effective local economic development in the Commonwealth and has endorsement from Commonwealth Heads of Government.

Accessing an impressive and established address book of local, national and international local government practitioners across the Commonwealth who are able to hold frank and open discussions as part of the “Commonwealth family”.

Using existing relationships with Heads of State; Governments (usually via ministries of local government); local government associations in Commonwealth and non-Commonwealth countries; regional local government forums; the Commonwealth Secretariat and other Commonwealth organisations; development partners, international local government organisations; and private sector partners working with local government.

Ensuring that local government’s needs and priorities are raised and recognised at the highest level through its associated Commonwealth organisation status and access to the wider Commonwealth policy debate, including through Commonwealth Heads of Government Meetings and other ministerial meetings.

For these reasons we believe the only realistic option for providing support to local government strengthening through a Commonwealth-based intervention is by working through CLGF. The options considered below do not therefore include alternative delivery mechanisms.

Option 1: – Funding to CLGF via an Accountable Grant arrangement

We propose to agree an Accountable Grant with the CLGF to enable them to develop and deepen the LED programme further in this new programme. Doing so provides for more oversight and engagement with the financial aspects of the programme than was allowed for under the Memorandum of Understanding used for the previous programme and facilitates better quality assurance and engagement throughout the project delivery work. The detailed management of programme is described in the Management Case below.

The programme is described in detail on the CLGF proposal at Annex 1. That proposal, together with this Business Case and the logical framework at Annex 2, will provide the key attachments to the Accountable Grant and will provide the framework for the delivery and the monitoring and evaluation of this programme.

Option 2: Counterfactual ‘Do Nothing’ Approach

Better local government service delivery can be achieved in different ways. DFID country offices can and do manage programmes to deliver similar objectives. However, CLGF is able to facilitate an approach to capacity building on a pan-Commonwealth basis with an active local government membership; which provides inherent advantages for gaining traction and developing productive working relationships whilst still supporting country-led priorities. Without the programme:

- The evidence base, and the material available to local government practitioners through the CLGF knowledge hub, for local economic development would be weaker,
- CLGF’s advocacy and knowledge management/best practice roles would be less well informed,
- There would be fewer opportunities to bring Commonwealth local government practitioners, associations and local government Ministries together to build networks/alliances, to share the experience of what works and fewer opportunities to learn how to improve service delivery capacity in Commonwealth countries.
- There would be fewer opportunities at the regional level for the exchange of good practice and to promote inter-regional learning.
- At the international level, without the additional support, the Commonwealth’s advocacy work, delivered by CLGF on behalf of local government, would be significantly weaker and less strategic.

CLGF and DFID

In November 2016, CLGF completed a successful four year DFID-supported programme working across the Commonwealth. The programme centred around building capacity at the local government level in three regions: West Africa, Southern Africa and South Asia, but included provision to promote regional exchange and strengthen knowledge management and research capacity to ensure that relevant knowledge resources and experiences were shared across the Commonwealth.

The CLGF programme 2012-2016, ‘Support to decentralisation and local economic development’, focused on improving local authority service delivery to contribute to the achievement of the Millennium Development Goals (MDGs) and the Sustainable Development Goals (SDGs). CLGF focused national pilot level work on strengthening local government’s role in local economic development as a means of enabling more inclusive local development. The programme was annually evaluated by DFID and scored an A+ (Outputs moderately exceeded expectation) In the Project Completion Review in February 2017[6].
[6] https://devtracker.dfid.gov.uk/projects/GB-1-202947

The proposed 2017-2020 programme builds on key lessons and outcomes from that initial phase of work. Having designed and delivered the national pilots to support LED in selected countries, CLGF and its partners have developed the track record, tools, experience, technical capacity and resources to roll out the LED methodology regionally/nationally in selected countries, and to fast-track the implementation of LED in countries where LED is not yet established, but where there is some experience, or a commitment to introducing the LED approach.

The key lessons from the previous programme, captured in the Project Completion Review, included:

The importance of raising awareness and understanding of LED as a strategic approach to enhance local development, not just a series of projects: Under the pilots, awareness raising, training, local economic assessments and guidelines for the development and implementation of LED strategies were developed, resulting in country-specific toolkits and a process for implementation which can be adapted for wider expansion nationally, but also for use in other Commonwealth countries.

The importance of a consultative approach: Securing the buy in of key CLGF members and partners (ministries, local government associations and individual cities and councils), and working closely with them to ensure that LED builds on their existing responsibilities and priorities remains key to the success of the approach.

The need to balance short term expectations with a long term sustainable process: A challenge for CLGF under the previous programme was to balancing the short term demand from councils to deliver practical investments/projects with the development of a more strategic and sustainable approach. This was achieved but will remain a tension that needs to be actively managed in the proposed project.

LED builds on the convening power of local governments: The national pilots showed that working in partnership with other community stakeholders such as the private sector, civil society etc., builds understanding and trust between local government and other partners, including the private sector. It helps local government to better understand the powers and leverage that it has in supporting LED, but equally ensures that the private sector and other partners have a better understanding of how local government works and some of the constraints that it faces. The collaborative approach resulted in LED initiatives which were responsive to local needs and priorities, and capitalised on the strengths of key stakeholders.

The potential for leverage: While the earlier CLGF project began the process of developing bankable LED projects and leveraging additional funding few reached the point of doing so under the 2012-2016 programme (it was not a focus or agreed deliverable from the programme). Where progress was made, local government organisations seeking to leverage finance from the private sector reported that the modest initial investments the project supported, allied to their more strategic approach to LED and the involvement of CLGF as a credible “supporter” of the initiative, combined to create the conditions for more successful leverage. The evidence for this effect does, however, remains small and anecdotal and, in undertaking further work in this area, the proposed programme additional emphasis will be placed on building the skills and capacity to mobilise resources and develop “bankable” projects to build the evidence base.

The value of the Commonwealth as a means for exchanging lessons and good practice: Regional meetings were very positively evaluated both for content and the ability to share experience and lessons among countries with common challenges and contexts. They were also seen as an important means of effectively advocating and making the case for wider take up of LED across the countries of the target regions. As a direct result of the 2012-2016 Programme local government ministers were able to see the way in which the LED approach had been implemented on the ground and the results which were being achieved in neighbouring countries and local authorities which were part of the pilot. The fact that CLGF was able to demonstrate concrete results and benefits to senior policy makers and had involved them in that work helped ensure their appreciation of the LED process as a means of empowering local government to deliver development and poverty reduction. For example in the final regional forum in Southern Africa, 7 Ministers of Local Government used their time on a ministerial panel to positively endorse the LED approach, and directly requested continuation of the programme to build on the achievements to date and to roll out the approach to countries not yet actively involved.

The 2012-2016 programme tested the LED approach through a series of modest pilot investments. In order to embed the progress reflected in that programme the CLGF proposal makes a compelling case for a further phase of support to:
- Roll out the approach with local government organisations in selected countries to show the impact at scale;
- Further embed the LED approach in countries moving towards implementation, and demonstrate how a more strategic model results in economic development, investment and increased job opportunities in local communities;
- Improve the enabling environment for LED by ensuring continued engagement by national ministries of local government, LGAs and other stakeholders, resulting in more targeted policy making to empower local governments in delivering LED;
- Strengthen the capacity and ability of local governments to access finance for LED and demonstrate how to mobilise and leverage investment from other spheres of government, the private sector and other development partners;
- Share experience and good practice through the CLGF network, capitalising on the Commonwealth’s shared systems, structures, language, and good governance, but also a shared commitment to successful implementation of LED.

Advocacy and learning

CLGF contributes extensively to international advocacy directly, and as a founding member of the Global Taskforce of Local and Regional Governments, the official partner of the UN Major Group on Local Authorities, to ensure that the role of local government in achieving global development priorities is recognised. This concerted advocacy, bringing together the voices of many global local government organisations with powerful common messages, resulted in clear commitments in the five major global agreements - the Agenda 2030, the Paris Agreement, the Addis Ababa Action Agenda, the Sendai Framework for Disaster Risk Reduction and the New Urban Agenda – of the importance of local government as an essential partner in achieving sustainable development.

CLGF is working closely with other partners including UNDP and United Cities and Local Governments (UCLG) to raise awareness, build a stronger evidence-based case for greater support for LED’s role in this regard, and to provide practical tools to enhance LED. CLGF will be part of the team planning and delivering the next Global Forum on LED, in October 2017, and will also contribute to various European policy events to demonstrate the effectiveness of LED in enhancing local development and improving livelihoods. CLGF is an active member of the Cities Alliance and represents local government on the joint work programme on equitable economic growth.

C.	Commercial Case

The Commonwealth Local Government Forum (CLGF)

The Commonwealth Local Government Forum has an experienced project team in place and can draw on the materials, resources and, in particular, the network of partners developed under the previous DFID programme. The team draws on the experience it gained in delivering that programme but can also draw on a wider group of specialists and experienced practitioners from across its membership and extensive network.

CLGF has a Board which provides strategic policy and guidance, made up of Ministers and Mayors/local government leaders from across the Commonwealth. The Board is elected by the membership at the biennial General Meeting, and they then elect from among themselves a Chairperson and two Vice Chairpersons, one representing local government and one central government. The full Board meets annually, and a smaller Executive Committee meets physically twice a year but more regularly by teleconference, to ensure close Board engagement in financial oversight, strategic planning and decision making. CLGF has a Secretariat of core policy, programme and member-services staff, based in London, led by Dr Greg Munro. It works through a network of regional project offices (Southern Africa, West Africa, South Asia, Caribbean, Pacific and Sri Lanka) to deliver its programmes and projects in close partnership with its membership.

As an organisation, CLGF seeks to ensure that its finances are as transparent as possible. Its budgets are determined annually by the Board and reviewed quarterly by the Executive Committee. Budgets are linked directly to the CLGF business plan and risk management process. CLGF has an Honorary Treasurer (A serving local government chief executive) who meets regularly with finance staff to review finances against the agreed budget. CLGF’s accounts are audited annually, and endorsed biennially at the General Meeting which takes place at the same time as the biennial conference

Improvements in the performance and experience of the CLGF team over the lifecycle of the earlier programme can be seen by the results it was able to demonstrate through the Annual Review and Project Completion Review processes. The programme scored a B in the 2013 Annual Review, an A in 2014 and an A+ in the 2015 and 2016 Annual Reviews. The Project Completion Review in February 2017 similarly scored the project as an A+ (Outputs moderately exceeded expectations).

Value for Money

Value for Money was scrutinised closely under the previous programme. The Project Completion Review notes that “throughout the project, CLGF put in place procurement processes that looked to ensure value for money. These included competitive bidding when specialist services were required and for any purchases. In using practitioners from within its membership CLGF enabled the project to access specialist capacities at no or low cost to the project. CLGF and its project partners were required to get at least two quotes for all flights purchased to ensure that they identify the most cost effective options. All flights were economy class.

Under the previous programme CLGF planned to leverage complementary funding of £1.5 million from project partners and other sources. It exceeded this by leveraging £1.8 million. CLGF remains committed to the principal of using this programme to leverage funding to expand its impact and value for money and to demonstrate that alternative sources of funding are available. Over the life of this programme they have committed to leveraging complementary support to the value of 65% of the DFID contribution (approx. £2.5 million) in the form of additional financial resources and/or contributions in kind.

As a Commonwealth organisation CLGF is able to implement programmes that offer high levels of value for money due to its ability to generate economies based upon its membership, coverage and influence. It draws on an influential network across the Commonwealth (mayors/locally elected leaders, ministers and senior officials) that provides the basis needed for its programmes and activities.

As an associated organisation officially recognised by Commonwealth Heads of Government, CLGF is well-placed to influence policy development and lead on democracy and good governance at local level. A particular strength lays in its membership whose representatives are key players in local government in the Commonwealth and who can be drawn into CLGF’s work as experts and influencers. This network allows value for money to be further enhanced through the use of quasi “in house” Commonwealth expertise, where practitioners bring a wealth of skills and experience both technical and political as a free/low cost resource (e.g. specialist expertise can be deployed for just the cost of travel, accommodation and expenses with no commercial consultancy fees

Through the previous programme CLGF similarly demonstrated it has the convening power needed to ensure the buy in and commitment of the political and technical stakeholders and partners that are essential to the success of this programme. It remains well-placed to share best practice and results, to influence policy development and to provide a leading voice on issues relating to democracy and good governance at local level.

Proposed Funding Instrument

In line with Smart Rule guidance we intend to manage the programme through an Accountable Grant. CLGF meet the key criteria as;

- Funding is for a civil society, non-government or not-for-profit organisation or partnership and not a partner government or multilateral.
- Funding is being provided to an organisation whose primary purpose is not for profit and we have verified its status.
- We are confident that our decisions are not open to criticism of anti-competitiveness, and we can demonstrate that we are achieving value for money and maximum impact.
- The organisation (or group of organisations) has approached DFID with a proposal for funding.

We have worked closely with CLGF in the development of their funding proposal and we believe it represents the best way of delivering a programme that builds on the methodology developed in the earlier programme with a partner that has demonstrated a robust value for money approach and who has the network and reach to be able to share best practice and influence change and wider uptake.

The detail of the Accountable Grant will be agreed with CLGF following approval of the Business Case. The Business Case, CLGF proposal and the logical framework form the key attachments to Accountable Grant and will be the primary means of setting out our expectations and will provide the basis for monitoring project performance.

Financial Case

CLGF’s core functions are funded from annual membership fees. It also receives programme funding for its work from a cross section of different development partners, including;
- DFID,
- the European Union,
- MFAT (New Zealand),
- UN Women,
- DFAT (Australia), and
- UNDP.

CLGF also generates income directly from services such as its biennial conferences, and some corporate sponsorship both in kind, and through direct corporate partnerships with private sector partners with an interest in local government such as Microsoft and Barclays.

Although CLGF has a modest resource base, it is a nimble and cost effective organisation which draws significant strength and influence from its high level membership, and from a range of strategic partnerships, including with the EU, UNDP and United Nations Capital Development Fund (UNCDF) It is a successful networked organisation, and as such has been recognised by DFID and other organisations as “punching above its weight” in being able to deliver for its members and in profiling the contribution of local government to development internationally.

The proposed budget for the project is £3.9m. Funding will come from within UNCD's budget and provision has been made for this over the project period. The high—level breakdown of funding over the three years of the project is expected to be as follows:
2017/18 £1,200,000
2018/19 £1,450,000
2019/20 £1,250,000
A detailed project budget is included with the project proposal at Annex 1.

Management Case

The project will be managed by United Nations and Commonwealth Department alongside the programmes for the inter-governmental Commonwealth programmes. The Senior Responsible Owner will be the Commonwealth Institutions team leader supported by a Deputy Programme Manager.

CLGF is well positioned to be able to take forward this new programme of work, building on the earlier programme. That programme demonstrated how CLGF can work effectively to facilitate a cooperative approach across the public and private sectors, and civil society. They are seen as a trusted and respected partner in the proposed target regions and countries, and have been formally asked by them to continue to work to build on the 2012-2016 programme and to help embed and roll out LED.

Close working relations were developed between UNCD and CLGF during the previous programme to ensure both sides were able to keep abreast of developments and respond accordingly. These have been maintained in the development of the current proposal and this business case. However, as recognised in the PCR for the previous programme, this could, however, have been improved on and for this programme we intend to introduce a regular monthly project management meeting to monitor progress, to support effective project and financial management and to inform the annual review process.

The role of CLGF in providing quality project design, management, technical support, monitoring and evaluation

CLGF has a small Secretariat based in London, responsible for the overall management of the programme. The Secretariat works closely with dedicated project staff located in programme offices based in the regions where CLGF is active (Tshwane, Southern Africa; Accra, West Africa; and Mumbai, Asia). Two of the three offices are co-located within CLGF member organisations to ensure coordination and good value for money.

The CLGF programme staff in the Secretariat comprises:

A full time Programme Officer, who is responsible for overall programme coordination, definition of work plans, regular liaison with project staff in the field, compilation of project reports, technical and budgetary support to project staff and project implementation, ensuring alignment across regions, monitoring and evaluation, overseeing all payments and acquittals against agreed work plans/budgets, coordination with other CLGF projects, identification of technical experts and practitioner expertise, and overseeing a Commonwealth input into communications and events. The programme officer will convene regular skype calls with regional staff to ensure coordination and to maximise opportunities for lessons to be shared across the programme.

A full time Research Officer, responsible for overseeing CLGF’s research and lesson-learning related to the programme, identifying key lessons to support CLGF’s wider knowledge sharing role and to support the advocacy work of the organisation in favour of strengthening local government’s role in development. The research officer will contribute to designing terms of reference and producing materials to support events and learning opportunities, strengthening communications/messages/policy-based analysis, maintaining and enhancing the knowledge hub, managing the contribution of CLGF’s network of academic/research and professional organisations the Research Advisory Group (RAG) - to the programme, and supporting any monitoring and evaluation.

The team is supported by CLGF’s Director of Finance (partly funded by the project) who will lead on all project related finance, monitoring expenditure and cash flow, forecasting against agreed budgets and work plans, ensuring all financial documentation and receipting is in order, and preparation of financial reports and acquittals for DFID. He will also ensure that the project finances are audited on an annual basis.

The team will be managed by the Deputy Secretary General who will provide technical and political oversight of all programme work, coordination with other CLGF policy/programme work, leverage of additional funding support/resources, and will be responsible for management of the project offices and regional staff, under the overall oversight of the Secretary General.

Regional staff based in South Africa, Ghana and India will be responsible for working with local project partners to develop detailed local work plans and budgets, establish and participate in local multi-actor steering committees to coordinate national level activity, provide technical support and advice to local project partners, organisation of local events, identification of technical experts and practitioners, coordination with the programme officer and research officer on lessons learnt and ensuring opportunities for knowledge exchange and sharing. The regional staff will liaise locally with CLGF Board Members to ensure strong local political engagement and oversight of activities. They will also be responsible for identifying possible sources of funding to enhance the impact of the DFID contribution to be followed up with the programme officer/Deputy Secretary General.

CLGF’s Executive Committee will contribute directly to the annual review process. In line with previous practice, the Annual Report will be shared with DFID and also tabled at the annual Executive Committee Meeting in London. The Executive Committee comprises the Chairperson, two Vice Chairpersons and two other members (one central and one local government). The Honorary Treasurer, immediate Past Chairperson and Secretary General are ex-officio members. The Executive Committee meets up to four times per year - two meetings by teleconference and two face to face. DFID will be invited to attend the Executive Committee meetings held in London as an observer in order to discuss any key issues relating to the delivery and impact of the programme.

Programme methodology

CLGF takes a strategic enabling approach to LED planning and implementation, focusing on building an enabling environment where local government works with local business and community actors to strengthen its service provision and respond to locally agreed development targets. CLGF’s approach is consultative, based on building partnerships; it draws on the technical skills and expertise of local government practitioners with direct experience of working in a political environment; and aims to demonstrate practically the impact of new ways of working through support for implementation of LED activities on the ground.

In delivering the 2012-2016 programme, CLGF developed a framework methodology for enabling LED, which ensures a national approach, but makes provision for local implementation to demonstrate how the LED approach impacts positively on the lives of local people. The work is managed by experienced CLGF staff from the regions, and technical support is drawn from local government practitioners and other technical experts from within CLGF’s extensive network. However, the front line delivery of LED is very much the responsibility of local partners: Ministries of local government, local government associations and local councils, together with their local stakeholders, including the private sector, are responsible for delivering LED on the ground. Having established this methodology, and developed the necessary tools and resources to be adapted in different contexts, CLGF is confident that implementation and adoption of LED could be achieved more quickly in new partner countries.

The main risks identified for this programme and the mitigating actions are summarised in the table below:

Risk	Mitigating actions	Residual risk (Impact/Probability)
External / context risks
Change at a local or national level is likely and if it happens in a number of countries could unfavourably affect results. It often slows down the process whilst the new leadership develops their own priorities and programmes, sometimes rejecting those associated with the previous leadership.	CLGF will seek political buy-in from across the political spectrum to minimise the risk associated with multiparty democratic cycles. CLGF will monitor this and discuss necessary adjustments with DFID. Monitoring arrangements will be set out in the logframe.	Moderate / Unlikely
Delivery risks
In-country staff turnover and ministerial reshuffles (etc.) lead to a slowing down of project activities. .	Given the political nature of CLGF’s membership, this is likely to occur in one or more of the target countries during the life of the programme. It can, and will, be mitigated by CLGF ensuring there are appropriate handover processes in place and by spreading the risk by ensuring as many local staff and leaders as possible are engaged in and aware of programme activities.	Low / Probable
Operational
The limited timeframe impacts on CLGF’s ability to achieve genuine results and to capture project outcomes.	Although three years is a tight timeframe, the project benefits from building on an earlier programme. This means limited inception work needed and project activities can start quickly. CLGF’s on-going advocacy work and work to disseminate best practice is not project reliant so will continue to be supported. .	Low / Unlikely
UNCD lacks sufficient capacity and capability to effectively manage the programme.	The DFID Commonwealth team is properly resourced to reflect the requirements needed to support the implementation of the programme; although for Annual Reviews and the Project Completion Review additional advisory inputs are likely to be required and will need to be sourced from outside UNCD.	Low / Unlikely
Fiduciary
CLGF has inadequate risk management, oversight and assurance arrangements	The Due Diligence Assessment undertaken on CLGF prior to this programme confirmed that “CLGF is well managed and a review of evidence provided has shown adequate governance and internal controls are in place “. It also noted that CLGF has a proven track record of delivery and continues to ensure management systems are in place and fit for purpose. Further work will be needed to follow up on the formalisation of CLGF’s work with downstream partners and this will be undertaken as part of the proposed monthly monitoring discussions and as part of the Annual Review processes. Any issues identified will be tracked and followed up by the programme team.	Low / Unlikely

59	Against the risks that can be foreseen and with the mitigation measures planned, we consider the programme risk [at approval] to be Low.