Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value: £8,014,091		Review Date: June 2017
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A+
Risk Rating	Medium	Major	Major

Summary of progress and lessons learnt since last review

COUNTDOWN is a research consortium dedicated to investigating cost-effective, scale-up and sustainable solutions, necessary to control and eliminate the seven most common Neglected Tropical Diseases by 2020. It is operational in 4 countries – Ghana, Cameroon, Liberia and Nigeria. Operations in Nigeria commenced in early 2017.

COUNTDOWN has moderately exceeded expectations during the review period. It continues to engage well with national governments, resulting in effective policy influencing across multiple sectors. Collaborative efforts include with the Government of Ghana to improve access and timings of interventions for Lymphatic Filarisis, as well as work on female genital schistosomiasis. WHO has cited COUNTDOWN research in its fourth NTD report, ‘Integrating neglected tropical diseases in global health and development’ demonstrating the increasing influence of COUNTDOWN’s work in global NTD policy and control.

Eleven peer-reviewed articles have been published by COUNTDOWN in the review period, including in The Lancet, PLOS Neglected Tropical Diseases, Infectious Diseases of Poverty, International Journal of Parasitology and Parasitology Open.

COUNTDOWN has demonstrated a good focus on gender and equity. It is important that key learning on gender and equity in NTD policy and control programmes continues to be drawn out throughout the course of the programme.

Summary of recommendations for the next year

1. Research to draw out learning on gender and equity issues through a case study per country – by May 2018
2. COUNTDOWN to report on effective strategies for disseminating its findings to populations at risk of NTDs (as per the request from Ministries of Health) in the next annual report – by May 2018.
3. COUNTDOWN should improve forecasting over the next year and aim to have a variance (between budget and spend) in the region of 5%.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

Outline of the programme

DFID’s Research and Evidence Department (RED) commissioned a programme of NTD Implementation Research that will directly contribute to the achievement of the 2020 NTD elimination and eradication goals through providing a greater understanding of how best to cost-effectively and sustainably deliver integrated NTD Control Programmes at scale.

This is linked to DFID’s wider work on tackling NTDs, and DFID committed £245 million to supporting the control of Neglected Tropical Diseases (NTDs) over the period 2011-15.

The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) programmes to treat and control up to 7 NTDs (schistosomiasis, lymphatic filariasis, onchocerciasis, trachoma and three soil transmitted helminths) simultaneously.

Liverpool School of Tropical Medicine (LSTM) was awarded a contract of £7,012,587, which has recently been increased to £8,014,091 for delivering this research programme. The increased figure will allow the programme to upscale their work in Nigeria, a country with one of the greatest NTD burdens globally.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A – outcome met expectations

The outcome indicator for COUNTDOWN is improved availability, acceptability, affordability, and accessibility of NTD interventions to individuals and communities. COUNTDOWN met the target, to have at least one example of evidence influencing expanded access or more effective programming. COUNTDOWN piloted a tool on the timing of mass drug administration (MDA), and the evidence generated has been used, in partnership with Ghana’s national NTD programme, to improve access and timings of interventions against Lymphatic Filariasis. It has also worked with Ghana’s Ministry of Health on tackling the high rates of female genital schistosomiasis, successfully influencing female genital schistosomiasis being included in the National Research Agenda 2030 on Maternal & Child Health. Researchers from the four COUNTDOWN focus countries have also been asked to serve on national NTD steering committees.

COUNTDOWN research has been cited in the 4th WHO report on NTDs, Integrated Neglected Tropical Diseases in Global Health and Development as well as within the revised national planning for the four focus countries. COUNTDOWN is also piloting the global WHO draft Gender Toolkit in Nigeria and feeding this back to inform adaptations before finalisation.

Overall output score and description: A+ – outputs moderately exceeded expectations

COUNTDOWN has moderately exceeded expectations overall. Its research has proven to be highly relevant to policymakers, responding to their evidence needs. It has exceeded its targets in regard to publishing peer reviewed articles and products and undertaking capacity building on NTD research, incorporating a strong analysis on gender and equity throughout, in line with the global Leave No-one Behind agenda.

Key lessons
- Involving stakeholders from national government, international NGOs, local elders, chiefs and community leaders in planning, implementation and learning has led to strong buy-in for research conducted.
- Inviting local and national media to research advocacy meetings has led to increased coverage on NTDs, as well as a ripple effect on social media (especially Twitter).
- There is a need to reframe the discourse around NTDs to increase attention to socio-economic factors and address root causes of disease trends.
- The multi-disciplinary focus of COUNTDOWN provides multiple leverage points to influence decision-making on NTD programming.

Key actions
- COUNTDOWN to continue monitoring exchange rate fluctuations, particularly in Liberia where the USD/GBP exchange rate has impacted on partner budgets – ongoing.
- COUNTDOWN to finalise updating of its logframe in alignment with the DFID Health Research Results Framework – by August 2017.
- COUNTDOWN to speed up partner payments so that invoices submitted to DFID provide an accurate picture of expenditure – ongoing.

Has the logframe been updated since the last review?
No. COUNTDOWN is currently working on updated its logframe, to incorporate indicators from the DFID Health Research Results Framework.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones by March 2017	Progress
Evidence-based strategies identified through COUNTDOWN research and evidence synthesis initiatives.	Research begins in two additional COUNTDOWN countries (Nigeria and Liberia) and the on-going research in the two initial countries (Ghana and Cameroon) identifies 3 evidence based strategies in response to priority needs of NTD policymakers and programmes.	Met expectation: Research has begun in Nigeria and Liberia. / Three evidence-based needs have been identified in Ghana and Cameroon.
Open-access knowledge products: peer reviewed journal articles	8 peer reviewed articles submitted and accepted	Moderately exceeded expectation: / 11 peer reviewed articles have been submitted and accepted
Open-access knowledge products: presentations/ blogs/ briefs.	70 products developed and geographic dissemination mapped	Substantially exceeded expectation: / 147 products have been developed – geographic dissemination has been mapped where possible (most are global products).

Key Points:
Output 1 has moderately exceeded expectations. COUNTDOWN is generating high quality research evidence that responds to the priority needs of national stakeholders. In Cameroon COUNTDOWN is piloting bi-annual deworming of school-aged children to accelerate disease control targets, extending treatment to a wider group not currently targeted in the national school-based strategy, including pre-school and out of school children and all adults. It is also expanding access to the onchocerciasis treatment (doxycycline) to vulnerable groups who reject taking the current MDA of ivermectin due to fears about side effects. In Ghana COUNTDOWN is addressing equity issues through extending treatment to all age groups for schistosomiasis to test the acceptability and feasibility of the approach. Current research across all four countries has found that the lack of appropriate information on NTDs perpetuates transmission. Initial results suggest that challenges to effective MDA delivery include low community drug distributor motivation, limited awareness at community level on MDA programmes, the rejection of drugs due to side effects and traditional beliefs about NTDs being due to curses. Findings also highlight that female Community Drug Distributors may be seen as more effective vehicles for MDA; they are viewed as more approachable and better able to influence communities.

Eleven peer-reviewed articles have been submitted and accepted. This includes an early synthesis review on female genital schistosomiasis published in Science Direct, which was referenced in the 4th WHO report on NTDs. 147 products have been developed including 96 blogs, 42 presentations/posters, 1 book chapter and 9 media articles. The COUNTDOWN presentations at the COR-NTD and Health Systems Global meetings were well received, and demonstrated very strong, LMIC-driven leadership.

In regard to innovative contextual solutions to advances in global NTD science, two examples from the broad work that COUNTDOWN is doing are: (i) Cost effectiveness and acceptability of community wide mass treatment for controlling morbidity and eliminating transmission for schistosomiasis; and (ii) Impact and practical implications of the innovative use of doxycline in a community wide setting combined with a vector control strategy.

Summary of responses to issues raised in previous annual reviews (where relevant)
Researchers on national NTD steering committees have supported work to be operationally relevant.

Recommendations
1. Research to draw out learning on gender and equity issues from a case study per country – by May 2018
2. COUNTDOWN to report on effective strategies for disseminating its findings to populations at risk of NTDs (as per the request from Ministries of Health) in the next annual report – by May 2018
Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control.
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones by March 2017	Progress
Revised NTD national plans and roadmaps in SSA countries as updated by evidence of scale up of pro-poor, effective and efficient approaches.	Seminars involving a panel of research experts discussing the latest research findings have been facilitated within relevant National/State/ District policy-making institutions in 4 COUNTDOWN countries	Met expectation: Seminars have been held in Liberia, Ghana, Cameroon and Nigeria.
Multi sectoral networks influenced to include evidence-based NTD programme strategies in planning within and beyond the health sector.	COUNTDOWN examines NTD National/State/District operational plans in all 4 COUNTDOWN countries to determine NTD priorities and assess which would benefit from new evidence-based strategies and multi-sectorial working	Met expectation: Plans have been examined across all four countries.
Case studies demonstrate a portfolio of change in the utilisation of evidence occurring at a national, state and district level.	4 (2 additional case studies) describe policy/operational plan analysis priorities in two additional countries (Nigeria & Liberia)	Met expectation: Case studies have been submitted.

Key Points
This output has met expectations. In Nigeria, the newest of COUNTDOWN’s focus countries, there is ongoing data analysis for the baseline on successes, challenges and bottlenecks of NTD programming in two states with stakeholders from federal, state and local government, as well as communities. COUNTDOWN was launched during the 18th NTDs Steering Committee Meeting; the Research Sub-Committee of the NTDs Steering Committee has agreed to provide an advisory role to the work in Nigeria, which is expected to strongly support research relevance and uptake. In Liberia COUNTDOWN has been working alongside the Ministry of Health to understand perspectives of people chronically affected by NTDs. This is to inform the implementation of a strategic plan for integrated case management of NTDs, the first of its kind in Sub-Saharan Africa. COUNTDOWN also worked in partnership with the Ministry of Health to launch the Case Management Strategy and inaugurate the first Liberian NTD Ambassador. In Ghana, COUNTDOWN participated in a national level expert meeting on onchocerciasis and in Cameroon it was an official sponsor of a schistosomiasis annual conference which was held under the patronage of the Minister of Public Health and Minister of Basic Education; recommendations from the conference were presented at the WHO NTD Summit. COUNTDOWN was also invited, by the Bill & Melinda Gates Foundation, to join expert discussions on schistosomiasis and soil-transmitted helminths.

COUNTDOWN has successfully reviewed operational NTD plans in all its countries of operation. It has undertaken both policy and stakeholder analysis and reviewed bottlenecks in NTD control and elimination. This will supports its research to continue to be as operationally relevant as possible.

Contributions to global science include involvement of multi-disciplinary investigators and continued engagement with all stakeholders to understand how research can contribute to a change in policy and or practice and the steps they perceive necessary to achieve such change.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations N/A

Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country based research communities.
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones by March 2017	Progress
Involvement of multi-sectorial stakeholders at national, state and district level in developing linkages, partnerships, mentorships across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming	Evidence of physical meetings taking place between cross sectors and policy makers to manage research, synergising across sectors	Met expectation: COUNTDOWN has been active in cross-sector meetings including in Water, Sanitation and Hygiene (WASH) and Maternal and Child Health.
COUNTDOWN stakeholders engaged in implementation research training to conduct research and effectively disseminate and make use of the research	Prioritised recommendations for improved NTD Implementation research capacity at appropriate levels (district, state, national) in at least 3 COUNTDOWN countries	Moderately exceeded expectation: Capacity building gaps were identified for building research capacity and 14 initiatives undertaken in total across all 4 countries in the review period.

Key Points

This output has moderately exceeded expectations. Globally an important strategic agenda is to strengthen evidence on how to deliver effective WASH interventions for NTDs and embed these findings in guidance and practice. Poor water and sanitation means that reinfection rates for people who are dewormed is very high. COUNTDOWN is collecting WASH data to determine associations with schistosomiasis and soil transmitted helminths to help determine relevant control strategies. In Ghana COUNTDOWN was successful in putting female genital schistosomiasis on the National Research Agenda 2030 on Maternal and Child Health. COUNTDOWN has also contributed to the Strategic Technical Advisory Group (STAG) on monitoring and evaluation of NTDs in Nigeria.

Capacity building initiatives across all four countries have exceeded expectations. Capacity assessments were undertaken and COUNTDOWN has been working to fill identified gaps. This includes, but is not limited to, training on conducting evidence synthesis, research techniques on paper/poster writing, health economics data, as well as on using specialist software.

Summary of responses to issues raised in previous annual reviews (where relevant)
COUNTDOWN joins a regular meeting with other DFID-funded NTD programmes to increase collaboration. The assessment of cost-effectiveness and sustainability of innovations being tested by the programme is supported by the commencement of health economics research. Rapid diagnostic research is no longer being undertaken and the use of molecular technologies have been vastly scaled back (used for quality assurance only on small samples) as a result of DFID advice.

Recommendations

N/A
D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key partnerships have now been established in the focal countries and there is now a greater emphasis on delivering research on the ground. Research (personnel) costs are still the most significant cost driver but there is a shift in activities from recruiting staff and developing workplans to delivering results that will have a lasting impact on NTD control. Spend to date is made up of Programme Management (30%); Control Strategies (25%); Applied Social Science (18%); Monitoring & Evaluation (7%); Research Uptake and Capacity Building (6%); Health Economics (3%); Evidence Synthesis (1%), with the remaining 9% representing agreed partner advances.

VfM performance compared to the original VfM proposition in the business case

COUNTDOWN seeks to advance value for money through their adherence to economy, efficiency, effectiveness and cost-effectiveness.
- Economy: through avoiding travel when other means of technology are available and combining meeting attendance where appropriate.
- Efficiency: drawing on teams experience for monitoring project activity. Sharing resources (field staff, vehicles, fuel) with other programmes operating in the same location.
- Effectiveness: establishing strong links and networks at international, national, district and community levels. Through country partners developing and implementing research plans and reaching out to all stakeholders fostering cross-sector working. Some of the results of the partnership and networks are described under outputs 1-3, above.
- Cost-Effectiveness: sharing resources and continuously monitoring partner costs to ensure that these are competitive and are based on actual need. COUNTDOWN have also secured open-access waivers saving costs associated with research outputs.

Assessment of whether the programme continues to represent value for money

The programme continues to represent good value for money. COUNTDOWN had developed expertise in building evidence to address priority issues for NTD control programmes, and how to ensure gender and vulnerability are included in disease control programmes. Extensive work has been undertaken to define what vfm means for the programme, drawing on examples and best practice from the literature and similar implementation research programmes

Quality of financial management

There are some financial delays in reporting from Sightsavers, due to reports needing to pass through their headquarters. Current invoices submitted to DFID do not provide an accurate picture of the level of expenditure due to the delay in processing payments to partners and this is something that will be discussed during the forthcoming reporting year.

During 2016/17 the variance between budget and spend was approximately 10%. This represents an underspend of £263k against a contractual budget of approximately £2.55m for the year. Previous issues regarding claiming in advance of need have been fully resolved and quarterly invoices are submitted within an acceptable timeframe. COUNTDOWN should ensure that DFID is made aware immediately of any significant events that may impact on their ability to hit financial forecast targets.

Date of last narrative financial report	4 May 2017
Date of last audited annual statement	7 November 2016

E: RISK (½ page)

Overall risk rating: Major

The overall risk rating for COUNTDOWN remains Major.

Overview of programme risk

- The external context continues to be a major risk, due to the challenges of working in insecure states in Nigeria and Cameroon. For Nigeria, partnering with Sightsavers, an international NGO which has a long-standing presence in the focus states, has been a mitigating factor. For Cameroon, the review period has seen some local political unrest in Buea, which affected field work. The risk has since been reduced but COUNTDOWN continues to monitor the situation.
- The delivery risk continues to be major, as the programme is in early stages in Nigeria and Liberia.
- The operational risk continues to be moderate. DFID is well placed to manage the programme, through the Health Research Team, as well as strong involvement of the NTD hub of the DFID Policy Health Services Team.
- The safeguarding risk is minor, with minimal risk of harm from the research, especially as issues around equity and ethics are central to COUNTDOWN’s work.
- The fiduciary risk is reduced to moderate, and previous challenges with financial management have been addressed.
- The reputational risk has been increased to moderate, due to an increasing global attention on NTDs, putting COUNTDOWN’s work in a greater spotlight.

Outstanding actions from risk assessment

DFID will continue to work with COUNTDOWN as they mitigate the risks of working in the countries and will discuss risk management and mitigation at regular meetings throughout the year.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

COUNTDOWN is on track to deliver its outputs against the planned timeframe. There was some slippage on the timelines for health economic activities due to the lack of availability of selected economists, which has now been addressed and the work is underway. The political unrest in Buea, Cameroon, led to readjustment of the workplan but there was no implication to the completion of activities.

Performance of partnership(s)

COUNTDOWN partners have clear annual workplans which are overseen by the COUNTDOWN management team in LSTM. Quarterly reports are submitted by each partner to LSTM to help track progress. This includes any preliminary findings, progress against indicators, planned activities, a review of risks, as well as financial reporting. A monthly skype meeting is also held between all partners. The COUNTDOWN programme management team make at least one trip a year to each focus country to support with activities.

Asset monitoring and control

COUNTDOWN maintain an asset register recording all items with a value in excess of £500. The register is updated regularly and is provided as part of the programme’s Annual Report and also available on request. The Programme Team have not undertaken any spot-checks to date, but reserve the right to do so at any time.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

This is not applicable for this programme. The partnership principles were not used in monitoring this project as it does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There was no formal evaluation for the programme during the review period. Partners communicate regularly to share lessons on emerging evidence. Quarterly programme monitoring reports assessing progress against indicators are provided by each partner to LSTM, who monitor that the overall programme is on track. Research outputs are monitored through ResearchFish, the online system to collect details about publications and other outputs. Succinct one pagers on research findings have been produced for the programme, which are highly accessible and should be continued.

Monitoring progress throughout the review period

This annual review was undertaken by members of the health research team in DFID’s Research and Evidence Division. The team included a Social Development Advisor, a Senior Health Advisor, a Health Advisor and the Deputy Programme Manager, with inputs from DFID policy advisers. DFID staff attended COUNTDOWN presentations (including at the Coalition for Operational Research for NTDs (COR-NTD) conference and Health Systems Global symposium), and had ongoing communication with COUNTDOWN throughout the year, including several face to face meetings in Liverpool.

Annual Review - Summary Sheet 2016

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value: £8,014,091		Review Date: 1 July 2016
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Medium	Major

Summary of progress and lessons learnt since last review

COUNTDOWN is a research consortium dedicated to investigating cost-effective, scale-up and sustainable solutions, necessary to control and eliminate the seven most common Neglected Tropical Diseases by 2020. COUNTDOWN has made good progress in the past year, with all milestones met or partially exceeded. It has established its research programme in Ghana and Cameroon, and following the approval to expand the research in Nigeria, and re-establish activities in Liberia, progress has been also been made establishing research in these countries as well.

There has been positive engagement with key policy makers in the targeted countries, including the Minister of Health in Cameroon involved in the in-country launch and an opportunity to engage with the World Health Organisation (WHO) African Regional Program Review Group for Neglected Tropical Diseases (NTDs) at COUNTDOWN’s partner meeting in Accra.

Publications have included four submissions of articles to peer reviewed journals, including Lancet Infectious Diseases and International Health, and COUNTDOWN staff co-authoring a book chapter on the Social and Economic Impact of Neglected Tropical Diseases in Sub-Saharan Africa.

As the programmes are developed, COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. DFID has also spoken to COUNTDOWN regarding tightening up its financial accounting, with accurate budgeting, and only claiming for expenditure that has already been spent.

Summary of recommendations for the next year
1. COUNTDOWN should ensure that its submissions to peer-reviewed journals and knowledge products; presentations/ blogs/ briefs are as operationally relevant as possible, and be targeted to key policy makers in affected countries and implementing organisations (ACTION: COUNTDOWN – ongoing)
2. COUNTDOWN should increase its collaboration with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. DFID will ensure that COUNTDOWN is involved in NTD partner meetings whenever these take place. (ACTION: COUNTDOWN & DFID – immediate and ongoing)
3. COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. (ACTION: COUNTDOWN – immediate and ongoing)
4. COUNTDOWN should reconsider its proposed work on products (particularly diagnostics), following discussion with DFID, and ensure this work is complementary to the work of the DFID funded Product Development Partnerships in this area. (ACTION: COUNTDOWN – November 2016)

DFID has discussed with COUNTDOWN regarding improving the financial management, with accurate budgeting, and only claiming for expenditure that has already been spent. (COUNTDOWN – already actioned, following meeting with DFID).