Amendment to Accountable Grant

Between

The Government of the United Kingdom of Great Britain and Northern Ireland acting through the Department for International Development (“DFID”)
and
The Save the Children Fund

Project Name: Multisector Humanitarian Response Programme – Yemen (MHRP)
Project Number: (300046-101)

I refer to the Accountable Grant letter for the above project signed by DFID and The Save the Children Fund on 15 June 2017. Following recent correspondence, DFID propose to increase the amount made available to The Save the Children Fund by £10,900,000 (ten million, nine hundred thousand pounds sterling). DFID also propose to change the project end date to 31 March 2020.

I propose that the figures and words “£1,100,000 (one million, one hundred thousand pounds sterling)” in paragraph 3 of the original Accountable Grant letter are deleted and replaced by the figures and words “£12,000,000 (twelve million pounds sterling)”.

I propose that the end date of “1st August 2017” in paragraph 3 of the original Accountable Grant letter is deleted and replaced by “31 March 2020".

I propose the funds allocation schedule
1 Apr 2017 – 31 Mar 2018 :	£1,100,000

in paragraph 3 of the Accountable Grant letter is deleted and replaced by:
1 Apr 2017 – 31 Mar 2018 :	£3,936,350
1 Apr 2018 – 31 Mar 2019 :	£4,032,981
1 Apr 2019 – 31 Mar 2020 :	£4,030,669

I propose the reporting schedule outlined at the end of paragraph 22 is amended to include the following lines with updated due dates for quarterly reports:
2nd Quarter (Jul 2017 – Sept 2017) – 15 November 2017
3rd Quarter (Oct 2017 – Dec 2017) – 15 February 2018
4th Quarter (Jan 2018 – Mar 2018) – 15 May 2018
5th Quarter (Apr 2018 – June 2018) – 15 August 2018
6th Quarter (July 2018 – Sept 2018) – 15 November 2018
7th Quarter (Oct 2018 – Dec 2018) – 15 February 2019
8th Quarter (Jan 2019 – Mar 2019) – 15 May 2019
9th Quarter (April 2019 – June 2019) – 15 August 2019
10th Quarter (July 2019 – Sept 2019) – 15 November 2019
11th Quarter (Oct 2019 – Dec 2019) – 15 February 2020
12th Quarter / final report (April 2017 – Mar 2020) – 15 May 2020

I propose the addition of a new paragraph – inserted after paragraph 33 of the original agreement: numbered 33. b)

“33. b) DFID may at any time during the programme request the Partner undergo independent monitoring through the DFID Yemen Independent Monitoring Programme.  DFID or its agents will be granted access, as required, to all project sites and relevant records. The Partner will ensure that necessary information and access rights are explicitly included within all arrangements with Downstream Partners.”

This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 012017.

Please sign both copies of this letter - return one to me and retain the other for you own records.

Signed for DFID:	Confirmed by Save the Children UK:
Name:	Name:
Position:	Position:
Date:	Date: