Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Strengthening prevention of gender-based violence in Rwanda
Programme Value: £4.6 million		Review Date: July 2017
Programme Code: 204142	Start Date: August 2014	End Date: August 2018

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	n/a	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate

Acronyms:
CA – Community Activist (s)
GBV – Gender Based Violence
GLSGBV – Great Lakes Sexual and Gender
Based Violence Programme
GoR – Government of Rwanda
IPV – Intimate Partner Violence
ISD – Inclusive Societies Department
IZU – Inshuti z’Umuryango/Friends of the Family
MIGEPROF – Ministry of Gender and Family Promotion
MINALOC – Ministry of Local Government
MIS – Management Information System
NCC – National Children’s Commission
OL – Opinion Leaders (s)
PAC – Programme Advsiory Committee
RWAMREC – Rwanda Men’s Resource Centre
RWN – Rwanda Women’s Network
WB – World Bank
WS – Women’s Space (s)
WSF – Women’s Space Facilitator (s)
WW – What Works
VAC – Violence Against Children
VAWG – Violence Against Women and Girls

Summary of progress and lessons learnt since last review

The Strengthening Prevention of Gender-Based Violence (GBV) in Rwanda programme made solid progress during its 3rd year. The Indashyikirwa consortium saw a smooth transition from couples training to activism, and further training of opinion leaders (OL). Local-level advocacy has also succeeded in reducing illegitimate costs charged by authorities to survivors of GBV when attempting to access services, which deterred reporting to officials. The Inshuti z’Umuryango component trained nearly 30,000 volunteers (Izu), with over 3,000 now operational in 9 districts. A key achievement of the recent national budget process was the allocation of funds by the National Children’s Commission (NCC) towards the sustainability of the Izu cadre. The What Works (WW) evaluation (funded by DFID’s Inclusive Societies Department (ISD) as a separate programme - 203709) completed collection of midline data and made good progress in publishing qualitative findings.
[note] The programme is made up of 3 components: Indashykirwa - consortium-delivered community prevention, awareness raising and advocacy, a What Works impact evaluation of Indashyikirwa, and Inshuti z’Umuryango – a cadre of national child protection para-professionals.
[note] The government-led approach is rolling out the ‘operationalisation’ of Izu in phases across the country, with lessons being learned from the initial cohort to improve and inform this process. See output indicator 1 for more.
[note] Quantitative baseline findings have not yet been published following the recommendations of MIGEPROF. See Output 4 for further information.

This Annual Review (AR) highlighted a number of strengths of the programme across all components, including:
- Emerging stories demonstrating significant improvement in individuals’ lives, due to the cessation of severe emotional, economic, physical and sexual violence;
- The early signs of a slow break-down of taboos. Both men and women involved in the programme highlighted that they are experiencing some backlash from other community members, but that they are persevering because ‘the benefits are worth it’;
- Strong integration of Indashykirwa and Inshuti z’Umuryango actors and systems with existing government support structures, particularly sector and district-level authorities. Authorities are grateful for their reduced workload (due to a positive reduction in perpetration/reporting and more cases being resolved within the community) as well as the reduction in time for cases to be resolved (as a consequence of an overworked system). Authorities also noted that the programme is supporting sectors to reach their imihigo (performance contract) targets on GBV (number of parents’ evenings on GBV topics and number of Intimate Partner Violence (IPV) cases reported at sector level).
  [note] As often occurs during anti-GBV programming, reporting in Murama sector initially increased due to confidence in support systems and reduced taboos, but cases reported directly to the police or sector level have now decreased as perpetration of violence has reduced overall.
- Families involved in the programme are increasing their household income/moving out of poverty due to better communication, sharing workloads and sharing financial decision making. A village leader who received OL training commented: (my wife and I) ‘do things on time now. And we can do extra things as well as agriculture, because we have more time now.’

The final year of the programme represents a critical period for all components with a number of risks/opportunities:

In 2016, the Ministry of Gender and Family Promotion (MIGEPROF) secured funding from the World Bank (WB) Great Lakes Sexual and Gender Based Violence (GLSGBV) programme to implement the Indashyikirwa couples curriculum and Women’s Spaces (WS) in four districts in Eastern province for one year, including an impact evaluation (separate to the impact evaluation being conducted by DFID through WW). The districts chosen by GLSGBV are those in which Indashyikirwa is not operating. The inception of the GLSGBV programme has faced substantial delays, with MIGEPROF currently in the process of securing the same consortium as that delivering the DFID programme – CARE, Rwandan Mens’ Resource Centre (RWAMREC) and Rwanda Women’s Network (RWN) – to deliver activities. As such, all programme partners have been involved in both supporting and mitigating possible risks emerging from this arrangement over the past year. For example, the WW team fed into a slight revision of the curriculum for GLSGBV, while the consortium has begun recruitment of sufficient human resources to ensure GLSGBV delivery does not negatively affect the ongoing delivery of the DFIDR programme. There remain considerable risks associated with this ‘parallel’ programme – including branding and the sensitive handling of data emerging from its impact evaluation – which must continue to be mitigated. However, the active engagement of all partners, including the WB, is encouraging and opportunities for learning and collaboration should not be overlooked.

A theme throughout the AR was the need for greater coordination. This includes within the Indashyikirwa consortium (for example, information sharing), between the components (and various partners), as well as the various actors at district and sector levels (and below). There are already promising signs from partners of increased collaboration, however it will be important to engage MIGEPROF and the Ministry of Local Government (MINALOC) as well for sustainability.

Change in the Senior Responsible Owner (SRO) and programme manager roles in DFIDR slowed momentum over the past year. There is now an opportunity for DFIDR to demonstrate greater leadership and support more proactive coordination across the GBV sector. There is already strong interest from all partners about the future of the programme. DFIDR has secured approval to undertake a design process for a possible follow-up/Phase II, and will consult widely as part of that process – likely to begin in late 2017.

Following the independent audit of the Indashyikirwa consortium completed in June 2017, a number of capacity building needs were identified which will require both DFIDR oversight and engagement. The consortium is demonstrating a harmonised and constructive approach in response to the audit, including the development of capacity building action plans.

A full list of recommendations for the next year can be found on page 7.

Responses to recommendations from Annual Review 2016:

Rec 1: CARE, RWN and RWAMREC to explore options for strengthening psycho-social support (including professional supervision structures) for field workers and community activists and women space facilitators, drawing on existing expertise/networks. [September 2016]
Complete: Training on psycho-social support was delivered to field officers and supervisors in June 2017 for Community Activists (CA) and Women’s Space Facilitators (WSF). This will be followed by a session for sharing experiences in July. A mechanism for tracking trends and support needs should be put in place.

- Rec 2: RWN to (a) closely monitor uptake of women’s spaces and outreach by women’s space facilitators to ensure reach to the most vulnerable women and girls, including those living with disability [ongoing]; (b) report separate data on number of i) incidents reported to women’s spaces ii) additional incidents reported to facilitators through outreach and iii) number of people engaging in dialogue at women’s spaces [starting next quarterly report]; and (c) together with RWAMREC and CARE to review and refine the field guide for the women’s space facilitators [ongoing].
- Ongoing: There was a lack of clarity among implementing agencies on this. Some changes were taken forward in the new logframe, but monitoring only started in the second quarter of 2017. Further efforts to include/track reach to the most marginalised, particularly women with disabilities, is needed.

- Rec 3: RWN (with RWAMREC and CARE Rwanda) to review advocacy approach on sector imihigo [by January 2017].
- Complete: An advocacy plan including sector Imihigo targets was developed for 2017.

- Rec 4: DFID Rwanda to redraft output indicator 2.3 to include advocacy work not related to imihigo [by January 2017].
- Complete: Completed during logframe review.

- Rec 5: RWN to include disabled persons representatives (individuals elected within local government structure) in future rounds of the opinion leader training, alongside journalists and newly elected officials [by May 2017].
- Complete: Eight OL with disabilities were included in OL refresher training in May 2017. RWN will provide a total number of OL with disabilities (including those captured in 2016 and February 2017 training) for the next quarterly report. Further effort must go into ensuring the inclusion of participants and beneficiaries with disabilities.

- Rec 6: DFID Rwanda to work with MIGEPROF to re-energise Programme Advisory Committee (PAC) to ensure synergies between UNICEF Violence Against Children (VAC) model and Indashyikirwa at operational level. [aim for next PAC in July 2016, and ongoing]
- Complete: The most recent PAC meeting was held on 12 July 2017, with all partners in attendance including MIGEPROF. Increased collaboration between the Indashyikirwa consortium, UNICEF and NCC was highlighted and promising ideas for ‘quick wins’ were identified. Arrangements are underway for a meeting between all implementing partners, led by the NCC by end of August.

- Rec 7: CARE, RWN, RWAMREC and WW develop plan to share lessons and evidence with CSOs through Profemme-coordinated GBV Prevention network, as part of the research uptake strategy [end August 2016].
- Delayed: Qualitative data to be shared with CSOs in September 2017.

- Rec 8: The WW research consortium should prioritise finalising two key agreements with programme partners: (a) a Memorandum of Understanding (MOU) to agree ownership and attribution of evaluation products, including the economic evaluation, and (b) the research uptake and stakeholder engagement strategy. This is increasingly important as evaluation papers start to be produced [by end October 2016].
- Complete: a) The MOU has been agreed pending final approval by the whole consortium. This should be expedited to conclude this process as soon as possible, however the MOU reflects current practice with limited risk arising from the delay. b) Research Uptake Strategy complete.

- Rec 9: The WW research consortium should ensure they take appropriate time to engage with programme partners at key points in the evaluation or in decision making. Wherever possible noting capacity constraints, engagement should be done in person rather by correspondence [ongoing].
- Complete.

- Rec 10: DFIDR to commission an independent assurance audit of the GBV prevention component, including the link between CARE and RWAMREC/RWN [by end 2016].
- Complete: The audit was completed by KPMG in June 2017 with an unqualified opinion. Action plans to respond to issues raised are under development, with early draftsseen by DFID.

- Rec 11: DFIDR to use quarterly/4-monthly coordination meetings to conduct regular reviews of risk matrix with implementation partners [start date September 2016].
- Ongoing: This was raised in the June 2017 quarterly meeting. A session to better support partners to understand DFID’s approach to risk is planned as part of ongoing capacity building.

- Rec 12: CARE to initiate quarterly Leadership group meetings between CARE (Country Director and Vulnerable Women programme coordinator), RWAMREC’s Executive Secretary and RWN’s Director, in order to improve partnership-working at a strategic level.
- Ongoing: This has been inconsistent and should be addressed.

- Rec 13: DFID Rwanda to revise Logframe in consultation with implementing partners and WW team (both minor edits suggested to outcome 1.2, outputs 2.1 and 4.1, but also a review of the entire logframe to avoid duplication between some output and outcome indicators, to clarify impact and outcome level indicators, and to refine the milestones and targets in the light of the baseline findings produced by WW. [by end December 2016].
- Complete: The logframe revision was completed in May 2017.

- Rec 14: DFIDR and DFID Violence Against Women and Girls (VAWG) team to explore options for evaluating long-term impact of model to evaluate whether behaviour change and social norm change are sustained beyond the current project and WW timeframe [ongoing].
- Ongoing: The WW evaluation needs an (either cost or no cost) extension in order to complete analysis of the evaluation, due to a 1 year delay in the inception period. This is pending with DFID UK, with the outcome expected by Dec 2017. Opportunities for additional evaluations to capture the sustainability of social norm change still need to be explored. The design of a possible follow-up or ‘Phase II’ programme may provide an opportunity for this if the current programme cycle does not.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204142/documents/
DevTracker Link to Log frame:

Rates of GBV are high in Rwanda. It is estimated that 43.9% of all women aged 15-49 have suffered physical or sexual violence. Rates of sexual violence are also high - 45% of women survivors of sexual violence first experienced sexual violence by the age of 18, and 16% by the age of 15. While IPV remains the most pervasive form of violence, Demographic Health Survey (DHS) data indicates a possible drop in IPV over recent years. The recently released DHS 2014/15 lists the percentage of ever-married women age 15-49 who report having often or sometimes experienced physical and/or sexual violence in the past 12 months committed by their husband/partner at 20.7% compared to 44.3% for the equivalent metric in 2010 (DHS 2010). These findings should be interpreted with caution given that DHS 2005 reports a rate of 27.1% for the equivalent metric, (noting DHS 2005 had differences in phrasing regarding frequency measurement and some missing data). Nonetheless, these figures are encouraging. The impact evaluation of this GBV-prevention programme will complement national-level data by providing invaluable in-depth information about the prevalence of IPV in the communities in which the programme is working, and testing what works to reduce such violence. Children are also no strangers to violence in Rwanda. One representative national survey indicates that nearly two thirds of male respondents and over 50% of women reported being victims of physical violence as children. In addition, 44% of male respondents and 40% female respondents confirmed that they had witnessed acts of violence between their parents.
[note] Republic of Rwanda (2015) Rwanda: DHS 2014/15. National Institute of Statistics of Rwanda and Ministry of Finance and Economic Planning.
[note] Republic of Rwanda (2014) DHS 2014/15. National Institute of Statistics of Rwanda and Ministry of Finance and Economic Planning.
[note] Republic of Rwanda (2005) DHS 2005. National Institute of Statistics of Rwanda and Ministry of Finance and Economic Planning.
[note] Sleigh H and A Kimonyo (2010) “Masculinity and Gender Based Violence in Rwanda. Experiences and Perceptions of Men and Women” Images research, commissioned by Rwanda MenEngage Network
The UK is providing up to £4.6m over 4 years (2014-2018) to strengthen capacity at community level to prevent violence against women and children in Rwanda. £3.99 million has been allocated to CARE International to further develop and roll out its community-level programming on Gender-Based Violence (GBV) prevention (Indashyikirwa – Agents of Change) in seven districts, working with two partner Rwandan civil society organisations (CSOs). Rwandan Men’s Resource Centre (RWAMREC) and Rwanda Women’s Network (RWN) are implementing the community-level interventions. Outputs include:
- Best practice community-based GBV and VAC prevention curriculum developed and implemented
- Improved civil society coordination and partnerships; and increased responsibility of Government of Rwanda (GoR) in the GBV prevention and response space at national and local levels
- Women's Spaces are established and provide information and support to community members and survivors of GBV
- Improved evidence base on ‘what works’ to prevent GBV in Rwanda
A separate research and evaluation component (WW) is being implemented alongside the programme, funded by DFID’s ISD as a separate programme - 203709 - ‘What Works to Prevent Violence Against Women and Girls’. WW are undertaking an impact evaluation of the Indashyikirwa component. This is the only AR specifically for WW in Rwanda, however the WW team are ultimately accountable to programme 203709.
£432,000 has also been allocated to the United Nations Children’s Fund (UNICEF) to support the development and roll out of a new community-level child protection system in Rwanda (Inshuti z’Umuryango – Friends of the Family), a key initiative in the GoR’s Family Promotion policy (2014).
This programme is aligned with the Single Departmental Plan Strategic Objective of ‘tackling extreme poverty and helping the world’s most vulnerable’.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome statement: Reduced prevalence of GBV and strengthened community-level mechanisms for the prevention of violence against women, girls and boys in programme sectors.

There is no new national prevalence data to report against this statement. Only one outcome indicator in the logframe (1.5) has measurable data for the past year, as identified below (the others are measured bi-annually in accordance with WW).

Indicator	Milestone	Progress
1.5 Sustainability of programme activities and results maintained through Government and civil society taking increased responsibility in the GBV prevention and response space at national, local and community levels	District and sector level authorities updated through meetings on the progress of the project and discuss with them their role for sustainability of the project now and after the period of intervention.	Achieved: 4 Quarterly meetings were held in each of the 7 Indashyikirwa districts with District and Sector authorities, WSFs, CAs, National Women’s Council, National Youth Council, GBV CSOs, and Police to update them on activities/GBV issues arising from the community.

The likelihood of achieving the outcome statement within the programme timeframe is high.
There is promising anecdotal evidence from beneficiaries of meaningful change taking place through the programme, which needs to be captured and shared as part of the body of evidence emerging from this programme. This includes the prevention/cessation of all four types of violence, and persistence with change despite backlash from other members of the community. These stories suggest that the assumptions in the Theory of Change are holding. The following are just a few statements from beneficiaries captured on the AR field visit:
[note] Emotional, Economic, Physical and Sexual violence.

“Now women are sleeping” – Male OL and district authority, speaking about both the burden of work and fear of violence that women in the district used to face, which he has seen decrease considerably.
“No church has healed me like the women’s space has” – female beneficiary and survivor of GBV including marital rape, who spoke to us about her experience. She initially approached the women’s space for help alone, but her husband now also attends dialogues and speaks at the WS.
“Now we have a cow!” – Male CA, who spoke about the shift in his family’s income and productivity following the couples training where they learnt about joint financial decision making. He also spoke openly about the physical and sexual violence he had perpetrated against his wife, which has stopped.
[note] The ownership of cows is particularly culturally valued and a sign of status in Rwanda.
“We now have free healthcare for our baby” – couple who could not afford to take their newborn to the hospital, and sought help from their local Izu.

What Works impact evaluation update

The midline couples cohort data collection was completed in November 2016 with 1628 treatment and 1637 control couples (97.2% retention rate from baseline). It is a violation of the Randomised Control Trial protocol to do any interim analyses with this data before the scheduled endline. There was no midline for the community cohort.

While the WW impact evaluation is an enormous asset to the programme, it has perhaps been relied on too heavily as the only source of lesson learning. In the remaining year, further efforts by all partners should be made to collect/analyse/share lessons learned and stories of change, to build a robust and varied body of evidence. Consortium partners and WW should workshop ideas about the various formats such evidence products could and should take. UNICEF, NCC and Save the Children (Inshuti z’Umuryango implementing agency) should also consider such possible outputs as more impact data becomes available.

Overall output score and description

Output	Risk	Weighting %	Score
Best practice community-based GBV and VAC prevention curriculum developed and implemented	Moderate	35	A
Improved civil society coordination and partnerships; and increased responsibility of GoR in the GBV prevention and response space at national and local levels	Moderate	20	A
Women's Spaces are established and provide information and support to community members and victims of GBV	Moderate	25	A
Improved evidence base on ‘what works’ to prevent GBV in Rwanda	Major	20	B

Recommendations:

For All/DFIDR:
1. Greater coordination is needed between i) consortium partners (especially at leadership level), ii) Indashyikirwa and Izu components, iii) partners and government stakeholders (especially MIGEPROF and MINALOC), and iv) implementers at community level, including WSFs, OLs, CAs, and Izu. While some of this is already beginning to happen and partners are taking ownership of the process, DFID has a role to play in facilitating stronger relationships. This will, in part be facilitated by a collaborative ‘mapping’ or timeline of the remaining programme period, drawing on all components. (Led by DFIDR, by December 2017)
2. Further efforts by all partners should be made to systematically collect/analyse/share lessons learned and stories of change (including as a result of activism) from the many sources available to the programme, to build a robust and varied body of evidence. Consortium partners and WW should workshop ideas about how best to do this and the various formats such evidence products could and should take. UNICEF, NCC and Save the Children (Inshuti z’Umuryango implementing agency) should also consider such possible outputs as more impact data/lessons learned become available. (Led by CARE and UNICEF, by August 2018)
3. Further effort must go into ensuring the inclusion of participants and beneficiaries with disabilities, and tracking reach to the most marginalised, particularly women with disabilities, including through more systematic disaggregation of data. This includes providing the total number of OL with disabilities. (Led by CARE and UNICEF, by next quarterly report)
4. Relevant partners to work collaboratively to both mitigate risks and capture opportunities arising from the GLSGBV programme. This includes addressing branding issues, considering where learning opportunities may be possible, and/or working to establish clarity and a shared understanding about the limitations of such opportunities where needed (including through commissioning additional reports/articles/briefs to set out and explain those opportunities/limitations if needed). (Led by DFIDR, ongoing)
5. PAC members should discuss entry points and concerns regarding possible child protection or anti-GBV commitments in household/family imihigo (performance contracts). (For agenda of December 2017 PAC meeting)
6. DFID to explore opportunities for additional evaluations to capture the sustainability of social norm change (beyond the life of the current WW programme). (Led by DFIDR, by August 2018)

For the Indashyikirwa consortium:
1. Consortium must focus on ensuring sustainability and a clear exit strategy from implementation sectors, as the programme moves toward a successful close-out. This must include the sustainability of WS and empowerment/independence of CA and OL. (Led by CARE, by December 2017)
2. Consortium to finalise and implement Capacity Building plans, with approval from DFIDR, and ensure all programme management best practice standards are met for the remaining year (Led by CARE, by October 2017 )
3. CARE to lead the organisation of quarterly leadership group meetings between CARE (Country Director and Vulnerable Women programme coordinator), RWAMREC’s Executive Secretary and RWN’s Director. (Led by CARE, by October 2017)
4. RWN to more systematically collect/analyse/share evidence of policy and/or practice change by local authorities as a result of activism. (Led by RWN, by December 2017)
5. RWN to lead consideration of how national-level OL could be engaged (for the final year, follow up or ‘Phase II’ programme, or independently of the programme) to strengthen the anti-GBV movement and scale up impact. (Led by RWN, by December 2017)
6. RWN to lead consideration of whether further support to WSFs (including training on bookkeeping and additional support for phone and transport costs) is necessary and/or feasible. This should include the development of a mechanism to track trends and support needs regarding psycho-social support. (Led by RWN, by December 2017)
7. All consortium partners to discuss possible approaches to strengthen or systematise targeted outreach to vulnerable/key groups such as people with disabilities and youth, to engage them in WS/CA activities. This should include increased outreach/facilitated coordination between CAs and the WSFs. (Led by CARE, by December 2017)
8. The next quarterly report must update on those indicators which did not yet have data against them for this AR (3.3 i, 3.4), ensure the disaggregation of the necessary data (3.3, 3.4) and distinguish between total incidents and cases received in WS (3.3). (Led by CARE, by October 2017)
9. New milestones for 2018 will need to be agreed between DFID and the consortium for the number of incidents (3.3 ii), given the degree to which this has been exceeded. (Led by DFIDR, by October 2017)

For the Inshuti z’Umuryango:
1. DFIDR, UNICEF and NCC to explore the capacity building needs of the many actors involved in the Izu system – from school leaders and local authorities to Izu themselves - to ensure the system works as designed. (Led by UNICEF, by December 2017)
2. DFIDR to follow up with UNICEF to better understand the direct links between Izu and children, and the role of Izu in explicitly preventing sexual violence against children. (Led by DFIDR, by December 2017)
3. UNICEF and NCC to consider the Management Information System (MIS) needs of NCC to manage the Child Protection system in the long term. (Led by UNICEF, by December 2017)
4. New milestones for 2018 will need to be agreed between DFID, UNICEF and NCC for indicators 1.3 and 1.4. (Led by DFIDR, by October 2017)

For What Works:
1. WW team to communicate more information about what evidence can, and can’t be shared, and when, including the remaining timeline of the evaluation at the next PAC meeting. (WW in December 2017 PAC meeting)
2. DFIDR and WW to expedite conversations with MIGEPROF (and other GoR stakeholders as necessary) to reach an agreement for baseline data to be published. (Led by WW by December 2017)

Has the logframe been updated since the last review?

Yes. The logframe underwent substantial revision in consultation with all partners, completed in May 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Best practice community-based GBV and VAC prevention curriculum developed and implemented
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	35
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes Increased

Indicator(s)	Milestones	Progress
1.1 Community GBV prevention curriculum improved and agreed based on evidence, lesson learning and exchange between CSOs and the GoR	Refined GBV prevention package under implementation	Achieved: Couples curriculum began implementation June 2016. Activism training (now completed) was refined and new messages were developed based on scriptures and laws. The WS module was refined to include new tools.
1.2 Number of Indashyikirwa curriculum-trained couples actively promoting positive attitudes against GBV in target sectors	Community Activism training completed with 420 CA operating in communities and supported in activism actions	Achieved (As per milestone)
1.3 Number, types and frequency of interventions taken by Community Activists and Izu to promote gender equality and challenge GBV and VAC in Indashykirwa target communities	i)Community Activism training completed with 420 CA operating in communities and supported to implement 8,400 activism actions (2 activism actions/activist/month) in a variety of types of activism action e.g. training role plays, dialogue sessions / ii)3,000 Izu fully operational in nine districts of the country, reporting on the number of household visits conducted, campaigns/ or sensitization activities rolled out in the communities	Partially achieved: (i) As of June 2017, 7,140 interventions using drama and dialogues have been undertaken by CA. / Achieved: (ii) 3,537 Izu are operational and reporting in 9 districts - Nyabihu, Nyarugenge, Gasabo, Gicumbi, Rwamagana, Ngoma, Ruhango, Nyamagabe, and Gakenke. 22,228 home visits and sessions for families were conducted by Izu by June 2017.
1.4 Number of trained community based child protection officers (Izu) operating in Rwanda	Izu operational at community level in 12 additional districts (17 total). 12,360 Izu (16,968 total to date) receive initial training based on agreed curriculum.	Partially achieved: As above, due to a change in implementation strategy led by GoR. A phase-based approach is planned to progress operationalisation.

Key Points

Indashyikirwa has completed couples training, transitioned through activist training, and is now focused on sustaining the motivation of CA. While the milestone for interventions led by CA was not met, the vast majority of activists continue to be engaged. Further analysis should be undertaken to follow up with those activists who are not reaching their targets to encourage and support them where possible.

Couples received compensation for travel costs and food paid as a lump sum during training, and those who became CA may have had expectations that such compensation would continue (CA do receive reimbursement for transport, which may be inadequate in some circumstances). As the compensation was highlighted as a key factor encouraging couples to participate in the training, the lack of such an incentive is a concern for the sustainability of activism, and should be monitored.

Delays and changes in priorities for the roll-out of Inshuti z’Umuryango (a national system, rather than a discrete donor programme) has meant that it is at a different stage of implementation to Indashyikirwa. The entire cadre of 29,674 Izu have received ‘pre-service’ training nationally, but the ‘operationalisation’ – meaning that Izu are undertaking their responsibilities, and have received ‘in-service’ training and resources - will be rolled out in a phased approach. 45 sectors across 9 districts are currently operational and providing lesson learning to inform the operationalisation strategy for the next phases. Coverage of all sectors across the current 9 districts will be complete by end-2017, with the remaining districts to be rolled out over the course of 2018. This has led to a discrepancy between milestones for indicators 1.3 and 1.4, and makes the milestone for 1.4 largely redundant. The milestones for 2018 should be adjusted to reflect reasonable expectations based on the new national approach. High turnover of Izu has been raised as a problem and potential cost, and should be monitored.

Izu, where operational, are strongly integrated with district and sector level authorities, institutions such as schools, and other existing mechanisms of community para-professionals, such as community health workers. Where operational, the district social worker (a cohort of 68 state professionals) is receiving reports from the Izu Sector Coordinators, evaluating Izu and supporting advocacy efforts on issues raised by Izu on behalf of families.

Due to its early stage of implementation, there is little data available on the impact of Izu’s operations in their communities. An initial 6 month assessment has taken place and DFIDR expects to receive the report by end of August 2017. Anecdotal evidence gathered during the AR field visit suggests the key issues identified by Izu in their communities are: school drop out, family arguments/neglect, and malnutrition. These issues are overwhelmingly linked to poverty and lack of parental education. Izu are also supporting families to establish their imihigo/performance contracts with village leaders. This has led to strong increases in two key areas of the standard contract – enrolment in Mutuelle de Sante (the national health insurance scheme) and keeping children in school. Children self-exclude due to poverty and do not attend school if/when they are unable to access a clean uniform or the materials needed for lessons. These children instead engage in labour, and are likely to leave home to avoid being found by authorities. As many children in Rwanda are first-generation learners (where their parents have little or no education), Izu are working with parents to reinforce the importance of children completing their education.
[note] Anecdotally, the following are standard Family Imihigo targets: 1. Enrolment in Mutuelle de Sante (National Health Insurance); 2. Children in school; 3. Keeping the home clean 4. A western-style bed (with mattress) in the home; 5. Proper toilet in the home; 6. Proper kitchen in the home and kitchen garden; 7. Rainwater harvesting system in place; 8. Family planning uptake; 9. ‘Support or report’ neighbourhood issues; 10. Treat every child as your own; 11. Civic participation eg. Umuganda

The demands on Izu time to properly support the school/local authorities are high and generally perceived to be too much for volunteers. UNICEF and NCC are aware of this issue and working to mitigate it, in part through providing further clarity to all actors on the roles of Izu. All actors involved in the system – from school leaders and local authorities to Izu themselves, need further capacity building to ensure the system works as designed.

Recommendations
DFIDR, UNICEF and NCC to explore the capacity building needs of the many actors involved in the Izu system – from school leaders and local authorities to Izu themselves - to ensure the system works as designed. (Led by UNICEF, by December 2017)

DFIDR to follow up with UNICEF to better understand the direct links between Izu and children, and the role of Izu in explicitly preventing sexual violence against children. (Led by DFIDR, by December 2017)

UNICEF and NCC to consider the Management Information System (MIS) needs of NCC to manage the Child Protection system in the long term. (Led by UNICEF, by December 2017)

New milestones for 2018 will need to be agreed between DFID, UNICEF and NCC for indicators 1.3 and 1.4. (Led by DFIDR, by October 2017)

Output Title	Improved civil society coordination and partnerships; and increased responsibility of Government of Rwanda (GoR) in the GBV prevention and response space at national and local levels
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes Reduced

Indicator(s)	Milestones	Progress
2.1 Opinion Leaders and Local Authorities engage, participate in and support GBV prevention messaging and activities at sector level	600 OL and Local Authorities continue to receive and act upon referred cases by WSFs, promote and support an enabling environment for community outreach and activism activities, and improve functionality of GBV prevention platforms	Achieved: / 1. After OL training in Feb 2017, leader cohorts have developed activism plans with commitments / 2. 597 OL received refresher training in May 2017. / 3. An additional 589 village leaders (521 men, 68 women) recieved 3-day training in all 14 sectors in March 2017 to engage them in supporting community activism and WS activities. This was identified following the intial OL training as necessary to support an enabling environment, and was delivered by CARE’s own funds. / This indicator will in future be supported by evidence for output 3.4. Examples of OL (and WSF) advocacy are noted below, and must be more systematically captured in future.
2.2 Number of sector level Imihigo GBV prevention and response indicators that are reviewed, quality assured and monitored by RWN and Community members, disaggregated by sector.	i) Advocacy Action Plan with targets based on review of Imihigo performance contract agreed. / ii) GBV activity reports from Imihigo contracts reviewed against action plan. / iii) WSFs engage in advocacy actions in response to issues raised in sector-level quarterly meetings.	Achieved: / i) An advocacy plan with targets based on review of Imihigo was developed and has been received by DFIDR. / ii) GBV activity reports were not reviewed as access was restricted, new strategies are being explored to address this. / iii) WSF and field officers have facilitated 2 meetings in each of the 7 districts with district authorities and stakeholders to 1) review GBV commitments in Imihigo perfomance contracts 2016/17; and 2) discuss GBV issues raised from the community.
2.3 Number of information sharing and lesson learning interactions between CSOs and GOR at different levels on violence against women and children	Action plan on sharing and lesson learning interractions between CSOs and GOR on GBV issues in place	Achieved: A CSO network action plan was developed by CARE and Pro-femmes and has been received by DFID.

Key Points

Regular turnover in OL has been identified as a challenge – particularly within local authorities. Newly elected or appointed officials take time and training to learn about the programme and become OL themselves, engaging in activism and/or advocacy within their sphere. Refresher training for OL is one mechanism through which RWN are attempting to address this.

The RWN Advocacy plan for 2017 includes a range of issues emerging directly from WS, ranging from possible low-level corruption to the inclusion of GBV Imihigo targets at sector and district level. Following the recent logframe changes, stories of advocacy success have emerged but should be collected more systematically to better report against indicators 2.1 and 2.2 in the final year of the programme. For example, in Rurembo sector (Nyabihu district, Western province), OL led a review of the bylaws of Ingobyi z’Abahetsi associations (ambulance/stretcher service), which led to the removal of the fine of 20,000 Rwandan Francs which is charged for all cases of violence, in cases of GBV. In Kanamu sector (Rubavu district, Western province), OL led discussions with village leaders who had been seeking financial contributions (in some cases up to 10,000 Rwandan Francs) from victims of GBV before taking on their case. WSF are reporting that the practice has now stopped.

The role of OL is considered critical to expanding the reach of the programme beyond direct beneficiaries. Consideration should be given to how national level OL could be engaged (for the final year, follow up or ‘Phase II’ programme, or independently of the programme) to strengthen the anti-GBV movement and scale up impact.

A CSO Network Action plan was developed, led by Profemme and CARE, for the period March – June 2017. The plan focused on advocacy around International Women’s Day and GBV Imihigo targets. Another plan will need to be developed to follow up. The network, which meets quarterly, is still in a nascent stage and may need additional support to grow in ambition and influence.

The national VAC Network (including Ministry of Health and NCC) national prevalence survey of violence against children and youth aged 13-24 is to be validated by GoR by mid-2017. The report will inform major policy and programming interventions to prevent and respond to VAC, including those with disabilities.

Imihigo (performance contracts) were extended to household level in 2016, with possible repercussions – both positive and negative – for GBV. A better understanding of how household targets are decided, monitored, and held to account is needed. However anecdotal indications of ‘standard targets’ (as listed in footnote 11, page 10) have not yet raised significant concern.
[note] Examples of possible positive repercussions could be where targets are used to incentivise gender-equal behaviour within the household. Possible negative repercussions could arise if targets incentivise families (particularly women and children) to remain in abusive situations or reinforce gender-unequal norms.

As highlighted in the previous AR, efforts to ensure PAC meetings are meaningful and prioritised are still needed to support coordination and mitigate risks. As the programme nears its close, the PAC is a key forum through which to focus on sustainability, as well as maintain interest in the forthcoming impact evaluation.

Recommendations

RWN to more systematically collect/analyse/share evidence of policy and/or practice change by local authorities as a result of activism. (Led by RWN, by December 2017)

RWN to lead consideration of how national-level OL could be engaged (for the final year, follow up or ‘Phase II’ programme, or independently of the programme) to strengthen the anti-GBV movement and scale up impact. (Led by RWN, by December 2017)

Output Title	Women's Spaces are established and provide information and support to community members and victims of GBV
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	25
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes Increased

Indicator(s)	Milestones	Progress
3.1 Establishment of functional and sustainable Women's Spaces in target sectors	14 WS sustainability plans developed and approved in all 14 Sectors.	Partially achieved: Sustainability options for the 14 WS are being mapped from which a plan will be developed by end of August.
3.2 Number of Women's Space Facilitators receiving training and ongoing support	300 WSFs continue to be active in their work and receive ongoing support and refresher training	Achieved: 300 WSFs received refresher training and continue in their roles. Training topics included (i) basic facilitation skills (ii) reporting skills & (iii) communication skills. Monthly planning meetings are held to support WSFs in their day to day work at the spaces.
3.3 New cases received in the Women's Spaces seeking GBV counselling or support; and use of Women’s Spaces to engage with community members and indirect beneficiaries, (disaggregating by disability, age and location)	i) 800 new cases received seeking GBV counselling or support / ii)9,870 incidents of people engaging in WS	Exceeded: / (i) Indicator added in May 2017, data to be collected and reported at the end of this quarter. (ii) 107,079 incidents reported. These include cases received, people attending the spaces, and number of people reached by WSFs through community outreach. The vast difference between the milestone and result is because the milestone did not account for number of people engaged through outreach activities. Clarification on how to calculate this indicator will be set out by October 2017.
3.4 Proportion of counselling/ support cases referred by the Women's Spaces and receiving further support and Women’s Space Facilitator follow up; by: / # of referred cases / # of completed interventions	200 counselling and support cases referred to receive further support and follow up.	Indicator added in May 2017, data to be collected and reported at the end of this quarter.

Key Points

At the WS visited, economic and emotional violence are most reported (a trend widely observed). Only two cases of sexual violence were reported in the past year – an increase from zero. Anecdotally, economic and emotional violence reporting provides an entry point to discuss sexual and physical violence (which remain more taboo and less likely to be reported). One beneficiary told us that she only reported economic violence to the WS but was experiencing all types of violence, including frequent marital rape - and received the support she needed from the WS. A man also recounted that he used to rape his wife, but following training, both are happy with their sexual life. There is a strong sense that the increased awareness of rights and types of violence within the community is acting as a deterrant for perpetrators.

The sustainability of WS remains a priority. CARE and RWN are supporting individual WS to pursue relatively small-scale income-generating opportunities – such as the purchase and resale of stoves and sanitary pads. Whether these will prove sufficient and long-term sustainability approaches remains to be seen. CARE is also exploring a pilot to turn WS into social enterprises, seeking £500,000 GBP to support a pilot. The sustainability of WS is clearly concerning for WSF – those we spoke to discussed the need to purchase land and build a new house to home the WS.

Village outreach has proven to be a critical factor in the success of the WS. It is an important mechanism through which to ensure that the most marginalised are not left behind. Distance/travel costs tend to prevent older people and people with disabilities attending the space, while single mothers told us they had not attended the space before as they thought it was ‘only for couples’. Specific outreach to young people is also needed to engage them in WS and youth-specific activities. Some OL expressed concern that young women perceive the WS as places for ‘mothers and older women.’ As a result, young women and adolescents may not have safe spaces to positively engage on GBV and other issues. CA are also not engaging in the WS as systematically as expected, and outreach/facilitated coordination between CA and the WSF is needed to bridge this gap.

The next quarterly report must update indicators which do not yet have data against them (3.3 i, 3.4), ensure the disaggregation of data (3.3, 3.4) and distinguish between total incidents and cases received in WS (3.3). New milestones for 2018 will need to be agreed between DFIDR and the consortium for # of incidents (3.3 ii), given the degree to which this has been exceeded.

WS are coordinating well with existing structures at multiple levels. Village leaders send GBV cases to the nearest WS, and follow up to learn the outcomes. District officials regularly visit WS, as do sector, cell and village leaders. OL and WSF meet quarterly. These interactions are perceived to be supportive and friendly, rather than over-bearing.

WSF identified additional support needs, including training on bookkeeping (for sustainability activities) and increased financial support for phone calls and transport. They also raised that their psycho-social support meetings are too infrequent (currently monthly).

Recommendations

Further effort must go into ensuring the inclusion of participants and beneficiaries with disabilities, and tracking reach to the most marginalised, particularly women with disabilities, including through more systematic disaggregation of data. This includes providing the total number of OL with disabilities. (Led by CARE and UNICEF, by next quarterly report)

RWN to lead consideration of whether further support to WSFs (including training on bookkeeping and additional support for phone and transport costs) is necessary and/or feasible. This should include the development of a mechanism to track trends and support needs regarding psycho-social support. (Led by RWN, by December 2017)

All consortium partners to discuss possible approaches to strengthen or systematise targeted outreach to vulnerable/key groups such as people with disabilities and youth, to engage them in WS/CA activities. This should include increased outreach/facilitated coordination between CAs and the WSFs. (Led by CARE, by December 2017)

The next quarterly report must update on those indicators which did not yet have data against them for this AR (3.3 i, 3.4), ensure the disaggregation of the necessary data (3.3, 3.4) and distinguish between total incidents and cases received in WS (3.3). (Led by CARE, by October 2017)

New milestones for 2018 will need to be agreed between DFID and the consortium for # of incidents (3.3 ii), given the degree to which this has been exceeded. (Led by DFIDR, by October 2017)

Output Title	Improved evidence base on ‘what works’ to prevent GBV in Rwanda
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	20
Risk revised since last AR?		Yes, increased	Impact weighting % revised since last AR?	Yes, increased

Indicator(s)	Milestones	Progress
4.1 Independent impact evaluation for DFIDR GBV programme delivers high quality research findings	Operations research feeding regular findings and recommendations to implementing partners and DFIDR	Achieved: WW has completed midline qualitative interviews with couples, OL, and RWAMREC/RWN staff members; baseline interviews and observations with CAs. Findings and recommendations from this ongoing process evaluation have been regularly considered through workshops with implementing partners, resulting in changes including suggestions on how to address challenges and improve the programme. Early qualitative findings have also been used to inform community activism development and messaging. Quantitative baseline findings were considered with partners in August 2016 as planned for Milestone 2.
4.2 Evidence from impact evaluation is disseminated to relevant policy, programme and academic stakeholders in Rwanda	Key findings from baseline study and operations research disseminated to policy, programme, sector leadership and academic stakeholders	Partially achieved: Baseline data has not been published/shared due to GoR sensitivities around publishing high IPV figures (as per recommendations from MIGEPROF). Paper drawing on the baseline qualitative findings on household decision-making and financial provision has been submitted for publication (draft was shared with implementing partners.) Research Uptake and Stakeholder Engagement strategies are in place.

Key Points

The midline couples cohort data collection was completed in November 2016 with 1628 treatment and 1637 control couples (97.2% retention rate from baseline).

The WW global programme (including the team responsible for the Rwanda evaluation) is seeking an extension – either cost or no cost. In Rwanda, this will specifically enable full analysis (and possible rescheduling) of the endline, due to a one year delay during inception. The decision is pending with DFID UK, and expected to be known by Dec 2017.

WW have not yet published Rwanda’s baseline quantitative findings, as per recommendations from MIGEPROF. Due to the targeting of high-prevalence GBV areas in the programme design, baseline GBV prevalence findings are significantly higher than national DHS data. An agreement must be reached urgently with GoR for baseline data to be published, to avoid compromising the impact evaluation overall, and the broader WW programme. Failure to publish would constitute a marked drop in VfM for DFID which may negatively impact the viability of a follow-up or ‘Phase II’. The inability to publish, and therefore achieved planned dissemination milestones, is outside of the immediate control of WW, and the bulk of work associated with this output (indicator 4.1) has been achieved. However, the output has scored a B and we have raised the risk rating to Major to reflect the now significant potential for the output to not be achieved overall.

Over the past year, the WW team has made considerable effort to share and publish qualitative and process-related evidence, including an article in the Journal of Social Sciences Special Edition from the Global Conference of Women and Girls, co-authored by Rwanda Women’s Network; ‘A process review of the Indashyikirwa couple’s curriculum to prevent Intimate Partner Violence and support equitable, healthy relationships in Rwanda.’ In addition, a paper co-authored by a CARE member of the programme team which assesses the shifting perceptions of consequences of IPV among couples and OL has been accepted to a Special Edition Journal on Costs and Consequences of IPV in sub-Saharan Africa for Journal of Interpersonal Violence.

Two studies in support of the evaluation - on disability and the costs of the model – are currently pending ethical clearance. Once this is received, a timeframe will be developed. Interviews are likely to be conducted during the next rounds of quantitative assessment (November 2017).

There is enormous interest in the findings of the impact evaluation and the WW team have faced increasing pressure to share emerging evidence. The team has agreed to accommodate these requests where possible – including through short synthesis briefs, learning reports for the implementing partners, and hosting workshops with implementing partners to review the emerging findings - but have highlighted restrictions of the Randomised Control Trial protocol on interim data analysis. Communicating more information about what can and can’t be shared, and the timeline of analysis at the next PAC meeting may assist in managing expectations.

The WB--funded, MIGEPROF-implemented GLSGBV programme also plans to undertake an impact evaluation. Both DFIDR and WW have worked alongside the WB to ensure the two evaluations do not overlap. The evaluations will have different protocols and produce largely incomparable data. Due to similarities between the programmes there is inevitable interest from policy makers to view this as a learning opportunity. All partners should consider where learning opportunities between the two evaluations may be possible, and work to establish clarity and a shared understanding about the limitations of such opportunities.

Recommendations

Relevant partners to work collaboratively to both mitigate risks and capture opportunities arising from the GLSGBV programme. This includes addressing branding issues, considering where learning opportunities may be possible, and/or working to establish clarity and a shared understanding about the limitations of such opportunities where needed (including through commissioning explanatory work). (Led by DFIDR, ongoing)

DFID to explore opportunities for additional evaluations to capture the sustainability of social norm change (beyond the life of the current WW programme). (Led by DFIDR, by August 2018)

WW team to communicate more information about what evidence can, and can’t be shared, and when, including the remaining timeline of the evaluation at the next PAC meeting. (WW in December 2017 PAC meeting)

DFIDR and WW to expedite conversations with MIGEPROF (and other GoR stakeholders as necessary) to reach an agreement for baseline data to be published. (Led by WW by December 2017)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key drivers for Indashyikirwa are staff costs and operational expenses within the consortium to deliver and provide ongoing support for programme activities, accounting for 26% of the budget. Programme activities (7% of the budget) include:
- Delivery of the couples curriculum (5 months training)
- Training of OL and CA
- Equipping and renting the WS and coordinating among WSF
- Development of curriculums and modules for couples/OL, WSF and adaptation of the SASA material (this excludes the training of staff on those curriculums)

The remaining budget is spent on information, education and communication materials with GBV prevention messaging for the WS, CA, OL and village leaders, which guide community level dialogues and meetings. Training costs for the groups mentioned above, including venue, materials and supplies also use up the budget, as well as rental, equipment and supplies costs for the WS, transport costs for WSF, CAs and OLs in their monthly activities at village and sector levels, as well as coordinating and hosting stakeholder quarterly engagement meetings. The programme also spends on M&E including visits to each of the 14 sectors by RWN and RWAMREC field officers, to oversee the effective implementation of activities.

The key cost drivers of Inshuti z’Umuryango are the development of the curriculum and training cost for child protection volunteers. UNICEF has an acceptable 8% management fee.

VfM performance compared to the original VfM proposition in the business case
Interventions that prevent VAWG can be seen to save money for the public sector, for example in terms of reduction in healthcare costs. Prevention may also be seen to have an impact on economic growth (GDP) by improving educational outcomes and women’s participation in the workforce. This is anecdotally reinforced by beneficiary testimonies, as noted on pages 2 and 7. However, interventions to address VAWG often struggle to robustly calculate quantitative indicators of VfM.

The 2016 AR considered that set-up/implementation cost per sector for Indashyikirwa (i.e. the cost of operations only, excluding the development costs of materials) is a better unit of measurement for VfM than unit cost per participant. Set up cost per sector is the minimum unit of division in the programme design to inform potential future scale up. A rough estimate of the average cost per sector is £14,000 to reach approximately 4050 beneficiaries (noting that not all cells per sector are necessarily covered).

Alongside the unique evidence emerging from Component 3 of WW (on the economic and social costs of violence), a full costing and economic evaluation to better understand the VfM of the Indashyikirwa intervention in Rwanda will be conducted by health economists working with the London School of Hygiene and Tropical Medicine (LSHTM) as part of WW. The researchers conducted a scoping visit and developed a research plan spanning three countries which has been submitted for ethical clearance to the Rwanda National Ethics Committee, the South African Medical Research Council and LSHTM in London. Ethical clearance is expected by the end of August 2017; a timeframe will then be confirmed. This evidence will help to fill a critical gap in the literature on VAWG – a summary of the evidence in 2014 found only eight studies in low- and middle-income countries with cost data or economic evaluations, only two of which looked at cost-effectiveness.

Assessment of whether the programme continues to represent value for money
The programme continues to deliver economy and efficiency, with salary structures and per diems benchmarked to similar programmes in Rwanda. VfM approaches being implemented by partners include:
- Minimising training costs by using a training of trainers approach;
- Partners such as CARE leveraging their internal funding streams and resources to increase results, for instance the additional training of OL and psycho-social training;
- Building the capacity of community groups and OL to support services and ensure sustainability;
- Rigorous M&E processes to improve efficiencies and identify opportunities for learning.

The capacity building plan under development to address audit findings will also strengthen downstream partner systems and processes which will help to improve the long-term efficiency and effectiveness of local NGOs. While the main economic justification for this type or programming is equity (particularly gender equity), in its final year, the programme will also ‘step-up’ to ensure greater inclusion of vulnerable individuals, including people with disabilities, through deliberate targeting approaches.

Influencing
The GBV space in Rwanda has been dominated by a responsive, rather than preventative approach. In the original Business Case, UK support was proposed to complement other donors’ programming on GBV in response/service delivery: the “One Stop Centres” (Netherlands and WB regional programme) and providing services to GBV survivors (United Nations Development Assistance Plan). The uptake of the Indashyikirwa model by MIGEPROF with funding from the WB is an indication that the preventative approach, led by DFID, is gaining more traction in Rwanda both among GoR and other donors.
[note] Republic of Rwanda (2013) One Stop Centres: Strategy for Scale up
[note] See UNDAP 2013 - 2018

Similarly, the recent allocation of core budget funds by the NCC to the Izu cadre is indicative of GoR’s ownership of the child protection system. DFIDR’s total investment of £432,000 (alongside other donors) has contributed to GoR setting aside nearly £150,000 for the June 2017 – July 2018 Budget Year.

VfM Risks
As highlighted throughout the AR, the possible failure to publish WW quantitative GBV prevalence data would constitute a marked drop in VfM for DFID which may negatively impact both the assessment of the Programme Completion Review and the viability of a follow-up or ‘Phase II’ programme.

In April 2017, the mid-term review of WW acknowledged that the consultants implementing the research in Rwanda (Laterite) - alongside contractors in other WW countries – have been significantly impacted by the effect of Brexit on exchange rates. WW has recognised that the impact is likely to affect project delivery, and work is underway to encourage flexibility and contingency planning.

DFIDR remains concerned about the VfM of the MIS for Indashyikirwa, including quality and reliability of analysis. Indashyikirwa partners are aware of the need to prove added value in the short term.

Quality of financial management
The accountable grant with CARE provides for advance quarterly payments based on narrative and financial reports (which account for expenditure of the preceding disbursement and a forecast for the following quarter). UNICEF receives two payments per year of £54,000 each, with narrative and financial reports provided with each request for the next disbursement.

The table below provides an outline of expenditure to date and the balance remaining for the last year of activities. The programme is largely on track for completion in August 2018, despite delays during inception which affected implementation timelines. Over the remaining year, the programme will expect to spend the final 28% of the budget, and close monitoring and accurate forecasting by all partners will be essential to ensure completion on time and budget.

Indashykirwa Component		Inshuti z'Umuryango Component
Total Accountable Grant value	£3,983,099
Total expenditure up to April 2017	£2,294,355
Forecast between May and July	£351,900	Total Agreement Value	£432,000
Estimated forecast for August	£117,300	Total Disbursement to date	£378,000
Funding available for year 4	£1,219,544	Funding available for year 4	£54,000

The 2016 AR recommended DFIDR commission an independent financial and systems audit of Indashyikirwa, including the link between CARE and RWAMREC/RWN. The audit, which covered September 2014 to January 2017, (completed in June 2017) was unqualified, but provided recommendations on strengthening control systems for RWN and RWAMREC. A detailed capacity building plan to address audit recommendations is under development, with CARE leading implementation. DFIDR will provide technical support as needed.

A suspicion of fraud was raised by CARE to DFID on May 16 2017. CARE’s own investigation, as well as the independent audit, both verified that no fraud had been commited, and the incident was closed at the end of June (CARE). At the time of writing, the case is at closure stage in DFID’s Counter Fraud Unit, pending some minor clarifications with partners.

Date of last narrative financial report	11 July 2017
Date of last audited annual statement	09 June 2017

E: RISK (½ page)

Overall risk rating: Moderate, with a solid development return
Overview of programme risk
The independent audit findings indicate weaknesses within RWAMREC and RWN’s organisational and structural controls, which could lead to potential inappropriate use of funds/resources. As a result fiduciary risk has increased from Moderate to Major (though the overall programme risk remains at Moderate). Below are some of the mitigating actions put in place to manage this risk:
- Capacity building plans to address audit recommendations for RWN and RWAMREC
- DFID will run a risk management workshop for partners by August 2017 that will strengthen their capacity to effectively manage, prevent and address risk
- Closer engagement between DFID and the partners to ensure ongoing risk and financial management support, the programme’s SMART Rule and Smart Guidance compliance, as well as monitoring progress against audit recommendations implementation

A new reputational risk due to the WB-funded GLSGBV programme has been added to the register (graded Possible/Moderate after mitigation). This covers a range of issues, including the public not being able to differentiate the branding between the Indashyikirwa programme and the GLSGBV programme. This is to be taken forward as part of Recommendation 5.

Outstanding actions from risk assessment
DFIDR will actively engage all relevant stakeholders to manage and mitigate the newly identified risks (above), and also closely monitor the implementation of the capacity building plans.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Both Indashyikirwa and Izu components of the programme experienced start up delays. However, most of the logframe milestones are now on track. A challenge remains between the different timelines of Indashyikirwa implementation and WW research. The WW programme planned end date is December 2018, while this programme is planned to end August 2018. The community endline is currently planned for completion by February 2018, but would ideally take place August/September 2018. This leaves very limited time for WW to comprehensively analyse, receive approvals and disseminate findings by December 2018. WW has requested a (cost/no-cost) extension with ISD, for which a decision will be available in December 2017. If the extension is not approved, we face the risk that the WW researchers will not have enough time to analyse findings, receive the necessary approvals from MIGEPROF and Rwanda’s National Institute for Statistics and Research (NISR), and disseminate the findings before their contract ends. This could compromise the quality of the final research outputs and their uptake by local and international policy makers, academia and stakeholders.

Performance of partnership (s)
A theme throughout the AR was the need for greater coordination. This includes within the Indashyikirwa consortium (for example, information sharing), between the components (and various partners) of the programme, as well as the various actors at district and sector levels (and below). The most recent PAC meeting was held on 12 July 2017, with all partners in attendance including MIGEPROF. Increased collaboration between the Indashyikirwa consortium, UNICEF and NCC was highlighted and promising ideas for ‘quick wins’ were identified. Arrangements are underway for a meeting between all implementing partners, led by NCC, by end of August.

Change in the SRO and programme manager roles in DFIDR resulted in some loss of momentum over the past year. In the final year, there is an opportunity for DFIDR to demonstrate greater leadership to support more proactive coordination and partnership across the GBV sector. There is also already strong interest from all partners about what will happen at the closure of the programme.

The 2016 AR recommended that CARE initiate quarterly leadership group meetings between CARE (Country Director and Vulnerable Women programme coordinator), RWAMREC’s Executive Secretary and RWN’s Director, in order to improve partnership-working at a strategic level. Implementation has been inconsistent and should be addressed.

Asset monitoring and control
CARE maintains a comprehensive register for the consortium’s programme-funded assets, and conducts quarterly spotchecks with RWN and RWAMREC. DFIDR conducted an annual spotcheck of CARE as part of the AR and made recommendations to the finance team to ensure that all downstream partner assets are barcoded or individually tagged to ensure easy identification. DFIDR was not informed when a laptop was stolen from RWN, and requested copies of all paperwork and police reports relating to the theft. DFIDR is taking action in accordance with our Assets Management Policy in response to this issue, including working with the DFID Counter Fraud Unit. DFIDR will re-circulate the Assets Management Policy to all partners to ensure adherence at all levels.

There are no assets procured for the Inshuti z’Umuryango component.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
This programme is not subject to the partnership principles assessment.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The WW evaluation has collected baseline and midline data, and will commence the endline data collection processes towards the end of 2017. The Indashyikirwa consortium has a comprehensive M&E plan closely linked to the log-frame and workplan activities, with all three partners playing an active role in monitoring progress. Field Officers and Supervisors from RWN and RWAMREC are responsible for most of the community/activity level monitoring in all participating sectors.
[note] Monitoring tools include: - Training attendance lists showing the session number, names of participants, age, gender, residence of participants; - Observation checklist of couple training session, capturing theme, activity analysis, facilitator skills & content analysis; - Community Activism Report forms capturing the name of the activist, type of activities, approximate number of people at each activity, date, location and duration of activity, the content/theme of the training, and activity analysis documenting successes, challenges & community feedback from each event; - An outcome tracking tool capturing perceptions of the community on knowledge, attitudes, skills and behavior; - An opinion leader commitment tracking tool that doubles as a planning and reporting tool, which tracks commitments, actions and progress against planned initiatives; - Women’s Spaces registers showing the number of people attending and the discussion forums. This information is disaggregated by sex, age and location; - Observation Checklists capturing session quality and facilitator skills; - Women Space Activity Tracking template; - Activity Reporting Template; - Women’s Safe Space case register showing new and follow-up cases and disaggregated by age, sex and disability; - Women’s Safe Space referral tracking forms, including tracking the number of forms completed and returned to the Space; - Report showing number of cases received, support rendered and whether case was completed.

An automated MIS to capture data, track activity progress and automatically generate analysis and reports has been developed for Indashyikirwa and is managed by CARE. Initiated in July 2016, the MIS is not yet fully operational and has faced several obstacles during development, including contractual delays. A new consultant will review and finalise the system by the end of August 2017. DFIDR remains concerned about the added value for money the MIS will provide, the quality and reliability of analysis, and will continue to monitor this closely, alongside CARE.

Partners should be capturing stories of change brought about by the programme. While a lot of data and academic products will be generated by WW, there is an opportunity for partners to capture stories from participants that are easier for the general population (and policy makers) to read. Testimonies that have already been documented are being translated from Kinyarwanda to English. It is also important to capture the lessons learned by the NGOs at both operational and technical levels in implementing a successful GBV prevention programme. Consortium partners and WW should discuss the various formats such evidence products could take. UNICEF, NCC and Save the Children (Inshuti z’Umuryango implementing agency) should also consider possible outputs as more impact data becomes available.

Consideration needs to be given to evidence overlaps and/or differences emerging from the WW impact evaluation and the WB-funded GLSGBV evaluation. MIGEPROF have expressed an interest in seeing learnings from the two studies, despite distinct differences and lack of comparability in the findings. It is in the interests of DFID and the WB to support policy-makers to draw relevant and accurate conclusions from the two programmes if and where possible, to support evidence-based GBV programming in future.

UNICEF and the NCC have adequate systems in place to track the number of Izu trained, and the number of national training facilitators and progress against logframe milestones. This component is not included in WW. A rapid evaluation of the initial 6 months of operationalisation of Izu across 9 districts has been completed by Save the Children, and will be shared with DFIDR by end August 2017.

Recommendations:
The 2016 AR recommended DFIDR revise the logframe (completed) and for DFIDR and the DFID VAWG team to explore options for evaluating whether behaviour change and social norm change are sustained beyond the current project and WW timeframe (ongoing).

DFIDR to consider commissioning articles or explanatory pieces that outline the differences between the WW impact evaluation and GLSGBV evaluation. These should cover differences in methodologies and difficulties in comparison of data, but draw policy recommendations where possible. Similarly, further clarification may also be needed on the differences between WW data and DHS data on GBV. (ongoing)

UNICEF and NCC to consider the MIS needs of NCC to manage the Child Protection system in the long term. (Led by UNICEF, by December 2017)

Monitoring progress throughout the review period
DFIDR monitoring activities include quarterly meetings with all partners, regular field visits, and quarterly and bi-annual reports from UNICEF and CARE. DFIDR has introduced a single reporting template for both Indashyikirwa and Izu activities. DFIDR will reinstate monthly meetings with CARE and UNICEF, and more regular engagement with MIGEPROF beyond the bi-annual PAC meetings.

This AR was completed by a Social Development Advisor (DESA) and Programme Manager from DFIDR. Both reviewers are new to the programme but will take on leadership of it. Interviews were conducted jointly and separately with the Indashyikirwa consortium (CARE, RWN and RWAMREC), WW, UNICEF, and NCC. The AR period also included a quarterly meeting, PAC meeting, the WW Annual Scientific Meeting, and field visits to Kayonza district (Murama sector) and Rwamagana district (Muyumbu sector). Meetings were held with CA, WSF, OL and sector authorities, Izu, and male and female beneficiaries of the programme.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process