Project Completion Review- Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	27 July - 14 August 2017

Title: Creating Opportunities for Poor and Excluded people (COPE)
Programme Code:	Start Date: August 2013	End Date: June 2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	AR 2014	AR 2015	AR 2016	PCR 2017
Programme Score	A+	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

Between August 2013 and June 2017, Creating Opportunities for Poor and Excluded People (COPE), implemented by the Manusher Jonno Foundation (MJF), mobilised the collective efforts of poor and marginalised people in Bangladesh to demand better services and advocate for their rights. MJF has developed a network of 117 non-governmental organisations (NGOs) and supported them to build their credibility and capacity to influence change.

The programme built citizens’ knowledge and capabilities to claim their rights and entitlements, improved the responsiveness of government officials and public services to better address the needs of the poor and marginalised, and bridged local level activism with MJF’s national-level advocacy to push forward pro-poor policy. This resulted in marginalised and vulnerable women, men, girls and boys in project areas having better access to public goods, resources and services. For example:

- 8,818 acres of government khas land[1] and water bodies were redistributed to 26,454 landless people
  [1] Khas land is government/public land intended for redistribution to people who depend on agriculture for a living but own no or less than 10 decimals of land. (All the land records of the government under Register No. 8 and Khatian No. 1 represent Khas land)
- 164,000 poor and excluded people (including people with disability, Dalits, destitute women, ethnic minorities) gained access to social safety net benefits totalling £7.87 million.
- 45,852 women survivors of violence have gained compensation, resolution or legal services and 15,867 child marriages were stopped following campaigns on gender norms and the harmful practices of early marriage and VAWG.
- 10,508 children from ethnic minority children were given opportunity to have primary education in their mother tongues in their schools.
- 11,964 working children have been withdrawn from hazardous work and enrolled into formal primary education and another 9,142 working children were reassigned to non-hazardous labour.
- Through securing decent working conditions 63,920 workers (including 46,270 garment workers and 17,650 shrimp workers) received the minimum wage and other legal entitlements.
- 10,099 potential migrants (including 1,922 women & 8,177 men) received training and support for safe and legal migration to their destination countries for work.
- MJF has supported partner NGOs to organise public hearings identifying over 1,667 health and agriculture service issues. 1421 of the issues raised were solved through successful negotiation with the respective agencies at the local level.
- The programme contributed to increased recognition of and responsiveness to marginalised communities within intervention areas. Beyond log frame results, 260,076 marginalised people benefitted from government run basic health care services, 83,657 received agriculture support and 140,580 poor people were provided with safe drinking water provision.

The programme demonstrates how the collective efforts of a professionalised network of NGOs can effectively influence pro-poor policy and its implementation, systematically including the voice of poor and minority communities into the legislative process. For example:
- Drawing on evidence generated by grassroots partners, MJF advocated for improved implementation of the Domestic Violence Act (2010), for compulsory marriage registration under the Hindu Marriage Registration Act and gender sensitive microfinance rules and regulations.
- MJF and partner NGOs assisted the government on the drafting of an Anti-Discrimination Act. They have also ensured the effective implementation of existing laws such as the Rights and Protection of Persons with Disability Act 2013 (RPPD Act), for example by formulating the Rules of RPPD Act 2013 and Neuro Development Disability Protection Trust Act 2013.
- Representing workers in the garment industries, MJF and its partners have supported the drafting of labour laws and regulations the outline employment rights and minimum wages for garment workers. As a result of their sustained efforts, in 2015 new labour rules and workers’ welfare foundation rules were enacted, and MJF partners are now following up the implementation of these rules at the factory level.
- MJF and its partner NGOs supported the Parliamentary Caucus to draft the Indigenous People’s Rights Act, which will cover the rights of the indigenous community (adivasis) of both the plains and the Chittagong Hill Tracts. MJF also is supporting the Human Rights Commission to drafting the law for a separate land commission for the Plain Land Adivasi community.

COPE moderately exceeded expectations across all intended outcomes, and scored A+ at both outcome and output level.

Financial Position

Original Programme Value	£24.75 million [out of which £24.2 million was given to MJF through an accountable grant and £550,000 remained with DFID for audit, monitoring, reviews and other technical assistance]
Extensions/ amendments	In December 2016, a cost and time extension was approved for a further £1.8million to extend over three months until March 2017. In March, a no-cost time extension for a further 3 months was approved. The programme ended on 30th June 2017.
Log-frame revisions (with dates)	2014: Log frame was revised to include clearer definitions for indicators and to capture qualitative changes / 2015: The target for outcome indicator 4.b on khas land was reduced from 9,000 acres to 6,000 acres. In addition output indicator 3.1 was reworded to reflect the kind of education provided (non-formal education changed to preparatory education)
Total programme spend	£26,235,174

Follow up actions required following closure

DFID’s Project Officer will write provide an asset disposal submission to the Head of Office regarding the by September 2017. Other actions relate to integrating the findings from this programme into the planning and initiation of DFID’s new programme with MJF

Summary of new recommendations for future work

[R1] MJF: To invest in and build the capacity of national-advocacy platforms to drive change at scale.
[R2] MJF: To increase internal investment in monitoring and evaluation, research, and knowledge management capabilities as well as increased collaborations with external research institutions.
The new programme should: (i) commission impact evaluations to test the efficacy of the specific interventions (particularly child labour, violence against women and youth which remain untested); (ii) undertake longitudinal research to examine the longer term impact of their work; (iii) invest in knowledge management to enable sharing of lessons on what works, and to demonstrate the relevance of the work to a wider range of private and non-traditional donors. (See output 2 and 3 and M&E section).
[R3] MJF: To establish an annual event for partners to bring together and identify cross-cutting, common advocacy goals and strategies across all MJF programme components and to inform the overall advocacy strategy.
[R4] MJF: To develop a strategy for addressing cross-cutting issues including violence against women and girls (VAWG), disability, access to justice, and use of social accountability tools.
[R5] MJF: To explore with partners how citizen and pressure groups have previously selected elites; to identify good practice examples and where lessons have been learnt; and to set out options for utilising elites that can minimise the risks that existing power structures are reinforced
[R6] MJF: To more systematically link to mechanisms that build household resilience to reduce household vulnerability to natural disasters or illness, which limits or reverses programme gains.
[R7] MJF: To generate data and evidence of its work, including through collaborations with external institutions, and improve its understanding of the changing funding landscape. MJF’s financial sustainability could be included as one of the outcomes of the new programme, with the proportion of funding from non-DFID sources as an outcome indicator.
[R8]: MJF: To design VAWG outcome and output indicators to capture prevention and response interventions – in line with DFID guidance.
[R9] MJF: To increase internal investment in research and evidence and collaborations with research institutions on VAWG – with particular attentions to VAWG prevention.
[R10] MJF: To assess and mitigate the risk of gender-based violence as a result of economic development interventions across MJF’s work. This should include monitoring VAWG, both as an unintended consequence and impact of interventions.
[R11] MJF and DFID: To identify evidence gaps on child labour and in-build testing and evaluation methods to build the evidence base.
[R12] MJF and DFID: To design child labour outcome and output indicators to capture prevention and response interventions – in line with guidance from DFID’s child labour team.
[R13]: MJF: The new programme should consider plans for measuring whether and how social audits and scorecards contribute to better-performing public services
[R14]: MJF: To (i) develop innovative indicators that can be used to calculate the value for money of empowerment, rights and advocacy programmes, and (ii) use the total cost transfer ratio to calculate the cost effectiveness of social protection and livelihoods projects.

Review process.

A review team of five DFID staff including a policy adviser (lead), economist, rural livelihoods adviser, social development adviser (project lead adviser) and deputy programme manager (project officer) held focus group discussions and interviews with MJF and NGO partner staff, civil society stakeholders, beneficiaries, citizen action groups, service providers, and government officials at a range of administrative levels over a period 27 July to 14 August 2017. This report builds from these observations, wider programme documentation and research.

Partner	Programme Component	Location
Polli Sree	Combatting Violence Against Women	Dinajpur
Eco-Social Development Organisation (ESDO)	Child Labour	Thakurgaon
RDRS	Governance Performance Monitoring	Rangpur
ASOD	Rights of the Marginalised – Landless	Rangpur
Action on Disability and Development (ADD)	Rights of the Marginalised – Disability	Rangpur

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme and what it has achieved

The UK government has provided a total of £26.24 million to the COPE programme, implemented by the Manusher Jonno Foundation (MJF). The programme ran between August 2013 and June 2017 and included a six months cost and no cost extension. Australia’s Department of Foreign Affairs and Trade (DFAT) provided a further AUD $6 million (now worth approximately £3.6 million) for 3 years between 2012 to 2015. COPE followed the UK-funded Rights and Governance Challenge Fund (RGCF) programme (2008-13), also implemented by MJF, in providing funding, technical and organisational support, and access to national policy influence for non-governmental organisations (NGOs) and community based organisations (CBOs).
.
The impact of the programme was for poor, marginalised and vulnerable people[2] to enjoy a better quality of life in an environment of democratic freedom and security. In order to achieve this, the programme engaged with people whose entitlements to basic resources and services are denied, whether due to negligence of service providers, lack of inclusive policies and programmes, lack of information about their rights and how to access them, or low social status. It supported 117 NGOs delivering five programmatic pillars: (i) Ensuring Rights of the Marginalized Population; (ii)Socioeconomic Development of Chittagong Hill Tracts; (iii) Combating Violence against Women; (iv) Protection of Working Children and Vulnerable Workers; and (v) Ensuring Responsiveness of Public Institutions. MJF’s role also encompassed capacity building for its partners and national level policy advocacy.
[2] Poor, marginalised and vulnerable people include Dalits, religious and ethnic minorities, sex-workers, fisher folk, working-children, workers and migrants, persons with disability, people with different sexual orientation, women.

The programme successfully adapted to a changing political and security context. For example the 2014 Annual Review noted how MJF and partners continued to deliver effectively and adaptively throughout the serious disruption caused by political violence including hartals, sieges and demonstrations. In 2014-2015, the programme’s logframe was revised to include clearer definitions for indicators and capture qualitative changes. And, in 2015, the programme reduced its target on the number of acres of additional khas land and water bodies leased to poor and marginalised people (outcome indicator 4b) and its total value (£) (4d). This amendment reflected emerging challenges with political instability and unavailability of local government representatives, limiting the ability to engage with government agencies and service providers. Despite the original set back, the programme has since exceeded these revised targets.

The programme consistently delivered at pace and at scale. In 2015 and 2016 DFID’s Annual Reviews reported all but two outcome milestones had been achieved. By the programme’s end in June 2017, it had exceeded all outcome and five out of six output indicators.

The poor and marginalised gained increased use of public services; increased their participation and representation at national and local political structures; and their legal rights and access to resources were realised. For example, a total of 164,000 poor and excluded people gained access to social safety net benefits worth £7.87 million; 45,852 women survivors of violence have gained compensation, resolution or legal services; 11,964 working children have been withdrawn from hazardous work and enrolled into formal primary education and another 9,142 working children were reassigned to non-hazardous labour.

To deliver such transformative changes, MJF and partners worked systematically to support and equip community groups with the skills, knowledge and know-how needed to claim rights. Local citizen groups used civic action tools including public hearings and score cards to gain access to services and monitor their quality. And where necessary, they launched their own advocacy campaigns to demand rights. The programme harnessed citizens’ ability to influence, providing leadership training and supporting some of the most marginalised to participate in local committees and political structures. Simultaneously, NGO partners and local citizen groups provided tailored training and helped overstretched government officials with specific tasks such as mapping landless households for khas land allocation. In this way, the programme also strengthened the capabilities of government officials and service providers to respond to the needs of the poor and marginalised.

The programme’s national advocacy efforts contributed to progressive shifts in policy, legislation and budget allocations for the poor and marginalised. One such example is the role MJF played in steering through the Rights to Information Act (RTI) (2009). Under the COPE programme, RTI has been effectively used by citizen groups, including by Disability Persons Organisations (DPOs) to request information about their entitlement to state-provided social protection. This has helped citizens to claim rights.

The programme’s achievements reflect both the results of proactive project-led initiatives, and changes brought about by government initiatives, some of which were influenced by MJF and partners’ policy-advocacy. For example MJF reports that the preparation of lists of eligible safety net recipients by project partners was bolstered by government drives to distribute Vulnerable Group Feeding (VGF) cards, and a 20% increase in the national budget allocation for safety nets. Together, this contributed to a total of 163,906 poor and marginalised people benefitting from government social safety net services worth £7.87 million during the programme.

The programme supported UK and global objectives. It contributed to DFID Bangladesh’s priority to improve equity, empower citizens and increase access to services and social protection. It supported the UK Aid Strategy’s objective to strengthen global peace, security and governance and to tackle extreme poverty and it contributed to the Sustainable Development Goals’ commitment to Leave No One Behind.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment: A+, moderately exceeded expectations.
All outcomes exceeded their targets.

MJF and partners have effectively supported marginalised and vulnerable women, men and children to gain better access to public goods, resources and services as well as supported structural and progressive changes in policy and law to address the rights of poor, marginalised and excluded people. The overall Theory of Change (TOC) for the programme was robust. The review team assessed that the original programme assumptions in line with the TOC are still valid and that outputs contributed to the programme’s outcome.

	Indicators	Target (Cumulative)	Achieved
1.a	Number of poor, marginalised, and vulnerable households who gained access to government safety net services.	138,000 / M: 96,600 F: 41,400	Moderately exceeded expectation 163,906 / M: 11,8010 F: 45,896
1.b	Total amount (in £million) of social safety net support received by programme beneficiaries	6.62	Moderately exceeded expectation 7.87
1.c	Number of boys and girls in project areas and communities who were supported & completed primary school.	53,000 / B:25970 G:27030	Moderately exceeded expectation 59,550 / B:29180 G:30370
2.a	Number of women victims of violence receiving compensation, resolution or legal services.	39,600	Moderately exceeded expectation 45,852
3.a	Number of marginalised men and women elected to local bodies (union parishad)	300 M:90 F:210	Met expectation 317 / M: 95 F: 222
4.a	Number of workers having annual pay increase through collective bargaining. (25% men 75% women.)	60,000 / M:18,500 F: 42,000	Met expectation 63,920 / M:18,710 F:45,210
4.b	Number of acres of additional khas land and water bodies leased to poor and marginalised people.	7,700	Moderately exceeded expectation 8,818
4.c	Number of women and men in programme areas having paid work and self-employment.	42,500 / M:15240 F:27260	Moderately exceeded expectation 49,290 / M:18540 F: 30,750
4.d	Total value (in million £) of government khas land and water bodies accessed by beneficiaries.	6.16	Exceeded expectation / 7.05
5.	Number of working children (aged 14-17) withdrawn and reassigned from non-hazardous work. 75% boys, 25% girls) a) Withdrawn / Reassigned	10,900 / B:7,500 G:3,400 / 8000B:5,800 G:2,200	Met expectation (110%) 11,964 B: 8,345 G: 3,619 / Moderately exceeded expectation 9,142 B: 6,905 G:2,237

Output Score and Description: A+, moderately exceeded expectations.

In line with the ToC, the below outputs are believed to have helped contribute to these outcome changes. In each output chapter, this PCR report further identifies lessons and factors that contributed to the change process.

Output	Overall Score	Impact Weighting
1. Marginalised people are organised to claim their rights and fight discrimination	A+	30%
2. Women’s groups equipped to challenge violence against women and girls	A+	20%
3. Rights of working children and vulnerable workers protected and strengthened	A+	20%
4. Capacity of citizens in project areas to monitor activities of government service delivery institutions	A+	10%
5. More sustainable civil society organisations	B	10%
6. Evidence generated, synthesised, and used to advocate for changes in various social development policies	A+	10%
Cumulative Score	A+	100%

Lessons and how these have been shared

1. The strong links between its grassroots community mobilisation and national policy-advocacy has been a key factor in MJF’s ability to affect change.

MJF has extensive national reach with a vast network of local citizen groups. Its ability to link local level activism and the voices of the poor and excluded to national policy-advocacy is MJF’s comparative advantage and has enabled it to scale up localised successes. MJF’s work influencing a national minimum wage for shrimp workers’ is one such example:

“We worked with local shrimp worker representatives and used the Right to Information Act to assess the proportion of workers’ receiving the existing minimum wage. This real-time information enabled us to apply pressure on policy-makers and factory inspectors to implement the correct wage. In three months, our shrimp workers confirmed a dramatic change. We also used this information to inform our advocacy for a new minimum wage for all shrimp workers”, MJF staff member.

In addition, many national forums – including government working groups and national campaigns - rely on MJF for real time information about local needs and how policies are being implemented on the ground. This is supported by evidence from DFID’s macro evaluation[3], which suggests MJF’s impact on public services was strengthened when part of a more strategic intervention in policy-making. To further strengthen these vertical linkages:
[3] http://itad.com/wp-content/uploads/2017/07/SummaryFindings_Briefing_2-v7.2-high-res.pdf

[R1]: MJF: To invest in and build the capacity of national-advocacy platforms to drive change at scale.
[R2]: MJF: To increase internal investment in monitoring and evaluation, research, and knowledge management capabilities as well as increased collaborations with external research institutions. Policy-advocacy should be informed by high-quality research and evidence. Furthermore, the effects of policy and programmatic interventions on outcomes should be more robustly measured (See outputs 2 & 3)

2. MJF’s ability to bring together disparate social justice movements has been an effective strategy for achieving advocacy results

In pursuing its principles of solidarity, MJF has often brought together disparate social justice movements to work towards common goals. This can be an effective strategy for exerting the pressure needed to influence change. At the national level, this has included MJF’s work drafting an Anti-Discrimination Act, which brings together marginalised groups. At the local level, the PCR team spoke to Disabled Persons’ Organisations (DPO) that had mobilised community based organisations in their district to form a human-chain around a police station refusing to respond to a reported case of rape against a disabled woman. This solidarity with wider rights-based groups was seen as critical in applying enough pressure to hold the police to account. To strengthen horizontal linkages, greater collaboration is needed between programme components:

[R3] MJF: To establish an annual event for partners to bring together and identify cross-cutting, common advocacy goals and strategies across all MJF programme components.
[R4] MJF: To develop a strategy for addressing cross-cutting issues including violence against women and girls (VAWG), disability, access to justice, and use of social accountability tools[4].
[4] Strategies for mainstreaming should include consideration for: effective monitoring and evaluation (including DFID’s guidance on Disaggregating Programme Data by Disability); staff development; and organisational structures for incentivising responsibility (e.g. use of focal points, staff appraisal objectives etc).

3. The use of both representative individuals and elites has been an important means to influence change. However, there are trade-offs that should be given greater consideration.

MJF partners have formed layers of local citizen groups. Citizen groups at the lowest village level are equipped with the knowledge and skills needed to claim rights. This is then complemented with pressure groups formed at each administrative level from Union to District levels; these groups are made up of a mixture of representative community members (like parents of child labourers) and local elites (including local government officials). The PCR team found that the balance of representative individuals and elites were an important factor in the increased responsiveness of local government. However, in some cases NGO partners raised concerns that they were using the same elites that sit on every local forum and public service committee and, therefore, could be reinforcing existing power structures. It remains unclear whether the NGO partners were selecting these group members or whether local communities were empowered to identify the individuals themselves. The selection of elites and associated trade-offs require further investigation from MJF:

[R5] MJF: To explore with partners how citizen and pressure groups have previously selected elites; to identify good practice examples and where lessons have been learnt; and to set out options for utilising elites that can minimise the risks that existing power structures are reinforced.

4. Communities empowered to own the agenda, are claiming rights across the full spectrum of social, economic and political empowerment.

MJF partners’ holistic, flexible approach enables the poor and marginalised to claims rights across a full spectrum of social, political and economic empowerment. The PCR team observed women’s groups originally intended to address VAWG, were in fact forming saving groups, supporting women to run for leadership positions, tackling domestic violence and campaigning for better drainage systems in their community. This autonomy in establishing their own priorities for rights-claiming was critical for its sustainability and perceived legitimacy in the community, and saw women claiming a broad spectrum of rights beyond VAWG. This reflects evidence that suggests social, economic and political empowerment is both mutually dependent and reinforcing. However, this approach to claiming rights across all three dimensions should be more systematically included in thematic theories of change. At present many NGO partners are linking citizen groups to existing economic activities they deliver through non-COPE funding; but this is not systematically captured or monitored by MJF.

[R6] MJF: To more systematically incorporate evidence-based strategies that build household resilience to reduce household vulnerability to natural disasters or illness, which limits or reverses programme gains. (See Output 1)

5. The funding landscape is changing; evidence is required to inform funding strategies.

MJF has not made progress to diversify its sources of funding during the lifetime of the programme. It continues to rely on DFID for over 80% of its funding. As such, financial sustainability remains a significant and urgent priority for the next phase. MJF needs to understand the changing funding climate and trends; this will support both MJF and wider civil society to form more strategic resource mobilisation strategies. It also needs to generate evidence on the effectiveness of its work in order to attract grant from donors, such as private foundations, that are increasingly using data to inform funding decisions.

[R7] MJF: To generate data and evidence of its work, including through collaborations with external institutions, and improve its understanding of the changing funding landscape. MJF’s financial sustainability could be included as one of the outcomes of the new programme, with the proportion of funding from non-DFID sources as an outcome indicator. (See Output 5)

These lessons are supported by and build upon a series of case studies and a synthesis paper produced in February 2016 to analyse the challenges and achievements of the RGCF and COPE programmes, with a focus on sharing lessons and identifying the factors that contributed to change.[5] The lessons have been shared with MJF and will be discussed further during the design of the new programme.
[5] Holland, Jeremy, and Molin, Rikke. 2016. “Case Studies of the DFID Rights and Governance Challenge Fund (RGCF)/ Creating Opportunities for the Poor (COPE) Programme Bangladesh: A synthesis paper.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Marginalised people are organised to claim their rights and fight discrimination
Output number per LF		01	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Achieved
1.1. Number of people supported by the project to practice their citizen rights and tradition	Total: 440,000 / M: 140,000 / F: 300,000	Moderately exceeded expectation. Total: 497,941 / M: 131,624; F: 366,317
1.2. Number of people from marginalised groups taking part in local government bodies and local forums (70% women, 30% men)	Total: 15,000 / M: 3,500 / F: 11,500	Substantially exceeded expectation. Total: 20,191 / M: 3,911; F:16,280
1.3. Number of children in project areas learning in mother tongue in their schools	Total: 6,000 / B:2,900 / G:3,100	Substantially exceeded expectation. Total: 10,508 / B:4,888; G:5,620
1.4. Number of children enrolled in primary schools	Total: 95,900 / B: 46,990 / G: 48,910	Met expectation. Total:102,989 / B: 50,465; G: 52,524
1.5. Number of men and women received skill development training and entrepreneur assistance	Total: 43,000 / M: 14,000 / F:29,000	Moderately exceeded expectation. Total: 55,054 / M: 17,502; F: 37,552
1.6 Number of poor and marginalised people in target communities in CHT who increase their monthly income by £9 through income generating activities	Total: 8,750 / M:3,600 / F:5,150	Substantially exceeded expectation. Total: 13,170 / M:6123; F:7,047

Key Points

Output exceeded expectation. Religious and outcaste minorities (Dalits and Harijans), plain land Adivasis, sex workers, disabled persons, char dwellers, landless people and fishing communities were supported to advocate their rights across 7 divisions and 44 districts.

“I became aware about land rights by joining the landless movement, supported by ASOD [an MJF partner]. This helped me to acquire 100 decimal of government khas land that I have used for cultivation. I established links with the local agricultural office where I learnt about improved production practices that helped me to increase my income. I can now afford more nutritious meals for my family and finally support my children’s education.” Abdus, a beneficiary of MJF in Gangachara, Rangpur.

The PCR identified a number of interconnecting factors that contributed to the effectiveness of poor, marginalised citizens in claiming their rights and influencing change. Firstly, the autonomy of citizen groups to identify their own priorities– beyond a narrow focus on programme outputs - helped to generate a sense of sustained ownership. And all local-level citizen groups visited during the PCR were continuing to meet regularly after the close of the programme. Secondly, citizen groups’ increased skills and professionalism contributed to their perceived legitimacy in the community. For example, the PCR team met with Disabled Persons’ Organisations (DPOs) that felt more valued by the community for helping others to access social safety nets; this had enabled them to generate funds from community members. Thirdly, with this community backing and with the skills needed to engage with and even support over-burdened officials, citizens seemingly achieved both credibility and influence:

“We reached out to our community leaders to help contact local government representatives. Once the government representatives heard that we are organised, and with a whole village behind us, they arranged an appointment to meet us and we organised a public hearing. … When they learned about the poor condition of the community clinic, they immediately allocated £750.” A Local Citizen Group member.

However, particularly in the case of the landless, the PCR team noted that households’ continued vulnerability to natural disasters or illness limited and in some cases reversed these programme gains.

While citizen groups largely worked collaboratively with local officials, in some instances, uninvited citizen action including campaigns and protest were perceived to be more effective tools for influencing service providers. One example was where a police officer refused to respond to a reported case of rape against a disabled woman. DPOs mobilised community based organisations to form a human chain around the police station. The collective pressure was viewed by DPO members as an effective strategy that resulted in the police taking action.

Government service providers were more effectively able to respond to the needs of the poor and marginalised. The increased dialogue between organised citizen groups and service providers was, in some cases, a catalyst for change: “Now I don’t have to deliver services individually…community groups have established links with us” Mahfuza Begum, Sub-Assistant Agriculture Officer, Rangpur Sadar.

The quality of capacity building training provided to officials, service providers and local committees (including participatory planning and budgeting training) contributed to increased responsiveness. For example, by activating school management committees and building their capacity, the programme was able to effectively increase enrolment of 102,000 marginalised children in government-run primary schools. Citizens’ improved leadership skills and their increased awareness of governance structures resulted in more than 20,000 marginalised people taking part in local government bodies and local forums (e.g. legal aid committees, disability allowance selection committees). However, further review is needed to understand whether these representatives from marginalised groups had sufficient say and influence in the decision making of these committees.

The balance of representative individuals and elites in the pressure groups was an important factor in the increased responsiveness of local government – particularly for issues with high vested interests such as khas land distribution. However, in some cases, NGO partners raised concerns that they were using the same elites that sit on every local forum and public service committee and, therefore, could be reinforcing existing power structures [see overarching lesson 3].

In the Chittagong Hill Tracks (CHT), the programme’s focus on service delivery was a necessary foundation for influencing local rights claiming and national policy-advocacy. MJF and its partners worked in a distinct way in the CHT, with a dedicated programme team, reflecting the unique needs of CHT and its political context. The programme has improved community livelihoods in CHT through income diversification and sustainable resource management. MJF and partners assisted communities to establish links with and access 61 government and community schools. As a result, 10,508 children received learning in their mother tongue in schools. MJF’s policy-advocacy also contributed to the government introducing pre-primary textbooks in five ethnic languages.

Recommendations for future programmes
[R6] MJF: To more systematically link to mechanisms that build household resilience to reduce household vulnerability to natural disasters or illness, which limits or reverses programme gains.

Output Title	Women's groups equipped to challenge violence against women and girls.
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Achieved
2.1. Number of dowry-less marriages in programme areas	13,500	Moderately exceeded expectation. 15,082
2.2. Number of women victims of violence in project areas supported to have access to medical and /or legal assistance.	51,000	Moderately exceeded expectation. 54,576
2.3. Number of early marriages (i.e. girls under 18 years) prevented in project areas. Programme works to prevent (outside beneficiary groups) and to actively stop people from marrying underage girls.	13,200	Moderately exceeded expectation. 15,867

Key Points

Output moderately exceeded expectation and exceeded its overarching outcome indicator, with 45,852 women survivors having received compensation, resolution and legal services.

The Combating Violence Against Women and Girls (CVAWG) programme builds from MJF’s experience over the last 12 years. Its Theory of Change takes a holistic, multidimensional approach to preventing and addressing VAWG – working in 29 districts across five strategic areas - participation, prevention, protection, provision and policy advocacy. This coalition of 21 partners and 12 sub-partners is the strongest across all MJF programme areas, with organisations formally meeting more regularly than others, every four months, to share lesson learning and best practice.

The sustained investment in women’s leadership at all levels has been a contributing factor to influencing the increased provision of public services and resources to address VAWG. MJF’s comparative advantage in preventing and addressing VAWG has been rooted in its systematic investment in women’s formal and informal participation. Women (particularly survivors of violence) have been developed into leaders within their communities and provided with training on women’s rights, leadership and mediation. These women mediate in family conflicts and are supported to take part in community and local government committees as well as elected positions of power: 33,881 women leaders have participated in salishes and other mediation forums as panel members, 436 women group leaders have been elected to participate in ongoing Union Parishad elections, and 108 women have been awarded by the government-issued “Jayita” awards. MJF’s investment in capacity building has supported a women-led alliance of organisations, elites and citizens mobilised and professionalised under a shared commitment to advance gender equality.

MJF has contributed to some improvements and greater coordination in government officials and service providers’ responsiveness to address VAWG (see indicator 2.b). Women’s groups and NGO partners were regularly engaging service providers to ensure provision and quality of services. For example, Polli Sree facilitate a monthly police coordination meeting to support police officers to address specific cases and plan action around early marriage, dowry harassment and domestic violence. The PCR team also met a Men’s Action Group consisting of police, teachers, government officials and agricultural workers, working with women’s groups to engage communities and service providers.

“Before, we could not imagine that citizens could play a role in government. But after joining with the programme, we learned how we could….we work together and it works. We have reduced child marriage and violence against women in our area.” Union Parishad Chairman, Patohat, Birampur, Dinajpur.

While the use of elites and male allies was viewed by NGO partners’ as an important means for influencing service providers, this all-male group were unable to confirm they would continue to meet. In line with the PCR’s overarching lesson 3, the next programme should consider how its’ balance of elites and representatives can be strengthened to achieve sustainable change.

MJF has utilised the collective efforts of its strong women-led alliance and its good relationship with government, to effectively influence policy and legislation that directly and indirectly links to VAWG. MJF has a long history of mobilising the voices of marginalised women to reform VAWG policy and legislation including the Domestic Violence Act (2010), it’s Rules (2013), and the Hindu Marriage Act (2012). During the COPE programme, MJF used its strong relationship with government to influence a National Action Plan to Prevent Violence against Women and Children (2013-2025) and a National Centre on Gender Based Violence. MJF’s approach includes a focus on direct and indirect policy required to address VAWG, with MJF’s draft land law including measures to reform gender inequitable land and inheritance law.

The effective use of high-quality research and evidence is now needed to inform and measure MJF’s approach to preventing VAWG. MJF have utilised a number of innovative strategies to prevent VAWG including its work piloting Model Villages or violence-free zones; the one-meal a day advocacy campaign; network of change agents; and increased focus on girls’ participation in sport. However, the current model does not measure or evaluate how prevention interventions are contributing to changes to attitude and behaviour. Furthermore there is an opportunity for the programme to more effectively utilise emerging evidence of what is effective, promising or ineffective action in prevention. Partners’ identified the biggest risks were now protecting hard-won gains from the influence of extremist ideologies and backsliding in legislation and policy. Across the broader portfolio, MJF staff identified the continuing problem of high rates of violence against garment workers.

Summary of responses to issues raised in previous annual reviews (where relevant)
AR 2016: To better ensure cross-learning between work on Rights of the Marginalised and Governance and in areas such as gender and disability [It was agreed this would be taken forward in the new programme]
AR 2016: To explore linkages with PKSF to promote the use of the revised Micro-Credit Regulatory Authority guidelines addressing VAW, in the context of a proposed new programme on Pathways to Prosperity for the Extreme Poor, and establishing referral for victims of VAW to access livelihood opportunities. [It was decided this would be taken forward in the new programme].
AR 2016: To ensure better coordination with DFID’s Access to Justice work with more substantial policy dialogue and activities supporting justice system reform [It was agreed Access to Justice would be incorporated within this programme component in the EPRB programme. However, this PCR has recommended Access to Justice is mainstreamed across programme components more broadly].
AR 2016: To introduce an emphasis on sensitising boys and men. [It was decided this would be a focus of the new programme, however this PCR recommends a stronger evidence-based focus on prevention more broadly. See below recommendation].

Recommendations for future programmes

[R8]: MJF: To design VAWG outcome and output indicators to capture prevention and response interventions – in line with DFID guidance.
[R9] MJF: To increase internal investment in research and evidence and collaborations with research institutions on VAWG – with particular attentions to VAWG prevention.
[R10] MJF: To assess and mitigate the risk of gender-based violence as a result of economic development interventions across MJF’s work. This should include monitoring VAWG, both as an unintended consequence and impact of interventions.

Output Title	Rights of working children and vulnerable workers protected and strengthened.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Achieved
3.1 Number of students Preparatory Education Session (PES) from child centres	Cumulative : 31,000 / Boys:22000 / Girls:9000	Moderately exceeded expectation. Total: 40569 / Boys:24033 / Girls: 16536
3.2 Number of workers in decent working conditions supported by the programme (30% men, 70% women)	Cumulative: 53000 / Men: 15000 / Women: 38000	Moderately exceeded expectation. Total: 65,468 / Men: 24598 / Women: 40870
3.3 Number of migrant workers in project areas receiving training and support for safe and legal migration. (70% men, 30% women)	Cumulative: 7600 / Men: 5600 / Women: 2000	Moderately exceeded expectation. Total: 10,099 / Men: 8177 / Women: 1922

Key Points

Output moderately exceeded expectation.

i) Child Protection and Development (CPD): This stream, which is aligned in line with the Child Labour Elimination Policy and the Labour law, consists of five pillars: prevention, rehabilitation, protection, development and sustainability.

Through its focus on rehabilitation, MJF has effectively withdrawn and reassigned children engaged in the most hazardous forms of child labour. MJF has worked first to remove the child from hazardous work and then provide preparatory education for more than 40,000 children. This is a year-long intervention that has fed children into the formal education system. While MJF’s ultimate aim is to eliminate child labour, under Bangladeshi law, children of 14 and over are allowed to work. Recognising that poverty is stopping families sending older children (14-17) to work, MJF has adopted a temporary arrangement to move children into non-hazardous work through reassignment or vocational apprenticeships.

MJF’s effort to mobilise local citizen groups has contributed to the increased responsiveness of local schools to rehabilitate child workers and monitor those at risk. The PCR team visited delivery partner ESDO which has established Child Rights’ Protection Committees and Forums at various administrative levels. At the community level, committees consist of parents, religious leaders, duty bearers and Union Parishad officials; these groups have provided practical support to increase schools’ capacity to survey and monitor out-of-school children. However it should be noted that there remains an evidence gap on the impact of its community awareness activities on child labour outcomes.

MJF has demonstrated considerable influence on national-level policy and legislation. The State Party Report on UNCRC in 2015 acknowledged MJF and its partners’ continued contribution to addressing child labour in Bangladesh, and a number of MJF’s recommendations from its alternative report were included in the concluding comments of the official session. The systematic use of high-quality research and evidence is now needed to inform and measure the effects of policy and programmatic interventions on child labour outcomes. For example, NGO partners have linked families’ of child labourers to a range of different income-generating activities and approaches to reduce household vulnerabilities. However, given that child labour is rooted in complex household decision-making, the new programme should now in-build testing to monitor its effects – including the effects on children’s unpaid labour and household chores – using a gender and age lens.

ii) Workers’ Rights including migration: This predominantly focuses on improving working conditions for those in 32 ready-made garment (RMG) and shrimp factories.

Workers have gained information about their rights, organised into associations and unions, and been supported in efforts to effectively negotiate for decent working conditions. Here decent working conditions are measured by receiving wages on time, use of leave entitlements and adherence to standard working hours. The programme also developed support groups including worker, elites and local government officials to bridge demand and supply side accountability. At the end of the programme, 12,455 workers in garment and shrimp sectors received more than BDT 60 million in maternity, termination, retrenchment, wage grading, and/or lay off benefits.

MJF has used its strong link to grassroots citizen action to influence national policy and legislation, and monitor its implementation. MJF has a long history in supporting government in drafting policy and legislation. During the COPE programme, MJF led the drafting of the Labour Law Rules from 2009 to 2015, which involved extensive (and often daily) consultation with NGO partners and grassroots level civil society organisations. Through these processes MJF has gained credibility and built strong working relationships with government stakeholders. It meets regularly with the government, ILO and NGOs to coordinate action for workers’ rights; it is an observing member of the tripartite committee; and is a member of the National Occupational Health and Safety Network.

MJF has made some progress in mainstreaming VAWG across its focus on workers’ rights, responding quickly to cases of violence. It has also worked to prevent such violence; addressing previously exploitative sub-letting rental housing arrangements and challenging attitudes and behaviours among middle management and supervisors. However all staff and partners noted violence against women garment workers continues to be a significant problem that will need to be addressed at scale through systematic monitoring and evaluation of interventions.

Potential migrant workers were provided with services such as information and training, visa checking, online registration, opening bank accounts, and complaints handling. Many of these services are provided by potential and returnee migrants supported to form community groups. At the higher levels, community-led Migration Protection Committees (including local elites and government officials) provide mediation services, file cases, connect citizens to legal aid, and use their position to influence the responsiveness of duty bearers. Following the enactment of the Overseas Employment and Migrants Welfare Act 2013, MJF continues to advocate for the effective implementation of that law and are included as members of the core technical group under the government’s “Standardisation of the Pre-departure Orientation Services (PDOS) Training Programme for Potential Migrants”.

MJF’s future priorities will shift under the new programme, with more targeted advocacy efforts in high-return areas and greater focus on ensuring implementation of existing policy: Specific priorities include: influencing for a national minimum wage and safety regulations for workers across sectors; addressing the migrant legislation implementation gap through training for law enforcement actors; targeted advocacy efforts to reduce migration costs; greater demand and supply side support to returning migrants; and mainstreaming VAWG prevention and equality for disabled people.

Summary of responses to issues raised in previous annual reviews (where relevant)
AR 2016: MJF’s possible linkages with DFID’s new PROKAS project include work addressing the risks of exploitation linked to labour migration will be taken forward under the next programme.
AR 2015: Following the review, NGO partners agreed to focus in the areas of garments and migration - and promote the rights of informal sector workers through research and advocacy only.

Recommendations for future programmes
[R11] MJF and DFID: To identify evidence gaps on child labour and in-build testing and evaluation methods to build the evidence base.
[R12] MJF and DFID: To design child labour outcome and output indicators to capture prevention and response interventions – in line with guidance from DFID’s child labour team.

Output Title	Capacity of citizens in project areas to monitor activities of government service delivery institutions
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Achievement
4.1 Number of people involved in project areas to monitor health, agricultural extension, education, social protection, nutrition services available to the poor.	22,300 / M:12,300 / F:10,000	Moderately exceeded expectation. Total: 27,056 / M:12,310 / F:14,746
4.2 Number of Government institutions monitored by partner organisations using social accountability tools: / a) Agricultural Extension Offices / b) Health Facilities / c) Social safety net programmes / d) Schools	a) Agricultural Extension Offices: 180 / b) Health Facilities: 360 / c) Social safety net programmes : 120 / d) Schools: 240	Significantly exceeded expectation. / a) Agricultural Extension Offices: 244 / b) Health Facilities: 475 / c) Social safety net programmes : 162 / d) Schools: 321

Key Points

The output moderately exceeded expectation. For this output, the indicators are linked to MJF’s governance programme on Responsive Public Institutions. The programme focuses on both demand and supply side interaction between citizens and local officials or public servants (e.g. doctors, teachers, agricultural extension workers) to make the latter more responsive, thereby addressing two critical issues; a) quality of participation and capacity of targeted communities to claim their rights and b) responsiveness of government mechanisms and processes which improve their accountability. Implementation of the Right to Information (RTI) Act (2009) and improving local legal services for the poor (particularly women) also constitute two important streams under the programme.

Citizens were effectively converted into active rights-claiming groups with the skills needed to monitor services available to the poor. For this, MJF’s nine partners worked with communities to mobilise citizens into active rights-claiming groups operating at four levels (Ward- Union-Sub-district-District). In total, during the course of the programme, these groups approached 1,202 local institutions (including education providers, health centers, and infrastructure services) to articulate their needs and demand services. After initial dialogue was built, performance was predominantly monitored through public hearings, leading to better performance of these institutions. Simultaneously, MJF systematically worked to improve the capacity of these service delivery institutions to respond to these demands. For example, of the 1,667 health and agriculture service issues raised through public hearings, 1421 of the issues were solved through successful negotiation with the respective agencies at the local level. Furthermore, 3192 elected officials and citizen forum members were trained on the rules and policies of local development and around social safety-net programmes. As a result of programme activities, 76 working Union Parishads have now developed participatory multi-year development plans.

Citizen forums operating across all administrative levels played an important bridging role between service providers and local communities. Under the separate Local Governance programme, partner organisations used social accountability tools such as social audits, scorecards, and public hearings to involve beneficiaries and stakeholder groups in monitoring public services, including provision (e.g. attendance of health staff and teachers and numbers of visits by extension officers) and quality. The PCR found that the public hearings were most systematically used by partners; they were seen by citizens, officials and service providers as an effective tool for building relationships and constructive dialogue, developing joint action plans and monitoring progress.

“After we conducted a local public hearing, my colleagues and I made an implementation Plan. We started disclosing information through Ward Shava and notice boards for the public. For instance, we provided £750 to the community clinic for renovation work and we will construct a boundary wall to make it secure as per public demand.” Chairman, Union Parishad, community health clinic committee

The Right to Information Act was systematically used by NGOs and citizens to gain information on their rights to services and resources. During the programme, MJF partner organisations helped to file a total of 6168 requests for information from the government. From these they received 2360 responses on a number of issues including khas land, primary school drop-out rates and social safety net allocations. Beneficiaries were supported to use this information to exert pressure on local authorities to ensure that more equitable services are provided (as in the case of safety net provisions) or more accurate information is made available.

MJF’s work bridging local justice mechanisms to district and Supreme Court level has been an important strategy for improving marginalised groups’ access to justice. Access to Justice was a standalone project intervention during the COPE programme covering 134 Unions, 45 Upazilas and 16 districts. At the macro policy-advocacy level, noticeable wins included the revision of the Legal Aid Services Act (2013) and MJF’s membership within the Supreme Court Legal Aid committee. At the local level, working through five partner NGOs, 90 union legal aid committees and 100 Village courts were (re)established – with MJF playing an important bridging role up to district and supreme court level. In these areas the utilization rate of the government’s legal aid fund has increased. For example, 5,300 women victims were linked with and received support from the Government legal aid fund. The new programme currently plans to embed access to justice within the VAWG intervention. While this is critical, the PCR found that for all marginalised groups (including disabled people, the landless, indigenous populations), addressing barriers to justice remains a core component of rights claiming and should be effectively mainstreamed across programme components.

Summary of responses to issues raised in previous annual reviews
AR 2016: MJF’s future Access to Justice programme should better coordinated with other programmes with more substantial policy dialogue and activities supporting justice system reform. [Instead of a separate programme component, the new EPRB programme highlighted that the Access to Justice would be incorporated within the VAWG component. However, this PCR has recommended that this is mainstreamed across other programme components more broadly.]

AR 2016: MJF should consider how RTI can integrate grievance redress at the local level. [It was agreed that RTI would be incorporated in the new programme.]

Recommendations for future programmes

[R13]: MJF: The new programme should consider plans for measuring whether and how social audits and scorecards contribute to better-performing public services.

Output Title	More sustainable civil society organisations
Output number per LF		5	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Achieved
5.1 Number of small partners receiving financial support other than from MJF	Cumulative: 12	Met expectation.14
5.2 Percentage of MJF budget coming from sources other than DFID	Annual: / 2017: 26% / 2016: 25% / 2015: 23% / 2014: 21%	Did not meet expectation. / 2017: 18% / 2016: 3% / 2015: 28% / 2014: 23%

Key Points

This output aimed to improve the financial sustainability of MJF and its smaller partners by encouraging it to diversify its funding sources. The output did not meet expectation, as MJF did not make sufficient progress to become more financially sustainable. However, the programme met the log frame target for MJF’s smaller partners receiving funds from other funding sources.

MJF works with a diverse range of partners; some that are very large and well established in their own right and others that are much smaller and more dependent on MJF both as a source of funding and for capacity building and guidance. To work with multiple partners, MJF has developed mainly a two pronged approach, working directly with some organisations as partners[6] and indirectly with smaller organisations as sub-partners through their direct partners. MJF also provides capacity development support to a group of small partners who applied to MJF for funding but failed to qualify due to their poor capacity.
[6] Most of the MJF’s larger and more established partners already receive funds from more than one source. They are not wholly dependent upon MJF sources of funding.

One of MJF’s goals is to build the capacity of these small partners to stand on their own feet. These smaller partners are local community based organisations and groups, which are predominantly based in rural areas. Most of these groups start with few formal structures and policies in place. They usually do not have the skills to run a formal organisation nor to apply for grants. MJF has clearly defined criteria for organisations to qualify for funding. Where organisations do not meet the requirements, MJF selects some of these small groups to provide handholding support to become more capable and formalised. The groups are selected based on the field of work, credibility among the local community and their ability to work constructively with the government. MJF provides training to the selected organisations on management, finance and writing funding proposals. Once they qualify for funding, MJF provides them with a small grant of around £5,000 for one year to implement a project. Independent reviews confirm MJF’s ability to help smaller partners become more capable by developing their management and financial systems.

All of MJF’s smaller partners reported securing funding from other sources since the inception of the programme. The review team met with representatives of 6 smaller partners. All of the partners spoke highly of the assistance that MJF provided them in improving their capability. Some of them stated that they are now able to apply for funds without MJF’s assistance. However, MJF does not systematically record the level of funding received by its partners and its change over time. It is, therefore, not possible to assess whether the smaller partners are making sustained progress towards reducing its financial dependence on MJF.

MJF has not made enough progress in diversifying its sources of funding during the programme period. DFID’s contribution to MJF’s budget remains about the same at the end of the programme as it did at the beginning. In the year that ended on March 2017, 18% of MJF’s funding was from sources other than DFID against a target of 26%. At the baseline in 2012, 20% of MJF’s funding was from outside DFID. The figure increased to 28% by March 2015, before falling to 3% in the following year. This was primarily due to AusAid’s project with MJF coming to an end. However, MJF managed to find five new donors in 2016-17, which helped to bring back the proportion of non-DFID funding close to the baseline level. MJF has received funds from Swedish International Development Cooperation Agency (SIDA), Australian Department for Foreign Affairs and Trade (DFAT, previously AusAid), Comic Relief, Global Community Engagement and Resilience Fund (GCERF) and the World Bank between August 2013 and June 2017. However, most of this funding has been of relatively short-term duration, which has not helped MJF to become more financially sustainable. The continued dependence on DFID for 82% of its funding[7] has meant that MJF goes through periods of severe financial uncertainty.
[7] This 82% of DFID funding covers both COPE programme and another DFID funded SGSP programme.

The new programme (Excluded People’s Rights) sets financial sustainability as of the main outcomes. MJF will invest more in research and evidence, which will help it attract funding from a range of sources including private foundations. It will also provide training and consultancy services to other organisations to generate revenue.

The 2016 annual review presented erroneous figures for output indicator 5.2 as MJF provided incorrect data and the review team did not verify the data provided. As a result, the last annual review reported MJF’s non-DFID funding in 2015-16 to be higher (20%) than was actually the case (3%). This review presents the corrected data for all review periods.

Summary of responses to issues raised in previous annual reviews (where relevant)
AR 2015: Following the 2015 AR, DFID commissioned a 4-member technical assistance team to support MJF’s strategic planning exercise in 2016. As an outcome of this exercise, a draft guideline was developed on the basis of which MJF is recommended to finalise its Strategic Plan during the new programme phase. This will be a guiding document for MJF’s future work.

Recommendations for future programmes
[R7] MJF: To generate data and evidence of its work, including through collaborations with external institutions, and improve its understanding of the changing funding landscape. MJF’s financial sustainability could be included as one of the outcomes of the new programme, with the proportion of funding from non-DFID sources as an outcome indicator.

Output Title	Evidence generated, synthesised, and used to advocate for changes in various social development policies
Output number per LF		6	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Achieved
Number of policy advocacy campaigns on rights and governance	4	Moderately exceeded expectation: 11

Key Points

Output moderately exceeded expectation.

MJF has a strong focus on bringing voices from the grassroots into government policy advocacy in order to realise the rights of marginalised and vulnerable people, with some effective results. This output was intended to assess how MJF’s role in managing COPE programme extended beyond fund management and in particular to reflect MJF’s upstream policy work but the indicator does not properly reflect the output statement. The statement refers to the collection and use of evidence to advocate for social change whereas the indicator mentions the number of policy advocacy campaigns that MJF has undertaken without any reference to evidence.

MJF’s comparative advantage is its ability to use its networks’ reach to bring the voices of the disadvantaged people into policy discussions with the government. It has developed substantial credibility and influence within the government, which it uses to advocate and realise the rights of marginalised and vulnerable communities. This is evident from the long list of laws and policies where MJF has been instrumental through its advocacy and activism as well as its collaboration with the government. It gives technical assistance to the government in drafting laws and provides feedback from its partner network. For example, special development fund allocations for disadvantaged groups such as Dalits followed after intensive advocacy by MJF and its partners. As a result, the allocation for the Dalit community in the national budget increased by 13% in 2014-15 compared to the previous year. Drawing on evidence generated by grassroots partners, MJF has advocated for compulsory registration under the Hindu Marriage Registration Act and gender sensitive microfinance rules and regulations.

MJF must strengthen is its use of research evidence to inform its work. Better data and evidence would help increase the credibility of MJF’s work and bolster its work in driving change. The need for high quality research and evidence is particularly crucial for an organisation like MJF, which works to change laws and policies that affect vulnerable groups. Changes in laws and national policies can have far-reaching unintended consequences. For example, a ban on child labour from formal sector firms can lead to more children working in hazardous work in informal businesses. Research can help minimise the potential for unintended consequences and help create awareness.

The business case for the Excluded People’s Rights in Bangladesh programme identifies the need for MJF to strengthen research capability.

The following table shows a sample of the policies/laws for which MJF and its partners have made contribution in terms of drafting, enactment and implementation.

Theme under COPE	Implementation	Enactment	Drafting
ROM	Rights & protection of Persons with Disability Act 2013 (RPPD Act)	Ministry of Social Welfare has been formulated Rules of RPPD Act 2013 / Neuro Development Disability Protection Trust Act 2013.	Anti-discrimination law
VAW	Domestic Violence (prevention and Protection) Act-2012 and rules 2013 / Hindu Marriage Registration Act-2012 and Rules 2013 / Gender Responsive and Assertiveness Micro Credit Policy 2015 ( USHA) / Writ petition to the High Court in 2015 on dissolution of marriage by Hindu women who wants to divorce.	Micro Credit Regulatory Authority adopted 7 recommendations in MRA rules, which MFI’s are now bound to follow. This is a result from National Caucus of Women’s Economic Empowerment	Women and children repression prevention act-2000(amendment 2003)- reviewed and recommendations submitted to MOWCA (Naripokkho)
Workers’ rights	Bangladesh Labour Rule 2015, / Worker Welfare Foundation Rule 2015, Domestic workers welfare policy 2015 and implementation of 5% increment in RMG and Shrimp workers / Migration Policy 2016	Bangladesh Labour Rule 2015, / Worker Welfare Foundation Rule 2015.	Domestic workers welfare and protection policy 2015. / Migration Policy (2016)
Monitoring of government service delivery institutions	RTI Act / New Agriculture Extension Policy (2006) / Local Governance Acts	Information Disclosure Policy guidelines and provision for government ministries and departments integrated in National Integrity Strategy	Advocacy with Information Commission for amendment of exemption list (section 7) of RTI Act
Local Governance	Decentralisation policy for enactment / Local Government Acts (UP, Upazila, City Corporation) for implementation	Campaign on ‘transfer of subjects to Upazila and Union Parishad’ cabinet division has issued a circular on 14 October 2015 instructing transferring salaries of all transferred employees to the Upazila Parishad.	Drafted the Democratic Decentralisation Policy for the country

Summary of responses to issues raised in previous annual reviews

AR 2014: It was suggested this indicator should be divided into three sub-indicators by measuring MJF’s contribution to the drafting of laws, the enactment of laws and the implementation of laws. The 2015 AR further recommended that the indicators will need accompanying narrative to provide evidence of MJF’s contribution. Although the indicator was not amended, the information under this output has been provided using these categories and shows that this categorisation allows MJF to better capture the range and extent of work being done under policy advocacy.

AR 2016: MJF has developed a draft advocacy strategy in response to the 2016 Annual Review recommendation. Further revision of this strategy paper is required in line with the new programme’s priority thematic areas.

Recommendations for future programmes

[R2] MJF: To increase internal investment in monitoring and evaluation, research, and knowledge management capabilities as well as increased collaborations with external research institutions.

## D: VALUE FOR MONEY& FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

MJF report that it did not face any upwards pressure on their major cost headings over the programme period. However, it estimates that it lost around BDT 80,000,000 (£800,000) due to depreciation of sterling. This led it to proportionately reduce the grants to partner NGOs. MJF states that this did not have a significant adverse impact on meeting the log frame targets.  MJF reports that it minimised the impact of the exchange rate losses by stopping salary increments for staff. The partners also reduced some front line staff to adjust to reduced level of funding.

VfM performance compared to the original VfM proposition in the business case

The programme did not have a value for money strategy or track any VfM indicators. VfM indicators were not included in the log frame. However, the programme collected data on the cost of running programme activities as well as estimated monetary benefits of some outcomes such as land redistribution and social safety nets. For example, the programme helped redistribute 8,818 acres of land to 26,454 landless people. MJF estimates that the value of land redistributed amounts to £264 per person. The business case stated that the value of land redistributed would amount to £167 per person. The land redistribution activities cost around £45 per beneficiary, which yields a benefit-cost ratio of 6:1. The programme helped 164,000 people get access to social safety net benefits totalling £7.87 million. This amounts to £48 per person on average. It cost the programme approximately £20 per person to run activities such as meetings to select safety net recipients, yielding a benefit-cost ratio of about around 2.4:1. The programme did not track the changes in income as a result of the livelihoods training or changes in social attitudes and/or behaviour due to the work on preventing VAWG and discrimination.

Assessment of whether the programme represented value for money

The programme collected limited quantitative data on the social and economic changes that it helped achieve. Some data are available for outcomes such as land redistribution and increasing access to social safety nets. In both of these cases, the estimates of costs and benefits suggest that value for money was achieved. The thematic case studies commissioned by DFID states that the programme achieved considerable gains in redistributing rights to the most marginalised and challenging accountability relationships across many sectors in a challenging political environment. The fact that the programme met or exceeded all of the output and outcome milestones also points to the success of the programme. However, in the absence of relevant data, it is difficult to make a definitive assessment of the extent to which the programme delivered value for money.

Value for money recommendations

[R14] The review team recommends that the new programme develops innovative indicators that can be used to calculate the value for money of empowerment, rights and advocacy programmes. It also recommends using the total cost transfer ratio to calculate the cost effectiveness of social protection and livelihoods projects. This is a measure of the average total cost needed to deliver £1 of benefits to households, which is used in many DFID social protection and livelihoods programmes.

Quality of financial management during programme

Financial management of grants

The MJF’s Finance and Admin department consists of 14 members of staff and uses an integrated financial management system. MJF have put in place effective processes and internal controls in its NGO selection process and grant management. Internal controls ensure: different MJF staff are assigned to review the application and carry out spot checks; the person who is made the financial appraisal is not the finance contact point; the finance contact person is rotated at intervals; the finance contact person will not have sole responsibility for partner NGOs in their home district; financial approval authority lies with the programme contact person and/or management according to the DOA.

The activity based financial reporting system enables MJF to track all expenditures against budget line. The team prepare a risk assessment of all partner NGOs using a score sheet. This is used to divide partners into four categories of risk. Any that fall under the high risk category are monitored more frequently and receive more extensive support.

MJF conducts regular and thorough monitoring of programmes and provide extensive feedback to partners. They visit partner organisations twice a year to review their books of accounts and status of implementation of previous recommendations. After each monitoring visit, a report is submitted to partners, where partner NGOs and then MJF management are required to comment. Implementation of agreed action is then followed up on during the subsequent visit.

In 2015, both MJF and DFID staff conducted a series of additional visits to partners to build awareness and capacity to adhere to DFID’s latest policy addressing fraud, risk management and corruption. MJF took strong action where it identified the misuse of funds or inadequate financial controls. One partnership was terminated due to misuse of funds; in doing so MJF followed its partnership termination policy and informed DFID Bangladesh who later consulted with DFID HQ’s Counter Fraud and Whistleblowing Unit. DFID is planning further financial training with MJF, including on how to identify potential fraud.

Partner NGOs receive financial management training and support through staff orientation and training. This is provided to three members of staff per organisation including their director, programme manager and finance manager.

Internal financial management

In 2014, DFID carried out a due diligence assessment (DDA) of MJF. The findings confirmed MJF had adequate programme and financial management systems in play especially in the area of organizational governance, controls over support to downstream partners, audit, recruitment and procurement of goods and services. Minor recommendations were made including upgrading monitoring processes to report against qualitative changes, which was addressed.

MJF’s last audit, conducted in December 2016, had no major observations. In previous annual reviews, DFID has noted MJF prepared appropriate action plans for audit observations. Previous observations typically included staff not being paid on time, advances not being adjusted promptly or individual instances where VAT had not been deducted from payments to suppliers on transactions where it should have been. After every three years, both Internal and External auditors are changed. DFID’s last independent audit was conducted in 2015; recommendations were taking forward by DFID and in discussions with MJF staff. MJF follow the International accounting Standard in its annual report presentation. The audited financial reports are uploaded in its official website.

In the new programme MJF will:
- Finalise a best practice guide on financial management – synthesising information and support for partners. This will be an online resource and public good available to partners and non-partners.
- Phase in online financial reporting for partner NGOs.

Date of last narrative financial report	July 2017
Date of last audited annual statement	December 2016

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall risk rating of this programme is moderate. The Lead Advisor and Programme Manager of the COPE programme carried out the 2016 Annual Review and as part of this set out risks, agreed mitigating actions, timescales and staff (both DFID and MJF) responsible for them. The PCR team was content that MJF regularly assessed risks to programme implementation and took a high quality approach to risk management to minimise impact. This is based on some of the following examples and factors:

Strong working relationships with Government: Through its collaborative support to government in drafting policy and legislation for the poor and marginalised, MJF has built good working relationships with a broad range of government stakeholders – including the NGO Affairs Bureau. MJF’s strong working relationship with government has enabled MJF’s partners to pursue uninvited civic action – including mass protests and action.

Strategic and politically astute support to NGO partners addressing high-return but high-risk issues of rights and governance: MJF’s local and national coalitions have helped to support frontline staff and community activists from any possible backlash from powerful groups or vested interests. This has been particularly apparent in the way in which MJF mobilised quickly and worked through its networks to protect and ensure the safety of activists working on high-risk areas of land and workers’ rights. Furthermore, DFID also have an ongoing dialogue with the government on how national NGO regulations could be modernised and made less cumbersome and better targeted.

Strong and robust systems in place for managing financial, fraud and corruption risks: As detailed in the previous section, MJF has strong financial management systems in place and demonstrates zero tolerance of the misuse of funds or inadequate financial controls.

Responds quickly and effectively as new risks are identified: In the 2015 Annual Review, DFID identified that data protection risks might arise from the personal data stored in MJF’s on-line M&E systems. MJF responded quickly, conducting a review of confidentiality and personal risk posed by this online data entry. Accordingly, it established security protocols and ensured all data was anonymised.

In the next programme – Excluded People’s Rights in Bangladesh – financial sustainability remains a significant risk to the future ability of the foundation to champion the rights of the poor and marginalised and to hold governments to account. The section on output 6 has suggested specific recommendations.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The COPE Programme was implemented between August 2013 and June 2017; this included a three months cost extension (Jan-March 2017) and another three months’ time extension (April-June 2017). The programme exceeded all output and outcome indicators within this revised and approved timetable.

Performance of partnership (s)
The PCR team observed that DFID and MJF had formed a strong partnership, with regular and high quality communication between teams. Furthermore, the relationships formed between MJF and its NGO partners are frequently identified as one of the programme’s greatest strengths. This was identified in a recent case study report which noted that MJF had formed relationships based on trust, day-to-day contact, and even stronger support for partners during periods of political crackdowns and backlash. MJF’s agile approach enables it to respond flexibly as partners identify emerging opportunities and challenges.

Asset disposal and value obtained by DFID
The DFID team carried out a physical spot check of the assets held at the MJF Office on 24 January 2017. The assets included: mobile phone, telephone set, desktop, laptop, car, motorcycle, bicycle, computers, furniture etc. Most of these items were carried forward from the previous RGCF programme. Some items were procured during the COPE programme period (2013-2017). MJF provided an inventory list to DFID which was updated in January 2017; all listed assets were found in order.

DFID’s Project Officer also visited offices of partner NGOs in three districts (e.g. Dinajpur, Rangpur and Saidpur) from 12-14 February 2017 and checked the assets in line with DFID guidance.

The new Business Case for the Excluded People’s Rights in Bangladesh programme has been approved and will be implemented over 5 years. After the completion of the spot check, DFID has recommended that MJF should prepare a comprehensive asset list, including descriptions of their condition. This will help DFID to make a decision on the asset requirements for the new programme.

G: CONDITIONALITY (½ page)

Partnership principles assessment

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

While MJF already has in place systems to ensure accurate and consistent reporting against output indicators, the 2015 independent M&E review, commissioned by DFID, recommended that MJF should be more consistent to gather evidence of its qualitative and transformative impact in future. To undertake manageable and incremental steps to improve the generation and management of evidence, the review proposed small adjustments to the organisational structure,[8] the introduction of evaluative peer reviews based on partners’ qualitative assessment scorecards, prioritisation of learning and communication and the introduction of regular impact assessments. These are proposed to contribute to enhance the ways in which MJF and its partners capture, aggregate and share the results of their work. For impact assessment, the following three activities were recommended by the M&E review:
[8] to strengthen its quantitative, qualitative monitoring system along with its internal M&E capacity

- Piloting of a peer review process in which partners come together to reflect on and challenge each other and their contribution to change.
- MJF to conduct a periodic longitudinal impact assessments[9] on the longer-term impact of advocacy gains on the lives of the poorest, including critical non-material dimensions of poverty such as dignity and (gendered) empowerment.
  [9] For this, it proposes MJF to subcontracts an independent local outfit with strong qualitative and participatory research skills.
- Commissioning of case studies, drawing on the outcome attribution and impact monitoring data across a range of 6 programmatic areas (VAWG, child labour, workers’ rights, land rights and RTI), on powerful change processes, including learning from failure. The objective is to document and understand change processes and how MJF and its partners have contributed to these.
The piloting of a partners’ peer review and the case study work both were completed that described MJF’s contribution to increased accountability and poverty reduction amongst the poorest and most marginal groups in Bangladesh. The case study work concluded that over its 12 years of intervention through RGCF[10]/COPE programme, MJF made considerable gains in redistributing rights to the most marginalised and challenging accountability relationships across many sectors and in a challenging political context. Lessons learned from the case studies were supported by a much wider evidence base drawn through a macro evaluation of DFID’s support[11] to social accountability initiatives. This DFID-wide evaluation found that supporting formal citizen engagement is necessary to achieve improved higher-level service delivery at scale and that social accountability can achieve improved services for marginalised groups.
[10] RGCF: Rights & Governance Challenge Fund
[11] DFID’s Empowerment & Accountability Macro Evaluation, 2016; This evaluation was carried out by Itad on behalf of e-Pact as part of the Macro Evaluation of the Strategic Vision for Girls and Women supported with UK Aid from DFID

The 2016 AR team was satisfied by the amount and quality of evidence and data collected as part of this case study and DFID’s macro-evaluation work that addressed key evaluation questions around the quality of the long-term relationships being built by partners with communities; the growth and achievements of multi-stakeholder coalitions and networks; the quality of interaction with the government at different levels; and the role of MJF as an active interlocutor between the micro and the macro, linking pro-poor policy level advocacy. In this context, the review concluded that an impact evaluation is not essential since the major aspects of evaluation have already been well captured and well documented.
Recommendation for future programmes
[See R2]: The new programme should commission impact evaluations to test the efficacy of the specific interventions. In particular, the work on child labour, violence against women and youth are untested. These interventions should be designed in a way that allows them to be evaluated. MJF can work with external research organisations to design and evaluate interventions. An external review of MJF’s monitoring and evaluation systems also recommended that MJF should undertake longitudinal research to examine the longer term impact of their work. It also recommended the programme should invest in knowledge management to enable sharing of lessons on what works, and to demonstrate the relevance of the work to a wider range of private and non-traditional donors.

Monitoring progress throughout the programme
MJF has a well-developed system of monitoring its partners’ activities and financial management. A DFID-commissioned 2015 independent M&E review completed a thorough assessment of MJF’s monitoring system and found that the organisation had developed a strong monitoring system with detailed quarterly reporting from partners. MJF invests time and effort to develop their partners’ capability and monitors them closely throughout the project implementation period. It takes remedial action to respond to partners’ poor performance, including by withholding payments. As notes above, it terminated one NGO partnership due to poor financial management after efforts to improve its financial management did not succeed.

As stated earlier, based on M&E review’s recommendation, MJF piloted peer reviews for two projects, where they invited partners to appraise each other’s work using a scorecard method. MJF report this initiative to have been very effective and they plan to roll it out extensively across their portfolio.  MJF previously had a scoring mechanism for their projects, which has fallen out of use over time. These should be reintroduced as it provides a simple metric that can incentivise partners to improve their work and also allow MJF to easily assess the performance across their entire portfolio.

MJF needs to develop its systems and capability to collect and use routine monitoring data to improve programme performance. It also needs to collect data to track outcomes of their projects.