Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	August 2017

Title: Transparency for Health Outcomes
Programme Code: / 203209-103	Start Date / April 2014	End Date: March 2018 – T4D has requested to extend the project by a further 18 months.
If programme was closed >1 month early please describe in a few words why.	DFID decided to end involvement (exiting in August 2017) due to delays in project delivery. This followed a request from the implementation consortium for an 18 month extension of the project (within the current budget that would have taken the project to Sept 2019). The continued support from other donors means that DFID can end its funding without significantly effecting the project.

Summary of Programme Performance

Year	2014	2015	2016	2017
Programme Score	A	A	A	B
Risk Rating	Minor	Minor	Major	Moderate

Financial Position

Original Programme Value	£1.4m (DFID contribution) / Joint funded project, total value $8.2m
Extensions/ amendments	None – 1 request received. Decided not to approve and close DFID involvement in the project.
Log-frame revisions (with dates)	The logframe reflects the strategy and deliver plan mutually agreed with T4D and the other donors. The original logframe had mainly end of project milestones. / At annual reviews in 2015 and 2016 and following Steering Committee meetings, some logframe target dates have been revised and interim milestones added, with DFID and the other donor’s agreement.
Total programme spend	£1.3m (to confirm sterling figure once US dollar amount released by accounts department)

Follow up actions required following closure
T4D will continue activities according to the revised workplan, funded by the other donors.
DFID’s Governance, Conflict and Social Development (GCSD) research team will maintain an interest in the final research products of the T4D project when they are published, but because of DFID staffing constraints we will not retain any formal role on the project steering committee.
We will continue to ensure that relevant DFID staff and research partners are aware of T4D’s research, and that T4D’s work is included in relevant synthesese of research evidence (e.g. in the areas of service delivery, transparency, and accountability).
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Quest 3952459
DevTracker Link to Log frame:	Quest 5200465

Outline of programme and what it has achieved
DFID has co-funded this project with the Bill and Melinda Gates Foundation (BMGF); William and Flora Hewlett Foundation (Hewlett); and with the Transparency and Accountability Initiative (T/AI – which is also co-funded by DFID’s policy division) also a member of the T4D Steering Committee. The total value, including DFID’s contribution of £1.4m, is $8.2m. At the start of the project, DFID’s contribution was about 25% of the total budget.
The project has four overlapping phases (currently at the final stage of Phase 1 and starting Phase 2):
1. Design Phase - a community-led project involving local civil society partners, for a mixed method evaluation that incorporates randomised controlled trials (RCTs) and qualitative methodologies.
2. Phase 1 - implementation of the design in two settings – Tanzania and Indonesia.
3. Phase 2 - to address the design and testing of replication studies in other countries (Malawi, Ghana and Sierra Leone).
4. Outreach and Dissemination - across all stages of the project.
The overall expected outcome was for policymakers, donors, practitioners, academics and other experts to have access to better evidence and engage in evidence-informed discussions about whether and how transparency and accountability (T/A) can improve health outcomes.
In 2014 DFID agreed to fund the project because a decade of research into the impact of T/A interventions had produced mixed evidence as to whether these have beneficial impacts, and much less on the extent of these benefits. Furthermore, available research had not provided an empirically verified account of what sorts of T/A strategies are best suited to different conditions and contexts. Reformers, policymakers, donors, and other practitioners lacked clear guidance on what sorts of T/A interventions to pursue — or, whether any T/A interventions can ultimately improve service delivery and health outcomes for poor people. These questions – and the need for better evidence – are still valid.
T4D’s aim is to deliver the following:
- High quality, policy relevant research products on the impact, generalisability, and scalability of T/A interventions being completed (Output One);
- Learning from the co-design process is accessible to practitioners (particularly CSOs) that implement T/A interventions (Output Two); and
- Evidence from research products being widely disseminated to T/A practitioners and donors, policymakers, academics, and other experts (Output Three).
Significant progress would need to be achieved on all of these outouts for the expected outcome to be delivered. T4D is led by the Harvard Kennedy School (HKS) and Results for Development (R4D), in a consortium that includes the University of Washington (USA), Pattiro (Indonesia), Clinton Health Access Initiative (Tanzania), and Abdul Latif Jameel Poverty Action Lab (J-PAL) Southeast Asia (Indonesia). In the last year T4D has started Phase 2 intervention and evaluation develpment in Malawi, Ghana and Sierra Leone; and is identifying partners for research in these additional settings.
Achievements:
T4D is a high quality research project, and is delivering the intended research products, partnerships, and policy engagement with prospective users of its research, but later than originally scheduled.
Research design and implementation in Tanzania and Indonesia was delayed by the need to revise and re-pilot interventions, and by delays in research approval in Tanzania and the election in Indonesia. As a result, delivery is around 18 months behind the original schedule. The plan to repeat the full RCTs in additional settings was revised to a plan to design and implement complementary smaller scale research in additional settings, and work on this is well underway in Malawi, Ghana and Sierra Leone.
DFID, and T4D’s other donors, have approved the revised workplan. However, DFID is ending is support as we are under pressure to rationalise the number of smaller projects in our portfolio. We are confident that T4D will continue to progress, and deliver its outcome, after DFID’s exit.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment	T4D is a high quality research project, but progress towards delivering its outcome has been slower than anticipated as research implementation and delivery of research products have been delayed. In the orginal programme design, final research papers would have been published by March 2018.
There have been a range of delays relating to the need to further refine intervention and research designs, and also in response to events such as elections in the study countries. These have pushed back implementation plans, and therefore the conclusion of field work and research outputs have been delayed by around 18 months.
However, despite this, engaging policy makers is underway, not least in planning and designing the research interventions. T4D reports that it has exceeded its year 4 milestones for its outcome indicators, such as for citations and downloads of its research outputs, and numbers of people attending its events.
Output Score and Description	As DFID leaves the project, our overall output score is ‘B’ - overall implementation delays mean that final research outputs will be delayed by around 18 months when compared with the original plan. Our assessment is that T4D has scored A for two outputs and B for two outputs. However, T4D has clearly communicated the project delays to DFID and the other donors, and we accept that the revised implementation plan – with later delivery targets – was accepted by all donors. We are confident that T4D will achieve the intended outputs, though later than originally intended.
Lessons and how these have been shared
For T4D, lessons learnt in co-designing an intervention with implementation partners (e.g. health NGOs) have been documented and proactively disseminated in blogs, briefs and other outputs. Similarly, T4D’s approach to developing its methods, and the theoretical framework for the research, have been published and presented for various stakeholders including to DFID audiences.
For DFID in 2017, funding a single consortium to deliver a very focussed research project of this relatively small size is now unusual. In the last 5 years, our norm is to fund larger programmatic approaches that deliver a portfolio of research projects and products, and within which the delays in one sub-project can be offset by the ‘on time’, or faster than expected progress, in others. In these programmatic approaches, the use of competitive granting mechanisms and robust grantee management (including termination of failing projects), has helped to ensure pace and avoid delays.
These mechanisms were not possible in the T4D design, and the opportunities for DFID’s more directive management to manage implementation risks were also limited by the co-funding arrangement. Moreover, T4D’s intensive ‘co-designing’ approach to intervention (with numerous iterations with implementation partners) also increased the likelihood of delays in implementation, albeit with the benefit of improved relevance and quality.
Commissioning larger budget, programmatic, and portfolio approaches is also a more proportionate and efficient use of scarce DFID staff resources. Therefore we would be unlikely to co-fund a similar project to T4D again, though the theme – transparency and accountability in health – has and is being further researched, and in additional settings, under other DFID research programmes, including J-PAL Governance Initiative, and the Anti-Corruption Evidence (ACE) Research Programme Consortium led by the School of Oriental and African Studies (SOAS) and under the Empowerment and Accountability (E and A) Research Programme led by the Institute for Development Studies (IDS).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	High quality, policy relevant research products on the impact, generalizability, and scalability of T/A interventions are completed.
Output number per LF		1	Output Score	B (moderately did not meet expectations)
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
1.1 Development of testable / theoretical framework for which T/A approaches are appropriate under which conditions.	Brief written and disseminated including how theoretical framework included in intervention in phase 2. / Final theoretical framework paper incorporating research findings – by end of project	Completed - see ‘T4D Phase 2 Concept” (2016) http://t4dev.org/articles/7 / N/A as this is an end of project milestone. The paper produced in 2014[1], and the publication of evaluation design and methods working papers in 2016[2], are preparatory steps for the final framework paper.
1.2 Number of papers based / on study results and research citations of study results	4 papers ready for publication (1 per RCT; plus one crosscutting), 50 research paper citations, 100 popular media citations – by end of project	N/A for this report. Preparatory work is progressing, including interim publications, but the production of these papers (the key outputs) will be later than the original 2018 target date.
[1] Stephen Kosack and Archon Fung (2014) “Does Transparency Improve Governance,” Annual Review of Political Science, vol. 17, pp. 65-87
[2] The two 2016 working papers ‘T4D Phase 2 concept’ and ‘Transparency for Development Intervention Design’ are available http://t4dev.org/articles/7

Key Points
Production of research outputs will be later than expected because of delays in implementation. These delays have been described in earlier DFID annual reviews and are summarised in the commercial section below. Despite T4D making progress on a range of fronts, because of the limited annual milestones for output 1, and because the overall production of research papers will be around 18 months later than was expected when DFID committed funds to T4D, we judge that a score of ‘B’ is justified for this output.
In this reporting year (the final one that will be co-funded by DFID), delivery of interventions has been completed in Tanzania and Indonesia (a total of 200 treatment villages completing intervention meetings, and community representatives in each village designed social actions to undertake to address health problems), and baseline data collection has been completed, including largescale surveys and qualitative research. The endline data collection in Tanzania and Indonesia is the main activity in the year ahead.
In addition, in this reporting year the T4D team instigated Phase 2 activities in three further countries – Malawi, Ghana and Sierra Leone. The Phase 2 Interventions will be launched in these countries between June and October 2017. The evaluation approach in Phase 2 will be mixed method and experimental in design, but will be smaller in scale than that applied in Phase 1 and in RCTs more generally – a total of 15 villages, with 5 in each country. Rather than seeking a precise estimate of an average impact across a large number of treatments, Phase 2 will focus on understanding as fully as possible the variation around that impact, particularly variation in the intervention’s intended mechanism. It will do so by augmenting the typical experimental approach used in RCTs with other empirical methods designed to understand, reliably and from multiple perspectives, the intervention, the environment in which it was implemented, and the causal pathways it took on its way toward any effect. This approach was approved by the project Steering Committee.
The theroretical framework, published in 2014 as an output in Phase 1, has been further refined and a updated paper sent to reviewers for comment.

Output Title	Learning from co-design process is accessible to practitioners (particularly CSOs) that implement T/A interventions
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of implementing partners that report having benefitted and learned from the co-design process.	5 - by end of project	N/A for this report though activity underway.
2.2 Number of briefs, blog posts, / and other practical guides produced related to the intervention design, co-design process, and approaches to improving transparency and accountability in health.	15, at least 10 specifically targeting global South / practitioners. (Year 4). / 30, at least 20 specifically targeting global South / practitioners. (End of project)	Completed - 21 briefs and blog posts now available on the project website. These cover emerging lessons and findings from Phase 1 and the design of Phase 2. / N/A - as end of project milestone.
2.3 Development of an intervention that can be rigorously evaluated	Completion of draft intervention design documents for phase 2 (Year 4) / Completion of pre-analysis plan for / Phase 1 (Year 4) / Final drafts of intervention design / guidelines, revised based on / evaluation results (End of project)	Completed - general documentation for overall intervention model; and documentation on intervention co-design (country specific) for Ghana and Malawi are completed. / Sierra Leone documentation is almost complete. / Completed - Plan developed and due for registration with the American Economic Association prior to endline data collection for Tanzania and Indonesia RCTs. / N/A as end of project milestone.

Key Points
There was no milestone for indicator 2.1 in Year 4. However T4D documented a range of interactions with partner CSOs and other organizations working on transparency, accountability, and health that have reported integrating lessons from Phase 1 and 2 intervention design and pilot observations into their own work. This includes the Indonesian partner Pattiro expanding the T4D intervention model to its new projects in education and disability.
In this reporting year, T4D put significant effort into producing short actionable blog posts and other resources that would be useful to practitioners working in T/A and in community-led health programmes. As a result,15 new briefs and blog posts are available on the Ash Center ‘Challenges to Democracy’ blog and the R4D blog. These disseminate emerging lessons and findings from Phase 1 and the design of Phase 2. T4D will continue the blog series (including the ‘Views from the Field’ and ‘Stories and Stats’ series) until the end of the project.
The T4D team completed a pre-analysis plan for Phase 1 RCT data collected in Indonesia and Tanzania. The plan outlines the impact estimation strategy, including the regression model to be used; declares the primary, secondary, and intermediate outcomes; and discusses the subgroups of interest. This plan will be registered with the American Economic Association prior to endline data collection.

Output Title	Evidence from research product is widely disseminated to T/A practitioners and donors, policymakers, academics, and other experts.
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		Milestones	Progress
3.1 Development of an outreach and dissemination strategy including the identification of key / stakeholders.		Report on dissemination outputs and results based on strategy (End of project)	N/A as end of project milestone. / Preparation is generally on track, e.g. building the new stakeholder lists (Malawi, Ghana and Sireea Leone) to work towards outreach in preparation for final project stages.
3.2 Number of research papers, / policy briefs, and other materials on project results produced.		5 (Year 4) / 10 (End of project)	Exceeded – see list below / N/A
3.3 Number of blogs, thought / pieces, podcasts, and other media products on lessons from the research and implementation / process.	10 (Year 4) / 20 (End of project).		Exceeded – 11 briefs/blog posts so far focus on the lessons from the research process. / N/A

Key Points
Reports from T4D’s theoretical and design work are available at Publications and working papers:
1. “Does Transparency Improve Governance” (by Steve Kosack and Archon Fung),
2. “Transparency for Development: Intervention Design and Evaluation Approach” (working paper),
3. T4D Baseline Report, T4D Phase 1 Evaluation Design Report,
4. “An Approach to Small-Scale Mixed-Method Evaluation” (working paper, outlining Phase 2 evaluation methodology),
5. “Citizen voices, community solutions” (working paper, outlining our approach to the Phase 1 intervention design).
There are also Intervention Materials:
- Community Scorecard Surveys
- Social Action Stories
- Facilitator Manuals
and Evaluation Materials:-
Baseline Report

By late 2017 the following drafts will be finalised and published online:
- Phase 1 Evaluation Design Report - (Quest 5784285)
- An Approach to Small-Scale Mixed-Method Evaluation - (Quest 5784285)
- Citizens Voices, Community Solutions - (Quest 5784279)

Output Title	Succesful management and implementation of health-focused T/A intervention and evaluation in five countries
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		Milestones	Progress
4.1 Number of communities in which the T/A intervention has been succesfully implemented.		Completed in 200 communities and launched in another 15 (year 4) / Total of 215 (end of project).	Partially completed. / Phase 1: 2 focus countries Tanzania and Indonesia (100 communities in each). / Phase 2: 3 focus countries Ghana, Malawi and Sierra Leone. 5 communities in each. Ghana/Malawi launching July. Sierra Leone in September? / N/A
4.2 Development of new evidence highlighting the role of community level T/A in health outcomes..		Qualitative tool data compiled, cleaned and analysed. Reports from ethnographers completed. (year 4) / Completion of baseline report from RCT data. (year 4) / Design of endline protocols completed (end of project)	Completed - Qualitative data collected, translated and cleaned – analysis underway. / Completed - Baseline report highlighting findings from surveys inTanzania available on line. / N/A
4.3 Successful launch of T/A intervention over 2 phases of work	Selection of 3 Phase 2 partners. Completion of Phase 2 intervention design and materials. Launch of Phase 2 intervention in 3 countries (year 4). / Completion of evaluation design and final protocols for evaluation data collection. (year 4). / Completion of Phase 2 intervention in 3 countries. Data from evaluation compiled, cleaned and analysed (end of project)		Partially completed. Phase 2 launches in Malawi, Ghana and Sierra Leone are scheduled to be complete by October 2017. / Completed / N/A

Key points

Output 4 was added to the logframe in 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from 2015 and 2016 annual reviews related to logframe changes to accommodate and respond to delays in implementation. T4D has strengthened the logframe, with changes approved by the Steering Committee, though some indicators still have end of project milestones only.
2016: The T4D logframe should be revised in relation to recent progress refining the Phase 2 design and updated Communications strategy:
1. Ensure Phase 2 does not lose focus on testing the hypothesis of a link between improved transparency and accountability and health outcomes (T4D, ongoing).
2. Ensure that each sub-output has meaningful indicator for each year, drawn from workplan (DFID and T4D agree revised indicators and milestones by July 2016).
2015: The T4D logframe should be revised in relation to
1. revised delivery plan and milestones approved by project Steering Committee (immediate)
2. ensuring that each sub-output has a meaningful indicator for each year, drawn from workplan (by Aug 2015).
3. accommodating the expected re-design of Phase 2, including the expectation that T4D will not deliver a third RCT of the intervention in a new setting, but instead focus on priority evidence in transparency and accountability through other methods (to be approved at SC in Feb/March 2016 in time for new logframe to be basis for next A/R).
Recommendations for future programmes
Since committing to co-fund the T4D programme, DFID research has undergone several important shifts, which mean that we would be unlikely to fund a similar sized and focussed research programme again.
First, DFID’s Research Budget has increased, including for governance, conflict and social development research, but administrative resources have remained relatively flat. Therefore RED’s ability to fund small projects has reduced – in fact we actively seek more efficient ways of commissioning and managing research at scale. This includes a major new Research Programme in Empowerment and Accountability which was let through competition, and has completed its inception phase.
Second, we have greatly expanded our support for field experiments, and have done this through thematic competitions, initially in governance and more recently in governance, crime and conflict. These competitions have funded some high quality RCTs in health and accountability, therefore the need to directly fund specific RCTs (such as those by T4D) has diminished. Our experience is that portfolio approaches, competition, and rigorous grantee management, help to manage risks and avoid the delays that have been experienced in T4D, and also reduce their impact if RCTs are funded in larger batches (some may be delayed but others will deliver on time, therefore the overall supply of research products is not completely halted).
Third, DFID is committed to operationally-relevant research and has a strong demand from operational teams and policy makers for evidence on the effectiveness of interventions. While high quality research requires sufficient time, the delays in T4D mean that policy makers have looked to other sources, rather than waiting for T4D to deliver. In reality there is a trade off between research quality (including the iterative design process adopted by T4D) and timeliness. Funding a larger portfolio of diverse accountability research helps to safeguard against delays.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers continued to be the direct/indirect staff costs plus travel, research consumables and management costs. HKS ensured that all partners complied with DFID project and financial management requirements and established sufficient governance structures to deliver the programme.
DFID’s total contribution to this co-funded project is the US dollar equivalent of £1.4m (towards a total fund of US $8.2m). Payment has been made on an annual basis in US dollars to match the funding agreements of the other project partners. Funds have been released based on T4D’s approved workplans and budget forecast.
HKS’s good practice standards are passed on to partners and aim to obtain VFM on all aspects of the project. HKS and has continued to work with consortium partners to find savings in existing budget lines such as linking travel arrangements from their work on other projects to coincide with this project to reduce travel costs, using possible longer term realtionships and commitments with partners to agree lower costs, and making use of skype and online ‘Webinars’ to maintain contact and open communication between partners without incurring travel costs. Where possible they have used existing communication platforms as a first choice rather than create new outlets to reach their audiences when disseminating publications and raising awarness of the T4D project.
DFID has just received the revised workplan and forecast and are arranging for the final payment to be released. The funds are released in US Dollars and the final payment is about to be released. This will be within the budget but the exact amount will only be known once the transfer has been made. (add sterling amount XXX against total budget – will be within total)
VfM performance compared to the original VfM proposition in the business case
Although DFID is withdrawing from the project, the research activities will continue and it is still expected to achieve the intended outputs and outcome. Although DFID will still have access to the project outputs the late delivery has had a negative impact on the project’s overall VFM. The results will be available around the new project completion date of September 2019.
Assessment of whether the programme represented value for money
Implementation delays and the proposed 18 month extension were the major factors in DFID’s decision to leave the project. Although delivery has been more or less within the original VfM proposition in terms of economy, the delayed outputs have reduced the efficiency of DFID investment and also required a longer input of DFID staff time and administration than we had budgeted for.
The delayed research products will unavoidably reduce the effectiveness (impact) of the investment: even if the research products are of the high quality and number expected, they will inform policy and operations later than expected, with the risk that bad decisions have been made by policy makers in the intervening period.
Quality of financial management during programme
HKS is responsible for the overall financial management of the programme and applies its own organisational financial regulations across the program to ensure proper control and efficient use of resources. The project funds are reported accurately showing spend by each of the 3 individual donors.

Date of last narrative financial report	28 April 2017
Date of last audited annual statement	2016, final audited statement will be provided after project completion

E: RISK (½ page)

Quality of risk management over the life of the programme
T4D conducted a detailed risk assessment as part of its original proposal and has continued to review and update risk assessment and mitigation measures. T4D’s assessment is that the overall risk continues to be low. T4D’s table below reviews specific risks identified in the proposal, and mitigation strategy for each risk. The final column updates each risk for this reporting year (year 4).
RISK	DESCRIPTION	MITIGATION STRATEGY	UPDATED / ASSESSMENT (year 4)
1. Insufficient statistical power	Intervention may have an effect but evaluation may not detect it statistically	We will perform conservative power calculations at the outset of each evaluation to ensure that the evaluation can detect policy-relevant effects.	For Phase 1 of the project, we conducted conservative power calculations to address this risk. Various implementation challenges might lead us to lower sample sizes than ideal but we are working diligently to build sampling designs that, subject to these implementation challenges, can maximize statistical power.
2. Spillovers	The treatment spills over to control units, threatening the ability of the evaluation to credibly estimate the impact of the intervention	We plan to mitigate spillover effects by randomizing at the level of the facility catchment area or higher. We will select communities with sufficient geographic distance from each other so that there are limited opportunities for the population in the catchment area of any of our facilities to be exposed to treatments occurring in the nearest adjacent community.	For Phase 1 of the project, we pursued this strategy as planned, randomizing at the puskesmas/ dispensary level while the intervention is taking place at a level below (village level). After observing the implementation in the majority of villages so far, we are confident that there will be little or no spillover based on the very local nature of the actions and targets of actions that the community representatives are pursuing.
3. Implementer and other stakeholders are not faithful to the random treatment assignment	Because of political pressure implementer or stakeholder implements the intervention in control areas or fails to implement them in treatment areas	Implementer will be selected because of their willingness to participate in a randomized evaluation and a training/ presentation to all staff will highlight the benefits of this approach. In advance of random assignment, implementers will specifically be asked whether there are facilities/ communities where they believe they will come under pressure to implement the intervention – if so, we will allow them to conduct the intervention in these facilities/ communities, but will not include them in our sample or data collection activities.	We have now collaborated with five partners on planning the implementation of the intervention in five different countries. Following discussions with our implementing partners regarding the importance of random treatment assignment, we have carefully monitored the implementation of the intervention in the Phase 1 countries (and will also do so in Phase 2) using field visits by PIs, by our local study coordinators, and by CSO supervisors. Based on these observations, we are confident that the intervention has only been implemented in the treatment villages.
4. Implementer does not fully implement the intervention in the full sample of treatment communities	Implementer has problems in delivering the intervention to all communities/facilities in our treatment groups during the specified timeframe due to capacity constraints or other unforeseen hurdles	Independent field staff (study coordinator) answering to the research team will work closely with the implementing partner during intervention planning and design, and will monitor progress, identify any challenges and possible solutions (e.g., increasing implementation staff/ capacity if the intervention is rolling out too slowly, etc.).	As part of the observation and monitoring described in the row above, we have also monitored whether implementation is happening in these target villages in the Phase 1 countries; further, based on successful results from monitoring in Phase 1, we will take a similar approach in Phase 2. Based on these observations, we are confident that the intervention is being implemented in all treatment villages.

In the last 2 years DFID has strengthened its approach to risk assessment, including adopting a four point scale (Minor / Moderate / Major / Severe) and breaking down risks into specific categories that span the project/programme implementation cycle. Last year the assessment was ‘Major’. In this reporting period we have assessed the risk as ‘Moderate’ as there has been good progress, and project implementation is now more or less back on track with the revised implementation plan.
At PCR, and with hindsight, T4D’s risk assessment focussed strongly on the risks to research quality, but weakly on contextual risks and related implementation risks that caused some of the delays experienced.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Note of delays;-
- Project inception phase was delayed while ethical approval was obtained to conduct research in Tanzania (from National Institute for Medical Research – NIMR).
- Work in Indonesia was delayed due to national elections. As a result, the co-design (with local partners) of the intervention to be evaluated took almost 18 months to complete rather than the anticipated 6 months
- After both country interventions had been designed and piloted in sample sites it was discovered that several components did not work as expected when implemented on a large scale. The Tanzania intervention was subsequently revised and piloted, with the T4D steering committee agreeing that it was better to accept delays, rather than proceed with a low-quality intervention.
- The Tanzania pilot was successful, so the Indonesia intervention was also redesigned.

The project has increased momentum but given the time taken to get to this stage and the additional 18 month required for project completion we have decided not to continue with the project
Performance of partnership (s)
The GCSD team has ensured that T4D’s research in Tanzania and Indonesia is recorded in country by country records of DFID’s centrally managed programmes, and DFID Tanzania in particular has been kept updated of work in country.
Asset disposal and value obtained by DFID
The only asset purchased using DFID funds is one laptop and HKS will retain it on record against this project. Asset disposal will be included in our project closure process.
G: CONDITIONALITY (½ page)
Partnership principles assessment	N/A as no funds flow to governments.
H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
Throughout the project’s life, T4D has submitted annual reports and DFID has participated in 6 monthly steering committees meetings with T4D and the other donors. Steering Committee meetings have reviewed progress and draft workplans, and have also been the venue for discussing and approving proposed changes in the project strategy and implementation. DFID has reviewed products on the T4D website site, including Blogs and research outputs.
In addition to delivering the impact evaluations and reporting to donors on logframe indicators, T4D implements a range of monitoring approaches to ensure that the interventions to be tested, and evaluation data collection, proceed according to time and quality plans. It summarises these in its annual reports.
Monitoring progress throughout the programme
Annual reviews and this PCR were conducted by DFID’s Programme Manager and the Team Leader (Senior Governance Adviser), GCSD. This PCR was based on a desk review of T4D’s 2017 Annual Report, financial reports, and publications, followed up with questions to and responses from T4D.