Annual Review - Summary Sheet

Title: Security and Risk Management in Hostile Environments
Programme Value: £1,819,617		Review Date: August 2017
Programme Code: 203978	Start Date: July 2013	End Date: March 2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A	A	A
Risk Rating	Minor	Minor	Moderate

The Security and Risk Management in Hostile Environments project promotes improved safety and security by strengthening NGOs’ security and risk management practices, essential for delivering humanitarian assistance to people in need. It does this through three complementary programmes and partners: the International NGO Safety Organisation (INSO), the European Interagency Security Forum (EISF), and by RedR UK. This annual review covers the progress of all three, between July 2016 – July 2017.

1. Red R – Mission Ready: “Mission Ready” online security training, is a cost-effective method of reaching a wide audience and equipping users with the knowledge and skills to manage their own security. The target of Mission Ready is primarily field-based national staff, unable to attend face-to-face security training. Statistics gathered during the reporting period show that people of 81 different nationalities, operating in 85 countries, used the training, demonstrating its global reach. The second “Remote Security Management” module, has gone live, and like the first, uses gaming technology to promote interactive learning. The first module was translated into Arabic, making it now available in 4 languages. Marketing by RedR has generated licence purchases from a number of large organisations, but there is still some way to go to meet the targets agreed.
2. European Interagency Security Forum: EISF has continued to grow in size as a network. In the reporting period it increased its membership by 5% and demonstrated high levels of member engagement. 89% of member organisations actively engaged with EISF, and it recorded over 26,000 users of its website and nearly 12,000 document downloads, demonstrating its relevance and usefulness to the sector. EISF has continued to engage specialists and organisations on a cost free basis, ensuring high quality products and events at low cost. EISF fills an important niche in the humanitarian security sector and DFID should consider providing further support once this project comes to an end.
3. International NGO Safety Organisation: In March 2017 the Minister of State agreed further support to INSO to build global capacity in humanitarian safety through organisational strengthening, and to develop its Conflict and Humanitarian Data Centre (CHDC). This is a secure, cloud-based database containing all security incidents recorded across INSO’s network. It will provide a reliable new evidence base for humanitarian operations, while supporting wider global awareness on the issue of NGO safety. INSO is in the process of developing two new country platforms in Cameroon and South Sudan, as well developing the CHDC. Recruitment for two senior posts is underway.

Key Recommendations and Actions for the final year of the programme :
1. Given its importance, DFID will continue to prioritise support for NGO security and risk management beyond the end of this project.
2. RedR will actively market and promote Mission Ready to ensure it reaches agreed user targets.
3. DFID will co-ordinate with other key and potential donors to promote a wider funding base and co-ordinated strategic approach for EISF.
4. Once INSO is established in South Sudan, CHASE will advocate for additional support from the DFID country programme.
5. Update logframes to the end of the financial year, and begin preparations for the end of the project and the Project Completion Report.
A. Introduction and Context

DevTracker Link to Business Case:	4609266

Threats to aid workers continue to rise to unacceptable levels, with national staff on the frontline continuing to face the highest risk. In the reporting period 104 national and 9 international staff were killed, 73 national and 10 international staff were kidnapped and 56 national and 21 international staff were wounded in the course of their work. Figures for kidnap of national staff have almost doubled since the last reporting period, and the numbers of national staff killed have increased by 20%. Only last week 6 Red Cross volunteers were killed in the Central African Republic.

The highest risk locations are those affected by active conflicts, primarily civil wars and ethno-religious violence. Aid workers in South Sudan experienced the vast majority of incidents (41), followed by Syria (27), Afghanistan (13), DRC (9), Somalia (8) and the Central African Republic (7). (Source: Aid Worker Security Database). With increasing numbers of conflict driven crises – including four potential conflict related famines in 2017 – the need for donor support that promotes safe access for humanitarian aid workers, and therefore increased delivery of aid to the most vulnerable, is stronger than ever and DFID should continue to support this as a priority.

DFID Ministers and officials have made public statements about the dedication and sacrifices shown by humanitarian aid workers, including strong public statements around World Humanitarian Day and memorial events every August. Practical support for proactive measures which help safety and security for aid workers are a very effective way of combatting the risks and threats and of honouring aid workers.

These three programmes are complementary and are managed and monitored by CHASE as a coherent three-part programme.

(i) Accessible and effective training: A NGO-led partnership between RedR and Digital Training Solutions (DTS) has developed an innovative approach to humanitarian security training using interactive gaming software designed to improve knowledge retention through immersive learning. It complements existing face-to-face training, but as an e-learning package is able to reach more users at lower cost. It helps teach key skills, such as raising the awareness of personal security, preparedness and planning, direct and remote security management, personal risk assessments, and travel security. CHASE is jointly supporting the project with OFDA (US government), providing £270,000 to support the design and build phase of the training programme
(ii) Improved NGO security management and awareness: The European Interagency Security Forum (EISF) is a network of European NGO security focal points. It leads best practice in humanitarian security management, enhancing the safety and security of aid workers and allowing increased and sustainable access to populations in need. The impact of EISF’s work has been the professionalisation of NGO approaches to security management. EISF has also enabled smaller international and national organisations – often with limited resources for security – to meet acceptable standards of care. CHASE is providing £250,000 to EISF between 2013 – 2018.
(iii) Building global capacity in humanitarian safety: The International NGO Safety Organisation (INSO): INSO was established in 2011 to support the humanitarian community with information, analysis and advice. INSO has established a comprehensive network of field level safety platforms that provide daily support to more than 800 national and international NGOs in 11 high risk and Level 3 countries including Syria, Iraq, the Central African Republic, DRC, Somalia and Afghanistan. By improving NGOs’ contextual awareness and strengthening their capacity to respond INSO plays a vital role in protecting aid workers and ensuring safe humanitarian access. DFID provided £594,000 core support to INSO in 2014/15 under this project, and in March 2017 the Minister of State, following the Portfolio Quality Review and building upon CHASE’s original grant from 2014/15, approved the further £364,658 for 2017/18.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

1. RedR Mission Ready

Outcome	Safety and security of humanitarian actors is increased as a result of take up of Mission Ready
Indicator(s)	Milestones	Progress
1. Number of active users of Mission Ready (completed courses or currently using a course)	1,000 users (2yrs after launch)	618 active users, 1,191 licences issued
2. Evident changes in knowledge of Mission Ready users	Analysis component of tool indicates increase in knowledge for +900 participants. (2 yrs after launch)	67% (198 individuals out of 295 who have completed the course)

‘Field Security Management’ (FSM) was released in Arabic, French, Spanish and English in 2015, and an offline PC application was made available in 2016. During the reporting period the second Mission Ready course ‘Remote Security Management’ (RSM) was released in English in 2016, and translated into Arabic in 2017.

Mission Ready is a well-researched and executed product. RedR and DTS have delivered 2 courses comprising 10 interactive scenarios, in 4 languages, with offline functionality. It has achieved an average rating of 4.4 / 5 by users who have completed it. The training has been accessed by 59 organisations, from people of 81 different nationalities operating in 85 countries, demonstrating its global reach.
The numbers of active users – 618 two years after launch compared with the 1,000 target – is lower than hoped and RedR will need to do more to actively promote the training to meet the targets set at the beginning of the project. Learners are also taking longer than expected to complete the course. This may indicate that it is being used as a learning platform that users return to as part of a monthly study plan, or that users dip into certain topic areas when they feel the need or context arises. Since the last review, RedR have added a progress bar to Mission Ready to make it easier for the learner to understand how much of the course is still to be completed. RedR hope this will improve course completion.

RedR have sought to improve uptake of the course through continued promotion of the platform. In 2017, Remote Security Management’s Arabic translation launch took place in Amman. RedR sent out press releases to many news outlets in advance of the launch which led to media interest in Mission Ready. The launch also led to an attendee making an order for a significant number of licenses for their local partners in Yemen. Videos from the launch will be used to further promote the course online. RedR is also actively marketing Mission Ready via social media which has generated some interest. For instance, a large international NGO recently purchased a bulk order of 190 licences, after hearing of the training via LinkedIn and organisations such as Save the Children and the Danish Refugee Council have purchased licences.

Has the logframe been updated since the last review? RedR have revised Outcome Indicator 2, Output Indicator 1.2 and Output Indicator 2.2 to reflect the issues faced with the course completion rates and the logframe will be updated following the Annual Review.

2. European Interagency Security Forum

Outcome	Security Risk management improved across the humanitarian sector through stronger relationships and greater trust
Indicator(s)	Milestones 2	Progress
1. % of EISF members who utilise EISF services	80% of members utilise EISF services, with a 5% growth in membership per year	89% with 4 new members
2. Number of stakeholders and external experts who facilitate at EISF events	At least 10 external experts facilitate at EISF events	12 (8 external experts at EISF forum, plus 4 at ‘Accountability in Abduction’ workshop)
Outcome	Knowledge and experience on humanitarian security risk management is shared using EISF platform
Indicator(s)	Milestones	Progress
3. % of EISF members who utilise EISF website	70% of members utilise EISF website with a 5% growth in membership per year	Currently unable to measure who has signed in to members area. EISF following up with website provider.
4. Number of visits to EISF website and number of downloads per month	An average of 3,500 visits and 750 documents downloaded	26,820 individual users and 11,806 documents downloaded
Outcome	Integrated security risk management skills and knowledge improved
Indicator(s)	Milestones	Progress
5. Number of workshops / learning events organised by EISF per year	3 workshops / learning events	3 workshops
6. Number of articles tackling gaps in SRM implementation produced by EISF per year	2 articles tackling gaps in SRM implementation produced by EISF	2 articles

EISF has made solid progress towards its outcome of improving security risk management across the humanitarian sector through stronger relationships, greater trust. Four new members joined EISF over the reporting period, representing an increase of 5% in membership.

The value of the EISF to the NGO security sector is demonstrated by 89% of its members utilising its services, either through attendance at events such as the forum, workshops and country level meetings, joining information sharing groups, or asking / answering questions of the Secretariat and other members. The value of EISF is also reflected in its continued ability to attract external experts to speak at its forums and other events. Its website analytics demonstrate its relevance and value: the EISF website recorded 26,820 unique website users and 11,806 document downloads in the reporting period. EISF are speaking to their website provider to determine if it is possible to track how many people have signed into the members area of the website.

EISF has continued to lead on best practice, demonstrated through its publication of the HR module of ‘Security to Go’ and ‘Security Risk Management: a basic guide for smaller NGOs. EISF further promoted learning and knowledge sharing by running two forums and a workshop on ‘Accountability in Abduction Management’.

DFID funding under this project will end in March 2018 and EISF’s other two major donors – US OFDA and the Swiss Federal Department of Foreign Affairs (FDFA) – are expected to review their contributions.

Has the logframe been updated since the last review? Yes, negotiations were held with EISF in July regarding adjustments to the logframe.

3. International NGO Safety Organisation

Outcome	NGOs have access to high quality safety information, analysis and coordination services that help them operate and deliver aid more safely
Indicator(s)	Milestones	Progress
1. The percentage of registered NGOs indicating that INSO services improve their ability to operate and deliver more safely	0%	Too early to say. Will be assessed through country level surveys and reported at the end of the project

INSO funding commenced in April 2017, therefore this annual review only covers the first three months of INSO activities (April – June), so is light touch at this stage.

INSO has made satisfactory progress against the organisational development milestones that will enable it to continue to provide a high level of information, analysis and coordination services for NGOs. Its recruitment milestone (90%) was just missed (86%). It has made some progress against its organisational development plan (21% achieved, just exceeding the 20% milestone), but slightly lower progress against the risk register (50% achieved with a milestone of 55%). These slightly low scores were due to the unexpected departures of two senior members of staff. Despite this, significant organisational developments were achieved, including the identification, recruitment and appointment of three new Trustees to the INSO Board of Directors. This marked the most significant expansion at the governance level since INSO was formed, effectively doubling the size from 3 to 6 members.
INSO has applied its Direct Project Support (DPS) funds in Palestine (Gaza), South Sudan and Cameroon. South Sudan and Cameroon are new platforms, both of which exceed INSO’s minimum threshold of 30 participating organisations. South Sudan has more than 300 NGOs registered and Cameroon has 45. INSO has experienced some difficulties operating in the Occupied Palestinian Territories (OPTs) which may affect its long-term presence there. Once it becomes established in South Sudan it will need to explore longer term support for its platform beyond its application of DPS funds.

During the reporting period two necessary pre-cursors to the development of Conflict and Humanitarian Data Centre (CHDC) have been developed. The Application Programming Interface (API) will allow NGO partners to self-manage their registration information, and the Partner Portal will become the new home for partner data and the primary means by which NGOs register with INSO. The Partner Portal will allow partners to directly manage their own registration data and will be the basis upon which they are allowed access to the CHDC and other future online services such as country level repositories.

Overall output score and description

Mission Ready

Output 1: An innovative online security training system is available to the humanitarian sector through 6 interactive film-based scenarios A – Met expectations

Output 2: A series of high quality learning programmes to support the scenario is available to the humanitarian sector including documentaries, expert interviews and written content. A – Met expectations

European Interagency Security Forum

Output 1: Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders is expanded and strengthened. A - Met expectations

Output 2: Members actively share information and respond to requests, EISF website and social media is an up to date resource for humanitarian security issues, and EISF ensure the global debate on humanitarian security issues considers the needs of EISF members. A – Met expectations

Output 3: Capacity of member for security risk management is improved and horizons broadened, EISF Secretariat identifies skills gaps in security risk management and develops means to address them, and practical tools and guides produced to fill skill gaps in humanitarian security. A – Met expectations

International NGO Safety Organisation

Output 1: INSO is able to govern, operate and upgrade its existing project portfolio. A – Met expectations

Output 2: INSO develops new platforms, data analysis, mapping and research tools that improve support at both the country and international level. A – Met expectations

## C: DETAILED OUTPUT SCORING

1. MISSION READY: INNOVATION IN HUMANITARIAN SECURITY TRAINING

Output Title	An innovative, online security training system is available to the Humanitarian sector through 6 interactive film-based scenarios.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestone 2	Progress
1.1 Number of scenarios made available to the Humanitarian sector	4 scenarios	Exceeded. Online system available and fully functioning. Downloadable PC application training available. Available in 4 languages.10 interactive scenarios in two separate courses
1.2 Participant feedback on relevance of online scenarios	Average Participant score from 1,000 participants across all 3 factors is higher than 4/5. (2yrs after launch)	Average score 4.4 from 295 participants who completed the course.

Output Title	A series of high quality learning programmes to support the scenarios is available to the Humanitarian sector including documentaries, expert interviews and written content
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestone 2	Progress
2.1 % of proposed programme of learning tools made available to the Humanitarian sector	50%	Achieved. 11 expert interviews; 1 course introduction documentary; 1 impact report; 9 downloadable pdf resources; 2 audio lessons in incident reporting; 10 audio recaps. 1 group study guide for FSM, 1 individual study book for RSM
2.2 Participant feedback on overall quality and relevance of all learning tools.	Average Participant score from 1,000 participants across all 3 factors is higher than 4/5 (2 yrs after launch)	Average score 4.4 from 295 participants who completed the course

Key Points

RedR have made good progress, either meeting or exceeding some of the milestones, but missing the targets for others. The two courses have now been developed: Mission Ready Field Security Management and Remote Security Management. Both are online, available, and fully functional. A downloadable PC version has also now been made. Average participant scores on the relevance and quality of the courses and their materials is high, although the survey is not from as many participants as originally planned. User uptake is lower than originally hoped for and RedR will need to reflect on their marketing strategy in order to meet the targets agreed at the beginning of the project.

Field Security Management (FSM) is set in an East African context, and is now available in 4 languages: English, Arabic, Spanish and French. Remote Security Management (RSM) is set in a Middle Eastern context, and is currently available in English and Arabic. In February 2017, DFID agreed an additional £10,197 to allow the Field Security Management module to be translated into Arabic. Launch events have been held in London (twice), Kenya, Pakistan and Jordan. At the time of writing, a total of 1,191 licences (for both courses) had been distributed, accessed by 59 different organisations, from people in 81 different countries.

Once the training is complete a survey is conducted automatically to gauge the impact of the course. This is sent to both users and their line managers at 3 month and 12 intervals to assess the medium and longer term impact of the training. An Impact Assessment of the Field Security Management training was conducted in April 2017. It found that:

- more than 1,000 licences had been distributed, with 639 of them activated, and 295 users having completed the training.
- 83% of users rated the course good or excellent, and 87% of users rated it relevant or highly relevant.
- 93%of users said they would recommend the course to others.
- 60% of users have worked or were working in hostile environments since taking the course.
- 78% of users agreed or strongly agreed the course had positively changed their behaviour and the behaviour of other staff within their organisation.

Between November 2016 and January 2017 qualitative feedback on FSM was gathered through interviews with course commissioners and users. Participants liked the option of being able to obtain online training as it offered flexibility and the fact that it could be done around other work commitments. It also allowed staff based in remote locations, which are often at the front line of humanitarian responses, to receive the training. Participants also liked the interactive nature of the training which made it more accessible and engaging.

Examples of positive impact of the course include the NGO Humanitaire International who had previously not had any safety or security policies in place developing new policies following the training. Similarly for staff at Forum SYD Somalia, the Somalia Office has now has put in place Standard Operating Procedures, and the course had contributed to the development of a culture of safer practice within the office.

Summary of responses to issues raised in previous annual reviews

1. The CHASE OT Security Adviser should remain on the Mission Ready Steering Committee: Action: This remains the case.
2. RedR should continue to develop an app and offline versions of Mission Ready to enable access in locations with poor internet. Action: Complete. A downloadable application of the training for PCs is now available.
3. RedR should develop its marketing approach to ensure maximum take up of Mission Ready in the sector, ahead of DFID funding ending in 2018. Action: Further work will be needed by RedR to promote and market Mission Ready to increase licence purchases and meet targets agreed at the start of the project.
4. DFID should continue to explore the possibility of further co-funding RedR to support the development of an interactive module on Protection training. Action: This was explored, but ultimately funding was allocated to other priorities.
5. DFID should continue to explore the possibility of further funding to RedR to allow it to expand its security training to UNDP for security focal points working in humanitarian emergencies through the new Specialist Services Business Case. Action: This was also explored, but advice received from within the department was that this work stream did not align with DFID’s current business case for UNDP.
6. DFID should promote uptake of the course internally for use by its staff. Action: RedR met with DFID’s Departmental Security Unit (DSU) to present the training but it was felt by DSU that the training was not suitable for use by DFID staff as it did not incorporate HMG-specific policies.

2. EUROPEAN INTERAGENCY SECURITY FORUM

Output Title	Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders is expanded and strengthened.
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1. % of EISF members who positively engage with EISF	60% attendance at EISF forums is maintained, with members scoring 3 out of 4 for quality and relevance, and 55% of members participate in at least one additional event per year	75% and 61%
1.2 Number of country coordination events supported per year	At least 4 country coordination events are attended and / or supported by EISF	4 UK, France, Spain, Germany
1.3 Number of stakeholders and external experts who support EISF research projects	At least one sector expert included in EISF research working groups	3 HR Module - Security to Go; Security Risk Management Guide for Smaller NGOs; Security Risk Management for staff with diverse profiles

Key Points

The first EISF forum of 2017 was held in Brussels in March. 55 participants attended from 49 member organisations. A further 11 member organisations attended the forum held in September in Echborn, meaning 75% of organisations attended at least one forum. 61% of organisations attended more than one event, such as the Accountability and Abduction workshop, or the joint EISF/FCO workshop.

Issues covered at the forums were wide ranging, with subjects as diverse as staff detention in the DRC, Duty of Care, terrorist threats in urban environments, and working with private security providers. The Q&A sessions were reportedly highly appreciated, providing an opportunity for participants to ask questions directly of peers and sector experts.

EISF have supported NGOs to establish and maintain country level coordination groups in the UK and France, as well as speaking at the Spanish Access Forum, and working with German NGOs to establish a coordination group there. Such meetings help organisations to forge links with peers working on similar issues and also provide learning opportunities that can then be reflected in improved policies and planning. The country focussed coordination groups have also organised security training, and in Spain ACH, Oxfam Intermon, and Medecins du Monde shared expertise and resources to deliver a one day personal security course in Spanish.

All EISF research projects included external experts in the working groups. This included the Human Resource module for ‘Security to Go – Common Humanitarian Standards’; ‘Security Risk Management: Guide for Small NGOs’; and a new research project being established on security risk management for staff with diverse profiles .

Output Title	Members actively share information and respond to requests, EISF website and social media is an up to date resource for humanitarian security issues, and EISF ensure the global debate on humanitarian security issues considers the needs of EISF members.
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 Number of member updates circulated per year	24 EISF updates circulated	34
2.2 Number of external vacancies and training events added to the EISF website per month	An average of 25 external notifications added per month	20 – 25
2.3 Number of original papers and translations produced per year	1 paper, 2 short research reports and at least 1 translation per year	4
2.4 Number of EISF blogs produced per month	An average of 3 blogs and service updates produced each month	6 over 6 months
2.5 Number of external events and working groups that EISF participate in	EISF participates in 8 external events and 2 working groups	11

A total of 34 updates were circulated during the reporting period. These covered issues including: Duty of Care for partner organisations, pre-deployment psychosocial health checks, policy development and risk thresholds, as well as questions about specific countries. Direct feedback to the Secretariat has been positive, with field offices appreciating the News Updates and Research Newsletters in particular.

Members and other organisations continue to advertise security related roles on the EISF website and during the reporting period an average of 10 – 15 vacancies per month were added, plus an average of 11 training events per month.

The TORs for the research project on staff with diverse profiles was completed, with a consultant team identified, and the research expected to be published at the end of 2017. EISF also contributed an article to the PEAR (People, Environments, Assets, Reputation) risk management magazine, as well as having articles under development on different technologies for incident reporting and information management, and Safety and Security at Sea, all due to be published during 2017.

EISF published 6 blogs during the reporting period, averaging 1 blog per month, missing the milestone target. These covered: The State of Emergency in Ethiopia and Aid Worker Security; Greater Accountability and Respect for Human Rights: A Contract Guidance Tool for Private Security Services; Counter Terrorism Legislation and NGO Security Risk Management; Zimbabwe: A Crisis Unfolding; Why should we address sexual violence in humanitarian workplace; and Women in Security.

The Secretariat continue to encourage sector experts to produce blogs for the EISF website, but 3 per month is proving a challenge as it can take a long time to get the blog to a suitable standard for publishing. EISF have therefore requested this milestone is changed. The Research Adviser has developed some guidelines for potential blog writers to improve the quality of blogs received.

EISF participated and contributed to variety of external events during the reporting period. These help EISF to understand what is happening in the broader sector and helps the Secretariat identify topics for blogs, speakers, events and sessions at the forums.

Events attended included: French Humanitarian Forum (FEH); Duty of Care conference, organised by Signa, Antwerp; Safety of Aid Workers Overseas, organised by the Irish Foreign Office, Dublin; DOCHAS presentation on the Duty of Care to Irish NGOs; exhibition stand at Borderless 2017 in Harrogate, and H2H event at Humanitarian Partnerships and Networks Week (HPNW) in Geneva.

In addition to this, EISF continue to remain actively engaged with various cross sector working groups, including: SLT Oversight Committee and Working Group; IASC Reference Group for Principled Humanitarian Action; UK civil military coordination group; BOND counter-terrorism group, and ATHA/ACF “community of practice” for protection of humanitarian action.

Output Title	Capacity of members for security risk management is improved and horizons broadened, EISF Secretariat identifies skills gaps in security risk management and develops means to address them, and practical tools and guides produced to fill skill gaps in humanitarian security.
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 Number of external stakeholder participating in EISF forums	3 external stakeholder participating in EISF forums	5 (International Humanitarian Law experts, School of Oriental and African Studies, Drum Cusac, Metropolitan Police)
3.2 Number of capacity building events facilitated by EISF	3 capacity building events participated in and / or organised by EISF	2 training events, plus 1 webtalk
3.3 Number of guides and tools produced by EISF	At least 2 guides or translations produced per year	4 - HR module of Security to Go; Abduction and Management Guide underway; translations into French and Spanish.

The March 2017 forum had external representation from sector experts on International Humanitarian Law; from School of Oriental and African Studies (SOAS) on the current crisis in Mali; from Drum Cussac on the geo-political situation in Francophone West Africa; and from the UK Metropolitan Police on the terrorist threat in urban environments. Such external speakers help introduce new and different perspectives and encourage innovative thinking in the sector.

EISF participated in the Signa event in Antwerp on improving the Duty of Care for NGOs. This included discussions on strengthening the links between security risk management and human resource management.

The EISF Secretariat also reviewed Disaster Ready’s online security training and found most of the resources were for mainly personal security rather than broader security risk management. EISF and Disaster Ready are working together to address this gap.

EISF is planning a series of 6 podcasts aimed at raising awareness of security risk management amongst the broader humanitarian sector. The first one featuring the CEO of Christian Aid was broadcast in June. Through the podcast series it is hoped to build the capacity of field based and national staff, increasing awareness of the importance of security and risk management for the safety and security of staff.

During the reporting period the HR module of the “Security to Go” guide was published, as well as restructuring it to allow for the inclusion of other modules in the future. In addition, the “Security to Go” guide was translated into French and Spanish, and the “Security Risk Management Guide for Smaller NGOs” was submitted to the publisher. A consultant has been identified to finish the Abduction Management Guide, which should be published shortly.

Summary of responses to issues raised in previous annual reviews

1. EISF should expand its donor base and secure funding from other European donors. Action: EISF is actively exploring new ways to expand its funding base, including looking for funding for smaller projects, submitting joint proposals with other organisations and approaching foundations and corporate funders.
2. EISF should do more to promote its activities on social media and consider reviving the area of the website where members can exchange information. Action: EISF is increasing its use of social media, using specific events and occasions to raise to awareness e..g tweets on International Women’s Day. The EISF twitter account is seeing an increase in followers month on month.
3. EISF should collaborate with relevant organisations to help raise the profile of NGO humanitarian security at external events. Action: EISF has been active at external events, collaborating with partners as described under Output Indicator 2.5.
5. EISF should update its Security to Go guide with new sections on sexual violence and human resource management. Action: The Security to Go human resource section has been updated, and EISF are currently in discussion with VSO about developing a guide on sexual violence.

3. INTERNATIONAL NGO SAFETY ORGANISATION

Output Title	INSO is able to govern, operate and upgrade its existing project portfolio.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		-	Impact weighting % revised since last AR?	-

Indicator(s)	Milestones	Progress
1.1 The number of identified key staff positions filled	90%	86% 19 out of 22 key staff in place
1.2 The % of Organisational Development Plan (ODP) projects completed	20%	21% Less than expected because of unexpected loss of staff capacity
1.3 The % of the 57 Measureable Indicators of the 2017 Organisational Risk Register completed	55%	50% Affected by loss of HR Director. Appointment of 3 new Trustees to the Board

Key Points

The latest grant for INSO was only approved at the beginning of April 2017 so reporting is light touch at this stage. A fuller report will be provided at the six month point, at the end of September.

Of the 22 key staff positions, 19 were in place at the time of reporting. The positions of Chief Analyst, Head of Internal Audit and IT Development Officer were vacant, but were being recruited for.

The termination of the Chief Analyst, and unexpected temporary departure of the Director of Human Resources, has meant an unexpected loss in capacity in the organisation. This has had a knock on effect on the INSO management team, absorbing much of the spare time available for development work. Recruitment for replacements is underway. As a result not as much progress has been made against the Organisational Development Plan projects as had been hoped, but some progress has however been made in important areas.

There was no progress on the outstanding Risk Register items because of the departure of HR Director, however the recruitment and appointment of three new Trustees to the INSO Board of Directors has taken place. This represents a significant expansion of INSO governance oversight, doubling it from 3 to 6 people. The new members have useful backgrounds in charity law, donors and governance, and fundraising. The newly expanded Board will be reviewing and updating INSO’s Risk Register, scheduled for January 2018.

Output Title	INSO develops new platforms, data analysis, mapping and research tools that improve support at both the country and international level.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		-	Impact weighting % revised since last AR?	-

Indicator(s)	Milestones	Progress
2.1 The number of humanitarian crises benefiting from Direct Project Support (DPS)	2	3 Palestine (Gaza), South Sudan, Cameroon
2.2 The number of NGOs benefitting from INSO direct project support activities per country	0	0 (but 45 NGOs in Cameroon are benefitting from support from INSO Nigeria while the Cameroon office is being set up, and numbers will increase significantly if registration is successful in South Sudan)
2.3 Conflict and Humanitarian Data Centre (CHDC): the development and activation of a centralised incident database and user interface	Finalise Application Programming Interface (API) to connect members to CHDC. Finalisation of Partner Portal.	Achieved

INSO Direct Project Support (DPS) funds were used in Palestine (Gaza), South Sudan and Cameroon over the reporting period.

In Palestine INSO services had to be suspended, pending investigation by the Ministry of Interior (MoI), who have taken exception to their (and other NGOs) presence. INSO have consequently scaled back their operations, suspending most staff and contracts. INSO are however hopeful once the investigation is concluded it will be able to operate again. The DPS grant is co-funded by the German Ministry of Foreign Affairs and the Swiss Development Cooperation (SDC), both of whom are keen to see INSO remain in place and resume services.

In South Sudan, DPS funds have been used to support start up activities, which have included two scoping missions to meet and coordinate with local stakeholders such as NGOs, donors and the Government. Registration documents have been a submitted to the relevant Ministries. Following negotiations, an agreement has been reached with the South Sudan Coordination Forum that if INSO is successful in its registration that it will transfer the security coordination mandate to them.

In Cameroon, DPS funds are being used to support a satellite office in Maroura, which will be attached to and managed by INSO Nigeria to help bring a regional approach to the Lake Chad crisis. INSO have assessed that the relatively high level of violence in the Far North, and the high number of NGOs present, justify a direct presence. Registration with the local authorities is underway and INSO plans on being able to draw on ECHO funding once approval is granted. While the office is being established support is being provided by INSO Nigeria to 45 NGOs in Cameroon.

As a result of the preparatory works in Palestine, South Sudan and Cameroon, no NGOs have yet benefitted from INSO services in these countries. If, however, INSO is able to operate in Palestine, 87 NGOs registered with them, and the Cameroon platform could potentially support a further 45. In South Sudan, if the transfer goes ahead, then more than 300 NGOs that participate in the Sudan Sudan Forum would benefit from INSO services.

Work has continued with the development of INSO’s Conflict and Humanitarian Data Centre (CHDC). The Partner Portal is now complete with live testing underway. This will become the home of partners’ data and will be the primary means by which NGOs register with INSO. It will allow them to directly manage their own registration data and will be the basis upon which they are allowed to access the CHDC and other future online services. Once testing has been completed the Partner Portal is expected to be in general use in the next reporting period. INSO have decided to try and develop the CHDC using a combination of in-house capacity, bringing in some external expertise as required. INSO are accordingly recruiting for a computer programmer.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance / VfM performance

This targeted investment by DFID to improve the safety and security of NGO aid workers is important, and an often overlooked and under-resourced area. The three projects currently supported under this programme represent an effective and cost efficient way for DFID to support improved risk and security management of our NGO partners. In doing so it allows them to reach those most in need, whilst also minimising the risks to themselves when delivering humanitarian assistance. With attacks on humanitarian aid workers remaining high this relatively small investment to deliver large scale humanitarian support offers good value for money for DFID.

Economy: RedR’s Mission Ready online training is substantially cheaper than face-to-face training when compared with other similar courses. The price has been kept low to keep it attractive for its primary target audience – national staff working in humanitarian response. The average cost of a licence is $8 for individuals and $48 for organisations. These costs can be further reduced when bought as a bundle and is also dependent on the annual turnover of the organisation. EISF members are required to pay a membership fee, which goes some way to reduce its reliance on donor funding. EISF is also actively exploring options to diversify its funding base,including approaching foundations and corporate funders.
Efficiency: Cost savings have been achieved by RedR by sharing resources with RedR Kenya during filming, negotiating discounts for accommodation and facilities, securing documentary interviews for free, obtaining multiple quotes to get the best price for translations, and using in-house resources to assist with subtitling all Spanish translations. EISF have managed to get some technical input for their papers for free, and the German Development Agency GIZ hosted and covered all expenses for the forum in September 2016 in Eschborn and are negotiating with a security provider to sponsor the September 2017 forum in London.
Effectiveness: “Mission Ready” online security training, is an effective method of reaching a wide audience, in particular national staff who may find it difficult to receive face-to-face training due to travel, visa or geographical restrictions. Statistics gathered during the reporting period show that people of 81 different nationalities, operating in 85 countries, used the training, demonstrating its global reach. EISF membership continues to grow, with 89% of its member organisations actively engaged with it, and over 26,000 users of its website, demonstrating its relevance and usefulness to the sector. INSO has established a comprehensive network of field level safety platforms that provide daily support to more than 800 national and international NGOs in 11 high risk and Level 3 countries, and this is set to expand significantly once the South Sudan and Cameroon platforms become operational. In addition the CHDC will be a resource available to all INSO members.

E: RISK

Overall risk rating: Moderate

Overview of programme risk: The overall risk rating for the project is judged to be moderate, up from minor last year, primarily due to the new funding now being channelled to INSO which is working in some challenging countries and RedR’s lower than planned user numbers.

- The development of the training material by RedR is now almost fully complete. The challenge, and risk, is now ensuring it reaches as many users are reached as originally planned.
- Most of EISF’s activities are considered low risk, given they operate mostly in Europe. EISF however recognises it needs to diversify its funding base further and to this end is considering new and innovative options such as approaching private sector and foundations. This will be important to enable it to continue to provide its valuable service to the humanitarian community.
- INSO is operating in some risky and difficult countries and is facing challenges establishing new platforms in Palestine, Cameroon and South Sudan. The organisation is also currently carrying vacancies for some key senior positions that have impacted upon its ability to advance some work streams. These posts are being recruited for, and DFID will monitor closely delivery against agreed logframe milestones in the next reporting period (end September 2017).

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The project is on course against the original timeframe with all DFID due to make final payments to all three organisations on or before the end of 31 March 2018. DFID is however actively considering what future support it could provide for humanitarian NGO security beyond the end of this project.

Performance of partnership(s)

RedR has developed a successful partnership with DTS throughout the life of the project to develop the training and set up systems to manage ongoing project activities effectively, working together closely to make changes to improve the platforms and resolve problems. All income from the sale of licences (£15,681) has been split between RedR and DTS (60:40) at the exchange rate of the time received and reinvested into Mission Ready platform activities. RedR needs to reflect on its marketing strategy and consider what more it can do to increase uptake and purchase of licences to reach agreed targets.

G: CONDITIONALITY

n/a

H: MONITORING & EVALUATION

Monitoring progress throughout the review period

RedR: Once the training is complete a survey is conducted automatically to gauge the impact of the course. This is sent to both users and their line managers at 3 month and 12 intervals to assess the medium and longer term impact of the training. However RedR have not received any feedback on the line manager surveys so propose to attempt to collect this data at the end of project evaluation through key informant interviews. An impact evaluation of Mission Ready’s Field Security Management course was also undertaken in April 2017. See Output 2 for a summary of its findings. In addition, RedR have provided progress reports for DFID for this Annual Review and in response to other ad hoc requests.

EISF: EISF provided DFID with a comprehensive 6 montlhly progress report for the period 1 October 2016 – 31 March 2017 against logframe milestones. The Executive Director also came to a meeting with DFID in July to discuss the progress of the project and discuss changes to the logframe. The next report is due at the end of September.

INSO: The INSO grant is only for one year and the organisation is providing DFID with quarterly progress reports. The progress report for the first quarter was light touch, but we are expecting to receive a much fuller mid-term report at the end of September. Progress against some of the milestones will however only be able to be measured at the end of the project. DFID met the Executive Director in July to discuss the project and agree logframe milestones.