Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performance over the course of its lifetime.

Review Date:	June 2016

Title: Achieving development effectiveness through improved UK NGO practice and transparency, and collective influencing of EU and international development goals.
Programme Code: 203953-101	Start Date: 1st May 2013	End Date: 31st March 2016

Summary of Programme Performance
Year	2013/14	2014/15	2015/16
Programme Score	A+	A+	A+
Risk Rating	Minor	Minor	Moderate

Financial Position
Original Programme Value	£2.7m
Extensions/ amendments	None
Brief details of the 3 most recent Log-frame revisions (with dates)	March 2016: Some amendments to language and targets to ensure consistency. Amendment to the targets for output 2.2 and the removal of outcome indicator 1.4 to reflect external opportunities and context. / Feb 2016: Clarification under output indicator 2.2.2 and impact indicator 3 on Bond’s role after the agreement of the Global Goals. / Jan 2016: Small changes to better reflect Bond’s work in the third year of the programme.
Total programme spend	£2.7m

Other DFID Funding
In 2015/16 Bond received DFID contracts and grants for the following areas of work:
- £103,879 for co-facilitation of the Supporting Syria and the Region Civil Society Organisations (CSO) conference run on 3 Feb 2016.
- £9,800 for work gathering evidence and input on the Multilateral Aid Review (MAR).
- £8,592 for the provision of in-house training courses to DFID.
- £8,450 for undertaking the DFID Fund Manager survey and producing the subsequent report.

Short Summary from each Annual Review over the life of the programme, 2013-15

Summary of Annual Review March 2014
In the first year of the programme, Bond put in place a new team structure to deliver the work and recruited to fill new posts. Despite reporting on less than a year’s work, this allowed Bond to reach or exceed targets in most areas of its work. DFID recognised areas of particular success in Bond’s work on effectiveness, transparency, impacting EU policy and global work on the Post-2015 agenda.

Overall output score: A+

Individual output scores (as per the outputs in the logframe at the time):
Output 1.1 Bond supports its target audience in gaining the skills, knowledge and tools that enable them to make improvements in their practice.	A+
Output 1.2 Bond supports its target audience to transparently publish data to IATI standards and beyond DFID minimum requirements.	A+
Output 1.3 Bond conducts a research programme to include case studies tracking the use of Bond's effectiveness tools, promoting active learning based on practice and experience.	B
Output 2.1 Bond supports its target audience to effectively engage with and influence European development policy and practice.	A
Output 2.2 Bond supports its target audience to effectively engage with and influence the process and outcome of the post-2015 agenda (at both European and international level).	A+

Significant progress was made on both outcome areas of the programme during this period. During this reporting period, Bond’s role in global work on post-2015 became increasingly visible, despite a lack of clarity on what the space for civil society engagement in this process was likely to be. Bond’s work in Europe, which was well-established before this programme started, continued to offer a strong proposition to Bond members and policymakers. On effectiveness and transparency, Bond enhanced the range of information, advice, signposting, training, consultancy and other direct support on offer. Bond found that publishing to IATI was largely seen as a compliance exercise, so plans for the transparency work were expanded to promote broader cultures of openness.

An area of delay in this reporting period was on the research programme (output 1.3), where the recruitment of researchers was pushed back as Bond focused on revising the logframe and monitoring and evaluation (M&E) plans. This ultimately had no impact on the quality and usefulness of the research. In addition, some small adjustments were made to plans on the EU work to factor in the timing of elections and new opportunities for influencing EU policy.

Summary of Annual Review April 2015
Bond continued to successfully deliver the programme in its second year. Investments in specialist job roles in the wider Bond team allowed it to get the most value out of its offer to members. Bond’s growing expertise in the areas of work funded by the grant meant that high scores were seen across outputs. Bond’s theory of change for the programme evolved to better reflect learning from the work to date in and emerging challenges for its members. Two areas of particularly notable success were over-delivery on IATI targets and the high number of collective submissions to EU policy processes.

Overall output score: A+

Individual output scores (as per the outputs in the logframe at the time):
Output 1.1 Bond supports its target audience in gaining the skills, knowledge and tools that enable them to make improvements in their practice.	A+
Output 1.2 Bond and NIDOS support their target audiences to become more transparent in the publication of information on their activities and results.	A+
Output 1.3 Bond develops and provides new effectiveness tools and services that are responsive to evolving needs of members, within a sustainable business model.	A+
Output 1.4 Bond develops and shares improved knowledge for the sector on how organisational effectiveness is affected by the provision and uptake of effectiveness tools and services.	A+
Output 2.1 Bond supports its target audience to effectively engage with and influence European development policy and practice.	A+
Output 2.2 Bond supports its target audience to effectively engage with and influence the process and outcome of the post-2015 agenda (at both European and international level).	A++

As well as delivering the programme to plan in 2015/16, Bond undertook a number of other activities on DFID’s behalf. Work on the future of Civil Society and the changing role of CSOs (subsequently added to the logframe) included running workshops, hosting Twitterchats and submitting a report to DFID. Secondly, Bond set up and ran a successful Ebola Response Hub, taking this task on at short notice. This work showed that Bond’s strengths in coordination and convening CSOs for improved effectiveness also translate to the humanitarian content. Additional work was effectively managed to ensure that it had minimal impact on plans for the remainder of the programme.

Bond made further progress on outcomes in this period, with signs of change already being seen at outcome level despite the long-term nature of this type of work. Bond reached a high number of organisations (including small NGOs) in its effectiveness work and services, contributing to a diverse range of changes within these organisations, with positive feedback from users. Bond sustained its engagement with policymakers and members in a key period of post-2015 negotiations, including convening the action/2015 coalition in the UK. It continued to offer its members a breadth of opportunities to engage with and influence policymakers at both European and global level. Work was also done to include the voice, perspectives and evidence of Southern partners in Bond’s policy work.

A. Introduction and Context (1 page) Focus on lifetime of the Programme

DevTracker Link to Business Case:	Business Case and Summary 203953
DevTracker Link to Log frame:	Log frame 203953

Outline of programme and what it has achieved
Bond is the UK membership organisation for non-governmental organisations (NGOs) working in international development. The UK government, through the Department for International Development (DFID), has provided Bond with total support of £2,708,106 over three years (2013-16). DFID support for this programme reflects the UK’s priorities for effective development cooperation, and agreeing a poverty focused and adequately-resourced framework to replace the Millennium Development Goals (MDGs) post 2015. A well-coordinated and effective UK civil society sector is better able to implement development best practice and to promote a poverty-focused international development framework. Both lead to longer term impact for poor people.

The intended programme impact has been: The programme’s target audience play a key role in achieving development commitments through meeting their own effectiveness goals, and influencing European Union (EU) and international development policy and practice.

DFID funding has supported two specific outcomes:
1. The programme's target audience effectively and efficiently achieve their own organisational goals and exhibit best practice;
2. Target audience engages with and influences EU development policy and the post-2015 agenda.

On results, this Strategic Grant Agreement (SGA) with Bond has aimed to benefit:
1. (indirectly) – the millions of people living in poverty who are (or could be) reached by EU aid programme and development policies that are effective and focused on poverty reduction.
2. (indirectly) –1.4bn people worldwide living in extreme poverty (under $1.25/day)[1] who would benefit from post-2015 efforts (and current MDG ones) that remain focused on poverty eradication for the greatest possible number of poor people.
  [1] Annex 1: Bond Key Costs & Drivers Key costs	% budget	Cost drivers	Actions to manage them Staff costs	56%	Market rates / Wage inflation / Staff retention / Staff turnover and sickness / Internal vs external skill mix / Ensuring relevant experience & skill when recruiting	Rates – using a variety of recruitment agencies to remain competitive / Inflation – government statistics and an internal negotiation process used as basis for change / Retention – salary spine points and bands ensure staff are rewarded for loyalty and development / Skill mix – regular review of business needs and costs between internal vs external skills mix / Fixed term contracts – where relevant, staff are recruited for a discrete period of time to deliver time-bound projects / Offering non-salary benefits including a pension offer, training, flexible working and training and development opportunities Policy and campaigns programme	13%	Subscription rates / Design costs / Room hire and catering rates	Bond reviews regular subscriptions to ensure that they are still providing valuable services / Bond has an ongoing relationship with a design firm, which ensures value for money by reduced rates for bulk orders, and ensures quality and speed in processing orders / Use of in house facilities for events wherever possible, prioritising office meeting space for Bond training and working group meetings / When hiring external space, a range of quotes are collected and reviewed / A list of free and good value venues is held internally / Increasingly events are hosted and funded by corporate sponsors Training programme	6%	Trainer and consultant fees / Room hire and catering rates	Bond pays trainers and other consultants a competitive fixed daily rate to ensure reasonable costs and minimise unexpected fluctuations / Trainer expenses are capped with maximum rates for accommodation and other limitations / Catering costs are regularly reviewed and providers changed to get the cheapest rates / Training is run in the Bond office rather than hiring external space Communications and advertising	6%	Design and print costs / Agency fees	Bond has an ongoing relationship with a design firm, which ensures value for money by reduced rates for bulk orders, and ensures quality and speed in processing orders / When working with other agencies, a budget is set in advance within which providers must deliver Events	6%	Available office space / Room hire and catering rates	Use of in house facilities wherever possible / When hiring external space, a range of quotes is collected and reviewed / A list of free and good value venues is held internally / Increasingly events are hosted and funded by corporate sponsors Establishment	6%	Office rental rates / Maintaining appropriate office accommodation for current and future needs / Maintaining IT capacity to match current needs	Rates – negotiating best rates for right location for staff and members / Utilisation – maximising use of existing office space for current and future needs including outsourcing for specific events or requirements / IT – adapting systems to accommodate future needs and opportunities for efficiencies Consultancy	5%	Market rates / Engaging the skill sets required to deliver internal and external programme needs	Use of external consultants kept to a minimum to cover short term needs and skills not offered within the permanent staff appointment / When consultants are used, negotiations are undertaken to ensure maximum value / Contracts are commonly offered on a fixed rate for delivery to ensure that costs are predictable Staff travel	1%	Market rates	Management control and approval of staff travel costs / New guidelines have been produced in Bond’s Finance Manual on the appropriate sorts of accommodation and travel options to ensure reasonable travel costs Financial	1%	Bank charges / Capital expenditure	Regular review of banking arrangements to ensure that charges are kept a minimum / Bond has recently changed banks to ensure value for money Total	100% APPENDIX A Extension reporting Review Date:	February 2017 Title: Bond Programme Code: 203953-101	Start Date: 1 April 2016	End Date: 31 December 2016 A. SUMMARY AND SUSTAINABLITY Summary of key achievements during the nine month extension period Bond continued to achieve excellent results during the extension period. In addition to the results covered in Section B, new developments in the policy environment saw Bond achieving further unexpected outcomes in response to Brexit and the publication of three government reviews: - Following the Brexit vote, Bond ran an event in October to discuss implications for EU development policy, including around the SDGs, where panellists included Linda McAvan MEP, Chair of the European Parliament Development Committee. Bond had extensive dialogue with the Charity Commission on its EU Referendum guidance and the impact of the Brexit vote on charities. Bond joined the Brexit taskforce at Concord and have been gathering information and consulting with members on Brexit impact, including mapping EU funding instrument eligibility for non-EU NGOs and sharing intelligence. - Following DFID’s publication of the Civil Society Partnership Review on 4 Nov, Bond published an analysis for members and coordinated with DFID to be a useful gateway to the report itself and to the two funding programmes that opened straightaway. Since then they have collaborated with Inclusive Societies Dept to deliver three events enabling more than 300 individuals from Bond member organisations to engage with DFID on the content and implications of the CSPR. Bond also provided analysis on the MAR and BAR in December. - Bond published several new reports in support of member innovation and sustainability, including ‘An introduction to Social Innovation in NGOs’ published in April and highlighted by Global Social Entrepreneurs Network as one of their ‘top 5’ innovation resources; and ‘Financial Trends in INGOs’ published in April, with over 1,200 page views since. Summary of the key changes and/or improvements that will be sustained at the end of the extension period The majority of the work delivered under this grant will be sustained, as Bond was able to agree a further extension to the original grant agreement with DFID for a programme to support NGOs in making the transition to the new policy funding and operating environment, FutureFit. Thus the work to support NGOs’ innovation, adaptation, learning and performance improvement will be sustained, with an additional focus on leaders and trustees (identified in Bond’s Effectiveness learning papers as a key route to securing sustainable organisational change). Bond will continue to support its members’ engagement with the SDGs and ‘leave no one behind’, and to respond to the implications of Brexit for EC funding and policy influencing, though some of its work with the EU will now be scaled back. DFID’s reviews set out clear priorities for its funding approach, and Bond will work with the sector and with DFID to help realise the new ambitions in the CSPR and help secure high-quality development outcomes and value for money. Bond is named in the CSPR as a key partner for DFID in delivering its transparency goals and expect to further develop the support they can provide to members and their partners to extend the scope of IATI publishing. Bond’s ability to increase the income it earns from paid services and to forge mutually productive partnerships with businesses help to ensure the organisation is on a sustainable footing, able to deliver services and products that its members find relevant and useful. However some of its ‘public goods’ work cannot be maintained without further grant funding. B: PERFORMANCE Principle 1	Consolidation of current SGA work to contribute towards the new Sustainable Development Goals (SDGs) Bond members have a developed plan for UK and pan-European engagement on SDG implementation and financing, and have carried out 4 collective actions in support of that At least 50 Bond and NIDOS members' report improved ability to learn from and adapt activities following use of Bond/ NIDOS Effectiveness and Futures services between April and December 2016 At least 40% of organisations receiving IATI support from Bond between April and December 2016 demonstrate usage either of their own and/ or others' open data to inform decision-making Risk:		Minor	Impact weighting (%):	65% Key Points - Summary of progress during the nine month extension Principle 1.1: Bond continued to convene members around the SDGs, creating the SDGs group (150+ organisations) with a subgroup on ‘Leave no One Behind’. Bond members produced a paper with principles for LNB. The Development and Environment Group published a paper on how to jointly implement the Paris Agreement and the SDGs, and the Disability and Development Group on the value for money of leaving no one behind. At EU level, Bond provided input to the work of CONCORD and enabled members to contribute to the EU consultation on the future of EU development policy and implementation of the SDGs, and the EU AidWatch report. Bond facilitated member engagement in international conversations around the Goals, including a joint Bond-Civicus meeting with UN Special Adviser David Nabarro (20 members). Bond represented members at the HLPF, where they co-hosted an event with Together 2030 and international partners on stakeholder involvement in national reviews (57 participants). Bond contributed to the creation and strategic guidance of the Action for Sustainable Development platform, including chairing the working group on monitoring and accountability. Bond published a report with analysis of countries’ reports to the HLPF, and recommendations for country and civil society reporting on SDG implementation. It is used by UN-DESA as a key training resource for governments on how to work better with civil society as part of VNRs. The report was launched at a webinar hosted by Together 2030, Bond and the Asia Pacific Regional CSO Engagement Mechanism, with 118 civil society representatives from all over the world. Principle 1.2: 172 Bond and NIDOS members engaged with Bond’s Effectiveness and Futures services between April and December 2016. 103 are estimated to have improved ability to learn from their activities as a result of using Bond’s services. NIDOS has run training for 18 members on funding, grant management and use of social media; held two MEL Working Group meetings on impact management and organisational level frameworks; and provided 13 organisations with targeted grant surgeries, mentoring support and Toolkit support. Bond has delivered a range of Effectiveness and Futures services, supporting peer learning through convening working group meetings on MEL; transparency; funding; and innovation, engaging over 170 members. Working with Inventium, Bond ran an innovation audit for 68 members, providing tailored analysis and producing a sector benchmarking report. 6 organisations used Bond’s Evidence Principles tool at an organisational level and two were supported to implement an organisational Health Check. Bond continued to develop and offer new resources on evaluation, including a Choosing Appropriate Evaluation Methods Tool, downloaded 771 times. Principle 1.3: During this time period, Bond ran 6 workshops and 1 use of IATI data workshop, plus a helpline, supporting 78 organisations. Bond saw multiple benefits from organisations interacting with IATI data (e.g. through d-portal.org) to support partnerships/share best practice for grant proposals, from seeing their own data used (e.g. Dev Tracker), thereby reinforcing the importance of investing in data quality; and from using the IATI data standard as a framework for communicating their own programme data (examples include Christian Aid’s Helicopter project, Overseas Development Institute’s transparency portal (in progress) and Oxfam GB’s re-engagement with Oxfam Atlas). Analysis through the 2016 survey plus subsequent info shows 43% of users of Bond IATI services have used this data to inform decision-making, exceeding the target. Principle 2	Organisational effectiveness At least 4 new learning papers on effectiveness, learning and transparency issues based on Bond's experience produced and disseminated The PPA Learning Partnership is hosted by Bond and remains vibrant; non-PPA-holders report making use of learning products Bond itself achieves an average score for "Monitoring" pillar indicators in the Bond Health Check is at least 3.5 (out of 5) Risk:		Minor	Impact weighting (%):	15% Key Points - Summary of progress during the nine month extension Principle 2.1: Four new learning papers were produced and disseminated, with the following titles: 1) Adaptive management: what it means for CSOs; 2) Effectiveness services: types and value; 3) Eight tips for designing effectiveness services that work; 4) Senior leadership roles in promoting NGO effectiveness. All papers were published on the Bond website, with a launch event held for the Adaptive management paper on 14 September 2016, attended by 42 members. Since then, the Adaptive management paper has been downloaded 708 times. Principle 2.2: In April 2016 the PPA Learning Partnership (LP) transitioned to Bond. Working closely with the LP Steering Committee, nine working groups (WG) transitioned onto MyBond; four merged into existing Bond groups, one merged into the Gender and Development Network; and two were closed. A number of the working groups have produced or contributed to learning products: - The Value for Money WG worked with Mango and Bond to produce “Assessing and Managing Value for Money: Lessons for NGOs”. The report was launched in October 2016, with 40 attendees, including 16 non-PPA-holders, and has been downloaded 217 times by 196 people. This publication helped contribute to Bond’s Disability and Development Group policy paper “The Value for Money of Leaving No one Behind”. - Following a series of three learning events engaging PPA and non-PPA holders, members of the Institutional Effectiveness LG supported Bond to produce “Adaptive Management: What It Means for CSOs”. The report was launched in September, with 42 attendees, including 19 non-PPA holders. The event was met positively, attendees commented on how useful the event was in highlighting practical steps for taking this agenda forward. The report has been downloaded 708 times by 655 people. - By March 2017, the Resilience, Partnerships and Beneficiary Feedback WGs will have finalised learning products using funds from the LP budget, as agreed. Principle 2.3: Bond did not run the HealthCheck during the reporting period, as the timing was not appropriate given staff changes. It was agreed at the progress meeting between DFID and Bond on 22 September 2016 that the baseline score for the monitoring pillar in the HealthCheck should be updated as per the January 2016 score. This was 2.89 out of 5, compared to 2.79 when the HealthCheck was last taken in 2013, and slightly lower than the 3.0 score anticipated. The results highlight the need for more systematic monitoring across Bond, including the creation of an organisation-wide MEL framework and embedding a stronger culture of evaluation, reflection and learning. It was agreed Bond would instead use as a measure of organisational effectiveness the introduction of a new project management approach. This was successfully introduced and rolled out across all work areas during 2016, leading to improved cross-team working, better coordination of communications and marketing messages and subsequent referrals of Bond members on to further services from the initial point of engagement. Principle 3	Diversification and innovation Bond grows its unrestricted income by 10% between 1st April and 31st December 2016 Bond develops at least 2 new paid-for or grant-funded services in support of innovation Bond has at least 2 new, additional formal partnerships in place to deliver services to members in a more efficient manner Risk:		Moderate	Impact weighting (%):	20% Key Points - Summary of progress during the nine month extension Principle 3.1: Bond’s unrestricted income from three services that support NGOs’ effectiveness - training, consultancy and recruitment - has grown 44% when comparing December 2015 to December 2016. This is largely due to an increase of consultancy income from £2,400 to £15,000 which includes IATI consultancy and consultancy on programme approaches and frameworks. It also includes IATI courses designed specifically for DFID staff. Bond achieved smaller increases of 13% and 18% in training income and recruitment advertisement fees respectively. The increased training income is due in part to the three new courses offered since April; Commercial Contracting with DFID, Business Model Innovation and Innovation Essentials. It should be noted that during this 9-month period, Bond was also able to attract further funding for their effectiveness work from Comic Relief (£50k). Principle 3.2: Bond developed and delivered three new paid-for or grant-funded services in support of innovation during this period, exceeding this target. This included two programmes of tailored training for the sector that are not being offered elsewhere: Business Model Innovation and Innovation Essentials. The 5-day Business Model Innovation programme was attended by 37 CEOs and senior leaders from 28 diverse member organisations including Oxfam, Mercy Corps, BBC Media Action, Computer Aid and Tree Aid. It generated £61,000 in income and received an average usefulness rating of 7.4 out of 10. The one-day Innovation Essentials course, delivered in partnership with Nesta, was attended by 16 individuals from a range of roles and organisations. It generated £4,100 in income and received an average usefulness rating of 7.3 out of 10. Both programmes are now being developed further for delivery again in 2017. The Future Funding Forum was an initiative aimed at funders interested in supporting a thriving civil society in the Global South. It was funded through grants totalling £26,500 from four funders: Comic Relief, Big Lottery Fund, Baring Foundation and Stars Foundation. The series of seven workshops included a day-long launch event attended by over 50 donors and representatives from civil society, and culminated in a series of briefing papers and a report, The Future of Funding, published in hard copy and on Bond’s website in December, with a total of 258 page views in the first month. Principle 3.3: During the reporting period, Bond agreed a new partnership with Open Data Services Cooperative to provide intensive support to individual organisations as part of Bond’s ‘IATI Boost’ service. Bond have signed partnership agreements with four corporate suppliers - Western Union, SGS Group, CCLA and Buzzacott. These bring dual sustainability benefits a) to Bond, in terms of sponsorship, gifts in kind, conference and online content; and b) to Bond’s members, in terms of access to specialist and technical advice and efficiency savings (e.g. through more cost effective money transfer). Bond’s existing partnership with the UK Alliance developed further over this period, benefiting all sizes of organisation across the UK. Working with Mango, Bond secured more than 20 participants for the next round of the cost benchmarking study. Bond’s partnerships with Civicus, Concord and IFP enable them to join up its activities with platforms in the global north and south in pursuit of the Global Goals. Bond have a number of new arrangements in the pipeline which will be explored further over the coming months. The target of two new partnerships has thus been significantly exceeded.
3. (directly) – UK development NGOs and their EU and international counterparts by strengthening their ability to achieve better outcomes for those they work with or on behalf of.
4. (directly) – 395 UK development NGOs (of which 40% are classified as small). Bond’s target of increasing effectiveness amongst 55% of its members by 2016 would contribute to the better use of £1.36 billion of expenditure.

Bond brings together over 470 organisations in its membership, which has a combined annual expenditure of £5.7 billion and a staff body (in the UK and internationally) of over 75,000 people.[1] It has therefore been well placed to support the UK NGO sector and its partners to coordinate their input to European and international policy processes and to improve their organisational effectiveness.
[1] From Bond’s paper – ‘Financial Trends for UK-based NGOs’, available here - https://www.bond.org.uk/sites/default/files/resource-documents/financial-trends-uk-ingos-0416.pdf

Two thirds of the budget funded Bond’s effectiveness programme, which helps UK-based NGOs to improve their effectiveness and transparency, and subsequently the development outcomes they achieve through their work with partners and beneficiaries. Over 700 organisations (members and non-members from within and outside the UK) accessed the effectiveness programme during the three-year grant timeframe. Outcome targets on effectiveness have been surpassed.

One third of the project budget was used to support Bond’s policy influencing work, with a focus on processes leading up to the adoption of the Global Goals in September 2015 and European policy and practice. Over 150 organisations have engaged with this work and during the programme, 70 influencing activities were facilitated by Bond on the post-2015 agenda and a further 30 on European policy and practice. These have contributed to significant policy change outcomes documented within this report.
Bond has also delivered additional activities not in the original logframe:

- Bond’s funding policy work has delivered the sector consultation on DFID’s Civil Society Partnership Review, work on cost benchmarking and opportunities for DFID to engage with the sector through the Funding Working Group.
- A significant area of new work is Bond’s Futures programme[2]. This supports UK NGOs to innovate and to consider how external trends may affect their work and strategic positioning. Publications and resources include Fast Forward[3], Tomorrow’s World[4] and predictions for 2016[5].
  [2] http://www.bond.org.uk/effectiveness/futures
  [3] https://www.bond.org.uk/resources/fast-forward
  [4] https://www.bond.org.uk/resources/tomorrows-world
  [5] https://www.bond.org.uk/development-predictions-2016
- In October 2014, Bond established the Ebola Response Hub to aid UK NGO coordination and collaboration, which engaged over 120 organisations in the two working groups that were set up. Bond partnered with the Start Network to lead the work, blending their humanitarian expertise with Bond’s networking and coordination expertise.
- Original plans for Bond’s post-2015 work were focused on a purely policy-based approach. As the programme progressed, Bond took on additional public awareness work, leading the action/2015 campaign in the UK. Moving forwards, Bond has established a Bond SDGs group to enable members to work together on policy and campaigning around SDGs implementation. Bond is also working with international partners, including CIVICUS and the International Forum of National NGO Platforms (IFP) to ensure there is an effective global platform for collective action around the goals.

Bond has delivered a high quality and comprehensive programme, implementing ambitious activities, achieving the vast majority of output targets, delivering programme outcomes and responsively supporting the sector in a range of other priority areas as strategically necessary.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages) Focus on lifetime of the Programme

Overall Outcome Assessment:
The external evaluation[6] of this programme (see the Monitoring & Evaluation section for details) shows that the outcomes of this programme have been fully achieved.
[6] https://www.bond.org.uk/sites/default/files/bond-dfid-2013-16-grant-eval-full.pdf

Outcome 1: The programme's target audience effectively and efficiently achieve their own organisational goals and exhibit best practice.

Organisations that have engaged with Bond’s effectiveness programme have seen increases in their ability to achieve their own goals. Bond has exceeded all three outcome targets related to this outcome, which related to changes in a combination of individual practices as a result of applying knowledge, skills or confidence from training and networking, increased organisational transparency and effectiveness.

This achievement reflects investment by Bond and NIDOS[7] in monitoring and gathering feedback from users of their services, and adapting those services in response to build on strengths and address any weak areas identified. Examples of such improvements include offering a new training course on demonstrating the impact of advocacy work,[8] complementing the Evidence Principles[9] with guidance on choosing between evaluation methods[10], improving terms of reference for evaluations[11]; and providing more tailored, actionable recommendations to Transparency Review participants.
[7] NIDOS is the Scottish international development platform that Bond partners with in its effectiveness work
[8] https://www.bond.org.uk/learning/how-change-happens-demonstrating-the-impact-of-your-advocacy
[9] https://www.bond.org.uk/effectiveness/monitoring-and-evaluation#evidence_principles
[10] https://www.bond.org.uk/data/files/Impact_Evaluation_Guide_0515.pdf
[11] https://www.bond.org.uk/resources/bond-tips-evaluation-terms-reference

1,902 individuals (target: 1,831) have applied improved knowledge, skills and confidence gained from Bond training, networking and events to improve their practice in a wide range of areas, from monitoring, evaluation and learning, to beneficiary engagement, to advocacy and fundraising.

111 Bond and NIDOS member organisations (target: 80) have improved their transparency in a variety of ways, including adopting open information policies, and publishing more information on their grant activities to IATI and/ or on their websites.

110 Bond and NIDOS members have increased their effectiveness (target: 97), particularly through increasing the quality of the evidence they generate with the help of the Evidence Principles and associated resources on evaluation; using the Health Check to inform strategic investments in identified areas of organisational weakness; and using data from the Cost Benchmarking Survey to improve budgeting and recovery of overheads and indirect costs.

Importantly for future efforts at improving NGO effectiveness, Bond’s work has generated substantial insights and learning about what works and what does not under different organisational circumstances. Documenting and promoting these lessons will be an important focus for the April – December 2016 extension period to this programme.

Outcome 2: Target audience engages with and influences EU development policy and the post-2015 agenda.

There has been substantial target audience engagement with EU development policy and the post-2015 agenda. This has had a significant influence on both policy agendas in which Bond’s convening role has made a significant and unique contribution. Bond has met all of its outcome targets in this area.

Bond’s use of participatory approaches with its members and provision of a neutral platform has maximised the engagement of target audiences. Bond has enabled participants who would not otherwise have been able to contribute (such as smaller organisations with limited staff capacity) to engage with and influence both policy agendas. Maintaining good relationships with decision makers has enabled Bond to enhance the impact of this collective engagement. Bond has also successfully used its ability to bridge policy and campaigning work to enable the participation of members wanting to campaign on the post-2015 agenda, involving 102 organisations. This has increased the number of members engaged in the agenda, and the depth of their involvement and influence. As part of the programme, Bond members and other NGOs have engaged with relevant policymakers on numerous occasions. Bond has also effectively engaged target audiences beyond its members in influencing work, including the UK Gender and Development Network, other national platforms in Europe, CONCORD, and globally with other platforms’ participation in action/2015 through the IFP.

On EU development policy, 30 influencing opportunities and engagements were developed during the programme, including a roundtable meeting between members and senior staff from EU institutions and member states to discuss a draft Gender Action Plan. Positive feedback has been received by policymakers on the role Bond has played in EU work, and decision makers actively solicited Bond’s collective input, for example, to support the EU’s re-commitment to the 0.7% gross national income (GNI) aid spending target. EU development policies which Bond and its members have worked on reflect a number of key positions of UK NGOs and European partners. Examples include the EU recommitment to the 0.7% aid spending target[12], and the strengthened references to fulfilling human rights for women and girls in the EU Gender Action Plan II (applying to all EU external action and policy) compared to the previous Gender Action Plan[13].
[12] http://www.consilium.europa.eu/en/press/press-releases/2015/05/26-fac-dev-council-conclusions-global-partnership/
[13] http://www.consilium.europa.eu/en/press/press-releases/2015/10/26-fac-conclusions-gender-development/

On the post-2015 agenda there have been 86 influencing activities throughout the programme. This includes seven roundtables with DFID staff, three meetings between CSOs and the UK delegation during the international Global Goals negotiations, as well as collective written inputs and responses to the Global Goals negotiation and implementation. It is clear that the ability of the audience to engage in this way at different levels through the three years of the programme, and the role that Bond has played in supporting this, has enhanced collective influence on Agenda 2030.[14]
[14] http://www.beyond2015.org/sites/default/files/Review%20of%20Final%20Post-2015%20outcome%20doc%20and%20Beyond%202015%20positions%5B2%5D.pdf

Overall Output Score and Description: A+
Across the programme, Bond has successfully delivered against milestones, and in the majority of cases has surpassed targets. In the final year of the programme, Bond has achieved a score of A+ on five outputs and an A for the remaining output. This is testament to Bond’s capacity and expertise in the areas of work funded by this grant and provision of relevant services to meet demand from its members.

Areas of particular success are in the volume of participants and the results of their engagement in networking services and events as part of Bond’s effectiveness work (output indicators 1.1.3 and 1.1.4). Bond has consistently exceeded targets in this area: in the programme’s third year the percentage of participants reporting an increase in their personal knowledge and confidence as a result of their attendance in networking and events was 92%, against a target of 85%.

There has also been particular success in the number of joint influencing activities delivered as part of Bond’s work on the post-2015 agenda. In the final year of the programme, capitalising on the opportunity of numerous UN meetings and the summit itself, 24 influencing activities were delivered against the target of 7 (output indicator 2.2.2).

Lessons and how these have been shared
Bond has learnt a number of lessons about its work on this programme. These lessons have been shared throughout the programme, informally through Bond’s working groups and to make course corrections as necessary. The external evaluation[15] will be shared on Bond’s website and this review will be published to further disseminate these learnings.
[15] https://www.bond.org.uk/sites/default/files/bond-dfid-2013-16-grant-eval-full.pdf

In terms of Bond’s overall work, feedback from Bond members consistently shows the value they place on the coordination, convening and networking opportunities offered by Bond. This is the unique value of Bond and is an important pointer to the continued relevance and added value of such a network organisation for UK international development NGOs.

As part of a major review to develop Bond’s 2016-21 strategy, which took place during the programme period, input was gathered from across Bond’s network through interviews, surveys and events. Some of the main lessons and feedback from this process were:

- Bond’s membership appreciates it when Bond plays a challenging or ‘critical friend’ role, introducing diverse perspectives into debate.
- Bond's members are diverse and value the wide array of services and roles played by Bond, though it is a challenge for Bond to accommodate and balance these membership demands. Bond’s priorities are determined by ongoing feedback and more formal input opportunities. Bond’s general approach is to provide a constant level of service rather than individually tailored services, in order to best provide for the totality of the membership.
- Individuals within Bond’s member organisations often have only a partial view of Bond’s work.
- Bond’s initial forays into a more humanitarian focus, through the Ebola Hub, have been received positively by members.
- In the rapidly changing operating context, it is recommended that Bond further develop its relationships beyond NGOs and beyond the UK to ensure its relevance and sustainability.

These lessons heavily informed the development of Bond’s 2016-2021 strategy[16], which has been shared on Bond’s website.
[16] https://www.bond.org.uk/sites/default/files/resource-documents/bond_strategy_2016-21.pdf

Many of the more specific lessons learnt during the programme have been documented in Bond’s effectiveness case study research, outcomes survey and independent evaluation[17], such as the importance of engaging NGO leadership on effectiveness, and the limits to promoting transparency by making it a contractual requirement. These lessons will be documented, shared and promoted in accessible ways during the upcoming grant extension period (see Output 1.4).
[17] https://www.bond.org.uk/sites/default/files/bond-dfid-2013-16-grant-eval-full.pdf

On the effectiveness and transparency side of the programme (Outcome 1), the key lessons which would be deployed in any re-design or future programmes are:

- Providing more tailored, actionable recommendations from benchmarking tools like the Transparency Review increases the likelihood that use of such tools will prompt organisational change.
- Taking time to identify the right people to engage within organisations and the right time to influence change (for example during strategic review periods) enhances the likelihood that use of the Health Check will prompt organisational change.
- Focusing on the potential uses of open data by NGOs (including of their own data) is a more compelling way of encouraging greater publishing of data to IATI than either making a values-based case or by funders making it a contractual requirement. If the programme were re-designed, this would be prioritised at an earlier stage. Bond is promoting this lesson to other national platforms and governments, and more widely as a member of the new Governing Board of IATI.
- In organisations which have accessed Bond or NIDOS services, but in which there is no subsequent change in effectiveness and transparency, there is often either a lack of sufficient senior management support for and focus on changes in effectiveness and transparency, and/ or there are insufficient resourcing and incentives provided by funders.
- To further improve the quality of evaluations, their publication by NGOs, and their use within organisations, greater focus is needed on early engagement on budgeting and design at the start of projects; improvements in the commissioning and management process for evaluations; accessible communication of their findings, and better processes for learning and ‘uptake’ to inform action.
- In the inter-relationship between learning, accountability and resources, intermediaries such as Bond can help to improve ‘the system’ by working with both NGOs and funders.
- More direct engagement between NGOs and funders can increase mutual understanding around issues such as operational constraints and political imperatives. This can help avoid funder disappointment with implementation of their policies including around IATI and transparency and Payment by Results.

In considering the advocacy and lobbying element of the programme (Outcome 2) and thinking about programme design going forward, the main lessons are:

- The shift to a more strategic approach within the Bond Beyond 2015 UK group, with a focus on priority areas, increased the potential for impact. This focus on sustainability and inequality provided a strong common agenda.
- Parliamentary expertise is a crucial accompaniment to policy expertise. The addition of a parliamentary post at Bond during the programme has allowed the organisation and its members to greater capitalise on influencing opportunities. Political analysis being available earlier in the grant period would have been beneficial.
- Communication between groups is key to success, and Bond successfully facilitated communication between the Beyond 2015 UK group and other Bond groups, including the Financing for Development group
- The role adopted by Bond in its policy work – as a convener rather than a manager – is positively received by members. This approach has allowed other organisations to lead on specific issues, creating opportunities for broad engagement.
- If the programme were re-designed, Bond would consider how to further build in proactively seeking feedback on attribution of impact of its policy work from relevant stakeholders, and more systematically recording feedback received.

## C: DETAILED OUTPUT SCORING (1 page per output) This section should provide a summary of progress in Year 3 only, and should be repeated for each output.

Output Title	Bond supports its target audience in gaining the skills, knowledge and tools that enable them to make improvements in their practice.
Output number per LF		Output 1.1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Year 3)	Progress
1.1.1 # of individual participants in Bond’s training services (including open training and in-house training).	1,210 / (annual target)	1,138 (811 female (71%), 327 male (29%))
1.1.2 Of those participating in training, # and % reporting an increase in personal knowledge and confidence as a result	97% / (annual target)	98.5%
1.1.3 # of individual active participants in Bond’s networking services and events (specifically Funding, Transparency and Monitoring, Evaluation and Learning and Small NGO Working Groups, and related events and Bond Conference sessions).	500 / (annual target)	765 (524 (69%) female, 241 (31%) male)
1.1.4 Of those participating in networking and events, # and % reporting an increase in personal knowledge and confidence as a result	85% / (annual target)	92%

Key Points
The combination of training and collective learning through Bond’s working groups and events was successful overall in building NGO staff knowledge, confidence and skills on a range of issues relating to effectiveness, transparency, advocacy and funding.

Bond achieved 94% of the target number of training participants. There was ongoing growth in participation in bespoke, in-house training services, but it continued to be a challenge to achieve growth in open training course attendees. The quality and relevance of Bond’s offer remains high, and the price is competitive, but the availability of free resources online and informal learning opportunities poses a long-term challenge to growth in open training courses. Bond is seeking resources to invest in greater provision of online and blended online and in-person learning opportunities for members.

98.5% of participants in training reported a resulting increase in their personal knowledge and confidence. Some examples of applications of learning reported by training participants include:

- Informing a new or revised organisation-level monitoring, evaluation and learning (MEL) framework (All We Can and Cyan International);
- Introducing new procedures for managing EC grants (Near East Foundation; Christian Aid);
- Developing an advocacy guide book for local NGO partners (Y Care International).

DFID’s new learning strategy has focused on the theme of enhancing learning practice through “connections [between people], not collections [of documents]”. Bond’s working groups embody this principle, and this year they continued to attract good participation and enable joint learning. The specific working groups whose work directly relates to this programme’s objectives (MEL, Transparency, Funding, EC Funding and Commercial Contracts) typically met in person 2-3 times during the year, with an average of 35 participants per meeting. (The Small NGOs group – also listed in the logframe – did not meet in person last year.) These meetings were complemented by regular sharing of insights, resources and discussions on the online My Bond platform.

The use of standard monitoring and feedback forms increased, helping group chairs learn more about what sorts of formats and content were most valued by participants. Feedback on “usefulness” to participants and increases in their knowledge and confidence remained high and above target. However, the success of the groups and increased membership from diverse organisations meant it remained a challenge to satisfy the needs and expectations of all group members all of the time.

Although not captured in the logframe indicators, additional key developments this year were the increased co-hosting of events by Bond and the PPA Learning Partnership (LP), including on adaptive programming, and the decision for the LP to be hosted by Bond within the My Bond online platform from April 2016. Building on recommendations from the 2014/15 fund-level evaluation of PPAs, Bond will focus on enhancing two aspects at higher levels of the LP’s theory of change: better dissemination of PPA LP learning outputs to a wider audience, and engagement of non PPA agencies in groups.

Bond hosted another successful annual conference this year, expanding it to a two-day event for the first time. With nearly 1,000 participants, it constitutes the biggest NGO-hosted gathering of development practitioners in Europe. High-profile speakers led plenary sessions, and 36 parallel sessions discussed current issues, hearing from a wide range of experts from within and beyond the sector.

Summary of responses to issues raised in previous annual reviews (where relevant)
Bond made a number of changes to its web content on training courses to clarify the level of existing participant knowledge and capacity assumed, and what participants can expect to learn. Despite this, feedback about misaligned expectations was still received from a minority of trainees. Further prior engagement with prospective participants may be helpful, but the costs may exceed the benefits.

Bond has used feedback from its annual outcomes survey and from the case studies explored in the INTRAC research to improve its delivery and practice around training, networking services and events.

In the past year, some efforts have been made to establish sub-groups within larger working groups, including one on Organisational MEL systems. A workspace on Adaptive Development proved useful for sharing resources during and after the series of joint Bond and PPA LP events held on that topic. It would however require greater funding and staff resources to sustain more sub-groups.

Despite persistent efforts, Bond failed to secure external funding for the proposed KoLab initiative (developed with Oxfam, NESTA and the Young Foundation) to support small NGOs. The funders approached felt that the initiative was too risky and the cost-per-organisation too high.
Recommendations for future programmes
- Continue to build on the success of Bond working groups, providing opportunities for a wider range of NGO staff to participate, and ensuring groups are relevant to priority issues, for example relating content to the Sustainable Development Goals and Leave No One Behind.
- Take over hosting of the PPA LP, addressing previous evaluation recommendations, seeking to sustain their usefulness and productivity beyond the lifetime of the PPA funding mechanism, and ensuring efficient and effective DFID and CSO engagement.
- Seek investment to explore methods for widening participation in groups to southern NGO staff.
- Seek investment to explore online learning components within the open training programme.

Output Title	Bond and NIDOS support their target audiences to become more transparent in the publication of information on their activities and results
Output number per LF		Output 1.2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Year 3)	Progress
1.2.1 # of UK-based organisations publishing data to the IATI standard to at least DFID minimum requirements, supported by Bond/ NIDOS	170 / (cumulative target: 145 + 25 new orgs)	185 / (170 from year 2, plus 15 new) / (Additionally, 58 non-UK organisations supported to publish)
1.2.2 # and % of UK-based organisations publishing data to the IATI Standard that are going beyond the DFID minimum requirements (i.e. publishing to more than just the basic fields and/ or more than their DFID funding)	25% (42 orgs) go beyond minimum / (cumulative target)	30% (59 organisations)
1.2.3 # of Bond and NIDOS members participating in an annual Transparency Review, measuring the coverage of NGO data on activities and results published to IATI and/ or through their own websites	50 orgs in second completed survey; viability of sustaining the Transparency Review investigated	49 organisations in second survey. / Viability of making the Review a paid-for service examined, and found to be unsuccessful.
1.2.4 # of supporting resources developed by Bond to help organisations improve scores in the Transparency Review	2 resources developed / (cumulative target)	2 resources developed / (Guidance on developing Open Information Policies[18]; and reporting on publishing evaluations[19])
1.2.5 # of UK-based INGOs demonstrating use of IATI data to support their effectiveness and transparency	42 (cumulative target)	43
1.2.6 Bond’s transparency support and influencing contributes to increased transparency by organisations that are not members of Bond/ NIDOS [qualitative milestones re IATI Civil Society Organisation Working Group (CSO WG), CSO guidance work with Development Initiatives (DI), commercial suppliers, open philanthropy, other Platforms]	Bond supports 4 other national platforms with guidance on IATI and transparency, and publishes 2 publications on improving transparency (cumulative target)	4 platforms supported / (US, Dutch, 2 x Belgian) / 3 publications produced (2 x Transparency Review cohort reports[20]; and discussion paper on “Publishing Results to IATI[21]”) / Bond appointed to new governing board of IATI, and co-chaired predecessor “Members Advisory Group”
[18] https://www.bond.org.uk/effectiveness/open-information-and-ngos
[19] https://www.bond.org.uk/sites/default/files/resource-documents/making-evaluations-work-harder-1215_0.pdf
[20] https://www.bond.org.uk/resources/transparency-review-2015 and https://www.bond.org.uk/data/files/publications/Transparency_Review_250215.pdf
[21] https://www.bond.org.uk/sites/default/files/resource-documents/publishing-results-to-iati-0316.pdf

Key Points
Bond continued to successfully support NGOs to publish information to IATI. Having previously supported most UK NGOs with DFID grants to publish, more non-UK NGOs were supported in year three. This included implementing partners of DFID grantees, helping to enhance traceability of funds. There remained limited interest among NGOs without DFID funding to publish voluntarily to IATI, perhaps reflecting the resources required relative to the limited evidence of the use of published data.

The quality of Bond’s IATI training improved by increasing the emphasis on how IATI data could be used by NGOs for business intelligence and identification of prospective partners (including via DFID's DevTracker). Progress externally on developing applications for IATI data remained slow, and Bond developed its own Open Data Hub[22] and did preliminary work on visualisations of IATI data, in the form of maps. Bond took an active role in the governance of IATI as a member of the Governing Board to help increase pressure on the Secretariat to dedicate more effort to utilisation and quality of published data.
[22] https://www.bond.org.uk/effectiveness/open-data

Having supported a total of 243 organisations to publish to IATI – 54% of the 450 organisations globally publishing as of April 2016 – Bond increased its emphasis on sharing experience and learning with other national platforms and governments. With the Dutch government also requiring their grantees to publish to IATI and the Belgian government considering doing so, Bond worked with DFID to convene a meeting between those governments to discuss potential for harmonising requirements. Bond shared lessons learned on how best to support NGO publishing with the relevant national platforms. Bond worked with US
platform InterAction to help improve compatibility of their NGO Aid Map initiative[23] with IATI data. And, drawing together learning from its effectiveness and transparency work, Bond published a discussion paper[24] suggesting how IATI’s “results” module could be improved to ensure that any publication of results supports better learning and accountability.
[23] https://ngoaidmap.org/
[24] https://www.bond.org.uk/resources/publishing-results-to-iati

Bond carried out a second cohort of the Transparency Review, examining the openness of NGO websites. Reports for users were produced much faster than in the first cohort, with more personalised and action-oriented recommendations. This resulted in much improved feedback from users. 67% of users reported making more information available on their websites as a result. As in the first review, one of the lowest-scoring areas was publication of evaluations and results. Bond commissioned research to investigate reasons for this[25], and found that the main barriers were: concerns about the quality of evaluations and results information, scepticism about whether audiences would be interested in results information, and insufficient resources to put such information into more user-friendly formats.
[25] Published as “Making Evaluations Work Harder for International Development” - https://www.bond.org.uk/resources/making-evaluations-work-harder

Unfortunately, in spite of the popularity of the Transparency Review, an attempt to make it financially sustainable as a paid-for service in December 2015 was unsuccessful. Too few organisations were willing to pay, with feedback suggesting online transparency was not high enough a priority for many NGOs to pay for the service.

Summary of responses to issues raised in previous annual reviews (where relevant)
Previous issues around promoting the usefulness of IATI publishing, improving the Transparency Review service and investigating the reasons for limited publishing of results data are addressed above.

Recommendations for future programmes
- There is a need to promote a norm of greater transparency among INGOs; greater evidence of its value relative to the costs and potential risks is key to the “business case” for publishing.
- Pressure from funders should be combined with technical support to improve IATI data quality.
- There are real questions about the usefulness for either accountability or learning of using the IATI results module currently, but Bond has given recommendations for clear practical improvements.
- The potential and practicality of IATI publishing to reduce the burden of financial and/or narrative reporting to funders should be explored with both NGOs and funders.
- Globally, there is a need for catalytic investment in resources that would provide practical applications for the use of IATI data, and to support the infrastructure necessary for easy manipulation of IATI data.
- In the absence of a willingness to pay for the Transparency Review from NGOs, Bond should continue to seek grant funding for this popular and effective initiative.

Output Title	Bond develops and provides new effectiveness tools and services that are responsive to evolving needs of members, within a sustainable business model
Output number per LF		Output 1.3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.3.1 # of new tools/ resources/ services to improve effectiveness developed by Bond in response to evolving needs of target audience (e.g. on Value for Money (VfM), beneficiary feedback, evidence-sharing, organisational governance, Futures) that Bond members describe as useful	20 (cumulative target: 15 from years 1 and 2, plus 5 new)	22 (17 cumulative and 5 new[26])
1.3.2 A robust business model is in place for UK effectiveness services to ensure they are financially sustainable and strategically placed to further effectiveness and transparency within international development	Net annual income target for Effectiveness target of £120k met	£121,755 achieved
1.3.3 Bond facilitates consultation and engagement by members with the DFID Civil Society & Partnership Review	5 twitterchats / 2 face-to-face meetings / 1 consolidated submission facilitated by Bond	5 twitterchats / 2 face-to-face meetings / 1 consolidated submission facilitated by Bond[27]
[26] The 5 new are: Health Check Influencing Resources: https://www.bond.org.uk/healthcheck-resources; Impact Evaluation: A Guide for Commissioners and Managers: https://www.bond.org.uk/data/files/Impact_Evaluation_Guide_0515.pdf; Evaluation Terms of Reference Top Tips: https://www.bond.org.uk/resources/bond-tips-evaluation-terms-reference; Cost Recovery: What it Means for CSOs: https://www.bond.org.uk/sites/default/files/resource-documents/cost-recovery-0216.pdf and; The Health Check Big Picture Report: https://www.bond.org.uk/resources/the-health-check-big-picture-2016
[27] https://www.bond.org.uk/news/dfid-review

Key Points
Bond continued to adapt its effectiveness offer to meet emerging needs and to address learning about how to increase the effectiveness of its existing tools and services. It has proved challenging to do this in a way that is self-financing. The context of relatively flat or declining funding for the majority of Bond’s members (particularly small and medium-sized ones)[28], and the desire of many grant funders to focus on frontline organisations rather than network bodies like Bond are contributing factors.
[28] https://www.bond.org.uk/sites/default/files/resource-documents/financial-trends-uk-ingos-0416.pdf

To provide follow-on support for users of the Health Check (Bond’s organisational capacity assessment tool), Bond collated new key resources to support advocacy and influencing, which is a low-scoring area for many NGOs. Other new resources include the production of a second “Big Picture” report[29], collating results from all Health Check users for a sector-level view of strengths and weaknesses.
[29] https://www.bond.org.uk/resources/the-health-check-big-picture-2016

To complement the Evidence Principles (which help assess the quality of evidence), new resources focused on addressing key areas of weak evaluation practice, i.e. understanding the appropriateness of different evaluation methods, and improving evaluation commissioning practice. The former was commissioned jointly by the Cross Funders' MEL group of DFID, Big Lottery Fund and Comic Relief. Two further related pieces of work were started this year: a pilot peer review system for quality assurance of evaluations, and the development of a practical tool for choosing appropriate evaluation methods.

Bond also introduced a new cost-benchmarking survey in partnership with MANGO, which helps NGOs understand their total overheads and indirect costs, and to compare them to amounts recovered in grants and contracts from funders. This is important both for the financial sustainability of NGOs, and for clearer communication with funders and supporters about the reality of project and programme costs.

The growth in Bond’s effectiveness income over the past year was substantial, but below the ambitious target set. Growth was driven by a combination of in-house training, consultancy services provided by Bond staff, and growth in Bond’s membership income (a proportion of which is attributable to effectiveness work). However, there was not the expected market for either the Transparency Review (see Output 1.2 above) or for a new paid-for service to help organisations wishing to publish large volumes of data to IATI to integrate this publishing with existing finance and grant management systems. Although used effectively by Plan UK and ActionAid, Bond found the market for the latter to be limited.

A new logframe indicator was added (1.3.3) in year three to reflect the work Bond took on in supporting civil society engagement in DFID’s CSPR. Bond co-hosted five twitterchats with DFID on the main CSPR themes; organised two consultation events; and collated a consolidated submission on behalf of NGOs. Bond enabled high quality input to be provided to DFID in an efficient manner, helping maximise the volume and diversity of agencies and individuals who contributed to informing the review findings.

Summary of responses to issues raised in previous annual reviews (where relevant)
To facilitate deeper engagement with members without requiring a significant increase in resources, Bond focused on strengthening the effectiveness of services through developing complementary resources (see above) and improving specificity of recommendations and actions on other tools, for example the Transparency Review. To ensure ongoing awareness of those services, Bond has continued to market them through Bond’s own channels, with targets for uptake met or exceeded.

Paid-for, bespoke, transparency services were explored in the last year of the programme, but proved to have a limited market. Consultancy services using associates were not found to be sufficiently profitable. Consultancy by Bond staff yields greater financial returns, but with small numbers of staff, further upfront investment – for which Bond currently lacks capital - would be needed to balance the provision of bespoke paid-for services with provision of and support for existing generic effectiveness tools.

The Ebola Hub was phased out over the year as the need declined. Bond captured learning from the experience in a review paper[30], and built on this for establishing a Syria Hub and Humanitarian Hub.
[30] Unpublished, but shared directly with DFID staff

With the recruitment of a full-time Head of Innovation and Foresight in July 2015, Bond was able to develop its Futures Strategy, resourced through the DFID grant and through income and grants earned for individual components of the Futures offer. Bond published “Predictions for 2016”[31] in early January and developed a number of outputs from April 2016, outside this reporting period. These include a review of financial trends in the sector[32]; an introduction to social innovation for NGOs[33]; a new Innovation Audit service[34], and a Business Models Innovation training programme[35]. This work area and these resources are of greater focus in the Results Framework for the grant extension period.
[31] https://www.bond.org.uk/development-predictions-2016
[32] https://www.bond.org.uk/sites/default/files/resource-documents/financial-trends-uk-ingos-0416.pdf
[33] https://www.bond.org.uk/sites/default/files/resource-documents/introduction-to-social-innovation-0416.pdf
[34] https://www.bond.org.uk/effectiveness/innovation-audit
[35] https://www.bond.org.uk/learning/business-model-innovation-for-ngos

Recommendations for future programmes
- Build on the gathering momentum of the Futures programme to help INGOs reflect on and adapt to a changing external environment, both in terms of programme- and business-model innovation.
- Continue to adapt services to accommodate a changing operating environment, new demands for innovation and partnership, and a changing workforce.
- Consider the balance between grant-funded work, paid-for services and generation of unrestricted income (e.g. membership fees and advertising) in funding effectiveness and transparency services. Grant funding may be more suited to the public-goods nature of much of Bond’s most distinctive work such as brokering engagement between funders and NGOs and convening learning groups. However, to appeal to more funders, Bond may need to broaden its offer beyond its current dominant focus on UK NGOs, already considered under the “internationalisation” strand of its new strategy.

Output Title	Bond develops and shares improved knowledge for the sector on how organisational effectiveness is affected by the provision and uptake of effectiveness tools and services
Output number per LF		Output 1.4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Year 3)	Progress
1.4.1 Bond conducts a research programme incorporating at least 8 NGO case studies and 3 overview reports tracking how the use of Bond’s and NIDOS’ different effectiveness tools and services influences learning and changes in practice over time in different types of NGOs, including consideration of impact on the final beneficiary (aligned with DFID and members’ strategic priorities)	Data on outcomes of service usage continues to be generated to produce key learning about the impact of the effectiveness tools/ services on practice, so also helping to further improve the tools and their use; final report produced.	3rd outcomes survey completed. / INTRAC case study research on 8 NGOs and 2 mini-case studies finalised. / External evaluation completed.
1.4.2 Number of Bond and NIDOS members using 1 or more of the Bond or NIDOS effectiveness tools or services, disaggregated by organisational size.	250 (of whom 75 are small; cumulative target; 200 plus 50 new users)	293 (of whom 114 are small (annual income <£500k)
1.4.3 Of those using tools or services each year, % reporting that they found the tools or services useful (i.e. score 7 or more out of 10 in feedback surveys)	90% of recorded Year 3 users (annual target)	84% of recorded Year 3 users
1.4.4 Number of other organisations or platforms using or recommending usage of 1 or more of the Bond or NIDOS effectiveness tools or services	110 (cumulative)	136

Key Points
Bond has generated substantial knowledge over the lifetime of this grant on how effectiveness is affected by the provision and uptake of tools and services. In year three, Bond has gathered a wealth of data on its work through its outcomes survey, the two-year INTRAC case study research, external evaluation, and the analysis of data carried out in reports such as the Health Check Big Picture and Transparency Review Cohort Report. Bond has made use of the data and learning during the programme, resulting in surpassing all outcome targets. It has been agreed that Bond will focus some of its efforts during the grant extension period to disseminating these lessons in public, accessible forms.

Use of Bond’s and NIDOS’ effectiveness and transparency services continued to increase in the final year of the programme. Interestingly, 17 organisations formerly counted under output 1.4.4 joined Bond this year, and thus were added instead to output 1.4.1. This suggests that use of Bond’s effectiveness services can help encourage organisations to join Bond.

The number of small NGOs (with annual income of less than £500,000) using effectiveness services continued to increase. NIDOS’ services, IATI support, the Transparency Review and the Health Check were the most popular services for small NGOs. This may reflect increased awareness among that group of services and more suitable offers to small NGOs, e.g. the Transparency Review.

The percentage of effectiveness service users reporting that they found the services useful increased from 78% in year two to 84% in year three. Although falling short of the ambitious target of 90%, Bond succeeded in raising its performance on the associated outcome indicator relating to effecting organisational change. Areas for improvement in the usefulness of specific services include:
- Slow delivery of results from the pilot Cost Benchmarking Survey;
- Meeting diverse expectations of users of training and the MEL Working Group;
- Sustaining momentum in the Commercial Contracts working group after a change in the chair role.

Summary of responses to issues raised in previous annual reviews (where relevant)
The scores for the % of organisations reporting “some” or “systematic” organisational change as a result of using Bond services increased for all nine services covered by the outcomes survey in the past year, reflecting the effort made by Bond to respond to earlier feedback.

Greater depth of engagement with service users was achieved through the introduction of new services and resources, mentioned above, and through improvement in the quality of some existing services like the Transparency Review and IATI publishing support.

Recommendations for future programmes
Bond’s effectiveness work has supported over 400 organisations over the three years of the programme (over 700 when training is included), and learning suggests that changes in individual organisations are highly varied and often small-scale. As an intermediary and membership-based organisation, Bond’s key choice in a resource-constrained context is between continuing to support “broad but shallow” change, or to try to achieve “narrow but deep” change. High specialisation is unlikely to be appropriate for Bond, but it may perhaps benefit in the future from focusing its effectiveness efforts on a select number of issues targeting specific segments of its membership where it can add most value.

 Future programmes should incorporate these lessons on what works in improving NGO effectiveness:
- Engage with funders to harness the value of donor resources and pressure to effect change, while ensuring that NGO operational realities and insights inform those donor policies;
- Seek to identify where NGO leadership on effectiveness and learning provides the most fertile ground for use of Bond support, while seeking to support other NGO leaders on how they can create a better enabling environment for improved effectiveness;
- Ensure that a compelling business case and rationale is made for efforts to improve effectiveness and transparency: there are many potential areas for improvement in NGOs compared to the limited resources and “bandwidth” for organisational change initiatives;
- Examine opportunities for extending the reach of Bond’s services to southern NGOs, e.g. through partnership with southern platforms, CIVICUS and the International Federation of Platforms;
- Seek opportunities to use learning about effectiveness and transparency to inform multi-disciplinary partnerships, and NGOs’ role in them.

Output Title	Bond supports its target audience to effectively engage with and influence European development policy and practice
Output number per LF	Output 2.1	Output Score	A+
Risk:	Moderate	Impact weighting (%):	25%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Year 3)	Progress
2.1.1: Collective UK and pan-European NGO action(s) to support Member States to move towards the 0.7% aid target and ensure the new Multiannual Financial Framework (MFF) includes adequate finance and instruments for aid and development.	NGOs publish annual reports and deliver influencing activities that track and push the EU and Member States to delivery their aid quantity and quality commitments: / Annual AidWatch report, London and Brussels launch events, capital-level actions. / NGO responses to May 2015 and November FAC 2015 (letters, briefings, meeting with EU officials etc.) / Briefing papers on any new financing for development commitments made by EU Member States following 2015 0.7% target.	AidWatch Report 2015 “Looking to the Future, Don’t Forget the Past – Aid Beyond 2015”[36] published. / Soft launch with one small event in Brussels and in the media (delays due to Brussels security alert), EU CSO summit on current trends on aid with over 100 participants. / Engagement around the EU Foreign Affairs Councils on 26 May with two briefing papers on FFD and aid; 26 Oct with 3 briefing papers on Global Goals implementation, refugee costs and migration, and Gender Action Plan; informal engagement around the informal FAC 10 December with inputs on the EYD, ODA and Global Goals implementation. / Policy briefing paper on aid quality and quantity[37] ahead of the 26 May FAC. Bond also initiated an EU-wide action to push for an EU 0.7% recommitment, including joint media and influencing and twitter action.
[36] https://www.bond.org.uk/resources/aidwatch-2015
[37] http://www.concord.se/wp-content/uploads/CONCORD-AW-Paper-on-0.7.pdf

2.1.2: Collective UK and pan-European NGO action(s) to ensure that aid effectiveness remains a core focus of the EU’s approach to aid and development.	At least 2 events and activities that convene key EU policymakers and NGOs / (annual target)	3 events and activities on development effectiveness around the Third FFD conference, convening NGOs and key decision makers including the EU. / 14 meetings and activities convening EU policymakers, MEPs and NGOs around the Third FFD conference, which covered aid quality and quantity. / Engagement to influence the EU position around the OECD DAC HLM in Feb 2016, convening UK and EU CSOs to influence member states and the OECD DAC - via briefing papers, meetings, media and social media actions and an online petition across Europe (signed by more than 115,000 people by 13/04/16).
2.1.3. Bond's target audience contributes to European Commission consultations on European policy and practice.	At least two collective UK NGO contributions to reviews or discussions of policy submitted by Bond. These might include submissions to policy consultations, reviews, enquires, dialogues, and engagement with the new Commission and International and International Development Commissioner and key UK MEPs. (annual target)	5 collective UK NGO activities and events on European Development policy, and the Global Goals (2 submissions to the EC consultation and FAC on the Gender Action Plan, 3 events with high-level participation such as the Development Commissioner Mimica or EEAS Gender Adviser). / Continuous engagement with around 10 UK MEPs (which included 1 event, 3 social media actions and meetings).

Key Points
Bond has continued to convene its target audience (members and other organisations) to engage with and influence EU development policy over the past year, resulting in significant impact. Bond has worked with members to further develop the strategic focus of this activity, and achieve more targeted member participation. As well as achieving logframe milestones, Bond has successfully achieved progress on the targets for this area of the programme, adapting its focus in response to political opportunity.

Bond has continued to work with the European Policy Group (EPG) of 170 members in the third year of the programme, during which time the group’s strategic focus has been further enhanced. Bond built on previous improvements to develop clearer aims for the EPG, with an agreed annual workplan, workstreams and a joint influencing strategy. This resulted in increased participation and deeper level engagement, for example, increased strategic influencing and input from the steering group (which was set up in the second year of the programme). The EPG sub-groups were informed by the wider group, developed activities on specific issues and fed back to the wider EPG on their expert issues.

In year three, the group focused on:
- Influencing an EU aid recommitment;
- Influencing the new EU Gender Action Plan;
- Contributing to a strong EU position on Financing for Development (FFD) and the Global Goals, and;
- Enabling more strategic outreach to achieve those objectives, including by targeting specific MEPs and European institution staff. This included continuous and increased communication, such as engagement around the themes of the European Year for Development. Given the strategic yet broad choice of issues, and professionalisation of working structures, members appreciated the stronger collective influencing approach, combined with the opportunity to bring in their expertise and specific focus areas.

Bond effectively developed and maintained relationships with key officials, and extended its reach with high level targets, for instance conducting two events with high-level stakeholders such as the Development Commissioner, the newly appointed European External Action Service (EEAS) Gender Adviser, senior representatives from the EU Presidencies, MEPs and UK government officials. For instance, on a high-level roundtable ahead of the final EU Gender Action Plan, one EPG member commented that ‘The roundtable meeting with the EEAS Principal Adviser on Gender was very well planned, timely and well executed – it was a great opportunity to understand this new role and a real achievement for Bond’. This enabled members who often work on specific issues to access officials and engage in a policy agenda which they would not have been able to do otherwise. Thanks to this opportunity to develop relationships, several members such as Water Aid, Helpage International, VSO and Christian Aid are continuing to engage on implementation of the EU Gender Action Plan.

As well as working with its own members and delivering more than 20 events and activities over the programme, Bond has also increasingly partnered with other stakeholders to achieve its objectives. Bond has strengthened its links to CONCORD to influence EU-based stakeholders more effectively and has partnered with National Platforms directly, for example to push for an EU aid recommitment, or reached out to other CSO networks. An example of Bond’s increased impact within CONCORD is Bond’s role across Europe ahead of the Third Financing for Development (FFD) Conference. As part of CONCORD’s FFD group, Bond took a leadership role in European civil society advocacy on international public financing in the run-up to the Conference in Addis Ababa, a crucial milestone in development finance and effectiveness. Bond generated joint influencing strategies, messages and activities on aid quality and quantity. In total, Bond convened and contributed to 14 influencing activities targeting the EU Institutions and Member States around the EU’s positions on international public financing for the FFD conference. This made both CONCORD and Bond, including its members, influential contacts for FFD officials prior to and during the conference.

Another key success, testifying to the increasingly influential role Bond has taken on across Europe and towards National Platforms directly, was Bond initiating EU-wide CSO action to push for an EU recommitment to the 0.7% aid target, and national implementation plans, in spring 2015. This included generating joint messages, influencing and media activities to shift EU Member States’ positions from only the UK supporting a recommitment to 0.7%, to getting it included in the Council Conclusions. Bond also partnered with National Platforms to share learnings and influence EU governments to reach 0.7% of GNI on aid spending. Bond provided specific support for partners’ policy influencing activities in those EU countries which have significantly reduced their aid spending, such as the Nordics. This contributed to the European Council recommitting to the 0.7% target, despite a backdrop of declining aid levels all over Europe. This laid the foundation for future efforts to increase aid levels and make it more effective.

Bond has built on previous work to ensure this work has influenced European development policy and practice. For instance, Bond is a key contributor to CONCORD’s AidWatch work such as an annual report that holds the EU to account on the quality and quantity of its aid spending. Over time, EU member states and institutions have recognised this as an impactful analysis. Member states such as the Luxembourg government have started using AidWatch figures in policy making. As a result of continuous influencing and this strong accountability tool, the OECD DAC in turn has also developed and adapted the way it provides aid statistics. It now provides much more detail and disaggregated figures in its own aid reporting. This meant that in 2015, for the first time, figures given were very closely aligned to the figures and methodology AidWatch has promoted and used over the past 10 years.

The European Council recommitted to a collective target of spending 0.7% of GNI on aid, with 0.15-0.2% GNI for aid to Least Developed Countries (LDCs), and a strong emphasis on poverty eradication. Bond’s contribution to this success is shown in a letter to Bond from the Secretary of State for International Development in which she stated “I continue to value your critical work with civil society networks in Brussels and other Member States to help achieve our shared objectives”. The EU also included a poverty focus when redefining aid as part of the OECD; and the Gender Action Plan II applies to all EU external policies[38], representing real progress. The European Council’s position on the post-2015 agenda reflected Bond and Beyond 2015's asks including for a post-2015 agreement to be universal, address the three dimensions of sustainable development in a balanced way and leave no one behind.
[38] http://www.consilium.europa.eu/en/press/press-releases/2015/10/26-fac-conclusions-gender-development/

Although momentum on aid effectiveness implementation plans has stalled since 2014, the EU (comprising the institutions and MS collectively) has showed a strong position on effectiveness including at the High Level Meeting in 2014, and by supporting strong aid effectiveness commitments as part of the FFD negotiations in 2015. In this context, Bond chose strategically to engage with the EU’s role in the global FFD process as a means of bolstering and furthering existing commitments on aid effectiveness for the future, through which Bond also reiterated the importance of each state producing an implementation plan. This was a successful approach contributing to the strong outcome from the FFD conference, providing a stronger global focus on effectiveness for the future. Key Bond and CONCORD priorities were included in the FFD3 outcome document, for example strong commitments to transparency, and effectiveness safeguards for public-private finance[39]. In addition, Bond also contributed to lobbying the EU on its position on the OECD DAC redefinition of aid which helped prevent significant reversals for aid effectiveness in this process.
[39] http://www.un.org/esa/ffd/wp-content/uploads/2015/08/AAAA_Outcome.pdf

Summary of responses to issues raised in previous annual reviews (where relevant)
Bond has continued working closely with its members and other stakeholders as well as in close partnership with civil society across Europe through its role as an active player and leading voice within CONCORD and directly with other national platforms.

Bond has continued to broaden its influencing approach and target audience beyond the European Commission, based on more developed target analyses, as noted above.

As per plans, Bond has not produced an MFF tracker report in 2015-16, and will focus efforts around the mid-term review of the MFF in 2017 if this takes place. Instead, it has focused efforts this year on more critical opportunities for influencing aid quality and effectiveness including the 0.7% recommitment, and EU positions and activity around the Third FFD Conference.

Recommendations for future programmes
- Continue to work with members in a participatory way to identify key opportunities for collective engagement and strategic influence on EU development policy and practice; and build on existing work to provide information and opportunities to members to support their engagement.
- Continue to identify opportunities and work tactically as appropriate with partner organisations and networks both within and beyond the UK.

Output Title	Bond supports its target audience to effectively engage with and influence the process and outcome of the post-2015 agenda (at both European and international level)
Output number per LF	Output 2.2	Output Score	A+
Risk:	Minor	Impact weighting (%):	25%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Year 3)	Progress
2.2.1: Number of supported efforts (submissions, dialogues etc.) at the national and Brussels/pan EU level influencing both the European Institutions and Member States to agree official EU position on post-2015.	At least 5 joint influencing activities supported, led, facilitated towards, at and in follow up to EU processes and related civil society regional coordination. / (annual target)	5 activities facilitated and led by Bond at European level to influence its institutions and member states. / This work included Bond playing an active role in the EU Post-2015 Taskforce, contributing to at least 4 position papers and responses to the zero draft and attending planning and coordination meetings in Brussels. Bond has engaged in CONCORD development of an “EU Plan for Implementation”[40] to influence the delivery of the post-2015 framework.
2.2.2: Number of supported efforts (submissions, dialogues etc.) at the national / regional / international levels aimed at influencing the UN and intergovernmental processes towards the Global Goals	At least 7 joint influencing activities supported and led by Bond, towards, at and following the UN GA Post MDGs summit (September 2015) and subsequent meetings on implementation of and indicators for the Global Goals (including the IAEG Meeting in October 2015). / (annual target)	Bond convened and led on 24 activities aimed at influencing international processes related to the Global Goals. / Ahead of the September 2015 UNGA Summit, Bond convened UK civil society advocacy, drafting joint responses to the zero draft and other collective inputs. Bond also led the action/2015 campaign in the UK, helping raise public awareness and support for the Global Goals. Bond’s work on Global Goal indicators and implementation included a series of research papers, as well as a key role chairing the global Beyond 2015 Indicators Task Force ahead of the Bangkok IAEG meeting.
[40] http://concordeurope.org/wp-content/uploads/2016/02/CONCORDPaper_ComponentsImplementation_Agenda2030.pdf?43b376

Key Points
2015 was the crucial year for agreement of the new post-2015 framework and Bond continued to act as the main convener of civil society around this agenda in the UK, building on its solid coalition to coordinate and enable members to influence the Global Goals debate in the UK, EU and internationally. As well as the milestones, Bond successfully achieved its target for this area of the programme. Over the lifetime of the programme, Bond facilitated and led the engagement of its members in 54 activities at the national and European level. In addition, Bond enabled its members to have an active voice and participate in 32 activities to influence the intergovernmental process towards the Global Goals.

The Beyond 2015 UK group continued to see high levels of engagement, with a membership of 156 organisations, enabling Bond members and other organisations to input into the post-2015 negotiations as well as the conversations around indicators. As one member of the group put it ‘the [Bond Beyond 2015 UK] coalition did a great job of convening the sector to come together around the SDGs, sharing intelligence, coordinating rapid input during the negotiations and presenting a united front to the UK government. This was no mean feat!’ To complement and amplify the messages from its policy influencing work via Beyond 2015 UK, Bond also worked with partners in the UK and internationally to raise awareness about this important year via the action/2015 campaign, which led campaigning and mobilisation activities in 153 countries across the globe.

Bond engaged constructively with the UK government during the negotiations, and provided detailed responses to zero drafts as well as input via seven roundtables between members and DFID staff. Beyond 2015 UK produced submissions to the Environmental Audit Committee inquiry on sustainable development as well as to the International Development Committee inquiry on the Global Goals, which led to Bond being invited to give oral evidence at the inquiry, and its contribution being cited several times in the Inquiry report published in June 2016[41].
[41] http://www.publications.parliament.uk/pa/cm201617/cmselect/cmintdev/103/103.pdf

During the international negotiations, Bond convened three meetings with CSOs and the UK delegation and ran a number of very well-received interventions at the UN General Assembly for and on behalf of its members. Bond co-organised the only official civil society event at the Summit in New York in September, as well as a side-event with SoS Justine Greening to discuss the means of implementation and the UK approach.

Following the Post-2015 Summit, Bond focused on the ongoing development of Global Goals indicators and implementation of the agenda. The Beyond 2015 UK group contributed early on to the debate on implementation with the paper “Bringing the Goals Home”[42], which highlighted some ideas for implementation of the goals in the UK. Bond convened a roundtable to discuss options for UK implementation, attended by six government departments and select committee representatives. Bond also contributed to CONCORD papers on EU Global Goals implementation and provided input on debates about implementation at EU and pan-European levels. Building on previous work championing the need to address inequalities, Bond also convened members to develop further thinking on how to operationalise the ‘leave no one behind’ principle and ensure it is embedded in all implementation plans.
[42] https://www.bond.org.uk/resources/bringing-goals-home

Bond Beyond 2015 UK proactively commissioned two pieces of work to influence the final indicators framework in a constructive way – on indicators for both climate change[43] and inequality[44] across the final goals, which were shared internationally with different UN Member States during indicators negotiations. Bond coordinated the global NGO working group on Global Goals indicators ahead of and at the Inter Agency Expert Group (IAEG) meeting in Bangkok in October 2015. Bond led the process of drafting CSO statements at the event and reported on the process to global civil society, facilitating civil society engagement in the indicators conversation.
[43] https://www.bond.org.uk/resources/climate-proofing-goals
[44] https://www.bond.org.uk/resources/reducing-inequality

In the UK, Bond convened a roundtable with the ONS, DFID and 25 NGOs to encourage debate about Global Goal indicators. Bond also provided input to Cabinet Office conversations around how to integrate the Global Goals into the new national action plan of the Open Government Partnership, helping reinforce the complementarity of Global Goals and OGP initiatives.

Bond led the action/2015 campaign in the UK, which involved 102 organisations, and ensured UK activity was effectively co-ordinated with global action/2015 campaign moments throughout the year, amplifying messages around FFD, UNGA and COP summits. Bond convened one collective activity per month in the UK throughout the year, ultimately reaching over 34,450 people.[45] Bond enabled participating organisations to align their work with campaign activities, increasing coherence across the sector and ensuring messages were aligned, ultimately making a stronger public case for ambitious Global Goals. Campaign activities got over 200 mentions in the media.
[45] A summary of some of the activities members could engage in in the run up to the Summit can be found here as one example - https://www.bond.org.uk/news/2015/09/path-summit

To launch the campaign youth activists met with the Prime Minister and other government officials to share some of the campaign messages. The coalition also organized an online ‘hackathon’ reaching millions of people for International Youth Day and in the run up to the UNGA. Ahead of the announcement of the goals, the coalition organised a roadshow to five UK cities, to speak to members of the public about the importance of the new goals. On 24 September 2015, 2,000 people gathered on Millennium Bridge in London to illuminate the Global Goals and thousands of people marched in London’s climate march, raising the profile of development issues and bringing the post-2015 conversations to the attention of the public.

This activity achieved significant impact on EU positions on the SDGs, as well as the final agreed framework. As noted earlier, the European Council’s position reflected Bond and Beyond 2015's asks for a new post-2015 agreement to be universal, address the three dimensions of sustainable development in a balanced way and leave no one behind[46]. The Global Goals and Agenda 2030 themselves reflect many of Bond and its members’ priorities, for example presenting a universal and holistic agenda that embodies the three dimensions of sustainable development, and including standalone goals both on inequalities and climate change, as well as targets to tackle poverty eradication and inequalities more broadly. Language around sustainable consumption and production also reflect Bond and Beyond 2015’s recommendations[47].
[46] http://www.consilium.europa.eu/en/press/press-releases/2015/05/26-fac-dev-council-conclusions-global-partnership/
[47] https://sustainabledevelopment.un.org/content/documents/5483bioregional3.pdf

Summary of responses to issues raised in previous annual reviews (where relevant)
Bond led and coordinated its members in their engagement in both the Beyond 2015 and action/2015 campaigns. This allowed it to feed the policy messages from Beyond 2015 UK to action/2015 activities in the UK ensuring coherence and helping amplify the same messages. Bond also played a key role in coordinating messages and activities between the action/2015 and climate coalition campaigns.

Bond facilitated the work of southern partners in the negotiations about indicators by chairing the global NGO working group ahead of the IAEG meeting in Bangkok. Through that group Bond helped share information internationally and coordinated letters that were shared at the national level in several countries with recommendations for more openness and transparency in the indicators process. Bond also had an active role in different action/2015 groups at the global level, supporting campaigning activities by southern partners in their countries ahead of key moments. Bond shared its own experiences and learning with southern partners at the Global Assembly of action/2015, which took place at the World Social Forum in Tunis.

Since the end of September 2015 Bond has focused its efforts on starting a meaningful conversation about the implementation of the Goals and on the continued development of indicators as explained above. Bond’s paper “Bringing the Goals Home” was one of the first pieces of work taking a forward look at implementation and has been cited as being very useful when beginning conversations about implementation. Bond’s engagement in the global indicators process was also part of this focus on ensuring the right architecture and conditions were in place to allow countries to start thinking about what implementation would mean for them, which continues to be the focus of Bond’s work. In addition, Bond has been very involved in ensuring that the learning, collaboration, knowledge and momentum of both Beyond 2015 and action/2015 is transferred into a new long-term initiative which will be about a joint civil society effort to see the goals delivered.

Recommendations for future programmes
- Bond should continue to use its convening abilities to facilitate civil society engagement in policy and influencing activities on the implementation of the Goals and to ensure that no one is left behind, building on the recently established SDG group and Leave No One Behind activity within this.
- Bond should support membership, partners and other national platforms to realign and reorganise their activities in this new implementation phase, helping coordinate UK, EU and international civil society’s efforts around Global Goals implementation. This includes continuing to contribute to the work of CONCORD’s newly established Hub on ‘Sustainable Development and Policy Coherence for Sustainable Development’ which covers Agenda 2030 implementation.
- Bond should continue to work with members and partners to raise awareness and build support for the Global Goals.
- Bond should build on its influencing and coordinating expertise to support southern civil society and help strengthen their capacity for advocacy efforts to hold their own governments to account on implementation.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page) Focus on lifetime of the Programme

Key cost drivers and performance
Key costs, and their drivers, have not changed significantly in the programme, with staff costs remaining the most significant cost of this work. Over the lifetime of the programme, Bond has invested significantly in developing its team and has recruited a number of specialist roles to ensure that it is able to deliver high quality work. In the first year of the programme, the Effectiveness and Learning team was significantly expanded in order to develop and support Bond’s services and tools, working closely with members to achieve the milestones set out in the logframe. This team has further grown since with the addition of staff to work on its Futures programme. Over the past three years Bond has also created and filled a number of specialist job roles in its Marketing, Membership and Communications team to ensure that Bond members are well-supported and understood, services are widely and effectively marketed and that learning and other content is shared across the Bond network. With this staff contingent, Bond has also undertaken additional, unplanned work, in collaboration with DFID, including the Ebola Response Hub and work on the distinctive role of UK NGOs. The development of this strong and highly skilled staff body within Bond has allowed it to offer support, expertise and value for money to its members and other stakeholders, including DFID.

Bond minimises its use of consultants by using internal staff capacity wherever possible, and the growth and increased expertise of the internal team helps to achieve this. Bond also capitalises on the knowledge and skills of its members to provide content and resources. Much of Bond’s web content, for example, is sourced from member contributions. Bond members chair almost all of the Bond working groups, putting in significant time to source content, run meetings and coordinate inputs from group members. For example, the European Policy Forum has a steering committee of seven staff from Bond members responsible for running the group, supported by Bond. Bond is also developing a corporate supporters scheme, enabling it to secure more pro bono support and ‘gifts in kind’ (such as the use of venues).

When Bond does require external support, there is an open tender process to ensure competitive pricing in line with Bond’s procurement policy. Day rates and value for money are key factors in the recruitment process. To ensure lower and more predictable costs, Bond negotiates on daily rates with consultants, and agrees fixed costs for work at the outset.

Bond is continuously finding new ways to manage its costs to ensure that it delivers value for money (further detail can be found on annex 1).

VfM performance compared to the original VfM proposition in the business case
The principal value for money proposition in the business case for this intervention was that funding Bond offers low transaction costs for DFID with the potential for significant benefit as a result of the work.
In 2013, as stated in the business case, Bond brought together NGOs with a combined expenditure of £2.9 billion. If improved effectiveness/efficiency delivered a saving of 0.1% (i.e. £2.9m) this would more than cover the cost of the grant (£2.7m). Given that the combined membership expenditure figure has now risen to £5.7 billion, the cost to DFID of the grant only equates to a 0.05% saving across the membership. It is reasonable to assume therefore that a grant to Bond offers exceptionally good value for money in terms of the change achieved for the cost outlay.
Given the realisation of almost all of the individual milestones in the programme, the achievement of outcomes and the consistent high ratings of Bond’s work, it is clear that the large potential benefits of Bond work have materialised. Looking at just the take-up of Bond’s effectiveness and transparency work, 1,902 individuals have cited evidence of positive changes in practice as a result of training and networking through this programme.

The transaction costs for DFID have remained low in only having to deal with one organisation directly in grant management terms, with the reach of the programme extending to Bond’s increased membership of over 470 members. This membership has a total staff (UK and international) of 75,800, so centralised funding of their membership organisation, with a single set of overheads, is a cost-effective way to leverage change. Bond also has reach outside this network, through working with a large number of non-member organisations. The last three years saw 331 non-member organisations access Bond’s effectiveness, transparency and training programmes.

Bond has also provided direct value for money to DFID, optimising on its ability to convene quickly and efficiently. This has offered DFID a rapid route to the sector when needs arise including the management of the Ebola Hub, delivery of CSPR consultation and advocacy work on EU aid quantity and quality. This has provided DFID with views from medium and smaller organisations, whose needs may otherwise have been overlooked. This input through Bond has helped inform DFID’s position on topics such as payment by results, contracting and cost recovery. The agreement for Bond to host the PPA Learning Partnership (LP) will also generate efficiency savings for DFID, including reduced staff time in the Inclusive Societies Department to support the LP, more coordinated engagement between Bond and PPA groups and DFID staff, and the ending of DFID’s online hosting of the partnership.

Assessment of whether the programme represented value for money
Bond has delivered value for money as outlined in its original business case. This programme has also represented value for money in some further ways.

Given Bond’s structure as a network organisation, it has an enormous multiplier effect. DFID recognised this as part of the first annual review of this programme.[48] All of the tools, resources and materials offered by Bond, including the large number of new ones developed throughout the programme such as Payment by Results[49] and Guide to Getting the Best out of Consultancy,[50] are offered to hundreds of NGOs and other organisations. Many of these services are available to members and non-members free of charge as ‘public goods’, reducing duplication of activity, and the related costs, across organisations. Bond’s multiplier effect is also relevant with regard to its convening and coordination work, bringing members and others together in the form of working groups and its annual conference, which now spans two days and attracts 1,000 delegates.
[48] See the report on Dev Tracker http://iati.dfid.gov.uk/iati_documents/4472904.odt
[49] http://www.bond.org.uk/data/files/publications/Payment-by-results.pdf
[50] http://www.bond.org.uk/data/files/A_guide_to_getting_the_best_out_of_a_consultancy.pdf

Throughout this programme, Bond has also demonstrated significant value for money to DFID through a range of additional services and areas of work that do not explicitly feature in the original logframe. This includes having established and managed the Ebola Response Hub at the request of DFID, working closely with DFID on its Civil Society Partnership Review and offering an annual Fund Manager survey which gives DFID feedback on their outsourced fund management relationships. DFID staff have commented that, among other things, Bond has helped DFID be more efficient and effective in its engagement with the sector.[51]
[51] Based on interviews with DFID stakeholders in the external evaluation of the programme

During the three-year programme Bond has increasingly automated certain functions, through using IT to reduce staffing support costs in a number of areas. For example, Bond no longer has a dedicated function for its recruitment offer, as members and other NGOs now upload their own adverts.

Bond has also maintained efficiencies in its finance support for the organisation. During the programme’s lifetime, Bond’s annual turnover has grown from £1.9m in 2012/13 to £3.6m in 2015/16. Despite this 90% increase in turnover, the finance team has only gained one additional staff member on a part-time basis, equating to a 25% increase. This efficiency has been aided by the introduction of a more efficient accounting software system which has allowed easier access to information across the organisation, and thereby enabled higher quality financial management.

Quality of financial management during programme
Bond as a network and as an organisation has grown significantly in recent years. With this growth in size, internal financial management systems have had to adapt and the Finance and Operations Team has grown slightly to accommodate this. Bond has carefully and responsibly managed this DFID grant, and its other funds, throughout the programme. More recently, with a new Director of Business Strategy and Finance in post, Bond’s financial systems and processes have been improved to allow for even clearer lines of accountability and stricter financial management across the organisation. This has included introducing a new, more streamlined, chart of accounts, the production of monthly financial reports for all project managers and a re-design of management accounts to ensure that they match the needs of heads of departments and directors.

Over time, the allocation of funds within the budget has changed in order to allow Bond to deliver planned work. This has meant a reallocation of funds from the activity to staff lines, which reflects the nature of Bond’s work in convening and supporting members and other key stakeholders. This change has been communicated with DFID through annual reports and quarterly meetings. It has also been reflected in the financial reports that Bond has submitted to DFID on a quarterly basis throughout the grant programme. Bond’s effective management of the programme funds mean that the total grant spend was on budget.

Date of last narrative financial report	29th April 2016
Date of last audited annual statement	31st March 2015

E: RISK (½ page) Focus on lifetime of the Programme

Quality of risk management over the life of the programme
The main risk for Bond throughout the programme has been the potential impact of significant changes to the external environment. During the three-year programme the political and policy context has changed significantly with a UK general election and subsequent change of UK government, a new European Parliament and set of Commissioners, and the Global Goals agreed. Bond’s membership has also undergone changes, growing to over 470 members, meaning a greater diversity of needs, and emerging priorities including questions on legitimacy, rapidly changing technology and changing funding models.

Continued flexibility has been essential to achieve milestones and ensure changes at an outcome level. This has included undertaking additional work where new strategic priorities emerged, including the Ebola Hub and CSPR. Pre-existing plans have also been adapted where necessary, including expanding the transparency programme to overcome the risk of it being seen purely as a compliance issue.

Specific risks in the programme have been identified in Bond’s risk register, which has been regularly updated to better reflect the external context, and has been discussed and shared with DFID throughout the programme. The means through which risks are mitigated are outlined in this register and have been reviewed regularly to ensure that Bond can adequately deal with existing and emerging risks.

In two cases, risks have materialised throughout the programme period. One of these was the necessary postponement of the AidWatch report launch and a few other EU policy meetings due to security alerts in Brussels in November 2015. In year two of the programme, Bond missed its effectiveness tool service satisfaction rate of 85% (achieving 78%) due to the increased breadth of its membership and number of members taking up services with differing needs and expectations. Work has since taken place to ensure that Bond finds the best way to support the needs of all members, including investing in more regular feedback mechanisms and internal systems to better disaggregate members, and using that to provide more segmented services and events with clearer marketing. This further work has led to satisfaction rates of 84%: a significant improvement, but short of the 90% target.

Overall the lifetime of the programme, most of the risks have not been realised or have been successfully mitigated against, meaning that they had no significant bearing on the success of the programme.

Overall Risk rating: Moderate

F: COMMERCIAL CONSIDERATIONS (½ page) Focus on lifetime of the Programme

Delivery against planned timeframe
At the end of the grant programme, Bond has delivered activities and outputs in line with the latest plans discussed and shared with DFID. Bond has also shown flexibility in adjusting plans and making resource reallocations to allow for the delivery of a range of work that has taken place above and beyond the grant-specific timelines. Where adjustments to plans have been required, including not running one iteration of the Transparency Review due to lack of willingness of organisations to pay for it so soon after the previous, free round, Bond has discussed these in detail with DFID.

Performance of partnership (s)
The success of all Bond’s work, including that covered in this programme, is dependent on effective partnerships with Bond members and a range of other groups and stakeholders. The external evaluation[52] of this programme recognises Bond’s strength at working in partnership: ‘As a trusted and credible representative of the voice of NGOs Bond is in a good position to play the role of critical friend to funders and other bodies, such as IATI.’
[52] https://www.bond.org.uk/sites/default/files/bond-dfid-2013-16-grant-eval-full.pdf

Bond’s membership has gone up from 395 when the programme began, to 473 members now. Bond plays a convening role with this network; fostering partnerships, learning and relationships within the membership. With the recent absorption of the DFID PPA Learning Partnerships, the number of Bond’s working groups has risen to 52 and My Bond now has over 5,500 users. The European Policy Group, Beyond 2015 UK, Monitoring, Evaluation and Learning and Transparency working groups have all been key parts of this programme. The groups, whether they be interacting in face-to-face meetings or online through My Bond, are a key way of learning for the network and partnership, through: showcasing best practice; collectively solving problems, and; peer learning. The groups also offer an opportunity for the network to develop common positions for advocacy purposes.

Close work in partnership with NIDOS in Scotland is a core part of the work on effectiveness, providing a means of broadening the reach of effectiveness and transparency tools and services.

In its European policy work, Bond represents the UK NGO sector on the board of CONCORD, the European NGO network of 2,400 organisations organised through national level networks or “platforms” across all 28 EU member states. Learning and expertise are shared across this platform in order to maximise influence and impact.

Bond is increasingly working with global networks to facilitate shared learning and practice between peers in the north and south. This is partly through collaboration with the IFP, and also through a close working relationship with CIVICUS, the global civil society network.

Bond and DFID have an effective grant management relationship, with clear expectations on reporting, a good level of flexibility, regular discussion and quarterly programme management meetings. There have, however, been some issues during the lifetime of the programme, including DFID reporting timeframes that were initially inconsistent with the timeline against which targets were set. There were also some changes to regular reporting requirements when grant contacts changed during the grant period.

Bond and DFID also work together on a large area of work outside this grant programme. This is an effective and positive relationship for both parties, ensuring that impact is maximised in a range of areas of mutual strategic benefit. There is an appropriate level of challenge in this work, with Bond playing a role in relaying its members’ viewpoints to DFID through a range of means including the Fund Manager survey and input into the CSPR. In addition to engagement on the CSPR, Bond continued to provide DFID with a valuable platform for insight from and engagement with NGOs. This included quarterly meetings with a range of DFID staff in Abercrombie House (with MANGO and Bond’s Commercial Contracts working group), issue-specific meetings (e.g. on disability data disaggregation), participation in a Cross Funders MEL group (with DFID, Comic Relief and the Big Lottery Fund), and engagement with DFID staff on learning topics via the PPA Learning Partnership steering committee. DFID staff have commented that Bond has helped DFID more efficiently and effectively engage with the sector.[53]
[53] Based on interviews with DFID stakeholders in the external evaluation of the programme

Asset monitoring and control
Bond maintains rigorous systems and processes to ensure that all of its restricted funding is used only for the intended purpose(s). Bond’s financial coding structure requires that all transactions be allocated to specific work, and these codes explicitly identify DFID-funded work. All costs are signed off by the budget holder and/or the relevant head of department. Payments are passed to the finance team and approved by two authorised signatories. The heads of department receive monthly management accounts and are required to check these thoroughly in order to ensure the correct cost allocations have been made. The management accounts are approved by the directors’ team.

G: CONDITIONALITY
Partnership principles assessment: N/A

H: MONITORING & EVALUATION (½ page) Focus on lifetime of the Programme

Evidence and evaluation
Bond commissioned an external evaluation of the grant in March 2016. Evaluation questions focused on both accountability and learning issues, including verifying achievements against logframe targets and assessing the contribution of Bond’s and NIDOS’ activities to the outcomes. The chosen evaluators were a team of three independent consultants: Ann Sanders, Janice Needham, and Catherine Sexton. They used a theory-based approach to the evaluation, and verified and triangulated Bond’s monitoring data through interviews with a sample of users of effectiveness services and participants in advocacy activities and external key informants.
The evaluation was complemented by a set of eight in-depth case studies that were carried out by INTRAC in 2014 and 2015. These non-representative case studies provided insight into organisations’ use of Bond and NIDOS effectiveness services, and whether and how changes were subsequently made to improve organisations’ effectiveness. Bond will be making both the evaluation and an anonymised version of the case study research public in mid-2016 on their website and via IATI. In addition, Bond will publish at least four brief outputs before December 2016 that will communicate particular learning points from the programme.

Some key evidence relating to the Theory of Change (ToC) for the effectiveness work includes:
- The ToC should have been more nuanced to reflect the diversity of organisations supported by Bond, as their size and funding sources influence whether and how Bond services are used;
- The role of NGO senior leadership in creating an enabling environment for uptake of and change from use of Bond and NIDOS services was under-estimated;
- There is limited evidence of use of Bond Effectiveness services “trickling down” to southern partners;
- It is not practical or proportionate to try to draw a direct link between use of Bond and NIDOS services and changes in the lives of beneficiaries, given the long chain of actors and assumptions involved, and the time required for change to be manifested at beneficiary level.

Although gender disaggregation is possible for some services which engaged individuals, for example training, disaggregation by gender or disability does not apply to organisation-level use of services and policy change work. Bond disaggregates many output-level effectiveness results by organisational size.

Monitoring progress throughout the programme
On the effectiveness and transparency side of the programme, Bond tracks use of all its services, except for downloads of publications, and annually gets feedback from users in an Outcomes Survey on (a) usefulness of services; (b) changes in personal knowledge, skills or confidence as a result; and (c) changes in organisational practices, systems and policies as a result of service usage. Bond aims for, and usually achieves, at least a 20% response rate to this survey. Survey results are extrapolated to all users of those services to determine results against outcomes and some output indicators. Examples of improvements made in year three based on feedback in year two are included in the outputs section above. In addition, for events and training, feedback is collected from all participants at the end of events. Bond staff use this data to improve services and consider the development of additional offers.

On the influencing work (Outcome 2), Bond staff keep a record of all events, joint outputs, submissions, meetings secured, and progress against policy change targets to monitor progress against logframe outputs. Records are then kept of public announcements and policies, relating to advocacy topics, and these are compared to advocacy “asks” to attempt to identify contribution to change. Use of member working group meetings and informal relationships with Bond’s target audience helps collectively review progress, hear feedback from members about their engagement and analysis of progress, and draw learning for next steps. At several stages in the programme, information has been gathered from policymakers about their experience and assessment of impact of Bond’s work. Interviews were conducted as part of Bond’s strategic review and two formal evaluations of Bond’s influencing work.

Bond and DFID held quarterly progress review meetings throughout the programme. The Project Completion Report was compiled by Bond staff primarily by drawing on information already produced using the monitoring and evaluation processes described above.

I: Disability (1 page) Focus on lifetime of the programme

Bond continues to address disability in a range of ways as appropriate to its working model and approach. Since Bond does not work directly with beneficiaries, its disability focus is related to its convening role.

One of Bond’s leading working groups is the Disability and Development Group (DDG). The group has delivered a range of work over the lifetime of the programme, and represents organisations working with people with, or at risk of, disabilities, who are living in poverty. The group is hosted on Bond’s social media platform – My Bond – and now has 297 members from 109 different organisations. It has held a total of 48 events during the programme lifetime, some of which DFID’s Disability Team have engaged with. Recent discussions have included responding to DFID’s new Disability Framework. Earlier in the programme, the DDG worked with other Bond groups to ensure that its post-2015 work maintained a disability thread, including keeping ongoing track of the number of mentions of disability in the Global Goals as well as through collaboration with Beyond 2015 UK’s policy work around on inequalities and the ‘leave no one behind’ principle.

A number of Bond members have a specific disability focus, including ADD International, Handicap International UK and the Asian People’s Disability Alliance, and these organisations are represented across Bond’s working groups. Best practice in disability inclusion is also demonstrated across the Bond membership, including organisations that do not necessarily specialise in disability.[54]
[54] https://www.bond.org.uk/news/2015/12/disability-inclusion-matters-education

During this programme of work, Sightsavers played an active role on the steering group for European policy work, and therefore ensure that disability and inclusion is included in Bond’s EU policy work.

Bond has published a range of content on disability, including profiling the work of relevant members and hosting a Twitterchat in December 2015 on disability inclusion, in line with the International Day of Persons with Disabilities.[55] DFID’s Disability Team in its Inclusive Societies Department took part in the Twitterchat, which generated over 1,000 Tweets from over 500 Tweeters.
[55] https://www.bond.org.uk/events/disability-inclusion-matters-twitter-chat

Bond encourages diversity in its workforce. When job roles at Bond are advertised, the text is included as standard: ‘Bond values diversity and works to advance equality. We encourage and welcome applicants from all sections of the community. Bond has flexible working hours, opportunities for some remote working and the office has full accessibility for wheelchair users’. A number of Bond’s HR policies ensure that those with disbailites are not discriminated against and that selection for employment, promotion, training or any other benefit will be on the basis of aptitude and ability. Many staff make use of Bond’s flexible working policies, with a number of part-time roles in the organisation, staff working compressed hours, making use of flexible start and finish times and working remotely.

The key messages used in Bond’s policy outputs are designed to be as inclusive as possible, and the voices and perspectives of disability NGOs are reflected at policy meetings and in other communications to policymakers. Bond’s web-based services, including the online Health Check, have been checked specifically to ensure their accessibility for the visually impaired. Bond plans to continue to ensure that the perspectives of its members who specialise in disability are integrated in its work throughout the nine-month extension period. This includes working with DFID on the Leave No One Behind agenda, of which ensuring that people with disabilities are not left behind by development efforts must be a key part. The important work of the DDG will continue, including further development of sub-groups on value for money and mental health.