Annual Review - Summary Sheet

Title: Mining Sector Reform Project
Programme Value: £643,632		Review Date: August 2017
Programme Code: 105844	Start Date: 19/10/2011	End Date: 30/07/2018

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	C	B	B	A	A+	A+
Risk Rating	High	High	High	Low	Minor	Minor

Summary of progress and lessons learnt since last review
There is strong evidence, both through reporting and interviews with different project stakeholders that the project is delivering results. Civil Society Organisations (CSOs) interviewed during the Annual Review process provided very positive feedback on the training provided by the Carter Centre (TCC) and how it helped them in their work. The training helped CSOs influence different stakeholders in the mining sector (e.g. government official and mining companies), and helped improve: their analysis of revenues and financial information, development of standards and technical definitions on social expenditure and standards by mining companies, advocacy efforts for increased transparency and contributions, and recommendation for the Extractives Industries Transparency Initiative (EITI).

A major achievement of the project was the payment of royalties from the DRC’s largest gold project, Kibali Gold Mine, to the province of Haut-Uele. Whilst it’s difficult to solely attribute this to advocacy efforts of Cadre de Concertation de la société civile de l’Ituri sur les resources naturelles (CdC), their contribution to this result is important. This payment sets an important precedent that CSOs and other actors could build on.
Other two main achievements were (1) obtaining the financial statement of the Société Minière de Kilomoto (SOKIMO); a DRC state owned enterprise, and (2) the development of the social expenditure framework.

Progress against recommendations for last year

Recommendation	Progress and comments
Review the logframe for the Carter Centre Accountable Grant to ensure that it sets the right level of ambition. New tools were developed for the logframe to monitor progress and it is sensible that the effectiveness and ambition of these indicators is revisited following the completion of this review	The logframe was not reviewed as the expectation was that DFID support would end in February. The logframe currently being finalised for the programme extension (by December 2017) and we will ensure that the level of ambition is set at the right level.
Visit Carter Centre downstream partners as an integral part of the project completion report process. Interaction with the civil society partners is a crucial method for assessing the progress of the accountable grant, outside of monitoring through the logframe. It is important that this is included in the project completion report to ensure feedback from the target organisations is a central part of this final review.	The DFID team met with two CSOs in Kinshasa and Lubumbashi . Feedback from these organisations, on the work with the Carter Centre, was positive, specifically regarding the strategic thinking that TCC adds to the partners’ work. One CSO also said the training provided was very specific, useful and, helped them do their work better.
Close the existing programme at the end of the Carter Centre Phase 2 Accountable Grant. In March 2017 the existing extractives programme will come to an end with the closure of the accountable grant. It is important that this is closed responsibly and lessons learned from the project fully documented.	There have been delays on the new business case and therefore the team decided to extend the current grant until July 2018 to ensure our support to the governance in the mining sector continues until approval of the new Business Case (BC_.
Develop a new BC for the mining sector. For the UK to continue its contribution in helping harness the extractives sector for the development of the DRC, we will propose a new business case setting out a new programme to replace the one closing.	The new BC is in development and expected to start at the end of this year.

Summary of recommendations for the next year
- The short term nature of the DFID support provided so far made it difficult for the Carter Centre to effectively measure and assess their impact (advocacy and influencing as well as capacity building beyond the evaluation of the specific training). The new extractives BC should consider this very carefully.
- There is evidence of the diffusion of the skills learnt by the different CSOs. This is not formally measured or assessed under the current logframe but something that should be considered, along other measures for sustainability of the projects’ capacity building activities.
- The new BC should also consider gender and women issues more carefully. The current project tried but didn’t fully succeed in securing long term attendance of women in the training events. That said our focus should not be limited to inclusion of women in training. Under the extended grant (until July 2018) the Carter Centre will work with a women led CSO which will help address this issue. This also could be an opportunity to identify specific issues that affect women and girls in the mining sector that could be considered in the new Business Case.
- The revised logframe, setting the right level of ambition for programme results in the next phase, should be finalised by December 2017.

A. Introduction and Context (1 page)

DevTracker Link to Business Case (BC): / BC addendum:	http://iati.dfid.gov.uk/iati_documents/4145425.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5567438.xlsx

As with the previous two annual reviews, the context in which this project is operating has not substantially changed since the original business case, however the project is radically reduced to that set out in the business case. The mining sector remains the most important source of revenue for the DRC and arguably the most important sector in the economy.

We have continued to provide support to an accountable grant to The Carter Centre, which works with civil society to increase accountability and transparency in DRC’s industrial mining sector. This remaining component is the subject of this annual review.

Context

The Congo has one of the richest and most diverse mineral endowments in the world. It is estimated to contain 45% of the world’s cobalt, 65% to 80% of its coltan, over 3% of its copper and 25% of industrial diamonds. Gold deposits are believed to be vast as are hydrocarbon resources, but these are currently underexplored. The DRC also produces tin, tantalum, cassiterite, zinc, rare earth metals, has large stocks of uranium, and a host of other valuable natural assets. Estimates of the country’s mineral wealth are very uncertain, although the UN has valued them as much as $24 trillion – $6 trillion larger than the GDP of the US.
The direct contribution of the extractive industries is huge. In 2014 natural resource extraction accounted for 22% of GDP (up from 11% in 2005), 95% of exports (56% in copper products alone), 11% of all formal employment and around 80% of foreign direct investment.
Whilst several important steps have been taken to improve the governance and transparency of the extractives industries, corruption is still a major factor undermining its developmental impact, and a lot more needs to be done to ensure extractives revenues benefit the Congolese people. Over the past two decades, mining concessions, including of state-owned mining companies, have been sold to private investors at a fraction of their market value. Additionally, while national fiscal revenues are in principle subject to parliamentary oversight, far less oversight or attention has been paid to provincial revenues from the extractives sector.
A key tool for improving the transparency and accountability is the implementation of the Extractives Industries Transparency Initiative (EITI). DRC was validated as EITI member in July 2014, which was an important step towards improving transparency. Under the EITI standards, countries need to publish data on companies’ payments to the state and governments’ receipts, as well as companies’ productions and export data, beneficial ownership and social expenditure.

ProMines

In 2011 DFID DRC launched the Mining Sector Reform Programme. The largest component of this was ProMines, a £27 million World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’. The project met some success, for example it: supported a proposed revision of the Mining Code; conducted a strategic environmental and social assessment of the mining sector; carried out an institutional audit of mining sector institutions, which has been useful to other donors, the government and civil society; and drafted a new strategy for SAESSCAM (a government agency supposed to support small scale artisanal miners). The project however failed to make sufficient progress and given its performance issues, outlined in the last two annual reviews, in 2014, DFID DRC made the decision to exit the trust fund, having committed £9 million. This decision was taken to protect British taxpayer money and ensure that it was well spent, rather than a strategic decision about the importance of intervening in the sector.

The Carter Centre Accountable Grant

From October 2013 to January 2015, DFID funded a first accountable grant with the Carter Centre. This was a separate component under the Mining Sector Reform Programme. The project worked with civil society on advocacy for transparency to increase the Government of DRC and mining companies’ compliance with their information disclosure obligations, including, but not limited to, those found in: the EITI Standard, the new Mining Code and Mining Regulation, ministerial decrees, contracts and conventions, corporate governance laws and international standards and best practices.

This project made good progress, producing two main deliverables: an analysis report of the legal and normative framework governing mining information, and; the Transparency Index, a measure of the scope and quality of information available for mining projects in the DRC. It also made a wider contribution improving the capacity of civil society organisations in the sector and helping improve the overall EITI process in the country.

Phase 2 of the accountable grant was agreed in September 2015 to continue to increase transparency in the DRC mining sector, following the success in helping the DRC becoming compliant with EITI requirements. The overarching impact of this second accountable grant is that the governance of mining sector revenues improves, and investment of these revenues is more responsible, sustainable and equitable. The project aims to support civil society in contributing to improved EITI implementation in the DRC as well as to use EITI data for more effective advocacy.

The project has three outcomes:

1. Congolese civil society partners, including civil society organisations (CSOs) that advocate for the empowerment of women and girls, are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting.
2. Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies.
3. Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges.

With civil society further empowered to substantively participate in the EITI process, to analyse revenues generated by the mining sector, and to advocate for fiscal governance improvements, they can influence reforms to improve accountability of mining sector revenues and ensure the sector better contributes to the DRC’s development.

DFID has agreed to extend phase 2 until July 2018 with an additional budget of £539,000 (as previously using residual funding from the ProMines). An assessment of the results under this extension will be measured in the PCR in 2018.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The project has three outcomes. Progress against all three of these outcomes has been positive.

Outcome 1: Congolese civil society partners, including CSOs that advocate for the empowerment of women and girls, are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting
Indicator	Target	Achieved
Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process.	8	10
Cumulative number of EITI contributions (e.g. memos, revenue estimates, etc.) from civil society teams receiving TCC’s technical support that achieve a quality of at least 50%.	8	12

Outcome 2: Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies.
Indicator	Target	Achieved
Quality of civil society team’s case study interim deliverables	75%	79%

For all EITI contributions under outcomes 1 & 2, the Carter Centre worked with four civil society organisations: ADDH[1] and IBGDH[2] based in Kolwezi. Each studied one Glencore subsidiary. The selection of Glencore projects allowed them to compare notes and work collaboratively. COSCCET[3] and DEDQ,[4] worked together on one case study that assessed the revenue impacts of the Frontier mining projects in Sakania. These case studies brought attention to very important fiscal governance issues, including excessive debt financing, asset sales without clear valuations and some questionable reporting under EITI, in some of the most significant mining projects in the country- KCC, MuMi and Frontier mining. This work generated media attention and dialogue related to the reform of the 2002 mining code.
[1] Action pour la Défense des Droits Humains
[2] Initiative Bonne Gouvernance et Droits Humains
[3] Comité de Suivi pour la Contribution des Communautés et Eglises à la Transformation Humaine
[4] Détectives Experts pour les Droits au Quotidien

Overall, CSOs partners submitted 14 recommendations to the multi-stakeholder group to improve the EITI process, of which 10 were addressed. A few examples of the contributions include: the completion of scoping studies prior to each annual EITI reporting exercise, explanation of mining prospection activities, and public dialogue on beneficial ownership and revisions to the DRC’s approach to beneficial ownership data.

The Carter Centre worked closely with partners on their EITI contributions which included a catalogue and verification of fiscal and parafiscal flows, evaluations of fiscal and parafiscal risks, and recommendations to address governance gaps. TCC assessed the first draft of such contributions and estimated their quality score to be 57%. After the initial assessment TCC provided feedback as part of the learning process and worked with partners to improve the quality of the deliverables. During AR interviews, TCC and partners were able to show anecdotal evidence of this. This is one area where the DFID team could engage proactively with TCC to improve the measurement of such results.

Outcome 3: Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges:
Indicator	Target	Achieved
Cumulative number of interim deliverables on using the data and associated advocacy from civil society teams receiving TCC’s technical support that achieve a quality of at least 50%.	25	36

To achieve this outcome, TCC worked with two more experienced CSOs, OCEAN and CdC.

OCEAN (whom DFID interviewed in Kinshasa) focused their analysis and advocacy on social expenditure for community improvements. As part of this work, TCC and OCEAN conducted site visits to mining companies’ social projects and interviewed community members. The visits and EITI data showed that social projects seem to be implemented without consultation with the community or local development planning and indicated that there is a misunderstanding of social expenditure definition. Working closely with TCC, OCEAN developed a framework that provided a list of criteria and definitions for social expenditure. Following various iterations and consultations, the framework was validated by a broad group of civil society and now forms the basis for the EITI DRC multi stakeholder group’s consultation on these issues. In addition, OCEAN produced a draft Prime Ministerial decree on mining company social investments, and another one for the Ministry of Mines on the ruling of sustainable development plans.

CdC focused their advocacy efforts on two issues: state-owned enterprise governance in the mining sector with a focus on gold-producing SOKIMO, and the subnational revenue sharing of the mining royalties to the state. The analysis and advocacy work of CdC was successful and resulted in a call by the Ministry of Mines for an audit. CdC also obtained copies of SOKIMO’s financial statements (an OHADA law requirement) and the report on the state as a shareholder.

One of the most notable achievements, which could be contributed to CdC’s work is the unprecedented payment of mining royalties of Kibali goldmine to the province of Haut-Uele.

Overall output score and description

Based on the Carter Centre logframe and interviews with partners the overall output score is A+.

Key lessons

- Sustainability: the short nature of support made measurement of impact of advocacy and capacity building challenging. Whilst this cannot be addressed in the coming year, it should be carefully considered under the new BC.
- Working with the public sector: one of the adjustments TCC made during this project is modyfing their target audience from appointed ministers and close staff to general secretaries at each ministry. This is very important in such a fluid political situation.
- Expansion of training activates to government officials. The project could in the future consider including government officials in the training to ensure they understand EITI requirements and other mining codes.
- Results and VfM measurement: Given the difficulty of measuring outcomes and impacts of this programme (influence) it is important that the new BC will seriously consider how to ensure a robust evaluation of impact can take place in the future.

Key actions
- DFID and TCC to explore working with universities and other organisations to build up institutional knowledge in the region.
- Gender: the project managed to secure some women participation but this was limited and not sustained. Although challenging given the number of women CSO in the sector, the new DFID BC should consider more carefully work that could address issues affecting women in the mining sector. The partnership between TCC and women led CSO may provide an opportunity to explore some options.
- The revised logframe, setting the right level of ambition for programme results in the next phase, should be finalised by December 2017.

Has the logframe been updated since the last review?

The logframe is under revision to include additional results for the extension of phase 2 until July 2018. There will be a change of the targets at the outcome and output level but no changes of the impact, outcome and output statements or the impact targets.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Congolese civil society, including women and CSOs that advocate for the empowerment of women and girls, is trained and is able produce contributions on EITI reporting and processes in the DRC.
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting at least 10%.	25% per quarter	An average 77%
Overall level of satisfaction among men and women of CSOs participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting.	25% per quarter	An average of 86%
Cumulative number of contributions by groups of members of civil society developed for use in advocacy with key targets of the EITI-DRC process	8	14

Key Points
TCC provided hands on training to four CSO partners (ADDH, IBGDH, COSCCET and DEDQ) to improve their ability to monitor and advocate for EITI improvements.

The indicators on skills acquired and satisfaction with the training were significantly exceeded. These were measured by pre and post training evaluations that TCC undertook in the project to assess the level of knowledge for the subject.

As mentioned under outcome 1&2 partners provided 14 contributions to the EITI process. These contributions included the completion of a clearly articulated scoping study prior to each annual EITI report exercise, the adaptation of production data to conform to existing publications of this information, explanations of mining prospections activities, public dialogue on beneficial ownership and revisions to DRC’s approach to it, development of a framework to guide social expenditure reporting.

The score for this output is A+ rather than A++ to account for the fact that DFID and TCC didn’t amend the logframe targets after the 2016 review.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation	Progress
New monitoring and evaluation tools were developed for the logframe to effectively monitor the Carter Centre progress. As these were new tools it was difficult to realistically set reaching objectives, and we feel the ambition needs to be increased for the remainder of the accountable grant.	The ambition under the logframe was not amended in the past year.

Recommendations
If feasible, DFID and TCC should consider whether government officials could be included in the training on the EITI process.

Output Title	Congolese civil society partners, including women and representatives of CSOs that advocate for the empowerment of women and girls, are trained on mining sector revenue flows and their impacts.
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on mining sector revenue analysis in at least 10%.	30% per quarter	An average of 70%
Satisfaction with TCC-led workshops held on mining sector revenue analysis.	65%	63%
Cumulative number of interim deliverables completed toward the final revenues impact case study.	20	27

Key Points
TCC provided hands on training to the four CSO partners trained under output 1 (ADDH, IBGDH, COSCCET and DEDQ) on eight modules related to mining sector and EITI process including but not limited to fiscal impacts of a mining project using the extractives industries value chain as an analytical tool, legal framework and contractual analysis, taxation and accounting concepts to financial statements and revenue flow analysis. Many of the CSO’s reported that the training had resulted in their staff being regarded as ‘experts’ and were consulted by government agencies to provide technical support for policy-making (e.g. one CSO was asked to help with an environmental assessment using the knowledge and skills learnt from the modules taught by the Carter Centre.

As in output 1, TCC measured the knowledge and satisfaction by conducting pre and post training evaluations that measured the level of knowledge and satisfaction with the quality of the training. This was confirmed during AR interviews where feedback on the workshops and training was very positive.

The skills partners developed helped them influence locals MPs, government officials and mining companies. Partners also requested more advanced training, more training around advocacy capacity building, and the inclusion of other actors in the training especially MPs and government officials who are mostly unaware of regulations they should implement and enforce. DFID could explore this option with TCC for this grant or future support.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

Output Title	Congolese civil society partners, including women and representatives of CSOs that advocate for the empowerment of women and girls, develop interim deliverables for an advocacy strategy.
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	34
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on data utilisation and advocacy at least 10%.	30% per quarter	An average of 96% participants increased their knowledge by 20%
Overall level of satisfaction with TCC-led workshops held on data utilisation and advocacy.	65%	80%
Cumulative number of deliverables developed for using EITI-DRC data analysis in the implementation of the advocacy strategy.	40	40

Key Points
TCC selected OCEAN and CDC – both with experience in natural resources governance – for this training. The two partners were interactively trained on design and implementation of advocacy strategies. The work also included interactive training on analysis of data needed for the advocacy.
In addition to overachievement of acquired knowledge as measured by the pre and post evaluations, there was also evidence of persistent diffusion of the skills learnt, for example the former CSO workers that had received TCC training joining other CSOs and government departments and developing their capacities. OCEAN also noted that the expertise they had acquired led to an invitation by the government to participate in an environmental assessment.

As noted under the outcome 3, there have been two notable achievements: the payment of Kibali goldmine royalties to the province of Haut Uele, and the development of the social expenditure framework. For the first achievement, which sets an important precedent, DFID working with TCC could do more to measure the impact and attribution of the project’s advocacy efforts.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations
- DFID and TCC to consider future evaluation to measure the impact and attribution of the influencing and advocacy strategies of the project.
- As part of the logframe review, for the next phase of the programme, the team should modify this output to focus on the implementation of the advocacy strategy.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The most significant cost drivers for the project are staff salaries, consultant fees, travel, and meetings. These costs represent the bulk of project activities as the Carter Centre’s work focuses on technical support to civil society partners, both in-person and at a distance, as well as on in-depth engagement on key extractive sector issues. DFID staff are in constant contact with partners, providing instruction and guidance, reviewing activity plans and deliverables, and discussing strategies. While this support is the key driver of cost in the form of salaries and missions, it is also the most significant driver of project performance. In conjunction with the enthusiasm of partners, having the right staff is essential for the project to deliver.

VfM performance compared to the original VfM proposition in the business case

As in previous reviews, the Carter Centre continues to ensure value for money, by focusing on the economy, efficiency, effectiveness, and equity of its interventions. This includes the continuous review and assessment of mission costs, reducing costs where possible; regular oversight for civil society partners, particularly with regard to spending; using existing tools and skills to implement project activities, thus saving time and money; limiting administrative overhead as much as possible; systematically involving women in project activities; and working closely with partners and civil society more broadly to develop the skills and environment necessary to ensure that the project achieves its full impact and that that impact is sustainable. In particular:
- Carter Centre staff regularly review mission costs (meetings and travel). This has led the Centre to identify ways to save costs on travel (combining meetings, lengthening a single mission to avoid multiple missions, etc.) and to update its budget appropriately on a quarterly basis.
- The Centre’s sub-grantee selection process included a rigorous assessment of organizations’ technical and organizational capacity, and Centre staff worked closely with selected partners to develop practical and efficient project budgets. In addition, one of the partners and some of the members of other partners have worked with The Carter Centre previously and thus had baseline knowledge of the Centre’s sub-grant policies and procedures, limiting the time needed for onboarding.
- The project relies largely on previously developed training modules (the Revenues Analysis Training Modules and advocacy training modules), which has resulted in staff time and resources saved.
- By using pre and post testing of participants knowledge it is possible to ascertain (some) of the benefits of the programme and therefore, provide us with a basic benefits to cost ratio allowing us to continuously assess the net benefits of the programme.

Assessment of whether the programme continues to represent value for money

The project continues to represent value for money. Resources have been used efficiently to provide hands-on support to civil society partners and participate in key discussions on extractive sector governance. Civil society partners have experienced a number of continued successes, including ensuring a significant monetary payment has been secured from a mining company to the state. In addition, VfM has been secured through the Centre’s reliance on existing tools, relationships, and technical expertise to implement and support project activities and its assiduous management of project resources.

Quality of financial management

The Carter Centre’s quarterly financial reports are timely and their staff is available for any questions and clarifications. The financial report narrative could benefit from some analysis on value for money and some comparisons. The latest financial report submitted to DFID include detailed information on the cumulative variances between the USD and GBP exchange rate in place at the outset of the project up to the project end. This serves both to place the amounts reported in a more realistic context and also highlights the Carter Center’s contribution to the project by using internal TCC funds to hold the effective exchange rate constant over the life of the project in order to assure full implementation of the agreed objectives.

Date of last narrative financial report	13 June 2017
Date of last audited annual statement	24 March 2017

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk

Delivery risk – minor – this is low given the programme continues to perform well and exceed expectation. TCC will be working with new partners in the coming year. DFID will stay in close contact with the team to ensure this doesn’t affect delivery.

Fiduciary risk – minor - a due diligence assessment was undertaken by thee DFID DRC governance team in August 2013 and refreshed in May 2015. The Carter Centre also undertakes due diligence of its downstream partners which ensures there are financial controls at all levels.

Security risk – moderate – there is overall increased tension across DRC and the areas in which The Carter Centre operates. The Carter Centre staff maintain close contact with partners and their security advisor. There were occasions when staff were asked to minimise travel but this so far had limited impact on the project activities.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The AG was extended until July 2018, with new/ additional results.

Performance of partnership (s)

The partnership with the Carter Centre has been productive. The team has been very engaged and willing to work with DFID on a range of issues, going beyond the remit of the accountable grant. Outputs are being delivered on time and are to date exceeding expectations. The Carter Centre are responsive to demands and keep DFID informed of developments. This is especially welcomed given that the core project team is based in Lubumbashi, not Kinshasa.

Asset monitoring and control

There are no assets related to the Carter Centre accountable grant.

G: CONDITIONALITY

Update on partnership principles (if relevant)

None

H: MONITORING & EVALUATION

Evidence and evaluation

Evidence for this annual review has been gathered from:
- Reporting from the Carter Centre
- Discussion and feedback from the Carter Centre in Kinshasa and Lubumbashi
- A field visit to Lubumbashi in August 2017
- Discussions with key stakeholders – OCEAN, IBDGH and COSCCET-DEDQ.

Monitoring progress throughout the review period

Catch up meetings were held with the project team on a regular basis whenever they were in Kinshasa alongside periodic phone calls. In July and August 2017 the Economic Development Team Leader, Deputy Programme Manager and the Project Officer met the Carter Centre in Kinshasa and held update calls with the team in Atlanta. The team also met the Carter Centre partner OCEAN in Kinshasa. These meetings were followed by a visit by the Economic Adviser and the Project Officer to Lubumbashi to meet the Carter Centre, IBDGH and COSCCET-DEDQ.

The interviews consisted of questions on the results reported, the relationship between stakeholders, lessons learnt and challenges that the project faced.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process