ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS – August 2017

SUMMARY INFORMATION
Project Name	Programme Evidence Facility
Country or region targeted	Rwanda
Type of cost extension (if applicable)	Time and cost extension
Original project budget	£1,000,000
Original project start and end dates	June 2014 - July 2018
Cost extension value (if applicable)	£632,203
New project end date (if applicable)	March 2019
Business Case Vault Document No.	3577382

INFORMATION
What is the project’s purpose?
The purpose of the facility is to improve the effectiveness of programmes and interventions in support of the EDPRS by helping GoR, and Development Partners design and deliver policies and interventions that are evidence based and offer value for money. The facility focuses on core cross cutting themes that will underpin Rwanda’s equitable and inclusive growth and open governance agenda. / Impact statement: “better poverty-oriented, more evidence based and more cost effective policies and programmes in Rwanda”. / Outcome statement: “enhancement of the evidence base used to inform key poverty reduction policies and programmes of the Government of Rwanda and Development Partners”.
What is the objective of the cost and time extension or other changes?
The objective of the cost and time extension is to accommodate increasing requests for evidence gathering exercises in response to the ongoing design and implementation of Rwanda’s longer term development plans such as EDPRS3 and Vision 2050.
What is the additional and total support the UK will provide?
The UK will provide additional financial support up to £632,203 to the Programme Evidence Facility and a time extension from July 2018 to March 2019. The cost and time extension would provide greater opportunities for more evidence gathering and use within sufficient time to engage strategically with GoR and key stakeholders.
What are the expected results?
The primary expected result of this project is as an enhanced evidence base to inform key poverty reduction policies and programmes of the Government of Rwanda and Development Partners. This will lead to better poverty-oriented and more cost effective policies and programmes.
What is the approach to implementation?
PEF is A DFID Rwanda Evidence Facility funding evidence gathering activities that support the delivery of Rwanda’s Economic Development and Poverty Reduction Strategy (EDPRS II). The facility is governed by a management committee consisting of Team Leaders, the project lead, DFID Rwanda’s A2L Economist, and the Deputy Head of office acts as Chair. The management committee convenes at least once a quarter, acting as the forum to discuss knowledge gaps and proposals to address such gaps. Proposals are presented by Team Leaders, delegating to individual team members as necessary. / Contribution to gender equality: / This project is expected to make a contribution to reducing gender inequality. It will do so by funding analysis and addressing key knowledge gaps to support the delivery of equitable and inclusive growth and an open governance agenda in Rwanda. This contribution, however, will depend upon the facility financing analytical work with a gender lens, and ensuring disaggregation of any data collected and/or analysed.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The original business (approved in August 2014) and the Theory of Change underpinning the original Business Case still hold.