Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Tax Administration Diagnostic Assessment Tool (TADAT)
Programme Value: £1,783,000		Review Date: August 2017
Programme Code: 204114	Start Date:24/07/2013	End Date: 30/12/2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	B	A	B
Risk Rating	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

Overall, the programme has made good progress in achieving its outputs but has not met the challenging indicator 2.1 (number of assessments in developing countries), thereby scoring an ‘B’ grade. The management of the programme by the TADAT Steering Committee continues to be on track. Although the use of TADAT by developing countries has noticeably slowed over the last year meaning that the Log Frame target has been missed, the review recommends that the target is reviewed so that it challenging but achievable for the next review. Indications from the online survey on TADAT that was conducted in November 2016 show that the TADAT framework is increasingly being used as a baseline to inform tax administration reform programmes of assessed countries. There is also significant evidence from DFID country programmes on how these assessments have facilitated dialogue around tax reform within countries’ revenue authorities.

A key lesson learned during this period is on the importance of understanding the context in which the TADAT assessment takes place, where different political and economic factors may affect the assessment itself, and the level of dialogue and uptake of recommendations around it by local revenue authorities thereafter. This partly places emphasis on the importance of communication around the tool itself, and that extends into all areas of the process around the assessment, including i) pre-assessment engagement ii) how Mission Leads and teams interact with contacts in local revenue authorities iii) how the findings are presented to local authorities, and iv) what processes there might be to follow up with local authorities after the assessment.

Summary of recommendations for the next year

	Recommendation
1	Logframe: It is recommended that DFID consult with the TADAT Secretariat on the suggested indicators to outputs 1 and 2 to reflect work being conducted by the TADAT Secretariat and better aligned to the TADAT Logframe: / Add indicator 1.2: TADAT is kept up-to-date with good practices that are tested, proven and applied by the majority of leading tax administrations. Target 2018: Position/guidance notes issued as necessary following approval by TADAT Steering Committee and Technical Advisory Group / Modify indicator 2.1: is recommended that DFID work closely with the Secretariat on agreeing a shared indicator outlining a) the total number of assessments it sets out to undertake and b) of those, how many are in developing in countries. / Add indicator 2.4: Number of institutional groups, and technical providers using the TADAT. Target 2018: All TADAT partners using the tool in assessments. / Add indicator 2.5: TADAT Secretariat ensures that assessments are of high quality. Target 2018: All TADAT Performance Assessment Reports go through certification process.
2	Risks: It is recommended that some risks are revised, and new ones added, and that they be monitored quarterly by DFID. / New Risks: / Insufficient ownership of TADAT assessment by tax authorities within developing countries / TADAT assessments do not respond to developing countries’ ways of working / DFID country offices and other donors are not engaged in TADAT assessments
3	Value for Money / It is recommended that DFID works closely with the Secretariat, following the results of the the Mid-Term Evaluation to assess the overall VfM of the programme, including a comparison of costs of similar tools. / It is recommended that the Secretariat conduct a VfM assessment to determine whether the cost and effort that they have put into training of assessors matches the demand that exists for assessors. This can either be done as part of the evaluation or by a quality assured Secretariat VfM assessment. / It is recommended that the Secratriat set out clearly to donors the rationale, purpose and value for money (including objectives of the project, costs and results etc.) of the development of e-TADAT and accompanying mobile application.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204114/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204114/documents

Context

The development of the Tax Administration Diagnostic Assessment Tool (TADAT), which is managed by a secretariat based at the IMF, is part of wider international efforts to strengthen developing country tax systems so that domestic revenues are better mobilised to fund public services and investment. TADAT follows on from the success of the public expenditure and financial accountability (PEFA) programme, run by the World Bank, which assesses the condition of a country’s public financial management. The two programmes complement one another with a similar design and structure.

Why UK support?

DFID’s funding of TADAT (i) supports the maintenance of a tool that promotes a global benchmark for the international community (ii) will have real practical uses as an essential element for developing countries when reforming their tax systems and (iii) be of use for donors when working to build capacity in developing country revenue authorities. Being a significant donor and partner in TADAT also reinforces the UK’s international leadership on tax and development.

Programme description

DFID provides funding over 4 financial years (from 2014/15 to 2017/18) to the Tax Administration Diagnostic Assessment Tool (TADAT). TADAT activity is managed by a small secretariat based in the International Monetary Fund (IMF). TADAT activity is directed by a Steering Committee comprised of representatives from the IMF, the World Bank and partner donor countries (the UK, Norway, Switzerland, the Netherlands, Germany, Japan and the European Commission), which is assisted by a Technical Advisory Group (TAG).

TADAT is a monitoring framework that measures the performance of a country’s tax administration at a point in time by carrying out assessments of essential tax administration functions against performance indicators. TADAT country assessments can facilitate discussion among country authorities and donors about tax capacity building and will be the basis for setting the direction of reform of tax administrations. Repeated application of the assessments should provide information on the extent to which a country’s tax administration is improving as a result of post assessment responses by the government and donors.

Ultimately, the implementation and use of TADAT will underpin more effective tax reform in developing countries, which will lead to higher tax revenues, better governance and provision of services to the public and less dependence on aid.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is: TADAT assessments will improve knowledge of the performance of a country’s tax systems and facilitate discussion amongst stakeholders (country authorities, international organisations and donor countries), and be the basis for the setting of the direction of tax administration reform.

Outcome Indicator	Baseline	2017 Milestone	Progress
1.1 Extent to which TADAT assessments facilitate dialogue about tax administration reform and directly influence donor programmes and tax administration reform plans	No dialogues or reform plans based on TADAT assessments	TADAT assessments facilitate dialogue and influence reforms plans in all cases	Largely on track
Source: Feedback from stakeholders as to the extent that TADAT assessments facilitate discussion - supplied by TADAT secretariat and DFID country programmes

Since the last Annual Review, there has been some evidence that TADAT assessments are being used largely to this effect; The TADAT Secretariat reported on the results of the survey (conducted in November 2016) in their annual report, which concluded that “the TADAT framework is increasingly being used as a baseline to inform tax administration reform programs of assessed countries. There was evidence of some tax administrations using it for internal benchmarking purposes and tax administration experts using the frameworks as a reference guide.” It also showed that assessment results were being integrated into reform programmes supported by partners in several countries (e.g. Rwanda, Tanzania). The TADAT Secretariat also noted that there has been increased use of TADAT, or aspects of it, by several countries as a tool for internal benchmarking (e.g. Afghanistan, Brazil, Ireland, Singapore, and Australia). Furthermore, the TADAT Steering Committee was informed that the TADAT received positive focus in June 2017 during the G20 and that there was demand for use of the TADAT indicators by the Addis Tax Initiative member countries.

There is strong evidence from DFID country programmes (e.g. Sierra Leone – explained below) where TADAT assessments have been undertaken that have facilitated dialogue on tax reform with local tax administrations and have helped inform DFID programmes moving forward. In Sierra Leone, the HMRC assessor involved in the assessment was very positive about the process, highlighting as key to its success, the engagement by the Mission Lead, or lead assessor, with the local Revenue Authority or ‘Point of Contact’. Dialogue around the TADAT was good, and the local Revenue Authority prioritized its reforms according to the assessment. For DFID in country, the TADAT assessment then helped restructure its revenue programme to inform its intervention, and it now uses TADAT indicators to measure its outcomes. In Ghana, a recent assessment took place that was well received by the local authorities, and there will likely be a follow-up mission in September to the development of an implementation plan for key actions.

However, there was one example of where an assessment was not as impactful; there was no clear follow up on the assessment. With the emergence of the recently developed Medium Term Revenue Strategies (MTRS) by the IMF, both revenue authorities and donors will have a focus for the development of reform plans that will target improvements to tax administration identified by a TADAT assessment, which will be a useful tool to incentivise reform after an assessment has taken place. However, an MTRS will not be available in all countries so efforts must be made to ensure that momentum generated by the assessment is not lost.

The 2016 annual review recommended that DFID work with the Secretariat to develop the formal survey that will monitor the use of assessments in developing reform plans, including through feedback from DFID tax programmes the results of which have helped to inform the assessment of the outcome of the programme This was done, and the survey that was conducted in November 2016 looked at how assessments impact reform programmes.

Overall output score and description

	Output	Score	Weighting %
1	TADAT infrastructure is in place – e.g. the assessment tool is finalised, the management structure is in place and TADAT is fully operational	A	30%
2	TADAT is globally recognised as producing high quality and standardised tax administration diagnostic assessments which are undertaken in a sufficient proportion of developing countries, identifying the relative strengths and weaknesses of their tax administration systems.	B	70%

Key lessons
- Training A) Significant focus has been placed by the programme on the training of assessors. DFID has expressed concern over the need to train such a high number of assessors, between 200-250 qualified assessors. However, the TADAT Secretariat noted that this number is needed as i) most assessors are already full-time employees and may not be readily available to participate in assessments when needed, and ii) assessors not attached to particular tax administrations would have to be paid a salary by the sponsoring agency and iii) those that are attached would normally take leave to be paid assessors. As a result, the TADAT Steering Committee resolved not to have a limit on the number of qualified assessors. However, it should be noted that interviews with HMRC assessors suggested that they had more capacity to undertake more assessments during the year, although generally HMRC restricted HMRC participation in assessments to DFID priority countries. It is therefore important to find a balance and re-visit the training strategy to articulate more clearly what the vision is.
- Training B) According to assessors, the process of the assessment itself is crucial in determining how the local revenue authorities accepts or internalises the results and recommendations of the assessment. This emphasises the importance of the quality of the team that is sent to do the assessments and the involvement of local partners. Crucial are the Mission Lead, and their counterpart or the Point of Contact within the local revenue authority. Another key point noted by an HMRC assessor, was that training local authorities on TADAT in advance of the assessment, proved beneficial, by creating a greater sense of internalisation of the issues raised, and ownership of action plans to address recommendations moving forward.
- Some concerns were raised from the survey and also in individual interviews around whether a TADAT Assessment could incentivise a Tax Administration to target ‘quick wins’ to improve scores rather than tackling the most pressing and difficult challenges of their administration; the TADAT Secretariat recognised this and stated that when communicating with tax administrations and their staff, it was crucial to make them aware of where the overall risks to revenue that should be addressed and not to just report assessment scores. This is done during the sessions where administration staff are trained on TADAT prior to the assessment (Uganda, Rwanda and Nigeria are currently undergoing this training). A DFID adviser mentioned that there could be benefit in adopting an approach similar to the Fiscal Transparency Evaluation (FTE) tool; where particular risks pertaining to the specific context are identified and flagged to the partner rather than just the broad assessment approach that TADAT and PEFA takes. The Secretariat may want to explore this further for how a similar approach could be taken up, if not in the TADAT framework then in post-assessment discusions or as part of the MTRS framework.
- Some countries where DFID operates may not be clear on the advantages of TADAT or how to use it. For example, in Kyrgyzstan the DFID country office were not aware that an assessment was happening. It is therefore recommended that DFID Advisers working on Tax reform programmes are identified and plugged into the Tax Community of Practice within DFID as much of possible.

Key actions
- Amend logframe in consultation with TADAT Secretariat, responding to the recommendations within the Annual Review.
- Incorporate DFID requests on measuring Value for Money within next Mid-Term external evaluation of the TADAT programme; TADAT secretariat to review VfM of training and e-TADAT.
- Review recommended risks, and monitor them on a quarterly basis.

Has the logframe been updated since the last review? Yes
Summary of changes
Output Indicator 1: Indicator 1.1 and 1.2 were merged to monitor the ongoing delivery of the programme work plan as monitored by TADAT’s Log Frame.
Output indicator 2.2: Given that no further actions were to be taken, this indicator ended in 2016 and the logframe was amended to reflect this.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	TADAT infrastructure is in place – e.g. the assessment tool is finalised, the management structure is in place and TADAT is fully operational
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Extent to which the assessment tool and the indicators are finalised	Annual work programme continues to be delivered. Management in steady state	Achieved
Source: TADAT Secretariat / Annual reports / 3 year external audit

Key Points

Indicator 1.1: Achieved. The indicator measures the performance against work plans and the steady state of management. According to the TADAT Secretariat and Annual Reports, the progress against indicators identified within the TADAT Secretariat’s own logframe (separate from the DFID programme logframe) are on track across the four outcome areas; preferred assessment tool, effective dissemination, systemic quality assurance, and positive impact. Although spend has not matched budget (see details below on financial performance) the programme has managed to achieve the targets set out for itself.

Summary of responses to issues raised in previous annual reviews (where relevant)
- It was recommended that indicator 1.1 and 1.2 be merged so that they monitor the ongoing delivery of the programme work plan as monitored by TADAT’s Log Frame. The logframe was modified to reflect this change.
- Recommendation to amend indicator 1 so that it measures the continual delivery of the work plan as delivered against the TADAT programme Log Frame. The logframe was modified to reflect this change.

Recommendations

Add indicator 1.2: TADAT is kept up-to-date with good practices that are tested, proven and applied by the majority of leading tax administrations. Target 2018: Position/guidance notes issued as necessary following approval by TADAT Steering Committee and Technical Advisory Group

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	TADAT is globally recognised as producing high quality and standardised tax administration diagnostic assessments which are undertaken in a sufficient proportion of developing countries, identifying the relative strengths and weaknesses of their tax administration systems.
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	70%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 The number of assessments undertaken by TADAT in developing countries	20 assessments in developing countries (2017)	Not met. 10 assessments (counting from May 2016 to April 2017) in developing countries. 19 TADAT assessments overall.
Source: TADAT Secretariat / Annual reports / 3 year external audit
2.2 Number of TADAT assessments facilitated and funded by DFID	Three TADAT assessments undertaken in DFID priority countries with BC funds (end 2016)	No longer measured.
Source: GOSAC / DFID country offices
2.3 TADAT is recognised as the principle assessment tool for objectively assessing tax administration performance	80% (indicative) of feedback from stakeholders through perception survey is positive Target (2018)	To be measured in 2018
Source: External perception of TADAT measured through perception surveys or other documented evidence across stakeholders.

Key Points
Indicator 2.1: The TADAT secretariat have reported that from May 2016 up till April 2017 (the TADAT secretariat’s reporting period), there were 10 assessments in developing countries (low income and lower-middle income), and nine in non-developing countries (upper middle and high income). However, due to the cluster of reviews in summer 2016, which were reported in last year’s annual report, only five of the developing country assessments fall within the reporting period for the DFID review year (August 2016-August 2017), meaning that they have fallen short of the DFID target.

Over the last year there has been a notable slow down in the number of assessments in developing countries following an initial spurt in the first year following launch. The upcoming assesments (Moldova, Mauritius, Belarus but also Niger) do not indicate that this trend is reversing. This is worrying as it means that TADAT is not delivering in the poorest countries.

The Secretariat has worked to address this by further promoting the tool to countries that have not yet had assessments. They foresee that there will be around 20 assessments annually, as per the workplan; with developing country interest being maintained through Addis Tax Initiative members and the proactive stance on assessments by the IMF and other partners. The African Tax Administration Forum (particularly the West African chapter) is also intent on promoting use of the tool (and assessments) amongst its membership. The TADAT Secretariat will continue its outreach work to promote the tool as the preferred assessment tool to developing countries. It is also up to donors (including DFID) to generate the demand in developing countries for use of the TADAT.

The delivery of TADAT assessments should rightly be focussed primarily in developing countries but the DFID Log Frame indicator of 20 developing country assessmentsa year, at the exclusion of upper middle income country assessments, is very challenging and given the current levels of demand not necessarily achievable. Although 20 assessments a year is a good steady state for the programme DFID should review and agree, along with the Secretariat a suitable assessment target indicator that is challenging but also achievable now that demand is clearer. The target should maintain a commitment to deliver a certain amount of assessments in the poorest countries. Futhermore, the DFID reporting year for this indicator should align with the TADAT Secretariat reporting year.

TADAT assessments from May 2016-April 2017
	Country (*developing country)	Income classification	Period	DFID AR
1	FYR Macedonia	Upper Middle Income	May 2016	2016
2	Namibia	Upper Middle Income	May 2016	2016
3	Vietnam*	Lower Middle Income	May 2016	2016
4	Zambia (repeat)*	Lower Middle Income	May 2016	2016
5	Georgia	Upper Middle Income	May 2016	2016
6	Albania	Upper Middle Income	June 2016	2016
7	Liberia*	Low income	June 2016	2016
8	Kyrgyzstan*	Lower Middle Income	June 2016	2016
9	Sierra Leone*	Low Income	August 2016	2016
10	Congo (DFID priority country)*	Low Income	July/August 2016	2017
11	Romania	Upper Middle Income	September 2016	2017
12	Barbados	High Income	October 2016	2017
13	Armenia*	Lower/Middle Income	October/November 2016	2017
14	Kenya (DFID priority country)*	Lower Middle Income	November 2016	2017
15	Dominican Republic	Upper Middle Income	December 2016	2017
16	Bangladesh (DFID priority country)*	Lower Middle Income	March 2017	2017
17	Peru	Upper Middle Income	March 2017	2017
18	Guyana	Upper Middle Income	March 2017	2017
19	Cameroon*	Lower Middle Income	April 2017	2017

* denotes developing country (low income or lower middle income)

Summary of responses to issues raised in previous annual reviews (where relevant)
Indicator 2.2: It was recommended that DFID works with its country offices to strongly encourage the use of TADAT as a diagnostic tool with the aim of leading and participating in further assessments in DFID countries. DFID, through the Tax Community of Practice, has engaged with DFID country offices on TADAT but might benefit from keep close watch of where assessments will take place, and communicating it to country offices as an extra layer of assurance.

Indicator 2.2.: It was recommended to change indicator 2.2. To reflect whatever the outcome of the review into how DFID programmes should engage with TADAT. Output indicator 2.2. Was removed and it is now expected that DFID country offices should contribute to funding TADAT assessments.

Recommendations
Indicator 2.1: It is recommended that DFID works closely with the Secretariat on agreeing a shared indicator outlining a new realistic target for a) the total number of assessments it sets out to undertake and b) of those, how many are in developing in countries. Looking closely at the annual cycle of assessments (from April to May following year), the Secretariat looks to conduct 20 assessments a year, of which around 10 assessments happen in developing countries. If agreed with the Secretariat, then the indicator could be ‘20 assessments annually of which 10 are in developing countries’ or alternatively the scope of the 20 developing country assessments could be expanded to include upper middle income countries.

Add indicator 2.4: Number of institutional groups, and technical providers using the TADAT. Target 2018: All TADAT partners using the tool in assessments.

Add indicator 2.5: TADAT Secretariat ensures that assessments are of high quality. Target 2018: All TADAT Performance Assessment Reports go through certification process.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are administrative costs for managing the Trust Fund (7%), and the maintenance and promotion of the TADAT tool (salaries of staff, technical experts and subsistence costs). To this end, programme budget for the reporting year (2,319,927) exceeded spend (1,561,840 USD) by 758,087 USD. This counters the narrative of the previous Annual Review where the TADAT Secretariat expected to see increased activity during this reporting year, raising its budget as a result. The main areas where spend was significantly below budget was on outcome 1 (preferred assessment tool) and outcome 2 (effective dissemination) within the TADAT logframe. The IMF attributes the main reasons for underspend on staff vacancies, a lag in the IMF’s financial systems, and prudent financial management. The steering committee has approved a budget for FY 2017/18 (year 5 of the programme) of US $2.2 million. Cost drivers over the next year include the mid-term performance evaluation of the Trust Fund, the development of a supplementary Field Guide for subnational TADAT assessments and preparation to refine the current national-level Field Guide.

VfM performance compared to the original VfM proposition in the business case
The Business Case indicated that DFID will be able to assess Value for Money throughout the programme by monitoring information as a member of the Steering Committee. A welcome development in 2017 was a strategic partnership agreement between DFID and the IMF’s Institute for Capacity Development within the Global Partnerships Division. The metrics have been shared with DFID, and by early August 2017, the Secretariat will have some data and an analysis to share with DFID on how to integrate these metrics into the TADAT programme.

In order to assess VfM more closely we have decided to use the opportunity of the upcoming Mid-Term Evaluation, working closely with the Secretariat, to make a comparisons of costs of similar tools (PEFA and other IMF trust funds). This will include a comparison with the cost of PEFA, testing the statement in the original business case that TADAT costs are less than PEFA. The Secretariat noted how existing platforms are using the outcomes of TADAT assessments to define and agree on reforms in tax administration areas; the Medium Term Revenue Strategy will be worth monitoring going forward.

Assessment of whether the programme continues to represent value for money
Given the good management and performance of the programme to date, the assessments undertaken in DFID priority countries and the effect they are having in promoting dialogue on reform (as evidenced during interviews and survey results), then it is the reviewers judgement that this programme continues to represent value for money. However, available comparable metrics are currently minimal making a quantitative assessment of overall VfM difficult.

It is recommended that the Value for Money of two components that have developed over the course of the programme be conducted; the Training of assessors and the E-TADAT.

- Training: As of May 2017 1,023 persons have been trained in the TADAT methodology and successfully passed the exam, of which 307 have been formally trained TADAT assessors. However, with 20 assessments a year and five staff on each assessment it is not clear where the demand will come from to utilise all of the resource, whether trained online at little cost or at a workshop with much greater unit cost.
- E-TADAT: The rationale, purpose and value for money of the development of e-TADAT and accompanying mobile application should be more clearly defined by the Secretariat.

Quality of financial management

Financial contributions are paid into a multi-donor subaccount established by the IMF that is used to finance activities of the TADAT Secretariat. The IMF administers the account for donors in accordance to its financial regulations, practices and procedures. The operations and transactions are audited as part of the IMF’s Framework Administered account and the reports are posted on the IMF’s external website. Further financial reporting is provided at Steering Committee meetings.

Date of last narrative financial report	June 2017
Date of last audited annual statement	Oct 21st 2016

E: RISK

Overall risk rating: Minor/Moderate
Overall, the programme continues to represent only minor risks given the administrative nature of the programme; where the risks around proving efficacy and Value for Money were the most relevant. Over the last year, the programme’s performance has been satisfactory. Most outputs identified within the TADAT logframe have been achieved, and there is evidence building that that programme will achieve the desired outcome.

Overview of programme risk
There are four programmatic risks identified i) recruitment of experts ii) the take-up of TADAT by developing countries iii) their capacity to implement necessary reform, and iv) the number of assessment carried out in DFID priority countries (see detailed assessment below). New risks have been identified and are recommended to be monitored quarterly (see *).

Risks	Current Rating	Assessment 2017	Suggested Rating
Tax authorities in TADAT countries have insufficient capacity to implement necessary reforms.	Rating: Major / Impact: Major / Likelihood: Possible	There are signs that TADAT countries are developing action plans/programmes with donor countries to implement reform. The risk remains that many countries do have the capacity to implement reforms but the risk will be mitigated as donors scale up resources through their ATI commitments	Risks remain
Too few assessments are carried out in DFID priority countries.	Rating: Major / Impact: Moderate / Likelihood: Possible	Several DFID priority countries have had assessments exceeding the target number within the logframe. However, the number of assessments in DFID countries and also developing countries has slowed over the last year and the risk remains that there the focus of TADAT moves away from those that most need it.	Risks remain
Take-up of TADAT by developing country tax administrations is low.	Rating: Major / Impact: Major / Likelihood: Unlikely	The majority of assessments are in developing countries; however, uptake has reduced over the past year. Secretariat should continue to promote TADAT in developing countries. Donors (including DFID) should continue to promote in their countries.	Risks remain
The TADAT Secretariat cannot recruit technical experts to carry out TADAT assessments.	Rating: / Impact: Major / Likelihood: Unlikely	As the previous AR identified, this risk was not realised, and focus should be on quality of assessors rather than numbers of accredited assessors.	Remove.
*Insufficient ownership of TADAT assessment by tax authorities within developing countries	New risk / Rating: Moderate	The risk is around how developing countries interact with the process of the TADAT assessment/process. To mitigate this risk, it is important to clearly identify to beneficiaries what the benefits of undertaking a TADAT assessment are, ensuring that ‘change champions’ are involved in the process within local Revenue Authorities and capable/experienced Team leaders used. Furthermore, communication on the risks around revenue should continue to be communicated ahead of assessments, and the tool should continue to seek feedback, incorporating and improving the tool to capture the realities, tailoring, as much as possible, to different countries’ systems.	Impact: Minor / Likelihood: Possible
Donor countries are not engaged in TADAT assessments thereby diminishing their impact.	New risk / Rating: Moderate	There is a risk that TADAT assessments happen without the knowledge of donor country offices; to mitigate this, it is important that the Secretariat and donors reach out to country offices in advance, where it knows an assessment will take place. The development and uptake of Medium Term Revenue Stratgies in developing countries will mitigate this risk as they will allow countries to take ownership of reform processes and provide a structure for all donors to engage with development of reform plans (including diagnostic).	Impact: Minor / Likelihood: / Possible

Outstanding actions from risk assessment
Risks continue to be treated in line with the Risk Matrix. There are no outstanding actions from risk assessments. However, it is recommended that the DFID team continue to monitor the risks closely, on a quarterly basis, and seek feedback from DFID country offices where assessments are being undertaken as much as possible.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The TADAT Steering Committee report on the logframe was agreed by the members of the Committee and progress towards achieving milestones within the logframe is on track.

Performance of partnership (s)
The working relationship between the TADAT Secretariat and DFID is good; DFID attends Steering Committee meetings and is engaged in programme deliverables. The TADAT Secretariat noted that the current governance structure has worked very well for the programme, and that the model used is being advocated for other IMF Trust Funds. DFID has taken up the role of Vice-Chair of the Steering Committee for the coming year and we move to Chair in mid-2018.

Asset monitoring and control
DFID is in regular contact with the TADAT secretariat. DFID receives annual account information about programme spend and monitors progress in the programme as a member of the Steering Committee.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not relevant

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
In November 2016, an independent survey was conducted that looked at the TADAT and how it is being perceived within beneficiary countries by assessors and beneficiary countries. This was also used to inform the outcome indicator within this Annual Review.

An independent Mid- Term Evaluation of the TADAT programme is scheduled to take place by December 2017; this will mainly focus on the lessons learned from completed TADAT assessments and the processes around them, and their overall impact within beneficiary countries.

Annual Review
The review was carried out by a Governance Adviser and quality assured by the Senior Responsible Owner (SRO). Extensive reporting on progress, together with supporting documentation, was provided by the implementing partners. The reviewer also interviewed DFID and HMG staff who have had experience with TADAT as assessors and Tax programmes within DFID country offices.

Monitoring progress throughout the review period
The programme sits within the Governance, Open Societies and Anti-Corruption (GOSAC) department at DFID; DFID monitors progress through its membership of the TADAT Steering Committee.

The team monitors progress through:
- Bi-annual Steering Committee meetings
- Progress reports (narrative and financial)
- Regular engagement with the TADAT Secretariat

The secretariat also produces a bimonthly TADAT newsletter that is made available to the public on the TADAT website (www.tadat.org).

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process