Annual Review

Title: Sustainable Urban Economic Development (SUED) Programme
Programme Value: £60M		Review Date: August 2017
Programme Code: 204338	Start Date: August 2016	End Date: August 2022

Summary of Programme Performance

Year	2017
Programme Score	C
Risk Rating	Major

This is the first annual review of the DFID Kenya Sustainable Urban Economic Development (SUED) programme. In May 2016, DFID Ministers approved £75m for the programme, however, following a subsequent DFID-wide budget review process the programme was reduced in size to £60m. As the 6-year programme extends beyond the UK government spending review period, a subsequent approval from Her Majesty’s Treasury (HMT) was also required prior to proceeding, which was obtained at the end of August 2016. Depending upon programme performance, there will be an opportunity to increase the budget and extend the programme timeframe by up to an additional 3 years in the future.

Kenya is rapidly urbanizing, with an urban population that is now expected to rise by over 50% by 2030. Poorly planned urbanisation can result in an array of poor informal settlements and population centres that are more vulnerable to environmental shocks. SUED will support fast growing towns in Kenya to put in place sustainable urban economic plans; improve their investment climate and draw in investment for climate-resilient infrastructure and value chain projects. The intended outcome is to increase incomes and job opportunities in value chain sectors that are resilient to climate change, improving the sustainability of cities. The intended impact is increased economic development in Kenya that lowers risks of fragility, is inclusive, economically sustainable and resilient to climate change.

The programme will be implemented by a:

1. Managing Agent (prime contractor) providing programme management, technical oversight and a coordination role, along with a consortium of firms/specialists (subcontractors) comprising of:
  1. urban economic planning firm,
  2. investment climate firm,
  3. investment firm, and
  4. other capacity building specialists; and

Complementary strategic partner, in this case the World Bank, to carry out business environment strengthening work at the national level, as well as at the county level in close coordination with the investment climate firm.

In addition, an independent Monitoring and Evaluation (M&E) firm will be put in place to support programme learning and adaptation, and to critically determine whether the programme is or is not achieving its intended outputs and objectives.

Summary of Progress

1. The first year of the programme has focused on mobilization, and specifically procurement of the Managing Agent consortium and the M&E firm, which has taken much longer than originally envisaged. This has been primarily due to:
  1. A protracted phase for developing the Managing Agent consortium and M&E firm ToRs, largely due to change overs in the DFID team, needing to get up to speed with a complex 72-page Business Case (plus 5 annexes) and the importance of ensuring complementary and reinforcing roles for each of the Managing Agent consortium, M&E firm and separate strategic partner (~4 months);
  2. A DFID wide ‘supplier review’ temporarily halting new procurement engagements (~1 month); and
  3. Additional procurement steps being designed (~1 month) and introduced, namely (i) development of a sourcing strategy (~1 month), (ii) obtaining approval from a Procurement Steering Board (PSB) (~2 months)[1], and (iii) obtaining approval from Cabinet Office (~1 month).
    [1] This step involved two submissions as the PSB required further clarifications on the programme.

1. Nonetheless, during the course of the first year, the DFID Kenya team has:
  1. Undertaken scoping visits to, and considered existing development plans for, some of the strategically identified secondary towns/counties such as Bungoma, Lodwar, Isiolo and Kwale (fieldtrips in January, February and June);
  2. Negotiated and agreed with the World Bank a concept note for a strategic partnership, along with establishment of a Trust Fund, which will start implementation as soon as is practicable following the outcome from the Kenya elections in August 2017 and taking off from where DFID Kenya support to substantially similar areas under the Building a Reliable Investment Climate in Kenya (BRICK) programme ended prior to the elections in June 2017; and
  3. Enhanced knowledge and understanding of urban economic development issues in Kenya through (i) hosting a substantial urban economic development market engagement event[2]; (ii) contributing in a World Resource Institute urbanization conference in Nairobi and University of Glasgow hosted Urban Big Data Centre discussion with DFID staff; and (ii) sharing Kenya urban trends/challenges at a DFID Infrastructure & Cities for Economic Development (ICED) programme session on the future of DFID infrastructure technical assistance (June) and participating in a study on “Boosting Youth Employment through Infrastructure Programming” (May) particularly important given that youth employment is a cross-cutting priority for the DFID Kenya office.
    [2] Which included a 31-slide PPT on key urban economic development issues/plans in Kenya.

Overall, the programme risk is assessed as ‘major’, primarily due to the delivery risk associated with the slow mobilization. See recommendations below on how best to mitigate this risk going forward.

Key lessons learnt

Procurement processes can be subject to change and may take much longer than originally anticipated, which can significantly delay programme implementation. Given the experience of SUED, programme teams should now factor in at least 12 months for carryng out procurement processes. This should also be carried out in close coordination with designated PCD counterparts and clear agreements on procurement milestones, holding each other to account for delivery at each step.

While procurement processes are ongoing, managing partner expectations on a regular basis is key to sustaining interest, enabling the market to prepare for opportunities and for stakeholders to plan accordingly.

Summary of recommendations for the next year

Prioritizing completion of the procurement process by January 2018 is fundamental for the programme to be able to achieve 2018 milestones on-time. By way of improvement measures, the DFID Kenya team should put in place concrete, weekly/monthly, procurement milestones between September 2017 and January 2018 and report to the Head of Office on progress in November 2017 and January 2018.

By end-October 2017, the DFID Kenya team and PCD counterparts should organize an after action review and share lessons with other programme teams on how best to prepare for, and avoid pitfalls of, the new procurement steps and processes.

As the SUED Managing Agent consortium won’t be in place until January 2018 but as current County Integrated Development Plans (CIDPs) end in December 2017, the DFID Kenya team should engage priority counties[3] after the August 2017 elections and prior to December 2017 to explore how best to input into development of the next 5-year county development plans.
[3] To be undertaken in coordination with the rest of HMG in Kenya and as part of the HMG ‘100 day offer’ to government after the Kenya elections.

In the SUED inception and implementation phases, working effectively alongside other new/evolving donor initiatives (such as the World Bank $300m urban planning credit to government and TradeMark East Africa’s Phase 2 support to ‘growth hubs’) should be prioritized and overseen early on through earlty establishment of the SUED Steering Committee.

In the SUED inception and implementation phases, DFID Kenya priorities of youth employment and a focus on Northern/ASAL counties in Kenya should be sufficiently integrated into SUED and opportunities to learn from and collaborate with ICED and DFID’s EARH team regularly assessed and pursued as appropriate.

A. Introduction and Context

DevTracker Link to Business Case:	n/a
DevTracker Link to Log frame:	n/a

Programme Overview

SUED will support inclusive economic development in Kenya by helping strategically identified towns that fall along secondary growth corridors in Kenya to put in place sustainable urban economic development plans; improve their investment climate, and draw in investment for key climate-resilient infrastructure and value chain projects. The programme will be delivered through World Bank technical assistance (see page 8 for detail) and a Managing Agent consortium which will provide the following support for the selected towns:
1. World class, experienced urban economic planners to help the towns develop plans that will revolutionize them into Kenya’s green growth hubs of the future;
2. Investment climate advisers to help the towns remove policy and regulatory constraints to private sector led urban growth;
3. Investment experts to help the towns develop and implement investment promotion strategies and draw in investment (including Public Private Partnerships (PPPs)) to fund profitable infrastructure and value chain projects identified in their urban economic plans. Seed financing will also be provided to projects as necessary; and
4. Other capacity building specialists to support priorities identified in the urban economic plans to enable towns to enhance their capacity and revenue generation in order to continue managing the increased activity levels even after the project ends.
Programme Objectives

SUED aims to increase incomes and job opportunities in value chain sectors that are resilient to climate change, improving the sustainability of cities. The intended impact is increased economic development in Kenya that lowers risks of fragility, is inclusive, economically sustainable and resilient to climate change.

Context

Kenya is the largest economy in East Africa and has achieved over 5% annual growth in the last decade.  However, Kenya suffers from high levels of poverty and the World Bank estimates that to reduce the poverty headcount from 43% (in 2005) to 15% by 2030, Kenya’s growth rate must rise to at least 6%. Towns and cities are important for economic growth as higher population density allows for greater specialization and deeper markets, and makes infrastructure and business support services more cost effective. Kenya is currently rapidly urbanizing with an urban population that is expected to rise by over 50% by 2030. However, poorly planned urbanisation can result in an array of poor informal settlements and population centres that are more vulnerable to environmental shocks. Accordingly, DFID is supporting emerging urban centres in Kenya to put in place sustainable urban economic plans; improve the investment climate and draw in investment for key climate-resilient infrastructure and value chain projects. This will include integrating digital technologies to build ‘smart’ towns/cities that improve the quality and performance of urban services and enable a better quality of life. Although the 3 major cities of Nairobi, Mombasa and Kisumu along the Northern Corridor in Kenya contain 50% of the country’s urban population, towns situated on secondary economic growth corridors linked to these centres are seeing the fastest population growth, with the urban population outside of Nairobi growing at 7.3% a year. Supporting these smaller, faster growing, population centres also presents an excellent opportunity for achieving more balanced growth by focusing on areas which have historically been more marginalized, such as towns in North/Northern Eastern Kenya and Arid and Semi-Arid Lands (ASALs) more generally.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

N/A – It is too early to measure performance against programme outcomes.

Overall output score and description

C – Outputs substantially did not meet expectation. The mobilization phase, and specifically procurement of the Managing Agent consortium and the M&E firm, has taken much longer than originally envisaged, and accordingly Output 1 has scored a ‘C’. Outputs 2 & 3 are not being marked in this annual review. Outputs 4 & 5 have both moderately not met expectations (with a weighted average resulting in a ‘C’ score overall for the programme).

Output	Impact weighting	Risk rating	Score
1. Improved capacity of selected secondary towns to plan and deliver market-driven urban economic planning	60%	Major	C
2. Facilitation of public-private financing of climate resilient infrastructure	N/A	Moderate	N/A for this annual review.
3. Facilitation of value chain development projects, connecting to economic growth corridors	N/A	Moderate	N/A for this annual review.
4. County level business environment reform interventions are undertaken	30%	Moderate	B
5. Increased knowledge and information on sustainable urban development	10%	Minor	B

Key lessons learnt

Procurement processes can be subject to change and may take much longer than originally anticipated, which can significantly delay programme implementation. Given the experience of SUED, programme teams should now factor in at least 12 months for carryng out procurement processes. This should also be carried out in close coordination with designated PCD counterparts and clear agreements on procurement milestones, holding each other to account for delivery at each step.

While procurement processes are ongoing, managing partner expectations on a regular basis is key to sustaining interest, enabling the market to prepare for opportunities and for stakeholders to plan accordingly.

Has the logframe been updated since the last review?

This is the first annual review. The original logframe specified that milestones would be defined at the inception phase; however, in order to measure progress for the first year, in May 2017 the logframe was revised to include milestones for the first year. Milestones for subsequent years will be defined in the inception phase as originally planned.

## C: DETAILED OUTPUT SCORING

	Output Title	Improved capacity of selected secondary towns to plan and deliver market-driven urban economic planning
	Output number:	1	Output Score		C
	Risk:	Major	Impact weighting (%):		60
	Risk revised since last AR?	N/A	Impact weighting % revised since last AR?		N/A
Indicators		Milestones		Progress
1.1 Number of high quality strategic economic development plans supported in selected secondary towns		Both the Managing Agent consortium and independent M&E firm procured by DFID.		The Managing Agent consortium tender was published in August 2017 and the M&E firm tender is due to be published in September 2017. Procurement is due to be finished for both in January 2018.
1.2 Effective roll-out of urban economic development plans in selected towns		Advance review of a range of County Integrated Development Plans (CIDPs) and key stakeholder plans		DFID Kenya team has undertaken a light review of select CIDPs (as they are due to end in December 2017) and carried out scoping visits to Bungoma, Lodwar, Isiolo and Kwale.
1.3 Increased private sector consultation in County urban economic planning process – number of meetings held; evidence of private sector input		None		N/A

Key Points

1. The mobilization of the programme, and specifically procurement of the Managing Agent consortium and the M&E firm, has taken much longer than originally envisaged. This has been primarily for the following reasons:
  1. Protracted ToR development phase: It took 4 months to design and agree ToRs for the Managing Agent consortium and M&E firm. This was laregly due to change overs in the DFID team, needing to get up to speed with a complex 72-page Business Case (plus 5 annexes) and the importance of ensuring complementary and reinforcing roles for each of the Managing Agent consortium, M&E firm and separate strategic partner. Given the importance of the programme and time period that had passed since an initial market engagement event in August 2015, the team planned a second market engagement event to elicit feedback on the proposed detailed ToRs prior to tendering. However, within 24 hours of the planned market engagement event in early December 2016, Ministers announced an extensive ‘supplier review’ across DFID that temporarily halted procurement processes, and the second market engagement event was postponed until January 2017.
  2. Additional procurement steps: As part of the supplier review, additional steps were designed and added to the procurement process which have taken extra time to complete (with SUED being amongst the first DFID programmes to test the steps). These comprise the following:
    1. Strategic Sourcing Strategy – a strategic sourcing strategy had to be developed (which comprised a further 45-page PPT plus 6 annexes) setting out details on how the procurement will strengthen commercial effectiveness.
    2. Procurement Steering Board (PSB) – the strategic sourcing strategy had to be approved by a newly established PSB (in addition to Head of Programme Sourcing) before it could be submitted to the Cabinet Office for approval. The PSB required clarifications before proceeding and so the strategic sourcing strategy had to be re-submitted a second time to the PSB for approval, which was obtained in June 2017.
    3. Cabinet Office – following the PSB approval, the strategic sourcing strategy was submitted to Cabinet Office (with a standard 28 day turnaround) and approval received in July 2017.
    4. DFID Procurement & Commercial Department (PCD) – finally, approval was obtained from PCD and the tender published in August 2017.

Nonetheless, during the course of the first year, the DFID Kenya team has undertaken scoping visits to, and considered existing development plans for, some of the strategically identified secondary towns/counties such as Bungoma, Lodwar, Isiolo and Kwale (fieldtrips in January, February and June 2017). Many of these field visits have been undertaken with other DFID teams to explore synergies across programmes. The review of CIDPs has been intentionally light given that they are due to terminate in December 2017. There is currently an important opportunity for DFID Kenya to input into the development of the next 5 year development plans (see recommendation below).

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

Rec 1: Prioritizing completion of the procurement process by January 2018 is fundamental for the programme to be able to achieve 2018 milestones on-time. By way of improvement measures, the DFID Kenya team should put in place concrete, weekly/monthly, procurement milestones between September 2017 and January 2018 and report to the Head of Office on progress in November 2017 and January 2018.

Rec 2: By end-October 2017, the DFID Kenya team and PCD counterparts should organize an after action review and share lessons with other programme teams on how best to prepare for, and avoid pitfalls of, the new procurement steps and processes.

Rec 3: As the SUED Managing Agent consortium won’t be in place until January 2018 but as current County Integrated Development Plans (CIDPs) end in December 2017, the DFID Kenya team should engage priority counties[4] after the August 2017 elections and prior to December 2017 to explore how best to input into development of the next 5-year county development plans.
[4] To be undertaken in coordination with the rest of HMG in Kenya and as part of the HMG ‘100 day offer’ to government after the Kenya elections.

Output Title	Facilitation of public-private financing of climate resilient infrastructure
Output number	2	Output Score		N/A for this annual review.
Risk:	Moderate	Impact weighting (%):		Not weighted as the output is not scored in this annual review.
Risk revised since last AR?	N/A	Impact weighting % revised since last AR?		N/A
Indicators	Milestones		Progress
2.1 Volume of i) public, ii) private and iii) public-private finance mobilised for climate resilient infrastructure projects	N/A		N/A
2.2 Leverage ratio for projects brought to bankability	N/A		N/A
2.3 Number of infrastructure projects in implementation with sustainable financing models	N/A		N/A

Key Points

The sequencing of SUED interventions means that this output will only yield results in the implementation phase of the programme (after inception phase) once the urban economic development plans have been developed and key infrastructure projects identified for which financing is required. As such, no milestone targets are assigned for this year.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
N/A

Output Title	Facilitation of value chain development projects, connecting to economic growth corridors
Output number:	3	Output Score:		N/A for this annual review
Risk:	Moderate	Impact weighting (%):		Not weighted as the output is not scored in this annual review
Risk revised since last AR?	N/A	Impact weighting % revised since last AR?		N/A
Indicators	Milestones		Progress
3.1 Volume of i) public, ii) private and iii) public-private finance mobilised for climate resilient value chain projects	N/A		N/A
3.2 Leverage ratio for projects brought to bankability	N/A		N/A
3.3 Number of value chain projects in implementation with sustainable financing models (by sector – e.g. in energy, waste, housing, construction, agro-processing)	N/A		N/A

Key Points

As with output 2, this output is expected to yield results once the urban economic planning process has been concluded and viable value chain projects identified. Accordingly, no milestone targets were assigned for this annual review.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

N/A

	Output Title	County level business environment reform interventions are undertaken
	Output number:	4	Output Score:		B
	Risk:	Moderate	Impact weighting (%):		30
	Risk revised since last AR?	N/A	Impact weighting % revised since last AR?		N/A
Indicators		Milestones		Progress
4.1 Mechanisms/institutions for hosting public-private dialogue (PPD): / - identified (Y1); / - number of regular PPD forums held (Y2-6); / - good stakeholder feedback on utility and uptake of PPD forums (Y2-6)		Strategic partnership in place between DFID and the World Bank to undertake complementary business environment reforms		A strategic partnership concept note has been negotiated and agreed with the World Bank. A World Bank Trust Fund has been set up and a MoU is due to be signed next month.
4.2 Number of targeted investment promotion strategies supported in conjunction with County and private sector stakeholders		Zero		N/A
4.3 Number of business environment reforms enacted by County government		Zero		N/A

Key Points

1. The DFID Kenya team has negotiated and agreed with the World Bank a concept note for the strategic partnership which will take the form of a World Bank executed Trust Fund, managed by the Trade & Competitiveness team. It will provide technical assistance to the following areas[5]:
  [5] The Trust Fund will support part of wider World Bank Group initiative which will carry out work in other areas not supported by DFID, namely trade logistics, agribusiness and manufacturing (which DFID supports separately through TradeMark East Africa, Kenya Markets Trust and Invest Africa – a DFID centrally managed programme).
  1. National and County level business environment reforms
  2. Investment Policy / Promotion
  3. Competition Policy
  4. Special Economic Zones
  5. Public Private Partnerships (PPPs)

At the start of the year, the World Bank was carrying out work in these areas funded by the DFID Kenya Building a Reliable Investment Climate in Kenya (BRICK) programme which was due to end in March 2017 but subsequently extended until June 2017. Given elections taking place in Kenya in August 2017, it was appropriate for SUED to put in place a strategic partnership with the World Bank for resuming activities from September 2017 onwards. A World Bank Trust Fund was set up in August 2017, and a MoU is due to be signed in September 2017, so that activities can start as soon as practicable after the Kenya elections period has ended.

It will be important to ensure that the business environment work carried out through the World Bank strategic partnership does not duplicate any work carried out by the Managing Agent consortium or other donor initiatives. For example, a World Bank $300m credit to the Government of Kenya for urban planning was approved in July 2017. It is due to be implemented by the Ministry of Transport, Infrastructure, Housing and Urban Development over a 6-year period. It presents an excellent opportunity to strengthen urban development in Kenya, though will require extremely close collaboration between (amongst others) DFID, the World Bank and Government. Furthermore, TradeMark East Africa’s work on ‘growth hubs’ along the Mombasa-Nairobi-Kisumu northern corridor is well placed to directly link in with SUED which will focus on connected secondary corridors.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

Rec 4: In the SUED inception and implementation phases, working effectively alongside other new/evolving donor initiatives (such as the World Bank $300m urban planning credit to government and TradeMark East Africa’s Phase 2 support to ‘growth hubs’) should be prioritized and overseen early on through earlty establishment of the SUED Steering Committee.

	Output Title	Increased knowledge and information on sustainable urban development
	Output number:		5	Output Score		B
	Risk:		Minor	Impact weighting (%):		10
	Risk revised since last AR?		N/A	Impact weighting % revised since last AR?		N/A
Indicators			Milestones (2017)		Progress
5.1 Number of quality knowledge products produced and disseminated to strategic stakeholders			None		N/A
5.2 Stakeholder engagement and uptake			Consultation on urban economic development issues with key stakeholders through early market engagement, Centrally Managed Programmes (CMPs) such as the Infrastructure & Cities for Economic Development (ICED) and Cities for Infrastructure for Growth (CIG) initiatives and other forums		The DFID Kenya team has engaged stakeholders and enhanced knowledge and understanding of urban economic development issues in Kenya through a substantial market engagement event, conference/session attendance, contributing to an ICED study and scoping areas for further collaboration going forward with DFID’s research hub.
5.3 Evidence of replication of SUED initiatives by other actors i) in SUED targeted counties, and ii) in non-SUED targeted counties			None		N/A

Key Points

1. Once in place, the independent M&E firm will be responsible for generating and sharing knowledge on what works and doesn’t work for influencing key stakeholders. However, there are no milestones for this in the first year. Instead, DFID Kenya has focused on enhancing knowledge and understanding of key issues with stakeholders through a number of means:
  1. Private Sector / Civil Society Market engagement: In January 2017, the DFID Kenya team hosted a substantial market engagement event in Nairobi (see also comment to output 1 on page 6) to discuss key issues affecting urban economic development in Kenya and to obtain and incorporate feedback into ToRs. Over 50 organizations were represented at the event. In June 2017, the DFID Kenya team were represented at a World Resource Institute (WRI) urbanization conference in Nairobi and a University of Glasgow hosted Urban Big Data Centre discussion with DFID staff.
  2. DFID centrally managed/in-country/research programmes: There are a number of DFID programmes that can contribute to and gain from SUED. There is a strong offering of support from the Investment Climate, Cities and Infrastructure team (which DFID Kenya has involved closely in the SUED procurement process), and specifically from the Infrastructure and Cities for Economic Development (ICED) centrally managed programme. The DFID Kenya team has engaged ICED in a couple of areas: sharing Kenya urban trends/challenges at an ICED programme session on the future of DFID infrastructure technical assistance (June) and contributing to a study on “Boosting Youth Employment through Infrastructure Programming” (May). The latter was particularly important given that youth employment is a cross-cutting priority for the DFID Kenya office (along with a focus on the Northern/ASAL counties in Kenya). Once SUED procurement has been completed, the Managing Agent is encouraged to work closely with ICED and the Cities and Infrastructure for Growth (CIG) centrally managed programme (which currently has also been caught up in a protracted procurement process) as well as maximise synergies with the DFID Evidence and Research (EARH) team’s complementary urbanization research studies.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

Rec 5: In the SUED inception and implementation phases, DFID Kenya priorities of youth employment and a focus on Northern/ASAL counties in Kenya should be sufficiently integrated into SUED and opportunities to learn from and collaborate with ICED and DFID’s EARH team regularly assessed and pursued as appropriate.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

It is too early to assess the performance of key cost drivers of the programme. The Business Case anticipated that the key underlying costs will be the cost of services, as much of the delivery of the programme will be through technical assistance. Costs will include advisory fee rates of the international specialist skills required for the delivery of the various aspects of the programme e.g. urban economic planners and investment specialists.

Value for Money (VFM) of contract negotiations is being ensured through the competitive procurement process for the Managing Agent and M&E firm that are ongoing and following standard terms of engagement for Trust Funds agreed by DFID centrally with the World Bank. VFM has been built into the Managing Agent consortium ToR through payment against a combination of quality outputs and performance in achieving the programme objectives (with an increasing weighting over time towards the latter), with performance assessed by DFID taking into account findings from the independent M&E firm.

VfM performance compared to the original VfM proposition in the business case

The table below outlines the key VFM indicators proposed in the Business Case. These indicators will be refined at the programme inception. Assessment of the VFM performance will be included in the next annual review.

Level	Proposed VFM indicators
Effectiveness	Unit costs of delivering different types of infrastructure; / Evidence to demonstrate whether DFID and other leveraged funds are altering lending/investment behaviour amongst private financial institutions who are partners under SUED – measured by replication of SUED activities beyond the targeted towns and counties / The proposed ratio of costs spent on developing vs. implementing the law/regulation/policy/strategy / Time savings due to significant improvements in service delivery / Reduction in number of days for PPP project to go through the full project cycle
Economy	Implementing partners will be monitored in terms of cost and quality information to ensure VFM in procurement of goods, services and operating expenses
Efficiency	Cost of technical assistance per programme town intervention / Management costs for each delivery mechanism/fund as a proportion of invested funds will be included.
Economic Return	Tracking during implementation of key assumptions made in cost-benefit analyses carried out during inception / Number of direct and indirect jobs created per programme town / Amount of additional capital leveraged from other public and private sector sources
Equity	Ratio of marginal benefits disaggregated by poverty threshold, gender and rural/urban location

Assessment of whether the programme continues to represent VFM
It is too early to assess VFM for the programme. There is a clear need for emerging towns in Kenya to put in place sustainable urban economic plans; improve their investment climate and draw in investment for key climate-resilient infrastructure and value chain projects. However, given the slow mobilization phase of SUED on top of a range of other political/contextual risks, there are major risks for the programme not achieving high VFM and this will need to be carefully monitored in the coming year.
Quality of financial management

This will be assessed at the next annual review once contracts/MoUs have been signed and are operational.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK

Overall risk rating

The Business Case assessed overall risk as ‘major’, which is still the case, particularly due to the slow mobilization phase. This will be reviewed regularly and may well reduce over the lifetime of the programme, particularly once delivery is back on track (see section F below).

Overview of programme risk

The key risk at the time of this annual review is the delivery risk associated with the prolonged procurement process. Prioritizing speedy completion of the procurement process is fundamental for the programme being able to achieve 2018 milestones on-time. At the start of the inception phase it will also be necessary for the Managing Agent, M&E Firm and World Bank to set out a clear approach to working together to mitigate any further delivery challenges. A current risk is the unknown impact of the August 2017 elections in Kenya and the ability to constructively engage at the county level. Other risks include poor donor coordination (to be addressed by recommendation 4 above) and a lack of interest from the private sector to invest in infrastructure and value chains at the county level (to be addressed by the work of the Managing Agent consortium).

Outstanding actions from risk assessment

None.
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

As already discussed, the start of programme implementation has been considerably impacted due to delays in mobilization. The DFID Kenya programme team is however confident that delivery will get back on track now that the tendering process has begun and particularly once service providers are in place in early 2018. Moreover, arrangement for the strategic partnership with the World Bank is nearly complete, with implementation expected to commence at full speed since foundational work has already been carried out through the DFID Kenya BRICK programme which recently came to an end in June 2017.

Performance of partnerships

To be assessed at the next annual review.

Asset monitoring and control

No programme assets have been purchased. The programme team will ensure that the procurement and management of programme assets is in accordance with DFID SMART rules.

G: CONDITIONALITY

Update on partnership principles (if relevant)

SUED will work in close partnership with the Government of Kenya, particularly at the county level. All support towards government will be through technical assistance. No funds will be channelled through government accounts.

H: MONITORING & EVALUATION

Evidence and evaluation

The programme will adopt a rigorous approach to M&E to support learning and adaptation and to determine whether the programme is successful or not. Procurement is underway for an independent M&E firm that will lead the M&E component throughout implementation, comprising:
1. Monitoring: The M&E firm will develop and implement a M&E framework (aligned with International Climate Funds reporting standards) which includes establishing baselines, setting up robust data collection systems and designing beneficiary/participatory mechanisms.
2. Evaluation: The M&E firm will use the OECD-DAC evaluation criteria as a guiding framework to assess the relevance, effectiveness, efficiency sustainability and impact of the programme.
3. Learning: The M&E firm will develop knowledge/research products which address the evaluation questions and summarise monitoring findings that are underpinned by rigorous and systematic analytical approaches, and develop and implement a dissemination strategy.

Monitoring progress throughout the review period

Activities will be monitored through the coming year, and clearly set out in the programme inception report, as well as formally assessed at the next annual review.

The annual review process

This annual review was undertaken by Ian Mills (Head of Sustainable Economic Development, DFID Kenya) and Eunice Ogolo (Senior Programme Officer, DFID Kenya), with inputs from other team members, in particular Dennis Kwena and Elizabeth Mwihaki. The report has been quality assured by the Accountability and Results Team in DFID Kenya.