ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Support to South AFRITACS (201614)
Country or region targeted	The 13 members of AFRITAC South are Angola, Botswana, Comoros, Lesotho, Madagascar, Mauritius, Mozambique, Namibia, Seychelles, South Africa, Swaziland, Zambia and Zimbabwe
Type of cost extension (if applicable)	Bridge funding
Original project budget	£7,000,000
Original project start and end dates	13 December 2010 to 30 June 2017
Cost extension value (if applicable)	£1,120,000
New project end date (if applicable)	30 June 2018
Business Case Quest Document No.	Pre Business Case, Project Memorandum – 2882649

INFORMATION
What is the project’s purpose?
AFRITAC South (AFS) is one of five Regional Technical Assistance Centres established as collaborative ventures between the IMF, recipient countries and bilateral and multilateral donors.[1] AFRITACs South provides capacity development through the provision of short and long-term experts, regional seminars, training and professional attachments. Through these centres, member countries receive support in core macroeconomic and financial management areas, including revenue administration, public financial management, financial sector supervision, monetary policy framework operations, and economic and financial statistics. / The overall purpose of the AFS’s programme is to contribute to strengthened economic management in its beneficiary countries, which will, in turn, facilitate economic growth and reduce poverty.
What is the objective of the cost extension or other changes?
The primary objective of the extension is to enable AFS to continue providing high-quality technical assistance to meet the growing demand from its member countries. This extension will help to ensure that neither progress to date nor momentum is lost as a result of short-term funding constraints. / The AFS programme has performed well, scoring an A in each of its last five DFID annual reviews. The last external evaluation in 2015 rated the programme overall as ‘excellent’ with regards to the relevance and effectiveness of outputs and ‘good’ on effectiveness, efficiency and sustainability of outcomes. The evaluation made 23 recommendations, the majority of which have now been implemented. Feedback from beneficiaries is positive, for example, 91% strongly agreed or agreed that training helped them better perform at work. Finally, member countries all contribute funding which highlights the value they place on support. / The programme fits well with DFID’s strategy and the priorities of the department, including contributing towards: / progress on Sustainable Development Goal 16 (more effective and transparent institutions); / commitments in the bilateral development review, to ‘support our partner countries to make faster progress towards a sustainable exit from aid, helping them to collect more and fairer tax, spend public money more transparently and accountably on behalf of all citizens; / DFID’s Addis Tax Initiative commitment to double spend on tax reform in the developing world by 2020; and, / the Single Departmental Plan targets on tax and PFM. / . / Extending funding for one year enables AFS to continue delivering results while DFID undertakes a detailed assessment of whether and how to renew longer term support to Phase II. It also creates the time and space for DFID to analyse options to scale up our support to public financial technical assistance and capacity building more broadly. / Budget and Financing / Phase II of AFS will run from August 2017 to April 2022 (four years and nine months), with a total budget of over $59 million (USD). AFS has so far received funding pledges from donors totalling about $31 million (before a UK contribution) and member countries are expected to contribute a further near $8 million. The IMF will make a contribution of nearly $3 million. This currently leaves an approximate financing gap of over $17 million (before a UK contribution). / In addition, AFS have reported that it is facing short-term cash flow constraints, as new donor funding for Phase II has been committed but much of it is not expected to flow until later in IMF FY 2018. The principal donors are the EU, Germany, the Netherlands, the UK and Switzerland. AFS has requested that development partners and members do all they can to expedite the release of contributions. / A contribution from the UK in the coming months would enable AFS to continue ongoing operations at pace, avoid unnecessary disruption on the planning and implementation of activities, and help the centre through this period of low liquidity. Without a further UK contribution, AFS would probably have to find ways to scale down activities.
What is the additional and total support the UK will provide?
The extension is for £1.12 million over twelve months from 1 July 2017 until 30 June 2018. It would pick up when the current DFID programme finishes on 30 June 2017 and run through nearly all of the first year of Phase II implementation. / It would bring the total support the UK has provided to AFS since its inception to £8 million in the period from December 2010 to end June 2018. This is made up of £7 million to Phase I and £1.12 million bridge funding for the first year of Phase II. This is a steady profile of £1.12 million per year and would continue UK support at a consistent level. (Although the UK burden share would fall as Phase II is more expensive due to expanded activities and it is shorter in duration than Phase I ended up being after its extension).
What are the expected results?
The expected project impact is “sustainable economic growth and poverty reduction in AFRITAC South countries”. The expected project outcome is “improved economic governance in AFRITAC South Countries” which is measured through logframe indicators tracking performance against Public Expenditure and Financial Accountability (PEFA) indicators and Open Budget Survey data for each country. Demand for IMF TA by partner countries is high, including for peer learning activities and TA under financial sector regulation and supervision (where the volume of TA is expected to increase by 35% in FY18 compared to FY17 funding allowing). / Over the next IMF financial year (May 2017 – April 2018) AFS’s work will cover 300 milestones (detailed in the 2017 report to the steering committee). DFID funding will contribute to a share of these results. Each of these milestones relates to a specific country output. The table below shows a breakdown of the work by the main thematic areas. / Thematic Area FY 2018 / In field person weeks % / Public Financial Management 250 38 / Tax Administration 80 12 / Customs Administration 80 12 / Financial Sector Supervision 70 10 / Monetary Policy and Operations 95 14 / Financial Market Infrastructure and Payments 38 6 / Real Sector Statistics 67 10 / Total 680 100 / Some notable achievements over the last year are listed below. / Promotion of trade facilitation as part of customs administration. AFS supported six countries (Angola, Botswana, Mauritius, South Africa, Zambia, and Zimbabwe), to have fully operational post clearance audit team in customs. The other member countries’ post clearance audit teams are in place but in an infancy stage. / Improved financial sector regulation and supervision. In Botswana, IMF support enhanced the skills of the supervisors in stress testing, including the introduction of a stress testing framework covering solvency and liquidity risks to allow more effective implementation of stress testing. This will help to underpin greater stability in the financial sector. / Improved statistical capacity. The IMF supported Zambia to develop and publish quarterly GDP estimates (in current and 2010 constant prices) for the first time. The timeliness of annual estimates has also significantly improved. This will give the government a much timelier picture of economic activity, thereby improving fiscal and macroeconomic planning. / Over the next year, there will be a more achievements like these across the thematic areas in the table above. The nature of the results varies considerably across different countries, with the common theme being progress towards more effective financial and economic management.
What is the approach to implementation?
The programme is run under a Letter of Understanding with the IMF. AFS is overseen on a day-to-day basis by the AFS coordinator who is based at AFS headquarters in Mauritius. Its programme of TA is typically provided through one to two week missions to countries by advisers who are based full-time with AFS, supplemented by short-term advice from experts taken from the IMF roster and backstopping from IMF Headquarters. / Monitoring and Communications / AFS is implementing a new results-based management framework to improve planning, monitoring, reporting and coordination of all activities. Transition to this system is expected over the next year. As well as improving results reporting this will also help align donor reporting requirements, thus reducing the burden on IMF. / AFS produce an annual work plan in March, quarterly bulletins, six monthly reports (tracking progress on results and budgets and refining the work plan) and a comprehensive annual report. Alongside this, there are publications on the IMF and AFS websites, social and local media. / Governance / The current governance structure will remain. The steering committee will comprise of member countries, development partners, including donors and regional organizations, and IMF staff. The steering committee meets annually. In future, DFID will meet with the other main donors (Germany, EU, Switzerland, Canada and Australia) to discuss progress and priorities ahead of the steering committee. DFID will have meetings with the IMF on a biannual basis. Performance reports to DFID will be available on an annual basis. / DFID informally earmarks its contribution towards low income and fragile countries. According to the latest steering committee report, 57% of in field person weeks will be directed towards middle income countries, 8% towards high income and 36% low income in FY18. At DFIDs request AFS is exploring whether the allocation to low income and fragile states could be increased. / Costs and Value for Money / AFS provides a breakdown of the annual budget by the main thematic areas (as well as other spend categories) as detailed below: / AFS Budget, April 2017-May 2018 / Project/Activity Spend (US $ millions) Percentage of / annual spend / Tax Administration 0.7 7% / Customs Administration 0.7 7% / Public Financial Management 2.3 24% / Financial Sector Supervision 0.7 7% / Monetary Policy/Operations 0.8 8% / Financial Market Infrastructure 0.4 4% / Real Sector Statistics 1.3 13% / Financial and Fiscal Law 0.1 1% / Administration 0.5 5% / Governance 0.1 1% / Regional Seminars, Workshops and Training 0.8 8% / Contingency 0.2 2% / Trust Fund Management 0.6 6% / IMF Contribution 0.6 6% / Total 9.7 100% / DFID has pushed for improved VFM reporting, and this will remain a priority issue. The IMF has developed a new central approach to improving VFM; the first set of standard metrics from this system will be ready over the summer. More detailed breakdowns of budgeting costs and fee rates will improve transparency and enable better assessment of VFM. / DFID priorities over the next 12 months / Communications – DFID wants to see more ambitious efforts to get TA reports published, not just shared with funders. / Value for money – application of the new central VFM guidance; more transparency over cost breakdown and fee rates. / Results and reporting – implementation of the results based management framework and more streamlined donor requests. / Country coverage – greater share of support to low income and fragile states. / Coordination – continue improvements in linking up with other donors (in country) as well as key regional organisations (e.g. CABRI and ATAF). / The quality of a country’s public financial management and of its fiscal and monetary policy expertise has direct impact on its ability to manage its finances and grow its economy. AFS’s work to support good public financial management, the design and implementation of budgets, better tax collection, stronger financial systems and better data leads to improved service delivery, which can have a direct impact on women’s quality of life. This can be particularly beneficial where the investments are concentrated in sectors that affect women including maternal health, child health and education. AFS’s training interventions are also useful for addressing issues of gender equity. Future phases of programming will seek to disaggregate further the impact of activity in terms of their relationship with gender empowerment. / Improved PFM, financial sector regular and monetary policy will help to reduce corruption and illicit flows (therefore reducing opportunities for potential flows to terrorist groups). This programme provides support to government in the form of training and technical capacity (no direct financial aid to government). IMF is an established and trusted partner and risks of diversion of DFID funds to a terrorist organisation are very low.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The Phase II programme document highlights a number of lessons learned during Phase I that will be applied. These includes: / Start by identifying the issue to be addressed, instead of starting with the solution, and ensure effective ownership by the beneficiary. / Understand the space for reform and advice on concrete and sustainable steps. Given the synergies between political economy and technical work, it is important to recognize that reform requires both technical and organizational reforms, and to identify the constraints within which reform can be implemented. / Build networks within and across ministries, central banks, and other public sector organizations. For statistics, broadening support beyond statistics agencies to key data users and policymakers would create an impetus for improving the quality and use of data. / Work with all Capacity Development stakeholders. Collaboration both across IMF departments and with other CD providers and donor partners gains momentum and adapts ideas, while more explicitly working toward regional integration and harmonization objectives.
[1] The full set of AFRITACs is (i) East Africa (AFE), (ii) Central Africa, (iii) Francophone West Africa (West I), (iv) Southern Africa and (v) Anglophone West Africa (West II).